U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 1) BCP Number: XX | 2) BCP Title: Pixel Optoelectronics/Optical Hybrids |
| --- | --- |
| 3) Budget Number: WBS 1.1.1 | 4) MSA Title: U.S. ATLAS |
| 5) Date Submitted (Project Office): MM/DD/YY |
| 6) Change Designation: Priority [ X ] Routine [ ] | 7) BCP Level Level 0 [ ] Level 2 [ ] Level 1 [ ] Level 3 [X] | 8) Directed Change? Yes [ ] No [X ] |  |
| 10) Point of Contact: Abe Seiden 11) Phone: (831) 459-2923 12) FAX : (831) 459-5777 12a) E-mail: abs@scipp.ucsc.edu 13) Address: SCIPP/Natural Sciences II/University of California Santa Cruz/1156 High Street, Santa Cruz, CA 95064 |
| 14) Change Description: Release of management contingency for the procurement of optoelectronics integrated circuits and optoboards |
| 15) Change Justification: Baseline funding for procurement of optoelectronics integrated circuits and for optical hybrids(optoboards) is insufficient for 2-hit pixel system. |
| 16) Impact of Non-Approval: An insufficient number of optoelectronics integrated circuits and optoboards would be procured and the pixel detector could not be completed. |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 17) BCP Number: XX | 18) BCP Title: Pixel Optoelectronics/Optical Hybrids |
| --- | --- |
| 19) Impact on Cost Baseline: | Baseline (AY$ in Thousands) | Proposed (AY$ in Thousands) | AY$ Change |
| Production(Optoelectronics) 1.1.1.4.3.3.2 Optical hybrids Note that $ values are FY03 and not $AY | 38K 40K | 76K 90K | 38K 50K |
| 20) Impact on Funding Profile: The required funding profile is Baseline FY03 FY04 Production(Optoelectronics) 38 1.1.1.4.3.3.2 Optical hybrids 28 12 Management contingency FY03 FY04 Production(Optoelectronics) 38 1.1.1.4.3.3.2 Optical hybrids 50 Total FY03 FY04 Production(Optoelectronics) 76 1.1.1.4.3.3.2 Optical hybrids 78 12 |
| 21) Explanation of Impact on Cost and Funding Baselines: The cost baseline will increase by the amount of the change. |
| 22) Impact on Schedule Baseline: The baseline schedule becomes Start Date End Date Production(Optoelectronics) 11/20/03 4/7/04 1.1.1.4.3.3.2 Optical hybrids 10/23/03 9/15/04 |
| 23) Explanation of Impact on Schedule Baseline: FY03 funds are required for optoelectronics production to have funds transferred to CERN(committed) in time to begin production on the schedule above. Funds must be available at OSU to begin optical board production and thus sufficient FY03 funds must allocated although actual production will begin in early FY04. |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 24) BCP Number: xx | 25) BCP Title: Pixel Optoelectronics/Optical Hybrids |
| --- | --- |
| 26) Impact on Scope Baseline: |
| Item | Baseline | Proposed | Change |
| Production(Optoelectronics) 1.1.1.4.3.3.2 Optical hybrids | ICs for 50 optical boards used 89 BeO boards used | ICs for 100 optical boards 200 BeO boards used | ICs for 50 optical boards 111 BeO boards used |
| 27) Explanation of Impact on Scope Baseline. The proposed funding would provide 50% of the total optoelectronics ICs. The remainder is funded by Germany. The proposed amount will provide funding for BeO boards and loading of passive components. Optical components(VCSELs and PIN diodes) are now to be provided to the US and Germany by Taiwan. The US and Germany will now split the loading of optical components and subsequent testing. |
| 28) Other Impacts: (Health, Safety, Environment, etc.) None. |
| 29) Interim or Corrective Actions: None. |

U.S. ATLAS PROJECT

BASELINE CHANGE PROPOSAL (BCP)

| 30) BCP Number: XX | 31) BCP Title: Pixel Optoelectronics/Optical Hybrids |
| --- | --- |

PROJECT DISPOSITION - LEVEL 3

| 32) REVIEW RECOMENDATIONS: |
| --- |
| U.S. ATLAS Project Manager W. Willis | Disposition [ ] Approve [ ] Reject |
|  | DATE: |
| BNL Associate Laboratory Director T. Kirk | Disposition [ ] Approve [ ] Reject |
|  | DATE: |

# LHC PROJECT MANAGER DISPOSITION – LEVEL 2

| DOE/NSF U.S. LHC Project Manager J. Yeck | Disposition [ ] Approve [ ] Reject |
| --- | --- |
|  | DATE: |
| NSF Project Manager | Disposition [ ] Approve [ ] Reject DATE: |

## AGENCY DISPOSITION - LEVEL 1

| 33) Joint Oversight Group | RECOMMENDATION |
| --- | --- |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| ATLAS/CERN | RECOMMENDATION |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| Title: Date |  |
| DISPOSITION |
| Chairperson Date [ ] Endorsed [ ] Approved [ ] Rejected |
| 34) Explanation (If Action is Approved with Conditions, or Not Concurred Upon) |