Board of Scientific Counselors Meeting

Division of Intramural Research

National Institute of Allergy and Infectious Diseases

National Institutes of Health

# Background

The Board of Scientific Counselors (BSC) for the National Institute of Allergy and Infectious Diseases (NIAID), Division of Intramural Research (DIR) provides critical review and evaluation of the Division’s various research programs. The continued excellence of DIR scientific programs requires the rigid and objective review process provided by the BSC. The results of this review are used to guide resource allocation to existing programs and to assist the Institute in planning for new initiatives and for changes in program direction.

The BSC consists of approximately nine (9) permanent members, who all are senior scientists from organizations outside of the NIH. In addition, each review session includes several ad hoc members chosen for their expertise in the specific areas of the Laboratories being reviewed.

## Statement of Work

DIR requires a contractor to perform the following tasks to support the June 4 – 6, 2007 BSC meeting:

Task 1 – Secure a block of hotel rooms and arrange direct billing

- Within 1 week of contract being awarded- Secure a block of hotel rooms at the Hyatt Regency in Bethesda within the government per diem for three nights – June 3, June 4, and June 5, 2007; maximum 18 rooms.  Review terms of hotel contract with project officer or designee prior to final commitment. Once head count is confirmed, may need to decrease room allocation

- Beginning February 15 until meeting concludes on June 6, 2007- Communicate regularly with hotel on numbers, to avoid cancellation charges

- By April 1- Arrange with the hotel to create a direct billing for the room and tax charges

Task 2 – Travel Reimbursement of Reviewers

- January 5, 2007- The contractor shall create and submit to the project officer or designee a draft expense form for the traveling reviewers (approximately 18) to use in order to get reimbursed for the following expenses: ground transportation (i.e. mileage, taxi, and parking), and per diem. Approximately 9 travelers will also receive an honorarium.

- January 9, 2007- The project officer or designee will communicate necessary changes to the form to the contractor

- January 12, 2007- The contractor shall revise the form accordingly, prepare it as a final draft, and submit it to the project officer or designee for approval

- January 17, 2007- The project officer or designee shall provide the contractor with approval for the form

- June 4, 2007- The project officer or designee shall personally deliver expense form to all traveling reviewers. Travelers will submit expense form and receipts directly to contactor after the conclusion of the meeting

- Upon receipt of expense form- The contractor shall review expense forms submitted to ensure they are in accordance with government policies

- Within 2 weeks from receipt of each expense form- The contractor shall create and mail a check to each traveler

Evaluation Factors

Understanding of the Technical Requirements (40%)

- Demonstrates knowledge and understanding of the NIH Travel policies

- Describes, task-by-task, how the project activities will be managed effectively and efficiently within the time frames specified

Competence and Availability of Personnel (40%)

- Provides personnel experienced with working with hotels and government travel policies. Resume(s) of person(s) to be assigned to contract should be provided in proposal.

Past Performance (20%)

- Demonstrates recent successful experience in managing similar contracts of related work