### Proposal to Expedite PWG’s Completion of the Transmission Expansion Report

Mindful of SSG-WI’s commitment to FERC to deliver by September 2003 a report describing both the open process that has been developed to produce the SSG-WI Transmission Plan, and a preliminary assessment of the options for transmission expansion to support load growth in the Western Interconnection, and mindful of the considerable effort that will continue to be needed in order to meet this challenging objective, this paper proposes the formation of a planning study lead team to direct and co-ordinate the study work needed to complete the report in a timely and satisfactory manner.

Specifically, we propose that each member RTO should nominate an appropriately qualified person to sit on the planning study lead team.  This team is tasked to work with the Study Technical Support chairman (Jeff Miller) to coordinate and direct the efforts of the PWG members’ voluntary contributions to the study work through the various technical sub-groups, and to ensure that study products meet the objectives and goals of the Planning Work Group.  The study lead team will report to, and receive guidance from, the Planning Work Group on all matters relating to the study.  The Study Technical Support chairman will be supported by technical sub-groups as necessary.  Two in particular should be formed:

- a generation/load group to advise on existing and new generation, including fuel and prime mover costs and types, typical/actual economic and performance data, and prospective siting locations; and

- a transmission group to inform and advise on the technical aspects, feasibility and security of proposed transmission expansion options, including circuit data, flowpath ratings and nomograms.

It is proposed that the planning study lead team and the Technical Support Chairman should meet periodically, in open session with other PWG members willing to contribute their time and expertise in order to agree study scenarios, to set work targets and deadlines, to ensure that the necessary information is reported and exchanged between the study executors and the technical sub-groups, and generally to review progress.  To maintain momentum toward completion of the study, it is recommended that the team should meet every 2 weeks, beginning with a kick-off meeting at RTO West @ PDX, 10th March.

The topics to be covered could include:

- data collection for Y2008 base case study; identify/agree base case study scenarios;

- decide Y2013 generation/load expansion options; agree the ‘no transmission expansion’ Y2013 study scenarios; collection/compilation of Y2013 study data.

- review base case results; agree process for extracting PWG report information from raw output

- review of ‘no transmission expansion’ Y2013 study results; development of ‘best’ transmission expansion options; agree Y2013 study scenarios for combined generation/transmission expansion.

- augment study database to reflect ‘best’ transmission expansions for Y2013

- review generation/transmission expansion study results for Y2013

- agree format and scope of results to be collated/extracted for PWG report; define format of handover of study database to PWG

(NB: PAC estimate a minimum of 4 weeks to complete a cycle of scenario analyses: we would not therefore be able to deliver analysis results at each meeting).

Estimated PAC resources involved: 7-10 man-days attending/preparing for meetings.

SSG-WI PWG Generation/Transmission Expansion Plan

## Strawman Proposal for Study Scenarios (based on e-mail to D Eubank, 8/31/02)

To help focus SSG-WI PWG's discussions of study scenarios for the PWG's work program, may I suggest the following:

#### Y2008 base cases

- Set up the Y2008 study network based on the WECC case 07HS1A

- Define system load in Y2008 as per the WECC 10-Year Coordinated Plan Summary 2002-2011

- Identify the new generation (mainly renewables and Gas CCGT, those already planned and some projected) needed to cover this load increase - plus a planning margin of 12% (or 18%? tba)

- Select average hydro year production figures at Federal and other major projects

- Define a reference gas price for Y2008 (possibly with some localisation across the region) & fix the coal price.

This defines the central base case, Case 0

Then: as Case0, with low hydro production, and low gas price (say 70% of the reference) >>> Case 1

high hydro		            low gas				            >>> Case 2

low hydro 		            high gas (say 150% of the reference)      >>> Case 3

high hydro		            high gas				            >>> Case 4

This will provide PWG with 5 reference cases (congestion patterns, LMPs, etc) from which to compare the merits of the proposed expansion options under a range of hydro and fuel price assumptions.

#### Y2013 expansion cases

- Define system load growth to Y2013 by extrapolating the WECC 10-Year Summary

- Define (with help of technical advisory group) the quantity, type and location of new generation (plus planning margin) to cover this load increase.  Consider at most 3 generation expansion scenarios:

  - G1: mostly gas-fired CCGTs

  - G2: mostly renewables (mainly wind), with small amount of gas

  - G3: combination of coal and wind, with small amount of gas

- For each generation scenario, technical advisory group defines the ‘best’ transmission expansion option(s): T1, T2 and T3 (these may have several features in common), and also determines the impact of T1-T3 on WECC interface constraints.

- Repeat the analysis of Case 0 for each G/T combination, evaluating the resulting pattern of congestion, LMPs etc., with and without the selected transmission expansion

- If there is time, repeat the evaluation of the G/T combinations for cases 1-4

Note: this programme of work could entail anything from 8 to 20 scenarios to be set up, executed, interpreted and reported on.  At roughly 1/2 man-week per scenario, we may exceed the original 8 man-weeks volunteered by PAC, and may run out of time to complete the work for September 03.

##### Estimated PAC effort: 10 m-weeks (may be reduced if other utilities can share simulation burden)

plus ? m-weeks from PAC(T) on network expansion, results assessment, etc

SSG-WI PWG Generation/Transmission Expansion Plan

Proposal for Planning Study Data Collection – based on e-mail to KM 1/22/03 with revised dates

1. PAC have extracted the relevant network data (busses, branches, phase-shifters, loads and generator locations) from a WECC loadflow case (2007 Approved Operating case, 07HS1).  The network data is 99% complete and verified, and some 80% of the WECC generating resources have been mapped onto the generator busses in the loadflow network.  We have also populated a generator database with unit performance and economic data drawn from a variety of sources - some of which are commercially sensitive and may not be freely shared with SSG-WI members.

2. PAC offer to complete data collection and database construction for the PWG planning studies to the following program:

3. By Feb 21st, PAC will circulate the partially complete network data forms to transmission data collectors.  They will be asked to confirm/correct the network data for their area and to augment the data with details of known and planned transmission expansion up to Y2008, to confirm/ correct/complete the mapping of generators to busses in their area, and to send their responses direct to PAC by Feb 28th, for final approval at a March 3rd meeting of the Study Team Lead.

4. By Feb 26th, PAC will compile tables of typical and/or published generator data (of economic and performance data as required for the planning studies), identifying the source of such data and verifying its availability for unrestricted use by SSG-WI members in their joint and individual studies. (We may defer this verification step until it is known if and how SSG-WI will control access to the data).  We will use these typical/published data to populate the unit-specific generator data forms, and circulate them to SSG-WI data collectors (and/or a separate Generation Advisory group) to review and notify PAC of any required additions/changes by March 3rd.

5. On receipt of all responses (or failing that, with the approval of SSG-WI PWG to make appropriate approximations), PAC will compile the network and generator data into a database for use in the Base Case study.  This task will be complete by March 7th, allowing analysis of the Base Case study to begin in week commencing March 10th (Mar 3rd).

6. After further Study Team Lead meetings (April 28/29th), PAC will modify the study database to reflect the Y2013 generation, load and transmission additions, to be in a position to complete the planning studies by end-May.

Estimated PAC effort: 4m-weeks on data collection and database creation/maintenance (in addition to what has already been expended)

plus ? m-days from PAC(T) on data confirmation/preparation