| 1) BCP Number: CDF 001 |  | 2) BCP Title: Project Rebaseline |  |
| --- | --- | --- | --- |
| 3) Budget Number: |  | 4) Title: Run IIb CDF Detector Project |  |
| 5) Date Received (Field Office): |  | Date Received (Program Office): |  |
| 6) Change Designation: Scope Reduction | 7) BCP Level: Level 0 [ ] Level 2 [ ] Level 1 [ X ] Level 3 [ ] | 8) Directed Change? Yes [ X ] No [ ] | 9) Program: SC-20, Office of High Energy Physics |
| 10) Point of Contact: Paul Philp |  | 12) FAX: (630)840-3285 |  |
| 11) Phone: (630) 840-4481 |  | 13) Location: FAO |  |
| 14) Change Description: The MIE cost of the baseline is reduced by $14.2 million from $25 million to $10.8 million. There is no change in the scheduled date of Critical Decision 4 “Project Completion.” The scheduled date for Critical Decision 3b is delayed two months. The proposal drops the construction of the replacement silicon vertex detector. Some tasks that fell within the silicon vertex detector subproject related to trigger, data acquisition, and radiation monitoring will be moved to the data acquisition subproject and used with the current silicon vertex detector. 15) Change Justification: (If Directed Change specify authority and documentation) At the time of Critical Decision 3, the acquisition executive chose to split the critical decision into two parts, 3a and 3b. CD-3a approved limited construction for one year with the intention that Tevatron luminosity performance could be evaluated before proceeding to CD-3b and full construction. Fermilab finalized their plans for the luminosity upgrades and an Office of Science review of that plan was held. Using the plan and the results from the review, the director of Fermilab with advice from the Fermilab Program Advisory Committee determined that the best option to maximize the physics of Run II was to not take a long shutdown for the installation of the replacement silicon vertex detector. They also determined that the current silicon vertex had a good probability of survival due to the lower Tevatron luminosity projections. This decision was endorsed by a subpanel of HEPAP at its September 29, 2003 meeting. |  |  |  |
| 16) Impact of Non-Approval: Should this baseline change not be approved there are two possible outcomes. The silicon vertex detector would be built but never installed. Alternatively approximately a year of running would be lost while it was installed. Under the original Tevatron upgrade plan this would have been compensated by a higher performing accelerator, but under the current upgrade plan the performance is not high enough to allow for such a long shutdown. |  |  |  |

| BCP Number: CDF – 001 |  | BCP Title: Project Rebaseline |  |  |
| --- | --- | --- | --- | --- |
| 17) Impact on DOE Cost Baseline: |  |  |  |  |
| 18) Impact on Funding Profile (BA): # Approval of this Baseline Change Proposal will provide DOE MIE funds in FY 2004 and FY 2005. The changes to the DOE MIE funding profile are shown below: |  |  |  |  |
| 19) Explanation of Impact on Cost and Funding Baseline: The project cost is significantly reduced by the cancellation of the silicon detector. The detector activity will now be limited to the completion of approximately 5% of the full system. |  |  |  |  |
| 20) Impact on Schedule Baseline: All milestones within WBS 1.1 will be eliminated from the baseline. |  |  |  |  |
| Milestone (No. and Description) | Baseline (Month/Year) |  | Proposed (Month/Year) | Change |
| CD-3b | 9/03 |  | 11/03 | 8 weeks |
| CD-4 | 11/06 |  | 11/06 | 0 weeks |

| BCP Number: CDF– 001 | BCP Title: Project Rebaseline |
| --- | --- |
| 21) Explanation of Impact on Schedule Baseline: The CD-3b approval milestone has been delayed to November 2003 to allow the extra time needed to adequately prepare the BCP and CD-3b approval documents. |  |
| 22) Impact on Scope Baseline: The scope of the baseline no longer contains the silicon detector. |  |
| 23) Explanation of Impact on Scope Baseline: Additional procurements in support of the Silicon Detector subproject current baseline will not be placed. Some contracts already underway will be terminated for convenience. Some prototypical stages of the Silicon Detectors will be completed, tested, and documented. Remaining scope will be assessed for optimal use with the current detector. |  |
| 24) Other Impacts (Health, Safety, Environment, etc.) None |  |
| 25) Interim or Corrective Actions: Efforts at the Silicon Detector (SiDet) fabrication facility have been tentatively redirected to support the actions proposed in this BCP. |  |

| FIELD DISPOSITION - LEVEL 2 |  |  |
| --- | --- | --- |
| 26) Members | Recommendations |  |
| Paul Philp Date Run II Project Director Fermi Area Office |  |  |
| Jane L. Monhart Date Fermi Area Office Manager |  |  |
| PROGRAM DISPOSITION - LEVEL 1 |  |  |
| 27) Advisors (Specialized Support, as required) |  | Recommendations |
| Michael Procario Date Run IIb Program Manager Office of High Energy Physics |  |  |
| ACQUISITION EXECUTIVE - LEVEL 1 |  |  |
| Disposition [ ] Approved [ ] Endorsed [ ] Rejected Robin Staffin Date Associate Director Office of High Energy Physics | Comments: |  |