| PROJ. NO. | FUND YEAR | IHS AREA | HEALTH CARE FACILITY (APPLICANT) [IHS AWARD AMT. / TOTAL PROJ COST] | LOCATION | PROJ. TYPE | P.L. 93-638 CONTRACT AWARD DATE | DES OFFICE (CO) [PM] | STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 508 | 2001 | PO | White Swan Health Clinic (Confederated Tribes and Bands of the Yakama Nation of Yakama Reservation, Washington) [$1,475,375 / $2,097,300] | White Swan, WA | R | 01/21/2003 | ES-S (LS) [NDG] | DESIGN START: February 19, 2004 DESIGN COMPLETE: May, 2006 CONSTRUCTION START: Pending CONSTRUCTION COMPLETE: Pending STATUS COMMENT: 4th bid opening on August 3, 2006. Tribe approved additional $400K in August to enable award. The Tribe has yet to award the construction contract. |
| 510 | 2002 | PO | Inchelium Health Care Facility (Confederated Tribes of the Colville Reservation) [$2,000,000 / $3,868,572] | Inchelium, WA | R | 08/27/2002 | ES-S (LS) [PTN] | DESIGN START: July, 2001 DESIGN COMPLETE: July, 2002 CONSTRUCTION START: August 15, 2002 CONSTRUCTION COMPLETE: July 8, 2004 STATUS COMMENT: Contract close-out pending Tribe spending remaining funding. |
| 511 | 2002 | PH | Reno-Sparks Indian Colony Clinic (Reno-Sparks Indian Colony) [$2,000,000 / $8,640,621] | Reno, NV | R | 12/20/2002 | ES-D (B0) [MB] | DESIGN START: August 18, 2003 DESIGN COMPLETE: June 1, 2004 CONSTRUCTION START: Pending CONSTRUCTION COMPLETE: Pending STATUS COMMENT: Project has been designed but is awaiting BIA to put the land in trust/on the rolls before construction starts. DES received SF-269A for 7/1/06 to 9/30/06. Total outlays this period is $352,501.32. |
| 513 | 2002 | PO | Roger Saux Health Center (Quinault Indian Nation) [$968,931 / $1,446,124] | Taholah, WA | R | 11/09/2002 | ES-S (LS) [GFK] | DESIGN START: October, 2002 DESIGN COMPLETE: January, 2005 CONSTRUCTION START: May 5, 2005 CONSTRUCTION COMPLETE: November 1, 2006 STATUS COMMENT: Punchlist items being completed, should receive close out report by first of year. |
| 518 | 2003 | AK | Chenega Bay Health Clinic (Chugachmiut) [$1,230,015 / $1,306,919] | Chenega Bay, AK | R | 10/03/2003 | ES-S (LS) [JB] | DESIGN START: May 28, 2004 DESIGN COMPLETE: May 16, 2005 CONSTRUCTION START: September 1, 2005 CONSTRUCTION COMPLETE: December 19, 2006 STATUS COMMENT: Project ready for closeout pending final financial report showing all funds expended. The Tribe was contacted in October 2006 and is aware of this need and is working on expending all remaining funds. |
| 519 | 2003 | NS | Narragansett Indian Health Center (Narragansett Indian Tribe of Rhode Island) [$1,375,105 / 1,556,800] | Charlestown, RI | R | 11/21/2003 | ES-D (LS) [MB] | DESIGN START: August 9, 2004 DESIGN COMPLETE: Pending CONSTRUCTION START: Pending CONSTRUCTION COMPLETE: Pending STATUS COMMENT: Tribe has been requested by COTR to send revised schedule, SF-269, and cost estimate. They are still waiting on the status of additional grant requests. Estimated submission date of design development phase plans is 1/15/07. |
| 520 | 2003 | BI | Chippewa Cree Health Center (Chippewa Cree Tribe) [$2,000,000 / $10,000,000] | Rocky Boy’s Indian Reservation, Bonneau Village, MT | R | 01/22/2004 | ES-S (LS) [HLP] | DESIGN START: December 1, 2003 DESIGN COMPLETE: October, 2004 CONSTRUCTION START: February 7, 2005 CONSTRUCTION COMPLETE: December 2006 STATUS COMMENT: Project construction completed in Jan 2007. No word on a dedication ceremony yet. |
| 521 | 2006 | PO | Cowlitz Health Center Cowlitz Tribe [$1,010,500/$1,956,700} | Longview, WA | E&M | 05/17/2006 | ES-S (LS) [NG] | DESIGN START: August 2006 DESIGN COMPLETE: January 2007 CONSTRUCTION START: April 2007 CONSTRUCTION COMPLETE: April 2008 STATUS COMMENT: 35% design submittal received in DES 11/27/06 and comments were provided. Tribe agreed to re-submit the 35% submittal by approx end of Jan 2007. |
| 522 | 2006 | PO | Cow Creek Satellite Clinic Cow Creek Band of Umpqua Tribe of Indians [$1M/$2,195,752] | Canyonville, OR | E&M | Need Award | ES-S (LS) [NG] | DESIGN START: ? DESIGN COMPLETE: ? CONSTRUCTION START: ? CONSTRUCTION COMPLETE: ? STATUS COMMENT: Kick-Off meeting held 6/29/06. Tribe confirming site and starting environmental review. No project schedule submitted yet. HQE letter sent 12/4/2006 stating they have until March 31, 2007 to secure their funding and sign the contract. |
| 523 | 2006 | PO | Siletz Clinic Expansion Confederated Tribes of Siletz Indians [$2M/$7.5M] | Siletz, OR | E&M | 05/17/2006 | ES-S (LS) [NG] | DESIGN START: ? DESIGN COMPLETE: ? CONSTRUCTION START: ? CONSTRUCTION COMPLETE: ? STATUS COMMENT: Kickoff meeting held 6/30/06. Tribe submitted NEPA to PO Area for review in Dec 2006. Project schedule update (beyond provided in application) is still needed. Tribe needs to re-secure Tribal funding. |
| 524 | 2006 | PO | Makah Health Center Makah Indian Tribe of the Makah Indian Reservation [$2M/$2,684,330] | Neah Bay, WA | R | 05/24/2006 | ES-S (LS) [NG] | DESIGN START: August, 2006 DESIGN COMPLETE: September 2007 CONSTRUCTION START: ? CONSTRUCTION COMPLETE: ? STATUS COMMENT: Design schematics submitted to DES in December 2006 and review comments were provided. |
| 525 | 2006 | AK | Hooper Bay Sub-Reg Clinic – YKHC – Village of Hoppe Bay [$1.7M/$8,021,389] | Hooper Bay, AK | NS | Need Award | ES-S (LS) [JB] | DESIGN START: DESIGN COMPLETE: CONSTRUCTION START: CONSTRUCTION COMPLETE: STATUS COMMENT: All funding certified by Area to DES. No project schedule submitted yet. Award pending receipt of Denali Commission funding by the Tribe. HQE letter sent 12/22/2006 establishing a March 31, 2007 deadline to secure additional funding. |
| 526 | 2006 | AK | Kake Clinic Exp SEARHC Village of Kake [$2M/$3,880,764] | Kake, AK | NS | 6/16/2006 | ES-S (LS) [JB] | DESIGN START: 4/30/06 DESIGN COMPLETE: 12/15/06 CONSTRUCTION START: 6/1/07 CONSTRUCTION COMPLETE: 9/1/08 STATUS COMMENT: 100% design submittal received in DES in late Dec 2006. Review comments due to Tribe by Jan 16, 2007. |
| 527 | 2006 | CA | Shingle Springs Rancheria Health Clinic Shingle Springs Band of Miwok Indians [$2M/$8.5M] | El Dorado County, CA | R | 7/25/2006 | ES-S (LS) [JB] | DESIGN START: DESIGN COMPLETE: CONSTRUCTION START: CONSTRUCTION COMPLETE: STATUS COMMENT: All funding certified by Area to DES. Kickoff conference call completed in September. No project schedule submitted yet. Tribe submitted 100% design to DES in late Dec 2006. No technical review requested. Tribe may need to secure additional funding. |
| 528 | 2006 | BE | Peter Christian Health Clinic Replacement Lac du Flambeau Band of lake Superior Chippewa Indians [$2M/$??M] | Lac du Flambeau, WI | R | Need Award | ES-S (LS) [JB] | DESIGN START: DESIGN COMPLETE: CONSTRUCTION START: CONSTRUCTION COMPLETE: STATUS COMMENT: Project approved by HQE 9/25 w/funding from canceled Pechanga project. Need contract award. Need kick off mtg. Tribe must obtain their funding by 9/30/07 or project will be canceled and funding will be reprogrammed. |

# LEGEND FOR IHS AREAS:		LEGEND FOR DES:

AQ	=	Albuquerque		DES	=	Division of Engineering Services, OEHE, IHS	 PTN	=	Paul Ninomura, ES-Seattle

AK	=	Alaska		ES-D	=	Engineering Services-Dallas			 HW	=	Howard Wellspring, ES-Dallas

BI	=	Billings		ES-S	=	Engineering Services-Seattle 			  NG	= 	 Nathan Gjovik, ES - Seattle

CA	=	California		OEHE	=	Office of Environmental Health and Engineering 	  JB 	= 	 John Bausch, ES - Seattle

CO	=	DES Contracting Officer

NS	=	Nashville	PM	=	DES Project Manager

PO	=	Portland	BO	=	Bill Obershaw, ES-D Contracting Officer

LS	=	Linda Shaw, ES-Seattle

LEGEND FOR PROJECT TYPE:	EH	=	Eddie Hall, ES-S Project Manager

E	=	expansion	HLP	=	Hank Payne, ES-Seattle

E & M	=	expansion and modernization	DB   	=	Dale Burson, ES-S Contracting Officer

NS	=	new satellite	MB	=	Mark Burke, ES-Dallas

R	=	replacement	CLB	=	Casey LaFran, ES-Seattle

Note, all dates in (   ) are estimated dates.  Dates without (   ) are actual dates that milestones

SAP Contract (Completed-Closed Out-Achieved)

Project No. 501	Purcell Outpatient Clinic					Project No. 515	Bois Forte Health  Clinic of Minnesota Chippewa Tribe

Project No. 502	Mariposa Indian Health Clinic					Project No. 517	Campo Satellite Clinic –Southern Indian Health Council

Project No. 503	Tribal Medical & Dental Clinic-The Klamath Tribes			Project No. 521	Ball Club Village Clinic-Leech Lake Bank of Ojibwe

Project No. 504	Pueblo Jemez Health and Dental Clinic

Project No. 505	Stigler Clinic –Choctaw Nation of Oklahoma

Project No. 506	Yreka Clinic – Karuk Tribe of California

Project No. 507	Ho-Chunk Health Care Center

Project No. 509	Santa Ysabel Health Care Facility

Project No. 512	Las Vegas Paiute Colony Health Care Facility