## reviews sheet
Time Key: |  |  |  | Status Key:
red WBS/device is needed for summer 2003 shutdown |  |  |  | fuscia (dated expected) | Review & Documentation needed
green WBS/device is needed for US BO |  |  |  | underline (date to reviewer) | Engineering note in review process
blue WBS/Device needed for DS BO |  |  |  | bold - ready for Schuh Committee | Engineering Note Complete & Reviewed
purple WBS/Device needed for summer 2004 shutdown |  |  |  | italics (date to committee) | Engineering note to Schuh Committee
|  |  |  | pink, not sure of data | qeustions
updated 11/10/03 by DAH |  |  | Dates Listed are from "Early Start" Date in April 03 Schedule
WBS | Device/Procedures | Hazards | Location | Design Review Date/Link | Safety Reviews: M, S, E, F, O, R, T | Projected Installation Date | Review Status
1.1 | NuMI Installation |  |  | 2002 dec_04.html |  | 2004-12-08 17:00 | on going
1.1 | NuMI Radiation Safety |  |  | 2002 july_17.html |  |  | covered in Shielding Assessment
1.1 | NuMI Commissioning |  |  | 2003 march.html |  |  | complete
1.1 | NuMI Accident Conditions |  |  | 2003 march.html |  |  | complete
1.1.1 | Specs and Design for Primary Beamline |  |  | 2002 nov_01.html |  |  | complete
1.1.1 | Beam Optics Design |  |  | 2002 apr_02.html |  |  | complete
1.1.1 | Beam Extraction Permit System |  |  | Aesook Review | D&P post-shutdown |  | NuMI review fall 2003
1.1.1 | Primary Beamline Instrumentations |  |  | 2002 jun_25.html 2002 nov_01.html | n/a | 2004-02-18 17:00 | complete
1.1.1.a | BPM |  |  | specs reviewed 3/03 (NG) | n/a |  | complete
1.1.1.b | Multiwire |  |  | Tech Review of specs 10/02 | n/a |  | complete
1.1.1, 1.1.3 ** | Kicker Magnet & PS & Cooling Sys (F17 test setup) |  | Testing in service building. Using fence & procedures ala MI8 | 2002 july_01.html | n/a - in existing test facility with previous reviews |  | complete
1.1.1, 1.1.3 | Kicker Magnet & PS & Cooling Sys (Kicker-load cooling with active system and circulating coolant) | M | Installation in MI tunnel uses standard tunnel access procedures | 2002 jun_14.html | Installation review (internal) required MSD/BD | 2004-07-06 | date?
1.1.1, 1.1.3 | Kicker Magnet & PS & Cooling Sys | T | After significant beam losses on kicker. Maintenance procedures needed? | Design 6/14/02 | Toxic material hazard after radiation exposure - Operational review needed in '04 |  | date?
1.1.1 | Kicker magnet |  | EE | 2002 feb_01.html | n/a |  | complete
**** | Kicker magnet- stands |  | EE | generic magnet stand EN | EN 1321-ES-296397 | 2003-12-09 17:00 | Schuh yes Pushka yes
*** | Kicker magnet-installation |  | EE | R.Reily wrote Installation Procedure | HA needed | 2004-07-06 08:00 | n/a
1.1.1 | Lambertsons (3) |  | EE | generic (MI spares) | n/a |  | complete
**** | Lambertsons (3) - stands |  | EE | EN calcs included in Installation Procedure (by L.Sauer) | EN 1321-ES-296XXX | 2003-12-09 17:00 | Need Puskha approval then it goes to Schuh
*** | Lambertsons (3) - installation |  | EE | L.Sauer wrote Installation Procedure | HA needed | 2004-07-12 17:00 | n/a
1.1.1 | HV101 EPB (6) |  | EE |  | n/a |  | n/a
**** | EPB (2) Stands HV101-1,2 | M | EE | Need aisle side and refurb. Note | EN 1321-ES-296390,96 | 2003-07-30 | Schuh yes Pushka Yes
| EPB (4) Stands HV101-2,3,4,5 | M | EE | Need aisle side, refurb. , and cradle Note | EN 1321-ES-296390,96,98 |  | Schuh Yes Pushka Yes
*** | EPB Installation (HV101 -1 thru 6) |  | EE | L.Sauer Note approved by J.Misek | EN 1321-ES-296402 | 2003-08-26 08:00 | n/a
1.1.1 | Q101-Q106 3Q120 (5) |  | EE |  | n/a | 2003-08-26 08:00 | n/a
1.1.1 | Q104 3Q60 |  | EE |  | n/a | 2003-08-26 08:00 | n/a
| Q101 Stand | M | EE |  | n/a |  | n/a
| Q102-Q104 Stands | M | EE |  | EN 1321-ES-296390,96,97 |  | Schuh yes Pushka Yes
| Q105 Stand |  | EE |  | EN 1321-ES-296399 |  | Schuh yes Pushka Yes
| Q106 Stand |  | EE |  | EN 1321-ES-296400 |  | Schuh yes Pushka Yes
| Quad Installation (Q101) |  | EE | standard magnet mover installation | n/a |  | n/a
| Quad Installation (Q102-104) |  | EE | L.Sauer Note approved by J.Misek | EN 1321-ES-296402 |  | n/a
| Quad Installation (Q105-106) |  | EE | ??? | ??? |  | n/a
| HQ107 stands | M | EE | changed to Q108-style stand | MD-ENG-03-001 |  | Schuh yes Pushka Yes
| Q107 Installation |  | EE | L.Sauer to write Installation Procedure | HA needed |  | n/a
1.1.1 | V108 B2 (5) |  | NS |  | n/a | 2003-09-23 08:00 | n/a
**** | B2 Stands | M | NS |  | MD-ENG-03-001 | 2003-08-26 | Schuh yes Pushka Yes
*** | B2 Installation |  | NS |  | MSDN-ME-000036+ HA needed | 2003-08-26 | n/a
| HQ108-112 Stands |  | NS | Same stands as for NS B2's | MD-ENG-03-001 |  | Schuh yes Pushka Yes
| HQ108-112 Installation |  | NS |  | MSDN-ME-000036+ HA needed |  | n/a
1.1.1 | HQ113-HQ116 3Q120 (4) |  | CR |  | n/a | 2003-11-13 08:00 | n/a
| Transport/Installation Carts |  |  | MD-ENG-03-002 6 March 2003 | MD-ENG-03-002 | 2003-10-27 | Schuh yes Pushka Yes
| Magnet Installation Lifting Fixtures |  |  | MD-ENG-03-004 6 March 2003 | MD-ENG-03-004 | 2003-10-27 | Schuh yes Pushka Yes
1.1.1 | HQ117-HQ121 3Q120 (5) |  | Pre-TGT |  | N/A | 2003-12-08 08:00 | n/a
| HQ113-HQ121 Stands |  | CR/Pre-TGT | MD-ENG-017 (M.Wong) | MD-ENG-017, went to Schuh 10/20 | 2003-10-27 | Schuh yes Pushka Yes
| HQ113 - 121 Installation |  | CR/Pre-TGT | complete (M.Wong) |  |  | n/a
1.1.1 | V118 B2 (4) |  | Pre-TGT |  | N/A | 2003-12-08 08:00 | n/a
* | B2 Stands | M | Pre-TGT | MD-ENG-017 (M.Wong) | MD-ENG-017, went to Schuh 10/20 | 2003-10-27 | Schuh yes Pushka Yes
* | B2 Installation |  | Pre-TGT | complete (M.Wong) | HA needed | 2003-12-08 08:00 | n/a
1.1.1 **** | Magnet Installation Lifting Fixtures |  |  | MD-ENG-03-005 6 March 2003 | MD-ENG-03-005, FESHM 5022 | 2003-10-27 | Schuh yes Pushka Yes
1.1.1 **** | Magnet Installation Transport/Installation Carts |  |  | MD-ENG-03-003 6 March 2003 | MD-ENG-03-003 | 2003-10-27 | Schuh yes Pushka Yes
1.1.1 | Beam vacuum pipe |  | CR,Pre-TGT | Already installed in CR, Pre-TGT next | n/a by FESHM, since OD under or at 12" | 2004-07-16 08:00 | n/a
1.1.1 | Be Window before target | T | TH |  | Tied to TGT Review | 2003-12-01 | Tied to TGT Review
1.1.2 | do we need to do prev completed, such as horn test stand? |  | look through the book inherited from Dave Boehlien
1.1.2 | Target and Horns
1.1.2 | Chase cooling system | R | TH | http://www-numi.fnal.gov/numwork/reviews/july_30.html | final review on 7/30/03, EN by A.Stefanik , to be reviewed | 2004-05-27 08:00 | final review on 7/30/03
1.1.2 | Radioactive component handling & work cell | R | TH | 2002 feb_27.html |  | 2004-04-19 08:00 | covered in Shielding Assessment
1.1.2 | Target hall radiation shielding | R | TH | Rad Safety review 7/17/02, 2002 july_17.html | Shielding Assessment on Safetydocs web page | 2004-03-23 | covered in Shielding Assessment
1.1.2 | Neoprene Air Seal | F | TH |  | Approved by J.Priest | 2004-03-01 | ?? Need email confirmation
1.1.2 | Tgt module | M | THC | 2002 aug_01.html | EN not yet complete E.Villegas | 2004-05-20 08:00 | EN not yet complete E.Villegas
1.1.2 | Target (inc. Be windows) | R,T | THC | 2002 aug_01.html | documentation complete & reviewed | 2004-08-02 08:00 | in Pushka review
1.1.2 | Baffle | R,T | THC | 2002 aug_01.html | documentation complete & reviewed | 2004-08-02 08:00 | in Pushka review
| Target Module Installation | M | THC |  |  |  | n/a
1.1.2 | Horn 1 module | M | THC | 2001 aug_10.html | MD-ENG-012, R.Silva | 2004-05-25 08:00 | Schuh yes, Pushka yes
1.1.2 | Horns 1 and 2 | M,E | THC | 2001 aug_10.html | K.Anderson'sTalk | 2004-06-17 08:00 | in Pushka review
| Horn 1 Module Installation | M | THC |  |  |  | n/a
1.1.2 | Horn 2 module | M | THC | 2001 aug_10.html | MD-ENG-013,R.Silva | 2004-05-28 08:00 | Pushka Yes, ready for Schuh
| Horn 2 Module Installation | M | THC |  |  |  | n/a
1.1.2 | Module assembly/test stand (module plus components stand) | M | MI8 | EN: J.Misek (in progress), ok'd by Sims, being checked by Wands/Pushka | went to Schuh 10/20 | 2003-10-22 | Schuh yes, Pushka yes
1.1.2 | Module assembly stand | M | MI8 | EN: V.Sidorov, reviewed by J.Sims, | reviewed by Pushka and Sims | in use on surface | in Schuh review
1.1.2 | Module transportation stand | M | TH |  | n/a |  | n/a
1.1.2 | Horn lifting fixture (horn 1 & 2) | M | MI8, TH | Gary Trotter author, load tested in March. EN almost ready | MSG-EAR-03-322, B.Wands (LD#138) |  | in Schuh review
1.1.2 | Work Cell | M,T | TH | EN: A. Szymulanski | Very thick EN Awaiting load test and scan/copy | 2004-03-01 | EN Reviewed, awaiting load test
1.1.2 | Chase Duratek shielding | M | 10% prototype in Meson Detector Bldg | A.Stefanik has HA |  |  | complete
1.1.2 | Chase Duratek shielding | M | THC | A.Stefanik has HA |  |  | complete
1.1.2 | Target Pile Shielding Installation | M | THC |  |  |  | n/a
1.1.2 | T Block Steel Cutting Procedure | M |  |  | MD-ENG-03-008, A. Stefanik |  | n/a
1.1.2 | Target Pile: Zero Layer Grout |  | THC | EN Complete | MD-ENG-03-015, A. Stefanik |  | n/a
1.1.2 | Target Pile Shielding: Weld Sizing for Laminated Steel Filler Blocks |  | THC |  | MD-ENG-02-015, A. Stefanik |  | n/a
1.1.2 | T-Blocks | M | Prototype in MAB | Calculations done, assembled and tested, A.Stefanik reviewing EN | MSG-EAR-01-294, A. Stefanik, B.Wands | 2004-08-23 08:00 | still in internal review
1.1.2 | T-Blocks | M | THC | Tested as fabricated |  | 2004-08-23 08:00 | n/a
1.1.2 | T-Block Installation | M | THC |  |  | 2004-08-23 08:00 | n/a
1.1.2 | Green Duratek block lifting fixture (Tongs) | M | THC | In fabrication process, missing one piece for each tong | LD#142, J.Kilmer, B.Wands | 2003-10-27 | passed second load test-otherwise Pushka & Schuh approved
1.1.2 | Green/Blue Duratek block lifting fixture (basket) | M | THC | load tested on 10/20/03 | MD-ENG/03-0014, I. Fang, LD#145 | 2003-10-27 | in Schuh review
1.1.2 | T-Block lifting fixture | M | THC | Complete, in use | MSG-EAR-01-293, B.Wands, LD#130 | 2004-05-04 08:00 | Pushka yes, Schuh yes
1.1.2 | Module lifting fixture | M | MI8,TH | Complete , in use | LD#132, B.Wands |  | Pushka yes, Schuh yes
1.1.2 | Stripline block assembly fixture |  | TH | EN: B. Boettinger, now D. Tinsley and R. Silva | EN + review to come | 2004-04-27 08:00 | EN + review to come
1.1.2 | TSB transporter cart | M | TH | n/a (standard) |  |  | n/a
1.1.2 | R Block | M | TH | Complete |  |  | n/a
1.1.2 | monitor readout module (Budal, Bdot) | E | TSR | Eventually need Ducar approval | below Schuh threshold |  | n/a
1.1.2 | Neutrino Device Instruments |  | TSR | n/a | n/a |  | n/a
1.1.2 | Hot Cell Door Transportation Stand | M | TH | EN to come, not designed yet | EN to come, not designed yet |  | EN + review to come
1.1.3 | Conventional magnet power supplies | E | MI60, MI65 | 2003 mar_PS.html |  | 2004-02-05 08:00 | n/a
1.1.3 | Kicker magnet PS (included in 111) | E | NA |  | SAR & LOTO to come | 2003-08-27 08:00 | SAR & LOTO to come
1.1.3 | Kicker PS installation |  | TSR |  | n/a |  | n/a
1.1.3 | Horn power supply | E | MI8 test stand |  | NuMI safety comm, complete |  | complete
1.1.3 | Horn power supply | E | TSR | complete | SAR & LOTO for PS Room | 2003-10-28 08:00 | update SAR & LOTO for PS Room
1.1.3 | Horn Power supply Installation | M | TSR |  | EN + review to come (includes TL) |  | EN + review to come
1.1.3 | Flexjoint |  |  |  | 1 EN for TL joints, TL & stands |  | 1 EN for TL joints, TL & stands
1.1.3 | Horn transmission line | E | TH,TSR | 2003 apr_23.html | 1 EN for TL joints, TL & stands | 2004-04-19 08:00 | 1 EN for TL joints, TL & stands
1.1.3 | transmission line Stands | M,E | TH,TSR |  | 1 EN for TL joints, TL & stands | 2004-04-19 08:00 | 1 EN for TL joints, TL & stands
1.1.3 | transmission line installation | M | TH,TSR |  | Horn PS & TL installation EN together | 2004-04-19 08:00 | Horn PS & TL installation EN together
1.1.3 | Lifting Fixture: Penetration Stripline Assembly installation | M | TH | EN being written by Rafael Silva | ??? |  | ???
1.1.3 | Lifting Fixture: stripline conductors | M | machine shops | EN being written by Vladimir Sidorov | ??? |  | ???
1.1.4 | Decay pipe (note 1) | R | DR
1.1.4 | Decay Pipe Upstream end lifting fixture | M | THC | LD#143, D.Pushka | LD#143, D.Pushka |  | Pushka yes, Schuh yes
1.1.4 | Decay pipe vacuum vessel | M | DR | MD-Eng/01-004-A, Chicago Bridge and Iron, ed by E.Chi, add Soyars note | All but vacuum test(as per FESHM 5033) | Done during civil constr/ | Reviewed and Ready for Schuh
1.1.4 | Upstream decay pipe end cap | M | Test at MAB | contains MSG-EAR-02317 | All but vacuum test(as per FESHM 5033) |  | in Schuh Review
1.1.4 | Upstream decay pipe end cap | M | THC | contains MSG-EAR-02317 | All but vacuum test(as per FESHM 5033) | 2003-11-24 | in Schuh Review
1.1.4 | US decay pipe end cap installation |  |  |  |  | 2003-11-24
1.1.4 | Downstream decay pipe end cap | M | Test at MAB | MD-Eng/01-004-B, E.Chi, add Soyars note and small test result | All but vacuum test(as per FESHM 5033) |  | Pushka yes, ready for Schuh
1.1.4 | Downstream decay pipe end cap | M | AH | MD-Eng/01-004-B, E.Chi, add soyars note and small test result | All but vacuum test(as per FESHM 5033) | 2004-09-27 08:00 | Pushka yes, ready for Schuh
1.1.4 | DS decay pipe end cap installation | M | AH |  |  | 2004-09-27 08:00
1.1.4 | Absorber | R,M |  |  | EN written, include core, shielding? | 2004-09-27 08:00 | EN written, include core, shielding?
1.1.4 | Absorber aluminum cores (8) | R | AH |  | EN written, include core, shielding? | 2004-09-30 13:00 | EN written, include core, shielding?
1.1.4 | Absorber stacking procedure |  |  |  | HA needed |  | n/a
1.1.4 | Base of Shaft Materials Handling |  |  |  | HA needed |  | n/a
1.1.4 | Absorber shielding | M | AH |  | EN written, include core, shielding? |  | EN written, include core, shielding?
1.1.4 | Installation crane headframe (note 2) | M | AH |  | need? |  | need?
1.1.4 | Fork truck lifting fixture (note 3) | M | AH,AP |  | need? |  | need?
1.1.5 | Muon monitors | O,E | MA1,MA2,MA3 | 2002 july_24.html | ODH calcs needed | 2004-03-29 08:00 | ODH calcs needed
1.1.5 | Muon Monitor Installation |  | MA1,MA2,MA3 |  |  | 2004-03-29 08:00
1.1.5 | Hadron monitor | O,E | AH | 2002 july_24.html | ODH calcs needed | 2004-10-14 08:00 | ODH calcs needed
1.1.5 | Hadron monitor Installation | M | AH |  |  | 2004-10-14 08:00
1.1.6 | Alignment | none | n/a | n/a |  |  | n/a
1.1.7 | Infrastructure: Water, Gas and Vacuum |  |  | 2002 mar_06.html |  |  | complete
1.1.7 | MI-62 (upstream) LCW |  | in MI-62 and MI | 2002 oct.html complete | 2002 oct.html complete | 2004-01-29 08:00 | complete
1.1.7 | MI-62 (upstream) Heat Exchanger | M | in MI-62 | Reviewed and Installed |  |  | Schuh yes, Pushka yes
1.1.7 | Beamline Vacuum pipe | M | MI to TH | n/a because pipes all under 12"OD (FESHM5033) | n/a | n/a | n/a
1.1.7 | Beamline Vacuum pipe Vacuum System | M | MI to TH | EN by Jim Klen, being reviewed by D.Pushka | EN in review process | 2004-07-16 08:00 | EN in review process
1.1.7 | Decay Pipe RAW system | R | TH and AA tunnel | MD-ENG-03-023 | Currently in internal review |  | Currently in internal review
1.1.7 | Absorber RAW system | R | in Absorber access tunnel | MD-ENG-03-024 | Currently in internal review | 2004-02-02 | Currently in internal review
1.1.7 | Absorber RAW system Installation | R | in Absorber access tunnel |  |  | 2004-02-02
1.1.7 | Target RAW system | R | in Absorber access tunnel | MD-ENG-03-021 | Currently in internal Review | 2004-04-05 | Currently in internal Review
1.1.7 | Target RAW system Installation | R | in Absorber access tunnel |  |  | 2004-04-05
1.1.7 | Horn 1 and 2 RAW system | R | in Absorber access tunnel | User, peer & Rad. Safety Reviews 2002 nov.html Complete | User, peer & Rad. Safety Reviews 2002 nov.html Complete | 2003-10-30 | Comments received,review on 9/05/03, request additional review
1.1.7 | Horn 1 and 2 RAW system Installation | R | in Absorber access tunnel |  |  | 2003-10-30
1.1.8 | Cables | F | All areas |  | status & what does Bob think is needed? |  | n/a?
1.1.8 | Cable installation |  |  |  | n/a | 2004-03-08 | n/a?
1.1.8 | NuMI stub monorail | M | in NuMI stub |  | n/a? |  | n/a?
1.1.8 | NuMI stub monorail - install |  |  |  | n/a? | 2003-08-08 | n/a?
1.1.8 | Beam transport |  | Primary beam transport |  | what is this? |  | n/a?
1.1.8 | Radiation safety interlock system | E,R | Main Injector to Absorber Hall access tunnel |  | will be reviewed according to FESHM |  | n/a?
1.1.8 | Controls |  |  | 2003 mar_L3.html | n/a? | 2004-04-27 | n/a?
all | All | see below (1) | Main Injector to MINOS Hall | Internal 7/17/03 |  | Final review / Shielding Assessment, 1/04 | Final review / Shielding Assessment, 1/04
all | All | all | Main Injector to MINOS Hall | SAD |  | start through BD by 6/04 | start through BD by 6/04
all | access procedures |  |  |  | draft complete & reviewed internally |  | OK'd by Schuh
all | training req. |  |  |  | draft in progress |  | n/a
1.1.2 + 1.1.3 + 1.1.7 | Horn power supply, Horn to raw, target, module, etc | see below (2) | Target hall |  |  |  | n/a?
1.2 | Infrastructure | see below (3) | All new underground areas |  |  |  | I think this is covered in other reviews, access procedures, etc. You can ask Ducar.
2.1 | Magnets: Steel and Coil
2.1.1 | Steel Plane Fabrication | M,S | S,NM,MH |  | M: S:
2.1.2 | Steel Handling Fixtures | M | S,NM,MH |  | M: |  | JK 11/22/99
2.1.3 | Near Detector Support Structure | M,S | NM,MH | NI: 8/24/2000 | M: S: |  | IF 1/31/00
2.5.1 | ND Support Structure installation(SB&O ) | M | MH |  |  | 2004-01-08 17:00
2.5.3 | Detector Installation | M | MH |  |  | 2004-02-24 08:00
2.5.3 | Remove Planes from Detector | M | NM | n/a |  | 2004-02-24 08:00 | IF 2/23/00
2.5.3 | Load truck at New Muon Lab | M | NM | n/a |  | 2004-02-24 08:00 | IF 2/23/00
2.5.3 | Move planes down shaft | M | MSA | n/a |  | 2004-02-24 08:00
2.5.3 | Base of Shaft Materials Handling | M | MSA | n/a |  | 2004-02-24 08:00
2.5.3 | Mounting Planes on Detector | M,S | MH | n/a |  | 2004-02-24 08:00 | IF 1/31/00
2.1.4 | Magnet Coil | E | S,NM,MH | NI: 4/13/2000 | E: | 2004-08-24 08:00 | JK 10/26/01, JK 8/17/01
2.5.3 | Coil Transport down Shaft | M | MSA,MH |  | M: | 2004-08-24 08:00
2.5.3 | Magnet Coil Installation | M | S,NM,MH | n/a | M: | 2004-08-24 08:00 | 2002-02-07
| Magnet Coil Welding Procedure | F | MH |  | F:
2.1.4 | low current coil tests | E | MH |  | E:
2.1.4 | high current coil tests | E | MH |  | E:
2.1.4 | remote operations of coil | E | MH |  | E:
1.1.8 | LCW System | M | MH
2.1.5 | Detector Plane Prototypes | M,S,E | NM |  | M: S: E: |  | IF 2/23/00
2.2 | Scintillator Detector Fabrication
2.2.1 | Scintillator Strips | n/a | ANL | n/a | n/a |  | n/a
2.2.2 | Fiber | n/a | ANL | n/a | n/a |  | n/a
2.2.3 | Scintillator Modules | M | ANL,MH | n/a | n/a |  | n/a
2.2.3/2.5.2 | Scintillator Module Installation | M | NM |  |  | 2002-02-18 08:00
2.5.2 | Plane Assembly | M | NM |  |  | 2002-02-18 08:00
2.5.2 | Unload truck at New Muon Lab | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
2.5.2 | NM materials handling (Ingrid's cart) | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
2.5.2 | Mounting planes on Detector | M | NM | n/a |  | 2002-02-18 08:00 | IF 1/31/00
2.5.2 | Unload ND Steel Planes | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
2.5.2 | materials handling (Ingrid's cart) | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
| Attach Modules to Steel | M | NM | n/a |  | 2002-02-18 08:00
2.5.2 | Mounting Planes on Bookend | M | NM | n/a |  | 2002-02-18 08:00 | IF 1/31/00
2.2.4 | PMT's | n/a | MH
| PMT Installation into Alner Boxes | n/a | MH
2.2.5 | Spectrometer Mux Boxes | n/a | ANL,NM
| Mux Box Installation | n/a | MH
2.2.6 | Light Injection System | E | ANL | NI: 9/22/2000 | E:
2.2.7 | Assembly and Test Equipment | n/a | ANL | n/a | n/a |  | n/a
2.2.8 | Factories | n/a | ANL | n/a | n/a |  | n/a
2.3 | Electronics DAQ, and Database
2.3.1 | Near Detector Front End | E | MH | NI: 4/17/2002
2.3.1 | Fiber Cables |  |  | NI: 4/17/2002
2.3.1 | All Other Cables |  |  | NI: 4/17/2002
2.3.1 | PMT (Alner) Boxes |  |  | NI: 4/17/2002
2.3.1 | Printed Circuit Boards (Master, Minder) |  |  | NI: 4/17/2002
2.3.2 | Far Detector Front End | n/a | S | NI: 10/24/2000 | n/a | done | n/a
2.3.3 | Data Routing and Trigger Farm | n/a | NM,S |  | n/a |  | n/a
2.3.4 | DAQ and Triggering | n/a | NM,S | NI: 2/20/2001 | n/a |  | n/a
2.3.5 | Database--UMN | n/a | NM,S | NI: 2/13/2001 | n/a |  | n/a
2.3.6 | Auxiliary systems (clock, gps) | n/a | NM,S | NI: 2/20/2001 | n/a |  | n/a
2.3.7 | Electronics Management | n/a | n/a | n/a | n/a |  | n/a
2.3.8 | Slow Control and Monitoring | n/a | NM,S | NI: 1/9/2001
2.5.3 | Electronics Installation | E | MH |  |  | 2004-04-20 08:00
2.5.1 | Rack Installation | E | MH |  |  | 2003-09-23 08:00
2.3.9 | HV System | E | NM,S
2.5.3 | HV system Installation | E | MH |  |  | ???
2.4 | Far Detector Installation
2.4.1 | Completed Design Tasks | n/a | n/a | n/a |  | done
2.4.2 | Management | n/a | S | n/a |  | done
2.4.3 | MINOS Construction Oversight | n/a | S | n/a |  | done
2.4.4 | Soudan Lab Infrastructure | n/a | S | NI: 3/24/2000 |  | done
2.4.5 | Detector Installation | M,E | S |  |  | 6/3/2003
2.5 | Near Detector Installation--for most, see under other WBS elements
2.5.1 | Infrastructure | M,E | MH |  |  | 2004-01-08 17:00
2.5.3 | Power Distribution System | E | MH |  |  | 2004-08-27 08:00
2.5.4 | FNAL Outfitting Systems-LCW?
2.5.5 | SB&O Experimental | n/a | n/a | n/a |  |  | n/a
| Locations: |  | Review Types: | Operational Reviews may include:
| NS=NuMI Stub |  | M=Mechanical | ORC's (Detector)
| EE=Extraction Enclosure |  | S=Structural | NuMI Internal Reviews
| CR=Carrier Region |  | E=Electrical | FESHM's
| Pre-TGT=Pre-target |  | R=Radiation
| TSA=Target Shaft area |  | T=Toxic Materials
| TSR=Target Support Rooms |  | O=Oxygen Displacing Gasses
| HP=Horn Pit |  | F=Fire
TH=Target Hall
| THC=Target Hall Chase |  | Key, notes:
| DR=Decay Region |  | Review & Documentation needed | fuscia (dated expected)
| AH=Absorber Hall (but not MA1) |  | Engineering note in review process | underline (date to reviewer)
| AP=Absorber Passageway |  | Engineering Note Complete & Reviewed | bold - ready for Schuh Committee
| MA# = Muon Alcove 1,2,3,4 |  | Engineering note to Schuh Committee | italics (date to committee)
| MSA=MINOS Shaft Area |  | qeustions | pink, not sure of data
| MHP = MINOS Hall Passageway |  | LD#: lifting device number, original is in WH11X Binder, includes load test and review of calcs
| MH=MINOS Hall |  | NI: NuMI Internal (Review)
| NM=New Muon Lab |  | Means the date is wrong--now included in SB&O contract, and is done |  | orange
| S= Soudan |  | (note 1) Rad: ground water activation, prompt and residual radiation, air activation |  |  | blue
| ANL=Argonne Nat'l Lab |  | (note 2) Elect: good ground for water skid? Module? Target? |  | green
| MI65= itself |  | (note 3) Fire protection, FIRUS, access limits |  | yellow
complete as of 7/03 means reviews completed, comments from reviews being addressed, elements not thought to need Schuh
review.
Note on E9: HTML Source: http://www-numi.fnal.gov/numwork/reviews/
Note on F9: M = Mechanical G = Flammable Gas E = Electrical F = Fire ) = ODH R = Radiation T = Toxic Material

## 1.1.2 Document Status
WBS | Device/Procedures | Hazards | Location | Design Review Date/Link | Safety Reviews: M, S, E, F, O, R, T | Projected Installation Date | Review Status
1.1.2 | Neoprene Air Seal | F | TH |  | Approved by J.Priest | 2003-03-04 | ?? Need email confirmation
1.1.2 | Tgt module | M | THC | 2002 aug_01.html | EN not yet complete E.Villegas | 2004-05-20 08:00 | EN not yet complete E.Villegas
1.1.2 | Target (inc. Be windows) | R,T | THC | 2002 aug_01.html | documentation complete & reviewed | 2004-08-02 08:00 | in Pushka review
1.1.2 | Baffle | R,T | THC | 2002 aug_01.html | documentation complete & reviewed | 2004-08-02 08:00 | in Pushka review
1.1.2 | Horn 1 module | M | THC | 2001 aug_10.html | MD-ENG-012, R.Silva | 2004-05-25 08:00 | Schuh yes, in Puskha review
1.1.2 | Horns 1 and 2 | M,E | THC | 2001 aug_10.html | K.Anderson'sTalk | 2004-06-17 08:00 | in Pushka review
1.1.2 | Horn 2 module | M | THC | 2001 aug_10.html | MD-ENG-013,R.Silva | 2004-05-28 08:00 | iterating with reviewer (Ang Lee)
1.1.2 | Module assembly/test stand (module plus components stand) | M | MI8 | EN: J.Misek (in progress), ok'd by Sims, being checked by Wands/Pushka | went to Schuh 10/20 | 2003-10-22 | Pushka Yes, in Schuh Review
1.1.2 | Module assembly stand | M | MI8 | EN: V.Sidorov, reviewed by J.Sims | went to Schuh 10/23 | in use | Pushka Yes, in Schuh Review
1.1.2 | Horn lifting fixture (horn 1 & 2) | M | MI8, TH | Gary Trotter author, load tested in March. | MSG-EAR-03-322, B.Wands (LD#138) went to Schuh 10/23 |  | Pushka Yes, in Schuh Review
1.1.2 | Work Cell | M,T | TH | EN: A. Szymulanski | Very thick EN Reviewed, to be copied | 2004-03-01 | EN Reviewed, to be copied
1.1.2 | T-Blocks | M | Prototype in MAB | EN Complete | MSG-EAR-01-294, A. Stefanik, B.Wands | 2004-08-23 08:00 | in internal (Stefanik) review
1.1.2 | Green Duratek block lifting fixture (Tongs) | M | THC | In fabrication process, missing one piece for each tong | LD#142, J.Kilmer, B.Wands | 2003-10-27 | all but load test--otherwise Pushka & Schuh approved
1.1.2 | Green/Blue Duratek block lifting fixture (basket) | M | THC | load tested on 10/20/03 | MD-ENG/03-0014, I. Fang, LD#145 | 2003-10-27 | Pushka Yes, in Schuh Review
1.1.2 | T-Block lifting fixture | M | THC | Complete, in use | MSG-EAR-01-293, B.Wands, LD#130 | 2004-05-04 08:00 | Pushka yes, Schuh yes
1.1.2 | Module lifting fixture | M | MI8,TH | Complete , in use | LD#132, B.Wands |  | Pushka yes, Schuh yes
1.1.2 | Stripline block assembly fixture |  | TH | EN: B. Boettinger, now D. Tinsley and R. Silva | EN + review to come | 2004-04-27 08:00 | EN + review to come
1.1.2 | monitor readout module (Budal, Bdot) | E | TSR |  | below weight threshold |  | n/a
1.1.2 | Hot Cell Door Transportation Stand | M | TH | EN to come, not designed yet | EN to come, not designed yet | 2003-04-04 | EN + review to come
Note on E1: HTML Source: http://www-numi.fnal.gov/numwork/reviews/
Note on F1: M = Mechanical G = Flammable Gas E = Electrical F = Fire ) = ODH R = Radiation T = Toxic Material

## Status Sheet
Status 11/10/03, DAH
[6 empty] | NuMI | Schuh
A=B+C+D+E+F+G+H
| A | B | C | D |  | E | F | G | H | I
horn 2 module md-eng-013 (Reviewed by Ang Lee) | Total # EN, Doc needed* | ENs, Docs to be completed* | # in Presently in or ready for NuMI review process | # ready for Pushka | # being reviewed by Pushka | # ready for Schuh | # being reviewd by Schuh | # reviewed by Schuh, iterating (includes ones needing FESS or DP review) | # Completed and OK'd by Schuh and Pushka | Final Sign-off Complete
All NuMI EN/ ES&H Documentation Deemed Necessary | 65 | 28 | 5 | 1 | 3 | 3 | 4 | 1 | 1 | 20
All MINOS EN/ES&H Documentation Deemed Necessary | 20? | 6? | 11? | [6 empty] | 3?
*best guess, numbers good to +/- 2 for total & needed
Still need for summer shutdown: | Status:
#REF! | #REF!
Lambertson Stands | Need to assemble calcs into note
High Priority
CT/Pre-Tgt Stand EN--DONE!
Upstream Decay pipe end cap
tongs (LD142) and Basket (LD145) tongs passed load test after modification
Verification for Q107 and 108 stands being similar enough to B2 stands in NS--Rick Ford verified this…within Q111 range
1 |  | Target Module (E.Villegas) | Absorber RAW and Intermediate systems (MD-ENG-03-024) | Work Cell (A.Szymulanski)) (not load tested yet) | target, (web page) | horn 2 module md-eng-013 (Reviewed by Ang Lee) | upstream decay pipe end cap msg-ear-02317 (not vacuum tested yet) | horn 1 & 2 RAW systems (schuh requested additional internal review) | green duratek block liftung fixture (LD#142) Passed 2nd load test, addendum tadded to original EN | B2 Magnet Installation Lifting Fixtures MD-ENG-03-005
2 |  | Stripline Block Assembly Fixture (D.Tinsley, R. Silva) | Decay Pipe RAW (MD-ENG-03-023) |  | baffle (web page) | downstream decay pipe end cap md-eng/01-004-b (not tested yet) | green/blue duratek block liftung fixture (basket) md-eng/03-0014 (LD#145) |  |  | CT Transport/Installation Carts MD-ENG-03-002
3 |  | Hot Cell Door Transportation Stand | Target RAW (MD-ENG-03-021) |  | horns 1 and 2 (web page) | decay pipe vesselmd-eng/01-004-a (not testted yet) | Horns and Target/Baffle Module assembly stand (Sidorov) |  |  | PT/CT Magnet Installation Lifting Fixtures MD-ENG-03-004
4 |  | Lambertson Stand EN 1321-ES-296XXX | t-blocks msg-ear-01-294 (A.Stefanik doing review by end of November)) |  |  |  | horn lifting fixture msg-ear-03-322 (LD#138) |  |  | PT Magnet Installation Transport/Installatoin Carts MD-ENG-03-003
5 | [9 empty] | Horn 1 module MD-ENG-012
6 | [9 empty] | Q105 stands EN 1321-ES-296399
7 | [9 empty] | Q106 stands EN 1321-ES-296400
8 | [9 empty] | extraction magnet stand cradles EN 1321-ES-296398
9 | [9 empty] | NuMI Stub stands md-eng-03-001
10 | [9 empty] | extraction aisle side support EPB stands EN 1321-ES-296390
11 | [9 empty] | Generic extraction Magnet Stands EN 1321-ES-296397
12 | [9 empty] | numi extraction magnet stands support refurbishment EN-1321-ES-296396
13 | [9 empty] | q107 stands, now same as MD-ENG-03-001
14 | [9 empty] | decay pipe upstream end lifting fixture ld 143
module lifting fixture ld 132
t- block liftung fixture msg-ear-01-293 ld-130
MI-62 Heat Exchanger
CT/Pre-Tgt Stand EN (M.Wong) MD-ENG-017
module assembly/test stand, (J.Misek)
Access Procedure

## 1.1.1 Documents
Note Number | Title | Author | Status
LD137 | CT/PT Magnet Lifting Fixture | D.Pushka | In binder
1321-ES-296XXX | NuMI Lambertson Installation (and Stand) | L.Sauer | In binder
MD-ENG-03-003 | Magnet Transport Cart (PT area) | D.Pushka | In binder
1321-ES-296390 | Aisle Side Support | L.Sauer
1321-ES-296396 | Magnet Stand Support Refurbishment | L.Sauer | In binder
1321-ES-296397 | Generic Magnet Stand | L.Sauer
1321-ES-296398 | Magnet Stand Cradles | L.Sauer | In binder
1321-ES-296399 | Q105 Stand | L.Sauer | In binder
1321-ES-296400 | Q106 Stand | L.Sauer | In binder
1321-ES-296402 | Extraction Magnet Installation Procedure | L.Sauer | In binder
MD-ENG-03-001 | NuMI Stub Magnet Stands

## Sheet1
ORC for Load test of MINOS Strongback for 25,000 Capacity
ORC for MINOS using Materials Handling Fixture w/Wooden Mock-up of Steel Plates
ORC for Hanging Planes on the 4-plane Prototype
ORC for MINOS using Materials Handling Fixture
LD 107 cover sheet, and ORC for Hanging 4 ND planes on Near Strongback
ORC for oad test of MINOS Near Strongback for 8000 lbs
ORC for MINOS using Final (Far) Strongack and Procedures to Hang Steel Planes
ORC for Removing West Prototype (Far) Planes using Production Strongback
ORC for Operation of Near Prototype Magnet Coil and Power Supply
ORC for Operating the Far Coil Prototype
NuMI- Near Detector Support Structure Design Calculations

## Installation Procedures
WBS | Device/Procedures | Hazards | Location | Design Review Date/Link | Safety Reviews: M, S, E, F, O, R, T | Projected Installation Date | Review Status
1.1.1 | Kicker magnet-installation | 0 | EE | R.Reily wrote Installation Procedure | HA needed | 2004-07-06 08:00 | n/a
1.1.1 | Lambertsons (3) - installation | 0 | EE | L.Sauer wrote Installation Procedure | HA needed | 2004-07-12 17:00 | n/a
1.1.1 | EPB Installation (HV101 -1 thru 6) | 0 | EE | L.Sauer Note approved by J.Misek | EN 1321-ES-296402 | 2003-08-26 08:00 | n/a
1.1.1 | Quad Installation (Q101) | 0 | EE | standard magnet mover installation | n/a | 0 | n/a
1.1.1 | Quad Installation (Q102-104) | 0 | EE | L.Sauer Note approved by J.Misek | EN 1321-ES-296402 | 0 | n/a
1.1.1 | Quad Installation (Q105-106) | 0 | EE | ??? | ??? | 0 | n/a
1.1.1 | Q107 Installation | 0 | EE | L.Sauer to write Installation Procedure | HA needed | 0 | n/a
1.1.1 | B2 Installation | 0 | NS | 0 | MSDN-ME-000036+ HA needed | 2003-08-26 | n/a
1.1.1 | HQ108-112 Installation | 0 | NS | 0 | MSDN-ME-000036+ HA needed | 0 | n/a
1.1.1 | HQ113 - 121 Installation | 0 | CR/Pre-TGT | complete (M.Wong) | 0 | 0 | n/a
1.1.1 | B2 Installation | 0 | Pre-TGT | complete (M.Wong) | HA needed | 2003-12-08 08:00 | n/a
1.1.2 | Target Module Installation | M | THC | 0 | 0 | 0 | n/a
1.1.2 | Horn 1 Module Installation | M | THC | 0 | 0 | 0 | n/a
1.1.2 | Horn 2 Module Installation | M | THC | 0 | 0 | 0 | n/a
1.1.2 | Target Pile Shielding Installation | M | THC | 0 | 0 | 0 | n/a
1.1.2 | T-Block Installation | M | THC | 0 | 0 | 2004-08-23 08:00 | n/a
1.1.3 | Kicker PS installation | 0 | TSR | 0 | n/a | 0 | n/a
1.1.3 | Horn Power supply Installation | M | TSR | 0 | EN + review to come (includes TL) | 0 | EN + review to come
1.1.3 | transmission line installation | M | TH,TSR | 0 | Horn PS & TL installation EN together | 2004-04-19 08:00 | Horn PS & TL installation EN together
1.1.4 | US decay pipe end cap installation | 0 | 0 | 0 | 0 | 2003-11-24 | 0
1.1.4 | DS decay pipe end cap installation | M | AH | 0 | 0 | 2004-09-27 08:00 | 0
1.1.4 | Absorber stacking procedure | 0 | 0 | 0 | HA needed | 0 | n/a
1.1.5 | Muon Monitor Installation | 0 | MA1,MA2,MA3 | 0 | 0 | 2004-03-29 08:00 | 0
1.1.5 | Hadron monitor Installation | M | AH | 0 | 0 | 2004-10-14 08:00 | 0
1.1.7 | Absorber RAW system Installation | R | in Absorber access tunnel | 0 | 0 | 2004-02-02 | 0
1.1.7 | Target RAW system Installation | R | in Absorber access tunnel | 0 | 0 | 2004-04-05 | 0
1.1.7 | Horn 1 and 2 RAW system Installation | R | in Absorber access tunnel | 0 | 0 | 2003-10-30 | 0
1.1.8 | Cable installation | 0 | 0 | 0 | n/a | 2004-03-08 | n/a?
Note on E1: HTML Source: http://www-numi.fnal.gov/numwork/reviews/
Note on F1: M = Mechanical G = Flammable Gas E = Electrical F = Fire ) = ODH R = Radiation T = Toxic Material