Mission B

LS Contract	Contract Name	DETAILED STATUS	Launch Date / Site	Configuration

LSM	Jane Doe	Jan-01	/	CCAFS	7X25	10

Element	Description	Budget	 Encumb/Liens	Available

TOTAL	XX,XXX	XX,XXX	XXX

Basic Launch Services	xx,xxx	xx,xxx	0

Contract Mods	xx,xxx

055	CLIN 15AC2 - XTH GEM	x,xxx

055	CLIN 15CG-1 - SPACECRAFT DESPIN SYSTEM	xxx

055	CLIN 15H - 10FT FAIRING	x,xxx

055	CREDIT CLIN 15CK-1 UPPER STAGE TUMBLE 	-xxx

055	CREDIT CLIN 15G  9/5 FT FAIRING	-x,xxx

055	EXERCISE CLIN B -MISSION B 7X25-10	xx,xxx

Liens	x,xxx

Mod 055	Incentive for CLIN B - $802,289 each	x,xxx

Mission Uniques	X,XXX	X,XXX	XXX

Contract Mods	x,xxx

055	CLIN 15CA-1 PAYLOAD ENVIRON. CLASS 10K	xx

055	CLIN 15CB-1 FAIRING INTERNAL CLEANING TO 500 A	xxx

055	CLIN 15CD-1PAYLOAD PURGE LINE	xx

055	CLIN 15CL-1 PAYLOAD PURGE	xx

055	CLIN 15M 24" DIAMETER DOOR	xxx

086	CLIN 15K-1	xxx

086	CLIN 15K-2	xxx

091	GN2 PURGE LINE

100	REVISE Mission B PAYMENT SCH

108	REVISE PAY SCH-MISSION B;REMOVE UNUSED

111	ATP WITH MISSION PECULIAR ACTIVITIES-TYPE I 	xxx

116	REVISE MISSION B PAYMENT SCH

120	DESIGN, FABRICATE, & INSTALL  AND EXTENDED 	xxx

127	ATP FOR NS SERV-DESIGN & BUILD 2 HAT

131	IMPLEMENT CLIN 15AF-1 2 TIMES	xx

131	IMPLEMENT CLIN 15AF-2 5 TIMES	xx

136	DEFINITIZE CO 127 & EQUIT ADJ FOR HAT 	xxx

143	CHG EXISTING A/C SHROUD TO REDUCE RF

149	ATP WITH MISSION PECULIAR ACTIVITIES/3RD

153	DEFINITIZES CO 149-3RD STAGE BLANKET 	xx

179	Credit CLIN 15CB-1	-xxx

179	Exercised CLIN 15BF-1	xxx

179	Fabricate, Test and Install Thermal Isolation Ring 	xxx

Task Assignments	x,xxx

ML-019R1	INTEGRATION MEETING	xx

ML-041R1	DRAFT MISSION SPECIFICATION	xx

ML-042A	COUPLED LOAD ANALYSIS	xx

ML-044	UPDATED TRAJECTORY	xx

ML-054	COUPLED LOAD ANALYSIS	xx

ML-063	MISSION INTEGRATION MEETING	xx

ML-097	TESTING SUPPT	x

ML-107R4	GN2 PURGE STUDY	xx

ML-109	COUPLED LOAD ANALYSIS	xx

ML-122R3	SPECIAL GN2 PURGE TEMP STUDY	xxx

Monday, May 21, 2001	2:25:24 PM

MISSION B

LS Contract	MED-LITE	DETAILED STATUS	Launch Date / Site	Configuration

LSM	Bobbi Gnan	Jan-01	/	CCAFS	7X25	10

Element	Description	Budge	 Encumb/Liens	Available

ML-055	DELTA PRE-MECO AND MECO EVENTS	xx

ML-132R7	RADIO FREQ MONITOR TEST	xx

ML-135	DUAL TMIG FEASIBILITY STUDY	xx

ML-136R2	MASS CAPABILITY STUDAY AT 95%	xx

ML-141R2	EARLY CONTROLS & STRUCTURAL DYNAMICS	xx

ML-144R3	RF ATTENUATION OF THE C-BAND	xx

ML-147R2	TRAJECTORY ANALYSIS	xx

ML-149R1	PRE-ENVIRONMENTAL TEST REVIEW	xx

ML-151R2	RF HAZARD ANALYSIS	xx

ML-153R2	MISSION B SECOND DTO	xxx

ML-154R1	3RD COMPATIBILITY DRAWING/DSS & BL	xx

ML-155	LSP SUPPT-MISSION B TRAJECT REVIEW	xx

ML-158	LSP SUPPT-MISSION B VIBRATION TEST	xx

ML-160R2	RF SHIELD KIT FOR THE 10' FAIRING	xx

ML-170	CANCELLED/COMBINED BACK WITH ML-153

ML-171	New PAF/Third Stage Spacer for Lateral Load Relief	xx

ML-173	Red Team Mission Unique Review	xx

ML-175	RF Shield for the Fairing A/C adapter	xx

ML-176	Pedigree Review for the MISSION B Launch Vehicle	xx

ML-177	Expanded Flight Operations Support	x

ML-182	Third Stage and PAF Cleaning to CV-5	xx

Launch Delay-Mods	x,xxx

Mod 138	REVISES TARGET LAUNCH DATE FROM 11/7/00 TO 	x,xxx

Mod 154	REVISE TARGET LAUNCH DATE FROM NET 12/18/01 	xx

Mod 155	REVISED TARGET LAUNCH DATE FROM NET 1/22/01 	xxx

Launch Delay-Liens	xxx

ME-113/MOD 175	LAUNCH DATE CHG FROM 1/22/01 TO 1/30/01	xxx

Liens	xxx

Claim for Vehicle Processing - Star 48 motor at Astrotech	xxx

Pedigree Review	xxx

Payload Processing	YYY	YYY	0

Cost (Accrual/Disb)	yyy

CC-12345B	Credit Card Purchases (Misc PRs)	yy

CC-12345B	yy

CC-12345B	y

CC-12345B	USAF 45th S/W PAFB	y

NASZ-ZZZZZ	PGOC Payload Processing (3 records)	yyy

NASZ-ZZZZZ	SGS Payload Processing	y

Outstanding Obligation	yyy

CC-87456B	USAF 45th S/W PAFB	y

NASZ-ZZZZZ	SGS Payload Processing	yy

Liens	yyy

$YY0,000 Budget	PAYLOAD PROCESSING Gov't PPF SAEF 2 to complete	yyy

Telemetry Support	ZZZ	ZZZ	0

Liens	zzz

Anticipated Telemetry & Ground Station HBK	zzz

TELEMETRY - Budget $ZZZ	zz

Monday, May 21, 2001	2:25:24 PM