Human Capital Readiness Line of Business

Crosswalk between GBFEB activities and OPM mandates

| OPM Lines of Business | GBFEB Status | Status | Notes/Comments |
| --- | --- | --- | --- |
| Establish REGIONAL Human Capital Council by 6/30/06 | Yellow |  | GBFEB Council established 10/06 with USDA/FNS as Lead Agency. |
| Identify Council Members by 6/30/06 | Green | Completed |  |
| Develop charter for the Council by 9/30/06 | Green | Completed |  |
| Promote OPM Approved Human Capital Programs (OPM webpage) | Green | In process | Executive Director to research and identify approved programs that meet this requirement. Council needs to recommend programs for approval to promote for FY07. |
| Promote FEB Approved Human Capital Programs 9/30/06 | Yellow | In process | Research and identify existing GBFEB programs that meet this requirement. Council needs to recommend GBFEB programs for approval to marketing/outreach for FY07. |
| Sponsor Two Human Capital Best Practices Forums by 9/30/2007 | Yellow |  | Expand of existing/ongoing GBFEB programs, initiatives and activities to meet FY07 requirement. |
| Government-wide Recognition Programs | Green | In process. | Public Service Recognition Week; Excellence in Government Awards; Support Personnel Awards Program; and Congressional Memorial Awards. |
| Succession Planning | Yellow | In process | Survey GBFEB members to identify areas of interest/need. Council to make recommendations based on results. |
| Promote Agency Performance Management System Programs | Red |  | Executive Director to research and obtain clarification necessary to define LOB. Council needs to determine and recommend action steps to meet requirement. |
| Sponsor Two Human Capital Training programs based on local needs by 9/30/2007 | Green | In process | Survey GBFEB to determine local needs. Council to make recommendations based on results. |
| TBD | Green |  |  |
| TBD | Green |  |  |
| Monitor ADR Programs throughout FEB service area and complete a cost/benefit analysis for service expansion by 9/30/2007 | Yellow | In process | Continue to monitor and evaluate GBFEB Shared Neutrals Program, including utilization in FEB service area. Council to make recommendations on potential service expansion. |
| Market FEB recruitment and retention services to member agencies and conduct two Public Service Outreach events by 9/30/2007 | Green |  | Recommendation needed to Board as to whether any shift is warranted based on local needs for FY08. |
| Recruitment and Retention Services | Green |  |  |
| Recruitment | Green | In process | Priority services are 1.i and 1.ii. Other as resources permit. |
| Campaign to Promote Public Service and Federal Employment | Green |  | FY07 student targets: (1) Hispanic (2) Disabled. Develop outreach plan that defines roles and responsibilities, FY07 GBFEB goals/objectives, strategies to achieve objectives, and outcome/output measures. |
| Partnership for Public Service Program | Green |  | Develop outreach plan that defines roles and responsibilities, FY07 GBFEB goals/objectives, strategies to achieve objectives, and outcome/output measures. |
| Other: FEB 101 Sessions; Informational briefing meetings with new agency heads (includes GBFEB informational package); “What Public Service Means to Me” Scholarship Program | Green |  |  |
| Retention | Green | In process |  |
| Award Programs: Support Personnel Awards; Excellence in Government | Green |  | Executive Director to schedule. |
| Shared Neutrals Program | Green |  | Summer 07 Strategic Planning session to include discussion on building GBFEB capacity. |
| Pre-retirement Seminar | Green |  | Summer 07 Strategic Planning session to include discussion on possible expansion to mid-career employees. |
| Public Service Outreach Events | Green | In process | Existing activities: Outreach to Veterans (dissemination of information relating to programs and services available in the Federal Service); Campaign to Promote Public Service and Federal Employment event; “What Public Service Means to Me” Scholarship Program |
| TBD | Green |  |  |
| TBD | Green |  |  |

12/21/06

Emergency Preparedness, Employee Safety and Secuurity Line of Business

Crosswalk between GBFEB activities and OPM mandates

FY 2007

| OPM Lines of Business | GBFEB Status | Note / Comments |
| --- | --- | --- |
| 1. Implement an Emergency Planning Intergovernmental Working Group or Committee | Yellow | In process |
| a. Identify Members | Yellow | In Process COOP Working Group and other Federal EP officials represented. Will continue to on developing stronger, more formal state / local relationships. |
| b. Articulate Leadership | Yellow | In Process EPA New England will call a meeting of principals in January 2007 |
| c. Establish a Charter / mission | Red | Estimated January 2007 – following EPA meeting |
| d. Establish communication / meeting plans | Red | Estimated January 2007 – following EPA meeting |
| Implement an “All Hazards Emergency Plan | Green | In place since 2004. Launched just prior to the Democratic National Convention. Leverage current FEB Homeland Security Committee / COOP Working Group. Build on opportunities to connect with state and local government provided by FEMA. |
| Establish a 24/7/365 database of contacts for agencies; | Green | Completed 95 % agency participation |
| b. Develop 24/7/365 communications system | Yellow | In Process Working to refine or seek alternatives to: EDIAL telephone communications system (provided by GSA) and Federal Protective Service web portal (provided by DHS / ICE / FPS.) Work group to review protocol re: activation of these communication systems, appropriate distribution of contact information and schedule for updating contact information and systems. |
| Establish succession plan (and ensure that person / organization has devices) | Yellow | In process Council to discuss plan; Protocol re: Weather - succession established 12/06 |
| To the best of our ability and resources, collect and share information to and from Headquarters establishments within 24 hours (i.e. policy guidance, pay and leave, request for information; | Green | Ongoing / Completed Liaison with OPM, White House, GSA, OMB Example: Distributed OPM’s Human Capital Guidance re: pandemic flu and White House Plan |
| Provide Emergency Management Training, Educational Programs and Technical Assistance to our Members | Green | Ongoing / Completed In the first quarter of FY 2007, we hosted a Be Ready “train the trainer” seminar, a Seminar on Pandemic Flu and a tabletop exercise on Pandemic flu |
| Engage State and Local Officials on Workforce Planning Issues | Yellow | Expand upon outreach efforts with State and Local counterparts. Some progress has been made but no formal relationship has been established. In 2007, we will engage with FEMA’s existing Regional Interagency Steering Committee (RISC), that includes Federal emergency managers, law enforcement and first responder as well as state and loccal partners. We will engage in FEMA’s new Emergency Support Function -ESF 15 – External Affairs – as it evolves. |

12/21/06