## Budget Control and Summaries
2005-09-08 23:27 | version: | 5 | (5=changes post-MRI05: OD slot width)
| nsf, doe, mri? | doe | controls the EPO section and detector scope in the case of the “MRI” flag
contingency: | yes or no? | no
spares: | yes or no? | yes
Param: Work hours/yr | 1750 | assume 85% efficiency on 2080 hrs
Parms: Work hours/wk | 33.6538
Param: PAS machine shop | 48 | FY06 costs
Param: Rochester Mech Eng | 65 | FY06 costs
Param: FNAL-resident Tech | 37.7143 | FY05 costs
Param: Eileen's FNAL tech I | 26 | as per Eileen, 8/15/05, includes “OPTO/VAC/FRINGE”. Does this include G&A? not sure
Param: Eileen's FNAL tech specialist | 52 | as per Eileen, 8/15/05, includes “OPTO/VAC/FRINGE”. Does this include G&A? not sure
Param: Eileen's lab assistant | 20 | as per Eileen, 9/6/05, includes “OPTO/VAC/FRINGE”. Does this include G&A? not sure
Param: Roch Grad Student | 0 | would be $25.6K stipend+fringe -> $33.0K
BoE Categories | Contingency | Cat. ID
vendor quote | 10% | 1
vendor quote, Yen or Euro sensitivity | 30% | 1a
factory as previously built | 20% | 2
one-time as previously built | 30% | 3
designed | 40% | 4
FNAL (Eileen) | 40% | 5
Labor Roll-Ups | Hours |  | Months
Cable/ODU Labor (WBS 4)
Rochester Mech Eng | 134.1923 |  | 0.92018
Rochester Rochester PAS Machinist | 1155 |  | 7.92
Rochester Technicians | 7883.3538 |  | 54.0573
FNAL Technicians | 1381.5556 |  | 9.4735
WLS Fiber Labor (WBS 2)
Rochester Mech Eng | 0 |  | 0
Rochester Rochester PAS Machinist | 0 |  | 0
Rochester Technicians | 275 |  | 1.8857
FNAL Techs | 3307.34 |  | 22.6789
Contingency Categories
Sub-category roll-ups | current calc. |  | w/ cont | w/o cont | cont frac. |  | BoE Type | BoE Source
Cable/ODU (WBS 4)
optical cable tester M&S | 9650 |  | 13510 | 9650 | 40% | 4, | as-realized and engineering estimate costs | UR CMS light injector (2004); as-realized costs for hardware; engineering design and vendor quotes for DAQ
optical cable tester design | 3250 |  | 4225 | 3250 | 30% | 4, | as-realized and engineering estimate costs | UR CMS light injector (2004); as-realized costs for hardware; engineering design and vendor quotes for DAQ
optical cable tester assembly | 3428.5714 |  | 4457.1429 | 3428.5714 | 30% | 4, | as-realized and engineering estimate costs | UR CMS light injector (2004); as-realized costs for hardware; engineering design and vendor quotes for DAQ
optical cable mapper M&S | 760 |  | 1064 | 760 | 40% | 4, | physicist estimate | estimate from physicist generated parts list, experience with UR CMS light injector (2004)
optical cable mapper design | 1312.5 |  | 1837.5 | 1312.5 | 40% | 4, | physicist estimate | estimate from physicist generated parts list, experience with UR CMS light injector (2004)
optical cable mapper assembly | 2949.2308 |  | 4128.9231 | 2949.2308 | 40% | 4, | physicist estimate | estimate from physicist generated parts list, experience with UR CMS light injector (2004)
connector M&S | 84621.69 |  | 110962.917 | 84621.69 | 31.13% | 1a, | vendor quote | Fujikura/DDK USA, July 2005 quote
clear fiber M&S | 182486.6585 |  | 238687.1561 | 182486.6585 | 30.8% | 1a, | vendor quote | Kuraray in MINERvA quantity, October 2004; shipping based on extrapolation from smaller quantity, June 2004
QC equipment | 9835 |  | 13023.5 | 9835 | 32.42% | 1,4 | vendor quotes, physicist estimate | based on early MINERvA prototyping studies
clear fiber QC labor | 3394.2857 |  | 4752 | 3394.2857 | 40% | 4, | physicist estimate | based on early MINERvA prototyping studies
gluing | 9142.52 |  | 11191.124 | 9142.52 | 22.41% | 1,2 | direct extrapolation from as-realized costs, vendor quotes | UR CDF Enplug upgrade (1994) experience with same connectors; vendor quotes for items
light-tighting M&S | 21734.614 |  | 29388.7494 | 23771.2806 | 23.63% | 2,4 | direct extrapolation from as-realized costs of different project, physicist estimate | MSU STAR cable construction in 2004
light-tighting design | 4160 |  | 5460 | 3900 | 40% | 4, | direct extrapolation from as-realized costs of different project, physicist estimate
light tighting fixture prod. labor | 51840 |  | 70464 | 53760 | 31.07% | 2,4 | direct extrapolation from as-realized costs of different project, physicist estimate
other cable consumables | 298.615 |  | 418.061 | 298.615 | 40% | 4, | physicist estimate, based on as-realized cost of other projects | UR CDF Enplug upgrade (1994) experience with same connectors; vendor quotes for items
cable production labor | 291142.9714 |  | 407600.16 | 291142.9714 | 40% | special | extrapolation from as-realized costs (contingency reflects spread in different projects) | MSU STAR cable construction in 2004 and UR CDF Endplug (1994), as realized. STAR cost (most applicable project) is lower; used CDF/STAR average with CDF cost as contingent; labor costs from extrapolation of hours and UR rates
polishing consumables (bits, etc.) | 76278.5 |  | 115430.2 | 76278.5 | 51.33% | 2, | direct extrapolation from as-realized costs | as-realized costs from Eileen Hahn (FNAL Lab 8) from multiple projects, most recently GLAST (2003); assumes Rochester cannot get special FNAL price of $112 but instead $150
polishing labor | 57907.7778 |  | 83626.4 | 57907.7778 | 44.41% | 5, | direct extrapolation from as-realized costs | as-realized costs from Eileen Hahn (FNAL Lab 8) from multiple projects, most recently GLAST (2003); assumes Rochester cannot get special FNAL price of $112 but instead $150
Category Total | 814192.9346 |  | 1120226.8334 | 817889.6012 | 36.97%
WLS Fiber (WBS 2)
WLS fiber M&S | 455588.0443 |  | 598394.5576 | 455588.0443 | 31.35% | 1a,4 | vendor quote | Kuraray in MINERvA quantity, October 2004; shipping based on extrapolation from smaller quantity, June 2004
WLS fiber QC labor | 6600 |  | 9240 | 6600 | 40% | 4, | physicist estimate | based on early MINERvA prototyping studies
mirroring M&S | 12247.4914 |  | 17146.4879 | 12247.4914 | 40% | 5, | direct extrapolation from as-realized cost | as-realized costs from Eileen Hahn (FNAL Lab 8) from multiple projects, most recently GLAST (2003); assumes Rochester cannot get special FNAL price of $112 but instead $150
prototype mirroring labor | 1483.24 |  | 2076.536 | 1483.24 | 40% | 5, | direct extrapolation from as-realized cost | as-realized costs from Eileen Hahn (FNAL Lab 8) from multiple projects, most recently GLAST (2003); assumes Rochester cannot get special FNAL price of $112 but instead $150
production mirroring labor | 90197 |  | 126275.8 | 90197 | 40% | 5, | direct extrapolation from as-realized cost | as-realized costs from Eileen Hahn (FNAL Lab 8) from multiple projects, most recently GLAST (2003); assumes Rochester cannot get special FNAL price of $112 but instead $150
shipping from FNAL to VA factories | 13771.4286 |  | 19280 | 13771.4286 | 40% | 4, | physicist estimate | MSU STAR cable construction in 2004 and UR CDF Endplug (1994), as realized. STAR cost (most applicable project) is lower; used CDF/STAR average with CDF cost as contingent; labor costs from extrapolation of hours and UR rates
Category Total | 579887.2042 |  | 772413.3815 | 579887.2042 | 33.2%

## DetectorParameters
Grand Totals
Number of Channels | 30992 | 0.8095
Channels in ID+CALS | 25088
Channels in OD | 5904
Volume of Scintillator (m^3) | 19.8073 | 7818840.9375 | 4951932.5937 | 4437811.4928 | 2598693.338 | 0
Embedded WLS Fiber Length (cm) | 5558249.422
Routed WLS Fiber Length (cm) | 3052568.48
Total WLS Fiber Length (km) | 86.1082
Clear Fiber Length (km) | 39.6056
Number of M-64s | 503
Empty M-64 Channels | 1200
Mass of ID (metric tons) | 10.7721
Mass of OD in ID region | 93.2082
Mass of CALS | 25.6239
Mass of OD in CAL region | 59.7845
Total MINERvA Mass | 189.3887
Plastic Region Mass (metric tons) | 5.8664
Data Rate (bits/spill) | 7933952
Channels in MR | 0
Channels in Veto | 0
Mass of MR | 0
Mass of Veto | 0
Detector Parameters | Current | Proposal design
Number of ID fully active modules | 30 | 30
Number of US Ecal | 6 | 6
Number of US Hcal | 3 | 3
Number of DS Ecal | 5 | 5
Number of DS Hcal | 5 | 5
Number of DS Muon Ranger | 0 | 3
Number of US Veto | 0 | 0.5
Planes(view) per module | 4
Scint Thickness (cm) | 1.7 | 0.66929
Scint Strip Width (cm) | 3.3 | 1.2992
ID/OD Gap (cm) | 5.08 | 2 | assuming need to bend 1.1inches when bend radius of >2.5” and that coil assemblies are 2” thick
Module Spacing (cm) | 0.635 | 0.25
Absorber Parameters
US ECAL Absorber Thickness (cm) | 0.19844 | 0.078125
US HCAL Absorber Thickness (cm) | 0.635 | 0.25
DS ECAL Absorber Thickness (cm) | 0.19844 | 0.078125 | needs to be 5/64”
DS HCAL Absorber Thickness (cm) | 2.54 | 1
ID “Absorber” Thickness (cm) | 0.2 | 0.07874 | this is the maximum of the Pb absorber and routing plate thickness
ID Pb Ring Width (cm) | 15 | 5.9055 | ok to be metric
ID Parameters
ID Strips per plane | 128
ID Minor Diameter | 209.55 | 82.5 | this should be exact since strips are extruded
Minimum Inner Height | 120.9837
Maximum Inner Height | 241.9675
Mean Inner Height | 181.4756
Total ID strips | 15360
Total ID M-64s | 240
Total ID scint volume (cc) | 7818840.9375
Side ECAL Absorber Volume (cc) | 242618.7489
Total ID Mass (Pb+Scint) (tons) | 10.7721
Calorimeter Parameters
US ECAL Strips | 3072
US HCAL Strips | 1536
DS ECAL Strips | 2560
DS HCAL Strips | 2560
Total CAL Strips | 9728
Total CAL M-64s | 152
US ECAL Absorber Volume | 181109.3829
DS HCAL Absorber Volume | 904346.7223
US ECAL Absorber Volume | 150924.4857
DS HCAL Absorber Volume | 6028978.1484
US ECAL Scint Volume | 1563768.1875
US HCAL Scint Volume | 781884.0937
DS ECAL Scint Volume | 1303140.1562
DS HCAL Scint Volume | 1303140.1562
US ECAL Mass (tons) | 3.6401
US HCAL Mass (tons) | 7.0849
DS ECAL Mass (tons) | 3.6246
DS HCAL Mass (tons) | 11.2742
Common OD Parameters
ID Planes per OD Plane | 2
Width of Slot for Active Elements | 2.54 | 1 | 1" is spec for flame cut (previously was width plus 1/4" but revised as per vendor minimum supported)
Width of Active Elements | 1.9 | 0.74803 | DOE proposal onward has 1.9cm (approx. square) extrusions, (previously was 1")
Steel width #1 | 5 | 1.9685 | agrees with English units drawing to one mil
Steel width #2 | 10 | 3.937 | agrees with English units drawing to one mil
Outer Steel width | 10 | 3.937 | agrees with English units drawing to one mil
OD Steel Thickness | 3.81 | 1.5
Main OD Parameters
Active Elements per Tower | 6
Independent Elements per Tower | 12 |  | a tower is 1/6 of a hexagon
Total Modules covered by OD | 25 |  | this does not cover first 15 modules of ID nor US CALs
Total OD frames | 50
Total Towers | 300
Total OD Channels | 3600
Total OD Strips | 3600
Total OD M-64s | 75
Number of Steel #1 | 2
Number of Steel #2 | 4
Total width | 75.24 | 29.622
Minimum OD Minor Radius | 109.855 | 86.5
Maximum OD Minor Radius | 185.095 | 145.7441
Minimum Side Length | 126.8496 | 49.9408
Maximum Side Length | 213.7293 | 84.1454
Mean Side Length | 170.2895
Total OD scint volume (cc) | 4437811.4928
Total OD Steel volume (cc) | 11678451.2969
Total Routing Plate volume (cc) | 5125.0316
Length of the OD | 257.175 |  | this calculation embeds information about which planes are included
Total Minor Diameter | 370.19
Total Major Diameter | 427.4586
Mass of OD (Scint+Steel+Routing) | 96.4899
Mass of OD in ID region | 57.894 |  | this calculation embeds information about which planes are included
Mass of OD in DS ECAL region | 19.298
Mass of OD in DS HCAL region | 19.298
Thin OD Parameters
Active Elements per Tower | 4
Independent Elements per Tower | 8 |  | a tower is 1/6 of a hexagon
Modules covered by this OD | 24 |  | this covers first 15 planes of ID and US CALs
Total OD frames | 48
Total Towers | 288
Total OD Channels | 2304
Total OD Strips | 2304
Total OD M-64s | 36 |  | two module/two side granularity assumed
Number of Steel #1 | 2
Number of Steel #2 | 2
Total width | 50.16 | 19.748
Minimum OD Minor Radius | 109.855 | 86.5
Maximum OD Minor Radius | 160.015 | 125.9961
Minimum Side Length | 126.8496 | 49.9408
Maximum Side Length | 184.7694 | 72.7439
Mean Side Length | 155.8095
Total OD scint volume (cc) | 2598693.338
Total OD Steel volume (cc) | 6838666.679
Total Routing Plate volume (cc) | 3126.1622
Length of the OD | 210.5025 |  | this calculation embeds information about which planes are included
Total Minor Diameter | 320.03
Total Major Diameter | 369.5388
Mass of OD (Scint+Steel+Routing) | 56.5028
Mass of OD in ID region | 35.3143 |  | this calculation embeds information about which planes are included
Mass of OD in US ECAL region | 14.1257
Mass of OD in US HCAL region | 7.0629
MR/Veto Parameters
Strips per plane | 219
Minimum Strip Length | 213.7293
Maximum Strip Length | 427.4586
Mean Strip Length | 320.5939
MR/Veto Absorber Thickness | 10
Total MR/Veto Channels | 0
Total MR/Veto M-64s | 0
Total MR/Veto Scint Volume | 0
MR/Veto Abs Volume | 0
Length of the MR | 0
Mass of MR (metric tons) | 0
Length of the Veto | 0
Mass of Veto (metric tons) | 0
Densities
“Pb” Absorber Density | 11.2056 |  | Lead Calcium (0.065%) Tin (1.5%) Alloy (fractions by weight)
Scint Density | 1.03
Steel Density | 7.87
Routing Plate Density | 1.87
Alloy Worksheet |  | weight frac | density | volume frac
Our Ca/Sn hardened lead alloy | Pb | 0.98425 | 11.35 | 0.97153
| Ca | 0.00065 | 1.55 | 0.0047597
| Sn | 0.015 | 7.31 | 0.02329
| Al | 0.0001 | 2.7 | 0.00042037
Clear Fiber Cable Length |  | PMT Boxes at 10, 12 and 2 O'Clock on the detector
ID, CALs, MR, Veto per fiber | 131.8646 | ID fibers are WLS out to connector at edge of pan at 9 (U), 11 (X and U), 1 (X and V), 3 (V) O'Clock, then need to bring to the nearest PMT box. Assume half the length of an outer side; add 25cm slop
OD per fiber | 110.4917 | OD fibers are WLS out to connector at edge of pan. Connector at 8, 10, 12(x2), 2 and 4 O'Clock. All local (only slop) except 8 and 4 O'Clock (1/3 of total) which require 1.2*OD. Add 25cm slop
ID Total | 2025440.9944
US ECAL ID | 405088.1989
US HCAL ID | 202544.0994
DS ECAL ID | 337573.4991
DS HCAL ID | 337573.4991
MR/Veto | 0
OD | 652343.1058
Grand Total | 3960563.3967
Note on B6: Assumes joint strips in OD share a fiber
Note on B7: Assume OD thickness*1.3 for ID channels and half that for OD channels, plus 10cm for pigtail
Note on B18: revised calcuation per Dave C. (9 Jan 2005): 2 16 bit ADCs per channel, 4 times slices; add an equal amount of data for timing readout (no sparsification)
Note on B40: Kevin McFarland: all of the material is in one signal plane at the front of the module. This is the thickness PER PLANE
Note on B41: all of the nuclear target material is in one single plane at the front of the modules, 2.5cm/4
Note on B49: Remember: one strip on edge must be halved to round off with square!
Note on B90: Under the assumption that we use two fibers per OD extrusion
Note on B95: One strip per two fibers
Note on B96: Assumed granularity is 2 sides and per module
Note on B105: Uses the mean side length to estimate mean strip length
Note on B106: Use mean side length to estimate mean absorber length
Note on B111: This doe not include HCAL plates that extend into the OD
Note on B118: Under the assumption that we use two fibers per OD extrusion
Note on B123: One strip per two fibers
Note on B124: Assumed granularity is 2 sides and per TWO modules
Note on B133: Uses the mean side length to estimate mean strip length
Note on B134: Use mean side length to estimate mean absorber length
Note on B139: This doe not include HCAL plates that extend into the OD
Note on B149: Kevin McFarland: actually it's two modules of 15cm steel and one with no steel. This is the average.
Note on B163: Assume G-10

## Fiber and Connector Costs
Revised cost or spare fraction
New item
Requires Revision?
| Units to Build |  | Spare Fraction | Waste Fraction | Relative To | Notes
| WLS Fibers | 33936 | 7.353% | 2% | channel count | sensible, but we need feedback from Jeff.
| WLS Fiber Length (cm) | 10159847.5166 |  | 7.754% | WLS fibers | 0.8% waste from cut-back QC test (25m/3km)+0.8% waste from mirroring (2.5cm but 3m fiber length)+1% breakage+5% (guess) waste from left-over length in canes
| Clear Fiber Cables | 4603 | 10% | 4% | PMT count | 10% spares, 4% destroyed in production
| Fiber Length in Cables (cm) | 4890913.4234 |  | 7.957% | Cables | 0.8% waste from cut-back QC test (25m/3km)+2% waste from cut/polish (2.5cm, avg. length of 1.2m)+5% (guess) waste from left-over length in canes
| Optical Decoder Units (PMT boxes) | 2287 | 9.3% | 4% | PMT count | need # of Tony's box production count (550 produced, 503 needed, 9.3%), 4% destroyed in production
| Length of Fiber in finished ODU (cm) | 50 |  |  |  | 50cm per ODU fiber: final product per box <8” needed length+5cm extra for cookie installation (double this for ODU), undoubtedly still an overestimate
| Fiber Length in ODUS (cm) | 1936448.64 |  | 5.84% | ODUs | 0.8% waste from cut-back QC test (25m/3km)+4% waste from cut/polish (2.5cm, avg. length of 0.5m)
| Cable and ODU connectors | 13780 |  |  |  | derived
| Pan Connectors | 4242 | 7.353% | 2% | channel count | sensible, but we need feedback from Jeff.
| All Connectors | 18022 |  |  |  | derived
| Fiber and Connector Costs |  | Notes
| Prototype Connector Cost (per unit) | 6.12 | Fujikura cost estimate for prototype quantity, summer 2005 ($4.40/unit+$3.44/box); includes shipping?
| Connector Cost (per unit) | 2.895 | Fujikura cost estimate for bulk, original summer 2004 ($2.51/unit, including box); summer 2005 revisit got ($2.51/unit + $0.77/box); includes shipping?
| WLS Fiber Cost (/m) | 3.25 | Kuraray quote Y11(175ppm), J-type, S-35 fiber, July 2005, based on 88km quantity. Shipping included? |  |  |  |  | 29.48% | increase since Sept 2004
| Clear Fiber Cost (/m) | 2.06 | Kuraray quote CLEAR-PSMS-35J, 1.2mm, July 2005, based on 42km quantity. Shipping included? |  |  |  |  | 11.96% | increase since Sept 2004
| Mirrors (per WLS fiber) | 2.37 | Eileen via Howard (including G&A)
| Cable Manpower |  | Notes
| Tech-hours/ODU | 0.92 | revised estimate from Howard 17 August 2005, 0.92 hrs/cable, contingency must include at least 1.1 hrs/cable (which is 20%). I go for 30%
| Tech-hours/cable for light tight | 0.3 | revised estimate from Howard, 17 August 2005
WBS | Cable and Connector Parts Costs | M&S | EDIA | Labor |  | Notes
| Optical Cable Tester (sub-category) |  |  |  |  | quantity (1), built by Rochester
| GPIB Interface and Cable | 600
| Lab View License | 1000 |  |  |  | academic price
| Windows DAQ Computer | 0 |  |  |  | donate from existing Rochester stock
| Keithley 7001 Switching System | 2500 |  |  |  | approx. catalog prices
| Keithley 6485 Picoameter | 1250 |  |  |  | “
| Keithley 7058 Scanning Card | 1000 |  |  |  | “
| Parts for Optomechanical Bench | 3300 |  |  |  | way inflated cost based on Budd design for CMS HCAL light injector (2004); parts cost for this were ~$2300, incl. machining
| Machine Shop Time |  |  | 1920 |  | 40 hrs; based on Budd CMS HCAL light injector (2004); polishing fibers, plexiglas piece with pin diode; scintillator machining
note that aluminum machining for holders is included above in “parts” above
| Design of Optomechanical Bench |  | 3250 |  |  | 50 hrs; estimate a little over two weeks for design and assembly
| Physicist Oversight of Design |  |  | 0 |  | 60 hrs
| Assembly Time |  |  | 1508.5714 |  | 40 hrs
| Readout Assembly |  |  | 0 |  | 4 wks, graduate student, Rochester operating funds by common agreement
| Total OCT costs | 9650 | 3250 | 3428.5714
| Labor Gathered from Above | UR Engineer | UR Rochester PAS Machinist | UR Technician
|  | 50 | 40 | 40
| Optical Cable Mapper (sub-category) |  |  |  |  | quantity (1), built by Rochester
| Design |  | 1312.5 |  |  | 3 days, engineer
| Physicist Oversight of Design |  |  | 0 |  | 4 days
| LEDs, Filters, Power Electronics | 260 |  |  |  | HB estimate, aug '05
| Parts for Bench/Box | 500 |  |  |  | guess
| Machine Shop Time |  |  | 1680 |  | 35 hours, HB estimate, aug '05
| Assembly Time |  |  | 1269.2308 |  | 1 wk technician, HB estimate, aug '05
| Readout Assembly |  |  | 0
| Total OCT costs | 760 | 1312.5 | 2949.2308
| Labor Gathered from Above | UR Engineer | UR Rochester PAS Machinist | UR Technician
|  | 20.1923 | 35 | 33.6538
Connector Parts (sub-category)
| Prototype Connector Cost | 2448 |  |  |  | quantity 400, unit cost from above
| Connector Cost | 52173.69 |  |  |  | unit cost from above, n.b., includes Jeff's pan connectors
| Connector Mold (Ferrule Tooling) | 30000 |  |  |  | Fujikura cost estimate, original summer 2004; summer 2005 revisit got some #. Can this be right?
| Total Connector Costs | 84621.69
Cable Polishing Parts (sub-category)
| Param: Connectors/relap= | 45 |  |  |  | 42-48 is estimate from Eileen w/ 6 conn. fixture; Howard says 36 is very conservative
| Param: Relaps/diamond set= | 7.5 |  |  |  | 5 is "conservative" re-lap estimate from Eileen w/ 6 conn. fixture; Howard says 7-8 is realistic
| Derived: Diamond Sets Required= | 37 |  |  |  | derived, each set survives #relaps+1 cycles
| Derived: Total Relaps Required= | 271 |  |  |  | derived
| Cable Polishing Fixture (one time) | 5000 |  |  |  | Should use as-realized since this is done? Old cost: M&S Cost, Eileen via Howard (including G&A)
| Polishing Diamonds | 25900 |  |  |  | $700 unit cost
| Relapping Diamonds | 40650 |  |  |  | outside vendor,$150 per relap
| Carbide Bits | 3080 |  |  |  | $10 unit costs, one per diamond cycle
| Compressed Air Cans | 808.5 |  |  |  | $5.25 unit cost, 0.5 per diamond cycle
| Kapton Tape (rolls) | 448 |  |  |  | $28 unit cost, 0.05 per diamond cycle
| Misc. supplies | 392 |  |  |  | Eileen 8/16/05: “stock room+non-stock room (texwipes)” category
| Total Polish Supplies Costs | 76278.5
QC Equipment (sub-category)
| QC diamond polisher | 5550 |  |  |  | verbal quote (PM mfg) to HB, aug '05, including fixture
| ferrules QC/prototypes | 1785 |  |  |  | 700, HB aug '05 quote, Moore-Addison
| camera | 1000 |  |  |  | HB aug '05: Nikon D50 (bh web quote)+estimate for mount ($300)
| tooling for QC bench | 1500 |  |  |  | HB estimate, aug '05
| Total QC Equipment | 9835
Fiber for Cables and ODUs (sub-category)
| pre-forms required in order | 18 |  |  |  | maximum 3km of fiber in a pre-form, QC repeated each pre-form; add one for prototype fiber
| Clear Fiber for Cable Prototypes | 14541 |  |  |  | this is what is in Rochester 2005 SOW
| Production Clear Fiber | 140643.6585
| Shipping from Japan | 27302 |  |  |  | scaling freight fraction from prototype order. is shipping in quote?
| QC: tech time for cable |  |  | 3394.2857 |  | 5 hours per cut-back test cable
| QC: physicist time, analysis code |  |  | 0 |  | 1 physicist-week
| Total | 182486.6585 | 0 | 3394.2857
| Labor Gathered from Above | Rochester Mech Eng | Rochester PAS Machinist | Technician
|  | 0 | 0 | 90
Glue for Cables and ODUs (sub-category)
| Glue Station Tools | 1500 |  |  |  | previous estimate, less centrifuge costs
| Centrifuge | 480 |  |  |  | Fisher Scientific F49018 catalog
| Scale | 119 |  |  |  | Fisher Scientific S68724 catalog
| Refrigerator | 200 |  |  |  | 5cu ft fridge, Sears catalog item #04695499000
| BC600 Epoxy | 1722.5 |  |  |  | 125/unit, 1000 connectors/unit
| Glue Cups and Syringes | 987.02 |  |  |  | assuming 20 connectors/cycle, 3.5 cents/unit ($0.7 cup)+27 cents (syringe: EDF HPD,5110CP-B,5118-B, 0.73/unit cost+$35 fixed cost)
| Other consumables (tape, air, etc.) | 4134 |  |  |  | $.3 per connector
| Total | 9142.52
Other Consumables for Cables and ODUs (sub-category)
| Cable Storage Boxes | 207.135 |  |  |  | 50/box, 6”x6”x70” ($225/100 units, fast-box.com)
| ODU Shipping Boxes | 91.48 |  |  |  | 50/box, 6”x6”x40” ($100/50 units, fast-box.com)
| Total | 298.615
Cables and ODU Labor (sub-category)
| Prototyping Labor |  |  | 0 |  | have no estimate currently for prototyping time!!
| Cable Production Labor |  |  | 239063.3143 |  | see above for unit labor costs
| Light-Tighting Labor |  |  | 52079.6571 |  | see above for unit labor costs
| Total | 0 | 0 | 291142.9714
| Labor Gathered from Above | Rochester Mech Eng | Rochester PAS Machinist | Technician
| Prototyping (overlap with ODU) | 0 | 0 | 0
| Production |  |  | 7719.7
| Cable and ODU Polishing Labor (sub-category) |  |  |  |  | does Eileen's tech rate include FNAL G&A?
| param: polishes per hour | 36
| param: time to replace diam. (hrs) | 2
| derived: time for diamond cycle | 3.25
| derived: cycles per shift | 2
| derived: total shifts spent polishing | 153.1111
| Polish Connectors |  |  | 9952.2222 |  | 36/hr. tech I
| Diamond Exchange |  |  | 32032 |  | 2 hrs/change. tech spec.
| Machine Maintenance |  |  | 3980.8889 |  | 1hr/shift, tech 1. Shift is integral # of cycles.
| QC/Supervision |  |  | 11942.6667 |  | 1.5hr/shift, tech spec
| Total | 0 | 0 | 57907.7778
| Labor Gathered from Above | Tech 1 | Tech Spec.
|  | 535.8889 | 845.6667
Light-Tighting for Optical Cables (sub-category)
| param: # of molds | 20
| derived: # of mold cycles | 461
| Design and Prototype Molds | 1094 | 4160 | 5760 |  | design work cost is as realized (to date) including cost of building prototype, doubled.
| Mold Construction | 6912 |  | 46080 |  | estimated by RF after prototype, july 2005
| RTV | 5983.9 |  |  |  | 260/unit, 400 connectors/unit
| Black Shrink Tube | 6017.364 |  |  |  | $0.3/ft
| EDF Gluing Machine | 815.36 |  |  |  | HB Quote, EDF Ulltra 1400+100y5152-6 Adapter
| Syringe and Barrel | 759.19 |  |  |  | need 2*#cables/#mold units, HB quote (5113CP-B, 24.49/box of 15)
| Syringe Tip | 152.8 |  |  |  | need 2*#cables/#mold units, HB quote (5115-B, 15.28/box of 50)
| Total | 21734.614 | 4160 | 51840
| Labor Gathered from Above | Rochester Mech Eng | Rochester PAS Machinist | Technician
| Design | 64 | 120
| Production |  | 960
WLS Fiber (sub-category)
| pre-forms required in order | 35 |  |  |  | maximum 3km of fiber in a pre-form, QC repeated each pre-form; add one for prototype fiber
| WLS Fiber for Tests, Prototypes | 61295 |  |  |  | this is what is in Rochester 2005 SOW, including $38K supplement
| WLS Fiber | 330195.0443
| Shipping from Japan | 64098 |  |  |  | scaling freight fraction from prototype order. is shipping in quote?
| QC: tech time |  |  | 6600 |  | copied from clear fiber: 5 hours per cut-back test cable
| QC: physicist time, analysis code |  |  | 0 |  | copied from clear fiber: 1 physicist-week
| Shipping to Virginia Scint. Factories | 10000 |  | 3771.4286 |  | 100 hrs of tech time for shipping prep.
| Total | 465588.0443 | 0 | 10371.4286
| Labor Gathered from Above | Rochester Mech Eng | Rochester PAS Machinist | Technician
|  | 0 | 0 | 275
| WLS Mirroring |  |  |  |  | the strategy with this cost is just to scale from Eileen's very complex calculation
| prototype to ice polish&mirror | 200
| # of fibers per sputtering | 720
| # of test fibers per sputtering | 6
| derived: total number of test fibers | 288
| derived: total mirrored fibers | 34224 |  |  |  | does Eileen's tech rate include FNAL G&A?
| Prototype labor, lead tech |  |  | 299 |  | take from Eileen's R&D mirroring sheet (090605), scaled to # fibers above
| Prototype labor, tech |  |  | 659.88 |  | take from Eileen's R&D mirroring sheet (090605), scaled to # fibers above
| Prototype labor, lab assistant |  |  | 145.8 |  | take from Eileen's R&D mirroring sheet (090605), scaled to # fibers above
| Prototype labor, supervisor |  |  | 378.56 |  | take from Eileen's R&D mirroring sheet (090605), scaled to # fibers above
| Prototype Materials | 141.4914 |  |  |  | take from Eileen's production mirroring sheet (090605), scaled to # fibers above but doubled since prototype quantities
| Production labor, lead tech |  |  | 5989.36 |  | take from Eileen's production mirroring sheet (090605), scaled to # fibers above
| Production labor, tech |  |  | 51090.52 |  | take from Eileen's production mirroring sheet (090605), scaled to # fibers above
| Production labor, lab assistant |  |  | 17698.6 |  | take from Eileen's production mirroring sheet (090605), scaled to # fibers above
| Production labor, supervisor |  |  | 15418.52 |  | take from Eileen's production mirroring sheet (090605), scaled to # fibers above
| Production Materials | 12106 |  |  |  | take from Eileen's production mirroring sheet (090605), scaled to # fibers above
| Total | 12247.4914 |  | 91680.24
| Labor Gathered from Above | Tech 1 | Tech Spec. | Lab Assistant
| prototype | 25.38 | 13.03 | 7.29
| production | 1965.02 | 411.69 | 884.93