Executive Summary

César Chávez High School Case Study

Victor Forberger

Center for Urban and Regional Policy

Northeastern University

Throughout the 1990s, the Phoenix high school system has been under tremendous pressure to improve the education it provides.  The Arizona state government has at times been openly hostile to public schooling and its charter school law is one of the most liberal in the nation.  A classroom and a small number of students is generally sufficient to set up a charter school, draining revenue from the traditional public schools -- a problem made worse by the fact that per capita spending on public school students in Arizona already ranks near the lowest in the nation.  In addition, the state's heavy emphasis on standardized testing has led to the requirement that students pass a specialized exam starting in the 2001-2002 academic year to graduate high school.  Hence, the school district finds itself with growing competition from charter schools just when students must meet rigorous and unyielding standards of achievement.

At the same time the district has had the problem of managing one of the fastest growing school populations in the nation.  Much of that growth has been from Mexican-American and Native-American groups.  These groups historically have not received a great deal of educational advantages.  Standardized testing has proven to be an extremely difficult obstacle for them.  The district has been deeply concerned about how to improve the educational opportunities for such students but has found that a simple emphasis on educational achievement is not enough.   The superintendent of the Phoenix Union High School District, René Diaz, believes that if grades and test scores are to improve, teachers and staff within a school must have the authority to plan and carry out educational directives on their own.  To save the district's schools, Diaz and others came to believe that fundamental changes in the relationship between teachers, staff, school administrators, and parents were needed.

A beginning at such change came with the implementation of Interest-Based Bargaining (IBB) in 1995.   IBB was used for the first time to resolve collective bargaining disputes between the district and the three employee associations present in the district’s schools.  Two of these associations belong to the National Education Association (NEA) -- the Classroom Teachers Association (CTA) representing the classroom teachers and the Classified Employees Association (CEA) representing the support staff at the schools.  A third association, the Administrators Association (AdA), represents managerial interests in district schools.

Turning to IBB occurred after the superintendent imposed a contract settlement that did little to reduce the animosity among the parties or muffle criticism of the public school system from the media.  After being trained in this style of negotiating by outside consultants, collective bargaining among the three associations and the superintendent's office became less antagonistic, provided most of the parties with satisfactory results, and no longer attracted the critical attention of the media.  In the process, it gave all the involved parties a greater appreciation of what each confronted and how difficult classroom education was becoming.

Yet, while IBB improved the labor relations in the school district, it had little effect on the schools themselves.  To that end, in the spring of 1998 the district and the associations adopted a plan for the joint labor-management-community administration of a new school scheduled to open in August 1999.  This new initiative would replace the traditional collective bargaining relationship in a school with a revolutionary cooperative agreement among teachers, support staff, administrators, parents, and students.

Such a plan was not automatically embraced, and many were skeptical of the entire idea.  To build support for the plan, Doug Kilgore, the NEA's UniServ Director in the area, organized a series of study sessions on joint labor-management relationships for Superintendent Diaz and the leaders of the respective associations.  Those sessions culminated in early 1998 with a tour of the Saturn Automobile plant in Tennessee to study how the United Autoworkers and General Motors had developed their unique style of workplace cooperation.  Each association was represented on this trip.  Participants returned seeking to follow the Saturn model as best they could.

Association and district leaders recruited volunteers from the ranks of the three associations and formed a design team to begin planning the joint relationship and educational operations of the new school. This design team began work on a charter document along with exercises and meetings through which the participants might learn about each other.  Facilitators from within the superintendent's office and from the NEA-affiliated associations assisted the parties during these meetings.   Private-sector consultants were also brought in to train the parties in joint labor-management relationships, and some members of the design team even made a second trip to Saturn to learn more about labor-management cooperation.  These meetings took place during after-school hours and on weekends.  During its initial meetings, the design team selected the principal for the new school.

The combination of three problems, however, undercut the efforts of the design team.  Budgetary constraints, too little time, and the failure to address some outstanding tensions between labor and management leaders on the design team meant that some key disagreements about the nature of the joint relationship at the school were never addressed.  As a result, school administrators along with some of the teachers and the support staff never fully embraced the joint relationship for governing the school, the work of the parties was diverted over disputes over how to manage the school, and the school's governance structure did not develop into what district leaders had originally hoped it would.  The AdA representatives on the design team were especially concerned by their belief that some aggressive union members looked on the design team as a way to put the "workers" in charge and to make administrators at the school unnecessary.  In response, the administrators dug in to defend their authority against any challenge to their role.  This distrust coupled to the inherent weaknesses of the design team -- its volunteer character and the participants' limited budget and time -- pushed development of the labor-management relationship to the background as participants struggled to open the new school on time.

As a result, there was little common ground between teachers and support staff on one side who wanted to create a completely new and as "perfect" as possible school and on the other side those administrators whose mission was to open the school on time.  For the latter group, trying to build and open a new school while simultaneously designing an entire new governance structure to run it required too much effort in too little time.  As the meetings dragged on through 1998 and the school's scheduled opening was drawing ever closer, they began to act on their own initiative, bypassing the design team and the procedures it had established.

The members of the design team were still meeting, however, juggling their work and personal lives on top of their commitments to this new joint relationship.  By the end of 1998, they had largely finished the design of school operations.  Learning systems, hiring protocols, and procedures for supplies, materials, and personnel were in place.  Moreover, a compact was now complete, providing a governance structure that brought members of the three associations together at a variety of decision-making levels -- from the classroom to school policy-making.

Unfortunately, when the school opened in August 1999 such plans had no one to carry them out.  The decision-making bodies specified in the compact were barely functioning or did not exist at all because there were no written guidelines for how people would implement the compact and the plans of the design team.  Moreover, between one-third to one-half of the new teachers and support staff at the school were hired with no idea about the nature of the joint relationship, nor did they have any training in how worker-management cooperation was supposed to work.  Further, the link to the community and parents -- the third triad to the school's structure -- was all but forgotten.

The failure to come together at the beginning of the process, the pressure on the parties to put aside all issues but those related to the planning and opening of the new school, and the limited authority participants had in the design process because of their volunteer positions made keeping the project centered around establishing school policies and rules a difficult prospect from the start.    Instead of working together on how to govern the school jointly, several teachers and a few support staffers ended up waging a battle with administrators over who would manage the school.  Confrontations and allegations of conspiracies became common occurrences, and all sides acknowledged that these failures to get along were not helping the students get the education they needed.  Even such a simple a problem as keeping students out of the school's hallways during class time proved too elusive to solve in this climate.

Despite these setbacks, during the first year some of the teachers and staff who had participated in the original planning started reaching out to their colleagues to explain the unique goals and structure of the school and to invigorate still-dormant decision-making bodies. At the end of the year, all the governing bodies spelled out in the compact were at least functioning.  But, an effort during the second year of the school's existence to get the joint relationship fully implemented failed, and district and association leaders decided to end the experiment.  The substance of a joint relationship did not exist, and the continued in-fighting among school personnel made a joint relationship increasingly an impossibility.

Nonetheless, there was much that succeeded at César Chávez.  The joint effort in planning the new school, the ideals regarding school governance now taking hold among teachers, support staff, and frontline administrators, and the creation of the new school itself showcased a remarkable endeavor.  Unfortunately, this effort was diverted into an unhealthy debate over school management that no one had any authority to resolve, and as a result a new culture as well as a practical understanding for working together never developed.    As a result, new programs were achieved but fundamental change was not.