EMWIN Transition Plan

December 17, 2003 Version

EMWIN Transition Plan

Introduction

Changes to the NOAA’s GOES N-series satellite frequency assignments and transponder characteristics will require corresponding upgrades to the National Weather Service (NWS) Emergency Managers Weather Information Network (EMWIN) broadcast from the GOES satellites.  The National Environmental Satellite, Data, and Information Service (NESDIS), responsible for satellite and ground system design and implementation, and the NWS are working together to plan for the implementation and transition of the new EMWIN services within the future GOES N-series – the GOES-N,  -O, and -P.  This EMWIN implementation and transition plan identifies the related issues and actions required to achieve a successful transition.  The GOES related broadcast changes consist of a:

- Change in the broadcast frequency … from 1690.725 MHz to 1692.700 MHz

- Reduction in the power level of the broadcast … from 51 dBmi to 43 dBmi to meet ITU regulations.

- Change of signal modulation … from Frequency Shift (FSK) to Binary Phase Shift Key (BPSK), and

- Introduction of Forward Error Correction Coding (FEC) … using a Reed-Solomon Convolutional Code

- Replacement of WEFAX … by LRIT.

The EMWIN data rate will remain as it is currently at 9.6 Kbps.  The EMWIN data content will also remain the same.

A transition from current EMWIN operations (EMWIN-I) to the GOES N-series era EMWIN operations (EMWIN-N) is required as a result of these changes.  This plan documents those required activities to develop, test, and make available a new EMWIN receiver system to the vendor community for the transition.

## Background

The EMWIN mission is the timely dissemination of NWS warnings, watches, forecasts, and other products to the nation’s emergency management community, and many other public and private organizations.  A goal of EMWIN is low user cost access to a live stream of weather data and other critical emergency information.  One means of providing this access is dissemination through the GOES satellites, and direct reception with a low cost receiving system.  In some communities, the EMWIN signal received from GOES is then rebroadcast by the NWS and other public and private agencies as an audio signal on a dedicated VHF or UHF radio frequency.  This rebroadcast signal can be received, by anyone within the 40-50 mile broadcast area, using an inexpensive radio receiver, a demodulator, and a personal computer.

When the GOES N-series becomes operational it will render current EMWIN receiver systems unable to receive and process the EMWIN datastream and thus will require changes to existing EMWIN receiver systems in order for users to continue to receive and demodulate the EMWIN-N broadcast.  The new receiver systems are needed to accommodate the changes in frequency and modulation technique and the addition of Forward Error Correction.  NOAA plans to minimize the impact of these changes on both the receiver system vendor community and the user community by building in a transition period in which new receiver systems are designed, built, marketed, and become operational.  During this period the existing EMWIN-I broadcasts will continue and early coordination with the user community conducted.

The first launch of a GOES N-series satellite is currently planned for December 2004.  A six-month checkout period is planned for January through June 2005.  If the then-current constellation has experienced no problems (likely GOES-10 and –12), following the checkout period, the satellite will be placed in a storage orbit until it is needed.  It is now planned to be in storage until as late as July 2008, when it will replace the operational GOES East at its end-of-life.  To summarize, the earliest operational date of GOES-N is July 2005, while the latest date of first GOES-N operation is July 2008; the most probable operational date is somewhere between these two dates.

Transition Concept

A phased transition is planned from EMWIN-I to EMWIN-N, barring premature satellite failures:

- The EMWIN transition activities began with the award of a prototype receiver system development contract to demonstrate a technological solution to meet the changed EMWIN broadcast characteristics,

- The second phase will be the release of the prototype and development information to prospective vendors; their production of systems; purchases by users and users installing the new systems to receive the existing EMWIN-I broadcasts from the GOES satellites,

- The third phase, which will overlap the Second Phase, will be the periodic broadcast of a duplicate EMWIN GOES N-type datastream from a normally stored satellite

- The fourth phase will be the broadcast of the EMWIN-N datastream from the GOES-N satellite, currently planned as GOES East

- The Fifth Phase will be the broadcast of the EMWIN-N datastream through the GOES West satellite.

NESDIS stores spare satellites in geosynchronous orbit over the US until they are needed to replace operational satellites that have failed.  In the stored configuration most of the full time communications links and all of the instrument functions are not available due to the physical orientation of the satellite.  NESDIS removes such satellites from their stored configuration annually around the summer or winter solstice for the purpose of verifying the health of the satellites and their instruments, and to realign their stored configuration.

NESDIS’s Office of Satellite Operations (OSO) schedules a nominal 10-15 day period each year in June for the purpose of verifying the health of the stored satellites.  During these periods, the EMWIN-N datastream can be broadcast through the satellite.  OSO testing activities do not affect or interfere with the EMWIN signal.  These periods will provide users and vendors the opportunity to test their systems in the new operational environment.

The intention is to minimize user impact by retaining the current frequency and modulation for all operational broadcasts from the GOES I/M satellites.  Test broadcasts from the I/M satellites will retain the current frequency but the new BPSK modulation.  All broadcasts (test and operational) from the GOES N/P satellites will use the new frequency and new modulation.  When GOES N first becomes operational, one satellite from the I/M series and one satellite from the N/P series will be the operational CONUS constellation.  During that period, EMWIN will be broadcast at two different frequencies and modulations.

The Fourth Phase will be the broadcast of the EMWIN-N datastream from the GOES-N satellite, currently planned as GOES East.  The Fifth, and final, Phase will be the broadcast of the EMWIN-N datastream through the GOES West satellite.

Initially the broadcast frequency remains the same so there should be no change to the receiving frequency.  Once switched to GOES N-series spacecraft, the receiver will need to be “tuned” to the new frequency.  If this is not possible due to the characteristics of a specific manufacturer’s receiver, then a new receiver may be necessary.  This is highly dependant on current user hardware specifics and design details of the receivers of various vendors.

The Transition Concept is enabled by the flexibility of the new EMWIN receiver system.  The new receiver system uses a completely different approach than the current EMWIN receiver systems.  The new EMWIN receiver system is based on a custom software application residing in a commercial/off-the-shelf personal computer with an analog/digital sound card that will replace the custom hardware demodulator module of the current EMWIN systems.  The EMWIN functional schematic is shown in Figure 1 below.

Assuming the user’s existing PC has a capable sound card and sufficient computing resources, the cost implications to the user are minimized.  In the information technology world, relying on capabilities of any existing systems, which are more than 2-3 years old, has some risk.  Processors need to be Pentium-class machines.  Sound card functionality has changed exponentially in the past 3-5 years, so the assumption should be to upgrade the hardware.  The current minimum PC available on the commercial market is a 1.0 GHz Pentium processor with 128 MB memory and a 20 GB hard disk operating Windows NT/2000/XP.  This processor will utilize 20 to 25% of processing to service the custom software.  The analog/digital sound card used in the development was able to accommodate a sample rate of 96 KHz with an analog bandwidth of more than 46 KHz.  The development system used an M-Audio 2496 Audiophile series card.

Figure 1.  EMWIN Functional Schematic

We believe the new software required for demodulation of the information received from the sound card will not add a significant volume to the existing software.  The PC minimum requirements will be much more heavily dependent on the EMWIN software and storage requirements than on the changes to the system caused by the change in the demodulation and FEC.

All users will need to make a change to their front-end receive equipment to accommodate the frequency change between EMWIN-I and EMWIN-N, with complexity ranging from a receiver crystal change or re-tuning, to receiver replacement, depending on the flexibility and adaptability of their current units.

The custom software will be a variation of the software originally created for use in the NOAA GOES Low-Rate Information Transmission (LRIT) system.  Additional information on LRIT can be found at:

http://noaasis.noaa.gov/LRIT

The variation is the addition of software to de-modulate the existing Frequency Shift Keying (FSK) signal to the existing software supporting the new EMWIN-N Binary Phase Shift Keying (BPSK) modulation.  Switching between BPSK and FSK will be by keyboard or mouse input.  Both the current LRIT system and the EMWIN-N will use the same Forward Error Correction technique, R-S Convolutional.

The Transition Concept is based on the expectation that industry, using NOAA-provided technical information, will produce commercially available receiver systems in a timely manner for the user community.  The ability of the new receiver system to operate in either the current or the new environments makes it possible to provide a lengthy transition period without dedicating the use of an additional satellite to emulate the GOES-N era data stream solely for test and evaluation purposes.  It is expected the new systems will be placed in service as they are acquired which will provide an extended period of operational use.  The annual broadcast of EMWIN-N datastream from a normally stored satellite will provide opportunities for users to verify their systems will continue to perform normally when receiving the broadcast from the future GOES N-series satellites.

GOES-8 and -9 are now located in the Central Pacific, at 166 East and 155 East respectively, in view of the West coast, Hawaii, and are under the control of NOAA’s Fairbanks (Alaska) Command and Data Acquisition Station (FCDAS).  Their imaging and sounding abilities are greatly reduced, but their communications capabilities are fully functional.  These satellites can provide opportunities for vendors to test their systems at any time of the year with a live EMWIN (-I or –N, but not both simultaneously) datastream upon a request to the NESDIS Office of Satellite Operations.

If requested, and if:  1) the basic attitude control functions of the satellites continue to operate; 2) the communication functions of the satellites continue to operate; and 3) no other higher priorities arise, then the broadcasts from GOES-8 and 9 can continue until the lack of fuel to support North-South maneuvers and the inevitable inclination growth (>3 degrees) makes them impractical for EMWIN operations … sometime in 2006 for GOES-8 and 2007 for GOES-9.

Assuming users install the new systems, they will be able to operate them in either the “FSK No FEC” mode (current EMWIN-I) or in the “BPSK with FEC” mode (GOES N EMWIN-N) by changing the configuration of the software driver.  Thus the users can use the new systems to receive the current EMWIN-I broadcasts, testing that their systems operate correctly.  When the GOES-N broadcast is available, they can reconfigure the software driver, change the frequency, re-point the antenna, and receive EMWIN-N from GOES-N, verifying their systems work in the GOES-N mode as well.

The footprints for the satellite constellation are provided in Appendix 2.

Transition Activities

Transition activities include:

- Receiver system development, test, evaluation and acceptance

- NWS dissemination of transition plan and information to customers and vendors

- Vendors provide new systems to market

- User transition to new systems

- GOES-N operational

The receiver system test and evaluation phase commenced with the contract award for a prototype receiver system compatible with the planned frequency, power level, and formats required for EMWIN-N reception.  The vendor will deliver a dual demodulation  (FSK and BPSK) receiver system capable of operating in either current or planned operational modes for EMWIN.  The desired demodulation will be selected by a simple keystroke or mouse click configuration change.  The detailed EMWIN Transition Schedule is in the Milestone Section below, and a summary of the Technical Characteristics is found in the Users Manual.

The receiver system development and evaluation activities start with contract award, with expected tested prototype receiver system available by November 2003.  NESDIS will provide a simulated broadcast of EMWIN-N data streams using GOES-N power levels, modulation, and format.  The vendor will be responsible for demonstrating the proposed solution provides a level of service consistent with the current EMWIN-I broadcast.  This activity ends with acceptance of the demonstrated capability by NESDIS Office of Systems Development (OSD) Ground Systems Division and NWS Chief Information Officer (CIO).

The NWS will continue to disseminate transition information as provided by NESDIS and provide customer outreach support to the EMWIN user community.  The NWS will ensure timely EMWIN transition updates, technical information and current FAQs are posted on the EMWIN home page:

http://iwin.nws.noaa.gov/emwin/index.htm

Information messages will also be made available to the user community and vendors through the EMWIN operational broadcast. The NWS will also respond to the user community on all data and transition schedule issues.  NESDIS will continue to provide technical support to the NWS so the NWS can continue its coordination with receiver system vendors.

User transition activities span both the development of EMWIN-N receiver systems and the purchase and installation of those receiver systems by EMWIN users.  NWS will continue to notify current and potential users of the necessity to have new equipment prior to the switchover to GOES-N operations.  The method of notification is at the discretion of NWS and is expected to include means such as direct communication with current customers, broadcast messages via the Internet, and through NWS publications.

The user will install a new system or reconfigure their existing system by removing the existing demodulator, re-connecting the RF output to the IF, if the IF is a separate component, and then to the PC sound card input port, and configuring the new sound card driver software module (.dll) using the PC keyboard.  The user will re-point the receiving system antenna to GOES-11 and begin to receive the EMWIN datastream: -I or  -N at the EMWIN-I frequency.

The point of contact for the arrangement of test periods using the Pacific constellation will be in NESDIS OSD.  The current Point of Contact is: Angelo Wade, E/OSD, (301) 457 5210 x122.   NESDIS OSD will accept requests based on an oral, E-mail, or written request.  A written test plan and schedule will be required from the manufacturer, and a minimum 2-weeks notice.  There will be no costs to the manufacturer.  All requests are subject to deferral for spacecraft or National emergencies.

The vendor’s design of the new receiver system will involve new software, at least the AVTEK .dll, and probably new hardware, an IF converter.  The majority of the testing plan should be executed in the vendor’s facilities.  The only need for testing using the a satellite transmission path should be a validation that the end-to-end system functions properly.

Vendors and customers will have the opportunity to test and validate their new equipment using current EMWIN broadcasts and, periodically, validate that their new equipment operates satisfactorily in the EMWIN-N mode by ingesting the annual transmissions from the normally-stored satellites either emulating GOES-N broadcasts or actually broadcasting from the normally-stored GOES-N satellite following its launch and checkout.

If vendors are able to supply the first new systems in time for the June 2004 test period, the User Transition Phase could last from June 2004 to as late as July 2008.

NOAA Responsibilities

During the EMWIN transition period, the following responsibilities are planned:

- NESDIS/OSD

- Develop this transition plan

- Award prototype receiver systems demonstration contract

- Evaluate/certify demonstration system performance

- Coordinate with NWS on activities and progress

- Assist NWS on future receiver systems vendor coordination

- Participate in EMWIN conferences,

- Establishment of dates for transition and cutover in coordination with NWS

- NWS/CIO Office

- Notify customers and vendors of the start of transition activities

- Issue periodic user notification messages

- Participate in EMWIN conferences

- Provision of communications access circuit to WCDAS

- Coordination of dates for transition and cutover.

The Point of Contact for users and vendors is William Johnson, NWS/OCIO1, (301) 713 0863.  NESDIS will designate a Technical Point of Contact who will assist the NWS by responding to tasking by the NWS when necessary to answer vendor inquiries that cannot be answered by the NWS.

## Contingencies

There was a single identified risk:  Failure to demonstrate the successful prototype receiver system solution by the end of October 2003.  The prototype receiver system was not completed in time to meet this milestone and is now encroaching on the time required by vendors and EMWIN customers to implement, test, and place into operation new equipment.  NESDIS has confidence the demonstration receiver system will meet the requirements because of prior technical coordination with the contractor and the contractor’s past experience with the similar LRIT systems.  NESDIS fully recognizes the impact of the milestone slip and is working with the NWS to recover from the impact of the slip.

Milestones

Milestones for the EMWIN transition originally agreed to by NESDIS and NWS are:

1. June 30, 2003		Contract for demonstration version of a User Workstation

2. September 30, 2003	Delivery of a demonstration version of a User Workstation

3. October 31, 2003	Complete NESDIS test and documentation of User Workstation with EMWIN-I

4. November 1, 2003	Final EMWIN-I/N Transition Plan and User Guide available for distribution

5. November 30, 2003	Complete NESDIS test and documentation of User Workstation with EMWIN-N

6. December 31, 2003	Final EMWIN-N signal and front-end processor specifications for User Workstation available to vendors

7. March 31, 2004 		Integration and Test of EMWIN-N uplink equipment at

WCDAS

8. April-July 2004	Vendors test new workstation (from West Coast or Hawaii) using GOES-9 or GOES-8

9. June 20, 2004	Vendors test new workstation using normally stored GOES-11

10. Fall-Winter 2004		Deployment of new workstations to Users

11. July 2005		Transition GOES-East to the EMWIN-N

12. March 2006		Transition GOES-West to the new EMWIN-O

#### Current Status

The current status of the milestones for the EMWIN transition is as follows:

1. June 30, 2003	Contract for demonstration version of a User Workstation - Completed

2. September 30, 2003	Delivery of a demonstration version of a User Workstation.  The signal processing software for a User Workstation was demonstrated in September

3. October 31, 2003	Complete NESDIS test and documentation of User Workstation with EMWIN-I.  This milestone was not met because the contractor had not completed the development.  A NESDIS test was performed on November 11.  The documentation of a User Workstation using the EMWIN-I signal will be delivered before December 31.

4.  November 1, 2003	Final EMWIN-I/N Transition Plan and User Guide available for distribution.  This milestone was not met because NWS and NESDIS were unable to agree on a final Transition Plan before November 1 and the User Guide was not completed.  The agencies have agreed on and signed this version of the Plan.  The User Guide, a presentation of the technical issues that could affect the replacement or upgrade of existing user receiving systems, will be completed before December 31.

5.  November 30, 2003	Complete NESDIS test and documentation of User Workstation with EMWIN-N.  A NESDIS test was performed on November 11.  The documentation of a User Workstation using the EMWIN-N signal will be delivered before December 31.  The NWS has requested some further testing for system latency and longer term error performance.

6.  December 31, 2003	Final EMWIN-N signal and front-end processor specifications for User Workstation available to vendors.  The specifications are expected to be available by December 31.

## Concurrence

__________S/S_____________________		_______S/S____________________

Richard G. Reynolds					Larry Curran

NESDIS						NWS

E/OSD							W/CIO1

Appendix 1

EMWIN Acronyms

ASM		Attached Synchronization Marker

BER 		Bit Error Rate

bps 		bits per second

BPSK 		Binary Phase Shift Key

CADU		Channel Data Access Units

CCSDS	Consultative Committee for Space Data Systems

dB		decibel

dBmi		Decibels milliwatts isotropic, meaning referenced to a zero-gain antenna

EIRP 		Effective Isotropic Radiated Power

EMWIN 	Emergency Manager’s Weather Information Network (NOAA/NWS)

EMWIN-I 	EMWIN as transponded through the GOES-I/M series spacecraft, with associated frequency and modulation characteristics

EMWIN-N	EMWIN as transponded through the GOES N-Series spacecraft, with associated frequency, modulation, and coding characteristics

FCDAS 	Fairbanks (Alaska) Command and Data Acquisition Station (NESDIS)

FEC 		Forward Error-Correcting Code

FSK 		Frequency Shift Key

G/T 		gain-to-noise temperature ratio

GOES 		Geostationary Operational Environmental Satellite (NOAA/NESDIS)

GOES-I/M 	A series of GOES spacecraft launched between 1994 and 2001, and operationally designated GOES-8/-12

GOES N-series	The next generation GOES spacecraft (GOES-N, -O, and –P), with the first launch planned in December 2004

ITU		International Telecommunications Union

LRIT 	Low-rate Information Transmission

NESDIS	National Environmental Satellite, Data, and Information Service (NOAA)

NOAA 	National Oceanic and Atmospheric Administration

NWS 		National Weather Service (NOAA)

OSD 		Office of Systems Development (NOAA/NESDIS)

R-S 		Reed-Solomon

WCDAS 	Wallops (Virginia) Command and Data Acquisition Station (NESDIS)

WEFAX 	Weather Facsimile

Appendix 2

Footprint of GOES satellite CONUS constellation

Pacific Constellation