National Aeronautics and Space Administration

Goddard Space Flight Center

EO-1

Operations Test Plan

January 15 , 1999

Note: Document updated often

(

Revision History

| Version 1 1/15/99 | Jerry Hengemihle email: jerryh@microtel-md.com tel: 301-345-4005 |
| --- | --- |

(

Table of Contents

1.	Overview	1

1.1.	Scope	1

2.	Applicable Documents	1

2.1.	Applicable Documents	1

2.2.	Reference Documents	2

3.	EO1 Mission Overview	Error! Bookmark not defined.

4.	Operations Ground System Overview	Error! Bookmark not defined.

5.	Operational Elements and Interfaces	1

6.	Launch Operations Concept	31

7.	Relationship to Requirements	Error! Bookmark not defined.

8.	Test Definition – S, T, M	3

9.	Top level Tests, Test Responsibilities, Test Dates	4

9.1.	Subsystem Validation Tests S –Tests	4

9.2.	Mission Readiness Tests (T-Tests)	4

9.3.	Simulations (Category M)	4

10.	Key Dates from Swales I&T Plan	5

10.1.	Date MOC time Spacecraft Test Planned	5

11.	Test Reporting and Discrepancies	5

12.	Ground System Subsystem tests (S-Tests)	7

12.1.	S1 CGS Acceptance Test	7

12.1.1.	Spacecraft simulator	32

12.1.2.	Command and Telemetry Test	7

12.1.2.1.	Telemetry	7

12.1.2.2.	Telemetry Data Archive	8

12.1.2.3.	Commands	8

12.1.2.4.	STOL Processing	8

12.1.2.5.	Terminal Display System	9

12.1.2.6.	Command and Telemetry Data Base	9

12.1.2.7.	Page Display Database	9

12.1.2.8.	Automated Procedure Library	9

12.1.2.9.	Hard Copy Output	9

12.1.2.10.	Access Control	10

12.1.2.11.	Lights Out Operations	10

12.1.2.12.	Command Management System (CMS) Test	10

	The CMS shall interface with the MOPSS to receive a daily activity plan (DAP).	10

12.2.	S2 MOPSS ATP	11

12.2.1.	MOPSS Test Phases & Schedule	11

12.2.2.	Test Plan	11

12.2.2.1.	Version 1.0	11

12.2.2.2.	Version 1.1	11

12.2.2.3.	Version 2.0	12

12.3.	S3 Wallops Ground Station Testing	12

12.4.	S4 FDSS ATP	13

12.4.1.	Test No 1	13

12.4.2.	Test No 2	13

12.4.3.	Test No 3	13

12.4.4.	Test No 4	13

12.4.5.	Test No 5	14

12.4.6.	Test No 6	14

12.4.7.	Test No 7	15

12.4.8.	Test No 8	15

S5	DPS  ATP	17

12.4.9.	DPS Test Phases	17

12.4.9.1.	DPS Release 1 Testing –    August 98	17

12.4.9.2.	WARP Format Test    October 98	17

12.4.9.3.	CCSDS Telemetry Processing Test  December 98	18

12.4.9.4.	Level 0 Processing	18

12.4.9.4.1.	ALI Level 0 Processing Test  Feb 99	18

12.4.9.4.2.	LAC Level 0 Processing Test  Feb 99	19

12.4.9.4.3.	Hyperion Level 0 Processing Test May 99	19

12.4.9.5.	Ground Station Interface Test	20

12.4.9.5.1.	X-band Tape Test   Dec 99	20

12.4.9.5.2.	S-band Tape Test   Dec 99	20

12.4.9.5.3.	S-band SAFS Test   Dec 99	20

12.4.9.6.	SVF Interface Test     Mar 99	21

12.4.10.	DPS Test Schedule	21

12.5.	Year 2000 Testing	22

13.	Mission Readiness Tests (T-Tests)	23

13.1.	T1 - MOC – Spacecraft Interface Test	23

13.1.1.	Pre-test configuration and documentation.	23

13.1.2.	Test Objectives	23

13.1.3.	Test Personnel	24

13.1.4.	Test Responsibilities	24

13.1.5.	Spacecraft Configuration	25

13.1.6.	Control Hand-over Protocol	25

13.1.7.	Test Reporting	25

13.1.8.	Some Phone Numbers	26

13.2.	T2   Spacecraft – MOC –MOPSS – CMS – FDSS Interface Test	26

13.2.1.	Spacecraft to MOC Interface	27

13.2.2.	MOPSS to CMS	27

13.2.3.	CMS – ASIST	27

13.2.4.	CMS – Spacecraft	27

13.2.5.	FDSS to MOPSS	27

13.2.6.	FDSS to ASIST	27

13.3.	T3  Spacecraft – MOC - MOPSS – DPS - SVF Interface Testing	28

13.3.1.	Spacecraft to DPS	28

13.3.2.	DPS – SVF	28

13.3.3.	DPS – MOPSS	28

13.3.4.	DPS – ASIST	29

13.4.	T4  RF Compatibility Test	29

13.5.	T5  MOC - Ground Stations Interface Test	29

13.6.	T5.1  MOC – TDRSS Interface Test	29

13.7.	T6  MOC – WTR – Interface Test	29

14.	Mission Simulations (M-Tests)	30

14.1.	M1 Normal Operations / Safehold Recovery Simulation	30

14.2.	M2 Flight Timeline Simulation	30

14.3.	M3 L&EO Operations Simulation	31

# Overview

## Scope

This document defines the Operations Test Plan for the NASA EO-1 program.

## Operational Elements and Interfaces

The operational elements of the EO1 mission are:

- CGS		Command/Telemetry Ground System

- MOPSS		Mission Operations Planning System

- WGS		Wallops Ground Stations

- FDSS 		Flight Dynamics System

- DPS		Data Processing system

- SVF		Science Validation Facility

- TDRSS		Tracking and Data Relay Satellite System

- EO-1 S/C		EO-1 Spacecraft

- EO-1 L/V		EO-1 launch vehicle

- FOT		Flight Operations Team

The testing of the individual operational elements for application to EO-1 flight operations and verification of the interactions and interfaces between the elements is the intent of this document.

# Applicable Documents

## Applicable Documents

EO-1 Command and Telemetry Handbook (spec tbd)

EO-1 Detailed Mission Requirements (spec tbd)

Radio Frequency Interface Control Document Between the Earth Orbiter (EO-1) Spacecraft and the Ground Network (GN) and the Space Network (SN). January 1988

EO1 Space To Ground ICD

## Reference Documents

CCSDS 101.0-B-3: Telemetry Channel Coding. Blue Book. Issue 3. May 1992.

CCSDS 102.0-B-4: Packet Telemetry. Blue Book. Issue 4. November 1995.

CCSDS 201.0-B-2: Telecommand Part 1 -- Channel Service. Blue Book. Issue 2.

November 1995

CCSDS 202.0-B-2: Telecommand Part 2 -- Data Routing Service. Blue Book. Issue 2.

November 1992.

CCSDS 202.1-B-1: Telecommand Part 2.1 -- Command Operation Procedures. Blue

Book. Issue 1. October 1991.

CCSDS 701.0-B-2: Advanced Orbiting Systems, Networks and Data Links:

Architectural Specification. Blue Book. Issue 2. November 1992.

# Roles and Responsibilities

## GSFC Management

Dan Mandl 		–  Ground Systems Manager

Randy Harbaugh	-  Mission Readiness Manager

## FOT

Joe Howard  -- Lead FOT

Leo McConville

Alicia Cost

Seth Shulman

Bruce Trout

Tom Moore

Tom Berry

### Subsystems

Larry Alexander	FEDS

Paul Garza 		Networks and Ground Stations

Jim Dowling		ASIST

Bob DeFazio		FDSS

Randy Harbaugh	MOPSS

Rusty Whitman	CMS

## Support

TBD 			Simulation Director

Jerry Hengemihle 	Test Planning

## Spacecraft

Earle Moyer		I&T Manager

E.J.Bickley		Test Conductor

Mark Perry		Spacecraft Systems

# Test Definition – S, T, M

Subsystem validation tests (S test) are performed on each individual subsystem before any integrated tests are performed.  These tests are specifically used to test the hardware, software, and operability of the elements of the ground system.

Integrated tests (T tests) test the interfaces between elements and the specific interface requirements.

Simulations ( M tests) are tests where the primary objective is to train or test the FOT.  These can also accommodate testing system functionality.  Various types of simulations will be held at all stages of pre launch operations.

# Top level Tests, Test Responsibilities, Test Dates

## Subsystem Validation Tests S –Tests

Responsible Person

S1	1/99	CGS Acceptance Test			Joe Howard

S2	1/99	MOPSS ATP				Bruce Trout

S3	1/99	Wallops Ground Station		Jim Henderson

S4	1/99	FDSS ATP				Bob DeFazio

S5	1/99	DPS  ATP				Jerry Hengemihle

S6	1/99	Year 2000 Testing

## Mission Readiness Tests (T-Tests)

T1	11/98 Spacecraft – MOC Interface Test

T2	1/99	Spacecraft – MOC –MOPSS – CMS – FDSS Interface Test

T3	3/99	Spacecraft – MOC - MOPSS – DPS - SVF Interface Testing

T4	3/99	RF Compatibility Test

T5	6/99	MOC - Ground Stations Interface Test

T5.1	tbd	MOC – TDRSS Interface Test

T6	9/99	MOC – WTR – Interface Test

T7	10/99  Fully Integrated End-to-End System Test

Mission Readiness Test responsible persons

T1		Earl Moyer, Joe Howard

T2		Earl Moyer, Joe Howard, Bruce Trout, Bob Defazio

T3		E.Moyer, J,Howard, B.Trout, J.Hengemihle, L.Moy

T4		Earle Moyer, tbd

T5		Joe Howard, Jerry Hengemihle, Ralph Zimmerman

T5.1		Joe Howard, Jerry Hengemihle, Paul Garza

T6		Joe Howard, TBD

T7	     EMoyer., TBD VDBG, TBD GS, J.Howard, B.Trout, Jerry H, L.Moy

## Simulations (Category M)

M1	4/99	Normal Operations / Safehold Recovery Simulation

M2	8/99	Flight Timeline Simulation

M3	8/99	L&EO Operations Simulation

M4	12/99	Launch Rehearsal

Mission Simulations Responsible persons

Spacecraft – 		Moyer, Perry

MOC – 		Howard, Trout

Ground Stations – 	Jim Henderson

Networks – 		Tom Russel

FDF – 			Bob Defazio

Sim director -		tbd

# Key Dates from Swales I&T Plan

Pre-Environmental Review			3/99

Pre-Ship Review				9/99

Flight Readiness Review			11/99

Schedule of MOC opportunities from Earle Moyer  10/5/98

## Date	MOC time	Spacecraft Test Planned

10/30		16 hrs		Command & telemetry functional

11/25		24 hrs		ACS software testing

3/10		20 hrs		Comprehensive Performance Test

5/7		16 hrs		CPT with flight ALI

5/31		tbd		RF compatibility

6/3		16 hrs		TB/TV	orbit simulations

7/15		16 hrs		CPT with SA installed

7/29		tbd		RF compatibility

8/16		16 Hrs		TV/TB orbit simulations

9/30		4 hrs		MOC command and telemetry

# Test Reporting and Discrepancies

- DR database maintained on EO-1 Web site

- Discrepancy Reports

- Opened by FOT

- Assigned to subsystems – subsystem leads will add to subsytem DR system if needed

- Closed after retest

- Open item status viewable via EO1 web-site

# Ground System Subsystem tests (S-Tests)

## S1	CGS Acceptance Test

This document defines  the test plan for the EO-1 MOC Command and Telemetry System (CTS).  The CTS requirements will be met by the Combined Ground System (CGS) provided by NASA GSFC code 581.

The CTS for flight operations is the same system being used for I&T.  The Flight Operations Team (FOT) is assisting with spacecraft I&T.  The FOT involvement with spacecraft I&T will allow the CTS to be tested during I&T.  The FOT will also gain useful knowledge of the spacecraft and will lessen the need for special training.

### Command and Telemetry Test

The MOC – Swales command and telemetry test will verify a large number of the requirements allocated to the ASIST data system.  For the most part, the test procedures will be developed and debugged by the FOT for use in spacecraft I&T.

The following requirements will be verified by this test.

#### Telemetry

- The CTS shall process the EO-1 CCSDS channel access data units (CADUs) and virtual channel data units (VCDUs).  Virtual Channels 0, 1, and 2 shall be processed.  VC0 is real-time spacecraft housekeeping.  VC1 is playback spacecraft housekeeping from the onboard recorder.  VC2 is playback spacecraft events.

- The CTS shall be capable of accepting and processing EO-1 telemetry.  The EO-1 data rates and encoding formats are defined in the EO-1 Space-To-Ground ICD

- The CTS shall provide data quality checking of the VCDUs and append quality information to each source packet.

- The CTS shall process and display and limit check EO-1 real-time data at rates up to 32 KBPS according to the specifications contained in the EO-1 project RDL data base.  This includes conversion from raw to engineering units.

- The CTS shall provide the capability for viewing unformatted telemetry data.

- The CTS shall be capable of optionally checking any telemetry data item (analog or discrete) against a set of user definable limits and report limit violations.

- The CTS shall provide the capability to dump and verify the contents of each EO-1 flight processor memory, tables and stored command system. Additionally the system shall process messages generated by the flight software.

- The CTS shall provide S-band level-zero processing functions.  Telemetry data shall be organized as time ordered files with all duplicate packets removed.

- The CTS shall be capable of short and long term statistical trending of telemetry data points.  The time frame and data display format shall be user selectable.

#### Telemetry Data Archive

- The CTS shall provide online and offline data storage for archiving telemetry data and shall provide a mechanism by which authorized users can retrieve stored data.  The CTS shall provide a replay capability based on ground receipt time, or spacecraft time

- The archive shall be sized to store the last 120 days of spacecraft housekeeping data online.

- All EO-1 spacecraft data for the life of the mission shall be archived via offline data storage.  Separate archives are to be maintained for each virtual channel/physical channel combination.

- The system shall maintain an online catalog describing the location of each archived data set and the spacecraft times of the data within each data set.

#### Commands

- The CTS shall be capable of sending command data to the EO-1 spacecraft via the ground stations at 2 kbps.  The commands shall conform to the CCSDS COP-1 protocol and data formats as defined in the EO-1 Space-To-Ground ICD.

- The CTS shall maintain an online data set and printer log of all commands issued to the spacecraft

- The system shall maintain a list of critical commands that will require spacecraft controller approval prior to the sending of the command. The primary spacecraft controller must explicitly allow each of the critical commands to be forwarded to the spacecraft

- The system shall provide the capability to construct and send real-time commands.

- The CTS shall provide for the management and local editing of uplink code images for the onboard processors including the C&DH Mongoose-5, the WARP Mongoose-5, and the RSNs.  The system shall be capable of maintaining multiple versions of the load images, naming each version so that it can be later referenced.

- The CTS will provide tools for the generation of stored command loads.  The system shall provide tools that allow the user to generate absolute time sequences (ATS) and relative time sequences (RTS) from a language that is compatible with the on-line spacecraft controllers language.

#### STOL Processing

- The system control language shall provide a capability to compose mathematical expressions of system variables in support of pre-launch and on-orbit activities, including functions of one or more variables, common unary and binary operators, and logical expressions.

- The system shall support the modularization and execution of subprocedures.  The system shall support flow control expressions, such as unconditional branching, conditional branching and looping.  The system shall support conditional, unconditional and timed waits (pauses in execution).

- The spacecraft controller shall have full interactive control in real time over the execution of procedures, including stop, start, abort, wait, branch and subprocedure execution.

#### Terminal Display System

- The CTS shall be capable of displaying 6 pages on a single display.  Operator command line displays, STOL procedure execution displays, telemetry pages, and event pages shall be displayed simultaneously.

- Display data fields shall be updated at a  rate of 1 Hz using the latest telemetry values received from the spacecraft.

#### Command and Telemetry Data Base

- The system shall provide a command and telemetry database facility for the definition, editing, display and configuration control of all EO-1 command and telemetry.

- The command and telemetry definitions are to include packet formats, mnemonics, and engineering unit conversions.

- database will support definition of onboard system tables.

#### Page Display Database

- The system shall provide a page display database which shall be capable of holding at least 600 page display definitions.

- The database shall support the definition of purely textual displays and mixed text and graphical displays.

- The pages shall consist of a combination of text, strip, scatter, and graphical representations of any telemetry mnemonic, CTS variable, or derived data points.

#### Automated Procedure Library

- The system shall be capable of managing 2000 automated procedures.

- The system shall provide a text editor in order to perform definition and modification of procedures.

- The system shall provide a preprocessor which shall verify the structural content of procedures and preclude structurally incorrect procedures from being executed by the on-line system.

#### Hard Copy Output

- The CTS shall provide at least one line printer.

- CTS shall have the ability to print telemetry, derived data points, and operator generated events.

- All commands sent to the spacecraft will be logged to the line printer

- The CTS shall provide at least one page snap printer.

- The CTS shall provide the capability to print screen dumps of displays, system events, print telemetry snapshots of any display page whether or not the specified page is active, and generate plots of operator selected data versus time.

#### Access Control

- The CTS shall provide control stations and configured computer accounts for the set-up, operations and control of the CTS system.

- Open/Closed network connections is TBD.

#### Lights Out Operations

- The CTS shall provide support for lights out operations which includes autonomous handling of ground stations passes, autonomous monitoring of spacecraft health, and operator notification when problems are detected.

#### Command Management System (CMS) Test

The CMS test will verify the ground systems ability to accept input from the MOPSS and to generate and upload for execution to the spacecraft stored command loads sufficient to operate the EO1 autonomously.  The configuration for the CMS test is shown in the figure below:

The requirements verified by the CMS test are the following:

##### The CMS shall interface with the MOPSS to receive a daily activity plan (DAP).

- The CMS shall compile the DAP to produce stored command uploads.

- The CMS shall perform command constraint checking.  The CMS shall provide the capability to edit constraint definitions.

- The CMS shall provide for operator edits of SCP loads.

- The CMS shall allow events to be defined.  Examples in South Atlantic Anomaly zone crossing, ground station pass, apogee, etc.

- The CMS shall accept and utilize a constants file.

## S2	MOPSS ATP

The MOPSS will be developed and tested in an incremental fashion.  Capabilities will be added as needed eventually producing the final system to be used for flight.  The MOPSS test phases are described in section 3.1.  The test schedule is given is section 3.2.

### MOPSS Test Phases & Schedule

The MOPSS will be released in three phases; Version 1, 1.1, & 2.  Testing of the incremental capabilities will be test with each release.

Test Schedule

MOPSS Release 1 Test				8/98

MOPSS Release 1.1 Test				10/98

MOPSS Release 2 Test				12/98

### Test Plan

#### Version 1.0

This release will test the following capabilities:

- Ingest and display FDF orbital predicts

- Allow operator key in of TDRSS and GS event schedule

- Schedule activities/commands relative to orbital/GS/TDRSS events

- Allow user to block out periods when imaging is not allowed

- Ensure nadir imaging is not scheduled during black out periods

- Provide capability to view and modify EO1 timeline

- Provide capability to build an activity plan reflecting timeline

- Provide capability to schedule activities relative to events

- Allow for the user to manually schedule activities/commands

- Provide file management activities – over lapping data products, products updates, etc.

- Allow user to browse and modify auxiliary data for events/activities, etc.

- Provide feedback to the operator when constraints or conflicts occur

- Basic report generation support

#### Version 1.1

This release will test the following capabilities:

- Support ingest and display of SVF provided ground image scene request

- Allow user definition/edit of scene requests

- Support calculation and display image times based on requested scence lovcation and predicted EO1 orbit position

- Schedule activities relative to image events

- Ingest FDF generated maneiuver plan and command sheet

- Schedule orbit maneuver related sequences

- Provide capability to create an updated activity plan

#### Version 2.0

This release will test the following capabilities:

- Display, allow selection, and transmit GS schedule from WSG

- Receive and display GS schedule from WSG

- Support ingest and display of cal scene requests

- Automatically ‘select’ images and schedule image related commands

- Interface w/FDF algorithms to schedule activities/commands for momentum management and attitude maneuvers for nadir and cal images.  Note that different interface for nadir and cal images.

- Assign WARP file Ids for each data stream to be stored for each DCE

- Generate and image summary report which lists attributes of each DCE (time, location, DCE type, data streams stored, file Ids, DCE #, etc.

- Perform resource utilization checks (WARP memory available, instrument on time, etc.)

- Verify WARP file Ids correlate to DCE, DCE type, and data stream type (ex. MS/PAN dark cal, MS/PAN int cal, MS/PAN image, etc.)

- Verify each WARP file ID assigned a unique number

- Provide momentum management/attitude maneuver related constrint checking

- Enhanced report generation support

## S3	Wallops Ground Station Testing

## S4	FDSS ATP

### Test No 1

- Accept attitude telemetry (including GPS data) into the EO1ADS telemetry processor from ASIST (D)

- Accept real time attitude telemetry into EO1RTADS from ASIST.  (D)

- Generate OBC attitude validation reports and transfer to the MOC  (D)

- Extract GPS Single Point Solutions (SPS) from telemetry during every working day or when required.   SPS data will be smoothed on the ground to provide an EO-1 orbit when needed.  (1.3-7.2)

- Extract raw GPS data from telemetry for early orbit validation of the

- on-board GPS orbit determination.  (1.3-7.3)

### Test No 2

- Perform ground validation of the on-board attitude from the Autonomous Star Tracker (AST) via playback data.  (1.3-1.3)

- Perform ground estimates of true attitude, gyro biases via real time telemetry.  (1.3-1.4)

- Generate real time attitude displays in the MOC.  (D)

- Generate the attitude history file and prepare it for usage in FDSS applications software  (D)

### Test No 3

- Provide engineering data for attitude maneuver command inputs.

- (1.3-3.4)

- Provide predicted momentum management command inputs for

- imaging periods.  (1.3-4.4)

- Provide instrument calibration command inputs.  (1.3-4.5)

- Perform computations for instrument alignment support.  (1.3-3.1)

- Perform sensor, star tracker, and gyro calibration, including estimates of alignments, biases and scale factors.  (1.3-2.1)

- Provide OBC up-linked input table parameters for alignment and calibration.  (1.3-4.2)

- Prepare calibration and attitude command and control products for transmission to FORMATS/MOPSS and/or the MOC.  (D)

- Transmit calibration and attitude command and control products to FORMATS/MOPSS and/or the MOC.  (D)

### Test No 4

- Generate the X band phased array station inviews data.  (1.3-4.1)

- Generate predicted sun/moon interference to the AST.  (1.3-4.6)

- Generate science planning aids for scheduling of co-fly images taken with Landsat-7.  (1.3-9.8)

- Generate planning aids for meeting constraints required for instrument calibration maneuvers and corresponding command generation data.

- (1.3-4.5)

- Prepare attitude utilities to generate products for transmission to FORMATS/MOPSS and/or the SVF.  (D)

- Transmit products from attitude utilities to FORMATS/MOPSS and/or the SVF.  (D)

### Test No 5

- Accept launch vehicle state vector from WTR in PODS.  (D)

- Smooth SPS on the ground to provide an EO-1 orbit when needed.

- (1.3-7.2)

- Validate on-board GPS orbit determination solutions using ground based

- S-band tracking.  (1.3-7.4)

- Provide post-maneuver orbit determination with GPS or S band ground based tracking.  (1.3-6.8)

- Provide backup orbit determination using S-band tracking data from GN ground stations.  (1.3-8.1)

- Accept S-band tracking data from the ground stations for pre-processing.  (D)

- Provide pre-processing for S-band tracking data when it is received in the MOC (1.3-8.2)

- Validate the EO-1 OBC orbit propagation.  (1.3-7.8)

### Test No 6

- Generate OBC orbit validation report and transfer to the MOC.  (D)

- Provide tracking data evaluation for S-band tracking during early orbit

- (not performed in the MOC).  (1.3-8.3)

- Accept launch vehicle state vector from WTR in AUTOCON-G.  (D)

- Generate both an EO-1 and a Landsat-7 10 day predictive ephemeris (old Code 500 format) with planned maneuvers and transfer to the MOPSS.

- (1.3-7.6)

- Generate an EO-1 6 week predictive ephemeris (old Code 500 format) with planned maneuvers and transfer to the MOPSS.  (1.3-7.7)

- Convert AUTOCON-G ephemerides if necessary to make them compatible with FDSS product generation modules  (D)

- Generate EO-1 maneuver plans required to maintain the co-fly requirement with Landsat-7.  (1.3-5.3)

- Generate the maneuver planning file and transfer to FORMATS/MOPSS.  (D)

- Generate the maneuver command file and transfer to FORMATS/MOPSS.  (D)

- Perform post-maneuver calibration of all delta-V maneuvers.  (1.3-6.7)

- Generate a post-maneuver evaluation report for the FOT.  (D)

- Accept the Landsat-7 state vector from the Landsat-7 MOC.  (1.3-7.5)

- Accept the Landsat-7 maneuver file from the Landsat-7 MOC.  (1.3-7.5)

- Provide mission analysis studies including; trajectory design analysis, mission propellant budget, launch window, and end-of-life analysis.

- (1.3-5.1)

- Design a post orbit insertion strategy to place the spacecraft in its mission orbit.  (1.3-5.2)

- Design an operational orbit plan to meet the co-fly imaging requirements with Landsat-7.  (1.3-5.3)

- Provide post orbit insertion orbit maneuver support to achieve / maintain proper phasing with Landsat-7.  (1.3-6.2)

- Provide orbit maneuver support to achieve / maintain a frozen and sun-synchronous orbit for EO-1.  (1.3-6.3)

- Provide orbit maneuver support to maintain ground track control for

- EO-1.  (1.3-6.4)

- Provide orbit maneuver support for EO-1 inclination maneuvers to maintain the required MLT at the descending node.  (1.3-6.5)

- Perform orbit evolution analysis for EO-1 and Landsat-7 to determine future delta-V burn scenarios.  (1.3-6.6)

### Test No 7

- Accept AUTOCON-G ephemerides in STK and STK utilities for product generation.  ( D)

- Generate predicted ascending and descending node crossing times and longitudes.  (1.3-9.1)

- Generate predicted South Atlantic Anomaly entrance and exit times.

- (1.3-9.2)

- Generate predicted satellite shadow entrance and exit times.  (1.3-9.3)

- Generate predicted sub-satellite point shadow entrance and exit times.

- (1.3-9.4)

- Generate predicted ground station inviews.  (1.3-9.5)

- Generate the sun angle for power monitoring. (1.3-9.6)

- Generate acquisition data for the ground stations and the NCC.  (1.3-9.7)

- Generate Extended Precision Vectors (EPVs) for both EO-1 and

- Landsat 7 for uplink to the EO-1 spacecraft.  (1.3-9.9)

- Generate ground track data.  (1.3-9.10)

- Generate predicted Mean Local Time for ascending and descending nodes crossing times.  (1.3-9.11)

- Generate predicted entry and exit times for miscellaneous zones of exclusion.  (1.3-9.12)

- Generate solar array lunar eclipse entry and exit times.  (1.3-9.13)

- Generate sun angles at WRS scene centers.  (1.3-9.14)

- Capture forecast scheduling file from WOTIS and provide to FORMATS/MOPSS.  (1.3-9.15)

- Generate EO-1 TDRS inviews data for special coverage periods. (D)

- Prepare STK products for transmission to FORMATS/MOPSS.  (D)

- Transmit STK products to MOPSS, ground station, and the NCC where

- applicable.  (D)

### Test No 8

- Provide procedure for transfer of SLP file from the FDF to the FDSS in the MOC.  Test procedure.  (D)

- Provide procedure for transfer of the Time Conversion Coefficients file from the FDF to the FDSS in the MOC.  Test procedure.  (D)

- Provide procedure for transfer of JPL Export Ephemeris file from JPL  to the FDSS in the MOC.  Test procedure.  (D)

- Provide procedure for updating environmental files required by

- AUTOCON-G and PODS.  Test Procedures.  (D)

- Accept the attitude maneuver notification report from ASIST.  (D)

- Accept pre-maneuver pressure and temperature data from ASIST.  (D)

- Accept the post-maneuver ACS data from ASIST.  (D)

- Accept the post-maneuver pressure and temperature data from ASIST.  (D)

- Accept the cloud prediction report from NOAA.  (D)

- Obtain Landsat-7 state vector and a Landsat-7 maneuver plan from the

- Landsat-7 MOC every working day.  (1.3-7.5)

- Verify the FDSS’ ability to operate autonomously or in a scripted mode.

- (D)

## S5	DPS  ATP

The DPS will be used extensively during spacecraft I&T to verify spacecraft functionality including the WARP, X-Band transmitter, and the instruments.   Additional tests are needed to verify the end-to-end data transfers via the ground stations.  These tests are TBD until a knowledgeable and responsible ground system representative is identified.

The DPS will be developed and tested in an incremental fashion.  Capabilities will be added as needed eventually producing the final system to be used for flight.  The DPS test phases are described in section 19.1.  The test schedule is given is section 19.2.

### DPS Test Phases

#### DPS Release 1 Testing – 			August 98

The first release of the DPS software will be tested on a FEDS workstation set up in the EO1 Mission Operations Center (MOC) located in building 14 at Goddard Space Flight Center (GSFC).  This test will verify the Flight Operations Teams ability to execute the programs comprising release 1 of the DPS software.  This test will use data files as input generated by Edwin Fung of the WARP test team.  The input data files will consist of the anticipated output of the WARP given a known data pattern as input (to the WARP).  Additional datafiles provided by Edwin will be used to verify the descrambling of the data bands testing the code provided by MIT.  What about LAC and Hyperion?

The DPS release 1 software will verify the following:

The DPS will process data as formatted by the EO-1 Spacecraft WARP data system.  The WARP data formats are defined in the EO-1 Space-To-Ground ICD.

The DPS shall be able to do the following front-end processing

- ingest CADU formatted data.

#### WARP Format Test				October 98

The WARP GSE will capture the WARP output and store the data to disk.  These files will be transferred to the DPS for processing.  The WARP output will be captured both encoded and unencoded from either I or Q data channels in a non-bit interleaved fashion.  The DPS will process the data files.  The results will be manually inspected to verify the output is as expected.   The WARP data inputs will be designed using ramping data patterns to allow easy detection of data dropouts, misordering, etc.  This testing will verify the following DPS requirements:

The DPS will process data as formatted by the EO-1 Spacecraft WARP data system.  The WARP data formats are defined in the EO-1 Space-To-Ground ICD.

The DPS shall be able to do the following front-end processing

- decode Reed Solomon data

- derandomize data

- ingest CADU formatted data.

#### CCSDS Telemetry Processing Test		December 98

This phase will verify the DPS processing of WARP data which has been stored to AMPEX tape and replayed.  A subset of the tests run in WARP functional testing will be checked. A high speed AMPEX tape recorder will be used during Spacecraft I&T to record high speed WARP and X-Band data.  The data will be bit interleaved by TBD equipment to simulate the ground station bit interleaving of the X-band data.  The data will be replayed into the DPS for procesessing.

This test will verify:

The DPS will process data as formatted by the EO-1 Spacecraft WARP data system.  The WARP data formats are defined in the EO-1 Space-To-Ground ICD.

The DPS shall be able to do the following front-end processing

- decode Reed Solomon data

- derandomize data

- ingest CADU formatted data.

This test will also verify the ability of the DPS to read data from the AMPEX tape

#### Level 0 Processing

##### ALI Level 0 Processing Test		Feb 99

After integration of the ALI onto the EO1 spacecraft, the ALI will be set in a mode to output known data to the WARP.  This data will be recorded and replayed by the WARP.  The replay data will be stored onto AMPEX tape and replayed into the DPS.  The DPS will process the data.  This test will verify:

The DPS will process image data from the Advanced Land Imager (ALI) Instrument.  The ALI data formats are defined in the ALI to WARP ICD.

The DPS shall be able to process the files containing the ALI housekeeping data taken during the image.  These files will be recorded on the AMPEX tape.

The DPS shall create an imageable PAN file as follows:

- Reorder odd/even pixel offset

- Extract the scan lines and place in band sequential order

- Provide identifiable fill for those portions of a PAN line that do not have data (might to reword this)

The DPS shall process the MS file as follows:

- Descramble the pixels

- Extract the scan lines and place in band sequential order

- Perform odd/even pixel reordering for bands 1, 1’, 2, 3, 4, 4’

- Perform correction for HgCdTe sampling for bands 5, 5’ and 7

- Provide identifiable fill for those portions of a MS line that does not have data

Each Data Collection Event (DCE) which is a set of the above processed files, shall have an associated start and stop image time which is derived from the housekeeping file.

The DPS shall have the following displays.  (TBD)

- Provide a quicklook display to indicate # of scan lines processes or some other indication of progress

The DPS shall respond to the following error conditions:

- Drop out in data on the AMPEX tape

- Process frames that have RS errors, however mark the data which came from those frames.

- In the case of sequence errors, the following should be done (TBD)

The DPS shall generate image report for each image

- # of search , check , lock flywheel frames

- dropouts

- gaps

- other errors

##### LAC Level 0 Processing Test		Feb 99

After integration the LAC will be set in a mode to output known data to the WARP (whether or not the LAC has this capability is TBD).  This data will be recorded and replayed by the WARP.  The replay data will be stored onto AMPEX tape and replayed into the DPS.  The DPS will process the data.  This test will verify:

The DPS will process data from the LEISA Atmospheric Corrector Instrument (LAC).  The LAC data formats are defined in TBD ICD.

The DPS shall process the LAC file as follows:

- Band order the scan lines for 250 bands

- The output of each detector shall be put into separate files that can later be assembled into a complete image.

The DPS shall be able to process the files containing the LAC  housekeeping data taken during the image.  These files will be recorded on the AMPEX tape.

Each Data Collection Event (DCE) which is a set of the above processed files, shall have an associated start and stop image time which is derived from the housekeeping file.

##### Hyperion Level 0 Processing Test	May 99

After integration the Hyperion will be set in a mode to output known data to the WARP (whether or not the Hyperion has this capability is TBD).  This data will be recorded and replayed by the WARP.  The replay data will be stored onto AMPEX tape and replayed into the DPS.  The DPS will process the data.  This test will verify:

The DPS will process data from Hyperion Instrument .  The Hyperion  data formats are defined in TBD ICD.

The DPS shall process the Hyperion  file as follows:

- Band order the scan lines for tbd  bands

- The output of each detector shall be put into separate files that can later be assembled into a complete image.

The DPS shall be able to process the files containing the Hyperion  housekeeping data taken during the image.  These files will be recorded on the AMPEX tape.

Each Data Collection Event (DCE) which is a set of the above processed files, shall have an associated start and stop image time which is derived from the housekeeping file.

#### Ground Station Interface Test

##### X-band Tape Test			Dec 99

What we need to verify is that the data put on the tape can be read back, and identified.  Any ground station info put on the tape needs to be tested.

Ideally, we would put the output of the WARP into the ground station receiver.  The input to the WARP would contain known data which we can verify after processing by the DPS.  This verification might be manual, or a file compare or a program which checks the data (this is TBD).

##### S-band Tape Test			Dec 99

The ground station would make a data tape and we will send to GSFC.  This test needs to be repeated for the S-Band backup mode via tape because the S-band takes a different data path.  It’s also anticipated that images will be spread across multiple passes and we need to verify that the DPS can handle a single image dumped on different ground station passes.

##### S-band SAFS Test			Dec 99

An electronic check of the S-Band backup mode transferring data electronically via the SAFS system also needs to be done.  This test should be performed via both SGS and Wallops ground stations.  This mode will probably be used for early orbit aliveness and functional checks of the instruments and the WARP.

#### SVF Interface Test					Mar 99

The DPS will generate a DLT tape of the level 0 processed data.  The SVF will process the level 0 data to verify:

- DPS shall process the input files and create TBD HDF formatted files; four files for PAN, TBD files for Hyperion, and three files for the LAC and housekeeping data.

- The DPS shall create an imageable PAN file as follows:

- Reorder odd/even pixel offset

- Extract the scan lines and place in band sequential order

- Provide identifiable fill for those portions of a PAN line that do not have data (might to reword this)

- The DPS shall process the MS file as follows:

- Descramble the pixels

- Extract the scan lines and place in band sequential order

- Perform odd/even pixel reordering for bands 1, 1’, 2, 3, 4, 4’

- Perform correction for HgCdTe sampling for bands 5, 5’ and 7

- Provide identifiable fill for those portions of a MS line that does not have data

- The DPS shall process the Hyperion files as follows:  TBD

- The DPS shall process the LAC file as follows:

- Band order the scan lines for 250 bands

- The output of each detector shall be put into separate files that can later be assembled into a complete image.

- Each Data Collection Event (DCE) which is a set of the above processed files, shall have an associated start and stop image time which is derived from the housekeeping file.

- The DPS shall place the processed files on a DLT tape.

-  Session per tape (TBD)

-  The files shall also be available for FTP

### DPS Test Schedule

DPS Release 1 Test				8/98

WARP Formatting Test			10/98

CCSDS Telemetry Processing Test		11/98

ALI Level 0 Processing Test			2/99

LAC Level 0 Processing Test			2/99

Hyperion Level 0 Processing Test		5/99

Ground Station Interface Test			12/98

SVF Interface Test				3/99

## Year 2000 Testing

Each individual element of the EO1 mission as listed in section 5 will be responsible for testing the individual element for year 2000 compliance.  No integrated EO-1 (T or M tests) tests are planned for year 2000 compliance.

# Mission Readiness Tests (T-Tests)

## T1 - MOC – Spacecraft Interface Test

Test T1 will verify the Spacecraft to MOC command and telemetry interfaces.  The planned configuration for this test is to have the MOC equipment located at GSFC building 14 monitor and control the EO1 spacecraft located at Swales in Beltsville, MD.  The schedule for test T1 is December 22,1998 at 19:00 GMT (2:00pm).  The anticipated duration of the test is 3 Hours.

### Pre-test configuration and documentation.

Activities to occur the morning of 12/22.

- Swales will provide the EO-1 spacecraft database to the MOC.

- Swales will place the flight software used during the MOC to spacecraft interface test under configuration control.  The configured software version numbers shall be documented by Swales. The configured version numbers shall be documented by the FOT as part of the test report.

- The ASIST team will place the ASIST software to be used for the test under configuration control.  The configured version numbers shall be documented by the FOT as part of the test report.

### Test Objectives

The primary objectives of test T1 will be to verify the following:

- The physical hardware in the MOC. .

- The ASIST/FEDS software capability to control the EO1 spacecraft from GSFC building 14 using remote connections to the spacecraft.  The remote connections are required during MOC Mission Readiness Tests, Mission Simulations, and flight operations.

- The following capabilities are primary objectives for test T1:

- Telemetry at 2 KBPS, 32 KBPS – MOC telemetry processing verification

- CCSDS packet commands

- Bypass Commands

- Special Commands

- COP-1 command protocol

- SSR Event dump

- M5 Memory load & dump

- M5 table load & Dump

- The following capabilities are secondary objectives for test T1:

- RTS load – real command sequence which simulates output from CMS

- Telemetry at 1 MBPS

- SSR Dump and post pass processing

- RSN memory load and dump

Test Restrictions

The FOT will NOT send commands to switch power services on the spacecraft.  The powered state of the spacecraft will not change during the test.

### Test Personnel

Swales will provide a test conductor (E.J.Bickley) and an electrical system lead  (Bruce Zink) to monitor the MOC testing at Swales.

The FOT will provide a primary test conductor (Joe Howard) and backup test conductor (Alicia Kost) at the MOC.

The ASIST team will provide a FEDS expert (Larry Alexander) at Swales, a FEDS expert (Tim Ray) at the MOC, and an ASIST expert (Jim Dowling) on call for support.

### Test Responsibilities

Code/Organization/Person	Responsibility

Larry Alexander		FEDS ground system

Tim Ray			FEDS/ASIST at MOC

Jim Dowling			ASIST user workstations – on call

FOT/Joe Howard		MOC lead Test Conductor

FOT/Alica Kost		MOC Test Conductor

Swales/Earle Moyer		Spacecraft configuration

Swales/E.J.Bickley		Spacecraft Database / Spacecraft test conductor

Swales/Bruce Zink		Spacecraft Electrical

ATSC/TriThai			Network Connectivity

NASA/Dan Mandl		Ground Systems & FOT management

### Spacecraft Configuration

Power via solar array simulator 28V direct power to power system electronics (PSE).

Battery will not be on-line.

Spacecraft electronics powered:

- PSE

- S-band receiver

- COMM RSN

- M5 processor

- ACE LVPC – all services OFF

- C&DH LVPC – all services OFF

The spacecraft clock correlation factor will be set to GMT via the I&T clock source.  This accuracy is anticipated to be +/- 5 seconds.

The spacecraft telemetry rate will be commanded to 32kbps with RS, pseudorandom, and rate ½ convolutional encoding.

### Control Hand-over Protocol

Voice communications will be established and verified using speaker phones at both the MOC and SWALES.  The connection will be maintained throughout the test.  Speaker phones will be muted except when communications are needed.

Telemetry data flow will be established between SWALES and the MOC.

After telemetry flow and satisfactory telemetry processing at the MOC are reported via voice communications, command hand-over will begin.

To hand-over commanding, SWALES sends command “UPL COP1 OFF” to initiate blind commanding.  The MOC sends command “UPL COP1 ON” to establish commanding.

When commanding is returned to SWALES, SWALES sends command “UPL COP1 OFF” followed by UPL COP1 ON”.  This sequence will be issued in the event the command link at SWALES needs to be re-established to handle either a failed command link from the MOC or a spacecraft emergency.

### Test Reporting

A post test report will be generated by the FOT documenting the results.

The on-line EO-1 Discrepancy Report tracking system will be used to record problems encountered for this test and all future MOC testing.  Problem reports will also be submitted to subsystem problem tracking systems as needed (i.e. ASIST DR tracking system, Spacecraft problem tracking system, MOPSS DR system, etc.).

### Some Phone Numbers

Larry Alexander 	301-286-9686

Jim Dowling  will be on call for ASIST problems during test

    - pager 202-259-1370  home 301-589-3762

Joe Howard		301-286-9507

Earle Moyer		(301)902-4318

Tim Ray 		301-286-0581

Swales Test Conductor – (301)902-4650   -- EJ Bickley or Leo McConville

Swales secondary phone line (301)902-4207

Swales FAX  301-902-4599

MOC 301-286-2686

MOC secondary phone line – not yet installed.

Here are the issues that needs to be completed:

- FEDS software for remote commanding installed and tested at Swales and MOC.

For questions or comments regarding this test plan contact Jerry Hengemihle via email at jerryh@microtel-md.com or telephone at 301-345-4005 or fax at 301-345-4007.

## T2   Spacecraft – MOC –MOPSS – CMS – FDSS Interface Test

Test T2 is the second ground system Mission Readiness Test.  The Mission Readiness Tests will verify the interoperability of the various ground system elements.  Test T2 includes the EO1 spacecraft, the ASIST/FEDS, CMS, MOPSS, and FDSS.   The inter-element interfaces will be verified by this test.  The planned configuration for this test is to have the MOC equipment located at GSFC building 14 monitor and control the EO1 spacecraft located at SWALES.

Generally, this test is intended to verify the spacecraft housekeeping data flows and the applicable requirements of the ground system.

The following interfaces will be verified:

Spacecraft – MOC

CMS – MOC

CMS – Spacecraft

CMS – MOPSS

MOPSS – FDSS

FDSS - ASIST

### Spacecraft to MOC Interface

This will reverify the testing from test T1.  Some additional command and telemetry capabilities will be verified.  Stored command loads and dumps, recorder dumps and processing.

Secondary

- C&DH M5/WARP code patch or reload

- RSN/Instrument code patch

- Spacecraft clock verification

### MOPSS to CMS

This test will verify the ability of the MOPSS to generate an EO1 daily activity plan(DAP).  The test will verify the ability of CMS to ingest the DAP in order to generate a stored command load for the EO1 spacecraft.

### CMS – ASIST

This test will verify the ability of the ASIST to upload and verify stored command loads generated by CMS.

### CMS – Spacecraft

This test will verify the successful execution of the command load by the EO1 spacecraft.  The load will have originated in MOPSS as a DAP, have been generated by CMS and uplinked via the ASIST/FEDS command telemetry system.

### FDSS to MOPSS

This test will verify the ability of MOPSS to ingest and utilize products from FDSS to generate a DAP.  The FDSS products will include:

- Prepare calibration and attitude command and control products for transmission to FORMATS/MOPSS

- Generate a maneuver command file and transfer to FORMATS/MOPSS

### FDSS to ASIST

This test will verify the ability of the ASIST to generate data products needed by FDSS.  The products include (tbd – need input from Bob Defazio).

- Accept attitude telemetry (including GPS data) from ASIST

- Extract GPS single point solutions from telemetry

- Extract raw GPS data from telemetry to validate on-board GPS orbit determination

- Process Star Tracker playback data

## T3  Spacecraft – MOC - MOPSS – DPS - SVF Interface Testing

Test T3 is the third ground system Mission Readiness Test.  The Mission Readiness Tests will verify the interoperability of the various ground system elements.  Test T3 includes the EO1 spacecraft, the ASIST/FEDS, MOPSS, FDSS, DPS, and SVF.   The inter-element interfaces will be verified by this test.  The planned configuration for this test is to have the MOC equipment located at GSFC building 14 monitor and control the EO1 spacecraft located at SWALES.

Generally, this test is intended to verify the science data flows and applicable requirements of the ground system.

Add a diagram showing the test configuration:

The following interfaces will be verified:

Spacecraft – MOC

MOPSS – DPS

DPS – SVF,ALI/MIT,LEISA, Hyperion/TRW/Stennis

ASIST – DPS (tbd depends on S-band backup mode)

FDSS

### Spacecraft to DPS

This test will verify the ability of the DPS to accept spacecraft generated X-band data.  The data will be processed to level0+.

### DPS – SVF

This test will verify the interface between the DPS and the SVF.  Both a DLT tape and an electronic interface will be verified.

### DPS – MOPSS

Is there an interface here?  How does DPS know about DCE numbers?

### DPS – ASIST

tbd

## T4  RF Compatibility Test

Test T4 is the forth ground system Mission Readiness Test.  The Mission Readiness Tests will verify the interoperability of the various ground system elements.  Test T4 includes the EO1 spacecraft the ground station compatibility test van.

## T5  MOC - Ground Stations Interface Test

Each ground station will be tested to verify  readiness to provide the command, telemetry, and tracking support as defined in the EO-1 DMR.

The Wallops scheduling system will be verified to insure all the scheduling capabilities required by EO-1.

The Wallops SAFS system will be verified.

## T5.1  MOC – TDRSS Interface Test

This test is intended to verify EO-1 telemetry communications via TDRSS. Spacecraft telemetry data will be routed to the RF SOC (tbd), uplinked to an operational TDRSS satellite,  and routed via the TDRSS network to the MOC.

Configuration codes will be provided to the TDRSS White Sands ground station database to include the EO1 spacecraft and 2 kbps telemetry data.

## T6  MOC – WTR – Interface Test

# This test is intended to verify voice and data communications between VAFB and the MOC.  This test will be performed before the launch rehearsal – test M4.

# Mission Simulations (M-Tests)

EO1 Operations plans 4 formal mission simulations to prepare the flight operations team, for EO1 operations.  The EO1 spacecraft team, the instrument teams, and the EO1 project personnel will support the mission simulations as needed.  The EO1 mission simulations and their tentative test dates are listed below:

M1	6/99		L&EO Operations

M2	7/99		Normal Operations / Safehold Recovery

M3	9/99		Contingency Operations

M4	11/99		Launch Rehearsal

## M1	L&EO Operations Simulation

The first mission simulation (M1) will simulate the EO1 launch countdown and early orbit operations. The estimated time duration of test M1 is 48 hours. The primary and secondary objectives for test M1 are as follows:

Primary

- Launch countdown command procedures and control from MOC

- Launch simulation, separation and deployment verification

- Spacecraft stabilization, power positive verification

- On orbit spacecraft power on and checkout

- ACS system verification

- Power system verification

- C&DH system verification

- GPS verification

- WARP operations

- On-orbit stored command loads and execution

- Ground station interface verification

- Operations via pass limited command and telemetry links

Secondary

- tbd

## M2	Normal Operations / Safehold Recovery Simulation

The anticipated time needed for test M2 is 48 hours.  The primary and secondary objectives of test M2 are as follows:

Primary

- Safehold entry – recovery procedure

- On orbit instrument power on and checkout

- Technology Validation procedures

- Trending points and parameters

- SVF interface / MIT interface / Stennis interface / TRW interface

Secondary

- Spacecraft and instrument team ground support equipment final readiness

- Sufficient and timely MOC access to commands and telemetry via ASIST

## M3	Contingency Operations Simulation

The anticipated time needed for test M3 is 48 hours.  The primary and secondary objectives of test M2 are as follows:

Primary

- Contingency / Anomaly conditions

Secondary

- tbd

## Launch Rehearsal Simulations

The I&T team will participate in spacecraft I&T through the comprehensive performance testing after delivery of the spacecraft to the launch site at Vandenberg.  A skeleton crew will remain at the launch site.  Final spacecraft tests, and procedures will be performed from the MOC.

# EO-1 Spacecraft simulator

In addition to spacecraft I&T, a spacecraft simulator will be set up in building 14 at GSFC.  This simulator will be used for procedure and flight software testing after launch.  The spacecraft simulator will also be used for Flight Software Maintenance.

## EO1 Spacecraft Simulator Overview

The EO1 spacecraft simulator will be used by the FOT to test commands, telemetry processing , STOL procedures, the FOT database,  operational stored command uploads, and for operator training.  An option to add a generic RSN breadboard to the configuration allows the EO1 spacecraft simulator to serve as a platform for flight software maintenance and testing.

The major components are the following:

M5 breadboard

Virtual Sat

Command & Telemetry Simulator

Generic RSN breadboard  (optional)

The Command and Telemetry Simulator (CTS) simulator will interface with the MOC FEDS on one side and the M5 flight computer on the other.  The CTS will simulate the ground station interface to the FEDS and the EO1 COMM RSN interface to the M5 flight computer.  In addition, the CTS will simulate the WARP M5, WARP RSN, ALI RSN, LACE, Hyperion, HK RSN and the PSE RSN.  The CTS will accept commands and will generate telemetry for each

spacecraft remote terminal.

The M5 breadboard is an exact duplicate of the flight computer used for C&DH software development.  The flight code version will be loaded into the EEPROMS.  This will give the S/C simulator an exact simulation of the M5 flight computer.

The VirtualSat simulator will simulate the EO1 ACE electronics, the ACS sensors and actuators, and the EO1 flight spacecraft dynamics.  VirtualSat is the same simulator used to test the EO1 ACS flight software.

The optional generic RSN breadboard will provide additional capabilities for exercising the generic capabilities of the RSN including memory and table loads and dumps.  This capability will be particularly useful for flight software maintenance.

## Hardware elements:

The EO1 spacecraft simulator consists of the following hardware elements.

1773 Star Coupler

M5 breadboard

Generic RSN breadboard (option)

VirtualSat:

PC

Condor single function card

Command Telemetry Simulator (CTS)

PC

Ethernet network card

SBS multi-function 1773 card

Miscellaneous

5V power supply

Test equipment rack or card cage (for breadboard and power supply)

Interconnecting cables

## Software Elements:

The EO1 simulator consists of 2 software CSCIs.  The VirtualSat software and the CTS software.

The VirtualSat software is provided by the Hammers Company.  There is no new development required.

The CTS software will be provided by tbd.

### VirtualSat Simulator Description

To be provided.

### EO1 CTS Software Description

The CTS will consists of four major components:  the ground station real time interface, the simulation user interface, the COMM RSN simulator, and the generic remote terminal simulator.

#### Ground Station Interface

1.  Simulate the ground station interface as implemented in the ground station PTP.  The interface uses TCP/IP “sockets” transferring data packets formatted using packet headers following the TRACE format.  The data format is specified in the EO1 Space to Ground ICD.

2.  The ground station interface will be capable of simulating real time ground station passes of operator specified length.  This simulation will consist of the same real time data transfer capability as the ground station PTP.

#### EO1 Spacecraft COMM RSN Simulation

1.  The COMM simulator will process the uplink data stream.  This processing will consist of:

- Preamble detection

- Sync detection

- Codeblock verification

- Codeblock packet formatting

- Codeblock packet data transfer to M5 via 1773 data bus

4.  The COMM simulator will process the downlink data stream.  This processing will consist of:

- VCDU packet reception from M5 via 1773 data bus

- VCDU packet formatting (PTP simuation)

- VCDU time stamp

- VCDU transfer to FEDS via tcp/ip socket interface

The COMM simulator will not simulate the following:

X-band data

2 Mbps S-band downlink ** may be an upgrade option

S-band Reed Solomon, convolutional, pseudorandom encode/decode

Ground station SAFS interface.

#### EO1 Spacecraft Remote Terminal Simulation

The CTS will simulate every EO1 remote terminal (except the ACE RSN). The simulator will provide telemetry housekeeping data packets to the M5 flight computer.  The simulator will accept commands from the 1773 data bus.  Invalid commands will be rejected and valid commands will be accepted.  The level of fidelity of command verification is TBD.

The remote terminal simulator will provide a user interface and a set of generic utilities for defining the contents of telemetry data packets.  The generic utilities will include the following:

Definition of packet data formats.

Definition of static data packet values

Data values incrementing at specific times by specific amounts

Data values changing at specified times

Data values change based on receipt of a valid command packet.

The CTS simulator will be capable of maintaining a user defined powered on configuration of each simulated remote terminal.  Remote terminals with powered off status will not respond to requests for telemetry and will not process commands.

#### Simulation User Interface

The CTS user interface will provide for configuration of the following:

- Powered status of EO1 remote terminals.

- Telemetry packet definition

- Simulation event scheduling

- ground station passes

- others event (tbd)

## CTS Software Design Requirements

The CTS software will be designed such that higher fidelity simulation capabilities may be added at a later date.  These design requirements include:

- High level programming language: C, C++, java, smalltalk, or Ada

- Structured or object oriented design methodology

# Text boxes

jth 10/5/98

ASIST

Cmd/Tlm

FEDS

1773

S/C Data Bus

Virtual-Sat

Spacecraft

Dynamics Simulator

Generic

RSN

Breadboard

(optional)

EO1

M5 Flight

Computer

EO1 Spacecraft Simulator

Command & Telemetry

Simulator

Ground Station I/F,

COMM RSN,

ALI,  AC, Hyperion,

PSE,

WARP,

X-band PA

jth  10/22/98

To ground station

tcp/ip

socket

Spacecraft Simulator

MOC