## TTB
ALCOHOL AND TOBACCO TAX AND TRADE BUREAU
FY 2006 YEAR END SCHEDULE
TTB
RESPONSIBILITY | TTB | Completed Date | Due Date | Responsible Party | Responsible Entity | Completed Date
4TH QUARTER / YEAR END:
Coordinate Y/E due dates with customers | Matt |  | 2006-08-18 | Mat | ARC
Last date to submit Travel authorizations through Gov Trip for travel prior to 9/30/06. | TTB |  | 2006-08-31 | TTB | TTB
Provide the Department with completed updated imputed cost forms - Appendix A. | Peggy |  | 2006-09-01 | Peg | ARC
Close Oracle accounting period 13 06 (AUG/06-06). | SSB |  | 2006-09-05 | SSB | ARC
Submit TIER period 11. | Stacy |  | 2006-09-06 | Sta | ARC
Notify customers that preliminary open items adjustments and certifications are due on 9/13 | Matt |  | 2006-09-06 | Mat | ARC
Department updates TIER Master Appropriation File (MAF) for bureau review - due 9/12 | Dept |  | 2006-09-06 | Dep | Department
IPIA - Provide draft report of the annual amount of high-risk erroneous payments in activities and programs, reduction targets, and progress made in reducing them during FY 2006 (as of 8/31/06) per the final instructions to bureaus and offices for conducting the assessment of and reporting on Improper Payments for FY 2006 to Treasury/AIC | FMB Processing |  | 2006-09-08 | FMB | ARC
Recovery Act - Provide draft report of Recovery Audit Program activity for FY 2006 (as of 8/31/06) to Treasury/AIC per the final instructions to bureaus and offices for establishing and maintaining a Recovery Audit Program and reporting requirements for FY 2006. | FMB Processing |  | 2006-09-08 | FMB | ARC
Bureaus submit draft FMFIA, FFMIA and A-123, Appendix A, Controls over Financial Reporting, Annual Assurance Statements to Treasury | TTB |  | 2006-09-08 | TTB | TTB
ARC provides capitalized asset report and capitalization policy for customer review. Comments on capitalization report are due by 9/25. | Dave |  | 2006-09-08 | Dav | ARC
Department posts updated imputed cost information from Appendix A forms on the DCFO Arena. | Dept |  | 2006-09-08 | Dep | Department
Bureaus review TIER Master Appropriation File (MAF) and report (e-mail) any needed revisions to AIC - Joe McAndrew (202) 622-0807. | Dana |  | 2006-09-12 | Dan | ARC
Preliminary open items adjustments and certifications due including perliminary FY 06 operating plans, if applicable | TTB |  | 2006-09-13 | TTB | TTB
Prepare A/R Allowance adjustment based on YTD August 2006; request required documentation from TTB; finalize on 10/6 | Stacy |  | 2006-09-13 | Sta | ARC
Monthly EFT Report due to Brian Lee | FMB Processing |  | 2006-09-15 | FMB | ARC
Monthly Prompt Pay Report due to Phil Howland | FMB Processing |  | 2006-09-15 | FMB | ARC
Monthly Reconciled/Unreconciled Cash Report due to Dan Waugh | Dave |  | 2006-09-15 | Dav | ARC
Upload August 2006 Statement of Financing to TIER repository. | Stacy |  | 2006-09-15 | Sta | ARC
Bureaus submit the completed updated omitted imputed cost forms (AIC Acctg. Policy Memo 05-01 - Appendix B) via TIER | Peggy |  | 2006-09-15 | Peg | ARC
Last date to submit year end payroll awards through HRD (after this date, awards may be included in September expense accruals) | TTB |  | 2006-09-15 | TTB | TTB
Department distributes OPM cost factors to bureaus | Dept |  | 2006-09-18 | Dep | Department
Begin preparing the OPEB calculations to impute costs of FEHB, FEGLI and FERS/CSRS pension expense (estimate 2 PP based on PP17). Post OPEB by 9/27. | Joy |  | 2006-09-18 | Joy | ARC
Update contact and Treasury Fund Symbol information for FACTS II. | Dana |  | 2006-09-20 | Dan | ARC
Monthly PAR meeting (10AM-noon) | Dana/Stacy |  | 2006-09-20 | Dan | ARC
Draft Shortfalls & Future Plans due in PRS | TTB |  | 2006-09-20 | TTB | TTB
Special payroll accruals for performance and special act awards, and non-routine overtime | TTB |  | 2006-09-22 | TTB | TTB
Any outstanding expiring fund commitments (i.e.single year - 06 or multi-year 05/06) must be obligated or decommitted. | TTB |  | 2006-09-22 | TTB | TTB
FY 2006 capitalized hardware descriptions, useful lives, salvage values and dates placed in service (previously expensed) due to ARC (requested on 9/8). | TTB |  | 2006-09-25 | TTB | TTB
Manual obligations in expiring funds are due to ARC | TTB |  | 2006-09-26 | TTB | TTB
Accounts receivable and accounts payable invoices are due. After this date, any revenue or expenses must be included in accruals | TTB |  | 2006-09-26 | TTB | TTB
Revenue and expense accruals are due including prior month expense accrual adjustments | TTB |  | 2006-09-27 | TTB | TTB
Book OPEB. | Joy |  | 2006-09-27 | Joy | ARC
Depreciation/amortization expense should be posted by today. | Dave |  | 2006-09-28 | Dav | ARC
Final certification and adjustments to open items are due by noon. | TTB |  | Noon 9/29/2006 | TTB | TTB
A-123, Appendix A - Report to Update Treasury DCFO on the final FY 2006 results and status of all Corrective Action Plans. | TTB |  | 2006-09-29 | TTB | TTB
Department conducts Bureau Heads meeting on critical PAR dates and deliverables. | TTB |  | 2006-09-29 | TTB | TTB
Book leave liability. Last actual pay period is 18. | Dave |  | 2006-09-29 | Dav | ARC
Send notification to FMB, TSD, CAB, PSD employees not to post any September transactions after October 3, regardless of SEP/06-06's posting availability as trial balances will be considered final after COB 10/3/06. | Dana |  | 2006-10-02 | Dan | ARC
Department submits Financial Statement Templates to FMS based on closing package requirement. | Dept |  | 2006-10-03 | Dep | Department
Bureaus will provide final narratives for MD&A strategic goals | TTB |  | 2006-10-03 | TTB | TTB
Run preliminary Budgetary/Proprietary Reconciliation | Dave |  | 2006-10-03 | Dav | ARC
JE 2007 commitments out of 47**** and 461004. Reverse in OCT/06-07. | Stacy |  | 2006-10-03 | Sta | ARC
JE 2007 obligations out of 480*** and 461004. Reverse in OCT/06-07. | Stacy |  | 2006-10-03 | Sta | ARC
Close 298001 to 101024 for custodial activity. | Stacy |  | 2006-10-03 | Sta | ARC
Close accounting period 14 06 (SEP/06-06). | SSB |  | 2006-10-03 | SSB | ARC
On a daily basis, begin running GL posted Discoverer report to ensure no activity has been posted in SEP/06-06. | Dana |  | 2006-10-04 |  |  | N/A
Submit TIER period 12. AIC submission due date is 10/10. AIC approval is required for period 12 resubmissions between 10/11 - 10/13. | Stacy |  | 2006-10-04 | Sta | ARC
September SF-224 Transmission (3rd workday) | Dave |  | 2006-10-04 | Dav | ARC
Based on bureau's TIER submission, initial draft financial statements will be generated through CFOV based on this data, and posted to the DCFO Web Repository for bureau review as of 12 06. | Dept |  | 2006-10-05 | Dep | Department
Provide an e-mail to customers to let them know the FFMIA/FMFIA assurance has not changed | FMB |  | 2006-10-05 | FMB | ARC
Review GWA Account Summary Statement for other ALCs impact to our September transactions. | Dave |  | 2006-10-05 | Dav | ARC
Complete FY 2006 A/R allowance calculation | Stacy |  | 2006-10-06 | Sta | ARC
IPIA - Provide final report of the annual amount of high-risk erroneous payments in activities and programs, reduction targets, and progress made in reducing them during FY 2006 (as of 9/30/06) per the final instructions to bureaus and offices for conducting the assessment of and reporting on Improper Payments for FY 2006 to Treasury/AIC | FMB Processing |  | 2006-10-06 | FMB | ARC
Recovery Act - Provide final report of Recovery Audit Program activity for FY 2006 (as of 9/30/06) to Treasury/AIC per the final instructions to bureaus and offices for establishing and maintaining a Recovery Audit Program and reporting requirements for FY 2006. | FMB Processing |  | 2006-10-06 | FMB | ARC
Submit TIER period 12 revisions (with AIC approval) for FACTS II Submission (FACTS II Window = 10/6-10/26). Upon notification from Treasury that FACTS II submission was successful, login to FACTS II and run and print SF-133's, SF-2108 and ATB's. Send copies of reports and certification statement to customers - certification due to ARC on 10/24. ARC certification on FACTS II website due 10/26. | Stacy |  | 2006-10-10 | Sta | ARC
Obtain and provide DOL expenses/charges to bureaus. | Dept |  | 2006-10-10 | Dep | Department
Post DOL expenses in October if they are posted after 10/3. | Stacy |  | 2006-10-10
DO/FMD will issue the 4th quarter Transactions by Fund and Vendor Report, which includes Working Capital Fund advance information. NOTE: Post in October if WCF liquidation is posted after 10/3. | Dave/Aaron |  | 2006-10-10 | Dav | ARC
Final report on actions taken to address FY 2005 Management Challenges/High-Risk Areas to be e-mailed to I-Ming Clark. | TTB |  | 2006-10-11 | TTB | TTB
Final performance data and explanations of shortfalls due into Performance Reporting System (PRS) | TTB |  | 2006-10-12 | TTB | TTB
Check "Judgment Fund" website for claims (http://www.fms.treas.gov/judgefund/) | Joy |  | 2006-10-12 | Joy | ARC
FMS 6652,6653,6654 &6655 Available - Prepare cash rec and determine if TIER needs to be resubmitted due to cash outlays. | Dave/Stacy |  | 2006-10-12 | Dav | ARC
Drafts due for: 1) Statement of Financing (if not fully automated); 2) Notes to the financial statements; 3) MD&A (future effects); and 4) Required Supplemental Information and Other Accompanying Information. | TTB/ARC |  | 2006-10-13 | TTB | TTB
Annual Assurance - Unaudited Bureau and Offices submit FINAL FMFIA, FFMIA, and A-123, Appendix A, Controls Over Financial Reporting, Annual Assurance Statement to Treasury (A-123 section only required if bureau or office is at the material 10% contribution level) | TTB |  | 2006-10-13 | TTB | TTB
Final Performance in PRS and PRS locks down | TTB |  | 2006-10-13 | TTB | TTB
Monthly EFT Report due to Brian Lee | FMB Processing |  | 2006-10-13 | FMB | ARC
Monthly Prompt Pay Report due to Phil Howland | FMB Processing |  | 2006-10-13 | FMB | ARC
Monthly Reconciled/Unreconciled Cash Report due to Dan Waugh | Dave |  | 2006-10-13 | Dav | ARC
Quarterly suspense clearing due to Dan W. | Dave |  | 2006-10-13 | Dav | ARC
Submit 4th quarter admininistrative debt information in prescribed format to Brian Lee. (federal receivables/delinquencies) | Stacy |  | 2006-10-13 | Sta | ARC
Department verifies preparer/certifier and TAFS information for FACTS II | Dept |  | 2006-10-13 | Dep | Department
Department adds 6653 Data to the TIER budget edit checks. Note: FACTS II window opens this date; closes 10/26; We should have period 12 loaded into TIER | Dept/ARC |  | 2006-10-13 | Dep | Department
Resubmit period 12 06 TIER file to include cohort data and/or adjustments for cash outlays. | Stacy |  | 2006-10-16 | Sta | ARC
Bureaus run WebTIER TEP and FAER reports, and begin elimination reconciliation processes (certification due 10/30/06). | ARC |  | 2006-10-16 | ARC | ARC
Download and verify FACTS II accounts and balances (window open 10/13-10/26; certification is due on FACTS II website 10/26). Send FACTS II 133s and 2108s to customers. Customer certification due to ARC on 10/24. | Dana/Stacy |  | 2006-10-18 | Dan | ARC
Department will provide draft Performance and Accountability Report to OIG and Chief of Staff, and post on DCFO Web Repository for bureau review and comment. | Dept |  | 2006-10-18 | Dep | Department
Bureaus submit first update of the unasserted claim representation letters to AIC (as of 9/30/06, updated through 10/15/06). Note: A combined unasserted claim and legal representation response is not permissible. | TTB |  | 2006-10-18 | TTB | TTB
Bureaus submit variance analysis of quarterly financial statements. | Stacy |  | 2006-10-18 | Sta | ARC
Bureaus provide first update of the legal representation letter to OGC including bureau CFO & legal council contingent liability figure concurrence (as of 9/30/06, updated through 10/15/06). Note: A combined unasserted claim and legal representation response is not permissible. | TTB |  | 2006-10-23 | TTB | TTB
FACTS II certifications due from customers (requested on 10/18). | TTB/Stacy |  | 2006-10-24 | TTB | TTB
Bureaus provide final comments on draft Performance and Accountability Report. | TTB |  | 2006-10-24 | TTB | TTB
Unaudited or partially audited bureaus provide full scope management representation letters to AIC | TTB |  | 2006-10-24 | TTB | TTB
SF 220-9 Report on Receivables Due from the Public prepared and sent with certification statement to customer for review. See the following website: http://www.fms.treas.gov/debt/dmrpts.html Available between 10/13-11/15 (certification due to ARC by 11/10) | Stacy |  | 2006-10-25 | Sta | ARC
Provide elimination certification documentation to Customers for 10/30 department certification | Stacy |  | 2006-10-25 | Sta | ARC
Bureaus submit Adjusted Trial Balance (final period 12), which incorporates all final adjustments, to TIER for preparation of final Department-wide financial statements, including the Net Cost Percentage Calculator, which is applicable to bureaus that report multiple programs on the SONC. | Stacy |  | 2006-10-26 | Sta | ARC
Resubmissions of period 12 TIER data due for FACTS II submission. Note: FACTS II window officially closes on 10/26. | Stacy |  | 2006-10-26 | Sta | ARC
ARC Certification is due on FACTS II website. | Dana/Matt |  | 2006-10-26 | Dan | ARC
Department completes FACTS II submission to FMS | Dept |  | 2006-10-26 | Dep | Department
Finals due for: 1) Statement of Financing (if not fully automated); 2) Notes to the financial statements, Required Supplemental Information and Other Accompanying Information (Excel File.) This also includes submitting the Closing Package notes (filename: CP_Notes.xls) to WebTIER. | TTB/Stacy |  | 2006-10-27 | TTB | TTB
Notes and supplemental information for closing package due | Stacy |  | 2006-10-30 | Sta | ARC
Bureaus provide final certified Department-wide and Government-wide elimination entry data to the Department through WebTIER TEP and FAER reports [began elimination process 10/16/06); provided to Customers on October 25 | TTB/Stacy |  | 2006-10-30 | TTB | TTB
JE 1010** accounts to close to 101001 in OCT/ADJ/06-07. | Stacy |  | 2006-10-31 | Sta | ARC
JE 310*** accounts to close to 310001 in OCT/ADJ/06-07. | Stacy |  | 2006-10-31 | Sta | ARC
JE 461001 balances to 445001 in OCT/ADJ/06-07 since 461001 balances cannot exist in FY 2007 beginning balances for funds that are subject to reapportionment in the new year. | Stacy |  | 2006-10-31 | Sta | ARC
JE all outstanding FY 2006 commitment balances in OCT/ADJ/06-07 (DR 47*001; CR 46*004 - using AF details); Reverse in OCT/06-07. | Stacy |  | 2006-10-31 | Sta | ARC
JE 46100* net balance in expired funds in OCT/ADJ/06-07 (DR 461006; CR 465001) to show 4650 in FY 2007 beginning balance | Stacy |  | 2006-10-31 | Sta | ARC
In OCT/06-07, reverse commitment JEs posted in SEP/06-06 and OCT/ADJ/06-07 that closed commitment balances. This reestablishes the activity in the new fiscal year, which is in agreement with PRISM. | Stacy |  | 2006-10-31 | Sta | ARC
In OCT/06-07, reverse obligation JE posted in SEP/06-06 that backed off FY 2007 obligations. This reestablishes the activity in the new fiscal year, which is in agreement with PRISM. | Stacy |  | 2006-10-31 | Sta | ARC
Bureaus e-mail update of the unasserted claim representation letters to AIC (as of 9/30/06, updated through 11/3/06). Note: A combined unasserted claim and legal representation response is not permissible. | TTB |  | 2006-11-03 | TTB | TTB
Bureaus email legal representation update to OGC thru November 3rd timeframe. Note: A combined unasserted claim and legal representation response is not permissible. | TTB |  | 2006-11-03 | TTB | TTB
Certification for SF 220-9 (Report on Receivables) provided by ARC on 10/25 is due. Also, submit Report on Receivables. Reporting window closes 11/15/06. | TTB/Stacy |  | 2006-11-10 | TTB | TTB
Provide 4th quarter TIER/TROR reconcilation and FMS certification to Brian Lee | Stacy |  | 2006-11-14 | Sta | ARC
Department submits FACTS I ATB and Notes to FMS through GFRS | Dept |  | 2006-11-14 | Dep | Department
Perform preliminary year end close review. | Stacy |  | 2006-11-15 | Sta | ARC
Close accounting period 15 - Postclosing TB (Annual close creates beginning balances in AP 00 - Oracle) | SSB |  | TBD | SSB | ARC
Close accounting period 02 07 | SSB |  | 2006-12-04 | SSB | ARC
TIER period 00 and 02 2007 transmission. | Stacy |  | 2006-12-06 | Sta | ARC