U.S. ATLAS PROJECT OFFICE

Physics Department

UPTON, NEW YORK 11973

December 5, 2006

Dr. Thomas Ferbel

SC-25/Germantown Building
U.S. Department of Energy
1000 Independence Avenue, SW
Washington, D.C. 20585-1290

Dr. Peter Bond

Associate Laboratory Director

Brookhaven National Laboratory

Upton, NY  11973

SUBJECT:  U.S. ATLAS Research Program Quarterly Status Report

Dear Sirs:

Attached please find U.S. ATLAS Research Program Quarterly Status Report No. 9 for the period July-September 2006.

Sincerely yours,

Howard A. Gordon

U.S. ATLAS Deputy Research Program Manager

Head, U.S. ATLAS Project Office

Distribution:

Abolins, M.

Alam, S.

Baker, K.

Barnett, M.

Bensinger, J.

Blair, R.

Bond, P.

Brau, J.

Butehorn, C.

Byon-Wagner, A.

Carolan, P. - DOE

Cleland, W.

Coles, M. – NSF

Crawford, G. - DOE

De, K.

Dodd, J.

Ernst, R.

Ernst, M.

Errede, S.

Ferbel, T. - DOE

Gilchriese, M.

Goldberg, M. – NSF

Gonzalez, S.

Grillo, A.

Harrison, M.

Hinchliffe, I.

Huth, J.

Kagan, H.

Kane, S.

Kirby, D.

Kogut, J. - DOE

Lankford, A.

Larsen, R. - DAP

Lissauer, D.

Lipton, R. - DAP

Lubatti, H.

Mantsch, P. – DAP

McFarlane, K.

Meyers, P. – PAP

Neal, H.

Nemethy, P.

Ogren, H.

Oh, S.

Parsons, J.

Pilcher, J.

Polychronakos, V.

Price, L.

Pripstein, M. – NSF

Rizatdinova, F.

Roser, R. - DAP

Rutherfoord, J.

Seiden, A.

Seidel, S.

Shank, J.

Shochet, M.

Skubic, P.

Sliwa, K.

Stroynowski, R.

Su, D.

Taylor, F.

Tuts, M.

Whitaker, S.

Willocq, S.

Wolbers, S. - DAP

Williams, H.

Willis, W.

Wu, S.L.

research program STATUS REPORT NO. 9

REPORTING PERIOD

July-September 2006

Table of Contents

1.	Executive Associate Project Manager’s Summary (J. Shank, BU)	4

2.	Technical Progress Reports	4

2.2 Software	4

2.3 Facilities	21

3.1 M&O Silicon	30

3.2 M&O TRT	30

3.3 M&O Liquid Argon	34

3.4 M&O Tile	34

3.5 M&O Muon	44

3.6 M&O Trigger	46

3.10 Technical  Coordination								  56

4.1 Inner Detector Upgrade R&D								  58

4.3 Liquid Argon Upgrade R&D								  65

4.5 Muon Upgrade R&D									  67

3.	Financial Report (Chuck Butehorn, BNL)	69

# Executive Associate Project Manager’s Summary (J. Shank, BU)

The computing effort for this quarter continued to be focused on running production for the Computing System Commissioning (CSC) exercises which started in earnest last quarter. The main software development was the release of 12.0.3, the software needed for the currently running production for CSC.  There were key meetings this quarter on Tier 2 facilities (T2 meeting at Harvard August, 2006) and on the Distributed Data Management (DDM) system (DDM workshop at BNL, Sept. 2006)).  These meetings allowed us to focus on ramping up our facilities to handle the increasing demands of the CSC exercises and handle the growing amount of simulated data that is distributed around the world. We continue to debug/harden the ATLAS DDM and work on easing DDM deployment. Throughout this quarter our Tier1 and Tier 2 sites were filled with CSC production running.

# Technical Progress Reports

## 2.2 Software

2.2 Subsystem Manager's Summary

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release 12.0.x validated | 30-Aug-06 | -- | 30-Nov-06 | Delayed (See #1) |
| Release 13.0.0 | 15-Feb-07 | [New] | 15-Feb-07 | On Schedule |

Note #1  Release 12.0.x continues to be validated, expected to be complete by end of 2006 and used for CSC simulation production

Srini Rajagopalan (Brookhaven National Laboratory)

The software effort during this quarter continues to be preparation for the upcoming Computing System Commissioning (CSC). Release 12.0.0 was released this quarter. The validation of this production release and addition of necessary functionalities continues. Release 12.0.3 came out on September 22, 2006 and included an extensively validated simulation and digitization packages. The intent is to use this production release for the simulation production for CSC.

Release 12.0.4 is expected in November 2006, and will include updated calibration constants needed to take into account new material and misalignment effects in 12.0.3 simulation. The highest priority is therefore production of calibration samples which will quickly be analyzed and updated constants made available in 12.0.4. 12.0.4 will then be used for reconstruction of the simulation production and subsequent CSC analysis studies.

Release 13.0.0 is expected to come out in February 2007 and Release 14 in June 2007. A validated release 14 will be deployed for the initial (900 GeV) LHC running.

PANDA, a major U.S. deliverable, is successfully being used for the CSC production. The U.S. is also increasing its focus on Distributed Data Management adding pressure to the ATLAS computing management to ensure that a robust system is developed and deployed in time for the CSC exercises. Alexei Klimentov (BNL) has now been appointed to focus on the U.S. Distributed Data Management effort.

The analysis support centers continue to mature with one-week analysis jamborees being held or planned at the three analysis support centers (ANL, BNL, LBNL).

2.2.2 Core Services

2.2.2.1 Framework

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration of Seal plug-in Mechanism | 14-Nov-05 | 14-Oct-06 | 11-Dec-06 | Delayed (See #1) |
| python-accessible Property Repository | 1-Feb-06 | -- | 1-Sep-06 | Completed |
| use GaudiPython to provide interactive access to (selected) framework functionality | 8-Feb-06 | 14-Sep-06 | 31-Jan-07 | Delayed (See #2) |
| High-level job configuration design and tools | 14-Feb-06 | 14-Nov-06 | 11-Dec-06 | Delayed (See #3) |
| History & Property Mech Integ | 14-Feb-06 | -- | 31-Jan-07 | Delayed (See #4) |
| flexible job reinitialization | 1-Jun-06 | 14-Sep-06 | 14-Jun-07 | Delayed (See #5) |
| port Gaudi and Control to 64-bit architectures | 1-Jul-06 | 1-Jul-06 | 1-Sep-06 | Completed (See #6) |
| Review ATLAS Python Scripts for usability (Indiana) | 1-Sep-06 | -- | 1-Sep-06 | Completed |
| Generic event dump (needed for validation tests) | 14-Sep-06 | 14-Sep-06 | 31-Jan-07 | Delayed (See #7) |
| Enhance AtRndmGenSvc | 11-Dec-06 | [New] | 11-Dec-06 | On Schedule (See #8) |
| common online/offline error reporting/handling | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Note #1  we implemented a prototype plugin mgr in Gaudi, still based on Gaudi DLL mechanism and the new Configurables. This will be put in production in release 13. It may be replaced in the future by a reflex-based scheme.

Note #2  started work on StoreGate access.

Note #3  Two CS summer students at LBL delivered a framework to access the PropertyRepository as their project work. Focus now is on

new-style job configuration: Job-level properties, ToolHandle, ServiceHandle (possibly DataObjectHandle), migrate all core examples to configurables, document migration procedure (basic documentation exists).

Note #4  awaits history persistency.

Note #5  some progress with framework tool but still no real-life test of the functionality. This may come with TDAQ "Large scale test" scheduled for next spring

Note #6  port completed in time. Unfortunately while Gaudi and Control compile and run fine in 64-bit machines, athena reconstruction jobs are much too big to run on lxplus. We should try to address this problem after release 13

Note #7  prototype in c++ available. During prototype development it appeared obvious that a python implementation is probably easier to write and maintain. This will be investigated till December and a final implementation will go in release 13

Note #8  automatically seed generator from the run/evt# stream ID, evaluate new random engine, possibly allow to choose random engine

2.2.2.2 EDM Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration with POOL-Cache Manager | 31-Dec-05 | 6-Sep-06 | 6-Sep-07 | Delayed (See #1) |
| Support for History Objects | 14-Feb-06 | 14-Jun-06 | 14-Jun-07 | Delayed (See #2) |
| evaluate the need of object aliases and versioning in StoreGate | 14-Sep-06 | -- | 14-Sep-06 | Completed (See #3) |
| Integrate CLID Database Generation | 14-Sep-06 | 14-Sep-06 | 11-Feb-07 | Delayed (See #4) |
| provide common base class for Element/DataLinks | 14-Sep-06 | 14-Sep-06 | 11-Feb-07 | Delayed (See #5) |
| support DataLinks across different stores | 23-Sep-06 | 23-Sep-06 | 11-Feb-07 | Delayed (See #6) |
| Prototype Support for Integer Keys | 30-Sep-06 | 30-Sep-06 | 11-Feb-07 | Delayed (See #7) |
| update DataList, evaluate DataMap and association objects | 1-Dec-06 | 1-Dec-06 | 1-Sep-06 | Completed |
| DataVector safe symlink mechanism | 11-Dec-06 | [New] | 11-Dec-06 | On Schedule (See #8) |
| New Style INavigableFourMomentum | 11-Dec-06 | [New] | 11-Dec-06 | On Schedule |

Note #1  low priority

Note #2  prototyped persistency using pickle. POOL needs Transient/Persistent separation. Low priority

Note #3  still need to test alias persistency, but a scheme is in place

Note #4  Not critical for release 13

Note #5  prototype under development. Not critical for release 13

Note #6-7  Not critical for release 13

Note #8  depends on ROOT schedule

2.2.2.3 Detector Description

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| CPU/Memory Optimization Effort Final Report (Pitt) | 1-May-06 | 1-Jul-06 | 1-Jan-07 | Delayed (See #1) |
| Initialization time performance study | 1-May-06 | 1-Jul-06 | 1-Jan-07 | Delayed (See #2) |
| Database preemption system delivery date (Pitt) | 1-Sep-06 | -- | 1-Jan-07 | Delayed (See #3) |
| Geometry Database overriders | 1-Sep-06 | -- | 1-Jan-07 | Delayed (See #4) |
| LAr Readout Geometry Revision | 1-Dec-06 | [New] | 1-Dec-06 | On Schedule |
| Readout geometry working for LAr (all clients) | 1-Jan-07 | [New] | 1-Jan-07 | On Schedule |

Note #1-2  Tied to the completion of the LAr Readout Geometry Revision.

Note #3-4  Delayed till the completion of the LAr Readout Geometry Revision.

Joe Boudreau (University of Pittsburgh)

Nearly all of the effort in this quarter went into preparing the CSC exercise. This included a large amount of database administration, debugging, declashing, and revising the geometry, particularly the geometry of the LAr (and particularly in the endcap and the crack).

In addition we made a large effort to revise, more or less completely, the readout geometry of the LAr. This will dramatically reduce the memory consumption, we think, and will also provide a much tighter coupling between readout geometry and simulation geometry, and a badly needed cleanup in the LAR detector description.

This is nearly done. The first layer is complete for 12.3.0. The second layer is also nearly ready and will go in immediately following the release of 12.3.0. We can foresee a little debugging thereafter. And following that we will make sure that this is useful not only for full ATLAS but also for the beam test configurations, and also for the digitization and reconstruction of those configurations.

2.2.2.4 Graphics

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Configuration Presets available in v-atlas | 1-Sep-06 | 1-Sep-06 | 1-Jan-07 | Delayed (See #1) |

Note #1  Joe will do this over the holiday break.

Joe Boudreau (University of Pittsburgh)

The v-atlas program was revised: it is now a python script and not a shell script that writes python scripts. Sounds minor but the impact of this small change on maintainability is impressive.

A full revision of the tracks display was carried out. Users can click on tracks and see their hits light up, as well as the surfaces. Muon tracks are displayed. And other nice features added to the interface. Very well received in the tracking group.

2.2.2.5 Analysis Tools

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| access Atlas Data from python | 8-Feb-06 | -- | 31-May-06 | Completed (See #1) |
| support event thinning for AOD data | 14-Sep-06 | 14-Sep-06 | 11-Dec-06 | Delayed (See #2) |
| runtime recompilation/reloading | 15-Sep-06 | 15-Sep-06 | 15-Jun-07 | Delayed (See #3) |
| automatic generation of transformations | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Note #1  works with pyROOT, now needs better interface to event store from athena.py

Note #2  prototype exists. Will go in release 13

Note #3  low priority. Awaits experience with interactive athena.

2.2.2.6 Grid Integration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Job Transformations in Python | 14-Feb-06 | -- | 14-Nov-06 | Delayed (See #1) |
| Prototype Implementation for Grid Monitoring Architecture | 30-Sep-06 | -- | 30-Sep-06 | Completed |
| extract job metadata from athena | 15-Dec-06 | -- | 15-Dec-06 | On Schedule |
| Improve message formatting and filtering | 15-Dec-06 | -- | 15-Dec-06 | On Schedule |

Note #1  infrastructure deployed in release 12 preproduction. Will need continuous maintenance, further development at least till release 13

2.2.2.7 Core Service Usability

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| add and use help string to Gaudi Property | 18-Feb-06 | -- | 18-Nov-06 | Delayed (See #1) |
| Configurable-based job configuration | 1-May-06 | 29-Aug-06 | 31-Jan-07 | Delayed (See #2) |
| provide job-level properties a la SimFlags | 1-May-06 | 29-Aug-06 | 11-Dec-06 | Delayed (See #3) |
| Integrated athena configuration and development environment | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |
| Job Configuration editor/browser/debugger | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Note #1  Help string handling added in gaudi. First tool using it is Job Options Inspector.

Note #2  Infrastructure almost finished. Further delays in release schedule have led to target the migration for release 13.

Note #3  prototype available. Further delays in release schedule have led to target the migration for release 13.

2.2.3 Data Management

David Malon (ANL)

As ATLAS approaches full-chain testing, more and more components require integration with upstream components, and hence are more subject to delays outside of U.S. Research Program control. Event-level selections, for example, require trigger decision information that is not yet available to event tag builders. Luminosity information essential to commissioning an offline cross-section calculation support infrastructure, and quality and detector status summary information necessary to support sample selection, are also not yet available.

As international ATLAS begins to think more concretely about data-taking, a number of task forces are being commissioned. A metadata task force is underway, as is a streaming study group, and an Analysis Object Data

(AOD) format task force will begin work in October 2006. U.S. Research Program participation in all of these is strong. These initiatives will doubtless provide important input to the ATLAS event store and data management efforts, but one of the consequences is that delivery of some components must be delayed until recommendations are formulated. The U.S. ATLAS Research Program should anticipate a significant last-minute influx of requirements in its 2007 effort planning.

2.2.3.1 Database Services and Servers

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Completion of FroNTier (data caching technology) testing | 1-Sep-06 | 1-Sep-06 | 31-Dec-06 | Delayed (See #1) |
| LCG 3D service deployment at U.S. ATLAS Tier 1 | 1-Nov-06 | -- | 1-Nov-06 | On Schedule |
| Database Deployment and Operations infrastructure ready for calibration data challenge | 1-Dec-06 | 1-Dec-06 | 31-Mar-07 | Delayed (See #2) |
| Completion of database deployment tests via DDM DQ2 | 1-Feb-07 | [New] | 1-Feb-07 | On Schedule |
| DDO infrastructure ready for Full Dress Rehearsal | 30-Jun-07 | [New] | 30-Jun-07 | On Schedule |

Note #1  September 2006: This milestone is now a collaborative milestone including non-U.S. contributors, subject to international ATLAS schedules.

Note #2  September 2006: delayed because of delays to the international ATLAS calibration data challenge itself

2.2.3.2 Common Data Mgmt Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support for Placement Control | 7-Nov-05 | 7-Aug-06 | 31-Jan-07 | Delayed (See #1) |
| Support for Multiple Transaction Contexts | 14-Nov-05 | 9-Oct-06 | 17-Apr-07 | Delayed (See #2) |
| User-level documentation for Athena I/O infrastructure | 27-Mar-06 | 17-Jul-06 | 28-Aug-06 | Completed (See #3) |
| Transient/persistent separation infrastructure for heterogeneous containers | 21-Aug-06 | -- | 21-Aug-06 | Completed |
| Extended ROOT/POOL options setting (e.g., 64-bit values) | 4-Sep-06 | -- | 4-Sep-06 | Completed |
| Support for files larger than 2 GB | 4-Sep-06 | -- | 4-Sep-06 | Completed |
| Refactorization of persistence packages and services | 11-Sep-06 | -- | 11-Sep-06 | Completed |
| Address cascade ("chain") effect in transient/persistent separation | 6-Nov-06 | [New] | 6-Nov-06 | On Schedule |
| Complete move to Configurables, and new Property model | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule |
| I/O performance optimization and tuning | 10-Apr-07 | [New] | 10-Apr-07 | On Schedule |

Note #1  December 2005: Agreement with ATLAS software management is to postpone this milestone until it is specifically requested or required by physics.

June 2006: This work will be deferred until after the ATLAS streaming study group makes its recommendations.

September 2006: International ATLAS streaming study group has not yet made recommendations. In the interim, POOL placement control capabilities have been extended.

Note #2  December 2005: A limited version will be introduced into early 2006 releases, but a more general strategy awaits the outcome of a spring 2006 event store developers workshop.

September 2006: Transaction context control will require changes to the LCG POOL code base. These changes are not expected before early 2007.

Note #3  31 March 2006: Partially complete; completion pending documentation of Release 12 infrastructure, which was delayed by international ATLAS.

September 2006: Twiki-based user-level documentation was improved after Release 12. Documentation to enhance usability remains a priority, though, and a new documentation-related milestone will be introduced soon.

2.2.3.3 Event Store

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Job-level history object and configuration persistence prototype | 2-Oct-05 | 18-Dec-06 | 10-Apr-07 | Delayed (See #1) |
| Unique EDO Identification Infrastructure | 31-Jan-06 | 25-Sep-06 | 10-Apr-07 | Delayed (See #2) |
| Infrastructure to support stream- and run-level metadata | 27-Mar-06 | 25-Sep-06 | 31-Jan-07 | Delayed (See #3) |
| Strategy for run-level, stream-level, file-level metadata | 22-May-06 | 25-Sep-06 | 18-Dec-06 | Delayed (See #4) |
| Back navigation support for bytestream data | 7-Aug-06 | 7-Aug-06 | 31-Jan-07 | Delayed (See #5) |
| EventHeader/EventInfo extensions to support luminosity blocks, etc. | 11-Sep-06 | 11-Sep-06 | 31-Jan-07 | Delayed (See #6) |
| EventSelector improvements | 11-Sep-06 | -- | 11-Sep-06 | Completed |
| Trigger decision representation in EventInfo/TriggerInfo | 11-Sep-06 | -- | 11-Sep-06 | Completed |
| Event store components for streaming studies | 25-Sep-06 | -- | 25-Sep-06 | Completed |
| Prototype alternative event streaming strategies | 11-Dec-06 | -- | 11-Dec-06 | On Schedule (See #7) |
| AthenaPOOL/bytestream event selector unification | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule |
| DataHeader evolution to support POOL tokens more efficiently, and to support bytestream references | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule |
| User-level event store documentation improvements | 12-Feb-07 | [New] | 12-Feb-07 | On Schedule |
| Utilities and optimizations to support an efficient skimming service | 10-Apr-07 | [New] | 10-Apr-07 | On Schedule |

Note #1  30 September 2005: Actual delivery may be later in the quarter because the prototype requires new versions of LCG dictionary software that will not be delivered to us until later in the quarter.

December 2005: This milestone must be delayed until some time after the corresponding control framework history infrastructure is in place.

September 2006: The corresponding control framework support has been descoped from Release 13, so event store support cannot be provided until a subsequent release.

Note #2  31 March 2006: Delayed pending outcome of May 2006 Physics Analysis Tools workshop

September 2006: Descoped from core and event data model plans for Release 13, and hence from event store work as well.

Note #3  31 March 2006: Delayed pending proposed ATLAS metadata task force

September 2006: International ATLAS metadata task force has begun work, but has provided no guidance or recommendations yet.

Note #4  31 March 2006: Delayed pending proposed ATLAS metadata task force

September 2006: International ATLAS metadata task force has begun work, but has provided no guidance or recommendations yet.

Note #5  September 2006: Implementation requires changes to bytestream I/O services provided by TDAQ. These will not be available until after the next TDAQ software release (currently proposed for November 2006).

Note #6  September 2006: Extensions sufficient to support luminosity block identification in streams tests have been added, but "final" work awaits TDAQ work on evolution of the ATLAS event header.

Note #7  September 2006: While event-store-specific components are ready, delays in preparation of data samples may cause some reduction in the scale of this prototype.

2.2.3.4 Non-Event Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Maintain NOVA for use by LAr calorimeter until COOL transition is complete | 31-Jan-06 | 1-Jul-06 | 31-Jan-07 | On Schedule (See #1) |
| Ensure event store integration with non-event data needed for cross section calculation | 3-Jul-07 | [New] | 3-Jul-07 | On Schedule |

Note #1  September 2007: NOVA may need support for a bit longer, while COOL transition (not a U.S. responsibility) is incomplete. Forecast is based upon international ATLAS Release 13 schedule.

2.2.3.5 Collections, Catalogs, Metadata

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Athena Interface/Read/Write Access to Collection-Level Metadata | 19-Dec-05 | 24-Jul-06 | 31-Jan-07 | Delayed (See #1) |
| Integration of Collection Support & Bookkeeping | 19-Dec-05 | 24-Jul-06 | 31-Jan-07 | Delayed (See #2) |
| Evaluation of strategies for support of variable-length structures in tags | 27-Feb-06 | 25-Sep-06 | 31-Jan-07 | Delayed (See #3) |
| Transition POOL collections to CORAL AttributeLists and component library model | 17-Apr-06 | -- | 7-Aug-06 | Completed |
| Support extensible collections, and collection reblocking | 22-May-06 | 7-Aug-06 | 31-Jan-07 | Delayed (See #4) |
| Integration and support of event-level metadata in commissioning tests | 25-Sep-06 | -- | 25-Sep-06 | Completed |
| Demonstrate tag database building and selection at a Tier 2 center | 11-Dec-06 | -- | 11-Dec-06 | On Schedule |
| Demonstrate tag-based selection for alternative streaming models | 11-Dec-06 | -- | 11-Dec-06 | On Schedule |
| Address primary key infrastructure issues | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule |
| Consistent reference handling, and primary reference naming | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule |
| Propose and implement appropriate primary key for ATLAS event tags | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule |
| Prototype tag query integration with detector status and quality information | 26-Mar-07 | -- | 26-Mar-07 | On Schedule |
| Prototype tag query integration with luminosity block information | 26-Mar-07 | -- | 26-Mar-07 | On Schedule |
| Implement relational collection model in MySQL | 10-Apr-07 | [New] | 10-Apr-07 | On Schedule |
| Prototype indexing strategies for tag database | 3-Jul-07 | [New] | 3-Jul-07 | On Schedule |
| Migration of POOL collections infrastructure to "component model" | 4-Dec-07 | [New] | 4-Dec-07 | On Schedule |

Note #1  September 2006: An underlying component (AMI, from Grenoble) is behind schedule. New effort from Glasgow has been recruited.

The revised schedule calls for delivery of this component in ATLAS Release 13, which has itself been delayed until January 2007.

Note #2  September 2006: An underlying component (AMI, from Grenoble) is behind schedule. New effort from Glasgow has been recruited.

Note #3  September 2006: Delayed pending LCG major POOL collections infrastructure changes.

Note #4  September 2006: The revised LCG schedule calls for delivery of this functionality, along with major POOL collections infrastructure changes, in time for ATLAS Release 13 in January 2007.

2.2.3.6 Distributed Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Set up Savannah portal for DDM operations | 10-Jul-06 | -- | 10-Jul-06 | Completed |
| Submit note on ATLAS DDM operations to ATLAS computing management | 25-Jul-06 | -- | 25-Jul-06 | Completed (See #1) |
| Automate input dataset delivery for production jobs | 25-Aug-06 | -- | 25-Aug-06 | Completed |
| Data integrity checking for Monte Carlo production | 25-Aug-06 | -- | 25-Aug-06 | Completed |
| U.S. ATLAS Data Management and Production Workshop at BNL | 30-Sep-06 | -- | 30-Sep-06 | Completed |
| Data transfer functional test (est. 9 Tier 1s, 50 Tier 2s) | 3-Nov-06 | [New] | 3-Nov-06 | On Schedule |
| Implement ATLAS SW projects table in MC production | 15-Nov-06 | [New] | 15-Nov-06 | On Schedule |
| Data integrity procedure for DDM catalogs | 30-Nov-06 | [New] | 30-Nov-06 | On Schedule |
| Set up MySQL local file catalog at CERN (backup to ATLAS LFC) | 21-Dec-06 | [New] | 21-Dec-06 | On Schedule |

Note #1  ATLAS note ATL-COM-SOFT-2006-008 (approved Aug 2006)

2.2.3.7 Data Access Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Provide database expertise via U.S. ATLAS Analysis Support Group | 2-Jul-07 | -- | 2-Jul-07 | On Schedule |

2.2.4 Distributed Software

2.2.4.1 Distributed Analysis

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support for long user jobs via long queues | 15-Jul-06 | [New] | 15-Jul-06 | Completed |
| Support event collection analysis with pathena | 20-Jul-06 | [New] | 20-Jul-06 | Completed |
| PanDA analysis in support of Physics Analysis Jamboree | 20-Aug-06 | 5-Jun-06 | 20-Aug-06 | Completed |
| Multitasking pilot deployment for analysis | 31-Aug-06 | [New] | 31-Mar-07 | Delayed (See #1) |
| Initiate extension of scheduler/pilot operation to LCG for pathena | 10-Sep-06 | [New] | 10-Sep-06 | Completed |

Note #1  Multitasking pilot itself was deployed in production, but the analysis multitasking feature itself remains under test and is not yet activated for general use.

Torre Wenaus (Brookhaven National Laboratory)

PanDA based distributed analysis tools were routinely available and in use during the quarter. Stable analysis pilot delivery was achieved following the improvements of the previous quarter. About 20 users have made use of pathena for PanDA based analysis during the last month; a similar number have run over 100 jobs with the system, and 7 have used it for more than 1000 jobs. The system was used in another Physics Jamboree at BNL in August, and a tutorial on PanDA for analysis was given at the ATLAS software week in September.

The multi-tasking pilot supporting concurrent running of production and analysis jobs from one pilot was deployed in production during the quarter, but its concurrent analysis job feature remained under test and not yet activated for general use. Capability was extended to support event collection analysis and long jobs. Work began to extend PanDA deployment for analysis to the LCG, based on a new scheduler/pilot system designed for broad deployment (see discussion of TestPilot in PanDA section 2.2.4.2).

2.2.4.2 Production System

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Achieve <10% production error rate due to PanDA | 31-Jan-06 | -- | 31-Jan-06 | Completed |
| PanDA migration to ATLAS production DQ2 | 10-Feb-06 | -- | 10-Feb-06 | Completed |
| PanDA production scalability test | 20-Feb-06 | -- | 20-Feb-06 | Completed |
| Active disk space management | 28-Feb-06 | -- | 28-Feb-06 | Completed |
| PanDA deployment at Indiana U | 15-Mar-06 | -- | 15-Mar-06 | Completed |
| Brokerage based on dynamic site resource information | 10-Apr-06 | -- | 10-Apr-06 | Completed |
| Site usage monitoring and reporting to OSG | 15-Apr-06 | -- | 15-Apr-06 | Completed |
| Teraport site integrated | 15-Apr-06 | -- | 15-Apr-06 | Completed |
| CERN instance of PanDA server deployed | 15-May-06 | -- | 15-May-06 | Completed |
| PanDA monitor extended to multi-instance, multi-site deployment | 20-May-06 | -- | 20-May-06 | Completed |
| User quota system integrated | 10-Jun-06 | -- | 10-Jun-06 | Completed |
| New DQ2 major release integrated | 15-Jun-06 | -- | 15-Jun-06 | Completed |
| Support grid data access from pilot jobs based on uberftp | 15-Jun-06 | -- | 15-Jun-06 | Completed |
| SLAC site integrated | 20-Jun-06 | -- | 20-Jun-06 | Completed |
| Support direct posix access to SE-resident data from PanDA jobs | 15-Jul-06 | [New] | 15-Jul-06 | Completed |
| Deploy grid data access from pilot jobs, for opportunistic site support | 31-Jul-06 | [New] | 31-Jul-06 | Completed |
| User quota system deployed | 31-Aug-06 | [New] | 31-Aug-06 | Completed |
| Define initial program in generic PanDA (OSG extensions) | 10-Sep-06 | [New] | 10-Sep-06 | Completed |
| Define initial program in PanDA/Condor OSG collaboration (OSG extensions) | 10-Sep-06 | [New] | 10-Sep-06 | Completed |
| Establish BNL Condor testbed for PanDA/Condor program | 30-Sep-06 | [New] | 30-Sep-06 | Completed |

2.2.4.3 Production Support

Torre Wenaus (Brookhaven National Laboratory)

Production support continued to be an integral part of the production system, distributed analysis and distributed data management efforts, with all participants in those programs contributing to production support. During the quarter Alexei Klimentov took on the new role of US ATLAS DDM Operations Coordinator, responsible for overall coordination of DDM activities in US ATLAS. Alexei is the ATLAS DDM Operations Coordinator, so our operations are well integrated with ATLAS. No specific production support milestones were called out in this quarter, it is an ongoing activity.

U.S. ATLAS continued to make major contributions to production support at the ATLAS level in both distributed data management operations and in production task definition.

2.2.5 Application Software

2.2.5.1 Generator Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Customized persistency for HepMC | 5-Jul-06 | -- | 5-Jul-06 | Completed |
| First version of enforced consistency of masses among all generators | 5-Jul-06 | -- | 5-Jul-06 | Completed |
| Herwig++ available and integrated | 5-Jul-06 | -- | 5-Jul-06 | Completed |
| Validated version of EvtGen interface for inclusive decays with Pythia and Herwig | 5-Jul-06 | -- | 5-Jul-06 | Completed |
| Sherpa in production. | 1-Dec-06 | [New] | 1-Dec-06 | On Schedule |
| Evaluation of Herwig++ for inclusion in release 13. | 10-Jan-07 | [New] | 10-Jan-07 | On Schedule |
| Evaluation of full migration of sherpa into releases (no external files). | 15-Jan-07 | [New] | 15-Jan-07 | On Schedule |
| Evaluation of Pythia 8 for inclusion in release 14. | 1-Jun-07 | [New] | 1-Jun-07 | On Schedule |
| Complete validation of all packages to be used for first data. | 1-Aug-07 | [New] | 1-Aug-07 | On Schedule |

Frederic Luehring (Indiana University)

An important bugfix was introduced into the ATLAS interface to Pythia. The Pythia bug was affecting the generation of the underlying event. Assistance was provided to other Generator package developers which resulted in the release of a new Generator interface for Matchig. The ATLAS interfaces of Sherpa were updated to the latest version (1.0.8). This version migration was needed for the ATLAS CSC event generation production. Assistance was provided to the Winhac developers during a very detailed validation process of the ATLAS-Winhac interface. Extensive interactions with the ATLAS user community took place, supporting them on their physics analysis tasks.

2.2.5.2 Tracking Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Understand existing b-tagging software. | 1-Aug-06 | 1-Oct-06 | 1-Dec-06 | Delayed (See #1) |
| Modify CBNT for increased functionality in monitoring b-tagging | 15-Oct-06 | [New] | 15-Oct-06 | On Schedule |
| Port modifications of CBNT to Athena Aware Ntuple. | 1-Dec-06 | [New] | 1-Dec-06 | On Schedule |
| Optimize b-tagging algorithm for release 13.0.0 | 26-Jan-07 | [New] | 26-Jan-07 | On Schedule |

Note #1  Best's replacement (Jain) has started on August 1 but will take some time to learn the b-tagging code.

Frederic Luehring (Indiana University)

V. Jain began working on 01-Aug-06. Jain as a replacement for D. Best. Jain will continue to work on b-tagging but in the context of the Event Filter using wrapped versions of the normal tracking code. Jain spent his time learning to use the new Tracking code within Athena and learning how the event filter is working. Jain will work on using Athena Aware n-tuples to study and optimize the b-tagging algorithms.

2.2.5.3 Calorimeter Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| clean-up of CaloCluster class & new fast CaloTower implementation | 11-Apr-06 | 31-Oct-06 | 27-Jan-07 | Delayed (See #1) |
| move hadronic calibration parameters into database | 3-May-06 | 31-Oct-06 | 27-Jan-07 | Delayed (See #2) |
| improvement of Navigation package wrt performance and storage requirements | 5-Jul-06 | 31-Oct-06 | 27-Jan-07 | Delayed (See #3) |
| investigate data compression for CaloCluster | 5-Jul-06 | 31-Oct-06 | 27-Jan-07 | Delayed (See #4) |
| fast CaloTower implementation | 1-Aug-06 | 31-Oct-06 | 27-Jan-07 | Delayed (See #5) |
| implementation of new EDM for navigable four-momentum typed objects | 31-Oct-06 | -- | 31-Oct-06 | On Schedule |
| testbeam converter support | 31-Oct-06 | 31-Oct-06 | 27-Jan-07 | Delayed (See #6) |
| use of conditioning data in reconstruction and simulations, esp. validation of "realistic" calo. | 6-Dec-06 | 6-Dec-06 | 25-Jun-07 | Delayed (See #7) |
| optimizations for commissioning/ATLAS data | 1-Jan-07 | -- | 1-Jan-07 | On Schedule (See #8) |
| conversion/transport of mySQL etc. conditions database to COOL. | 27-Jan-07 | [New] | 27-Jan-07 | On Schedule (See #9) |
| improve CaloCluster features to provide uncalibrated and calibrated signals for hadronic clusters | 27-Jan-07 | [New] | 27-Jan-07 | On Schedule (See #10) |
| transient/persistent object separation for CaloCluster done | 27-Jan-07 | [New] | 27-Jan-07 | On Schedule (See #11) |

Note #1  Delayed to release 13.0.0. framework problems

Note #2  postponed after first implementation ideas circulated - will be picked up again mid-October 2006. Expected for 13.0.0.

Note #3  Release 13.0.0 is delayed to 27-Jan-07, ongoing,10% done

Note #4  Release 13.0.0 is delayed and so is this milestone, started in context of new navigation implementation, 75% done.

Note #5  100% done, final test postponed due to framework pbs, now expected for 13.0.0

Note #6  Release 13.0.0 is delayed, ongoing, 95% done

Note #7  Release 14 is delayed to June 2007 starting, 25% done

Note #8  discussions only at this time, no demand

Note #9  100% done, software tested and ready to go, actual conversion is on demand from testbeam analysis: presently providing "on demand conversion service" for calorimeter testbeam communities

Note #10  New activity, 90% done.

Note #11  new activity, working prototype viable, awaiting final approval from calorimeter group, 90% done.

Frederic Luehring (Indiana University)

W. Lampl presently provides services for filling the COOL database with reconstruction parameter updates and conditions data for the calorimeter test-beams. The main activities here still are the FCal2004, and the H6 and H8 combined test-beam runs (2005). The versioning of the hadronic calibration constants using this database technology is also still ongoing, in close collaboration with MPI. He has also continued his work on calorimeter EDM improvements, in collaboration with P. Loch, and he is now contributing to the development of the object navigation code in the Athena data model, here again in collaboration with Loch and S. Binet (LBNL). As usual he still maintains his role as the principal consultant regarding electron/photon reconstruction for ATLAS, and he deals with demands from general ATLAS requiring his expertise in this subject as well.

2.2.5.4 Muon Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Implement and Test new EDM for Muon reconstruction for 13.0.0 | 12-Jul-06 | 26-Sep-06 | 26-Jan-07 | Delayed (See #1) |
| Implement and Test Truth EDM for 13.0.0 | 12-Jul-06 | 31-Oct-06 | 26-Jan-07 | Delayed (See #2) |
| Improve documentation of EDM packages | 31-Jul-06 | -- | 31-Jul-06 | Completed |
| Finalize EDM design, and work on transient / persistent separation for 13.0.0 | 26-Sep-06 | 31-Oct-06 | 26-Jan-07 | Delayed (See #3) |
| Integration of new muon reconstruction packages for 13.0.0 | 26-Sep-06 | 31-Oct-06 | 26-Jan-07 | Delayed (See #4) |

Note #1-2  This item is delayed because release 13.0.0 is delayed until the end of January 2007.

Note #3-4  Release 13.0.0 has been delayed to January 26, 2007.

Frederic Luehring (Indiana University)

For the period of July-September, Moyse has been working on more issues with the performance of our persistency technology, and has been involved in discussions about ways to improve this both within and outside the EMB. He has also been trying to fix remaining bugs for the 12.0.x releases, in particular with regards to the EDM/Geometry and Truth. Moyse has also introduced the Muon Reconstruction runtime package, to enable the Muon community greater control over Muon reconstruction (previously it was being managed centrally).

2.2.5.5 Monitoring Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Gatherer in tdaq-01-06 | 31-Jul-06 | [New] | 31-Jul-06 | Completed |
| DQMF Design Document | 31-Aug-06 | [New] | 31-Aug-06 | Completed |
| working tdaq-01-06 installation for LAr | 30-Sep-06 | [New] | 30-Sep-06 | Completed |

Frederic Luehring (Indiana University)

The SMU Monitoring Software effort has progressed in three components during the July-September period. The upgrade of the Gatherer for the tdaq-01-06 release was completed by Haleh Hadavand. Initial work to make further improvements for the upcoming tdaq-01-06 release was begun by Peter Renkel and Hadavand. Substantial efforts to integrate the TDAQ software into the LAr monitoring effort were pursued, resulting in successful use with several new tools, and also for early cosmics data. A revamped online shifter panel was designed and implemented by two SMU students under the guidance of Hadavand. The online monitoring setup for LAr was also rationalized and committed to CVS. Lastly, the design document for the Data Quality Monitoring Framework was finalized and submitted to the Monitoring Working group and Data Quality coordinator for review. Some implementations and design elements concerning algorithms have been begun.

2.2.6 Infrastructure Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Install and support ATLAS releases and associated external software at BNL | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |
| Support ATLAS software nightly builds at BNL and CERN | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

2.2.6.2 Librarian

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Install and support ATLAS releases and associated external software at BNL | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |
| Setup builds of the nightly releases distribution kits | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |
| Support ATLAS software nightly builds at BNL and CERN | 31-Dec-06 | -- | 31-Dec-06 | On Schedule |

Alexander Undrus (Brookhaven National Laboratory)

In this quarter the experimental ATLAS nightly builds were started on SLC4 32 and 64-bit platforms at CERN. In these nightly jobs the distcc program distributed the release compilation task to the cluster of computers. As a result the release compilation time was reduced by about factor of 3. For the standard SLC3 platform four branches of the nightlies were run (bugfix, development, experimental, and for trigger studies). The experimental distribution kit builds were created for the bugfix nightlies. These kits were further downloaded by the pacman tool and verified by the Kit Validation test suite. As a result the full chain of ATLAS software distribution undergoes tests in the nightly builds framework. Many improvements were made to NICOS, ATLAS nightly release tool, such as automatic removal of excessive static libraries from the releases, automatic notifications in cases when AFS nightly volumes are filled close to the capacity, better web pages design. The number of nightly integration tests performed in the ATN testing framework reached 97 (30% more as compared with the previous quarter). The scripts allowing to run an ATN test in users local areas were added to ATN. At BNL new stable ATLAS software and DB releases were promptly installed, usually in one to two days after CERN installation. As well as the following mirrors were available at BNL: ATLAS CVS code repository, ATLAS pacman code distribution cache, ATLAS nightly builds for the development and bugfix branches. The LXR server, alxr.U.S. ATLAS.bnl.gov, provided the collaboration-wide service for the fast searches in ATLAS software codes. The indexes for the latest stable releases were made available.

2.2.7 Analysis Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Signing of Analysis Support Center MOU | 1-Apr-06 | -- | 1-Apr-06 | Completed |
| Full operation of Analysis Forums | 1-Sep-06 | -- | 1-Feb-07 | Delayed (See #1) |
| First analysis jamboree at each ASC | 1-Oct-06 | -- | 1-Oct-06 | On Schedule |
| Follow-up with analysis jamboree participants | 1-Oct-06 | -- | 1-Oct-06 | On Schedule |
| US ATLAS Analysis Support HyperNews in working order | 31-Dec-06 | [New] | 31-Dec-06 | On Schedule |
| CSC Notes Jamborees | 31-Jan-07 | [New] | 31-Jan-07 | On Schedule (See #2) |

Note #1  Physics Analysis Forums awaiting dedicated CSC Notes Jamborees planned for Dec 2006 and Jan 2007 at BNL and ANL, respectively.

Note #2  Analysis jamborees focused on the physics analysis CSC notes will take place in Dec 06 and Jan 07 to stimulate analysis activities.

Stephane Willocq (University of Massachusetts)

During the period July to Sep 2006, the main analysis support activities were the Analysis Jamborees held at BNL in August and at ANL in September. US ATLAS physicists participated in a series of software tutorials on physics analysis tools and trigger-based analysis. Participants had the opportunity to work in subgroups organized according to physics analysis and/or detector performance interests. Feedback from the participants was excellent.

## 2.3 Facilities

2.3 Subsystem Manager's Summary

Razvan Popescu (Brookhaven National Laboratory)

Tier1 and Tier2 Facilities:

The Tier1 staff grew by 3 engineers, expected to work on dCache, grid services development and system monitoring. 20TB of high performance, high reliability, disk storage system had been released to operations in support of mission critical filesystem; the capacity upgrade of the main computing farm is complete, bringing the installed capacity to 1400 job slots and 525TB of distributed storage. WAN/OPN private L2 circuits are operational and had demonstrated production level services during the SC exercises (200MB/sec sustained incoming traffic from T0).

The Midwest T2 completed the upgrade of the site, reaching an installed capacity of 154k SI2K and 65 TB dCache distributed storage. DQ2 packaging and installation scripts were delivered for use on all T2 installations. The 10G service to Starlight is operational. The staff continued the support efforts for PanDA productions and DQ2 operations, while continuing final preparations for deployment of the two new MWT2 clusters at IU and UC.

The Northeast Tier 2 center has been in production operation for the past quarter, the work done has been dominated by PanDA production. International ATLAS users have also used the facility, at a lower priority level. The staff worked with the ATLAS SIT team in expanding the system of software distribution mirrors to the UM Tier 2 site in the US and the RAL Tier 1 site in the UK. NE T2 had participated in ATLAS coordinated DDM tests transferring data between T1<->T2.

The new UTA SWT2 cluster began running production jobs on July 6th. The long delay was due to infrastructure problems (power supply) and hardware problems (IBRIX file system). Currently, there are 3 clusters participating in managed CSC production: the old DPCC shared cluster with 100 CPUs, the OU_SWT2 cluster with 84 CPUs and the new UTA_SWT2 cluster providing 304 CPUs. A total of 40TB of storage is available, over the three installations. The DPCC cluster has also been made available for analysis jobs.

The ATLAS Great Lakes Tier2 (AGLT2) has joined US ATLAS as a Tier2 starting September 1, 2006. Michigan State has been focusing on required renovations to their server room. Current bids are in hand for installing 28 ton A/C capacity which would accommodate about 14 racks of equipment.

The University of Michigan has been focused on providing access to 59 dual processor Opteron nodes as our first 6 month Tier2 contribution. The DQ2 server has been installed on a 64 bit server, which is the first time this platform has been used for a production server. Michigan has spent a significant amount of time debugging PanDA related issue for our configuration. The AGLT2 should have 118 jobs slots validated and ready for use by US ATLAS sometime in October.

The Western T2 at SLAC joined U.S. ATLAS in September 2006. The installation of the first Tier-2 hardware at SLAC awaits major electrical work that is planned for early December 2006. SLAC is already offering batch services to ATLAS via OSG, using hardware whose primary role is to serve BaBar. The ATLAS usage in September was around 250 CPU hours per day. Over 2.5TB of dedicated ATLAS storage has been set up, using storage that will eventually be returned to BaBar when storage purchased with Tier-2 funds is installed.

Networking:

The LHC-OPN (T0-T1 Networking) met in Utrecht, Netherlands on September 22, 2006 to continue its work. During this meeting the working groups were reorganized. The Monitoring group (led by S. McKee, U.S. ATLAS) was deemed to have completed its work and a new group, led by Joe Metzger from ESNet, on "network instrumentation" has been established. This new working group will look at the next level of tools and installations required for the production networking environment.

The relevant network research projects have all progressed. Terapaths has deployed network management software at BNL and Michigan and is expanding into production with $30K/year per Tier2 (excluding SLAC) for the next two years. UltraLight is preparing new kernels and data transport applications focused on developing high-performance use of 10+ Gbit/sec networks. It is also continuing to develop a software stack for broader deployment based upon agents and VINCI services. OSCARS has been working closely with Terapaths, USNet, DRAGON, CHEETAH and others on interoperability.

The Grid Tools and Services effort focused on:

a) Programming for U.S. ATLAS PanDA executor

- Development of the JobScheduler in collaboration with Xin Zhao

- Development of a module to provide reliable and robust file movement from the execution directories to the local SE and file registration in the DQ2 server (DQ2ProdClient2.py)

- Packaging of the PanDA packages

b) Troubleshooting and support of U.S. ATLAS production activity

- DQ2 operation (cleanup, troubleshooting)

- Condor upgrade to 6.7.20 through ROCKS

c) U.S. ATLAS Tier2 Data Service activity (this activity involves a joint group from U.S. ATLAS Midwest Tier2 and Argonne National Lab). The goals of the activity are the design, prototyping and packaging of a service that could be deployed at ATLAS Tier2s and would include the following functionalities:

- Provide users the ability to access the Tier2's DQ2 server.

- Host or provide access to ATLAS specific database services, such as TAG and possibly conditions (IOV and calibration) databases.

- Provide a skimming service for Tier2-resident datasets through either command line or web interfaces.

d) Activity within the ATLAS worldwide collaboration

- Involvement in the ATLAS ProdSys protocol maintenance

- Involvement in the effort to define common ATLAS error codes returned by the production system

- Participation in the ATLAS monitoring effort (FZK-CERN).

e) Grid activities (OSG and Interoperability efforts)

- Participation in the Glue Schema v1.2 and v1.3 effort:

- Experiments to integrate PanDA with ReSS resource selection

- Participation in the OSG monitoring and information system activity

- Participation in the CE storage activity within OSG to provide guidance on how to use disk space from within the CE environment.

Grid Production:

We continued CSC production during this quarter. The primary focus was validation of Release 12 -- U.S. ATLAS continued to produce around 25% of the total MC data produced in ATLAS, validating releases 12.0.0, 12.0.1 and 12.0.2.

2.3.1 Tier 1 Facilities

2.3.1.1 Management/Administration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Expand U.S. ATLAS Tier1 Engineering Staff | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #1) |

Note #1  3 engineers have been added to the Tier1 staff to work on dCache, grid services development, web development and service maintenance.

2.3.1.3 Tier 1 Linux Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin CPU/dCache Disk Expansion Installation | 15-May-06 | -- | 1-Aug-06 | Completed |
| Central Disk Expansion Operational | 30-Jun-06 | -- | 30-Aug-06 | Completed (See #1) |
| CPU/dCache Disk Expansion Operational | 30-Jun-06 | -- | 31-Aug-06 | Completed |

Note #1  The new disk storage system had been integrated and supports the critical filesystems -- applications, workspace and home directories.

2.3.1.4 Tier 1 Storage Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Central Disk Expansion Installation | 15-May-06 | -- | 10-Aug-06 | Completed |

2.3.1.5 Tier 1 Wide Area Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SC4 Set-up Complete and Basic Service Demonstrated | 30-Apr-06 | -- | 30-Jul-06 | Completed |
| 20Gb/sec WAN -- OPN and regular circuits operational | 30-Aug-06 | -- | 30-Aug-06 | Completed |

2.3.1.6 Tier 1 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| 1125CPU,525Disk,200WAN=>Disk,300Tape,200WFAN=>Tape | 30-Jun-06 | -- | 30-Aug-06 | Completed |

2.3.2 Tier 2 Facilities

2.3.2.1 University of Chicago/Indiana

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| DQ2 packaging and installation scipts | 1-Jul-06 | [New] | 1-Sep-06 | Completed (See #1) |
| Deployment of 10G Cisco router and cluster switch at IU | 1-Aug-06 | [New] | 15-Sep-06 | Completed (See #2) |
| Final preparations of machine rooms | 1-Sep-06 | [New] | 1-Sep-06 | Completed (See #3) |
| Final procurement of MWT2 clusters, Phase I | 1-Sep-06 | [New] | 5-Oct-06 | Delayed (See #4) |

Note #1  Delivery of DQ2 packaging and installation scripts for MWT2 facilities (5 instances). Uses liberal ToA file for access to datasets on LCG sites as well as BNL Tier1.

Note #2  Cisco 6509 providing 10G service to UC campus border router, then to Starlight.

Note #3  Delivery of power receptacles and local network infrastructure at both UC and IU machine rooms.

Note #4  Installation of Phase I clusters at UC and IU.

Equipment: Phase I (operational)

CPU: 154k SI2K; Disk: 65 TB dCache

Edge servers for dCache, DQ2, OSG, /home, mgt

Misc items for networking and power

Rob Gardner (University of Chicago)

General theme of this reporting period was the continued support load for PanDA productions and DQ2 operations, while final preparations for deployment of the two new MWT2 clusters at IU and UC.

2.3.2.2 Boston University/ Harvard

Saul Youssef (Boston University)

The Northeast Tier 2 center (http://atlas000.bu.edu/NETier2/wiki/index.php/Main_Page) has been in production operation for the past quarter. Although we now have 27 ATLAS collaborators with local accounts and the ability to submit batch jobs, the work done has been dominated by PanDA production managed by the production team. International ATLAS users have also used our facility through usatlas3 at a low level - typically 1 batch job with a peak of 20. Short interruptions in availability have occurred for one PBS problem and an expired host certificate. We have worked with the ATLAS SIT team in expanding the system of software distribution mirrors to the UM Tier 2 site in the US and the RAL Tier 1 site in the UK. We have participated in ATLAS coordinated DDM tests transferring data from T1<->T2. A problem was revealed transferring large (>2G) files which is probably related to our DRM installation. We have worked with the production team in re-organizing how the ATLAS releases are distributed for PanDA production.

2.3.2.3 Southwest

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| UTA SWT2 Cluster running CSC production | 15-Jun-06 | -- | 7-Jul-06 | Completed |
| Reconfiguration of SWT2 Queues to balance managed production and distributed analysis users | 15-Jul-06 | -- | 15-Jul-06 | Completed |

Kaushik De (University of Texas at Arlington)

The new UTA SWT2 cluster finally began running production jobs on July 6th. The long delay is due to infrastructure problems (power supply) and hardware problems (IBRIX file system). The IBRIX problems are continuing, limiting our ability to make full use of the cluster. We are discussing the situation with Dell and IBRIX support. We expect a patch soon.

Currently, we have 3 clusters participating in managed CSC production. The old DPCC shared cluster has 100 CPU's. The OU_SWT2 cluster has 84 CPU's. And the new UTA_SWT2 cluster is providing 304 CPU's (holding a few in reserve for testing). DPCC has 20TB available to ATLAS (out of 45TB). OU has 4TB, while UTA_SWT2 has 16 TB available.

The DPCC cluster is also available for analysis jobs. We are waiting for DQ2 to become more stable before we increase DA activity - since not all AOD files are available yet.

We have started soliciting vendor quotes for our next purchase. This will add 100 TB of disk space, plus some CPU's. This cluster will primarily be used for user analysis support.

We continue to hold bi-weekly video meetings of the Southwest Tier 2 analysis group. A new SUSY analysis sub-group has also started holding weekly phone meetings.

2.3.2.4 Tier 2 Facility - University of Michigan

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Provide 118 PBS job slots | 1-Oct-06 | [New] | 23-Oct-06 | Delayed (See #1) |

Note #1  Problems with PanDA specific requirements and SLC4 x86_64 DQ2 have slowed our progress.

Shawn McKee (University of Michigan)

The ATLAS Great Lakes Tier2 (AGLT2) has just joined US ATLAS as a Tier2 starting September 1, 2006. This is our first quarterly report and includes details from both the Michigan and Michigan State sites.

Both Michigan and Michigan State sent representatives (Bob Ball, Chip Brock, Shawn McKee, Tom Rockwell) to the August 18th Tier-2 meeting at Harvard.

Michigan State has been focusing on required renovations to their server room. Current bids are in hand for installing 28 ton capacity which would accommodate 14 racks of hardware at 8kW per rack or less. The Department of Physics and Astronomy has agreed to take over one of two possible additional rooms adjacent to the current server room in order to provide expansion capabilities. This has opened up possibilities within the College of Natural Science and a second bid is in hand for a possible staged installation of 50 tons of cooling to add flexibility for continued T2/T3 growth as well as anticipated College needs. A spring completion is still anticipated and additional temporary space has been made available in the central campus HPC area for one more HEP rack of computing, for a total of two which will allow MSU to continue to move toward provisioning of a few test-bed AGL nodes

The University of Michigan has been focused on providing access to 59 dual processor Opteron nodes as our first 6 month Tier2 contribution. The DQ2 server has been installed on an SLC V4.4 x86_64 bit server (which is the first time this platform has been used for a production server) by Shawn McKee. The gatekeeper has been operational and running OSG V0.4.1 since the second week in September. We have edited the OSG monitoring tools to provide a correct view for resources from our site.

Michigan has spent a significant amount of time debugging PanDA related issue for our configuration. There seem to be many undocumented requirements beyond having a working OSG install that we have to deal with to create a fully operational PanDA-compatible site.

The AGLT2 should have 118 jobs slots validated and ready for use by US ATLAS sometime in October.

Michigan's permanent Tier-2 space will be ready for occupancy by November and we are planning the migration details.

Both Michigan and Michigan State sent representatives (Shawn McKee, Tom Rockwell) to the DDM workshop which was held at BNL on September 26 and 27, 2006.

2.3.2.5 Tier 2 Facility - SLAC

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SLAC 1st Phase Hardware in service | 15-Dec-06 | [New] | 15-Dec-06 | On Schedule |

Richard Mount (Stanford Linear Accelerator Center)

The installation of the first Tier-2 hardware at SLAC awaits major electrical work that is planned for early December 2006.

SLAC is already offering batch services to ATLAS via OSG, using hardware whose primary role is to serve BaBar. The ATLAS usage in September was around 250 CPU hours per day. Over 2.5TB of dedicated ATLAS storage has been set up, using storage that will eventually be returned to BaBar when storage purchased with Tier-2 funds is installed.

2.3.3 Wide Area Network

Shawn McKee (University of Michigan)

The LHC-OPN (T0-T1 Networking) met in Utrecht, Netherlands on September 22, 2006 to continue its work. During this meeting the working groups were reorganized. The Monitoring group (led by S. McKee, U.S. ATLAS) was deemed to have completed its work and a new group, led by Joe Metzger from ESNet, on "network instrumentation" has been established. This new working group will look at the next level of tools and installations required for the production networking environment.

At the Tier-2 meeting in Boston on August 18, 2006, the set of network related items were reviewed briefly and updated. Details are available at: http://www.usatlas.bnl.gov/twiki/bin/view/Admins/Tier2Workshop17Aug06 and http://www.usatlas.bnl.gov/twiki/bin/view/Admins/TierTwoNetworking. Some highlights include plans to produce and maintain network diagrams for each Tier-2, the setup and operation of dedicated NDT servers and longer term planning to deploy end-host agents to monitor and optimize network performance for end-hosts.

The relevant network research projects have all progressed. Terapaths has deployed network management software at BNL and Michigan and is expanding into production with $30K/year per Tier2 (excluding SLAC) for the next two years. UltraLight is preparing new kernels and data transport applications focused on developing high-performance use of 10+ Gbit/sec networks. It is also continuing to develop a software stack for broader deployment based upon agents and VINCI services. OSCARS has been working closely with Terapaths, USNet, DRAGON, CHEETAH and others on interoperability. A meeting to discuss this and US LHCnet is planned for sometime in October at FNAL.

Status of the NSF PIF (PLaNetS) and DOE SCiDAC (LHC-MI) proposals are still pending.

2.3.4 Grid Tools & Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Development of components for ATLAS production system (scheduler, broker) (Chicago) | 1-Oct-05 | 1-Oct-05 | 1-Oct-06 | Delayed (See #1) |
| Integration with distributed data management services and infrastructure (Chicago) | 1-Nov-05 | -- | 31-Jul-06 | Completed |
| Development on as needed basis, components for distributed production and analysis focusing on distributed grid data management (Chicago) | 1-Feb-06 | -- | 31-Jul-06 | Completed |

Note #1  Continued development of components for the scheduler to optimize distribution of pilots to sites.

Rob Gardner (University of Chicago)

This effort report covers the period of activity of Marco Mambelli, University of Chicago, from July 1, through September, 30 2006. The deliverables and milestones achieved are as follows:

* Programming for U.S. ATLAS PanDA executor

o Development of the JobScheduler in collaboration with Xin Zhao PanDAJobScheduler

+ Development of the JobScheduler itself

+ Coordination with Xin that is working on the Pilot development (new package that branched out)

+ Development of a module to provide reliable and robust file movement from the execution directories to the local SE and file registration in the DQ2 server (DQ2ProdClient2.py)

o Packaging of the PanDA packages (PanDAJS, PanDASrv, PanDAJDE, PanDA, auxiliary DQ-Client) together with Horst Severini. Provided the initial version of the packaging scripts and Pacman file templates; continued contributions with Horst in subsequent versions.

o Minor involvement in other PanDA components

* Troubleshooting and support of U.S. ATLAS production activity

o Troubleshooting of different problems involving

+ job submission at gatekeeper

+ file transfer

* MWT2 activity

o Troubleshooting of different problems

+ DQ2 operation (cleanup, troubleshooting)

+ Condor upgrade to 6.7.20 through ROCKS (with Marty)

+ Condor configuration

* The code and the documentation of the former U.S. ATLAS executor Capone is kept available for studies and comparisons:

o Release 1.2 is still the current one

* U.S. ATLAS Tier2 Data Service activity.

o This activity involves a joint group from US-ATLAS Midwest Tier2 (University of Chicago and Indiana University) and Argonne National Lab (Robert Gardner, Dan Schrager, Jack Cranshaw, Tom LeCompte, David Mallon, Sasha Vaniachine)

o Goals of the activity are the design, prototyping and packaging of a service that could be deployed at ATLAS Tier2s and would include the following functionalities:

+ Provide users the ability to access the Tier2's DQ2 server.

+ Host or provide access to ATLAS specific database services, such as TAG and possibly conditions (IOV and calibration) databases.

+ Provide a skimming service for Tier2-resident datasets through either command line or web interfaces.

o Group coordination (chairing meeting, taking minutes)

o Planning, scope definition and initial organization

o Prototype machine initial deployment

+ software installation

+ testing (with Jack Cranshaw)

* Activity within the ATLAS worldwide collaboration

o Involvement in the ATLAS ProdSys protocol maintenance

o Involvement in the effort to define common ATLAS error codes returned by the production system

o Participation in the ATLAS monitoring effort lead by John Kennedy (FZK-CERN).

* Grid activities (OSG and Interoperability efforts)

o Participation in the Glue Schema v1.2 and v1.3 effort:

+ Mapping of GLUE attributes to Condor old-ClassAds, lead by Gabriele Garzoglio (Fermilab)

+ Publishing of SRM-based SEs information

+ Involvement in the GIP (Generic Information Provider) activity within OSG

+ Definition of changes for GLUE 1.3

o Experiments to integrate PanDA with ReSS resource selection

o Participation in the OSG monitoring and information system activity (MIG)

o Participation in the CE storage activity within OSG to provide guidance on how to use disk space from within the CE environment.

+ Coordination of the meetings/discussions.

+ Updating of the Local Storage Requirements document (with comments and contributions from various parties) and of the administration and user documents.

2.3.5 Grid Production

Kaushik De (University of Texas at Arlington)

We continued CSC production during this quarter. The primary focus was validation of Release 12. We also continued to run Release 11 samples requested by physics groups.

U.S. ATLAS continued to produce around 25% of the total MC data produced in ATLAS. Releases 12.0.0, 12.0.1 and 12.0.2 were validated. Hundreds of software bugs were reported based on high volume grid production. Many hundreds of tasks were completed, with each release (and repeated for various transformation cache releases).

The shift team continues daily shifts (6 days/week). Yuri Smirnov is the shift captain. Nurcan Ozturk, Mark Sosebee and Tomasz Wlodek are on the shift team. Xin Zhao continues to maintain ATLAS software installations on the grid. Pavel Nevski is in charge of job definitions (ATLAS-wide).

## 3.1 M&O Silicon

3.1 Subsystem Manager's Summary

Alex Grillo (UCSC)

Pixel end-cap A was fully connected to the prototype service quarter panel in preparation for the 10% system test, however, some problems with cooling fittings were encountered and a sector outlet pipe was damaged. A new pipe connection tool has been designed and it may be necessary to replace the damaged sector. A determination will be made on 16-Oct. There have also been failures of some of the opto paks curing opto board QC at CERN. This problem is still being investigated. A tighter QC procedure has been instituted. It is likely that 20% of opto boards may be rejected by the more rigorous QC. The production of spare opto boards has been delayed pending a better understanding of this failure mechanism. In spite of these delays, the overall Pixel integration program is moving ahead and has gained one month on the schedule that was laid out in July for just-in-time installation next year.

The integrated Inner Detector Barrel (SCT plus TRT) was moved to the ATLAS cavern and installed in the cryostat on 24-Aug. It was moved to it final location (i.e. Z=0) on 28-Sep. Cable testing and installation is proceeding just ahead of “when needed” for each section of barrel and end-caps. Full readout testing of the barrel in-situ should commence sometime in late January once installation is complete, with cosmic ray tests to follow.

Spares ROD parts are ordered. It is expected that they will be delivered by the end of the calendar year. ROD software upgrades are ongoing.

3.1.1 Pixels

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Endcap A was fully connected to the prototype service quarter panel in the 10% system test. However problems were encountered with the threads of the cooling fittings, making it difficult to achieve good gas seals. A sector outlet pipe was damaged during disconnection of a leaky fitting. This has prompted a redesign of the pipe connection tooling. Preparations are underway to disassemble the endcap at CERN and replace the damaged sector, if needed. A determination if it is required will be made after the sector is operated with full power load and cooling, projected for the week of Oct. 16. Other components of the system test, including cosmic trigger and full cable connectivity are in place.

Failures of some optical paks have been seen in opto board QC test at CERN. An investigation to understand these root cause of these problems is ongoing. Nevertheless a more rigorous QC has been developed and opto boards that passed this QC will be loaded starting Oct. 22. The production of spare opto boards has been led back to allow further time to understand the failures. It is likely that 20% of opto boards may be rejected by the more rigorous QC, which means that all the spares will be used in the initial detector.

3.1.1.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start of Pre-Operations of Pixels Inside ID | 15-Mar-07 | -- | 15-Mar-07 | On Schedule |

3.1.1.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Spare Modules and Assemblies (LBNL) | 15-Sep-06 | 15-Sep-06 | 19-Oct-06 | Delayed (See #1) |
| Spare Opto Board Production/Test Complete (OSU) | 30-Sep-06 | 30-Sep-06 | 15-Nov-06 | Delayed (See #2) |

Note #1  Damage to a sector pipe at CERN during system test installation prompted the repair and qualification of sectors held in reserve at LBNL.

Note #2  Failures of optopaks in testing at CERN prompted us to hold the production of spared until further test results

3.1.2 SCT

3.1.2.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Installation of ID Barrel into UX15 (UCSC) | 11-May-06 | 15-Aug-06 | 24-Aug-06 | Completed |
| Complete Initial Test of ID Inside of UX15 (UCSC) | 15-Jul-06 | 15-Dec-06 | 15-Feb-07 | Delayed (See #1) |

Note #1  The ID Barrel was again delayed due to other installation conflicts but has now been positioned inside the cryostat and at its final position. Present installation schedule has installation (i.e. cables, pipes, fibers, etc.) complete mid to late Jan-07. Initial electrical tests should be completed within 4-6 weeks after that.

Alex Grillo (UCSC)

The integrated Inner Detector Barrel (SCT plus TRT) was moved to the ATLAS cavern and installed in the cryostat on 24-Aug. It was moved to it final location (i.e. Z=0) on 28-Sep. Both moves were performed without any known problems. Connection of cables and pipes for the TRT started the next day, 29-Sep, with SCT connections expected to start the first week of November.

Cable testing and installation is still proceeding. The Type-II and Type-III cable installation was completed prior to the September centering of the barrel. Also, the retrofit of PP3 units with extra electrical insulation was completed. Some Type-IV cables are still to be installed. However, all cables and power supplies associated with the barrel will be installed prior to the end of October allowing testing of the full chain with the dummy PP1s prior to connections being made to the SCT barrel.

Continuity tests of barrel connections will be performed as each section is cabled. Full readout testing of the barrel in-situ should commence sometime in late January once installation is complete, with cosmic ray tests to follow.

3.1.2.2 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Cosmic Ray Test with SCT Barrel | 15-Nov-06 | 15-Dec-06 | 15-Apr-07 | Delayed (See #1) |

Note #1  Given the delays in installation reported in the pre-ops section above, cosmic ray testing will not start until Feb-07. It is not clear how much time will be available for such testing but two months is certainly hoped to be a minimum, placing completion at mid-April.

3.1.3 RODs

Abraham Seiden (UCSC)

Spares parts are ordered. It is expected that they will be delivered by the end of the calendar year. Software up grades are on going.

3.1.3.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Spare RODs Completed | 1-May-06 | 1-May-06 | 1-Sep-06 | Completed |

3.1.3.2 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Firmware Upgrades Complete for CERN Requests | 6-Oct-06 | 6-Oct-06 | 6-Jan-07 | Delayed (See #1) |

Note #1  The software update is proceeding and is expected to be complete by January.

## 3.2 M&O TRT

3.2 Subsystem Manager's Summary

Harold Ogren (Indiana University)

This was a milestone laden period for the TRT barrel. In June we finished the SCT - TRT joint testing; In July we completed all final preparation tests on the HV, active gas, cooling, electronic readout, and DAQ; On August 24 the Inner Detector (TRT and SCT) was lowered into the ATLAS experiment and inserted into the central cryostat; On September 25 the cabling and piping outside the detector was completed and the ID was positioned at the center of the cryostat ready for connection to services and cabling of the  front face electronics. This will be completed in the month of  October.

3.2.1 TRT-Subsystem

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| SCT-TRT Joint Test Complete | 10-May-06 | -- | 19-Jun-06 | Completed |
| Barrel and SCT Install in ATLAS | 11-May-06 | -- | 9-Sep-06 | Completed |
| TRT Complete, EC-C Installed | 6-Jul-06 | 5-Dec-06 | 5-Feb-07 | Delayed (See #1) |
| EC-C Complete, EC-A Installed | 5-Aug-06 | 1-Jan-07 | 1-Apr-07 | Delayed (See #2) |

Note #1-2  schedule has shifted for endcap

3.2.1.1 TRT Pre-Operations

3.2.1.1.8 ID Integration

Rick Van Berg (University of Pennsylvania)

During the July-Sept. period the Barrel TRT was readied for installation and actually lowered into the pit and fixed in final position inside the cryostat. Electronics cabling and testing is scheduled to start in early Oct. after final connection and testing of the fluid services. Ben LeGeyt was central in planning the in-pit installation and testing program. He will lead the actual installation effort, aided by Godwin Mayers, Mike Reilly, and Rick Van Berg.

Integration tests of the Barrel will be completed using specialized test software with results written to the test data base. The main DAQ system is independent and that code is being tested against the new back end electronics (TTC, ROD, and Patch Panels) by Paul Keener and Mike Hance. All new drivers for the new hardware have been developed and are now fully compatible with the main ATLAS acquisition model. By mid Oct. we hope to have at least a few 32'nds of the installed Barrel under continuous power and DAQ control as a DAQ development setup and, as more backend electronics become available, as a full system test exercise in preparation for commissioning and alignment.

Both the end caps (A & C) are now complete in an electronics sense except for a few HV lines on EC-A. All electronics have been tested and verified by Ole Rohne and Franck Martin. The SCT endcap C was integrated with the TRT endcap in mid Sept, the A side endcaps should be integrated with each other in early Oct. EC - C has been moved to the test area in SR and preparations are underway for doing combined tests - including cosmic rays - to verify both systems. Two minor repairs are still needed on EC - A electronics. Godwin Mayers should complete those in mid Oct.

Harold Ogren (Indiana University)

During this period our activities focused on the cooling services.

Ogren was at CERN from May 15 until August 12. He assisted Kirill Egorov with the design, prototype tests, procurement of parts, and assembly of the cooling system test racks.

Egorov was in charge of the cooling system testing for the TRT. He designed a monometer test panel that is permanently attached to each of the four cooling rack stations near the experiment. They will allow us to monitor the leak rates of the 32 input-output lines for the Fluorinert cooling system of the TRT.

Egorov also was the principle technical contact for the TRT. He was responsible for finding a repairing any gas or cooling leaks on the manifolds during the testing phase prior to moving the ID. He also assisted in the HV tests and electrical test procedures. A postdoctoral physicist from Indiana University, Siva Subramania, also helped during this period with the computer monitor.

## 3.3 M&O Liquid Argon

3.3 Subsystem Manager's Summary

Ryszard Stroynowski (Southern Methodist University)

During the summer, the barrel calorimeter was tested for shorts. About 30 shorts showed up after the cool-down. A burn-out of shorts has been attempted by a discharge of large capacitors at the entrance to the cathode readout. This is a cumbersome procedure requiring demounting of the front-end readout and isolation of the supply voltage in the HV feedthrough. The burnout attempts have been successful for some of the problems in the presampler (front part of the calorimeter) but made no difference for the remaining three sectors. Since many of the shorts appeared at the bottom of the calorimeter, it was hypothesized that these are due to dirt particles that floated in during Argon filling. To test this, the cryostat was emptied and then refilled by condensation only. This process cleared some of the shorts but not all of them. A campaign to burn out the presampler shorts is planned for after the magnet tests.

The commissioning of the readout electronics is slow, mostly due to limited access and due to continuing problems with low voltage power supplies. The electronics commissioning for the barrel is coming to the end. About 15% of the boards required replacement of the components. The commissioning of the endcap electronics progresses well but is limited by the lack of the low voltage power supplies. Since there are just few of them, for each crate the power supply has to be mounted and connected and then moved to a different location. Most of the effort is shifting to the commissioning of the system of crates, its interaction with the back-end electronics and trigger.

The status of the low voltage power supplies became critical. MDI is continuing to retrofit the produced modules at the rate of about 2 per week, i.e., much slower than the promised 4/week. Unfortunately, the lifetime of the retrofitted units appears to be rather short. Several failed after the time of operations ranging from few days to few months.

The failure analyses provided by the company are generated with much reluctance and delay and at this time we still do not know whether the problems are related to the quality of workmanship or are due to some unidentified design flaw. BNL created a dedicated task force charged with identifying root causes of the failures with the report date in December. At the same time, the BNL engineers are completing specifications for an engineering study of a back-up solution. The discussions with Wiener has been initiated and the contract for such study and a prototype is expected to be placed in November/December.

The progress on the commissioning of the cryostat, Level1 receiver and of the Forward Calorimeter is described in the individual contributions below.

3.3.1 Mechanical Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Endcap (A+C) cold test in the pit | 15-Jun-06 | -- | 15-Sep-06 | Completed |

3.3.1.2 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commissioning of EndcapC in the Pit Complete | 1-Feb-06 | 1-Sep-06 | 1-Apr-07 | Delayed (See #1) |
| Re-commissioning Underground Complete | 1-Mar-06 | -- | 1-Nov-06 | Delayed (See #2) |
| Commissioning of Endcap A in the Pit Complete | 1-Aug-06 | -- | 1-Nov-06 | Delayed (See #3) |

Note #1  Schedule change put higher priority on cryogenics for toroid and solenoid than for the endcaps.

Note #2  Awaits endcap A connections

Note #3  has not started yet

3.3.1.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Barrel HV Operations (SB) | 1-Feb-06 | -- | 1-Jul-06 | Completed |

3.3.2 Electronic Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Commissioning of EndcapC Optical Links (SMU) | 1-Mar-06 | 1-Oct-06 | 1-Dec-06 | Delayed (See #1) |
| Operation of all Crates on the Truck | 30-Apr-06 | 30-Oct-06 | 30-May-07 | Delayed (See #2) |
| Operation of all Crates on the Truck stand alone | 30-Apr-06 | 30-Jul-06 | 30-May-07 | Delayed (See #3) |
| Commissioning of Low Voltage Power Supplies on the Barrel Complete | 1-Jun-06 | 1-Oct-06 | 30-May-07 | Delayed (See #4) |
| Commissioning of Low Voltage Power Supplies on the Endcap C Complete | 1-Jul-06 | 1-Nov-06 | 30-May-07 | Delayed (See #5) |
| Commissioning of Low Voltage Power Supplies on the Endcap A Complete | 1-Aug-06 | 1-Nov-06 | 30-May-07 | Delayed (See #6) |
| Complete Commissioning of EndcapA optical Links (SMU) | 1-Aug-06 | 1-Oct-06 | 1-Dec-06 | Delayed (See #7) |

Note #1  Schedule change postponed the installation of electronics on the endcaps for after the magnet tests are complete.

Note #2  late delivery of repaired power supplies from MDI

Note #3  will work on the final configuration only

Note #4-6 late delivery from MDI

Note #7  coupled to commissioning of crates, which are delayed due to power supplies problems

3.3.2.1 Pre-Operations and Commissioning

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Completion of Documentation of Level 1 Trigger Interface for Liquid Argon and Tile Calorimeters (Pitt) | 1-Dec-05 | -- | 1-Aug-06 | Completed (See #1) |
| Complete Commissioning of Barrel Receiver System (Pitt) | 31-Dec-05 | 31-Jul-06 | 31-Jul-07 | Delayed (See #2) |
| Maintenance Procedures for Receiver Modules Complete (Pitt) | 31-Dec-05 | -- | 15-Sep-06 | Delayed (See #3) |
| Start commissioning of EndcapC Receiver System (Pitt) | 1-Jan-06 | 15-Jul-06 | 15-Mar-07 | Delayed (See #4) |
| Complete Commissioning of EndcapC Receiver System (Pitt) | 1-Mar-06 | -- | 15-Oct-06 | Delayed (See #5) |
| Complete Commissioning of EndcapA Receiver System (Pitt) | 30-Jun-06 | -- | 30-Oct-06 | Delayed (See #6) |

Note #1  Documentation almost complete. Documents need to be updated with final versions of hardware. Technical part of documentation is completed. Report to EDMS needs to be updated.

Note #2  Need all FEC crates commissioned

Note #3  Need all FEC crates commissioned to finalize procedures

Note #4-6  Need all FEC crates commissioned

John Sondericker (Brookhaven National Laboratory)

For the last few reporting periods we have been looking into why the Quality Meters of the Barrel Cryostat appear to have a zero shift of some 100 pico farads. All of the meters worked well in bldg. 180 but upon cooling the cryostat down and filling with LAr, all of the six read with the zero offset. Cables and calibrations were checked and rechecked but everything was in working order. After some telephone discussions the problem was diagnosed to absorbed moisture in the G-10 spacers of the meters capacitor plates. A spare Quality meter at CERN was measured and read over 200 pf in the shipping box but when dry and calibrated read 120pf. Spare meters, resident at BNL, read 160pf in an air conditioned environment. Unfortunately, there are no plans to warm up the Barrel Cryostat at any time in the future so the offset problem will remain. Shifting the zero offset was tried but the circuitry does not have enough range to adjust out the error.

The four End Cap Cryostat Quality Meters are in the process of being welded into the system. Time will be allocated for drying the G-10 spacers, as determined by its room temperature calibrated tare value.

Bill Cleland (University of Pittsburgh)

During the third quarter of 2006, the Pittsburgh group has begun the manufacture of two new types of LSBs, designed to compensate for wiring errors in the endcap calorimeter (discussed in the previous quarterly report). The new boards have been produced, and the wiring of one type (R1x16L) is complete, and the wiring of the other (R1x8H) is under way. Tests of production prototypes of each have been made, and the mapping has been verified to be correct. Steps remaining are the burn-in and testing for both types of boards, which will be carried out in October-November. The set of patch cards (boards mounted below the baseplane which reroute 8 of the signals in two FEBs, also needed to solve the wiring problems) have been built and tested at BNL and were installed in the pedestals in September.

In the commissioning of the barrel system, we continue to work on the timing measurements of the L1 signals, where we compare the time measured in the L1 and main readout with that calculated taking into account all of the known cable lengths and PCB delays. This comparison is necessary to permit the setting of the delays in the TBB, which can only be done if the relative cable and PCB propagation delays for each depth layer are known.

Commissioning of the endcap A is also under way. The first step is to carry out connectivity tests, where we establish that the signals are seen in the expected channels when a given calibration channel is pulsed. We have looked at all baseplanes, and the only problems seen in the EMEC are those associated with the miswiring of the calorimeter mentioned above. For the HEC, some problems were seen, but these were traced to errors in the data base. For the FCAL, no problems have been seen, except for one bad channel, a known problem.

At Pittsburgh, we have been testing the small TOF system we have built to be used for establishing the timing between the two halves of TT15, which is split between the barrel and endcap. This measurement will provide the required length of the set of eight cables need to be made to perform the analog sums in the endcap receivers. The system is functional and its timing resolution is extremely good. It will be implemented at CERN after the endcap calorimeters are operational.

3.3.3 Beam Test

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Protvino Engineering Run (Arizona) | 25-Aug-06 | -- | 25-Aug-06 | Completed |

3.3.3.1 FCal Hadronic Tail Measurement

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FCal Electrical Test Bench Completed (Ariz) | 20-Apr-06 | 20-Aug-06 | 15-Dec-06 | Delayed (See #1) |

Note #1  All parts are in and assembly is nearly complete. Mostly in debugging phase now. But further delays are foreseen due to time-critical electronics for Shupe's ATLAS Cavern radiation backgrounds measurements.

John Rutherfoord (University of Arizona)

During July and August, commissioning calibration data was taken on FCalA. Several anomalies showed up. Most could be explained, a few will require further investigation, and one pointed to a new problem. Already in the TDR tests we had seen on a few channels which appeared to have a slightly higher Ohmic resistance at the signal feedthrough. The recent commissioning data showed no calibration pulse (other than a small crosstalk from adjacent channels) on five of the six such channels in FCalA. We realized that there must be a disconnect between the calibration line and the signal line. For good channels the TDR sees at the baseplane the pigtail and the calibration injection resistor in parallel. For channels with disconnected calibration line the TDR sees only the pigtail. This small difference in impedance is what we misinterpreted as a higher Ohmic resistance on the feedthrough.

The most likely cause of this disconnection is a poorly soldered calibration injection resistor on the baseplane right next to the baseplane connector to the FEB. We have looked at a spare FCal baseplane with an Ohm Meter and found that all 1,792 calibration injection resistors are connected. So it is a puzzle why five such channels show up on the FCalA baseplane. From TDR tests on FCalC we see no such cases of this anomaly so, when commissioning calibration data is taken on the C-end, we expect to find no disconnected calibration injection resistors.

Luckily the underside of the baseplane is not completely inaccessible although it is a major effort to remove all the boards in the Front End Crate, remove the crate, and then dismount the baseplane with all the warm (pedestal) cables. A campaign to make repairs is being planned.

We have been bombarded with a large number of “emergency” requests and have reacted promptly. For instance, Athena-based Monte Carlo studies of single particles directed into the FCal showed an alarming energy loss upstream of the FCal. This was traced to the Boron-doped polyethylene shielding in the “alcove” just upstream of the FCal. We were able to finger the problem as an incorrect (anomalously large) density entered into the Monte Carlo. We now have a piece of that boron-doped polyethylene and will make an accurate measurement of its density.

In the process of uncovering the problem with the Monte Carlo we learned that the pixels apparently contribute quite a bit of material, in their services, upstream of the FCal. This is puzzling since the pixels themselves cover only up to about η = 2.5 and particles from the IP aimed in the direction of the FCal don’t even exit the beampipe until well downstream of the interaction region. We are curious to find out what pixel services are so close to the beampipe so far downstream of the interaction point. We suspect another mistake somewhere in the simulations. But it has been hard to get information from the pixel group.

Sasha Savin has created an interactive (root-based) display program which allows the user to interrogate any channel in the FCals. The display shows either the C-end, the A-end, or the calibration test beam configuration. As an option one can superimpose a color-coded shading of channels to indicate the few dead channels and those channels requiring special attention in the analysis. Recently he added the capability to display the TDR data for the selected channel from his huge data base. He also displays the envelopes for normal channels so the novice can look for anomalous behavior.

Questions about the signal mapping keep coming up, mostly from the offline software groups. Often their questions are a bit orthogonal to the way we organized our mapping files so we have to work through the files in a new way. Because the mapping of the FCal is not straightforward, such requests can take quite a bit of work.

Rutherfoord spent the month of July at CERN working on setting up for our test beam run at Protvino. The EMEC, HEC, and FCal groups have each made very small pieces of their calorimeters. The FCal piece, dubbed the FCalchik, is 50 mm deep, 60 mm high, and 90 mm across. It has 16 tube electrodes with the normal liquid argon gap of 250 microns and 16 tube electrodes with smaller 100 micron gaps. The FCalchik also has a liquid nitrogen cooling loop near the periphery. (“chik” is a Russian diminutive suffix.) Each calorimeter piece will be housed in its own small liquid argon cryostat in order to isolate contaminants, should evidence for any show up. Each cryostat will have a standard ATLAS purity monitor, thanks to Christian Zeitnitz, formerly at Mainz, now at Wuppertal. Arizona is responsible for the FCalchik module, the argon purifying system for all three cryostats, and the beam trigger. Rutherfoord has also written the unpacking algorithms for the offline. The three cryostats will be placed in an extracted 60 GeV proton beam provided by the Protvino (formerly Serpukov) accelerator at IHEP. The FCal cryostat will come first. Then after some absorber will come the EMEC cryostat. After some spacing the HEC cryostat will come last. The positions are such that the ratio of the rates of energy density deposited in each module are close to those expected in ATLAS. Rutherfoord worked out all these rates and ratios. We will start with a few protons per rf bucket (1.0 microsec between buckets) and ramp up the intensity as far as possible, hopefully well above the design at the upgraded LHC. We plan an integrated exposure approaching a run year. One goal is to test Rutherfoord’s predictions for the critical ionization rate and the pulse shape changes which occur above that threshold. Setup at Protvino is scheduled for mid November and the first run is presently scheduled for sometime in December.

While at CERN in July Rutherfoord spent a few days at Orsay measuring the shape of the calibration pulse on the FCal baseplane, something our Orsay colleagues were eager to do but needed a little help. With Laurent Serin we measured this pulse shape on a spare FCal baseplane (now at Arizona). It was found that the calibration pulse shape varies slightly with baseplane slot number. That is, the distance the Front End Board is from the pulser board affects the pulse shape as injected into the preamp due to reflections on the traces on the baseplane. We are now analyzing this data and we find that once these pulses come out of the shaper, any differences are greatly reduced, as expected. While we will generate a correction due to these effects on the baseplane, this correction will be very small.

Also while Rutherfoord was there, he asked de La Taille to measure the transfer function of the preamp. Christophe did this and Rutherfoord is analyzing this data. Rutherfoord also learned that Fournier, with a graduate student, has measured the input impedance as a function of frequency for a number of preamps. The data goes up to about 100 MHz. We now have that data too and are trying to understand our own measurements of the preamp input impedance taken in the EMF in summer 2005 in terms of these new measurements. (Incidentally, Lanni has preamp input impedance measurements which are at odds with Fournier’s. We will try to sort this out.

## 3.4 M&O Tile

3.4 Subsystem Manager's Summary	Larry Price (ANL)

Extensive work was done on achieving a fundamental understanding of the problems with the low voltage power supplies (LVPS).  Progress during this reporting period set the stage for an engineering “Experts Week” at the beginning of October and crystallizing plans for modifications made by the end of October.  Meanwhile, roughly half of the Barrel Calorimeter was instrumented with LVPS with temporary overvoltage protection (OVP) so that other aspects of commissioning could proceed.  In cooperation with ATLAS Technical Coordination, most of the Barrel was provided with cables and services and the cables tested and validated by the end of this period.  Gap and MBTS scintillators were tested (to the extent possible with restrictions on the use of radioactive sources) and light sealed.  Barrel modules with LVPS were extensively tested and read out with the TDAQ system.  Joint cosmic ray runs were taken with the LAr and (at least once) the muon system.  The cosmic ray data taking increasingly became part of an ATLAS-wide effort of Phase 2 commissioning, aimed at advancing smoothly to a state where the whole detector can be read out together in preparation for LHC collisions.

3.4.1 TileCal - Specific Costs

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Module-by-Module Commissioning of Barrel | 30-Apr-06 | 1-Nov-06 | 1-Feb-07 | Delayed (See #1) |
| Complete Initial Calibration of Barrel | 31-May-06 | 15-Jan-07 | 15-Feb-07 | Delayed (See #2) |
| Begin Module-by-Module Commissioning of Extended Barrels | 15-Jun-06 | 1-Oct-06 | 1-Feb-07 | Delayed (See #3) |
| Begin Barrel Data Taking with Cosmic Rays and Full DAQ System | 1-Jul-06 | -- | 21-Jul-06 | Completed |
| Version 1.0 of Diagnostic/Monitoring Software | 31-Jul-06 | -- | 31-Jul-06 | Completed |
| Complete Module-by-Module Commissioning of Extended Barrels | 1-Nov-06 | 1-Mar-07 | 1-May-07 | Delayed (See #4) |
| Complete Initial Calibration of Extended Barrels | 31-Jan-07 | -- | 31-Jan-07 | On Schedule |
| Full Integration with LAr System; joint cosmics running started | 1-Mar-07 | -- | 1-Mar-07 | On Schedule |

Note #1  The need to retrofit low voltage power supplies with safety and anti-noise protections have delayed module commissioning.

Note #2  The need to retrofit low voltage power supplies with safety and anti-noise protections have delayed module commissioning.

Note #3  The need to retrofit low voltage power supplies with safety and anti-noise protections have delayed module commissioning.

Note #4  The need to retrofit low voltage power supplies with safety and anti-noise protections have delayed module commissioning.

3.4.1.1 Pre-Operations 	James Pilcher (University of Chicago)

(a) Repair and Maintenance of FE Electronics

During this period no PCB repair work was needed since no faulty cards were returned. Substantial repair will be reported in the next period.

(b) Commissioning and Integration work

During this period Chicago maintained a team of 8 people resident full time at CERN to contribute to commissioning and integration work. Six were supported by Research Program M&O funding.

By the end of this period all services were connected to the 128 barrel drawers of the barrel calorimeter. This includes the following connections: trigger, HV, laser, LV 200V local, LV 200V from USA15, LV Aux cables local, LV Aux cables from USA15, TTC fibers, CANbus cables for Integ/HV, CANbus cables for LV, smoke sniffer tubes, cooling tubes, cesium tubes. In addition, 68 LV supplies were installed in the calorimeter fingers.

On the extended barrel, A side, CANbus daisy chains and ferrites were installed in all fingers. Local AUX and 200V cables were installed and certified. Trigger cables were installed and certified. All other cables except HV were made ready for installation. About 90% of the cesium cabling and piping was completed.

On the extended barrel, C side, CANbus daisy chains and ferrites were installed in all fingers. Local AUX and 200V cables were ~70% installed but connections and QC were not completed. Installation of cable trays prevented work in Sectors 11,13 and 15. About 75% of the cesium cabling and piping was completed.

Chicago personnel played an extensive role in the services installation and testing.

An extensive effort is underway to provide, test and install a temporary version of the LVPS system for each electronics drawer. By the end of this period about 68 of the 128 supplies had been installed for the calorimeter barrel but it is understood that their operation is unreliable and that they will have to be removed once a more robust version of the supply is available. It is useful to have them installed to study other aspects of the calorimeter system.

Two members of the Chicago team have been helping with the QC of the completed LVPS assemblies.

Kaushik De (University of Texas at Arlington)

Two students from UTA are stationed at CERN full time to work on TileCal - Hyeonjin Kim and Rishiraj Pravahan. In addition, Carlos Medina spent the summer at CERN. Kaushik De spent a substantial fraction of time also at CERN.

Rishi and Heonjin took TileCal shifts and participated in various EB and ITC related pre-operations work. Special shifts were also set up every evening to calibrate the ITC scintillators with SR-90 radioactive source. The shifts also tested all EB channels (within a drawer) using MobiDick for light leaks or electronic problems. On average, one drawer was tested every evening. Results were fed back to the CF electronics group and reported in weekly Commissioning meetings.

We discovered a problem with the fiber sleeves just before closing the EB's for the magnet tests. There was significant risk of crushing fibers in some regions. UTA and MSU team members worked in emergency teams to fix these problems for a week, by cutting the sleeves. For the final two days, access was only possible from a basket lowered with a crane. The operations were successful in safely closing the EB's on schedule.

The process of cutting the sleeves created light leaks. The MSU team came back in September and put additional light protection sheets on the ITC scintillator region.

Joey Huston (Michigan State University)

During July-Sept 2006, the Minimum Bias Trigger Scintillators plus covers were installed on both the A and C sides. At the same time, the forward moderator sections were also installed. It was noticed that there was a conflict between the optical cables reading out the MBTS, cryostat and gap scintillators and the inner detector. To avoid any damage to the cables, the light sheath covering the clear fibers in the readout cables were cut. This necessitated a major modification of the light-tightening of the forward scintillators which was carried out in this time frame.

MSU technical personnel also assisted in the fabrication and installation of cables for the Tilecal system. They also modified the design and installed a magnetic shield for one of the finger power supplies on the C side.

Graduate student Brian Martin assisted in the above work and in addition worked on the diagnostic testing of the Tilecal readout.

James Grudzinski (ANL)

With regard to the ATLAS detector movement system, the system was used for several movements of both the A- and C-side End Cap Calorimeters including the first movements of the A-side as well as the first closing sequence for each side. The automatic leveling system was tuned and tested successfully during actual movements on the air pads. Progress was made in the final documentation of the system and the knowledge transfer in such a way that the movements at the end of this period were now being carried out solely by the CERN staff. System interfaces to the Metreel service cable carriers and the liquid argon safety line were implemented and tested. A new position sensor was incorporated. Discussions were continued with the team making the big wheel movement system in regard to the eventual integration with the detector movement system.

Robert Stanek (ANL)

After a large number of modified LV supplies were constructed, ANL and MSU personnel spent time getting these things installed and operational. Larry Price headed up the LV project at the organizational level. At the end of this period we had installed about 60 power supplies, and had learned how to live with them.

In addition to getting the barrel components operational, a large fraction of effort was spent on developing and understanding the results. The sheer volume of information is a problem we struggled to deal with and have developed many tools for the future for databases and analyses. Larry Nodulman, Rik Yoshida, Sergei Baranov and Dave Underwood have contributed valuable experience to guide this effort, and this has been key in keeping us on track.

Dave, in addition, had designed, constructed and installed a set of pulsed LEDs to commission and understand the optical system of the barrel. This has proved very important in monitoring the effects of the toroid field as well as knowing the timing across the detector.

Steve Errede (University of Illinois, Urbana-Champaign)

During the July-Sept 2006 period two members of UIUC, David Forshier and Irene Vichou continued to contribute to the commissioning of the TileCal detector, now fully assembled in the underground cavern UX15.

David Forshier, a technician, worked in the provisioning and QA of trigger cables for the two Extended Barrels. David helped in other services activities, including the installation of daisy chain cables around the two Extended Barrels and he showed flexibility in moving from one task to another.

Irene Vichou has continued to work on the commissioning of the TileCal detector, being the run coordinator for the phase I operations and the phase II coordinator (together with Christophe Clement). In both cases her role is to evaluate the priorities and feasibility of several subtasks and to plan in such a way that there are no conflicts and intermediate milestones are fulfilled in order to reach the full operation with the expected performance.

Concerning phase I (detector standalone operation) the following achievements have been made:

- Fulfillment of the connection of the Barrel part to the services provided by the Technical Coordination.

- Final certification of the FE electronics of the full barrel.

- Equipment of 1/2 of the Barrel with LVPS which have to be studied systematically for robustness and stability of operation.

- Extended checks of the FE electronics operation using the final RODs for readout and commissioning exercises.

- Very well elaborated procedures to evaluate with data the operation of the hardware in a very user friendly manner. This will facilitate the detection of problems or the decision making for an element to be certified.

Concerning phase II (integration with systems as Trigger, DAQ, DVS, other calorimeters):

- We have defined real milestones for the intermediate steps till October for the integration with the above systems.

- Integration with the ROSs in the DAQ part is in good progress, TileCal signals were given to the LVL1 calorimeter group for testing.

- Using a local back-to-back tower TileCal trigger, we have defined a combined run with the LAr EM calorimeter for mid-July for purposing of matching events together to common runs with cosmic muons.

Irene, as the person responsible for the definition of the EM scale of TileCal for data-taking (starting point for calibration) gave a summary talk on this subject at the ATLAS Hadronic Calorimeter Calibration Workshop held in MPI, Munich between 3 and 5 of May.

3.4.2 Calibration & Monitoring

3.4.2.1 Pre-Operations 	James Pilcher (University of Chicago)

During much of this period Chicago graduate student Martina Hurwitz was the co-leader of Team 5, responsible for monitoring the test and calibration data collected with the operational calorimeter modules. She has been working with Chicago students Imai Jen-La Plante and Eric Feng to streamline the process of extracting calibration constants using the charge injection system. In particular, a number of modifications and improvements are being made to Athena to facilitate the process.

Kaushik De (University of Texas at Arlington)

During the summer, after a long wait, we received permission to use a SR-90 radioactive source to test and calibrate the ITC scintillators. We were only allowed to use the source during the evening. Shifts were set up among UTA people for this purpose.

Each day, the CF team hooked up a MobiDick to one drawer on the EB. For the last few days, we had access to both MobiDick's. During the evening, a team of three people from UTA took data with the MobiDick using the source. Integrator data was taken with HV ON and OFF for all channels. The source was moved to expose all the scintillators serviced by the drawer. All data were recorded (and saved electronically).

These calibration runs showed that all channels that we were able to test had sufficient light. Some light leaks were discovered and fixed. Some channels had lower light than expected - though still above threshold. We expect these were caused by damaged/broken fibers. Overall, these runs were extremely useful in testing and calibrating the scintillators in place for the first time.

## 3.5 M&O Muon

3.5 Subsystem Manager's Summary

Frank Taylor (MIT)

At the end of September-06 some 28 BW sectors - all 16 of BW-C and 12 out of 16 of BW-A were assembled, tested and stored. In addition, 11 EIL4 stations were integrated with their corresponding TGCs and alignment bars and tested. The total number of EIL4 stations installed in UX15 is five.

Planning studies were undertaken on the SW assembly task to be conducted in B191. A service installation workshop for both the BWs and the SWs was scheduled for 12-13-Oct-06 at CERN.

The assembly of BW sectors in B180 proceeded well but the schedule continued to be threatened by rework necessary on the so-called H-beams (outermost beams of the sector) and the fabrication of needed storage tooling.

The delivery of alignment parts remained ahead of the critical path (defined by the mechanical assembly of BW sectors and EIL4 frames) and at the end of September all the BW alignment bars were delivered to CERN. In addition, all the alignment bars for the Small Wheel A were delivered to CERN. The alignment bars for SW C have been constructed at Freiburg and, after calibration, will be shipped to CERN in mid December.

A program was carried out to replace all CSMs used in the MDT EC system with upgraded ones that have less jitter by means of mounting a true 50 MHz clock. A clever hardware implementation was developed by the Michigan electronics team that used pre-existing connection points on the CSM board as solder points for the crystal clock mounted on a small mezzanine board. This upgrade program was successfully carried out and by the end of summer all CSMs were fixed and all BW and EIL4 stations were outfitted with the improved version.

The integration and testing of CSC proceeded in B184 with BNL, University of Arizona, University of California – Irvine and Stony Brook personnel. All CSCs were outfitted with final electronics and were mounted on their respective support frames. A trial installation and commissioning of the alignment fixtures were done using the CERN CMM. Cosmic tests were made.

3.5.1 MDT Pre-operations, Operations & Maintenance

3.5.1.1 MDT Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete all 16 EIL4 MDT-TGC Assemblies | 14-Mar-06 | 1-Aug-06 | 1-Nov-06 | Delayed (See #1) |
| Start SW Side C Assembly in B191 | 1-May-06 | 1-Oct-06 | 1-Dec-06 | Delayed (See #2) |
| Start of Phase 111 Commissioning in UX15 | 1-Aug-06 | 1-Oct-06 | 15-Dec-06 | Delayed (See #3) |
| Start of Phase 3 Commissioning in UX15 | 1-Aug-06 | 1-Oct-06 | 15-Dec-06 | Delayed (See #4) |
| Complete 12 Sectors BW-A | 30-Sep-06 | 30-Sep-06 | 30-Oct-06 | Delayed (See #5) |
| Pre-operations of MDT Chambers - Phase 2 (Boston) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #6) |
| Pre-operations of MDT Chambers - Phase 2 (MIT) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #7) |
| Complete all 16 Sectors BW-A (Additional 4) | 15-Jan-07 | 15-Jan-07 | 30-Oct-06 | On Schedule (See #8) |

Note #1  This project has been ahead of the UX15 critical path but was delayed due to CERN technical resources and various reworks necessary to make the Al frames (made in Russia) fit. At the end of Sep-06 11/16 stations were integrated and 5/16 installed in UX15. The integration of the EIL4 stations with support frames and TGCs was completed 29-Oct-06. As of 23-Nov-06 there were 11/16 EIL4 stations installed in UX15.

Note #2  The SW is significantly delayed - primarily due to the delays in gaining working space in B191 where the wheels will be assembled. A work-around plan was developed where the SW tooling will be located on the mezzanine, while the ECT and JD disks are occupying the floor. The steel work of the tilt table has proceeded slowly due to lower priority assigned to it by the CERN team (BWs - TGC & MDT before SWs). As of 23-Nov-06, the mezzanine was cleared ready to receive the tilt table and the table is ready to move into B191.

Note #3  The critical path for the MDT installation and commissioning is set by the installation and commissioning of TGC1 that has to go in first. The installation of TGC1 commenced on 05-Jul-06 but was not finished until 20-Nov-06.

Note #4  Delayed - the TGC1 wheel installation on the HO steel structure was completed on 15-Sep-06 but the installation and commissioning of the TGC1 chamber services is taking longer than expected. Some structural reinforcements had to be made to the TGC1 wheel as well. The load was transferred on 20-Nov-06.

Phase 3 commissioning will take place in steps - starting with single-sector tests immediately following the installation of a sector on the HO structure. The final Phase 3 work will be undertaken following the full integration of the wheel with the various service platforms attached to the hanging wheel following the load transfer.

Note #5  The completion of BW-A sector assembly in B180 has been following the accelerated schedule and on 30-Oct-06 all 32 sectors of both MDT BWs were completed in B180. The quality of the Al remains a concern and some rework of the sector outer beams was necessary.

Note #6  The BU workforce was augmented in late July with the addition of a student, a postdoc and a senior tech. Until the SW work starts they will concentrate on the BW installation and commissioning.

Note #7  A senior graduate was replaced by an undergraduate in June 06. She carried the same responsibilities as Scott and worked on Phase 1.9 and 2 and gas connections.

Note #8  Accelerated plan put in place to finish BW-A and was finished on 30-Oct-06.

3.5.2 CSC Pre-Operations, Operations & Maintenance

3.5.2.1 CSC Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Installation & Phase 2 Commissioning on SW in Bldg 191 | 1-Jun-06 | 1-Oct-06 | 1-Feb-07 | Delayed (See #1) |

Note #1  The Phase 2 Commissioning of the CSCs will not start until approximately Feb-07 after the chambers have been installed on the first SW in B191. See above discussion about the delays accumulated in the SW work.

The integration of the 32 CSCs with their spacer frames and on-chamber electronics is complete and under cosmic testing in B184. Remaining is the integration of the alignment devices on the chambers and their calibration using the CMM at CERN.

3.5.3 Alignment System Pre-Operations & Maintenance

James Bensinger (Brandeis University)

The complete set of Big Wheel alignment bars have been tested and installed in the sectors for the BW. All of the EIL4 alignment bars have been tested and either are installed in the EIL4 chamber frames or are available to the Seattle group for installation. Some difficulties have been encountered installing the EIL4 bars because of problems due the fact that these chambers are installed under difficult conditions with many other chambers in place. All of the bars for the Small Wheel side A are complete and the side C bars are complete and are being measured at Freiburg, expected completion by mid-December. All of the EO components are complete and have been shipped to CERN. The CSC components are still being developed and we anticipate delivery by the end of January.

3.5.3.3 Alignment System Maintenance (Beam Off)

James Bensinger (Brandeis University)

A temporary readout for the alignment system will be attached to the BW sectors as they are installed in the ATLAS pit. It will be made operational sector by sector as the sectors are installed. This will system will be used to determine of the installation of sectors are in their proper place.

## 3.6 M&O Trigger

3.6 Subsystem Manager's Summary

Andrew Lankford (University of California, Irvine)

Pre-operations activities included hardware commissioning and maintenance, software commissioning, and support of TDAQ and detector commissioning. Operations activities included maintaining the Region-of-Interest Builder (RoIB) hardware and software, software maintenance, and operations.

3.6.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Operations Cosmic Ray Support | 1-Oct-06 | -- | 1-Sep-07 | Delayed (See #1) |
| Complete Operations Cosmic Ray Support | 1-Jan-07 | 1-Jan-07 | 23-Dec-07 | Delayed (See #2) |

Note #1  Operations Cosmic Ray Support will begin after the LHC beam pipe is closed, which is currently scheduled for end of August 2007. Meanwhile, the TDAQ system is operated in support of ATLAS detector system commissioning.

Note #2  Operations Cosmic Ray Support will continue until the LHC delivers 900 GeV colliding beams late in 2007.

Andrew Lankford (University of California, Irvine)

Pre-operations activities included hardware commissioning and maintenance, software commissioning, and support of TDAQ and detector commissioning. RoIB commissioning, rack commissioning, and network commissioning continued. The hardware and software of the Pre-series system was maintained. Considerable effort was invested in software commissioning, including functionality, performance, and scaling tests. Tests of the full HLT/DAQ chain using pre-loaded simulation data on the Pre-series system were set up. A series of 24-hour technical runs on the Pre-series system was continued in order to test system robustness and operability. Commissioning of detector systems was supported, particularly through commissioning detector systems with the Readout Subsystem (ROS) and in developing software tools for monitoring and calibration. Commissioning and debugging of TDAQ systems was also supported, including a test of a full HLT/DAQ calorimeter slice on the Wisconsin testbed and tests of a full HLT/DAQ electron/gamma slice on the Pre-series system.

3.6.1.1 Supervisor RoI Builder

Robert Blair (ANL)

Jinlong has been in contact with Bruce Barnett and the expectation is that in October fibers will be pulled to allow for testing the LVL1 Calo system with the RoIB.

In July Jim tested the interface between the CTP and the RoIB.

Bernard Pope (Michigan State University)

The ROIB Input card was equipped with the HOLA LDC in the 3rd SLINK slot and is ready to take data from CTP. The remaining FILAR cards were received.

A meeting between the LVL1 and the ROIB teams took place to discuss the test plans for August.

The remaining HOLA cards for the ROIB setups were received. The LVL1-ROIB test was postponed in August, as the Level-1 team was busy with design reviews. However, in September, preparation of the test setup for a PC based RoI builder has started in the building 32 test bed. Three PCs have been equipped with the FILAR cards.

Ermoline made an oral presentation of the "ATLAS TDAQ RoI Builder and the Level 2 Supervisor system" during 12th Workshop on Electronics for LHC and future Experiments in Valencia.

The rack DCS work continues. The TDAQ DCS PCs are ready for installation.

DIN rails for ELMB and terminal blocks were installed in the first rack. Sensor cables were made and installed. The layout of the racks in the SDX1 counting room was re-entered in the Rack Wizard and all components were updated according to the latest definitions. The DCS PC was installed in USA15 (power, registration, networking, OS). PVSS and Framework were also installed and a development project started. A first meeting with the central ATLAS DCS team took place in order to discuss the integration of the TDAQ rack DCS into the overall ATLAS DCS. By the end of September, the CANbus PSU and one power module have been installed in the USA15 DCS rack. Therefore a complete DCS chain (DCS PC, PSU, ELMB, sensors) is available. Two prototypes of the operational rack panel (one with trending plots) have been developed. Ermoline reported on the status of the rack DCS work at the UC London TDAQ workshop.

3.6.1.2 Communications and Travel

Robert Blair (ANL)

Jinlong Zhang joined the ATLAS group in Sept. He will be resident at CERN. He spent two weeks at ANL learning about RoIB software and hardware. He then traveled to CERN to provide RoIB support, participate in test runs and to set up the support lab for the RoIB.

Werner Wiedenmann (University of Wisconsin, Madison)

dos Anjos and Wiedenmann attended the TDAQ week in London. dos Anjos presented a plenary talk about HLT integration and a talk about the automatic testing scripts in a parallel session.

3.6.1.3 Programming Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of a multi-node test bed for integ/testing/debug & performance Optimization of HLT code (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #1) |
| Support of HLT SW installation in point 1(HLT installation image) (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #2) |

Note #1  A multi-node HLT/DAQ testbed was operated throughout the year, culminating with a complete slice of liquid argon HLT algorithms in August. Operation will continue in FY07.

Note #2  Support of the HLT software installation for FY06 is complete. Support will continue in FY07.

Andrew Lankford (University of California, Irvine)

Hardware Commissioning:

Unel assisted in the commissioning of the final Readout Subsystem (ROS) nodes. Ciobataru and Stancu monitored the TDAQ network at Point 1. Some oscillations in data rates remain to be understood.

Hardware Maintenance:

Ciobataru and Stancu updated documentation and databases describing network equipment, connectivity, and configuration. Ciobataru continued development of a tool for monitoring network performance mpNetPerf, including uncovering the fact that the Linux kernel can drop UDP packets without notification under certain circumstances. This tool can now be used to determine the effective buffering capacity of any network configuration, which is a critical parameter for determining the setting of parameters in the Event Builder (SFI) software. Stancu provided graphical output and other tools for network database queries. Ciobataru participated in testing of a network emulator used for network switch testing and maintenance.

Software Commissioning:

Wheeler investigated the feasibility of using the Manchester University GRID cluster for running large and medium scale tests of the TDAQ software. Stancu supported these studies.

Wheeler worked on preloading of simulated event data into ROS’s for system testing and studied memory utilization. Subsequent system performance tests performed by Unel, Wheeler, and others focused on testing High Level Trigger (HLT) algorithms within the HLT/DAQ system. A system with multiple real ROS’s feeding data to LVL2 and EF systems was operated with simulated events. The system was successfully run overnight. It was triggered with the RoI Builder. Additional tests were also performed with the new TDAQ release (1.6).

Unel performed measurements of system performance of the most recent TDAQ release (1.6.0) in the absence of HLT algorithms. Unel organized a series of 24-hour runs of the TDAQ system to test robustness and operability. Wheeler participated in debugging the problems observed in these test runs, and she tested some prototype cluster monitoring tools. Kolos also participated. The September run used TDAQ release 01-06-00.

Ciobataru and Stancu assisted with the use of a network emulator to test the fault tolerance of TDAQ software applications under controlled conditions of network degradation.

Detector Support:

Bold added functionality to HLT services to ease detector commissioning. Kolos participated in debugging the latest TDAQ software release at Point 1, where some problems were observed by some detectors that were using it for commissioning. All issues were resolved.

TDAQ Support:

Stancu helped troubleshoot a standalone ROS setup for release 01-06-01. Unel assisted in converting the Liquid Argon Calorimeter ROS’s to the new TDAQ release. He also participated in standalone ROS testing performed at NIKHEF. In support of commissioning other TDAQ subsystems, Unel, Wheeler, Kolos, and Stancu participated in 24-hour technical runs on the TDAQ Preseries system at Point 1.

Robert Blair (ANL)

Jim Schlereth has put together code to allow for a run controlled PC equipped with QUEST cards to act as a LVL1 source. This will allow for large scale tests without the need for LVL1 components, The system from the LVL1 fibers through the EF can be tested this way with MC generated data.

Changes in the framework require some migration of the L2SV code to adapt to new streaming/routing requirements. Both the RoIB code and the L2SV code is being modified to use the new ERS.

Code to monitor differences that occur between the RoIB data and data recorded by the ROS has been included in the TDAQ release.

Bernard Pope (Michigan State University)

Alessandro DiMattia continued the work initiated in June, putting the online integration at low priority. On this item the work is presently stopped: He has not investigated the multithread problem, but has had no complaints from the people working on Testbeds concerning the functionality of muFast while operated in a single thread together with other LVL2 slices. Hence he concludes that everything is working well in this area.

Details of other items follows:-

1. DiMattia’s work for the HLT review has been terminated with the 1-day workshop held on the 21 of July. His presentation focused on items still opened on muFast. The slides can be found in the usual place

https://twiki.cern.ch/twiki/bin/view/Atlas/MuonHLTReviewLVL2muFast

2. Concerning the muFast extension, preliminary results are not encouraging: it is quite hard to reach performance on muon momentum measurement, using LUT methods, close to those obtained in the barrel. The reason of this it is probably the inhomogeneity of the magnetic field along the muon trajectory, which makes the description of the trajectory more complicated with respect to a naive model that assumes a constant curvature (like the one employed for the barrel). Di Mattia is investigating other possible sources of the bad performance (for example bugs in the analysis). This work is ongoing and, while the Israeli colleagues are more concentrated on the TGC data processing, he is focused on the pattern recognition in MDTs + some analysis for understanding if other variables can be exploited in order to make a more accurate description of the muon trajectory.

3. The muComb algorithm has been finalized and put into the CVS repository. Its performances, in the barrel region, appears to be very good, but they are not yet in a shape to be presented. In fact, during the work for implementing the Z-match between the reconstructed tracks it was realized that the single muon production has a bias: the muons have been generated with no vertex spread. This invalidates the results obtained in the z-match.

Di Mattia’s work in August was mainly focused on the extension of the Level-2 standalone muon reconstruction in the endcap. He also worked on the Level-2 muon combined algorithm. In more detail:

Endcap extension: in August some bugs in the reconstruction of the TGC data at level-2. Once fixed, the full production of the events (4*106) has been re-done. After looking at the new data produced, things appear to be less confusing than before. However there remain some problems for the momentum reconstruction, but the analysis for the pattern recognition seems to behave as expected. A big step forward has been achieved in September, by implementing a procedure that provides a "non optimized" estimation of the muon pT in the full endcap. This allows us to operate the muFast algorithm in the full spectrometer, even if the pattern recognition is not fully working yet. This latter is going to be implemented soon, because the procedure to be used has finally been identified. Preliminary results show that it can be used on the full endcap, even in those regions where the magnetic field is inhomogeneous, and that the corresponding efficiency is quite high. The details have been presented in the TDAQ workshop in London:

http://indico.cern.ch/conferenceDisplay.py?confId=a061351

The next step is the implementation of the data extraction for the calibration of the Spectrometer, and the finalization of the pattern recognition. The former is expected to be completed in early October.

muComb: results from the new production are fine and quite promising. They have been presented at the TDAQ workshop of London. The next step is to compute the trigger efficiency curve for the single muons.

The sharing/cross mounting of disk space between machines has been implemented on the MSU cluster. On each machine a /scratch/work directory was created and auto mounted through the autos to: /work/local and /work/<machinename> on the local machine and /work/<machinename> on all other machines

Di Mattia has started to use the MSUcluster for doing the massive productions needed for the trigger studies. As of now ~ 6*106 single muon events have been transferred and processed on the cluster. Di Mattia finds the cluster very efficient for the trigger processing, apart from the network speed which is very slow (10 Mbit/s). This produces a bottleneck while events are transferred from castor. However, an upgrade of the network speed could increase the sensitivity to the init time of the job, when it accesses the oracle database for configuring the geometry. Since the events are divided into files having 1000 muons, the init time cannot be neglected with respect to the overall execution time needed to process a file.

A meeting concerning the MSU cluster upgrade and video-conferencing organization took place in August between Schwienhorst, Ryan and Ermoline. It was decided to acquire four more dual CPU machines for the cluster and convert the single CPU machine (PCMSU001) to a video conferencing base station. By the end of the quarter, these additional machines have been received and they are being integrated into the existing cluster. At the TDAQ meeting in London, Pope, Schwienhorst, Di Mattia and Ryan planned work on the integration of different triggers in the Level 2 trigger as a whole. We also plan to work on triggers specific to Top Physics, most importantly those triggers needed for data coming from early runs. We are involved in analysis and documentation for CSC Technical Note 8.

Abolins also attended the London conference and participated in the inaugural meeting of the "Trigger Configuration Review Panel" chaired by Mike Medinnis. In addition, Abolins worked on issues facing the TDAQ Speakers' Committee in the coming year (with Hans Peter Beck and Haimo Zobernig)

Werner Wiedenmann (University of Wisconsin, Madison)

Pre-Ops Software Commissioning:

When running tests on distributed dataflow systems dos Anjos identified and fixed the following problems:

- A problem in the L2PU data collector. When requesting N ROB fragments only N-1 were returned. The problem was originally identified as discrepancy of reconstructed calorimeter energies when running online and offline.

- A problem in the ROS emulator (ROSE) when working with large preloaded datasets. The ROSE kept in memory all the ROB fragments which were found on the input files and not only the ones which were assigned to it. Fixes were provided for TDAQ 1.4.1, TDAQ 1.6.0 and the head version of the CVS repository.

- When cycling states problems in the ROSE (memory leak) and the L2 Supervisor were identified when working with preloaded data. For both problems patches were provided.

- An unpatched problem in the DFM application was identified which caused the back-pressure mechanism not working as expected. An overflow of events in the Event Building phase was observed. The problem was reported back to the main developers of the package.

Together with developers from the SLAC group Wiedenmann was running tests with HLT algorithms in athenaMT using the newly developed database proxy application "dbproxy". Several issues with badly formed SQL requests were identified and reported back to the developers.

TDAQ Support:

Complete selection slice for LAr:

A dataflow system was put together on the Wisconsin test bed running the e/gamma-, jet- and tau-selection code in Level-2 and Event Filter. In total 11 processors were used. The setup included

- 1 L2SV, 1 L2PU for Level2

- 8 ROS emulators for the ReadOut System

- 1 DFM, 1 SFI for the Event Builder

- 3 x ( 1 EFD, 2 EFPTs ) for the Event Filter

- 1 SFO running in dummy mode (no event output)

- the entire TDAQ online software infrastructure

The software was used from the releases TDAQ-01-04-01 for online, Athena 11.0.6 for offline and HLT-03-00-04 for the HLT infrastructure. A total of ~3500 fully simulated events (dijet and single electrons) were preloaded into the ROSEs and the L2SV. These events were preselected high-PT events and thus most of them actually triggered both Level-2 and Event Filter (EF), exercising all parts of the system. The whole system was controlled from the TDAQ panel and ran at about 10 Hz. The rate was limited by the processors used for the Event Filter applications. Progress was observed by looking at the various counters and histograms available in the TDAQ panel for the online applications. Further the HLT algorithms in L2 and the EF filled histograms which were regularly updated and could be inspected with the online histogram display (oh_display). The setup was shown to members of DOE and was also presented in the PESA meeting to the developers. In a second iteration the setup was upgraded to the latest bug fix releases of offline, TDAQ and HLT. Further the histogram "gatherer" application was integrated in the system. With this summary histograms of all Event Filter applications could be displayed in the online histogram display.

The setup was also used to perform stability test with several different input datasets. This included also a 25 h stability test on the Wisconsin testbed. In this test a total of 1.2 million events were processed in L2 and about 1 million in the EF with an overall average rate of 8-12 Hz. Memory leaks were identified in L2 of about 300 bytes/event and in EF of about 12 kbytes/event.

The integrated setup builds the basis for further testing with more applications on the preseries system.

Testing with release 11.0.5 at Point 1:

Tests were run with HLT algorithms for e/gamma selection from offline release 11.0.5 in Point 1. Problems occurred due to recycling of events: the same L1 identifier could appear multiple times in the dataflow system. To avoid this the system was artificially slowed down with a time delay in the L2 Supervisor. The investigation and possible solution of the problem is ongoing. It was also tried to use the real ROS for preloading the simulated data.

Testing with offline release 11.0.6 and HLT release HLT-03-00-05:

After the build of HLT release HLT-03-00-05 and HLT image version 0.6.2 Wiedenmann ran acceptance tests on the Wisconsin test bed before installation in Point 1. This included complete dataflow systems with Level-2 and Event Filter. Several issues were identified and patched for the final release. After installation in Point 1 partitions with the following configuration

- 1 L2PU + 8 ROS + 8 EF/PT

- 12 L2PU + 8 ROS + 16 EF/PT + 2 SFI

- 2 L2PU on one machine + 1 ROSE

- 12 L2PU (2 L2PU on one machine) + 1 ROSE

were used for further tests of the installation. During the tests it was observed when 2 L2PUs are run on the same machine the system slows down after about 3 minutes by about 10% in rate. Further it was observed that Event Filter Processing tasks don't use all of the available CPU resources. Both problems are presently not yet understood and under further investigation. Tests on the Wisconsin test bed have been therefore setup to reproduce the effects.

Work for project based HLT release:

Wiedenmann ran tests with the new project based HLT release candidates. Problems with the setup on AFS were identified. Further a problem in the ToolSvc setup with the HLT framework was identified and fixed. This was necessary for the monitoring setup for LAr commissioning.

3.6.2 Operations

Andrew Lankford (University of California, Irvine)

Operations activities included maintaining the Region-of-Interest Builder (RoIB) hardware and software, software maintenance, and operations. Considerable maintenance was performed on software that is a U.S. responsibility. Maintenance ranged from bug fixes, to accommodating changes in other software or operating systems, to implementing new functionality that experience has shown is needed. In the DAQ area, much of the maintenance activity focused on RoIB and LVL2 Supervisor software, Monitoring services, configuration database generation, Readout Subsystem (ROS) software, and Event Format library. In the HLT area, maintenance activity focused on HLT steering, Event Filter infrastructure software, and muon algorithms. Development of automated software testing continued. System administration activities are ongoing.

3.6.2.3 Programming Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support event read out library for detector commissioning & Cosmic Run (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #1) |
| Support for HLT Application Framework for detector commissioning & Cosmic Run (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #2) |
| Support of Level 2 Framework for detector commissioning & Cosmic Run (PSC) (Wisc) | 30-Sep-06 | -- | 30-Sep-06 | Completed (See #3) |

Note #1  Support of the event format library for FY06 is complete. Support will continue in FY07 as detectors commission, during the ATLAS cosmic ray run, and as event streaming is implemented.

Note #2  Support of the HLT Application Framework for FY06 is complete. This framework is used in TDAQ commissioning tests. Support will continue in FY07 as detectors commission and during the ATLAS cosmic ray run.

Note #3  Support of the Level 2 Framework for FY06 is complete. This framework is used in TDAQ commissioning tests. Support will continue in FY07 as detectors commission and during the ATLAS cosmic ray run.

Andrew Lankford (University of California, Irvine)

Software maintenance:

Unel worked on database generation for system configuration under new (1.6) and old (1.4) software releases. He also contributed to the evaluation and improvement of a new configuration database creation tool. He maintained the ROS software, adapting to the new version of scientific Linux and new drivers.

Bold developed and integrated a major part of the navigation package for the new HLT Steering. The navigation allows implementation of topological triggers and more flexible operations on event features. Meanwhile, he maintained the old steering code and prepared it for 12.0.x software releases. Changes were made in order to propagate the Begin Run transition to the HLT algorithms in order to facilitate quick changes from one run to the next.

Kolos updated the implementation of the interprocess communication (IPC) software and of the Online Histogramming software to use the common Error Reporting Service (ERS). He made some changes to the Online Histogramming as a result of the 24-hr runs. He also worked with students on some extensions to the Monitoring software.

Negri worked on Event Filter infrastructure software in preparation for the next major TDAQ software release.

Stancu worked with a student to interface the network monitoring tools with TDAQ Online Software.

Operations:

Unel continued to lead system administration activities. He automated some of the configuration and shutdown procedures. He worked on procedures for shifting critical functions from failed servers to live servers. He improved tools used for operational monitoring. Stancu participated in troubleshooting of network configurations and network monitoring tools, and he assisted in more general system administration duties during the vacation period.

Werner Wiedenmann (University of Wisconsin, Madison)

Software Maintenance:

dos Anjos started development of python bindings for the Event Storage and eformat libraries. The idea is that these bindings should allow people to rapidly develop scripts for dumping bytestream data. An initial prototype using SWIG (www.swig.org) for generating the Python bindings was created.

dos Anjos updated the automatic testing scripts to integrate with the most recent version of "PartitionMaker" and to use the "FarmTools" from the Point 1 Sysadmin group. Further the tools allow now to setup easily partitions using either the real ROS or the ROS emulator application. Tests were performed with the tools running Level-2 and Event Filter together.

For the next TDAQ-common release dos Anjos provided the following upgrades to the event format library:

- Possibility to get/set ROB and ROD source identifiers independently. This was a request by the ReadOut and Detector communities.

- Possibility to construct the same event format fragment repeatedly

- Possibility to copy the constructed event out of the scope of the construction

- Removal of excessive debug messages

The new code was tested on three different architectures, including a 64-bit SLC4 platform. Further the HLT interface was upgraded to comply with the new TDAQ state machine.

Wiedenmann integrated together with J.Stelzer the new Gaudi JobOptionsSvc with readout from the trigger database. Changes were done for the relevant Level-2 and Event Filter packages.

dos Anjos and Wiedenmann discussed with representatives from the muon group about the integration of the muon calibration software with Level-2 Processing Unit. This includes essentially the communication from the HLT framework and the muFast algorithm with the muon calibration data collection facility.

First discussions took place how to incorporate the new data streaming functionality in the HLT applications. dos Anjos and Wiedenmann took part in several meetings. Wiedenmann provided a chapter for the Level-2 part in the streaming document.

Operations:

Neng Xu provided system administration services for the trigger development cluster.

3.10 M&O Technical Coordination

Subsystem Manager's Summary	    	David Lissauer (Brookhaven National Laboratory)

Calorimeter Calibration Workshop:  A workshop to discuss the ATLAS calorimeter calibration took place in Barcelona Spain in mid-September 2006. There were about 120 participants in the conference that covered the full calibration chain from the online electronics calibration, online monitoring, level I trigger calibration and off line calibration. I was one of the six (6) people assigned to review the status of the calibration and comment on the status and action items to be taken. There has been quite a lot of progress since the last calibration workshop. The Barrel Liquid Argon and Tile have seen cosmic rays in the Experimental Hall and the procedure of the online calibration plus the calculation of the optimal filter co-efficient has been agreed upon in detail for the barrel EM. The rest of the calorimeters should follow the same procedure with small changes to take in to account the differences between the calorimeters.

There were many discussions and competing calibration schemes that would need to be followed by the offline code. Some of the schemes are quite similar and the efforts need to be merged. Some of the efforts are marginal and found to be not useful and need to be halted. Thus, how to converge on a baseline for the offline will be a major part of the effort in the coming year.

Barrel Calorimeter Magnetic Field Test: The magnetic field mapping has been successfully completed.  A significant amount of data has been taken and is now being analyzed.  Preliminary results already show that the calculations and measurements agree to the level of 20 Gauss. This is quite positive since there are still small corrections that need to be made on the exact location of the sensors, etc.

Barrel Calorimeter Services & Commissioning: The Barrel Calorimeter has been refilled. High voltage will be applied at the end of the month (August 2006) when the experts return from vacation.  Preliminary indications are that some of the problematic channels have improved – but final results will be known only by mid-September.

Barrel Calorimeter: The HV on the Barrel Calorimeter is being turned on. Cosmic ray data is already being taken with part of the calorimeter that is fully instrumented. The aim is now to continue to take data with the Barrel LAr and Tile calorimeters combined.  At the same time the signals for the Level I Trigger are already being checked.

EC-C&A Calorimeter Placement and Assembly:  Cable schleps have arrived and are being connected. The cryogenic lines and trigger cables are being installed and connected. The aim is to cool down the EC-A in October 2006 and EC-C early next year (2007).

EC Muon Big Wheel installation:  The first wheel assembly has been completed. The next step is to unload the wheel from the assembly frame on to the chariots and begin work on the assembly of the second wheel.

JD/Small Wheel Assembly: A series of meetings took place to discuss the assembly of the JD and Small Wheel. The second JD assembly has started. The main problem is the delay in the EC Toroid that restricts the space available for the assembly. (See next item.)

Pixel Review: The Pixel Detector had a Review in mid-July 2006 to determine how best to organize the effort to ensure that it will be ready for installation in time. There are a number of problems that have developed in this complicated system. The last issue had to do with the Barrel Al cables. The cables seem to damage easily and the manufacturing process is suspect.  A new run of cables with a slightly modified production procedure will take place in August 2006.  The Pixel is clearly on the critical path of the experiment. The main conclusion is that the effort needs a significant injection of experienced manpower for the integration efforts that need to be at CERN. TC is going to try to identify a few Sr. Physicists and Engineers to help in this effort.  Additional manpower is expected to come from some institutions that have not been involved in the Pixel Detector to date, but can spare some technical manpower.

EC Toroid: A major delay in the end cap Toroid has been found. The design problem associated with the assembly procedure is more serious than we thought a few weeks ago. The solution will take longer to execute because problems were found in the final steps of the procedure for closing the cryostat. The EC Toroid is needed for the present installation schedule to arrive in October/November of 2006. It is now clear that it will not be ready before April of 2-07. We have been working on modifying the installation sequence to allow us still to close the experiment on time on September of 2007. It is clear that at this time some of the systems will be physically in the Hall but would probably not be fully connected.  An example of this would be the second EC Toroid that will arrive very late. The pressure is being kept on, and investigations continue on how one might be able to advance the schedule.

LHC Schedule: There are now discussions on dropping the 450GeV run in 2007 and start up with 14 TeV in 2008 directly. This is mainly due to the fact that the machine does not expect to be able to be ready in time. This is still not an official statement – but we expect that this will become the official policy in the spring of 2007.

ATLAS Upgrade Project Office Meeting: On a continuing basis, ATLAS Project Office meetings are taking place. We heard reports from the cooling working groups, electronics and Liquid Argon. The organization is starting to take shape and people are working hard on defining the problems and developing R&D plans. In some cases the R&D plans are on going and are well advanced. It is clear that to be ready in the 2015 time scale we are already late and once the detector is installed, we will have to increase the pace significantly.

Operation Model:  In mid-July 2006, a task force of six (6) people were appointed to develop a sharing of the responsibility between the different ATLAS collaborators. With Marzio and Steinar we started to develop a job sharing classification that will classify each of the service jobs needed to run ATLAS to a special category. Some of these jobs are already covered by the M&O plans within ATLAS but a large number of jobs that traditionally are done by physicists will have to be distributed in an equitable manner. A meeting of the full task force took place and the needs of the Level 1 Trigger; Muon and Inner Detector systems were presented. The numbers are VERY large and one needs to understand better what fraction of the people are needed to be at CERN and what fraction are needed at their home institutions. But it is clear that a large number of full time people will be needed to start up the experiment. These are people with both software and hardware knowledge.  The operation at the start will involve multiple control rooms with one main control room that is mainly devoted to data acquisition and to ensure the slow controls are working.  In addition, multiple satellite control rooms for each of the systems that will check the data quality for the sub detector will be required.

ATLAS Upgrade Steering Group: The steering group met, and I reported on the status of the Project Office and the R&D activities.  Plans for the Upgrade Workshop in October 2006 were discussed.

Power Failure: CERN experienced a major power failure on the last weekend of July 2006. This is not an uncommon problem at CERN during the summer months. The more serious effect was that the backup power that was to be supplied by diesel generators failed to come up.  ATLAS was quite fortunate and no serious damage was done. But, if such a situation occurs when the experiment is fully operational it could create serious problems.

4.1 Inner Detector Upgrade R&D

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| First Pin Irradiation (Oklahoma) | 30-Jun-06 | 30-Nov-06 | 30-Sep-06 | Completed |
| Measurement of 3-D sensors (New Mexico) | 30-Sep-06 | -- | 30-Sep-06 | Completed |
| Efficiency measured for short strip detector (UCSC) | 1-Oct-06 | 1-Oct-06 | 30-Sep-06 | Completed |

Abraham Seiden (UCSC)

Work is continuing at a satisfactory rate in all areas. Very good progress on 3-Dim. detectors, one of the key R&D projects. Other key areas: staves, powering techniques, electronics technologies also showing good progress.

4.1.1 Detectors

Hartmut Sadrozinski (UCSC)

All reported pixel activities concern 3D detectors produced at Stanford U. Work on improvements of the yield is planned.

3D sensors irradiated with reactor neutrons up to 8.6x1015 n/cm2 were tested with an IR laser and satisfactory signals were seen. Un-irradiated 3D pixel sensors bump-bonded to the ATLAS pixel readout ASICs were tested in the H8 beam at CERN with scans of the bias voltage and angle of incidence. The patterns of the sensor hits and their location relative to the beam telescope hits was as expected.

University of New Mexico continued LCR meter-based 3D sensor capacitance measurements on un-irradiated 3D sensors as a function of frequency. By cooling the sensor to -20o C the bias can be increased to 100V. Work started on using TCAD for device simulations.

The work on detector technology covered the investigation of total ionizing dose (TID) effects in short strips and test structures with a 60Co gamma source. Saturation of the surface effects is observed at about 100 krad, with very large annealing of some effects. The breakdown voltage increased dramatically with TID irradiation, especially for the high p-spray dose, thus allowing the operation of the detectors beyond depletion pre-rad and for neutron irradiation.

The charge collection efficiency measurement on irradiated p-type and n-type MCz strip detectors was performed with our test set-up using a beta source. At the proton fluence of about 3 x 1014 neq/cm2, the two samples show very similar performance, since the low-resistivity n MCz has not yet “undergone type inversion”. This work will be repeated using the SCT readout which is now working for positive and negative pulses, and with detectors having been exposed to higher proton and neutron fluences.

The short strip work covered mainly stripixels. Testing at INFN of n-type stripixel is ongoing, and testing of p-type stripixels will resume soon. Short strip detectors from Hamamatsu are expected in early-mid October. Hamamatsu agreed to test up to 500 V. They will also provide 5 mechanical samples for flatness and gluing tests.

4.1.1.2 Investigation of Strip Technology

Hartmut Sadrozinski (UCSC)

We continued our large-scale investigation of total dose effects on silicon strip detectors (SSD) and test structures using a 60Co source. The irradiation with a total dose of about 600 kRad supplied in several steps was followed by three annealing steps of one week at room temperature and two weeks each at 60Co. There is no difference between Float Zone (FZ) and Magnetic Czochralski (MCz) bulk material, but a large dependence on the surface treatment (p-spray dose). Saturation of the flatband voltage and oxide charge is observed seen in all devices after about 100 kRad. In addition, about 60% of the increase in oxide charge annealed out after the first two anneal steps, after which it was constant. The interstrip capacitance shows large bias voltage dependence before radiation, which was much reduced after a dose of about 150 kRad, but it did not exhibit annealing. The breakdown voltage increased dramatically with TID irradiation, especially for the high p-spray dose, but also showed large annealing. It allowed the detectors to be depleted, which was not possible before TID irradiation (see below).

The charge collection efficiency measurement on irradiated p-type and n-type MCz strip detectors was performed with our test set-up using a beta source. The required temperature management to suppress the large leakage current is well under control.

Several different strip detectors were tested pre-rad in preparation of neutron irradiation at Louvain. The high dose p-spray detectors were pre-irradiated with gammas in our 60Co source to permit operation beyond depletion (see above).

A production review of the new 3 cm long detectors to be manufactured on 6" wafers by Micron Semiconductors was held July 14, and production has started.

The work on using the SCT readout for negative pulses has been finished successfully and we are starting to work on hybrids in collaboration with Prague and Freiburg. This will allow the readout of irradiated n- and p-bulk detectors with the SCT readout which has 20 ns shaping time.

4.1.1.3 Short Strips

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Detector Received (SB) | 30-Nov-06 | -- | 30-Nov-06 | On Schedule |
| Characterization Complete (SB) | 30-Mar-07 | -- | 30-Mar-07 | On Schedule |

David Lynn (Brookhaven National Laboratory)

Motherboard from second vendor via INFN Milano are still in production.

Testing at IFNF of n-type stripixel is ongoing. At BNL, probe station for pre-testing of stripixels is being upgraded and resumption of pre-testing of p-type stripixels is expected in about a month.

Viking board purchase order placed in early July did not go out of BNL until early September due to negotiations on terms and conditions between BNL and Samina-SCI. Board is expected for delivery in mid November.

At NYU, they are experimenting with a collimated laser mounted on an x-y stage. Plans for integrating with Viking DAQ at BNL are beginning.

Hamamatsu detectors are still expected in early-mid October. Hamamatsu agreed to guarantee currents up to 500 V, and to provide data up to that voltage. They will also provide 5 mechanical samples for flatness and glueing tests.

4.1.2 Front-End Electronics

Alex Grillo (UCSC)

The 0.13μm test chip containing ATLAS pixel analog front end circuits and various types of memory cells was irradiated at the LBNL 88” cyclotron with 50 MeV/c protons and 16 MeV/c light ions for SEU studies. On the whole, the results are very promising up to maximum fluence thus far tried, 1x 1015 p/cm2. See below for more details as well as SEU results. The results were presented in LECC06, Valencia, 28-Sep.

There has been some progress this quarter with the SiGe evaluation but not as much as was planned. Neutron irradiated parts have not yet been returned for post-rad testing, proton irradiations at the CERN PS have been delayed due to machine problems, and the gamma irradiations at BNL have been progressing at a slower than expected rate. The demonstration IC submitted to IHP in Germany for fabrication has been received and testing is about to start. Also, a formal proposal was submitted to the ATLAS Upgrade Steering Group for this SiGe evaluation work by a collaboration of ATLAS institutions interested in both the Inner Tracker and the LAr Calorimeter.

4.1.2.1 Deep Sub Micron for Pixels

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Submission of functional prototype chip. | 3-Jun-07 | [New] | 3-Jun-07 | On Schedule |

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

Test chip irradiation:

The 0.13μm test chip containing ATLAS pixel analog front end circuits and various types of memory cells as irradiated at the LBNL 88” cyclotron with 50 MeV/c protons and 16 MeV/c light ions for SEU studies. The front end circuits perform well up to the highest dose achieved at the moment, which is 1x1015 p/cm2. The linear energy transfer (LET) thresholds have been measured for SEU in five different latch structures. The cross coupled DICE type latches with custom geometry proved to be the most tolerant, with single cell cross section limit <10-11 cm2 at the highest LET of 26 MEV/(mg/cm2). This is not total surprise because the DICE architecture requires two simultaneous signals on different nodes to change state, whereas LET from ions is highly localized. Performance for high energy particles is expected to be worse from first principles as well as FE-I3 experience, but these tests have not been done yet. Collaboration with CPPM may possibly lead to such tests at CERN this year. Triple redundant cells were also studied, and for latched with measurable cross sections the upset rate was well predicted by probability and the single latch cross section, indicating no spatial correlation as expected for heavy ions. Results were presented in LECC06, Valencia, 28-sept.

4.1.2.2 SiGe for Strips

Alex Grillo (UCSC)

By the end of September, we still had not received the parts irradiated with neutrons at Ljubljana in January. This has been frustrating our efforts to complete the evaluation of the SiGe technologies. Furthermore, problems with the PS at CERN have delayed the irradiation with protons. The neutron irradiated parts are now scheduled to be shipped in early October. We hope this materializes. The RD50 facility has been able to complete proton irradiation of a few parts at the lowest fluences requested. The high fluence exposures should be completed in October.

We did receive an offer to irradiate some parts at a neutron source in Louvain, Belgium. This potentially could have advantages over the Ljubljana reactor in that there is no addition of thermal neutrons and the gamma background is expected to be much lower than with the reactor. We sent two parts to Louvain in September for a try using this new facility. If this works well, we will irradiate more parts in November.

There is not much new data on gamma irradiation at BNL. Partly this is due to vacations and other distractions by the people at BNL, but there has also been some confusion of the data files for electrical tests done in July. We are in the process of sorting this out with the BNL people and hope to resume these irradiation studies in October. It now appears that all of the parts delivered to BNL for gamma irradiation will not be completed until early December.

We were informed that IBM has added an 8WL SiGe technology along with the 8HP to their 130 nm CMOS technology. The 8WL technology has somewhat lower frequency performance but is also considerably cheaper. We have been assured by CERN that both the 8WL and 8HP will be available through the CERN/IBM frame contract. We will add the 8WL technology to our list to be evaluated. Our collaborator at Georgia Tech, John Cressler, has agreed to obtain some test parts for 8WL and make them available to us.

The demonstration IC on the IHP technology was fabricated and delivered to us in late July. We have now produced a test board on which to mount the IC and interface it to a Xylinx demonstration board and then to a computer. Testing in this configuration will start in October.

We submitted a proposal to the ATLAS Upgrade Steering Group in June to evaluate the various SiGe technologies for use in the upgraded ATLAS. BNL, Penn, Barcelona and IN2P3 joined us in this proposal. At the end of September, we were waiting for comments from the reviewers assigned by the USG.

4.1.3 Optical Readout

4.1.3.1 Diode Receivers

Flera Rizatdinova (Oklahoma State)

We irradiated four PIN diode arrays from TrueLight as a part of optoboards using 24 GeV proton beam at CERN. The integrated dosage was 70 MRad. All PIN diode arrays survived the irradiation. Responsivity of PIN diodes was measured before and after irradiation. It has been found that the responsivity of PIN diodes decreased by factor of 2 after irradiation compared to the initial one. We expect to have a full irradiated test setup in Oklahoma State University in a month.

4.1.3.2 Fiber Drivers

K.K. Gan (Ohio State University)

We irradiated four opto-boards with PIN and VCSEL arrays from various vendors using 24 GeV protons at CERN. Each board was instrumented with one silicon PIN array and a pair of GaAs VCSEL arrays. The PIN arrays were all fabricated by one vendor, Truelight, and the VCSEL arrays were fabricated by three vendors, Optowell, Advanced Optical Components, and ULM Photonics (two varieties, 10 Gb/s and 5 Gb/s). On the opto-boards, each of the PIN and VCSEL arrays coupled to radiation-hard ASICs produced for the current pixel optical link, the DORIC (Digital Opto Receiver Integrated Circuit) and VDC (VCSEL Driver Chip). Furthermore, the opto-boards were mounted on a shuttle system which enabled us to easily move in and out of the beam for annealing of the VCSEL arrays.

The test system consisted of four independent test boxes with each box monitoring one opto-board. The test boxes could generate various signal patterns, including pseudo-random data, and perform bit error rate tests. The signal transmitted from the control room via optical fibers to the PIN array on each opto-board was bi-phase mark encoded with a 40 MHz clock. Each PIN diode on an opto-board converted the optical signal into an electrical signal which was then amplified and decoded by a DORIC. The decoded clock and data were then routed to the VDCs which drove the VCSEL arrays and produced optical signals for transmission via optical fibers to the control room. Each test box then compared the sent and received data to check for bit errors and monitored the power of the incident light.

The test system was also used in the pre-irradiation characterization of the VCSEL/PIN arrays and will be used for the post-irradiation characterization after the opto-boards are returned to OSU with subdued radioactive level. Two of the boxes will be given to our colleagues at Oklahoma and Oklahoma State universities.

The test system monitored various parameters of the opto-boards throughout the irradiation. Of particular interest was the optical power of the VCSEL arrays vs. dosage. The power decreased during the irradiation as expected. We annealed the arrays by moving the opto-boards out of the beam and passing the maximum allowable current through the arrays for several hours each day. The optical power increased during the annealing. However, there was insufficient time for a complete annealing. Consequently both the A.O.C. and ULM 5 Gb/s arrays had no optical power at ~50 Mrad. The ULM 10 Gb/s arrays continued to have optical power of more than 100 uW up to 65 Mrad and the Optowell arrays survived up to at least 70 Mrad, the SLHC dosage. We believe that more arrays would have survived if we had more time for annealing.

The silicon PIN arrays survived the irradiation quite well. After the full SLHC dosage, their responsivity decreased to ~50% of the pre-irradiation level.

In summary, a test system has been designed and fabricated that can be used to monitor the opto-boards during the irradiation and for pre- and post-irradiation characterization. A silicon PIN and GaAs VCSEL array candidate have been identified to have radiation hardness suitable for the SLHC operation.

Jingbo Ye (Southern Methodist University)

The proposed test on the GOL as the optical link transmitter side serializer chip has two parts: the in-lab system test to characterize this chip especially its behavior in an optical data link system in terms of jitter transform and jitter contribution. There are other issues like the power up schemes, bit error rates and optical power budgets and sensitivities. The second part is the irradiation test to probe the upper limit in terms of total dose that the GOL can withstand.

The test system with the GOL has been fully debugged in lab. Most part of the jitter measurements have been carried out and GOL performs within IEEE standard for similar data rate serializer chips. Power up schemes have been checked. Bit error rates and sensitivities have been studied.

We are preparing for the irradiation test targeted in November. After that test, a complete report will be generated in the form of ATLAS note.

4.1.3.4 Multiplexers and Interconnect Circuits

K.K. Gan (Ohio State University)

Another important goal of the R&D program is to measure the bandwidth of the infrastructure of the current pixel optical link. The two critical components in the infrastructure are micro twisted-pair cables and fiber ribbons. The former transmit the LVDS signals between the optical components and the pixel modules. The latter transmit optical signals between the optical components and the counting room. The fiber ribbons consist of 8 m of radiation-hard, low bandwidth SIMM fibers fusion spliced to 70 m of radiation tolerant, medium bandwidth GRIN fibers. At the SLHC, we expect to transmit data at ~1 Gb/s, significantly more than the current 80 Mb/s.

Our previous measurements indicate that the micro twisted-pair cable can adequately transmit signals at 640 Mb/s and that transmission at 1,280 Mb/s might be acceptable. We have also previously measured the bandwidth of a fiber ribbon consisting of 13 m of SIMM fiber fusion spliced to 16 m of GRIN fiber. To more closely resemble the fiber used in the current pixel opto-link we repeated the measurement with a fiber ribbon consisting of 8 m of SIMM fiber fusion spliced to 80 m of GRIN fiber. The result indicates that the fiber can transmit signal up to at least 2 Gb/s. In summary, the current pixel opto-link infrastructure can transmit signals at a speeds required by the SLHC.

4.1.4 Modules

4.1.4.1 Stave Structures

Carl Haber (Lawrence Berkeley Laboratory)

The stave development R&D proposal was submitted to ATLAS earlier this year. Discussions were held with the upgrade steering group and the referees. Some clarifications were added to the proposal as a result.

In this period lab work has focused on testing a stave with serial powering. The serial power bus cable was received and checked out OK. These bus cables were laminated to stave cores. A set of six serial powered hybrids were mounted and bonded. All digital and analog functions were as usual compared with individual power. A number of modules were built with the existing sLHC hybrid and serial powering. In the test box these work well. Mounting a serial powered module on the stave, replacing one of the hybrids, shows good analog and digital performance  with noise and occupancy equivalent to off stave measurements. One anomaly is a somewhat lower gain seen on the stave and not yet understood. Work continues to add additional modules to the stave.

A paper was presented at the recent Hiroshima meeting. A paper will be presented 11/1 at the IEEE NSS and at the Liverpool upgrade meeting. A workshop was held in Berkeley after the Hiroshima meeting to discuss stave and other aspects of the tracker design. About 15 people, mostly from Europe were in attendance.

Detailed design work has been proceeding towards an ATLAS specific stave to be fabricated in 2007. A number of concepts are being addressed to deal with both single and double effective layers.

4.1.4.2 Hybrids

Carl Haber (Lawrence Berkeley Laboratory)

A new hybrid layout was started aimed at the 2007 ATLAS specific stave. The existing hybrid is 20 x 38 mm and holds 4 ABCD chips. The new hybrid will be 13 x 60 mm and hold 6 ABCD chips with serial powering.

4.1.4.3 Cooling Channels

Murdock Gilchriese (Lawrence Berkeley Laboratory)

Stave Mechanics and Cooling

The conceptual design of a 1m long stave structure with integrated cooling has mostly been completed by Innovative Technologies International in collaboration with LBNL. The conceptual design, as modeled, meets the following primary requirements:

Sag <60 microns worst case

Delta T to silicon <2o C

Stability on cooldown <15 microns (out of plane)

Radiation length <0.8%(structure+coolant only)

Extensive FEA models of the mechanical properties have been analyzed to understand the resultant sag from various assumptions. Thermal models have also been completed to understand both the thermal performance at temperature and the thermal induced strains. End connections have been modeled in detail with various options.

The final design concept is composed of high modulus fiber facings, a honeycomb core and a bent aluminum tube, slightly flattened in the prototype design, thermally coupled to the facings. Specifications for the fiber material and honeycomb have been developed. The tube will be existing material used in the pixel detector to save money.

The emphasis of the work has now shifted to the design of tooling for fabrication of prototypes. An initial fabrication sequence has been defined and models of the tooling at various points in the fabrication have been created.

4.1.4.4 Powering Schemes

Carl Haber (Lawrence Berkeley Laboratory)

We have focused on serial powering of actual staves, modules, and hybrids. We have collaborated with RAL on this. RAL designed and fabricated a serial powering pc board which works with the hybrid developed at LBNL. Tests of this system show good analog and digital performance including modules once the system is properly configured. The AC coupling of non zero neutral COM lines is important here and modifications to the circuit were made to handle this in a multi-drop configuration.

The circuit is being adapted and integrated into a new serial powered hybrid design for the 2007 ATLAS specific stave.

A serial powering bus cable for a fully loaded stave is being designed as well. This should handle up to 30 modules.

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

A first prototype of a switch IC for a divide by 4 DC-DC charge pump converter was fabricated with Austria Microsystems through CMP (France). This chip allowed characterization of 50V HV MOS transistors in 0.35um feature size and comparison to models. The relevant on-resistance for this process was found to be 20% higher than the models (which means 20% more silicon areas will be needed for the same current). Unfortunately the chip cannot be used to produce a usable DC-DC converter because parasitic transistors to the substrate create a current path to ground. This was not predicted by the models initially used, but the design kit has been updated since the submission and the new kit includes this effect. An irradiation of these transistors is scheduled for Oct 17 at the LBNL 88" cyclotron. A new test chip is being designed that includes clock drivers as well as switches with proper handling of parasitics. The target submission date is Feb. 07.

4.3 Liquid Argon Upgrade R&D

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Eliminate Layer Effect (Arizona) | 30-Sep-06 | -- | 30-Jun-07 | Delayed (See #1) |
| Design, layout and fab of Link on a Chip (SMU) | 31-Oct-06 | -- | 1-Feb-07 | Delayed (See #2) |

Note #1  This turns out to be an ill-defined milestone, considering our recent discoveries. While we certainly see the "layer" effect at low electric fields, it now appears that we weren't seeing any layer effect at and above the nominal field of 1 kV/mm. But we would like to confirm this with the new sources.

Note #2  Based on the knowledge we learned from the two irradiation tests, we decide to have two designs of the PLL block in order to compare their behavior in radiation environment, and this require extra time. The submission is decided by the foundry multi-project run schedule and the one that is after Oct.-06 is Feb.-07.

4.3.1 Layer Buildup due to Radiation

John Rutherfoord (University of Arizona)

This LHC Upgrade R&D work is on small sections of FCal1 electrodes into which strong Strontium 90 beta sources have been embedded. The strongest source is 50 mCi and it will reproduce the ionization rate expected in an FCal1 electrode at EM shower max at η = 4.7 at the design LHC luminosity. The other electrode has a 2 mCi Strontium 90 source embedded inside to provide a control. A third electrode has no source at all for yet another type of control.

The cryogenic recirculation pump we ordered to improve the argon purity was apparently delivered towards the end of July but we couldn’t find it. Not until last week did it finally show up in another office in the physics building. In the meantime we’ve removed the BNL getter from our apparatus to ship it to Protvino to help purify the argon for our test beam run. It will take quite some time to reconstitute our purification system since the Protvino tests are scheduled in small spurts into 2008.

We have asked the Russian power laboratory to laser weld one dummy source ampoule so that we can assess the quality of the weld. We are concerned about the surface roughness of the electrode rod in the vicinity of the weld. And, of course, the quality of the seal will have a bearing on the assessment of the safety of the source. For this test, however, no source will be enclosed in the cavity. We can perform a bubble test to see if there are any leaks.

The EGS simulation of the source inside the cavity in the electrode rod was finally completed. The result gives the ratio of energy deposited in the gap when the cavity is full of liquid argon to the case when the cavity is evacuated to be almost exactly 0.700. We now have to make our best estimate of this experimentally measured ratio for the two leaking sources. But this simulated value is quite close to the measured value, based on preliminary results.

Most of this quarter has been spent on preparations for our test beam run at Protvino. One goal of this test is to measure the pulse shape from the liquid argon gap as a function of the ionization rate. According to my predictions the triangle pulse shortens quite a bit as the rate goes well above the critical ionization rate. If this part of the Protvino test goes well we should have a very nice measure of the critical ionization rate which then gives the positive ion mobility.

Most of the costs of this test beam run at Protvino are being paid from our M&O funds so I won’t say much more about it in this report.

4.3.2 Readout Electronics

4.3.2.3 Digital Readout System

Gustaaf Brooijmans (Columbia University (Nevis Laboratory))

The receiver board needed for the test setup was built and debugged. It can now operate in synchronization with the transmitter. The test setup now has a transmitter board with an ALTERA Stratix GX FPGA which can be programmed with fake ADC signals and implements the digital logic. The data is sent to the receiver over the optical link at 3.3 Gbps. The receiver then transmits the data to the PCI card in the PC where it is transferred into the PC memory using DMA. This full chain is now operational, although high rate or large data volume tests have not been tried yet.

The PCI Express chip needed to upgrade our DAQ card from PCI to PCI Express became available over the course of the summer and a new card was designed. The design is complete and verified and fabrication has started. To complete the test setup, and ADC board using a TI 8-channel 12-bit ADC has also been designed. This will be fabricated soon.

4.3.2.4 Optical Data Link

Jingbo Ye (Southern Methodist University)

TID test on the SOS 0.25 micron technology was carried out at BNL in July and the result is positive: The test chips withstand 4 Mrad total dose from a Co-60 source. After one month annealing, the chips recovered to the range that are comparable to manufacturing process variations and we conclude that this technology is suitable for upgrade of the LAr readout. It may be able to withstand 100 Mrad total dose because the leakage current and threshold voltage shifts all saturate after about 100 krad. More tests will be need to see if this technology is also suitable for ID upgrade.

The SEE test is planned to be carried out in Boston with the proton source from MGH. The targeted date is Nov. 4. The preparation for this test is on-going.

The design of prototype LOC chip is progressing smoothly. We have finished the PLL design based on the self-biasing technique. The design for LC based PLL is in progress. The design of serializer and clock distribution has been finished. The targeted submission date for LOCV1 is Feb. 07 according to Peregrine's foundry schedule.

4.3.3 Trigger

4.3.4 Next Generation ROD

4.3.4.1 Next Generation ROD (BNL)

Hucheng Chen (Brookhaven National Laboratory)

We started testing Xilinx FPGA with Xilinx ATCA PICMG Design Kit, which includes one Xilinx FPGA-based ATCA 3.0 reference card and development software. With this card we can evaluate the system performance of ATCA platform, especially the serial data transfer rate on the backplane, we can also test the RocketIO speed and DSP performance of embedded PPC 405 core in Xilinx Virtex-II FPGA.

Altera Transceiver Signal Integrity Development Kit was ordered, this card has Stratix II GX FPGA, we will use it to test 6.375Gbps transceiver, Stratix II GX is planned to used in the first version of sub-ROD design. In the mean time, we are continuing the evaluation of DSP performance of the Altera Starix II FPGA.

We started the design of the ROD-tester which will be used to inject data to sub-ROD board collaborating with Univ. of Arizona, the discussion of the feature and interface between ROD-tester and sub-ROD is on-going.

4.3.5 Radiation Hard Low Voltage Power Supplies

4.3.5.1 Radiation Hard Low Voltage Power Supplies (BNL)

Jim Kierstead (Brookhaven National Laboratory)

Continuing with past efforts irradiation measurements of the factorized Vicor product line continue. As reported earlier two of the Vicor products which were irradiated to failure (50-60 krad) were returned to the company. One of the products a 1.5 volt/90amp ( V048F015T090) had a failure mechanism that was not clearly identified. The other was a V048F015T090 (VTM module)/P048F048T24AL (PRM module) combination operated at a modest load. The PRM module failed (was completely dead) but again the failed component was not identified. The controller was removed for further failure analysis. The VTM module was still operational.

Two additional irradiations have been performed at a dose rate of 300 Gray/hour. The first was a PRM/VTM (4 volt, 50 amp output) loaded at 35 - 40 amps. The pair stopped working at a total dose of 520 - 530 Gray, inferring that the behavior in gamma irradiation is not load dependent. In addition a Vicor BCM module was irradiated to failure between 400-450 Grays. This module failed with a shorted input which had not been observed before. Again both of these modules will be sent to Vicor for failure analysis.

Also as reported earlier the switching MOSFETs for these modules were supplied by Vicor on a separate test board. These devices were on continuously and failed to switch at total doses of 3.5x104 -4.5x104 Gray. A test to characterize these devices more completely by switching the gate/load during gamma irradiation at loads of 50 and 100% is scheduled for this quarter. This might reveal a more limiting condition if the threshold voltage changes affects the switching behavior at lower total doses than indicated in the previous tests. Also beam time has been reserved at Massachusetts General Hospital in December to measure Single Event Effects on both packaged Vicor products and single MOSFETs. Other products from other manufacturers will also be tested. This will also indirectly provide information on neutron displacement damage.

4.5 Muon Upgrade R&D

Abraham Seiden (UCSC)

The purchase of the foreseen radiation monitors has been completed and installation and cabling is in progress. This will continue, paced by the actual installation of the Muon system itself.

# Financial Report (Chuck Butehorn, BNL)