Harpers Ferry Center

Fredericksburg and Spotsylvania National Military Park

P.O. Box 50

67 Mather Place

Harpers Ferry, WV

25425-0050

304-535-6436 Phone

304-535-6176 Fax

National Park Service

U.S. Department of the Interior

Fredericksburg, Virginia

Contract Number C1105050001

Order Number ______________

Page 1

1.        	BACKGROUND

Fredericksburg, Chancellorsville, Wilderness, and Spotsylvania - more than 85,000 men wounded; 15,000 killed. No place more vividly reflects the Civil War’s tragic cost, in all its forms. These places reveal the trials of a community and nation at war.

2.	PURPOSE

The purpose of this contract is to provide production of one inkjet embedded in fiberglass wayside exhibit panel, with a thickness of .090, and one duplicate panel for Fredericksburg and Spotsylvania National Military Park, Fredericksburg, Virginia.

3.	SCOPE OF WORK

In accordance with the terms and conditions of the above-referenced contract, the contractor shall provide the National Park Service with all labor, materials, equipment, facilities, and travel necessary to provide one inkjet embedded in fiberglass wayside exhibit panel, with a thickness of .090, and one duplicate panel for Fredericksburg and Spotsylvania National Military Park, Fredericksburg, Virginia.

The contractor shall produce the panels as follows:

Nominal

Exhibit Number and Title			Trim Size		Quantity

Ex 210, Horror on the Orange Plank Road      	36” x 48”	2

The contractor shall provide one full size color proof of the exhibit panel to the Contracting Officer’s Representative (COR) for review and approval.

Contract Number C1105050001

Order Number______________

Page 2

4.	TIME FOR COMPLETION

All work, including Review and Approval specified in Paragraph 5 below, shall be completed on or before July 3, 2007, in accordance with the following schedule:

DESCRIPTION					 NOT LATER THAN

A.	Submission of full size color proof			March 27, 2007

B.	Submission of the production schedule				April 17, 2007

C.	Submission of exhibit panels					   May 22, 2007

D.	Completion of punch-list deficiencies, return of all		     June 19, 2007

Government-Furnished Property and final acceptance

of the work

5.	REVIEW AND APPROVAL

The COR will notify the contractor, in writing, of approval or rejection of the work in accordance with the following schedule:

APPROVAL TIME

DESCRIPTION	(CALENDAR DAYS)

A.	Review and inspection of full size color proof				14 Days

B.	Review and inspection of the production schedule			 	7 Days

C.	Review and inspection of the exhibit panels		     	14 Days

D.	Completion of punch-list deficiencies, return of all	         	14 Days

Government-Furnished Property and final acceptance

of the work

The COR will notify the contractor, in writing, of approval or rejection citing any additions, corrections, or suggestions within 14 calendar days.  Any additions or corrections shall be completed and submitted to the government within 14 calendar days.  In the event the government delays comments beyond the period specified, the contractor will be entitled to a day-to-day extension in the completion date.

Contract Number C1105050001

Order Number______________

Page 3

6.	CONTRACTING OFFICER’S REPRESENTATIVE

The Contracting Officer’s Representative (COR) for the purpose of this contract is:

Bruce Kaiser

National Park Service

Harpers Ferry Center

67 Mather Place, 3rd Floor

Harpers Ferry, West Virginia  25425-0050

Phone: (304) 535-6436

Email:	bruce_kaiser@nps.gov

7.	POINT OF CONTACT FOR DELIVERY

Seven calendar days prior to delivery, the contractor shall contact the COR and advise of exact dates and arrangements made for delivery.

8.	DESTINATION POINT

Upon completion of the work, the contractor shall send the deliverables to the following destinations:

A.		The full size color proof, production schedule and Government-Furnished Property shall be sent to the following address:

National Park Service

Harpers Ferry Center

67 Mather Place, 3rd Floor

Harpers Ferry, West Virginia  25425-0050

Attention:  Bruce Kaiser, COR

Phone: (304) 535-6436

Email:  bruce_kaiser@nps.gov

B.		The exhibit panels shall be shipped to the following address:

National Park Service

Harpers Ferry Center

Central Receiving

401 West Washington Street

Charles Town, WV  25414

Attention: Bruce Kaiser, COR

Phone:  (304) 535-6436

Email:  bruce_kaiser@nps.gov

Contract Number C1105050001

Order Number______________

Page 4

9.	GOVERNMENT-FURNISHED PROPERTY

The contractor shall be responsible for the security and protection of Government-Furnished Property (GFP) furnished to the contractor in connection with this contract.  Following acceptance of all work by the government, the contractor shall return, to the COR, all GFP not incorporated into the exhibit(s).

10.	ATTACHMENTS

The following listed documents are incorporated into this contract as follows:

A.	One CD-Rom which contains the Production Ready Files, dated December 11, 2006

B.	Layouts and Production Notes entitled, “Fredericksburg and Spotsylvania National Military Park,” consisting of two pages, dated December 2006

11.	PAYMENT SCHEDULE

Upon completion and acceptance of all work and receipt of a proper invoice, the contractor will be paid a firm-fixed-price of $______________ in accordance with the following payment schedule:

A.	Upon inspection and acceptance of the full size proof

$         10%

B.	Upon inspection and acceptance of the exhibit panels

$         80%

C.	Upon completion and acceptance of the punchlist deficiencies, return of all GFP and final acceptance of the work

$         10%