# Environmental Management

# Committee Meeting Minutes

# Wednesday, August 20, 2008, 5:30 p.m.

# DOE Information Center

| Committee Members Present | Others Present |
| --- | --- |
| John Coffman Betty Jones Gloria Mei Ron Murphree, Chair Tim Myrick, Vice-chair Bob Olson Maggie Owen Absent Rhonda Bogard Darryl Bonner Claire Campbell Susan Gawarecki Luther Gibson Charles Jensen John Kennerly Lance Mezga Norman Mulvenon Kerry Trammell | Dave Adler, Department of Energy (DOE-ORO) Miranda Clower, ORSSB Spencer Gross, Spectrum Ted Lundy, ORSSAB Bill McKay, EnergX Bill McMillan, DOE |

Operation of TRU Waste Processing Facility

Mr. McMillan began the presentation by saying an additional facility had been built recently at the TRU (transuranic) Waste Processing Center (TWPC) for storing packaged contact-handled (CH) waste to go to the Waste Isolation Pilot Plant (WIPP) in New Mexico for disposition. The facility will also be used for staging incoming waste for treatment from Bechtel Jacobs, Co. (BJC).

Mr. McMillan then introduced Mr. McKay, the EnergX deputy general manager for the TWPC. The main points of Mr. McKay’s presentation are in attachment 1.

TWPC is located on Hwy. 95 about ½ mile north of the bridge that crosses the Clinch River. The work scope for the center includes processing of four waste streams:

- Supernate liquid waste – completed in 2004; 430,000 gallons

- CH TRU debris waste; 1500 cubic meters

- Remote-handled (RH) TRU debris waste; 600 cubic meters

- TRU tank sludge; 2,000 cubic meters.

Processing of CH and RH TRU is currently underway. Processing of sludge is due to begin in 2013. The center has also treated low-level and mixed low-level waste that was sent to the Nevada Test Site for disposal.

Mr. McKay said waste coming from BJC to the center comes from the backside of the Oak Ridge National Laboratory and does not travel over public roads.

CH TRU is defined as having less than 200 millirems of radiation on contact. It can be processed by hand by workers wearing protective suits or using engineered barriers such as gloveboxes. RH TRU is material having readings greater the 200 millirems on contact. It must be handled remotely within a shielded ‘hotcell.’

Mr. McKay reviewed the CH processing activities (Attachment 1, pages 13-16). TWPC has been processing CH TRU since December 2005. A number of enhancement have made at the center including on-site  macro encapsulation, a drum venting system, and additional storage space.

Mr. McKay noted milestones to be met by the end of the fiscal year in September (Attachment 1, page 17-19). Certification for shipment of CH TRU to WIPP is expected in September. The FY 2008 production milestone of 187 cubic meters is behind two to four weeks because of delays in acceptable knowledge reports and waste certification activities running behind. Mr. McKay said an additional shift will be added to get the schedule caught up.

The first shipment of CH TRU to WIPP is scheduled for late September, but shipment can’t be made until certification has been achieved.

TWPC began processing RH TRU in May 2008. Mr. McKay showed a number of photographs of workers remotely handling and packing RH TRU (Attachment 1, pages 20-33). He explained how they remotely cut and package the debris in the shipping containers. The RH Production Status Summary is noted in Attachment 1, pages 34-38. Certification for shipping RH to WIPP is expected in the fourth quarter of 2008.

The FY 2008 milestone for processing 35 cubic meters of RH has encountered a number of challenges. The development of acceptable knowledge reports does not support production goals. Waste from the Radiochemical Engineering Development Center at Oak Ridge National Laboratory was the first to be processed. Development of an isotopic model was problematic so the waste stream was split into three groups – Group 1 was waste generated after 1991; Group 2 was generated between 1979 and 1991; and Group 3 was generated before 1979. Only Group 1 has an isotopic distribution model developed.

The Group 1 casks had high dose waste. The first waste cask was processed without incident. Others had high neutron doses, high decay heat, or exceeded the 72-B shipping cask criteria. This led to a revising of the cask processing sequence. Only 10 of the 17 drums from the Group 1 cask can be shipped.Limited RH storage capacity limits processing.

To mitigate these problems, production has shifted to Group 3 casks, most of which are expected to be CH level waste.

Because of a significant amount of waster found in two of the Group 3 casks it’s expected that most of the waste will be wet and will have to be dried. Mr. McKay said TWPC is working with the Tennessee Department of Environment and Conservation to find a disposition path for the cask water.

Mr. McKay said the sludge will account for about 46 percent of all the remaining waste volume and 72 percent of the remaining waste radioactivity. He said an innovative processing methodology is being developed that will be safer and more reliable. The process design is in the critical decision 1 stage. The plan calls for solidifying sludge rather than drying it, which allows for most of the waste to be sent to the Nevada Test Site as low-level waste. He showed a diagram of the process (Attachment 1, page 41).

Work on sludge will be a 24 hour, 7 day process.

At one point in his presentation Mr. McKay said there could be about 10 percent of waste containers that do not have a disposition path. Mr. Myrick asked if that could be a problem. Mr. McKay said some modification may have to be made but he didn’t expect it to be an expensive problem.

Mr. Myrick asked about operating costs. Mr. McKay and Mr. McMillan said cost across the lifecycle to 2013 is about $500 million. Annual operating costs are about 40 million with the highest being $60 million. The fluctuations are due to the number of shifts.

Discussion of any possible recommendation on presentation

The committee didn’t see a need for any recommendation, but felt periodic updates on the progress of processing and shipping TRU would be useful. An update was placed on the FY 2009 work plan for August 2009.

# Election of chair and vice-chair for FY 2009

# The committee elected the chair and vice-chair for FY 2009. Mr. Myrick nominated Mr. Murphree to serve as chair. Mr. Olson seconded and the Mr. Murphree was elected unanimously.

# Mr. Murphree nominated Mr. Myrick as vice-chair. Mr. Olson seconded and Mr. Myrick was elected unanimously.

# Develop work plan for FY 2009

# The committee developed its FY 2009 work plan (Attachment 2) based on suggested topics by DOE, the Environmental Protection Agency, and the Tennessee Department of Environment and Conservation during the August annual retreat.

Action Items

Closed.

- Mr. Adler will determine if there will be a public comment period on a permit modification to ship remote-handled transuranic waste in lead-lined canisters as contact-handle waste to the Waste Isolation Pilot Plant. Closed. Mr. Adler said there would be a public comment period if a decision is made to follow the proposal, but he said it could be months before a decision is made to do that.

# The meeting adjourned at 7:30 p.m.

# Attachments (2) are available on request from the ORSSAB support office.

# rsg