Proposal to USGS

Cooperative Agreement with University of Georgia

Scientific Oversight and Development of the North American Reporting Center for Amphibian Malformations (NARCAM)

October 19, 2005

Submitted by:

Name: J. Whitfield Gibbons, Ph.D.

Title: 	Professor of Ecology, University of Georgia

Head, SREL Environmental Outreach and Education Program

Savannah River Ecology Lab, Drawer E, Aiken, SC 29802

office 803 725-5852	Fax 803 725-3309	e-mail gibbons@srel.edu

Name: Brian D. Todd

Title: 	Ecology Doctoral Student,

University of Georgia, Savannah River Ecology Lab,

office 803 725-0422	Fax 803 725-3309	e-mail todd@srel.edu

Name: Judith L. Greene

Title: 	Senior Research Coordinator

University of Georgia, Savannah River Ecology Lab,

office 803 725-5988	Fax 803 725-3309	e-mail jgreene@srel.edu

Budget Estimate and Time Period (November 1, 2005 - September 30, 2008)

November 1, 2005 - October 31, 2006 - 	$60,023

November 1, 2006 - October 31, 2007 - 	$73,870

November 1, 2007 - September 30, 2008 - 	$83,875

Overview:

SREL Role

We propose to continue the current and ongoing activities of the Savannah River Ecology Lab (SREL) that involve maintenance of the NARCAM (North American Reporting Center for Amphibian Malformations) web site and scientific oversight of and responses to submitted records. We also propose to increase the utility of NARCAM through involvement with PARC (Partners in Amphibian and Reptile Conservation), directed educational efforts, and interactions with personnel at national parks, state parks, national wildlife refuges, museums, and academic institutions.

SREL has an instrumental role in the technical advisement of the site regarding its usability, format, and structure. We identify critical needs of the scientific community and general public that must be met to optimize the usefulness of the NARCAM site.

Deliverables - Ongoing

1A) To assure NARCAM's effectiveness, SREL will collaborate with USGS to delineate key features used for reporting amphibian malformations, ways to store, access and search past amphibian malformations records, and provide assistance in the design of mapping capabilities of amphibian malformations to inform the public and researchers of known occurrences. This is an ongoing process that continues to shape the NARCAM site.

1B) SREL will continue to serve as scientific reviewers for all incoming amphibian malformation reports. We examine and evaluate each new report and contact report authors when necessary to confirm authenticity or clarify the report contents. This critical activity ensures NARCAM’s continued role as a source for credible data on malformations occurrences.

1C) SREL will continue to serve as reviewers for all malformation information individually tailored for the site, including background information, relevant articles and instructional summaries.

FY2006 – Complete initial review of malformation literature to place on site (1C). Continue activities 1A and 1B.

FY2007 – Complete final revisions of site literature (1C). Continue activities 1A and 1B.

FY2008 – Continue activities 1A and 1B. Amend site literature as new information becomes available (1C).

Deliverables - New

2) An implicit goal of the NARCAM site is to inform and involve the broadest audience possible. To this end, we propose traveling to two national meetings to deliver oral presentations publicizing NARCAM and demonstrating its use as a resource. The first national meeting would capitalize on SREL’s relationship with the group Partners in Amphibian and Reptile Conservation (PARC). PARC has a broad membership base comprising members of the general public and private industry, students, teachers, academic, state and federal agency employees, and many other professionals. We will also coordinate with PARC to publicize the NARCAM product by linking from their amphibian conservation website. We will also present an oral paper at the international Joint Meeting of Ichthyologists and Herpetologists presenting an overview of what kind of research is possible with the NARCAM database. This meeting is attended by academic researchers, professors, and students. Presenting NARCAM to them will increase the visibility of the resource and will also allow us to solicit feedback from an audience that is likely to use the resource so we can continue to improve NARCAM’s functionality.

FY2006 – Travel to PARC National meeting and present NARCAM overview. Develop NARCAM summary and hotlink to publicize on PARC website.

FY2007 – Travel to Joint meeting and present oral paper

FY2008 –  Travel to PARC National meeting and to demonstrate enhanced site to participants; travel to museum collections within the state of Georgia to review collections and acquire additional data for pilot project

3) We propose to enhance NARCAM by generating an instructional package for biology teachers in primary and secondary schools. Students from a biology class were instrumental in bringing the issue of frog malformations to national attention when a group of Minnesota schoolchildren identified several deformed frogs in the summer of 1995. Subsequently, the issue of amphibian malformations and the investigative tale that accompanies it provide an engaging way of educating students about the problem, its proposed causes, and its environmental relevance. The instructional package will provide a historical overview of amphibian malformations, present the proposed causes of malformations, and contain interactive homework questions that will direct students to the NARCAM site for participatory output in order to answer questions about malformation occurrences in their area. Teachers will be encouraged to lead classes in search of amphibian malformations in outdoor activities and submit any malformation reports as a group activity. SREL has a long-standing outreach program that serves primary and secondary schools in the southeastern U.S. through hands-on programs with students and teacher workshops, and is therefore well-suited for the development of a NARCAM instructional package.

FY2006 – Complete draft of instructional package by coordinating with SREL’s on-site outreach educators.

FY2007 – Solicit feedback from teachers during SREL-hosted regional teacher workshops.

FY2008 – Finish revisions of instructional package and host on NBII website. Publicize product and allow downloading of packages for use as classroom activity.

4) We propose to develop a downloadable brochure (PDF) to be hosted on the NBII NARCAM website describing NARCAM and soliciting reports to the database. The intended audience will be national park and wildlife refuge employees, zoological museums, regional herpetological societies, and state park employees as well as the general public. The goal is to increase the awareness of the program and the use of the website as a reporting center.

FY2006 – Design brochure.

FY2007 – Complete draft of brochure.

FY2008 – Begin hosting brochure online at NBII’s NARCAM website.

5) We propose to increase the functionality of the NARCAM malformation database by contacting or visiting museums and zoological institutions to locate historic malformation occurrences that are currently unreported and adding them to the malformation database. We will accomplish this by developing a working strategy for the state of Georgia and then gauging its effectiveness for extrapolation to other states and regions. Our strategy will be: i) to identify all herpetological museum collections within the state, ii) to contact curators and directors of these collections to solicit their help in finding historic amphibian malformations, and iii) to use herpetological societies and university students to review museum specimens for malformations. We will coordinate the efforts and all subsequent data entry of reports.

FY2006 – We will examine all herpetological collections in the state of Georgia to identify unreported historic malformations among preserved specimens.

FY2007 – Deadline for data entry of all findings from statewide program in Georgia

FY2008 – Complete project summary and plan of action for adapting theses methods to other states/regions with the goal of increasing the size and scope of the NARCAM database.

USGS Role

1. USGS hosts the NARCAM Web site as part of the larger National Biological Information Infrastructure (NBII) Web site. USGS will continue to provide hosting, Web development, and technical expertise for the NARCAM Web site and the database of submitted malformations reports.

2. USGS continues to work collaboratively with SREL to increase data and information on malformations phenomena, including development of mapping applications to illustrate graphically the presence and extent of reported malformations.

3. USGS is responsible for maintaining NARCAM’s OMB certification for collection of voluntary reports of malformations observed by the public.

Proposed Budget

Deliverable 	PROJECT	 	FY2006	FY2007	FY2008

1	NARCAM 	Personnel

WEBSITE/	    Graduate Assistants	11870	15213	19255

REVIEWS	Travel 	        0	        0	       0

Equipment/Supplies	        0	    600	  1400

2	PRESENTATIONS	Personnel

Graduate Assistants	2000	2400	2800

Travel 	2800	3600	4400

Equipment/Supplies	      0	      0	      0

3	INSTRUCTIONAL 	Personnel

PACKAGES	  Graduate Assistants	2000	2400	2800

Research Coordinator	2500	4000	3000

Travel 	      0	      0	      0

Equipment/Supplies	3600	2400	1800

4	DOWNLOADABLE 	Personnel

BROCHURES	  Graduate Assistants	2000	2400	2600

Research Coordinator 	3500	3000	3200

Travel 	      0	      0	      0

Equipment/Supplies	1200	2200	3000

5	DATABASE  -  	Personnel

CONTACTS - 	  Graduate Assistants	2000	2400	2600

MUSEUMS,	  Research Coordinator	3500	4000	3000

HERP SOCIETIES	  Clerical 	2000	2600	4000

Travel 	2700	3300	4000

Equipment/Supplies	      0	  900	1000

Staff Benefits		3190	  3796	  3832

SREL Direct		8972	11042	12537

UGA Indirect		6191	  7619	  8651

GRAND TOTAL		60,023	73,870	83,875