Study Title (Protocol Number)

Participant  Recruitment, Retention and Adherence Plan

[Required components of the plan are in bold non-italicized font. Suggested approaches and strategies and study-dependent components od the plan are in italicized font.]

- Pre-initiation phase

  - Determine protocol staff assignments and document assignments

    - Assign dedicated recruitment coordinator

    - Assign alternate recruiters

    - Determine site PI role

      - Determine involvement (e.g., meet with every participant? consent every participant? see participant at every visit? etc.)

      - Assure PI availability to coordinator

      - Give appropriate decision-making authority to coordinator

      - Monitor recruitment

      - Meet w/ protocol staff regularly

    - Plan consistent site staff and trial contacts for patients (e.g., coordinator, PI, receptionist)

  - Evaluate protocol design with respect to “recruitability”

    - Evaluate feasibility of sample size

      - Consider availability of target population considering demographics

      - Consider availability of target population considering eligibility criteria

    - Consider protocol design effects on recruitment

      - Possible effects of placebo

      - Possible effects of  participant access to study drug if it is FDA-approved

      - Possible effects of  potential toxicity

      - Possible effects of complicated entry criteria and burdensome protocol procedures

    - Calculate availability of eligible participants based on

      - Consult with potential participants - consider feasibility study/survey

      - Review patient lists within each practice

      - Review the literature

      - Calculate

        - Number of eligible participants  at each site

        - Estimate number of eligible enrolled participants/ total eligible participants

      - Estimate accrual time (participants/month)

    - Consider protocol modifications (if recruitment goal is unrealistic)

        - Consider broadening eligibility criteria

        - Consider simplifying protocol

        - Consider decreasing sample size

        - Consider extending recruitment period

  - Identify referral sources

    - Contact referral bases

      - Advocates

      - Retirement communities

      - Senior centers

      - YMCAs, JCCs, etc

      - Health clubs

      - MD referrals

      - Churches

      - Community centers

      - Corporate strategies (i.e., enlist endorsement and cooperation from local industry to promote enrollment)

      - Alliances with disease specific organizations

        - Patient advocacy groups

        - Support groups

        - Charitable organizations

    - Cultivate working relationship with non-oncology specialists (e.g., GI, surgery, pulmonologists, ENT, gyn)

    - Survey potential referral doctors, get letter of commitment if possible

    - Re-evaluate sample size

  - Determine and document metrics for evaluation of recruitment and retention performance

    - Plan for quick recognition of lagging enrollment

      - Create and document recruitment timeline with milestones and evaluation points

      - Plan to monitor and document task completion for timeliness

        - Regulatory requirements

        - Weekly meetings

        - Meeting minutes

    - Plan to evaluate and document strategies: outcomes

      - Plan to track number of participants enrolled in a defined time period as a result of each strategy

      - Create screening log forms with attribution to specific strategy and reasons for ineligibility, or non-enrollment

      - Plan to calculate cost of enrollment per participant

      - Plan to maintain and monitor screening/enrollment logs

      - Plan survey of participants’ opinions re: strengths and weaknesses of strategies

    - Plan to track participant withdrawals and reasons for withdrawal

  - Train staff

    - Educate all participating staff re: protocol (after protocol is approved)

    - Develop and distribute protocol pocket cards

    - Provide Frequently Asked Questions document

    - Train support staff

      - Smooth clinic flow and hospitality

      - Procedural requirements (e.g., fasting)

      - Prepare procedures for when protocol is violated

    - Prepare script of protocol explanation

  - Promote comfortable and pleasant clinic environment/experience

    - Supply driving directions to schedulers

    - Coordinate well-organized clinic flow

    - Assure user-friendly test scheduling, drug dispensing, etc

    - Negotiate (if possible, insist upon) flexible appointment times (i.e., more than one day per week)

    - Plan to allow ample  time for participants with the clinical trial staff

    - Schedule periodic meetings between the clinic coordinator and the protocol staff meetings

  - Ensure adequate budget

    - Adequately compensate staff

    - Consider recruiter’s transportation to community, meetings

    - Consider participant compensation

    - Cover recruitment, retention and adherence tools (e.g., newsletter, mailings, protocol pocket cards, participant visit calendars, etc.)

  - Determine recruitment and retention strategies based on evaluation of protocol, target population, clinic, referral sources

    - Contact and inform referral sources

    - Advertisements

      - Newspaper

      - TV

      - Radio

      - Internet

      - Direct mailings

    - Public relations

      - Investigator interviews

      - Patient education

        - Investigator or coordinator educational sessions to relevant community

        - FAQ documents

    - Recruiters/study staff support

      - Newsletter for study sites/ consortium

      - Teleconferences for study sites/consortium

      - Recognition of  high recruiters (within consortium or study site)

      - Frequent contact with participating site coordinators

    - Minority recruitment strategies

      - Perform cultural assessment of local community

      - Consider centralized minority coordinator

      - Consider matched ethnicity recruitment coordinator

      - Have translator available

      - Minority community liaison

      - Meet with minority community leaders

      - Go to community

        - Meetings

        - Churches

- Active recruitment phase

  - Implement strategies as determined during pre-initiation phase of plan

  - Assess eligibility of individual potential participants

    - Begin supportive relationship with patient

    - Consider   poor adherence and retention potential

      - Exclude participants unlikely to comply and stay on study – unless you can provide compensatory support and follow-up

        - Known history of non-compliance/adherence

        - Socially unstable

        - Expressed difficulty with and numerous objections to protocol requirements

        - Cavalier attitude toward protocol

        - Verbalized minimization of cancer risk

        - Verbalized “active drug only”

  - Explore participant’s objections to enrollment

    - Clarify any misconceptions

    - Offer to resolve manageable logistical problems

    - Consider multiple objections as red flag indicating possible retention/compliance problems

  - Involve participant’s social network in decision-making

  - Continuously evaluate strategies as planned during pre-initiation phase of plan

    - Monitor and document task completion for timeliness

      - Regulatory requirements

      - Weekly meetings

      - Meeting minutes

    - Evaluate and document strategies: outcomes

      - Track number of participants enrolled in a defined time period as a result of each strategy

      - Maintain screening/enrollment log forms with attribution to specific strategy and reasons for ineligibility, or non-enrollment

      - Calculate cost of enrollment per participant

      - Survey of participants’ opinions re: strengths and weaknesses of strategies

    - Track participant withdrawals and reasons for withdrawal

    - Rapidly implement modified or alternative plans if recruitment is lagging

- Retention and adherence phase – Be proactive

  - Maintain communication with referring physicians re; participant progress

  - Establish and maintain rapport among staff during follow-up

    - Newsletter

    - All-site teleconferences

    - Buddy system among coordinators

    - Adequate staff compensation

    - Staff recognition/awards

    - Clinic non-protocol staff recognition

  - Establish and maintain rapport and communication with participants

    - Identify and track attrition red flags

      - Adverse effects

      - Missed appointments

      - Frequent appointment time changes

      - Major personal or family events

      - Health deterioration

      - Loss of support system

      - Do not promise support that cannot be maintained

    - Adverse effects (AEs)

      - Inform patients as to what to expect

      - Have prepared AE management protocol

    - Maintain current contact info

    - Enlist support of participant’s social network

      - Transportation

      - Encouragement

      - Agent compliance

    - Consider establishing a  support group

    - Provide remuneration as budgets permit

      - Parking

      - Time lost from work

      - Transportation

      - Child care

    - Ensure pleasant clinic visits

      - Limit waiting room time

      - Coordinate assessments (e.g., Blood work, imaging, etc.) with visits

      - Provide refreshments

      - Flexible scheduling

      - Toll-free numbers

    - Ensure consistent staff contact person and access to PI

    - Establish schedule for contact with patient

    - Consider retention tools

      - Calendars

      - Newsletter

      - Appointment reminder cards and calls

      - Anniversary cards

      - Certificates of appreciation and appreciation

      - Tee-shirts, mugs, magnets

      - Buddy system

      - Support groups