TABLE OF CONTENTS

EXECUTIVE SUMMARY	ES-1

1.0	Debriefing Overview	1-1

1.1	Introduction	1-1

1.2	Background of Race and Ethnic Advisory Committees (REAC)	1-1

1.3	Race and Ethnicity Advisory Committees Debriefing Scope	1-2

1.3.1	REAC Debriefing Topics	1-2

1.4	Booz·Allen & Hamilton Facilitation Methodology	1-5

2.0	Summary Discussions	2-1

2.1	Summary of Priority Issues	2-1

2.1.1	African American Advisory Committee Priority Issues	2-1

2.1.2	American Indian & Alaska Native Advisory Committee Priority Issues	2-3

2.1.3	Asian Advisory Committee Priority Issues	2-4

2.1.4	Hispanic Advisory Committee Priority Issues	2-5

2.1.5	Native Hawaiian and Other Pacific Islander Advisory Committee Priority Issues	2-5

2.2	Successes, Lessons Learned and Areas for Enhancement Summary	2-8

2.2.1	African American Advisory Committee Summary	2-8

2.2.2	American Indian and Alaska Native Advisory Committee Summary	2-14

2.2.3	Asian Advisory Committee Summary	2-20

2.2.4	Hispanic Advisory Committee Summary	2-30

2.2.5	Native Hawaiian and Other Pacific Islander Advisory Committee Summary	2-36

2.3	Common Themes	2-42

2.4	Conclusion	2-42

Appendix A – African American Advisory Committee	A-1

Appendix B – American Indian & Alaska Native Advisory Committee	B-1

Appendix C – Asian Advisory Committee	C-1

Appendix D – Hispanic Advisory Committee	D-1

Appendix E – Native Hawaiian and Other Pacific Islander Advisory Committee	E-1

Appendix F – Acronym List	F-1

# EXECUTIVE SUMMARY

Over the past several months, the U.S. Census Bureau (Census Bureau) conducted several formal internal debriefing sessions for Census 2000.  These sessions were designed to provide input into the 2010 Census planning process by gaining insight into successes, lessons learned and areas for enhancement from Census 2000.  The output of the debriefing sessions will be used to help the Census Bureau identify potential cost savings, operational, technical and coverage improvements for the reengineered 2010 Census.  As part of this debriefing strategy, the Census Bureau debriefed its Race and Ethnic Advisory Committees (REACs) on June 19 and June 20, 2001 at the Sheraton Reston Hotel in Reston, Virginia.

The five REACs represent several distinct populations: the African American Population, the American Indian and Alaska Native Populations, the Asian Population, the Hispanic Population and the Native Hawaiian and Other Pacific Islander Population.

The REAC members were debriefed on six critical Census 2000 topic areas—

Partnership Program

Recruitment and Hiring Initiatives

Master Address File/TIGER Database (MAF/TIGER)

Paid Advertising Campaign

Data Collection Strategies

Language Program.

REAC members were asked to focus on the following three areas—

Census 2000 Successes

Census 2000 Lessons Learned

Census 2010 Areas for Enhancement or Improvement.

Near the end of the 2-day session, REAC members were asked to look across all of the Census topic areas to identify priority concerns and report these during a closing plenary session. The plenary session debriefing included many common themes such as—

Greater diversity in management, mid-level and entry-level positions at Census headquarters in Suitland, Maryland

Better use of technology

Advancement and maintenance of Census outreach programs

A desire to start all Census programs as early as possible

Improved and increased communication among internal Census Bureau departments and partners

Increased funding for local and regional level outreach programs

Need for bilingual and bicultural enumerators.

The remainder of this report includes the successes, lessons learned, and areas for enhancement at a summary level with details for each topic area by Committee included as Appendix A through Appendix E.

# 1.0	Debriefing Overview

## 1.1	Introduction

On June 19 and 20, the five committees that comprise the Census Bureau's Race and Ethnic Advisory Committees (REACs) were debriefed on their views of six Census 2000 programs and initiatives.  The sessions were held at the Sheraton Reston Hotel in Reston, Virginia.  The information gathered from these facilitated debriefing sessions will be used as a part of the Census 2010 planning process.

Section 1 of this report describes the background of the REAC, identifies the scope of the debriefing sessions, describes the topics discussed at the sessions, and outlines the methodology used to debrief the REACs.

Section 2 gives an overview of the priority issues highlighted by the REACs, presents a summary of the discussions that took place during the 2-day sessions and summarizes the common themes discussed throughout all five REAC breakout sessions.

## 1.2	Background of Race and Ethnic Advisory Committees (REAC)

The REAC consists of five committees with representatives from several distinct populations: the African American Population, the American Indian and Alaska Native Populations, the Asian Population, the Hispanic Population and the Native Hawaiian and Other Pacific Islander Population.

Each REAC was chartered to provide an organized and continued channel of communication between the respective REAC populations and the Census Bureau.  Census 2000 challenges faced by the Committees included reducing the differential undercount for all population groups, and suggesting ways that Census data could be disseminated to the respective committee populations and other users, for maximum usefulness.  The REAC was also chartered to provide advice regarding tabulation plans for race and ethnic data.

The REACs were chartered to consider the goals of the decennial census when evaluating user needs for data provided by that Census.  Additionally, the Committees provide perspective concerning the research and design plans for the American Community Survey (ACS), the 2010 Decennial Census, and other related decennial programs.

The Committees function solely as an advisory body and are to comply fully with the provisions of the Federal Advisory Committee Act.

## 1.3	Race and Ethnicity Advisory Committees Debriefing Scope

The REAC members were debriefed on six critical Census 2000 topics—

Partnership Program

Recruitment and Hiring Initiatives

Master Address File/TIGER Database (MAF/TIGER)

Paid Advertising Campaign

Data Collection Strategies

Language Program.

Each of the six debriefing topics is described in more detail below.

### 1.3.1	REAC Debriefing Topics

##### Partnership Program

The Census Bureau formed partnerships with external stakeholders to—

Increase the overall response rate for Census 2000

Reduce the undercount of racial and ethnic groups and other hard-to-enumerate populations

Communicate a consistent Census message to all Americans.

Census 2000 partners included State, Local, and Tribal governments, community-based organizations, small businesses, rural community groups, media organizations, national affiliates, and faith-based organizations.

The Partnership Program allowed each partner to develop programs that were targeted to their specific populations.  Community outreach and education programs were combined with marketing, grassroots organizing, and special events to broaden the Census message to all segments of the U.S. population.

##### Recruitment and Hiring

The goal of the Recruitment and Hiring initiative was to hire and train a diverse, temporary workforce in sufficient numbers to complete Census 2000 operations on schedule and within budget.  The Census Bureau established a field network of 520 Local Census Offices (LCOs) and 12 stateside Regional Census Centers (RCCs) to carry out its recruitment and hiring mission.  Census 2000 recruitment and hiring strategies included hiring a diverse workforce, establishing a regionally competitive pay rate, and hiring employees who work where they live.

##### Master Address File/TIGER Database (MAF/TIGER)

Developing a reliable address file was an important requirement of Census 2000.  During Census 2000, the Census Bureau identified all living quarters, created a Master Address File (MAF) and linked the living quarters to a geographic database called the TIGER Database.  The Census Bureau's MAF/TIGER initiative involved partnership programs with other Federal, State and local agencies, Tribal governments, regional planning agencies, the private sector and community-based organizations.

The following are a list of Census 2000 MAF/TIGER initiatives—

Address List Development and Questionnaire Delivery – This program used various methods to develop the MAF and deliver questionnaires.  The methods used included Block Canvassing, Address Listing, Update/Leave procedures and List/Enumerate procedures.

Local Update of Census Addresses (LUCA) – This program used Tribal and local knowledge to review the MAF and provide input regarding its accuracy and completeness.

Legal Boundary Designations – Tribal and local officials helped the Census Bureau obtain accurate boundary information for local jurisdictions, Hawaiian Homelands, American Indian Reservations and "off-reservation" trust lands.

Statistical Boundary Designations – State, Local and Tribal government partners worked with the Census Bureau to delineate boundaries for a variety of statistical areas including Census tracts and Census designated places.  For the first time, the Census Bureau included a verification step where participating governments could check boundaries in the TIGER Database to ensure the correct interpretation and processing of the boundaries.

TIGER Database Updates – State, Local and Tribal government partners could provide updates to street information in the TIGER Database through map annotation or provision of digital geographic files to the Census Bureau.

##### Paid Advertising Campaign

For the first time, the Census Bureau implemented a paid advertising campaign to promote a decennial census.  The campaign included—

A national media campaign with radio, print and televised advertisements

Targeted advertising strategies

A poster campaign

A Census in Schools program

The Census 2000 Road Show.

##### Data Collection Strategies

In addition to basic data collection methods such as Mailout /Mailback, Update/Leave and List/Enumerate, the Census Bureau used a number of field operations and special enumeration procedures as alternative means to collect Census data.

The following is a list of Data Collection Strategies used by the Census Bureau—

Telephone Questionnaire Assistance (TQA) – The TQA provided answers to respondent's questions regarding the census questionnaire.  Census questionnaires and Language Assistance Guides could be obtained through the TQA.

Questionnaire Assistance Centers (QACs) – QACs were located in public facilities such as churches, convenience stores, libraries, and shopping malls so that residents could obtain one-on-one help filling out the Census 2000 Questionnaire.

The Be Counted Program – This program made census questionnaires available in public locations, such as libraries and post offices, to those who did not receive a census questionnaire.

Non-Response Follow-Up (NRFU) – Four weeks after Census Day temporary Census workers visited and enumerated households at non-responding addresses.

Coverage Improvement Follow-Up – This operation was added after NRFU.  Census workers visited and enumerated addresses that were updated by the U.S. Postal Service, addresses reported as vacant or deleted, and addresses that were added through LUCA appeals or through the New Construction Program.

Special Enumeration Procedures – This program implemented a set of coverage improvement strategies to count people who did not live in traditional housing units, including those who lived in group quarters, those without traditional housing and seasonal farm workers.  Group Quarters enumeration included residences such as nursing homes, colleges and prisons.  Service Based enumeration included residences such as shelters, soup kitchens, mobile food vans, and targeted non-sheltered outdoor locations.

##### Language Program

To motivate prospective respondents to complete the census questionnaire, the Census Bureau created a Language Program to provide Census assistance and information in languages other than English.

The key components of the Census 2000 Language Program are highlighted below—

Advance Letter – Provided potential respondents an opportunity to request an "in-language" questionnaire in Chinese, Korean, Spanish, Tagalog and Vietnamese.

Translations – Translated questionnaire guides were printed in 49 languages ranging from Albanian to Tongan.

Language Assistance Guides – These guides were available on the Internet, through the Telephone Questionnaire Assistance program and were distributed to QACs, LCOs, RCCs and to Census partners.

## 1.4	Booz·Allen & Hamilton Facilitation Methodology

The Census Bureau retained professional facilitation services from Booz·Allen & Hamilton Inc.  (BA&H) in May 2001.

BA&H used the After Action Review (AAR) methodology to debrief the REAC members.  The AAR methodology involves four primary phases: Planning, Preparation, Conduct, and Follow-up.

During the planning stage, BA&H team members met with Census Bureau staff to gather background information on the logistics of the meetings as well as the topic areas and committees.  With a common understanding of the objectives, approach, and topic areas, BA&H selected qualified facilitators and recorders.

During the preparation phase the facilitators and recorders reviewed background information on the Advisory Committee members and Census 2000 programs.  BA&H team members also participated in a training program to ensure each team member collected data in a similar manner and had a full understanding of the Census Bureau's debriefing objectives.  Finally, facilitators arrived at the debriefing site approximately 1hour before the sessions started to prepare the breakout rooms.

Facilitators gathered REAC participant views using the agenda set forth by the Census Bureau.  Each REAC debriefing session lasted approximately 1.25 to 1.5 hours.  For each topic area, facilitators asked for participants’ views on Census 2000 successes, Census 2000 lessons learned and areas for enhancement or improvement of Census 2010.

A BA&H recorder was in each debriefing room to document the views of the Committee members while the facilitator recorded the high level opinions of the participants on flipcharts.  At the end of each debriefing session, participants were asked to prioritize 5 to 7 successes, lessons, or enhancements for the topic area.  Each Committee met to prioritize the 5 to 7 issues that would be reported out during the plenary session at the end of the 2-day debriefing session.

As a part of the follow up phase, the recorders developed summary minutes for each Committee.  These summary minutes are included as Appendix A through E of this report.  These summary minutes are the basis of this Race and Ethnic Advisory Committee Summary Debriefing Report.  In addition to this report, the History Division of the Census Bureau captured formal minutes of the proceedings.  The formal Census Bureau minutes will be available at a later date.

# 2.0	Summary Discussions

This section presents a summary of the discussions that occurred during the two-day Race and Ethnic Advisory Committee (REAC) debriefings on June 19 and 20, 2001.  The views of the five REAC committees are summarized in this section.

The following six topics will be discussed in relation to Committee Member's views on Census 2000 successes, Census 2000 lessons learned, and areas for enhancement or improvement of Census 2010—

Partnership Program

Recruitment and Hiring Initiatives

Master Address File/TIGER Database (MAF/TIGER)

Paid Advertising Campaign

Data Collection Strategies

Language Program.

The views expressed in this section are solely those of the REAC committee members.  The views of Census Bureau staff, non-committee members or Booz·Allen & Hamilton are not reflected in this report.  The views expressed in this section do not necessarily reflect the views of the Census Bureau.

## 2.1	Summary of Priority Issues

Near the end of the two-day session, REAC members were asked to assess all of the Census 2000 debriefing topic areas to identify priority issues and observations. During the closing plenary session the Committee chairperson or spokesperson discussed these issues with the full advisory body and the debriefing attendees.  The priority issues discussed at the plenary session are outlined below.  Two Committees did not prioritize their issues into six topic areas, preferring instead to summarize overall priority areas.

### 2.1.1	African American Advisory Committee Priority Issues

Partnerships

The Census Bureau gained more credibility with race and ethnic groups after Census 2000.

Remember that partnering with human beings is important (technology should not replace human interaction).

Maintain and cultivate partnerships year round.

Provide funding to grassroots groups or organizations.

Maintain current outreach and partnership staff year round in Regional Census Offices.

#### Recruiting and Hiring

Hire a more diverse staff to fill important decision-making positions.

Remove financial disincentives for temporary workers to work for the Census Bureau and enhance the incentives.

Prepare to manage a larger part-time workforce for Census 2010.

Make better use of technology in recruiting and hiring practices.

Use more creative and unconventional methods to recruit and hire a diverse staff.

Publicize high-level Census Bureau positions to race and ethnic groups in forums that specifically target these race or ethnic groups.

Increase racial and ethnic diversity in decision-making positions to obtain a higher quality Census.

MAF/TIGER

Develop strategies to reach private sector postal box users and non-dwelling addresses.

Keep an accurate, up-to-date Master Address File.

Mail Census or Be Counted forms to P.O. boxes and private mailboxes.

Encourage the U.S. Postal Service to provide P.O. box Listings.

Conduct more effective pre-listing to identify P.O. box and private mailbox users.

Paid Advertising

Involve the REAC in the selection of contractors or subcontractors.

The Census Bureau needs a better contracting process for prime and sub-contractors.

Do not always reinvent the advertising campaign; doing so every ten years is wasteful of taxpayer's money.

Create and sell a consistent "brand image."

Make better use of local media in future advertising campaigns.

Evaluate advertising programs to measure the effectiveness of the mediums, languages, and images used in the campaigns.

The Census Bureau should strongly consider hiring a minority firm as the prime advertising contractor (as opposed to a sub-contractor).  This consideration should be based on quality and competency of the firm.

Data Collection

Openness of Bureau to use creative data gathering methods was successful.

Increased Census 2000 participation was due to partnership and paid advertising efforts.

More community groups were willing to use volunteer resources to increase Census 2000 participation.

The 1-800 number did not work effectively because the lines were continuously busy.

Census Bureau should thank U.S. residents and citizens for their participation in Census 2000.

Census Bureau should continue to show how Census participation would help citizens with local services (e.g., schools and roads).

Census Bureau should look into other Web-based technologies so it can provide additional assistance via the Web.

Census Bureau must apply more targeted resources to QACs and other data collection centers.

Census Bureau must broaden the role of the QACs to include community education and mobilization, not simply questionnaire assistance.

Census Bureau must determine a way to count people not attached to traditional households.

#### Language

The African American Advisory Committee strongly supports an effective Language Program.

Multi-lingual, dual-sided Census forms should be developed.

### 2.1.2	American Indian & Alaska Native Advisory Committee Priority Issues

Census Bureau should reaffirm its commitment to the government-to-government relationships it has with the Tribal Governments.

The timeline of all Census programs and initiatives should be started earlier.

Census Bureau should expand the focus of all decennial planning efforts to include the urban Indian community.

Census Bureau should continuously update geography through the American Community Survey.

Census Bureau must maintain communication with Tribal governments through the Government Liaison Program for the American Community Survey and throughout the dissemination of 2000 Census data.

Census Bureau should build a stronger cultural geographic component at headquarters for the AIAN community.

An increase of American Indian staffing at the regional level is needed to ensure greater and more consistent outreach to the Tribal governments.

Census Bureau should create or expand partnerships to advance each Census 2000 initiative (Recruitment and Hiring, MAF/TIGER, Paid Advertising, Data Collection Strategies, and the Language Program).

### 2.1.3	Asian Advisory Committee Priority Issues

#### Partnership Program

The Committee stressed the importance of the Census Bureau being able to provide adequate funding to local community organizations to assist in the Census.

#### Recruitment and Hiring

The Asian Advisory Committee suggested making additional efforts to recruit a diverse management team at the Census Bureau, specifically at the Senior Executive Service (SES) level.

#### MAF/TIGER

The Committee would like a method to identify and count separately, multiple families living in the same housing unit.

Analyzing demographic characteristics to facilitate targeted mailing.

#### Paid Advertising

The Committee supported making funds available to community-based organizations to spearhead targeted advertising campaigns for specific ethnic groups.

The advertising campaign should include letting the public know that follow-up programs are available to them. (QACs, TQAs, Be Counted)

#### Data Collection Strategies Debriefing

The Committee would like more bilingual Asian personnel to be hired for partnership and field operations to conduct outreach activities, enumerate households, and staff TQA and QACs.

#### Language Program

The Committee would like a targeted mailing of the Census form in Asian languages.

The Committee thought that the capability statements of the TQA and translation contractors should be evaluated more carefully to ensure quality control (e.g., breadth of the languages available).

### 2.1.4	Hispanic Advisory Committee Priority Issues

Early and continuous REAC involvement is necessary in the 2010 planning process.

Increase bilingual and bicultural (Spanish and English) staff within the Census Bureau across all levels, particularly in senior management, and for all programs, including ACS and Census 2010.

Increase all efforts to fully reach all speakers of languages other than English.

- Increase quality assurance for all translations.

- Expand use of in-language material, especially in the American Community Survey.

- Target areas with high concentrations of speakers of languages other than English with the appropriate number of bilingual and bicultural personnel and the use of appropriate in-language materials.

- Test products, services, and initiatives early and often.

Continue and expand partnership programs and add resources for local level participation (regional offices).

Build on successful paid advertising campaign for the 2010 Census and the American Community Survey.

Ensure all the above is applied to the ACS.

### 2.1.5	Native Hawaiian and Other Pacific Islander Advisory Committee Priority Issues

#### Partnership Program

The Committee strongly believed that if more Partnership Specialists were hired, outreach to the NHOPI community would have been more successful.  Partnership Specialists should be community leaders who have established relationships with the NHOPI community.

Encourage strong support from the Census Bureau staff at the headquarters and involve Federal, State Tribal and Local leaders.  Community leaders can stress the importance of the Census and get Pacific Islanders involved.

Support in-kind programs.  The Committee suggested re-structuring the in-kind funding program so community based organizations that help support the Census could apply for in-kind funds or grants.

Start outreach efforts several years before Census 2010 begins.

Establish a local Pacific Regional Office in Honolulu - The Committee strongly believes that establishing a local Pacific Regional Office in Honolulu would more effectively increase the outreach to the NHOPI community.

#### Recruitment and Hiring Program

Pacific Islanders were not represented in Workforce Profile D284. The Committee strongly insists on the addition of NHOPI statistics in this profile.

The Census Bureau should form partnerships with federal government staff who perform job-training services.

Develop action plans with milestones for recruiting, training, and hiring of potentially qualified applicants.  More time is necessary to properly plan for hiring qualified applicants.

Hiring should reflect high-density NHOPI communities.  The Census Bureau could recruit more Census enumerators by hiring Partnership Specialists that reflect the make-up of the community.

More recruiting and advertising targeted toward NHOPI communities are needed.  Advertisements and posters should be in Pacific Islander languages with Pacific Islander faces.

#### MAF/TIGER

Improve communications between MAF/TIGER initiatives and NHOPI Advisory Committee including sharing MAF format of Hawaiian Homelands and choosing a NHOPI point of contact.

Establish a MAF/TIGER Committee with representatives from the NHOPI Advisory Committee and Census staff.  Establishing a point of contact from the NHOPI Advisory Committee would help future MAF/TIGER initiatives on other Pacific Islands.

The Census Bureau should track the mobility and the immigration of Pacific Islanders (especially to the continental U.S.).  By tracking migration of Pacific Islanders to the continental U.S., the Census Bureau would have a better idea where Pacific Islanders are relocating and may have an indication of where the pockets of high-density Pacific Islanders are.

#### Paid Advertising Campaign

The Committee thought that they could have provided value-added support to the advertising campaign.  However, the Census Bureau was late in recognizing the NHOPI Advisory Committee.  (The national advertising campaign for the NHOPI community did not start until 6 months before the Census was to begin).

The advertising campaign had placed advertisements that were uncoordinated, confusing, and that misrepresented the NHOPI community.  (One poster depicted Asians dressed in Pacific Islander clothing, under words that were poorly translated to Samoan).

Advertising must be a national effort, not a local one (think globally act locally).

The Committee thought that advertising should target schools and make NHOPI community more aware about the Census. The campaign should be more educational; make people aware of the importance of the Census and what it means to their communities.

#### Data Collection

The Committee suggested that the Census Bureau use more Partnership Specialists who are trusted and respected by the NHOPI community.

The Committee suggested that the Census Bureau use the NHOPI community's network to get information.  The Census Bureau should use community centers, such as churches, schools, and other community based organizations (CBOs), to collect information.

Mailout/Mailback forms are the least effective in Hawaiian communities because of—

- Language barriers

- Literacy issues

- Confidentiality concerns

- Cultural issues

- Mistrust of government.

Mail-outs should use highly visual stimuli, (e.g., pictures and graphics) and should be simple and colorful.

#### Language Program

Translation of language should be done for accuracy and quality.  The Committee suggested that the Census Bureau establish a translation group with a representative from the NHOPI Advisory Committee.

The Committee suggested that the Census Bureau execute a better plan to allow time for proper translations.  By planning early, the language committee can—

- Identify languages

- Select language committee

- Translate, review and test the material

- Ensure questionnaires are also part of the language process

- Task the NHOPI Advisory Committee for consultation.

The Census Bureau should expand the number of languages in which the Census questionnaire is available beyond the current six.  Target languages by identifying Pacific Islander population clusters (e.g., States of Hawaii, California, Washington, Utah, Oregon, and Texas).

## 2.2	Successes, Lessons Learned and Areas for Enhancement Summary

Highlighted below is a summary of the Census 2000 successes, lessons learned and areas for enhancement or improvement of Census 2010 as cited by each REAC.  Details describing each of the issues highlighted in this section can be found in the summary minutes included in Appendix A to Appendix E of this report.

### 2.2.1	African American Advisory Committee Summary

| Partnership Program - African American Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Partnership Program as a whole was successful. |  | The Census Bureau should not lose focus that it takes people to make the Census a success. |  | Maintain and cultivate partnerships. |
| The Partnership Program gave credibility to the Census Bureau. |  | The Census Bureau should capitalize on technology but not lose sight of the value of partnerships or people. |  | Continue to work with the African American Advisory Committee to enhance the Partnership Program. There is a need for improvement. |
| The Partnership Program successfully increased civic participation. |  | The Census Bureau should maintain its partnerships. It should not be a small peak – big peak activity. |  | Maintain current outreach and partnership staff in Regional Census Offices. |
|  |  | Funding should be provided to grassroots organizations. |  | Build on the successful cooperation between various REACs. |

| Recruitment and Hiring Program - African American Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau used effective means to recruit and hire a diverse workforce. |  | Welfare recipients should have their temporary work income exempt from taxes. |  | Remove financial disincentives to work for the Census Bureau and enhance the incentives. |
| The Census Bureau recruited and hired a diverse workforce. |  | The Census Bureau should hire more minorities to fill important decision-making positions. |  | Prepare to manage a larger part- time workforce for Census 2010. |
|  |  |  |  | The Census Bureau should make better use of technology in its recruiting and hiring practices. |
|  |  |  |  | The Census Bureau should use more creative and unconventional methods to recruit and hire Census workers. |
|  |  |  |  | Target advertisements of high-level Census positions to racial and ethnic groups in ways that will reach the racial and ethnic groups. |
|  |  |  |  | Increase racial and ethnic diversity in decision-making positions to obtain a higher quality Census – not for purposes of affirmative action. |

| MAF/TIGER Program - African American Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| Coordination with the USPS was successful. |  | Develop strategies to reach private sector mailbox users and non-dwelling type addresses. |  | The Census Bureau should mail Census or Be Counted forms to P.O. boxes and private mailboxes. |
| The Census Bureau did a good job standardizing the geographical mapping of residential addresses. |  | Keep an accurate and up-to-date Master Address File. |  | The Census Bureau should encourage the USPS to provide them with P.O. box listings. |
| The LUCA program was effective. |  |  |  | Conduct a more effective pre-listing of addresses to identify P.O. box and private mailbox users. |
|  |  |  |  | As commercial mail use increases (e.g., MailBoxes Etc.) the Census Bureau must find better ways to capture where people live. |
|  |  |  |  | The LUCA effort requires better planning. |

| Paid Advertising Program - African American Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau undertaking of the paid advertising campaign was an overall success. Previous advertising campaigns were conducted in a less than strategic manner, via public service announcements, and not well targeted to minority populations. The paid advertising campaign for Census 2000 addressed advertising deficiencies experienced in previous Censuses. |  | The Census Bureau needs a better contracting process to select prime and subcontractors. |  | Use consistent branding for the Census. |
| Census posters were well received by the African American community. The posters resonated with African Americans, thereby heightening their awareness of Census 2000. |  | The Census Bureau should have minority decision- making representatives to facilitate the selection and efforts of the minority public relations contractors. |  | The Census Bureau should make better use of local media. |
| Ensuring that Young & Rubicam select subcontractors that possessed the required knowledge, expertise, and cultural sensitivity towards minority populations to make the paid advertising campaign successful. |  | Recreating the Census image every ten years is wasteful of taxpayer money. |  | Begin using after-action evaluations to measure effectiveness of processes and procedures. |
| Chisholm-Mingo brought to bear the understanding of various racial groups to assist in developing culturally sensitive and targeted advertising material. |  | Lack of consistent branding results in the Census Bureau creating a new and different identity and image for each Decennial Census. |  | The Census Bureau should strongly consider minority-based firms as prime contractors, not just subcontractors. This should be based on quality and competency. |
|  |  |  |  | Develop advertising material that is more targeted, politically correct and culturally sensitive. |

| Data Collection Program - African American Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The openness of the Census Bureau to use creative data gathering methods was a success because new methods were used. |  | The 1-800 number was not effective. The lines were continuously busy and often provided incomplete or incorrect information. |  | The Census Bureau should look into other Web-based technologies so it can provide additional assistance via the Web. |
| There was increased data collection and participation due to partnerships and advertising. |  | The Census Bureau should thank citizens for their participation in the Census. |  | Apply more targeted resources to QACs and other data collection centers. |
| More community groups were willing to use volunteer resources to increase participation. |  | It was effective to show how Census participation will help citizens with local services such as schools and roads. |  | Broaden the role of the QACs to include areas such as community education and mobilization. |
|  |  |  |  | Consider ideas on how to count people not regularly attached to households (i.e., homeless, mentally ill, or recluse.) |

| Language Program - African American Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Language Program successfully reached out to a broad, diverse group of languages. |  | The mailing of Census material should be more targeted. |  | The Census Bureau must perform a quality assurance check on the work performed for them by contractors. |
| The Committee was pleased with the work of the Chisholm-Mingo Group. |  |  |  |  |

### 2.2.2	American Indian and Alaska Native Advisory Committee Summary

| Partnership Program – AIAN Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The building of relationships between Tribal governments and the Federal Government was successful. |  | Complete Count Committees should be an ongoing process. |  | An increase of Native American employment in management positions at the regional level would help strengthen partnerships. |
| Government Liaison Programs were successful. |  | Maps were given to AIAN representatives too late for review and submittal by the Census Bureau deadlines. |  | The Census Bureau should assist in creating Partnership Programs with the AIAN urban community. |
|  |  | There was no point of contact within the Census Bureau exclusive to the AIAN community. |  | The amount of funding for the AIAN community should be increased. |
|  |  |  |  | Better communication is needed among the Census Bureau's own divisions. |
|  |  |  |  | The entire Partnership Program needed to start earlier. |

| Recruitment and Hiring Program – AIAN Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Recruitment and Hiring program demonstrated flexibility by its ability to adapt to different regions. |  | The Census Bureau front-loaded too many applicants. |  | The Census Bureau should increase local advertising related to Census job opportunities. |
| The Census Bureau was more effective in meeting payroll on time, most notably with field enumerators. |  | The Census Bureau was not able to recruit enough local speakers, perhaps resulting from low wages. |  | Increase number of American Indians in management positions at the Census Bureau headquarters. |
| For the first time, the Census Bureau hired local private contractors for dissemination of paid advertisement of recruiting needs to the local media. |  | The Census Bureau lacked a pro-active and energetic recruiting pitch. |  | Employees need more training on what the Census Bureau expects from them. |
| The Welfare-to-Work program provided opportunities for employment without penalty for federally assisted citizens. |  | The recruitment and hiring process started too late. |  | Wages should be higher in certain areas. |
|  |  |  |  | Potential candidates for the Welfare-to-Work program should be more informed regarding the benefits of income exclusions. |
|  |  |  |  | The Census Bureau should promptly inform job applicants about their employment status. |

| MAF/TIGER Program – AIAN Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Geography staff was able to make several adjustments after the 1990 Census. |  | The LUCA Program started too late. |  | An overall introductory statement is needed to describe what the Tribal role is in the LUCA initiative. |
| The LUCA Program was sited as an overall success. |  | Tribal Governments were not sure of their responsibilities for the LUCA Program. |  | LUCA Program timelines should be started earlier in the process. |
|  |  | Maps and addresses issued and/or used by the Census Bureau were too general. |  | Tribes should be consulted and involved when the Census Bureau is deciphering Tribal or legal boundaries. |
|  |  | Tribal boundaries that run over state lines should be clarified. |  |  |

| Paid Advertising Program – AIAN Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau was successful in funding separate advertising campaigns for several race and ethnic communities. |  | The Paid Advertising campaign started too late. |  | The Paid Advertising campaign should start earlier in Census 2010. |
| The print media, radio and television advertisements were all successful. |  | The AIAN community experienced excessive bureaucracy when it came to suggesting changes to the AIAN advertising campaign. |  | Advertisements should be more specific to each American Indian community and should include the urban communities of American Indians. |
| The Partnership Program had its own budget for advertising. |  | Alaska natives were not represented properly in the advertising campaign. |  | The Census Bureau should use more free publicity to increase Census awareness in addition to the Paid Advertising campaign. |
| The Committee was given the opportunity to work with the Census Bureau to develop the advertising campaign. |  |  |  |  |

| Data Collection Program – AIAN Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Committee deemed the data collection strategies of the 2000 Census a success. |  | Telephone Questionnaire Assistance (TQA) and Questionnaire Assistance Centers (QACs) were not effective for the AIAN community. |  | QACs located in border towns nearby reservations must reach out to the AIAN community. |
| Increased automation at Local Census Offices eased the data collection process. |  | The Census Bureau did not properly count transient AIAN citizens. |  | To gain an accurate count of serviced-based citizens, the Census Bureau should target communities of faith to assist with education and enumeration procedures. |
| The Census Bureau's coverage of the Navajo tribe was an improvement. |  | The List/Enumeration procedure is essential when enumerating on American Indian reservations. |  | The List/Enumeration procedure should continue to be used when enumerating on American Indian reservations. |
| The Non-Response Follow-Up (NRFU) procedure was a success. |  |  |  |  |

| Language Program – AIAN Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The interpreters provided by the Census Bureau were a good start for the Language Program. |  | Native American languages are becoming extinct because of the lack of recognition by the Federal Government. |  | The Census Bureau should recognize American Indian languages that have significant speaking populations. |
|  |  | The Census Bureau focused on other languages and not the numerous American Indian languages that are native to this country because the communities that speak these languages are small. |  | The Census Bureau should work with tribes to determine if there is a way to preserve the languages native to the tribes. |
|  |  | Cultural diversity is missing from the Census Language Program. |  | A strong cultural geographic component at the Census Bureau headquarters would help cultural differences between the Census Bureau and the AIAN community. |

### 2.2.3	Asian Advisory Committee Summary

| Partnership Program – Asian Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Committee believed partnerships allowed the Census experience to be more personal and intimate for Census participants. |  | The complete commitment of the partner, as well as the regional director, is necessary for the success of the Census. |  | The quantity of community specialist positions available should be increased. |
| The partnership program's ability to build awareness of the Census before Census Day was excellent. |  | The quantity of area covered by each area specialist was too large. |  | During the recruitment process, more Asians should be hired as community specialists. The Census Bureau also should hire a larger number of Asian Partnership Specialists, particularly for high-density areas such as New York and Los Angeles. |
| The partnership program built awareness of the Census, thus increasing the Census count throughout the country. As a result, participation of the hard-to-reach populations was also increased. |  | Balance is needed between a targeted Partnership Program versus a general approach. |  | The Census Bureau should publicize the contact list of the Partnership Specialists more widely so that the Partnership Specialists can be reached more easily. |
| Asian Community Specialists were hired to help build awareness. |  | Census awareness may not translate into the action of returning a Census form. |  | Additional funding for community-based organizations is needed. |
| The Partnership Program provided credibility to the community based organizations involved in the Census. |  | The Census Bureau should clarify the requirements necessary to become a partnership or community specialist. For example, clarify if U.S. citizenship is required to qualify a person as a partnership or community specialist. |  | The Census Bureau should put an infrastructure in place to distribute the partnership information more easily. |
| Partnership Program Continued – Asian Advisory Committee |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
|  |  | It took newly hired specialists a long time to build contacts with the community. |  | The Census Bureau should consider community service in addition to professional employment when hiring community specialists. |
|  |  | The Committee noted that the communities expected more from the partners than they could deliver or were expected to provide. In addition, the number of partners was not great enough to meet the needs of the community. |  | Partners should have a clearer understanding of their responsibilities and the resources available to them. |
|  |  |  |  | Positions should be open to U.S. citizens and legal residents. |
|  |  |  |  | The Partnership Program should be a continual process. The Census Bureau should maintain a full time specialist year round to establish continuity and to maintain the relationship with community. |
|  |  |  |  | Feedback on the evaluation of the program from the specialists is needed to understand the level of service provided. |
|  |  |  |  | All specialists should have periodic contact before, during, and after the Census with the Asian Advisory Committee for feedback and evaluation. |
|  |  |  |  | The Census Bureau should include schools in the Partnership Programs to distribute information to students. |

| Recruitment and Hiring Program – Asian Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| Awareness of the Census 2000 recruitment program was high. |  | The Census Bureau did not provide adequate expectations or guidance to the hiring managers. |  | The recruitment manual should be published ahead of time and made more widely available to Asian communities. Recruitment manuals should be made available to the REAC for their review. |
| The Census Bureau did a good job retaining temporary employees. |  | The Census Bureau was slow in providing hiring results to people who were tested. |  | The Census Bureau should try to be consistent in its management hiring process. Additionally, the Census Bureau should increase its efforts to recruit a diverse management team. |
| The number of Welfare-to-Work workers hired was good. |  | The more enumerators hired from the ethnic community the better. A familiar face is more trusted so the response rate would be correspondingly higher. |  | Census Bureau positions should be open to both U.S. citizens or legal residents. |
| Overall, the quality of the temporary employees was high. |  | The Census Bureau's employment test was viewed as culturally biased. |  | The Census Bureau employee test should be more culturally sensitive (through question formulation) to minimize cultural bias. |
| The Census Bureau's presence at national level conferences was well received. |  | The English used for the employment test was too difficult for certain applicants. |  | The Committee would like to see an assessment take place of recruitment advertisements. Advertisements should be language specific when targeted toward Asian communities. |
| Job fairs held by the Census Bureau were excellent. |  | The enumerators and the community groups should have a closer working relationship. |  | The Census Bureau should hire recruiters specific to the Asian community. |
| The Census Bureau's recruitment and hiring program reduced the Nation's unemployment rate. |  |  |  | Recruitment should take place at the natural gathering areas for the Asian community (churches, stores, ballroom dances, kareoke bars, restaurants, and conferences). |

| MAF/TIGER Program – Asian Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Committee viewed the overall MAF/TIGER program as a success. |  | The Committee identified issues with the program where there were two different households within the same address. |  | The Census Bureau should correct legitimate duplicate addresses in the MAF. |
| The Census Bureau did a great job of creating and maintaining the MAF. |  | The Census Bureau experienced difficulties in identifying and counting multiple families who lived in the same housing unit. |  | The Census Bureau should be able to create multiple households in the same housing unit for unrelated families. |
|  |  | The Committee noted issues with the delivery of Census forms to people using P.O. boxes. |  | The Committee would like to see the Census Bureau coordinate with the U.S. Postal Service to resolve P.O. box issues. In addition, the Census Bureau should use the U.S. Postal Service file to identify different family names used at the same address. |
|  |  | There was insufficient understanding of Census mapping techniques throughout partnerships, community specialists and professionals in the community. |  | The Census Bureau should use the assistance of landlords to identify multiple families living within a single dwelling. |
|  |  |  |  | The Census Bureau should spend resources to develop new technologies to improve the MAF/TIGER program. |
|  |  |  |  | The Census Bureau should analyze the demographic characteristics of areas with address list deficiencies and problems to identify areas for improvement. |
|  |  |  |  | The Census Bureau should provide a wider understanding of Census mapping techniques targeting partners, community specialists and professionals in each community. |
| Paid Advertising Program – Asian Advisory Committee |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Committee viewed the advertising campaign at the national level as very successful in creating Census awareness. |  | The Census Bureau should target ethnic communities through the use of familiar images in advertising. |  | The Census Bureau should target campaigns to specific Asian groups and utilize images of Asian American heroes. |
| The African American campaign used a talking Census form and civil rights songs, which was very successful. |  | The communities the Census Bureau may be trying to reach may not watch TV or read newspapers. |  | The Committee thought funding should be available to local groups to tailor advertising campaigns. |
| The increased accuracy in the Census count was a result of the advertising campaign. |  | Images and languages from the advertising campaign did not always match. |  | The Census Bureau should employ church groups and other community organizations for the advertising campaign and make advertising materials available to these groups. |
|  |  | Advertising funding requirements are not necessarily the same across minority groups. |  | The Committee would like to see a study conducted to analyze the correlation of the impact of advertising on rates of return. |
|  |  | Awareness did not always translate to returned forms. |  | The Census Bureau should evaluate the effectiveness of targeted campaigns specific to ethnic groups. |
|  |  | The poster selection process was too "hasty." |  | The advertising campaign should inform the public about follow-up programs available to them. Most people did not know about the additional avenues/venues available. |
|  |  | The Census Bureau did not develop region specific advertisements (i.e., urban vs. rural) |  | The Census Bureau needs a distribution strategy and infrastructure for advertising campaign material distribution (timing, resources, and guidance on location to have maximum exposure). |
| Paid Advertising Program Continued – Asian Advisory Committee |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
|  |  | Develop a better strategy to let people know about the additional avenues/venues for completing a Census form. |  | The Census Bureau should use the Internet in 2010 for both the advertising campaign and data collection. |
|  |  | Specialists were not always aware of the details of the advertising campaign (process, budget, and criteria for selection). |  | The Census Bureau should better assess the choice of outlets within each medium in order to advertise to more people (i.e., examine the process being used to choose newspaper A over newspaper B). |
|  |  | Poster distribution was not adequate and mostly stayed in warehouses. |  | Explore the feasibility of using electronic text messaging in promoting the 2010 Census. |
|  |  |  |  | The Census Bureau should study and understand how to target hard-to-reach communities. |
|  |  |  |  | The Census Bureau should hold Asian specific focus groups before and after the advertising campaign development. |
|  |  |  |  | Campaign materials should identify the specialist in the local community by giving their contact information. |
|  |  |  |  | The Census Bureau should go back to the communities after the advertising campaigns are developed to identify translation and/or cultural sensitivity issues. |
|  |  |  |  | Different advertising methods are needed to appeal to intergenerational diversity within an ethnic group. English-speaking advertisements should target 2nd and 3rd generation members of an ethnic group. |

| Data Collection Program – Asian Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Committee viewed the data collection process as very successful for enumeration. |  | The 1-800 number for the TQA program needed to be publicized more widely. The advertising campaign must coordinate with and promote the TQA program. |  | Local Census Offices and local community groups should be provided with a list of QACs in their respective areas. |
| The use of Web sites to report rates of return of Census forms was a success. |  | The Be Counted forms needed to be promoted after Census Day to let communities know that they could still be counted. Confusion over how long people had to return their forms was an issue. |  | The Census Bureau should use a Web page to allow people to check the status of their Census form. |
|  |  | Local Census Offices and local community offices did not have appropriate access to the list of QACs in their areas. |  | The Census form only allows six people to be enumerated on a single form for a housing unit. This should be increased. The Census Bureau should change the form to better capture the additional people in the household via phone, fax, or the Internet. |
|  |  | The Committee would like to see the Census Bureau designate QACs in a more timely manner. |  | The Be Counted program should be expanded to target hard-to-reach communities and it should work closer with community groups. In addition, the advertising campaign should address the Be Counted Program to promote the site location, timing of when forms are available, and the overall coordination process. |
|  |  | Problems arose during the NRFU as a result of the pressure on the LCO to complete the assigned task faster and ahead of schedule. |  | The Census Bureau should evaluate, strengthen, and improve the TQA program to monitor customer satisfaction and the treatment of callers. |
| Data Collection Program Continued – Asian Advisory Committee |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
|  |  |  |  | The Committee would like the Census Bureau to increase the ability of Census participants to file Census forms over the phone instead of making participants wait to get the forms through the mail. |
|  |  |  |  | Bilingual Asian enumerators should be assigned to Asian neighborhoods. |

| Language Program – Asian Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau carried through with their promise to have questionnaires in languages other than English. |  | The Committee commented that there is a difference between conversational and classical or traditional translations of Asian languages, which should be recognized when developing Census materials. |  | The Census Bureau should use Census 1990 data (or other relevant data) for analysis and comparison purposes. |
| The Census Bureau provided Language Assistance Guides in 49 different languages. |  | Translated forms should be evaluated to ensure they are asking for the correct information. |  | The Census Bureau should evaluate the response time between the request and receipt of in-language forms for Census participants. |
|  |  | Census participants experienced delayed responses to requests for in-language forms and guides. |  | The Census Bureau should do a targeted mailing of the Census form in a language other than English to Asian communities, instead of using the current two-step process beginning with the advance letter. |
|  |  | Language assistance guides were printed, but distribution problems existed. |  | The capabilities of the contractors should be evaluated more carefully to ensure credibility and breadth of languages. |
|  |  | Census participants had to rely on receiving the advance letter to request an in-language form, which is an ineffective two-step process. |  | To reach hard-to-reach Asian populations, multi-lingual advertising materials should explain why the Census process can be trusted by members of the Asian Community. Advertisements must address the "trust issue" with this population. |
|  |  | The literal translation of the Census forms created misunderstandings, instead of clarity, for the Asian community. |  | The Census Bureau should put two forms (in different languages) in the same envelope to target specific ethnic communities. |
|  |  |  |  | The Census Bureau should explore the use of more languages for the Census form. |
| Language Program Continued – Asian Advisory Committee |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
|  |  |  |  | The Census Bureau should print language specific messages on the outside of the advance letter envelope. |
|  |  |  |  | The Census Bureau should establish quality control standards for language translations. |
|  |  |  |  | A pre-testing of the Census form should occur with each language group after it is translated. |

### 2.2.4	Hispanic Advisory Committee Summary

| Partnership Program – Hispanic Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau, as well as Local governments, provided increased support and resources toward the Partnership Program. |  | The Hispanic Advisory Committee suggested that the Census Bureau use Partnership Programs better during Non-Response Follow-Up (NRFU) to create continuous awareness and advertising that the Census was not over. |  | The Committee suggested that a new acronym for the Non-Response Follow-Up (NRFU) be used so that it can be more easily advertised. |
| The use of multi-lingual programs (e.g., staff and advertisements) increased the success of the Partnership Program. |  |  |  | The Census Bureau should create a Census month or season instead of just a Census Day. |
| The Partnership Program increased the relevance of Census 2000 at a local level. |  |  |  |  |

| Recruitment and Hiring Program – Hispanic Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| Removing the hiring priority for U.S. citizens was a success because the Census Bureau could hire local legal residents who were representative of their communities. |  | Census Bureau staff at all levels did not and does not reflect the racial or ethnic diversity of the U.S. population. As a result of insufficient representation, decisions for Census 2000 were made that were not sensitive to the needs of the Hispanic population. In the few cases where Census Bureau staff reflects the diversity of the U.S. population, cultural sensitivities were taken into consideration and programs were generally effective. |  | A performance standard should be established to measure the success of having a diverse staff. Measurement should take into consideration all aspects of the program, including the person responsible and senior management. |
| The ability to pay prevailing local wages allowed the Census Bureau to obtain and retain more qualified people. |  | There is a need for a dedicated position or a greater capability within the PIO to respond to the needs and concerns of the Latino community (English and Spanish-speaking). |  | The Census Bureau and the Department of Commerce should build a larger pool of bilingual staff members (interns and regular staff) through recruitment and outreach efforts and strategies. |
| The Welfare-to-Work program was a success in Hispanic communities. |  | The 1-800 number did not have a Spanish language capability. |  | The Census Bureau should increase awareness of Census positions and hiring practices through local media and partnership programs. |
| The multi-lingual staffing test enabled more people to apply for a job with the Census Bureau. |  | The Census field offices did not reflect the diversity of the areas in which they were located. |  | The Census Bureau should add a Spanish language capability to the 1-800 number. |
| The advertising and promotion of available Census jobs was successful in informing the Hispanic community about employment opportunities. |  |  |  |  |

Please Note: The Hispanic Advisory Committee was not as familiar with MAF/TIGER Program as they were with other Census 2000 activities. The time spent during the MAF/TIGER debriefing session was used more as a question and answer period).  The Committee asked the Census Bureau resource person several questions to learn more about the program. The Census Bureau resource people recommended the Committee look at the home page of the Census Bureau's Geography Division to learn more about MAF/TIGER and how it operates.  The issues identified in this section arose from the questions answered by the Census Bureau resource person(s).

| MAF/TIGER Program – Hispanic Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| There was much improvement and accuracy in the geographic information for Census 2000. |  | The maps provided on the Geography Division's Internet site were hard to print in black and white. The maps were in color, but many people only had black and white printers. |  | The Census Bureau should create a map index by geography. |
| There was better cooperation from Local governments in Census 2000 than in past Censuses. |  | The Census Bureau needs a better understanding of local Hispanic populations. |  | The Census Bureau should develop the ability to print maps from the Internet in black and white. |

| Paid Advertising Program – Hispanic Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Advertising Program gave tremendous exposure to the Census on both the national and local level. |  | The Census Bureau needed better quality control on translations to avoid conveying the wrong message to diverse groups. |  | Because this was a new joint effort for national awareness, the Census Bureau should capture the knowledge gained through the successes and failures of the advertising campaign. |
| The television commercials were realistic and helped people relate and understand the importance of filling out the Census forms. |  | In some respects, commercials may have promised too much in regard to what people will receive as a result of filling out the Census form. |  | The Census Bureau should hire permanent individuals for the Communication Office and ACS staff that are bilingual and bicultural (Spanish and English) with expertise in advertising and communications. |
| The radio advertisements were effective in rural areas. |  | Primetime coverage and awareness was more effective than off-hour advertising used in the 1990 Census. |  | The Census Bureau should start the advertising process for Census 2010 two to three years earlier than what was done for the 2000 Census. |
| The advertising campaigns were sensitive to several cultural groups throughout the campaign. |  |  |  | Focus groups should be created and used throughout the advertising campaign. |
| Newspaper and magazine coverage was extensive. |  |  |  | The Census Bureau should continue to consult with the Hispanic Advisory Committee (and other REAC Committees) regarding appropriate advertising campaigns. |
| Funding for Census advertising increased the ability to successfully advertise Census 2000 to the population. |  |  |  | The Census Bureau should explore ways to increase the opportunities for smaller Hispanic advertising agencies to address the concerns of the Hispanic community. |
| Feedback and input from the Hispanic Advisory Committee was well received throughout the advertising campaign. |  |  |  |  |

| Data Collection Program – Hispanic Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Non-Response Follow-Up (NRFU) strategy was a successful way to capture additional populations not reached through the regular Census process. |  | Potential respondents should be able to receive in-language questionnaires from the Telephone Questionnaire Assistance (TQA) Line. |  | In-language questionnaires should be provided through the TQA line. |
|  |  | The TQA line should be able to respond to the large volume of calls. |  | QACs should be planned better and site selection criteria for QACs should be more strategic. |
|  |  | The Questionnaire Assistance Centers (QACs) should be more visible and in better locations. |  | The Census Bureau should budget to rent or buy QAC space, if necessary. |
|  |  | The quantity of staff and/or volunteers working at the QACs should be increased. |  | The Census Bureau should budget for more QAC staff. |
|  |  | A risk of duplication exists in the Be Counted Program with children from divorced households and college students. |  |  |
|  |  | The Be Counted Program should be more heavily advertised to be effective. |  |  |

| Language Program – Hispanic Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The incorporation of the mail-back card increased the multi-lingual participation in Census 2000. |  | The Census Bureau should not promise more than it can deliver (i.e., direct mail language forms). |  | All Language Program processes and procedures should be tested early and often. |
|  |  | The advance letter should be multi-lingual. |  | The Census Bureau should utilize the U.S. Postal Service, ACS, Census and other data to locate linguistically isolated populations. |
|  |  | Quality assurance should be tightened for all final translated materials. |  | The Census Bureau should solicit REAC support on the Language Program as early as possible. |
|  |  | There was insufficient testing of direct mail procedures (quantity and timing). |  | The Census Bureau should test for possible resistance to language specific materials prior to launching the Language Program for the next Census. |
|  |  | English and Spanish forms could not be produced and mailed at the same time. |  | Create strong partnerships and develop a budget to help Questionnaire Assistance Centers (QACs) meet the needs of a multi-lingual community. |
|  |  | The Census Bureau needs sufficient data regarding geographically isolated populations to improve the enumeration accuracy. |  | Integrate outreach efforts to speakers of languages other than English from the beginning of the Census 2010 process. |
|  |  | The in-language forms should be used where clearly appropriate. |  | Plan for and hire Spanish-speaking staff in the early stages of the Language Program. |

### 2.2.5	Native Hawaiian and Other Pacific Islander Advisory Committee Summary

| Partnership Program – NHOPI Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The fact that the Census Bureau initiated a Partnership Program in the NHOPI community was considered a success. |  | There was no outreach to Micronesians. |  | Provide incentives such as in-kind funds or grants for vendors to support community based organizations. |
| Census Bureau staff provided strong support to State and Local governments. |  | More time is needed to plan and develop effective Partnerships with state and Local governments. |  | The Census Bureau should hire more Partnership Specialists who are local leaders and are trusted and respected in their communities. |
| The Partnership Specialist in the Los Angeles area was very effective because he was trusted and respected in that NHOPI community. |  | The Census Information Center (CIC) stopped accepting applications for new members because of the Federal Register Notice deadline. |  | The Census Bureau should get more State and local leaders involved in the Partnership Program. |

| Recruitment and Hiring Program – NHOPI Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau provided preparation for the Census 2000 examination. |  | The NHOPI Advisory Committee thought that Pacific Islanders were "appalling absent" in the Workforce Report D-284, dated March 14, 2001. |  | The Census Bureau should place more emphasis on hiring Native Hawaiians and Pacific Islanders locally and nationally. |
| Census training occurred at civic organizations such as churches and schools. |  | A more defined process for applications and feedback to job applicants should be developed. |  | The Census Bureau should form partnerships with Federal Government staff who perform job-training services. |
|  |  | Advertisements and posters are needed in more specific Pacific Islander languages. |  | Use Partnership Specialists to recruit NHOPI citizens in their native communities. |
|  |  |  |  | Develop an action plan to prepare qualified applicants to take the Census exam and prepare for job interviews. |

| MAF/TIGER Program – NHOPI Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The MAF/TIGER Hawaiian Homeland efforts went well. |  | None of the NHOPI Advisory Committee members took part in any form on the MAF/TIGER initiatives. |  | The Census Bureau should establish a point of contact from the NHOPI Advisory Committee to participate in MAF/TIGER initiatives. |
| Census Bureau experts assured the data collected was accurate and concise. |  | The Census Bureau should track the mobility and immigration of Native Hawaiian and Other Pacific Islander to the continental U.S. |  | The Census Bureau should construct a MAF for the Pacific Islands for Census 2010. |
|  |  | The Census Bureau should communicate the enumeration of the Pacific Islands to the NHOPI Advisory Committee. |  |  |

| Paid Advertising Program – NHOPI Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The advertising campaign was well received in Southern California. |  | The advertising campaign was poorly planned and there were budget constraints. |  | The advertising campaign should be a national effort, not a local one (i.e., think globally act locally). |
| The Census Paid Advertising Campaign was open to suggestions by the NHOPI community. |  | The Committee thought that they could have provided value-added support to the campaign. However, the Census Bureau was late in recognizing the NHOPI Advisory Committee. |  | The Paid Advertising Campaign should target schools to educate people about the Census. |
| The State Governments of California and Hawaii participated in the advertising campaign. The California government provided funding for targeted advertising. |  | The Committee was disappointed with the Current Population Survey that did not identify the NHOPI community as a stand-alone demographic, thereby reducing the significance of the community. |  | The Census Bureau should seek leaders in the community to identify culturally sensitive issues. |
|  |  |  |  | The Committee suggested choosing a NHOPI Advisory Committee member to be part of the Advertising Planning Committee. |

| Data Collection Program – NHOPI Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| A Partnership Specialist, who was a minister and a civic leader, guided people to complete questionnaires. |  | The Census Bureau had to enumerate in the Hawaiian Homelands. |  | The Committee suggested the Census Bureau use the NHOPI community's network to obtain relevant information on the community. |
| The long form used for data gathering captured important information for the Census Bureau. |  | Pacific Islanders did not respond well to the Census Bureau mailings because the questionnaire was too intrusive. |  | The Committee suggested the Census Bureau hire more Partnership Specialists who are trusted and respected by the NHOPI community. |
|  |  |  |  | The Census Bureau's mail-outs should be specifically targeted to the NHOPI community to appeal more to the community. |

| Language Program – NHOPI Advisory Committee |
| --- |
| Census 2000 Successes |  | Census 2000 Lessons Learned |  | Census 2010 Areas for Enhancement or Improvement |
| The Census Bureau was successful in recognizing the Samoan language and becoming more sensitive to other languages. |  | The Census Bureau could improve on translations and word usage in its advertising campaigns. |  | The Census Bureau should target desired languages for Census 2010. |
| A Telephone Questionnaire Assistance (TQA) program was established so that respondents could call and request help in a variety of languages. |  | Members of the Advisory Committee could have provided value-added support to language translations. However, the Census Bureau was late in recognizing the NHOPI Advisory Committee. |  | The Census Bureau should establish a Translation Group with a representative from the NHOPI Advisory Committee. |
|  |  | Pacific Islander respondents called the Telephone Questionnaire Assistance (TQA) but were unable to receive assistance. |  | The Census Bureau should execute a better plan to allow time for proper translations. |

## 2.3	Common Themes

In reporting the priority issues during the plenary session, the REAC members presented many common themes. These themes are highlighted below.

All of the REACs expressed the desire to see more diversity in management, mid-level and entry level positions at Census Bureau headquarters.

The Census Bureau should use technology (e.g., text messaging, Global Positioning Systems [GPS], the Internet) to save time, to reduce manual processes and redundancy, and to improve data accuracy.

The Census Bureau should maintain its outreach programs on a consistent, small-scale basis between each Census.

All Census programs should start as early as possible before a decennial census and the Census Bureau should consult with REAC members earlier on all programs and initiatives.

Communication among internal Census Bureau departments and Census partners (e.g., Federal, State, Local, Tribal governments, and volunteers) should be increased and improved.

Quality control procedures should be instituted to review and evaluate subcontractor performance, accuracy of translated materials and applicability of advertising campaigns.

The Advertising Committee and advertising contractors should work directly with the Census Advisory Committees throughout all stages of the paid advertising campaign.

Funding for local and regional level outreach programs should be increased.

Census job applicants should be informed in a timely manner whether or not the Census Bureau will hire them.

Enumerators serving linguistically isolated populations should be bilingual and bicultural and should be placed in the most appropriate regions.

The Census Bureau should continue and expand its working relationship with the United States Postal Service to improve all Census data gathering initiatives and activities.

## 2.4	Conclusion

Overall, the REAC members agreed that Census 2000 was a success and a significant improvement over the 1990 Census.  The Committees urged the Census Bureau to continue to evaluate its Census 2000 programs and initiatives.  They encouraged the Bureau to expand upon the successful Census 2000 programs and initiatives and improve or discontinue the less successful ones.

The members of the REAC were pleased that they were a part of Census 2000 and now, the Census 2010 planning process and encouraged the Census Bureau to continue building relationships with the various Census Advisory Committees to improve Census 2010.

# Appendix A – African American Advisory Committee

# REAC - African American Advisory Committee

# Partnership Debriefing

# Tuesday, June 19, 2001, 1:05 p.m. – 2:35 p.m.

Facilitator and Recorder – Carlton McArthur & Brian Ince

Participants

Dr. Robert Hill – Senior Researcher, Westat

Dr. L. Patricia Johnson – President, Creative Marketing, Inc.

Gwendolyn E. Holmes – Assistant Vice-President, Hancock Bank

Dr. James S. Jackson – Professor, Institute for Social Research

John W. Mack – President, Los Angeles Urban League

Kermit N. Waddell – President/CEO, Economic Development Center of the Carolinas

Barbara Sabol – Program Director, W. K. Kellogg Foundation

Tracey-Ann Nelson – Public Relations/Public Affairs Consultant

Resource Person:

Betty Moohn – Assistant Branch Chief, Partnership and Data Services Branch, Field Division

Renee Jefferson-Copeland – Program Administrator, Customer Liaison Office

Committee Liaison:

Jimmie Scott – Assistant Division Chief, Demographic Statistical Methods Division

# Summary of Issues

# Census 2000 Successful Areas

The Partnership Program as a whole was successful.

The Partnership Program gave credibility to the Census Bureau.

The Partnership Program successfully increased civic participation.

# Census 2000 Lessons Learned

The Census Bureau should not lose focus that it takes people to make the Census a success.

The Census Bureau should capitalize on technology but not lose sight of the value of partnerships and people.

The Census Bureau should maintain its partnerships.  It should not be a small peak – big peak activity.

Funding should be provided to grassroots organizations.

# Ideas to Improve Census 2010

Maintain and cultivate partnerships.

Continue to work with the African American Advisory Committee to enhance the Partnership Program.  (There is a need for improvement.)

Maintain current outreach and partnership staff in Regional Census Offices.

Build on the successful cooperation between various REAC Committees.

# Issues in Detail

# Census 2000 Successful Areas

The Committee stated they witnessed people working together in the Partnership Program, in a joint effort and everyone was willing to work together.  The Partnership Program provided the foundation for the various Census 2000 activities and helped the Census Bureau gain credibility within the African American community.  The African American Advisory Committee was able to put the “seal of approval” on the information distributed to community members and gain their buy-in.  The African American community partnerships provided a means for other community organizations to get involved in Census 2000.

The Committee saw participation rates increase as a direct result of the Partnership Program.  The Committee noticed that across the board the community at large was involved.  People within the community were contacted and directed to act as compared to prior years.

The Committee noticed that the make-up of the Census Complete Count Committees included a more diverse representation of the socio-economic, racial and ethnic community.  There was a mobilization of blacks at both the national and local levels.  African American organizations across the country not only encouraged their communities to participate in the Census but it was believed by the Committee that this same energy lead to increased voter turn out during the Nov 7, 2000 presidential election.  Community education occurred as a result of the established Partnership Program.  Educational programs put in place by the Census Bureau ranged from ‘Census in School Programs’ to educating those in political office.

# Census 2000 Lessons Learned

The Census Bureau must remember that partnerships are based on human interaction and not machines.  The Census Bureau should not lose focus that it takes people to make the Census a success.  Not only in gathering the correct information but, also providing accurate information.  The Census Bureau is a bottom –up organization.

Partnerships helped reemphasize the collection and use of Census data (i.e., where the data comes from, where enumerators must go to collect the data, how the Census Bureau should organize the data, the thought process people use to fill out Census information, and how the Census Bureau should use the data).  As Information Technology advances, the Census Bureau should capitalize on technology as a tool, but not lose sight of the value of partnerships and the people factor.

The Committee recommended the Census Bureau keep the partnerships intact between the Decennial Censuses.  Partnerships should not be a small peak – big peak activity.  The Census Bureau should make an investment in maintaining these partnerships and encourage partnership development across racial and ethnic boundaries.

The Census Bureau should provide specific funding to community-based organizations such as churches, grassroots groups, and QACs by line item.  Over 160 organizations took part in aggressive outreach programs within their community and helped with gathering Census information.  The Census Bureau should encourage States to supplement funding to these organizations.

# Ideas to Improve or Enhance Census 2010

The Committee agreed there is tremendous room for improvement in the Partnership Program but they acknowledged that the Census Bureau has become more responsive to the African American community at large.

The Committee believes the Partnership Program should be started earlier.  Although the Committee saw an increase in partnerships during Census 2000, the Census Bureau started some partnerships too late.  By maintaining these partnerships, the Census Bureau could leverage these relationships with ongoing Census publicity and participation.  In addition, the Census Bureau should maintain outreach staff at current levels and capacity at their regional offices for ongoing Census activities such as the American Census Survey, Current Population Survey, and other monthly activities.

The Census Bureau should build on the successful cooperation that has developed between various Race and Ethnic Advisory Committees.  There was a strong need to maintain and cultivate partnerships between Decennial Censuses; people are an integral part of the Census process and the Census Bureau should remember the lessons learned from Census 2000.  Instead of recreating itself each time, the Census Bureau should continue and enhance the activities that work, and move forward.

REAC - African American Advisory Committee

Hiring and Recruiting Debriefing

Tuesday, June 19, 2001, 2:45 p.m. – 4:15 p.m.

Facilitator and Recorder – Carlton McArthur & Brian Ince

Participants

Dr. Robert Hill – Senior Researcher, Westat

Dr. L. Patricia Johnson – President, Creative Marketing, Inc.

Gwendolyn E. Holmes – Assistant Vice-President, Hancock Bank

Dr. James S. Jackson – Professor, Institute for Social Research

John W. Mack – President, Los Angeles Urban League

Kermit N. Waddell – President/CEO, Economic Development Center of the Carolinas

Barbara Sabol – Program Director, W. K. Kellogg Foundation

Tracey-Ann Nelson – Public Relations/Public Affairs Consultant

Resource Person:

George Grandy – Field Division

Committee Liaison:

Jimmie Scott – Assistant Division Chief, Demographic Statistical Methods Division

Summary of Issues

Census 2000 Successful Areas

The Census Bureau used effective means to recruit and hire a diverse workforce.

The Census Bureau recruited and hired a diverse workforce.

Census 2000 Lessons Learned

Welfare recipients should have their temporary work income exempt from taxes.

The Census Bureau should hire more minorities to fill important decision-making positions.

Ideas to Improve Census 2010

Remove the financial disincentives to work for the Census Bureau and enhance the incentives.

Prepare to manage a larger part-time workforce for Census 2010.

The Census Bureau should make better use of technology in its recruiting and hiring practices.

The Census Bureau should use more creative and unconventional methods to recruit and hire Census workers.

Target advertisements of high-level Census positions to racial and ethnic groups in ways that will reach the racial and ethnic groups.

Increase racial and ethnic diversity in decision-making positions to obtain a higher quality Census – not for purposes of affirmative action.

Issues in Detail

Census 2000 Successful Areas

The Committee remarked that the overall hiring process went well.  The Census Bureau seemed to understand the important role that “field work” plays in conducting the Census.  The Census Bureau hired Census workers from various communities including historically Black Colleges and Universities and the Hispanic Community.  The Committee stated that it was well known that the Census Bureau needed approximately 3.7 million personnel.

It was effective to have recruiters come from the communities from which they were hiring Census workers.  The recruiters had a very good understanding of the qualifications for the various positions they were filling.  Referrals lead to excellent responses from the local communities.  The short time span between referrals, contact with potential employees, and actual acceptance of positions also contributed to the successful hiring process.

The Committee thought placement of staff was appropriate for the enumeration activities.  The Committee stated they saw Spanish-speaking enumerators in Spanish-speaking communities.

The Census Bureau used ingenuity and community sensitivity in locating the appropriate testing facilities for potential Census workers.  The Committee noted for instance that the Census Bureau did not send $300,000 homeowners to an apartment house community center.

Census 2000 Lessons Learned

The Committee noted the Census Bureau hired hundreds of welfare recipients.  The Committee thought that some welfare recipients did not pursue Census jobs because local Social Services offices were not informed that Census income was exempt.  The Committee recommended that welfare recipients should be exempt from taxes on their Census income.  This would encourage more participation by welfare recipients and the elderly.

The 1-800 number used to obtain job information did not work efficiently, because the lines were continuously busy.  The Committee recommended that the Census Bureau install more lines to properly accommodate the volume of traffic.

The Committee remarked that the composition of the regional offices’ staff and their understanding of the workload could indirectly impact recruiting, data collection, and other Census Bureau activities.  The Committee strongly believed that the management staff should reflect the racial and ethnic diversity of the community.  By having a diverse staff, the Census Bureau could provide more effective outreach, orientation, and training programs.

Ideas to Improve Census 2010

In discussing Welfare Reform Legislation, the Committee stated that welfare recipients’ income received from decennial work should not count against Census qualifications.  This legislative change would become an incentive to welfare recipients and provide additional members to the part-time workforce.  Currently, military and retirees are the only community groups exempt to work the Census.

The Committee mentioned the part-time workforce performed most of the work during the Census (especially enumerator activities). A part-time work force also has the largest turnover rate.  On a continuing basis, the Census Bureau could lose over a hundred workers in a given day due to high temperatures and other conditions. The Committee remarked that as the population continues to grow, the Census Bureau will manage an even larger part-time work force.

The Committee recommended that the Census Bureau make better use of technology in its recruiting and hiring practices.  The Committee thought the Census Bureau could use the Internet to make job openings more visible to racial and ethnic groups.

The Committee stated the Census Bureau incorporated unconventional but effective methods into their Census activities.  One member of the Committee saw a Census employee testing twenty people in the back of the local grocery store.  In drug infested communities, the Census Bureau teamed up with local police departments to "take back the streets".  Once local police departments secured these communities, the Census Bureau used local bands and brought in local politicians to heighten the need for completing the Census forms.  Local enumerators "attacked" these communities to account for the cultural subset.  The cultural subset included unmarried men living with unmarried women, the unemployed, criminals, and gangs.  The Committee noted that some gang members were in the 10 to 12 age group and carried guns as an accepted behavior and life style.  Enumerators had to go into hostile areas to account for the homeless, incarcerated, and others not living in conventional tracts.  The Committee recommended that the Census Bureau use more creative and unconventional methods in future Census activities to capture the changing community landscape.

The Committee recommended the Census Bureau publicize headquarters and field management vacancies, and hire racial and ethnic groups into these roles.  By diversifying these management positions, the Committee believed the Census Bureau could increase undercounted group recruitment and make better decisions on recruitment and Census operations.  Several Committee members recommended that the Census Bureau institutionalize a diversified, managerial workforce that included permanent hiring practices and promotions.  The Committee wanted to see more racial and ethnic groups filling the GS 13 through 15 and Senior Executive Service (SES) level positions at the Census Bureau.  The Committee also mentioned that evaluations for exceptional performers should start earlier than at the five year, mid-decennial, period.

Other Relevant Issues

The Committee believed it would be hard to make some enhancements to recruitment since human resources are locally and geographically dependent on the economy.  The Committee cited the unemployment rate and regional wage adjustments as the two primary factors that would influence recruitment.

REAC – African American Advisory Committee

MAF/TIGER Debriefing

Tuesday, June 19, 2001, 4:15 p.m. – 5:30 p.m.

Facilitator and Recorder – Carlton McArthur & Brian Ince

Participants

Dr. Robert Hill – Senior Researcher, Westat

Dr. L. Patricia Johnson – President, Creative Marketing, Inc.

Gwendolyn E. Holmes – Assistant Vice-President, Hancock Bank

Dr. James S. Jackson – Professor, Institute for Social Research

John W. Mack – President, Los Angeles Urban League

Kermit N. Waddell – President/CEO, Economic Development Center of the Carolinas

Barbara Sabol – Program Director, W. K. Kellogg Foundation

Tracey-Ann Nelson – Public Relations/Public Affairs Consultant

Resource Person:

Lornell Parks – Geography Division

Committee Liaison:

Jimmie Scott – Assistant Division Chief, Demographic Statistical Methods Division

Summary of Issues

Census 2000 Successful Areas

Coordination with the USPS was successful.

The Census Bureau did a good job standardizing the geographical mapping of residential addresses.

The Committee thought the LUCA program was effective.

Census 2000 Lessons Learned

Develop strategies to reach private sector mailbox users and non-dwelling type addresses.

Keep an accurate and up-to-date Master Address File.

Ideas to Improve Census 2010

The Census Bureau should mail Census or Be Counted forms to P.O. boxes and private mailboxes.

The Census Bureau should encourage the USPS to provide them with P.O. box listings.

Conduct a more effective pre-listing of addresses to identify P.O. box and private mailbox users.

As commercial mail users increase, the Census Bureau must find better ways to capture where people live.

The LUCA effort required better planning.

Issues in Detail

Census 2000 Successful Areas

The Committee gave high marks to the cooperative working relationship between the Census Bureau and the United States Postal Service.  Committee members remarked that not everyone had the typical mailbox adjacent to or associated with their residential home, townhouse, apartment, or other dwelling place.  Some people use commercial mail boxes such as MailBoxes Etc. and Mailbox USA, because it provides a more secure means of getting mail especially for apartment dwellers, elderly, and/or residents without a "doorman" service.  People from across the economic spectrum use the commercial mailboxes that exist in every city.  People will use these P.O. boxes or commercial mail services for a selection or all of their mail requirements.

The Committee stated that the Census Bureau had an effective Tiger coding.  The Census Bureau did a good job standardizing the geographical and mapping of residential addresses.  The Committee stated they were pleased to observe Census Bureau staff updating old maps and listings.

The Committee commented that the LUCA program was effective.

Census 2000 Lessons Learned

The Committee stated the Field Offices of the Census Bureau worked with their local U.S. Postal Offices to capture current residential addresses.  During Census 2000, the Census Bureau sent enumerators if the Census Bureau did not get a response from their existing mailing list.  The Committee understood the importance of knowing where people live.  Future mailings of the Census Bureau must capture where people live and not just their mailing address.

The Committee stated that the Census Bureau had a daunting task to capture accurate and up-to-date Master Address Files.  As commercial mail users increase, the Census Bureau must find better ways to capture where people live.  The Committee remarked that people could change their physical residence without changing their commercial mail service or P.O. box.

Although there is no way to predict a natural disaster such as hurricane Hugo, the Census Bureau does not have a fail safe method to capture the families impacted from trailer park and/or home destruction.

Ideas to Improve or Enhance Census 2010

The Committee presented the fact that post office box and commercial mail service users did not receive the Census or Be Counted forms.  The Post Office does not provide this information to the Census Bureau due to privacy issues.  The Committee also stated that if someone was on vacation during the Census, the vacationing person(s) did not have their mail forwarded to their vacation location and therefore were not counted.

The Committee recommended that the Census Bureau should deliver Census forms to each post office box and commercial mail service.  The Committee noted that this might cause a duplication error if a given household has more than one post office or commercial mail service.  The Census Bureau must also distinguish between households and businesses using these same services.  The Committee thought a legislative change would encourage the U.S. Postal Service to provide P.O. box listings to the Census Bureau.  The Committee realized that the Census Bureau still should knock on every door to get information.

The Committee presented various examples of persons or families that represent hard-to-count population.  In rural America, we have some places where there are twenty homes per village with only one mailbox.  In another case, migrant farmer workers move from farm to farm to find seasonal work.  In another example, the Committee stated that several African Americans may share quarters with one mailbox.  To capture the number of families and/or persons living in a particular location, enumerators have tried counting water meters or any other means to capture accurate information that the Census Bureau could use.  The Committee stated that confusion existed with college students.  It was unclear to some Committee members how to count family members in college.  The Committee concluded that the Census Bureau needed to develop strategies to reach commercial sector mailbox users and non-dwelling users.  It was suggested that the Census Bureau should conduct more effective pre-listing activities to identify P.O. box and private mailbox users.

The Committee mentioned that the Census Bureau did not provide LUCA participants with feedback even after returns were six months late. The Committee agreed that the Census Bureau must work on planning better future LUCA activities.  Members of the Committee suggested using Intranet resources and other technologies to update LUCA participants.

REAC - African American Advisory Committee

Paid Advertising Campaign Debriefing

Tuesday, June 19, 2001, 8:30 a.m. – 10:00 a.m.

Facilitator and Recorder – Carlton McArthur & Brian Ince

Participants

Dr. Robert Hill – Senior Researcher, Westat

Dr. L. Patricia Johnson – President, Creative Marketing, Inc.

Gwendolyn E. Holmes – Assistant Vice-President, Hancock Bank

Dr. James S. Jackson – Professor, Institute for Social Research

John W. Mack – President, Los Angeles Urban League

Kermit N. Waddell – President/CEO, Economic Development Center of the Carolinas

Barbara Sabol – Program Director, W. K. Kellogg Foundation

Tracey-Ann Nelson – Public Relations/Public Affairs Consultant

Resource Person:

Kim Crews – Branch Chief, Census 2000 Public Information Office

Committee Liaison:

Jimmie Scott – Assistant Division Chief, Demographic Statistical Methods Division

Summary of Issues

Census 2000 Successful Areas

The Census Bureau undertaking of the paid advertising campaign was an overall success.  Previous advertising campaigns were conducted in a less than strategic manner, via public service announcements, and not well targeted to the minority population.  The paid advertising campaign for Census 2000 addressed advertising deficiencies experienced in previous Censuses.

Ensuring that Young & Rubicam select subcontractors that possessed the required knowledge, expertise, and cultural sensitivity towards minority populations to make the paid advertising campaign successful.

Chisholm-Mingo brought to bear the understanding of various racial groups to assist in developing culturally sensitive and targeted advertising material.

Census posters were well received by the African American community.  The posters resonated with African Americans, thereby heightening their awareness of Census 2000.

Census 2000 Lessons Learned

The Census Bureau needs a better contracting process to select prime and subcontractors.

The Census Bureau should have minority decision-making representatives to facilitate the selection and efforts of the minority public relations contractors.

Recreating the Census image every ten years is wasteful of taxpayer money.

Lack of consistent branding results in the Census Bureau creating a new and different identity and image for each Decennial Census.

Ideas to Improve Census 2010

Use consistent branding for the Census.

The Census Bureau should make better use of local media.

Start to use evaluations to measure effectiveness of processes and procedures.

The Census Bureau should strongly consider minority-based firms based on quality and competency; not as an affirmative action requirement.

Develop advertising material that is more targeted, politically correct and culturally sensitive.

Issues in Detail

Census 2000 Successful Areas

In 1990, the Census Bureau used public service announcements and other free advertisements.  The Committee noted that the Census Bureau ran the advertisements during times of low viewer or listener participation.  The advertisements had very little audience appeal since the Census advertisements were not focused on any racial or ethnic community.  The Committee overwhelmingly agreed that the paid advertising campaign definitely made a difference with Census 2000.  Census 2000 represents the first time the Census Bureau paid for advertising.  Members of the Committee remarked that the smallest newspaper and radio stations ran Census advertisements throughout Southeast and Southwest Georgia.  These paid advertisements made the African American community feel a part of the Census.

The Committee stated that the first advertising contractor did "inferior" work.  The advertising materials were demeaning and stereotyped African Americans.  The first contractor depicted African Americans with their hats turned backwards, and women with a large number of children carrying boom boxes.  The Committee stated that it commented on the poor work of the contractor to the Census Bureau, but the Census was not responsive to their concerns.  The Committee then solicited the help of the Black Caucus and asked for feedback on the African American campaign.

The Committee noted that the Census Bureau took quick action to bring in another contractor, The Chisholm-Mingo Group, which was an exemplary performer and won national awards for their Census work.  The Committee highlighted that the Chisholm-Mingo Group worked with the Committee on the advertisement vision and wording for media presentations.  The Chisholm-Mingo Group designed an advertising campaign that better depicted the African American community.  The Committee felt like they were Chisholm-Mingo Group’s clients although the Chisholm-Mingo Group worked for the Census Bureau.  The Committee gave Mr. Chisholm high marks for getting personally involved in the advertising campaign.  The Committee had no interest in reinventing the wheel and suggested that the Census Bureau re-use some of the Census 2000 advertising campaigns.

The Committee remarked that the African American community liked the Census Bureau posters.  The posters showed three to four generations congregating on a porch.  The poster appealed to various ethnic and racial groups since everyone could relate to family unity.

Census 2000 Lessons Learned

1-800 number was not effective because the lines were continuously busy.

The 1-800 staff was not sufficiently trained.

The Census Bureau should thank citizens for their participation in the Census.

It was effective to show how Census participation would help citizens with local services such as schools and roads.  The message that Census participation is a civic duty should be reinforced.

The Census Bureau needs a better contracting process for selecting prime and subcontractors. It was stated that the process was "arcane and inefficient".

The Census Bureau should have minority decision-making representatives facilitate the selection and efforts of the minority advertising and public relations contractors.  The Committee thought this would aid in getting more minority advertising contractors involved in the process.

Ideas to Improve or Enhance Census 2010

The Committee stated that decennial managers try to outperform their predecessors.  The Committee recommended the Census Bureau develop a trademark logo or brand image that everyone can remember.  The logo should have a standardized color scheme.  The Committee used the Uncle Sam theme as an example.  The Committee recommended that the Census Bureau develop a brand and use that brand to the full extent possible during marketing and advertising campaigns.

The Committee recommended the Census Bureau use resources to improve and evaluate the effectiveness of future paid advertisements.  The Census Bureau should use assessment techniques to capture lessons learned.  The Committee thought the Census Bureau could contact the various racial and ethnic groups and get their input on how the paid advertisements worked in their communities.

The Committee stated that minority firms could communicate effectively with everyone and not just within a particular racial and ethnic group.  The Census Bureau should strongly consider minority firms based on quality and competency.  The Committee highly recommended that the Census Bureau seriously consider the Chisholm-Mingo Group for prime contractor for the Census 2010 advertising campaign and any other Census Bureau advertising projects.  The Chisholm-Mingo Group had the creative expertise coupled with a strong understanding of cultural sensitivities.  The Committee highly praised a publication that the Chisholm-Mingo Group put together and recommended that all Census stakeholders get a copy of the Regional Partnership Report – Portrait of America, Vol.  II, 2000, FLD/00-PR2.

The Committee discussed the television, newspaper, and radio media buys made in New York for Census 2000.  The Committee noted that parts of the population were not included in the media buys.  The Committee recommended that the Census Bureau take a closer look at media buys.  In Los Angeles, radio is a better media buy than television listings.  The Committee suggested the Census Bureau develop a better understanding of small stations and how to leverage them in future Census activities.

REAC - African American Advisory Committee

Data Collection Debriefing

Wednesday, June 20, 2001, 10:05am – 11:15am

Facilitator and Recorder – Carlton McArthur & Brian Ince

Participants

Dr. Robert Hill – Senior Researcher, Westat

Dr. L. Patricia Johnson – President, Creative Marketing, Inc.

Gwendolyn E. Holmes – Assistant Vice-President, Hancock Bank

Dr. James S. Jackson – Professor, Institute for Social Research

John W. Mack – President, Los Angeles Urban League

Kermit N. Waddell – President/CEO, Economic Development Center of the Carolinas

Barbara Sabol – Program Director, W. K. Kellogg Foundation

Tracey-Ann Nelson – Public Relations/Public Affairs Consultant

Resource Person:

George Grandy – Field Division

Committee Liaison:

Jimmie Scott – Assistant Division Chief, Demographic Statistical Methods Division

Summary of Issues

Census 2000 Successful Areas

The openness of the Census Bureau to use creative data-gathering methods was a success because new methods were used.

There was increased data collection and participation due to partnerships and advertising.

More community groups were willing to use volunteer resources to increase participation.

Census 2000 Lessons Learned

The 1-800 number was not effective. The lines were continuously busy and often provided incomplete or incorrect information.

The Census Bureau should thank citizens for their participation in the Census.

It was effective to show how Census participation would help citizens with local services such as schools and roads.

Ideas to Improve Census 2010

In addition to frequently asked questions, the Census Bureau should look into other Web- based technologies so it can provide additional assistance via the Web.

Apply more targeted resources to QACs and other data collection centers.

Broaden the role of the QAC to include issues such as community education and mobilization.

Consider ideas on how to count people not regularly attached to households (i.e., homeless, mentally ill, or recluse).

Issues in Detail

Census 2000 Successful Areas

The African American community saw an increase in Census participation as a direct result of partnerships and the paid advertising campaign.  Public relations should not happen every ten years but on a continuous basis.  There should be some logic behind the Census Bureau’s public relations campaign.  The Census Bureau should have some paid advertisements before, during, and after significant Census Bureau activities.

The Committee mentioned that many community groups were willing to use volunteer resources, such as donated facilities, to increase Census participation.  The volunteer community groups stayed opened longer to collect Census forms as compared to the Census Bureau-sponsored facilities.  The Committee thought that with limited funding these community groups could help with testing potential enumerators and other Census Bureau staff, promote Census awareness, and increase future Census participation.

Census 2000 Lessons Learned

The Committee noted that the 1-800 number did not work; the lines were continuously busy.  The Committee also mentioned that the personnel working at the Census information sites were not helpful and the Census Bureau must conduct the proper training to correct this problem.

The Committee thought it would help if the Census Bureau thanked citizens for their participation and showed citizens how Census participation would help with local services such as schools and roads.  Currently, the Census Bureau has no feedback mechanism to relay what was or was not effective. The Committee thought that publicizing the fear factors that people must overcome for providing Census information would encourage better participation in the next Census.

Ideas to Improve or Enhance Census 2010

To supplement frequently asked questions, the Committee recommended that the Census Bureau look into other Web-based technologies so it can provide additional assistance via the Web.  The Committee also suggested that the Bureau add the capability for people to ask questions on the Web.  By using Internet technology, the Census Bureau could reduce the demand placed on the 1-800 number.  This additional service could benefit the American Community Survey (ACS), Census 2010, and other on-going Census activities.

The Committee thought that the Census Bureau should apply more targeted resources to QACs and other data collection activities.  One member of the Committee commented that storeowners should not determine Census participation.  One example given sited a check cashing storeowner's interest in the Census would determine the quantity of Census information that was distributed. The Committee recommended the Census Bureau seek Federal and State funding for QACs.

The Committee thought the Census Bureau must broaden the QAC role to include community education and mobilization responsibilities.

In America, a growing population uses mobile soup kitchens, shelters, jails, nursing homes, and other Federal-and State-sponsored programs.  The Committee commented that the Census Bureau was not able to effectively track these populations and resorted to using estimations.  The Census Bureau must consider how to count people not regularly attached to households.  The enumerators tried to locate and count this population, but some people did not want to be counted or in some instances, some were double counted.

Other Relevant Issues

The Committee discussed the "underground" population.  The "underground" population included persons without addresses, persons living in group quarters or serving prison sentences, and persons that may have "opted out" of living in "normal" society.  The National Urban League and the African American community realize that they must get these people to participate in the Census. Although the 1-800 number was busy, the Committee does not want the Census Bureau to discontinue the service because it would give the "underground" population another reason not to participate in the Census.

REAC - African American Advisory Committee

Language Program Debriefing

Wednesday, June 20, 2001, 1:15 p.m. – 2:15 p.m.

Facilitator and Recorder – Carlton McArthur & Brian Ince

Participants

Dr. Robert Hill – Senior Researcher, Westat

Dr. L. Patricia Johnson – President, Creative Marketing, Inc.

Gwendolyn E. Holmes – Assistant Vice-President, Hancock Bank

Dr. James S. Jackson – Professor, Institute for Social Research

John W. Mack – President, Los Angeles Urban League

Kermit N. Waddell – President/CEO, Economic Development Center of the Carolinas

Barbara Sabol – Program Director, W. K. Kellogg Foundation

Tracey-Ann Nelson – Public Relations/Public Affairs Consultant

Resource Person:

Debbie Griffin – Demographic Surveys Division

Committee Liaison:

Jimmie Scott – Assistant Division Chief, Demographic Statistical Methods Division

Summary of Issues

Census 2000 Successful Areas

The Language Program successfully reached out to a broad, diverse group of languages.

The Committee was pleased with the work of the Chisholm-Mingo Group.

Census 2000 Lessons Learned

The mailing of Census material should be more targeted.

Ideas to Improve Census 2010

The Census Bureau must perform a quality assurance check on the work performed for them by contractors.

Issues in Detail

Census 2000 Successful Areas

The Committee strongly supports and was very concerned about an effective Language Program since the African American Community speaks various languages regardless of nationality.

The Committee commended the Chisholm-Mingo Group for their outstanding focus group session with Creole-speaking Haitians.  The Chisholm-Mingo Group brought in Creole- speaking facilitators, which was very successful.

Census 2000 Lessons Learned

The Committee stated that the Census Bureau must do a better job of targeting and mailing their language questionnaire and forms to various racial and ethnic groups.

Ideas to Improve or Enhance Census 2010

The Committee stated the advance letter did not set a good tone for the Census.  The Census Bureau had to send the advance letter out twice because the contractor responsible for this function left off the last address digit.  The Committee stated that the Census Bureau must perform a quality assurance check of their contractor’s work.

According to the Committee, there is a growing Haitian American population that speaks Creole.  The Census Bureau should identify and target these growing populations in their programs.  They suggested that the Census Bureau develop multi-lingual, dual-sided Census forms.  Another possibility the Census Bureau should consider involves placing English and other languages on the same page.

The Committee did not see a standardized process for translating materials.  The Census Bureau should not treat language translation as a small issue.  It is a major consideration that requires greater coordination.

The language interpretation may be one reason people did not return their Census forms.  One pitfall to language interpretation stems from a misrepresentation of wording.  The assumption frequently made is that every language has a comparable word to English.

Translators had problems translating some words in English to languages other than English.

The process of trying to literally translate words or phrases from English into languages other than English is not always effective.  This is because many languages do not have words or phrases that can be used to replace or translate the English words or phrases (e.g., the word mortgage is not translatable in some languages because people cannot own property in some countries).  Because of this the Census Bureau should explore different ways of getting its message out to populations that speak languages other than English.  The Committee suggested leveraging partnerships to help develop language forms for large and small language populations.

# Appendix B – American Indian & Alaska Native Advisory Committee

REAC – American Indian and Alaska Native Advisory Committee

Partnership Program Debriefing

Tuesday, June 19, 2001, 1:05 p.m. – 2:35 p.m.

Facilitator and Recorder – Valerie Thwing and Jeff Shanahan

Participants

Dr. Ted Jojola – Professor, University of New Mexico

Larry Rodgers – Executive Director, Utah Navajo Trust Fund

Curtis Zunigha – Executive Director, Delaware Indian Center

Gregory Richardson – Executive Director, North Carolina Commission of Indian Affairs

Dr. Matthew Snipp – Professor, Stanford University

Resource Person:

Sydnee Chattin-Reynolds – Partnership and Data Services Branch, Field Division

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Committee Liaison:

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Summary of Issues

Census 2000 Successful Areas

The building of relationships between Tribal governments and the Federal Government was successful.

Government Liaison Programs were successful.

Census 2000 Lessons Learned

Complete Count Committees should be an ongoing process.

Maps were given to AIAN representatives too late for review and submittal by the Census Bureau deadlines.

There was no point of contact within the Census Bureau exclusive to the AIAN community.

Ideas to Improve Census 2010

An increase of Native American employment in management positions at the regional level would help strengthen partnerships.

The Census Bureau should assist in creating Partnership Programs with the AIAN urban community.

The amount of funding for the AIAN community should be increased.

Better communication is needed among the Census Bureau's own divisions.

The entire Partnership Program needed to be started earlier.

Issues in Detail

Census 2000 Successful Areas

According to the Committee the fact that government-to-government relationships were even built between the Census Bureau and the Tribal governments was a huge success.  It was said to be the foundation of the Census and AIAN Partnership Program.  However, it was clear to the Committee that this relationship must continue to grow so that there is more AIAN representation in the Census.

The Tribal Government Liaison Program was also cited as a successful initiative created by the Census Bureau.  The Census Bureau started Complete Count Committee's (CCCs) which were cited as important for communicating with and educating the Tribal governments on proper count procedures.  The Committee thought the Tribal Government Liaison Program was essential to educating American Indians on the Census process.  This added to the movement for greater Census Bureau related activities within Tribal governments.  Another important result of the Tribal Government Liaison Program was that Census Bureau staff at headquarters had the opportunity to personally observe the varied environments of the Tribes.

In conjunction with the Tribal Government Liaison Program, the Census Bureau started to swear in members of the AIAN community for official Census Bureau staff positions.  This process resulted in the American Indian community feeling a part of the process and fully included in Census Bureau procedures.  The American Indian community members were given roles that dealt with confidential materials that made the American Indian community feel more trusted and engaged in the Census process.  The swearing-in process also contributed to the improved relationship between the Census Bureau and the AIAN community.

Census 2000 Lessons Learned

The Committee thought that the Partnership Program was started too late.  The Committee thought that this left insufficient time for members of the AIAN community to complete necessary acts to prepare for Census 2000.  These acts included the preparations needed to stage successful advertising programs, update maps and more generally the underlying ability to react to changes and enhancements from the Census Bureau.

Although the CCCs were cited as a success, a lesson learned was that the CCCs were not an ongoing process.  This was an issue because the assistance they provided to the AIAN community stopped soon after Census 2000 activities ended.

Another Census 2000 lesson cited by the Committee was the lack of an ongoing "Indian Desk."  The AIAN community thought that communication with the Census Bureau suffered without a constant point of contact, otherwise known as the Indian Desk.  According to the Committee, the Indian Desk was only available for a short time during peak activities of Census 2000.  The Indian Desk should be an ongoing position at the Census Bureau.

Ideas to Improve or Enhance Census 2010

The Committee thought that a more balanced partnership could be realized if a member of the AIAN community held a management position at Census Bureau headquarters.  It was thought that this would help stimulate the Partnership Program.  It was thought that having someone that fully understood AIAN issues on the "inside" would ensure the views of the AIAN community were heard and the relationship between Tribal governments and the Census Bureau continued to grow.

The Committee stated that the urban American Indian community was disenfranchised from the Census 2000.  The Committee agreed that partnership efforts should be increased in urban American Indian communities.  It was believed that more urban American Indians could be reached and ultimately persuaded to participate in the Census through better partnerships with urban community leaders.

The Committee stated that more funding is needed for creating and sustaining partnership programs.  The Committee observed a need for more funding at local levels to make partnerships more effective.

Available funding for partnership programs should have been better publicized to the AIAN community.

The Committee thought the Census Bureau needed better communication within its own divisions. The Committee commented that the lack of communication among Census Bureau divisions resulted in slow turn-around times for changes, requests, and suggestions from the AIAN Committee.  Bureaucracy and "red tape" slowed the communication and implementation of new ideas.  The possibility of a partnership program within the Census Bureaus' divisions was a recommended area of enhancement for Census 2010.

The process of partnering with the AIAN community should be started earlier.  Data verification and advertising campaign improvements would be more easily executed if more time were available for the AIAN community and for the Census Bureau to implement the changes.

The most important Census 2010 enhancement stated by the Committee called for the continuation, development and reaffirmation of the government-to-government relationship that was developed between the Census Bureau and the Tribal governments.

REAC – American Indian and Alaska Native Advisory Committee

Recruitment and Hiring Debriefing

Tuesday, June 19, 2001, 2:45 p.m. – 4:15 p.m.

Facilitator and Recorder – Valerie Thwing and Jeff Shanahan

Participants

Dr. Ted Jojola – Professor, University of New Mexico

Larry Rodgers – Executive Director, Utah Navajo Trust Fund

Curtis Zunigha – Executive Director, Delaware Indian Center

Gregory Richardson – Executive Director, North Carolina Commission of Indian Affairs

Dr. Matthew Snipp – Professor, Stanford University

Resource Person:

Donna Stovall – Customer Liaison Office

Committee Liaison:

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Summary of Issues

Census 2000 Successful Areas

The Recruitment and Hiring program demonstrated flexibility by its ability to adapt to different regions.

The Census Bureau was more effective in meeting payroll on time, most notably with field enumerators.

For the first time the Census Bureau hired local private contractors for dissemination of paid advertisement of recruiting needs to the local media.

The Welfare-to-Work program provided opportunities for employment without penalty for federally assisted citizens.

Census 2000 Lessons Learned

The Census Bureau front-loaded too many applicants.

The Census Bureau was not able to recruit enough local speakers, perhaps resulting from low wages.

The Census Bureau lacked a pro-active and energetic recruiting pitch.

The Recruitment and Hiring process started too late.

Ideas to Improve Census 2010

The Census Bureau should increase local advertising related to Census job opportunities.

An increased number of American Indians in management positions at the Census Bureau headquarters is required.

Employees need more training on what the Census Bureau expects from them.

Wages should be higher in certain areas.

Potential candidates for the Welfare-to-Work program should be more informed regarding the benefits of income exclusions.

The Census Bureau should promptly inform job applicants about their employment status.

Issues in Detail

Census 2000 Successful Areas

The Recruitment and Hiring Program demonstrated a great deal of flexibility in different regions.  The Census Bureau was able to adjust its recruitment efforts to each region's specific needs.  The Committee was impressed with the improvements made since the 1990 Census. The AIAN Committee stated that great strides were made in this program since the last Census.

The Census Bureau paid employees in a timely manner.  The Committee discussed issues during the 1990 Census where employees didn’t receive their paychecks for as long as six months after the work was done.  However, they concluded that this problem was resolved during the 2000 Census and paychecks were distributed on time.

For the first time, the Census Bureau hired local private contractors for the dissemination of recruiting needs to the local media. This action helped the Census Bureau connect with certain AIAN communities.  As a result, AIAN communities felt a strong effort was made to better represent them in the 2000 Census.

The Committee commented that the income exclusions provided by the Census Bureau were a success.  American Indians on welfare or other federally assisted income and housing were given income exclusions while working for the Census Bureau.  The income exclusions allowed certain members of the AIAN community to work for the Census Bureau without affecting their income status.

Census 2000 Lessons Learned

The Committee thought the Census Bureau front-loaded applicants during the Recruitment and Hiring process.  The Census Bureau never stopped accepting applications and continued to advertise positions even though the positions had been filled.  Many applicants never heard any response about their employment status.  This left several members of the AIAN community disenchanted with the Census Bureau and more specifically, the hiring process.

The Census Bureau was not able to recruit enough qualified local speakers to work within the reservations.  The AIAN community was not sure what caused this deficiency.  However, the Committee did suggest that wages may not have been high enough to attract applicants.

The Committee thought that the Census Bureau's recruitment efforts lacked a pro-active, high-energy "pitch".  The Committee thought the Census Bureau was merely "going through the motions" at times during the process.  Although the Census Bureau made a valiant effort, members of the AIAN community sometimes sensed that the Census Bureau was reluctant to get out to the communities.

The Committee stated several times that although the Recruitment and Hiring Program was an overall success, the process started too late.  There was too little time available to help identify better applicants, which would have resulted in higher quality employees.

Ideas to Improve or Enhance Census 2010

The Committee stated paid advertising efforts for recruitment and hiring should be increased to make available positions known throughout local communities.  Advertising was not enough at the local level.  The Committee suggested that the Census Bureau utilize Tribal newsletters and more local media.

The Committee strongly agreed that the AIAN community desperately needs more significant representation at the Census Bureau's headquarters and in regional offices.  The Committee believed that the addition of American Indians to Census Bureau staff management positions would help ideas, suggestions, and initiatives receive more consideration at headquarters.  The Committee thought that the AIAN community is too small of a minority not to have more representation at a management level.

The Committee thought that employees require a more clear definition of expectations from the Census Bureau as to what their job duties entail.  Field workers were often unclear of what the Census Bureau expected out of them.  This led to confusion and less efficient work.

Wages should be higher in particular areas.  Many areas have different economies, and wages should be competitive to the local market.  One Committee member, who represented North Carolina, targeted low wages as a reason why the Census Bureau experienced difficulty hiring.

Income exclusions, which were also cited as a success, should continue to be publicized and emphasized within the AIAN communities.  The Committee thought that more applicants would result from better communicating this feature.  The income exclusions are designed to help federally assisted citizens keep their benefits while working for the Census Bureau.

The Committee suggested that procedures be developed to ensure all applicants receive a response from the Census Bureau after turning in a job application.  The Committee believed a status update by notification from the Census Bureau would help keep applicants informed and interested in the position.  Members of the AIAN community were unaware as to what happened after turning in an application, and often times never heard back from the Census Bureau.

REAC – American Indian and Alaska Native Advisory Committee

MAF/Tiger Debriefing

Tuesday, June 19, 2001, 4:15 p.m. – 5:30 p.m.

Facilitator and Recorder – Valerie Thwing and Jeff Shanahan

Participants

Dr. Ted Jojola – Professor, University of New Mexico

Larry Rodgers – Executive Director, Utah Navajo Trust Fund

Curtis Zunigha – Executive Director, Delaware Indian Center

Gregory Richardson – Executive Director, North Carolina Commission of Indian Affairs

Dr. Matthew Snipp – Professor, Stanford University

Resource Persons:

Al Pfeiffer – Geography Division

Jamie Rosenson – Geography Division

Committee Liaison:

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Summary of Issues

Census 2000 Successful Areas

The Geography staff was able to make several adjustments after 1990 Census.

Overall the LUCA Program was sited as a success.

Census 2000 Lessons Learned

The LUCA Program started too late.

Tribal Governments were not sure of their responsibilities for the LUCA Program.

Maps and addresses issued and used by the Census Bureau were too general.

Tribal boundaries that run over state lines need to be clarified.

Ideas to Improve Census 2010

An overall introductory statement is needed to describe what the Tribal role is in the LUCA initiative.

LUCA Program timelines should be started earlier in the process.

Tribes should be consulted and involved when the Census Bureau is deciphering Tribal and legal boundaries.

Issues in Detail

Census 2000 Successful Areas

The Committee would like to extend their appreciation to the Census Bureau's Geography staff for making many of the necessary changes and adjustments.  The Committee was impressed with responsiveness of the Census Bureau staff.  Another success was the creation of the Tribal boundaries.

The Committee was satisfied with the LUCA initiative and declared it a success.  The LUCA Program enabled American Indians to become stakeholders in the process of identifying addresses.  This encouraged the American Indian community to become a part of the Census process.  In previous years the Census Bureau performed these tasks without consulting the AIAN community, leaving the community disinterested in the Census process as a whole.

Deputizing local officials to be LUCA liaisons to review and update maps and addresses was also successful in making the AIAN community feel like stakeholders in the Census process.

Census 2000 Lessons Learned

Confidentiality is important to the AIAN community.  What happens to the information collected during the Census is important to the AIAN community.  The Census Bureau should understand these facts when attempting to collect information from the AIAN community.

Although it was considered an overall success, the LUCA program started too late in the Census process.  The time given to submit updates was not sufficient enough for the tribes to properly review and return the material.

The Committee stated the Tribal governments were unsure of their responsibilities for the LUCA program.  Some tribes were reluctant to share address information with the Census Bureau because of political ties with respective states.  This happened specifically with the Oklahoma tribes.

The Committee thought the maps and address files used by the Census Bureau were too general to document dwelling units without addresses.  The dwelling units were difficult to locate on maps because there was little relation in these communities to paved roads and landmarks.

The Census Bureau's inability to perform proper count procedure for tribes whose boundary lines ran over state lines.  The Committee was concerned that tribes with members living beyond state lines would not be counted because only one of the States recognized the tribe(s).  The Census Bureau did not work with State and Tribal governments to confirm tribes with boundaries running over state lines had been accurately counted.

Ideas to Improve or Enhance Census 2010

The Committee thought that an introductory statement is needed to describe what the Tribal role is in the LUCA initiative.

The Committee thought that tribes need clear insight as to what is done with the Census information.  All Census programs should educate communities on confidentiality issues and what is done with the Census information.

Continue to make tribes feel like part of the Census equation by continuing to include them in initiatives like LUCA.

Start the LUCA Program earlier.  The short turn-around time did not give the tribes ample time to make necessary changes and updates.  The Committee stated that only two weeks was given for this process.  They suggested that 30 to 60 days are needed to complete this procedure.

Tribal governments should be involved in the process or at least consulted when the Census Bureau is updating or trying to decipher Tribal vs. legal boundaries.  The Committee stated that they would like to use similar procedures that towns and counties use throughout the country to adjust or update boundary lines.

REAC – American Indian and Alaska Native Advisory Committee

Paid Advertising Debriefing

Tuesday, June 19, 2001, 8:30am – 10:00am

Facilitator and Recorder – Valerie Thwing and Jeff Shanahan

Participants

Dr. Ted Jojola – Professor, University of New Mexico

Larry Rodgers – Executive Director, Utah Navajo Trust Fund

Curtis Zunigha – Executive Director, Delaware Indian Center

Gregory Richardson – Executive Director, North Carolina Commission of Indian Affairs

Dr. Matthew Snipp – Professor, Stanford University

Resource Person:

Kendall Oliphant – Branch Chief, Census 2000 Public Information Office

Committee Liaison:

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Summary of Issues

Census 2000 Successful Areas

The Census Bureau was successful in funding separate advertising campaign for several race and ethnic communities.

The print media, radio and television advertisements were all successful.

The Partnership Program had its own budget for advertising.

The Committee was given the opportunity to work with the Census Bureau to develop the advertising campaign.

Census 2000 Lessons Learned

The Paid Advertising campaign started too late.

The AIAN community experienced excessive bureaucracy when it came to suggesting changes to the AIAN advertising campaign.

Alaska natives were not represented properly in the advertising campaign.

Ideas to Improve Census 2010

The Paid Advertising campaign should be started earlier than it was in Census 2000.

Advertisements should be more specific to each American Indian community and should include the urban communities of American Indians.

The Census Bureau should use more free publicity to increase Census awareness in addition to the Paid Advertising campaign.

Issues in Detail

Census 2000 Successful Areas

The Committee was pleased with the diversified advertising campaign.  They thought it was an historic step for both the Census Bureau and the AIAN community.  Although the Committee had suggestions for improvement, the advertisements were culturally sensitive enough to be proclaimed a success.

The print media was effective in making the AIAN community aware of the Census. The Committee thought the use of print media proved to be the most effective means of advertising for the AIAN community.  Local press full-page advertisements were effective in targeting the AIAN audience.  The posters seemed to be effective because they were mobile and could be placed in places such as offices, schools and buses.

In addition to the successful print media campaign, radio and television advertisements were also successful.  The Committee personally saw and heard many of these advertisements and was pleased with their effectiveness.

The Partnership Program had its own budget for advertising.  The Committee declared this a success.  The Committee was impressed with the amount of funding available in the Partnership Program in comparison to the national Paid Advertising campaign.

Census 2000 marked the first time the Committee was allowed to work with the Census Bureau to develop an advertisement strategy.  The Committee referred to this as a success.

Census 2000 Lessons Learned

The Committee stated that the Paid Advertising campaign, although successful, started too late.  The Committee did not have enough time to make the necessary changes and suggestions to the campaign.  According to the Committee, the Census Bureau made it seem that the Committee would be able to make changes and suggestions, but not enough time was allocated to incorporate those changes into the campaign.

It was also mentioned that the Census Bureau did not clearly discuss the channels for or the process of communicating with the advertising contractors to suggest changes or approaches.

The Committee expressed its discontent with the end result of their suggestions to the advertising campaign.  "Red tape" and bureaucracy with the contractors and Census Bureau were cited as pitfalls in the process of implementing changes to the AIAN advertising campaign.  The Committee was not allowed to directly interact with the advertising contractors.  With no direct contact, the Committee thought their suggestions were not executed.  The advertising contractor G&G was specifically cited by the AIAN Committee.  The Committee thought G&G did not demonstrate sufficient communication skills and did not want to participate in the "free flow" of ideas with the Committee.

Although no members of the Alaska Native community were present at the debriefing sessions, the Committee members thought that the Alaska Natives were disenfranchised due to the time and distance differences between them and their regional office in Seattle, Washington.

Ideas to Improve or Enhance Census 2010

The Paid Advertising campaign should be started earlier.  The campaign did not allow sufficient time for the Committee to interact and make necessary changes and updates to advertising slogans or ideas.  They suggested that the process could be started 2 years earlier than it was for Census 2000.

The Committee thought the advertising campaign needed to be more specific to different AIAN communities, including the urban community.  The Committee stated that "one size fits all" does not work with the various AIAN communities.  Advertisements should be specific to each American Indian community.  The Committee suggested that the Census Bureau partner with local tribes to develop advertisements on a smaller scale, which may prove more effective than many national ads.  "Seed grants" were suggested as a possible funding option to help fund the localized advertising campaigns.

More advertising should be directed to urban American Indian communities.  The Committee thought that urban communities did not receive enough attention from the Paid Advertising campaign.  The proportion of ads to the urban communities was not equal with the reservation-directed advertising campaigns.  Advertising on public transportation was recommended to reach the American Indian community in urban areas.

The Committee thought that publicity through local and national news was very effective in conveying the importance of the Census to the AIAN community.  The Committee recommended taking advantage of free advertising such as local television station news.  The AIAN community seemed to pay more attention to news articles and television stories because it made the AIAN community feel like an important aspect of the Census process after being seen and heard in the news.

REAC – American Indian and Alaska Native Advisory Committee

Data Collection Strategies Debriefing

Tuesday, June 19, 2001, 10:05am – 11:15am

Facilitator and Recorder – Valerie Thwing and Jeff Shanahan

Participants

Dr. Ted Jojola – Professor, University of New Mexico

Larry Rodgers – Executive Director, Utah Navajo Trust Fund

Curtis Zunigha – Executive Director, Delaware Indian Center

Gregory Richardson – Executive Director, North Carolina Commission of Indian Affairs

Dr. Matthew Snipp – Professor, Stanford University

Resource Person:

Mike Weiler – Branch Chief, Field Division

Committee Liaison:

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Summary of Issues

Census 2000 Successful Areas

The Committee deemed the data collection strategies of the 2000 Census a success.

Increased automation at Local Census Offices eased the data collection process.

The Census Bureau's coverage of the Navajo tribe was an improvement.

The Non-Response Follow-Up (NRFU) procedure was a success.

Census 2000 Lessons Learned

Telephone Questionnaire Assistance (TQA) and Questionnaire Assistance Centers (QACs) were not effective for the AIAN community.

A Congressman in Oklahoma publicly denounced the importance of filling out the Census long form.

The Census Bureau did not properly count transient AIAN citizens.

The List/Enumerate procedure is essential when enumerating on American Indian reservations.

Ideas to Improve Census 2010

QACs located in border towns to nearby reservations must reach out to the AIAN community.

To gain an accurate count of respondents in serviced-based facilities, the Census Bureau should target communities of faith to assist with education and enumeration procedures.

The List/Enumeration procedure should continue to be used when enumerating on American Indian reservations.

Issues in Detail

Census 2000 Successful Areas

The Committee agreed that the data collection strategy employed for the 2000 Census was successful.  The success is illustrated in the decreased undercount statistics between the 1990 and the 2000 Census.

The Committee thought the increased automation at Local Census Offices (LCO) was a successful component of the data collection strategy.  The increased automation reduced the burden of having to manually process data at the local level and resulted in increased productivity.  The increased automation allowed more time to be spent in the field.  Enumerators could concentrate on the American Indian reservations.

The Committee member representing the Navajo Nation declared the data collection strategy used to count the Navajo Nation a success.  The successful strategy resulted in a decrease in the undercount of the Navajo Nation as compared to the 1990 Census.

The Non-Response Follow-Up (NRFU) program was also cited as a success for the Navajo population.  The NRFU program proved to play a significant role in improving the undercount percentage of this population.

Census 2000 Lessons Learned

The Committee unanimously agreed that the TQA and the QACs were either unsuccessful or did not apply to the AIAN community.  The TQA had a very nominal effect on the AIAN community. In a few instances observed by Committee members, AIAN community members received no response after calling about missing forms.  The QACs were equally ineffective.  Many QACs did not have local American Indians that could help the members of these communities with their questions or issues.

The Committee concluded that the Census Bureau was not able to accurately count the transient citizens within the AIAN community.  The AIAN community includes many transient citizens and people living temporarily at other families' houses.  The Census Bureau lacked operative procedures to precisely calculate the number of this transient population.

Ideas to Improve or Enhance Census 2010

The AIAN Committee recommended that QACs be tailored to the communities they serve and that more QACs be placed throughout communities.  QACs located in border towns to nearby reservations failed to employ American Indians that could speak the local American Indian language.  The QACs require more American Indian participation to make them helpful for local Indians.

The Census Bureau should create an education program to let American Indians on reservations know the mission and the location of the QACs.

To gain an accurate count of respondents in serviced-based facilities, the Census Bureau should target communities of faith to assist with education and enumeration procedures. There are a large number of people in service-based facilities associated with communities of faith. Through partnerships with these communities, the Census Bureau could more easily reach service-based populations that travel to soup kitchens and shelters that are maintained by these communities of faith.

The List/Enumerate procedure should continue to be used when enumerating on American Indian reservations. The List/Enumerate procedures were said to be essential to obtain a true American Indian count for the 2010 Census.

Other Relevant Issues

An isolated occurrence in Oklahoma involved a Congressman denouncing the validity of the long form.  In this instance, he went as far as recommending that local citizens, including the AIAN community, not complete the long form.  The Congressman thought the long form was not necessary and that it asked for too much information.

REAC – American Indian and Alaska Native Advisory Committee

Language Debriefing

Tuesday, June 20, 2001, 1:15 p.m. – 2:15 p.m.

Facilitator and Recorder – Valerie Thwing and Jeff Shanahan

Participants

Dr. Ted Jojola – Professor, University of New Mexico

Larry Rodgers – Executive Director, Utah Navajo Trust Fund

Curtis Zunigha – Executive Director, Delaware Indian Center

Gregory Richardson – Executive Director, North Carolina Commission of Indian Affairs

Dr. Matthew Snipp – Professor, Stanford University

Resource Person:

Raj Singh – Assistant Division Chief, Decennial Statistical Studies Division

Committee Liaison:

Thelma Stiffarm – Program Administrator, Customer Liaison Office

Summary of Issues

Census 2000 Successful Areas

The interpreters from the Census Bureau provided a good start for the Language Program.

Census 2000 Lessons Learned

Native American languages are becoming extinct because of the lack of recognition by the Federal Government.

The Census Bureau focused on other languages and not the numerous American Indian languages that are native to this country because the communities that speak these languages are small.

Cultural diversity is missing from the Language Program.

Ideas to Improve Census 2010

The Census Bureau should recognize American Indian languages that have significant speaking populations.

The Census Bureau should work with tribes to determine if there is a way to preserve the languages native to the tribes.

A strong cultural geographic component at the Census Bureau headquarters would help cultural differences between the Census Bureau and the AIAN community.

Issues in Detail

Census 2000 Successful Areas

The Committee stated that the Language Program was a step in the right direction.  In some cases interpreters proved valuable and worthwhile.  The Language Program was a success in that it was a step in the right direction.  The program should be expanded upon to alleviate serious language barrier issues.

Census 2000 Lessons Learned

The Committee was passionate about the potential extinction of American Indian languages in the near future. The AIAN community would greatly benefit from the Census Bureau's recognition of American Indian languages that continue to be passed down from generation to generation in written and spoken word.  The Committee recognized that it would be impossible for the Census Bureau to incorporate every American Indian language into the Census program.  However, the Committee passionately believes that there are enough communities that speak some American Indian languages (like Navajo) that it would be worthwhile to incorporate these languages into the Census program (in written form if appropriate or by providing qualified interpreters). It was strongly thought by the Committee that working with the tribes to preserve native languages would serve to strengthen the relationships that are being built between American Indian communities and the Census Bureau and would significantly increase the response rates from this already undercounted population.

The Census Bureau failed to include cultural considerations into its Language Program.  The Committee agreed that cultural diversity should be inherently part of the Language Program.  Although the Census Bureau attempted to incorporate many languages into its Census 2000 programs, it failed to respect many cultural nuances that are unique to cultures and tribes (such as their local languages).

Ideas to Improve or Enhance Census 2010

The Committee would like the Census Bureau to incorporate American Indian languages that have a significant speaking population (like Navajo) into the Census 2010 Language Program (in written form if appropriate or by providing qualified interpreters).

The Committee recommended the creation of a "Cultural Geographic Office" to build relationships with the tribes and the Census Bureau. A strong Cultural Geographic Office located at the Census Bureau's headquarters could result in an improved Language Program and a strong cultural recognition program. For instance, the Committee believed that ideas generated at the field level (that had merit) seemed to undergo a filter by the time the idea reached the headquarters that undermined the initial energy that was created when the idea was generated.  A "Cultural Geographic Office" could help alleviate this phenomenon. The concept of a "Cultural Geographic Office" is similar to the idea of creating and maintaining a Census Indian Desk to provide help with the specific questions, issues and challenges that the American Indian community faces.  The AIAN Committee stressed the importance of having a first point of contact within the headquarters that understood AIAN issues and could be counted on.

Other Relevant Issues

The Committee thought that the Census Bureau focused on other languages because of the population size that speaks those languages.  Conversely, American Indian languages are not focused on due to the small population size that speaks these languages.  However, the Committee thought that it was important to note that this procedure disenfranchises tribes where the native languages are still prevalent.

Heavily spoken Native American languages such as Navajo are lacking recognition, and more importantly the respect from the Census Bureau.

# Appendix C – Asian Advisory Committee

REAC – Asian Advisory Committee

Partnership Debriefing

Tuesday, June 19, 2001, 1:05 p.m. -2:45 p.m.

Facilitator and Recorder – Kim Whetsell & Terri Russell

Participants

Jon Melegrito – Executive, Director, National Federation of Filipino American Associations

Cyril Nishimoto – Executive Director, IWA, Inc.

Dr. K.V. Rao – Associate Professor, Bowling Green State University

Dr. Piyush C. Agrawal – The Association of Asian Indians in America

Resource Person:

Vicki Burke – Field Division

Wayne Kei – Customer Liaison Office

Committee Liaison:

Jane Sandusky – Planning, Research, and Evaluation Division

Summary of Issues

Census 2000 Successful Areas

The Committee believed partnerships allowed the Census experience to be more personal and intimate for Census participants.

The partnership program's ability to build awareness of the Census before Census Day was viewed as excellent.

The partnership program built awareness of the Census, thus increasing the Census count throughout the country.  As a result, participation of the hard-to-reach populations was also increased.

Asian Advisory Committee specialists were hired to help build awareness.

The Committee thought the Partnership Program provided credibility to the community based organizations involved in the Census.

Census 2000 Lessons Learned

The Committee thought the complete commitment of a Census partner, as well as a regional director, is necessary for the success of the Census.

The Committee thought the quantity of area covered by each area specialist was too large.

Balance is needed in the Partnership Program between a targeted program and a general approach.

Awareness may not translate into the action of returning the Census form.

The Census Bureau should clarify the requirements necessary to become a Census partner.

The Census Bureau should clarify the requirements necessary to be a community specialist.  For example, clarify if U.S. citizenship is required to become a community specialist.

It took newly hired specialists a long time to build contacts with the community.

The Committee noted that the communities expected more from the Partnership Specialists than the Partnership Specialists could deliver.  In addition, the number of Partnership Specialists was not enough to meet the needs of the community.

Ideas to Improve Census 2010

The quantity of community specialist positions available should be increased.

During the recruitment process, more Asians should be hired as community specialists.  The Census Bureau also should hire a larger number of specialists, particularly for high-density areas such as New York and Los Angeles.

The Census Bureau should publicize the contact list for the established partnerships more widely so that they can be reached easily.

Additional funding of the community-based organization is needed.

The Census Bureau should put an infrastructure in place to distribute the partnership information more easily.

The Committee thought the Census Bureau should consider community service as well as professional employment when hiring community specialists.

Partnership Specialists should have a clearer understanding of their responsibilities and the resources available to them.

Partnership Specialist positions should be open to both U.S. citizens and legal residents.

The Partnership Program should be a continual process.

The Census Bureau should maintain full time, year-round Partnership Specialists to establish continuity and to maintain relationships with communities.

Feedback on the evaluation of the program and the specialists is needed to understand the level of service provided.

All specialists should have periodic contact before, during, and after the Census with the Asian Advisory Committee for feedback and evaluation.

The Census Bureau should include schools in the Partnership Program to distribute information to students.

Issues in Detail

Census 2000 Successful Areas

The Asian Advisory Committee thought that partnerships provided credibility to the community based organizations.

The Committee thought that the Partnership Program's ability to build awareness of the Census before Census Day was excellent.

Census 2000 Lessons Learned

The Committee viewed overall Census awareness as effective, but a lesson learned is that the awareness may not translate to the action of returning the form.

The Committee noted that the communities expected more from the Partnership Specialists than they could deliver or were expected to provide.  In addition, the number of Partnership Specialists was not great enough to meet the needs of the community.

The Committee thought that complete commitment of the Partnership Specialist, as well as the Regional Director, is necessary.  Regional Director commitment to the Partnership Program is a must.  In addition, integration between Regional Offices is needed in order to share resources such as transportation and budgets.

The Committee thought the large area covered by each Partnership Specialist affected the Partnership Program by limiting the amount of attention each Partnership Specialist could devote to each area. The Asian Partnership Specialists had too many areas to cover to be effective. The Census Bureau needs more Partnership Specialists, specifically, more multi-lingual specialists.

There was a problem in New York regarding what the requirements were for getting a Partnership Specialist position.  There was a question of whether community service was a requirement for participating in the Partnership Program.

The Committee noted that the Partnership Program did not have sufficient time to establish contacts within communities prior to the Census (one or two years is not enough).  It took newly hired specialists a long time to establish contacts in the community.

Ideas to Improve or Enhance Census 2010

To fully understand the effectiveness of a Partnership Specialist on a specific community, the Census Bureau should be more aware of how large an area the specialist is assigned to.  The Census Bureau should track if the Partnership Specialists are overworked during the Census process.

The Asian Advisory Committee suggested that community based outreach is needed to keep contact with communities.  While the outreach program was viewed as a success, it should be further developed.  The Committee would like to see strategic locations chosen for outreach such as shopping centers, schools, and other locations where Asians congregate.

The Census Bureau should provide a clearer definition of what the partners should do and what is expected from them. The expectation is tremendous and partners should understand their responsibilities and the resources available to them.

Partnership specialist positions should be open to both U.S. citizens and legal residents.

The Committee would like to see Census partners receive adequate resources.  The resources are important to make the partnership more effective to target to each specific community. Limited resources were available to partners during Census 2000.  The partners were provided materials for promotion, as well as assistance with those materials.  However, the Committee thought that funds should be made available to the partners to develop their own materials to promote the Census specifically for different communities.  Another potential solution would be for the Census Bureau to fund community-based organizations.  The resources needed to distribute Census information are crucial and an infrastructure is needed for distribution.

The Committee thought the Census Bureau should consider community service in addition to professional employment when hiring community specialists. The enhancement would look at what they've done in their paid work, and also assess what they have completed as service to the community.

During the recruitment process, more Asians should be hired as specialists to better meet the needs of the Asian community.

The Committee would like Partnership Specialist positions advertised more widely.  The Committee also suggested publicizing the contact list for the Partnership Specialists so that they could be contacted more readily.

The Committee suggested continuing the use of the Partnership Program in between censuses to further develop relationships with the communities.  Since keeping a full staff is not feasible, the Census Bureau should hire at least one person in each region to work full time on maintaining the relationships.

The Asian Advisory Committee pointed out that there is tension between the advertising program and the Partnership Program because the more that is spent on advertising the less you can spend on the Partnership Program.  The Committee thinks that personal contact with the people that you are trying to reach has more impact than an advertising campaign.  Money should be taken from advertising and redirected to the Partnership Program.  In areas where the Partnership Program is not able to reach the communities, community based organizations should be funded.

The Asian Advisory Committee would like Partnership Program evaluations to be completed by the staff hired by the Partnership Program.  This would help determine the lessons learned.  Feedback on the evaluation of the program is needed to know the level of service provided.  The specialists should have periodic contact before, during, and after the program with the Committee.  The Committee would like more engagement with the specialists and partners.  They would like the opportunity to meet with the specialists before and after the Census. They want to meet with the specialist to evaluate the Partnership Program.  If issues arise and they should get knowledge from others, the Committee would have the time to receive the information as a result of the periodic contact.

The Committee would like to include schools in the Partnership Program.  Getting information to the students and asking them about the Census would be beneficial.  The Committee suggested distributing the Census forms to students to give to parents, as well as speak to the parents to find out if the forms were completed.

REAC – Asian Advisory Committee

Recruitment and Hiring Debriefing

Tuesday, June 19, 2001, 2:45 p.m. - 4:15 p.m.

Facilitator and Recorder – Kim Whetsell & Terri Russell

Participants

Jon Melegrito – Executive, Director, National Federation of Filipino American Associations

Cyril Nishimoto – Executive Director, IWA, Inc.

Dr. K.V. Rao – Associate Professor, Bowling Green State University

Dr. Piyush C. Agrawal – The Association of Asian Indians in America

Resource Person:

Jan McStay – Partnership Specialist, Denver Regional Office

Committee Liaison:

Jane Sandusky – Planning, Research, and Evaluation Division

Summary of Issues

Census 2000 Successful Areas

The Committee believed awareness of the recruitment program was high.

The Census Bureau did a good job in the retention of temporary employees.

The Committee thought the number of Welfare-to-Work workers hired was good.

Overall, the Committee thought the quality of the temporary employees was high.

The Census Bureau's presence at national level conferences was well received.

The Committee thought the job fairs held by the Census Bureau were excellent.

The Census Bureau's recruitment and hiring program reduced unemployment rate for the nation.

Census 2000 Lessons Learned

The Census Bureau did not provide adequate expectations or guidance to the hiring managers.

The Census Bureau was slow in providing hiring results to people who were tested.

The more enumerators hired form the ethnic community the better. A familiar face is more trusted so the response rate would be correspondingly higher.

The Census Bureau's employment test was viewed as culturally biased.

The Committee thought the English for the employment test was too difficult for certain applicants.

The enumerators and the community groups should have a closer working relationship.

The Census Bureau did not hire enough Asian managers.

Ideas to Improve Census 2010

The recruitment manual should be published ahead of time and made more widely available to Asian communities.  Recruitment manuals should be made available to the REAC for their review.

The Census Bureau should try to be consistent in the hiring process used for managers.  In addition, they should make additional efforts to recruit a diverse management team.

The Committee thought the Census Bureau positions should be open to both U.S. citizens and legal residents.

The Census Bureau employee test should be more culturally sensitive (through question formulation) to minimize cultural bias.

The Committee would like to see an assessment take place of recruitment advertisements. Advertisements should be language specific to be targeted toward Asian communities.

The Census Bureau should hire recruiters specific to the Asian community.

The Committee thought recruitment should take place at the natural gathering areas for the Asian community (churches, stores, ballroom dances, karaoke bars, restaurants, and conferences).

Issues in Detail

Census 2000 Successful Areas

The Asian Advisory Committee was confident that awareness of the recruitment program was high. The materials informed interested applicants about the available positions.

The Committee thought that retention was high because of the available compensation.

The Committee saw the higher level of enumeration accuracy as a result of the employee quality maintained during the Census.

The Committee commented on the Census presence at conferences.  The Census Bureau participated by having a booth at national-level conferences, which the Committee thought was excellent. Although the booths were only designed for the distribution of general Census 2000 information, they also included recruiting information.  Having both types of information available helped to promote general awareness of the Census and available Census Bureau jobs.

Census 2000 Lessons Learned

The Committee would like the Census Bureau to provide hiring managers clearer expectations, as well as guidance on the application of procedures.

The Committee thought that the Census Bureau should provide results to applicants who are tested in a timely manner (tell them right away if they passed).

The Committee thought that response rates in specific ethnic communities would be greater if the enumerators were hired from their area.

The Committee expressed a desire to make the Census Bureau employment test more culturally sensitive.  The Census Bureau should assess the way questions are asked and/or presented.

The Committee would like the Census Bureau to use basic English for the tests to increase participation in populations with a lower level of reading capabilities.

The Committee thinks that a stronger relationship between the community groups and the enumerators will create better exposure for the enumerators within the community.  How successful the enumerators are is connected to the amount of contact they have with individual communities.  The Committee thought that doing this will increase the response from the Asian community.

Ideas to Improve or Enhance Census 2010

The Asian Advisory Committee would like the recruitment manual to be published ahead of time and made more widely available to the Asian community.  This will allow expectations to be known. In addition, this will increase the consistency across different geographical areas. Recruitment manuals should also be made available to the REAC for their review.

The Committee thought the Census Bureau should take additional efforts to recruit a diverse management team. Senior Executive Service (SES) positions should be open to both U.S. citizens and legal residents.

The Committee suggested that the individuals developing the employment tests should be culturally diverse so that the tests developed are culturally sensitive.

The Committee would like to see assessment of recruitment advertisements.  Advertisements should be language specific to be targeted toward Asian communities

The Committee suggested hiring community-specific Asian recruiters to recruit more Asian employees.

REAC – Asian Advisory Committee

MAF/TIGER Debriefing

Tuesday, June 19, 2001, 4:15 p.m. – 5:30 p.m.

Facilitator and Recorder – Kim Whetsell & Terri Russell

Participants

Jon Melegrito – Executive, Director, National Federation of Filipino American Associations

Cyril Nishimoto – Executive Director, IWA, Inc.

Dr. K.V. Rao – Associate Professor, Bowling Green State University

Dr. Piyush C. Agrawal – The Association of Asian Indians in America

Resource Person:

Linda Franz – Geography Division

Committee Liaison:

Jane Sandusky – Planning, Research, and Evaluation Division

Summary of Issues

Census 2000 Successful Areas

The Committee viewed the overall MAF/TIGER program as a success.

The Census Bureau did a great job of creating and maintaining the MAF.

Census 2000 Lessons Learned

The Committee identified issues with the program where there were two different households within the same address.

The Census Bureau experienced difficulties in identifying and counting multiple families who lived in the same housing unit.

The Committee noted issues with the delivery of Census forms to people using P.O. boxes.

The Census Bureau thought there was insufficient understanding of Census mapping techniques throughout partnerships, community specialists and professionals in the community.

Ideas to Improve Census 2010

The Census Bureau should correct legitimate duplicate addresses in the MAF.

The Census Bureau should be able to create multiple households in the same housing unit for unrelated families.

The Committee would like to see the Census Bureau coordinate with the U.S. Post Office to resolve P.O. box issues.  In addition, the Census Bureau should use the Post Office file to identify different family names used at the same address.

The Committee thinks the Census Bureau should leverage landlords to identify multiple families living within a single dwelling.

The Census Bureau should spend resources to develop new technologies to improve the MAF/TIGER program.

The Census Bureau should analyze the demographic characteristics of areas with address list deficiencies and/or problems to identify areas for improvement.

The Census Bureau should provide a wider understanding of Census mapping techniques to target partnerships, community specialists and professionals in the community.

Issues in Detail

Census 2000 Successful Areas

The Committee viewed the overall MAF/TIGER program as a success.

The Census Bureau did a great job of creating and maintaining the MAF.

Census 2000 Lessons Learned

The Asian Advisory Committee expressed concern with duplicated addresses within the same zip code.  Two different dwellings with the same address was also a problem.  The Committee would like more diligence to ensure legitimate identical addresses are not deleted.

Unrelated Asians living in the same dwelling were a concern for the Committee.  In the Asian community, one residence is often subdivided and there should be a method to identify and count multiple families living in the same housing unit.  Multiple families should not be included on the same form.

The Committee thought there was insufficient understanding of Census mapping techniques among community specialists and professionals in the community and throughout the Partnership Program.

Ideas to Improve or Enhance Census 2010

The Asian Advisory Committee thought the Census Bureau should correct duplicate addresses in the MAF.  Currently, the software deletes duplicate addresses.  This update is only needed for duplicate legitimate addresses.

There is often a case of different households in one dwelling.  The Committee would like the ability to create multiple households in the same housing unit for unrelated families.

The Committee thought that the Census Bureau should coordinate with the U.S. Post Office to resolve P.O. box issues.  The Post Office may have ideas to help the Census Bureau.  Perhaps the Post Office file could be used to identify different family names used at the same address.  In addition, landlords should be leveraged to identify people living within a dwelling. However, this may present a privacy issue.

The Committee suggests the Census Bureau spend more funding on technology to help with the MAF/Tiger program.  Spending resources on developing new technologies is important to continual improvement of the Census.  For example, satellite usage might be able to help identify vacant houses or new construction.

The Census Bureau should analyze the demographic characteristics of areas with address list deficiencies and/or problems to identify areas for improvement.

The Committee would like an expanded understanding of Census mapping techniques for Census partners, professionals in the community, and community specialists.  They should understand the maps and the mapping techniques to know where everyone is located.

REAC – Asian American Committee

Advertising Campaign Debriefing

Tuesday, June 20, 2001, 8:30am – 10:30am

Facilitator and Recorder – Kim Whetsell & Terri Russell

Participants

Jon Melegrito – Executive, Director, National Federation of Filipino American Associations

Cyril Nishimoto – Executive Director, IWA, Inc.

Dr. K.V. Rao – Associate Professor, Bowling Green State University

Dr. Piyush C. Agrawal – The Association of Asian Indians in America

Resource Person:

Leigh Moy – Economic Planning and Coordination Division

Committee Liaison:

Jane Sandusky – Planning, Research, and Evaluation Division

Summary of Issues

Census 2000 Successful Areas

The Committee viewed the advertising campaign at the national level as very successful in creating Census awareness.

The African American campaign used a talking Census form and civil rights songs, which were very successful.

The Committee thought the increased accuracy in the Census count was a result of the advertising campaign.

Census 2000 Lessons Learned

The Census Bureau should target ethnic communities through the use of familiar images in advertising.

The communities the Census Bureau may be trying to reach may not watch TV or read newspapers.

The Committee thought images and languages from the advertising campaign did not always match.

Advertising funding requirements are not necessarily the same across minority groups.

Awareness did not translate to an increased rate of return on forms.

The Committee thought the poster selection process was too "hasty."

The Census Bureau did not develop region specific advertisements (i.e., urban vs. rural).

There should be a better attempt to let people know about the additional avenues/venues for completing a Census form.

Specialists were not always aware of the details of the advertising campaign (process, budget, and criteria for selection).

The Committee thought distribution of posters was not adequate and mostly stayed in warehouses.

The Census Bureau should improve the selection criteria for hiring advertising companies, especially for a diverse group such as Asians.  The Census 2000 advertisements targeted toward Asian communities were unsatisfactory.

Ideas to Improve Census 2010

The Census Bureau should target campaigns to specific Asian groups and utilize images of Asian American heroes.

The Committee thought funding should be available to local groups to tailor advertising campaigns.

The Census Bureau should employ church groups and other community organizations for the advertising campaign and make advertising materials available to these groups.

The Committee would like to see a study conducted to analyze the correlation of the impact of advertising on rates of return.

The Census Bureau should evaluate the effectiveness of target campaigns specifically by ethnic groups

The advertising campaign should inform the public about follow-up programs available to them.  Most people did not know about the additional venues available.

The Census Bureau needs a distribution strategy and infrastructure for advertising campaign material distribution (timing, resources, and guidance on location to have maximum exposure).

The Census Bureau should use the Internet in 2010 for both the advertising campaign and data collection.

The Committee thought the Census Bureau should better assess the choice of outlets within each medium to advertise to more people (i.e., examine the process being used to choose newspaper A over newspaper B).

Explore the feasibility of using text messaging in promoting the Census.

The Census Bureau should study and understand how to target the hard-to-reach communities.

The Census Bureau should hold Asian-specific focus groups before and after the advertising campaign development.

Campaign materials should identify the specialist in the local community by giving their contact information for additional questions.

The Census Bureau should go back to the communities after the advertising campaigns are developed to identify translation and/or cultural sensitivity issues.

Different advertising methods are needed to appeal to intergenerational diversity within an ethnic group.  English-speaking advertisements should target 2nd and 3rd generation members of an ethnic group.

Issues in Detail

Census 2000 Successful Areas

The Committee viewed the advertising campaign at the national level as very successful in creating Census awareness.

The African American campaign used a talking Census form and civil rights songs, which were very successful.

The Committee thought the increased accuracy in the Census count was a result of the advertising campaign.

Census 2000 Lessons Learned

The Committee expressed a concern that though awareness was heightened, it may not have translated into a motivating factor in getting the community to participate in the Census.  The Census Bureau promoted awareness, but it was not specific to ethnic communities.  In essence, targeting ethnic communities was poor.  The Asian community needed to see familiar faces and hear familiar voices.

Those trying to be reached may not watch TV or read newspapers, so the media the advertising campaign focused on may not have reached the targeted community.

In some cases, the images and languages did not match, which should be improved for Census 2010.

Advertising funding was available, but the Committee thought the paid advertising group did not do a good job at allocating the funds.  The Asian community is more diverse than other groups; as a result, they need more funding for advertising.  Funding requirements are not the same across minority groups.

The advertising committee did not ask for feedback from the community for final advertising materials.  The Committee thought that some translations were unnatural and did not sound right.  This could have been avoided if the advertisers had worked more closely with the community.  The Committee sited an example where a television advertisement targeting suburban households did not go over well on the East Coast.  The Census Bureau should go back to the communities after the campaign is developed to identify potential problems such as translation issues and geographic differences.

The Committee thought that most people were not aware of the additional avenues/venues for completing forms such as the QAC.  There should be a better attempt at letting people know about the different avenues/venues.

The role of the Partnership Specialist is important and he or she should be informed about the whole process.  They should empower the specialist with knowledge so that the specialist is aware of the advertising campaign.  The Partnership Specialist should be aware of the process, criteria for selection, and budgeting of the advertising campaign.

Ideas to Improve or Enhance Census 2010

During the Census, the Census Bureau developed one campaign and then had to translate it into different languages.  In the future, the Committee would like to see the Census Bureau develop campaigns that target each ethnic group separately.  A different approach is needed for each group (i.e., Filipino, Korean, and Chinese) instead of one generic approach.

The Committee would like to see the Census Bureau target campaigns to the Asian community by utilizing images of Asian American heroes.

The Committee would like more thought to be given to the actual distribution of the posters and flyers.  Where the posters should be placed for the most effectiveness should be studied.  Resources are needed to maximize the effect of the advertising.  It would be helpful to local groups to have resources and strategic guidance on how to advertise more effectively.  The Census Bureau needs a distribution strategy (i.e., timing, resources, guidance on location to have maximum exposure) and an infrastructure for advertising campaign material distribution.  In addition, the local groups should be able to contact advertising representatives on the national level for advice and feedback.

The Committee would like to explore the feasibility of using text messaging in promoting the Census.  For example, cell phone users can receive text messages on their phones.  The advertising campaign's strategy should take into consideration all forms of technology for Census 2010.

The Committee suggested the Census Bureau should improve the selection criteria for the advertising companies hired, as well as the markets they contact.  In addition, the Committee thought the Census Bureau should better assess the choice of outlets within each medium to advertise to more people (i.e., examine the process being used to choose newspaper A over newspaper B).

The Committee thought the Census Bureau should study and understand how to target hard-to-reach communities.  The Census Bureau should use messages that speak specifically to this group to address their fears and concerns.  There is an increasing amount of immigrants that should be counted.  Given the Committee's knowledge of these people and where they reside, the Census Bureau should learn how to reach this population and craft an advertising campaign that speaks to them.  It is just as important to reach illegal residents as citizens.

The Committee would like the Census Bureau to recognize fully that the Asian community is very diverse.  The Census Bureau cannot apply the same advertising campaign for the Asian community as they do for the African Americans since the two groups are so different.  The Asian Advisory Committee would like advertising to allow the different groups to have the ability to create their own advertising materials.

The Committee suggested that English language advertisements specific to a group are needed as well as foreign language advertisements.  In addition, the Census Bureau should gear English-speaking advertisements toward second and third generation members of each ethnic group.

The advertising representatives should refer to the specialist in the local community.  The Asian Advisory Committee thought that the specialist should be available to answer any questions from the community.  A contact number is needed for people to call with additional questions.

The Asian Advisory Committee thought that more exciting advertising was needed for their community.  For example, the African American communities had a talking Census form, which was extremely successful and helped boost pride.  Print advertising images that are community-specific are needed, such as the American Indian campaign that had famous American Indians portrayed in their advertising.  The Committee would like similar advertisements for the Asian community.  The Committee would also like to see the Asian communities have more creative input into the advertising campaign.

Other Relevant Issues

The resource person mentioned that the Census Bureau is evaluating data right now for advertising for the Asian community.  The advertising agency shortchanged the Asian population because their complexity is much higher than say the African American community.  The saying "one size fits all" is not true in this case.  The agencies are doing work on tracking and exposure.  The Census Bureau hired an independent contractor that performed a survey on population awareness.  In addition, work is being done to determine the correlation of the advertising and rate of return.

For the Asian population, there is an added dimension to advertising to an ethnic group that is diverse as well as generationally diverse.  In addition to language and cultural differences, age adds complexity.  Where and how different advertising materials are placed in the communities is important.

REAC – Asian Advisory Committee

Data Collection Strategies Debriefing

Tuesday, June 20, 2001, 10:05am – 11:15am

Facilitator and Recorder – Kim Whetsell & Terri Russell

Participants

Jon Melegrito – Executive, Director, National Federation of Filipino American Associations

Cyril Nishimoto – Executive Director, IWA, Inc.

Dr. K.V. Rao – Associate Professor, Bowling Green State University

Dr. Piyush C. Agrawal – The Association of Asian Indians in America

Resource Person:

Raj Singh – Assistant Division Chief, Decennial Statistical Studies Division

Committee Liaison:

Jane Sandusky – Planning, Research, and Evaluation Division

Summary of Issues

Census 2000 Successful Areas

The Committee viewed the data collection process as very successful for enumeration.

The Committee stated the use of Web sites to report which forms had been reviewed as a success.

Census 2000 Lessons Learned

Local Census Offices and local community offices did not have appropriate access to the list of QACs in their areas.

The Be Counted forms needed to be promoted after Census Day to let communities know that they could still be counted if they did not receive a census questionnaire.  Confusion over how long people had to return their forms was an issue.

The Committee would like to see the Census Bureau designate QACs in a more timely manner.

The 1-800 number for the TQA program needed to be publicized more widely.  The advertising campaign must coordinate with and promote the TQA program.

The Committee thought problems arose during the NRFU as a result of pressure on the LCO to complete the assigned task faster and ahead of schedule.

Ideas to Improve Census 2010

Local Census Offices and local community groups should be provided with a list of QACs in their respective areas.

The Census Bureau should use a Web page to allow people to check the status of their Census form.

The Census form only allows six people to be enumerated on a single form for a housing unit.  This should be increased.  The Census Bureau should change the form to better capture the additional people in the household via phone, fax, or the Internet.

The Be Counted program should be expanded, particularly to target the hard-to-reach communities.

The Census Bureau should evaluate, strengthen, and improve the TQA program to monitor customer satisfaction and the treatment of callers.

The Committee would like the Census Bureau to increase the ability of Census participants to file Census forms over the phone instead of making participants wait to get the forms through the mail.

Bilingual Asian enumerators should be assigned to Asian neighborhoods.

The Be Counted program should work closer with community groups. In addition, the advertising campaign should specifically address the Be Counted Program to further promote the location of site, timing of when forms are going to be available, and overall coordination process with the community.

Issues in Detail

Census 2000 Successful Areas

The Asian Advisory Committee thought that the data collection process was successful and commended the quickness in enumeration. The process was extremely successful in providing the information over the Internet.

Census 2000 Lessons Learned

The Committee suggested Local Census Offices and local community offices did not have the list of Questionnaire Assistance Centers (QACs) in their respective areas.  This list would be a useful resource for the local offices to use.

The Committee thought the QAC offices needed to be designated by the Census Bureau in a more timely manner.

The Asian Advisory Committee did not believe that the Be Counted forms were available in a timely fashion.  The Be Counted forms were not well promoted before Census Day.  This is of critical importance for counting the hard-to-reach populations.

The Asian Advisory Committee suggested that the 1-800 number be publicized more widely, in the five languages other than English in which it was offered.  If the help line is only advertised in English, a large portion of the population will not know that it exists.

Pressure on the LCOs to complete the NRFU faster and ahead of schedule created problems during Census 2000.  The Committee thought the pressure applied to receive timely Census information forced avoidable errors.

Ideas to Improve or Enhance Census 2010

Local Census Offices and local community groups should be provided with a list of QACs in their respective areas.

The Census forms only allowed six people to be enumerated on a form for each household, which should be increased.  The Asian Advisory Committee identified how these additional people were counted as an issue for Census 2000. The Census Bureau should make it easier to capture the additional people in the household via phone, fax, or the Internet.

The Committee thought that the Be Counted program should be expanded, particularly as it addresses hard-to-reach communities.  The Census Bureau should be proactive and explore the expansion of the program.  The program must also address the hesitation of hard-to-reach communities to mail back their forms.  The Committee would like to see a formal study conducted for these hard-to-reach communities.

The Committee would like to see the TQA program strengthened.  Quality should be checked to ensure that consistent responses are given to callers.  There is a need to strengthen, evaluate and improve the TQA program to monitor customer satisfaction and the treatment of callers.

The Committee would like the Census Bureau to increase the ability of Census participants to file Census forms over the phone instead of making participants wait to get the forms through the mail.

The Committee would like to see the Be Counted forms available in a more timely fashion.  In addition, the mail back process should be streamlined with an increased availability of forms.  The Be Counted program should be better promoted to let communities know that they can still be counted after Census Day if they did not receive a Census questionnaire.

The Be Counted program should work closer with community groups. In addition, the advertising campaign should coordinate with the Be Counted Program to further promote the location of sites, timing of when forms are going to be available, and overall coordination process with the community.

Bilingual Asian enumerators should be assigned to Asian neighborhoods in Census 2010.

Other Relevant Issues

The Committee would like to see the break down for TQA between number of forms mailed out and number of forms taken over the phone.

REAC – Asian Advisory Committee

Language Program Debriefing

Tuesday, June 20, 2001, 1:15 p.m. – 2:15 p.m.

Facilitator and Recorder – Kim Whetsell & Terri Russell

Participants

Jon Melegrito – Executive, Director, National Federation of Filipino American Associations

Cyril Nishimoto – Executive Director, IWA, Inc.

Dr. K.V. Rao – Associate Professor, Bowling Green State University

Dr. Piyush C. Agrawal – The Association of Asian Indians in America

Resource Person:

Carol Briggs – Decennial Management Division

Committee Liaison:

Jane Sandusky – Planning, Research, and Evaluation Division

Summary of Issues

Census 2000 Successful Areas

The Census Bureau carried through with their promise to have questionnaires in languages other than English.

The Census Bureau provided language assistance guides in 49 different languages.

Census 2000 Lessons Learned

The Committee commented that there is a difference between conversational and classical or traditional translations of the Asian language, which should be recognized when developing Census materials.

Translated forms should be evaluated to ensure they are asking for the correct information.

Census participants experienced delayed responses to requests for in-language forms and guides.

Language assistance guides were printed, but distribution problems existed.

Census participants had to rely on receiving the advance letter to request an in-language form, which is an ineffective two-step process.

The Committee thought the literal translation of the Census forms created misunderstandings, instead of clarity, for the Asian community.

Ideas to Improve Census 2010

The Census Bureau should use Census 1990 data (or other relevant data) for analysis and comparison purposes.

The Census Bureau should evaluate the response time between the request and receipt of in-language forms for Census participants.

The Committee thought the Census Bureau should create a targeted mailing of the Census form in a language specific to Asian communities, instead of using the current two-step process beginning with the advance letter.

The capabilities of the contractors should be evaluated more carefully to ensure credibility and breadth of languages.

The Committee would like to see multi-lingual advertising materials address the issue of trust to reach the hard-to-reach populations.

The Census Bureau should find a way to put two forms (in different languages) in the same envelope so that a targeted mailing to specific ethnic communities can be done.

The Census Bureau should explore the use of more languages for the Census form.

In regard to the advance letter, the Census Bureau should print messages in languages other than English on the outside of the envelope.

The Census Bureau should establish quality control standards for language translations.

A pre-testing of the Census form should occur with each language group after it is translated.

Issues in Detail

Census 2000 Successful Areas

The Census Bureau carried through with their promise to have questionnaires in languages other than English.

The Census Bureau provided language assistance guides in 49 different languages.

Census 2000 Lessons Learned

The Committee noted that there is a difference between conversational and classical or traditional translations of the Asian language, which should be recognized when developing Census materials.

The Asian Advisory Committee expressed concern regarding the effectiveness of the resource guides.  In addition, the Committee thought some of the translations contained errors.

Although the Committee made a suggestion to the Census Bureau to write information in an Asian language to alert the recipient of its importance, the changes were not made.  The envelopes for the advance letter were already at the printer by the time the Census Bureau asked the Committee for their opinion.

The Committee thought that when a standard Asian template was used, important information was lost in the translation. The Asian Advisory Committee noticed that message translation affects its effectiveness.  The translated messages should have more than one translation so it is more effective to the varied audiences.  The Committee thought that levels of translation are needed and that literal translation of templates creates misunderstanding for the Asian community

Ideas to Improve or Enhance Census 2010

The Committee would like to see the Census Bureau continue to develop resource guides in different languages, but the translated guides should be tested to ensure proper translation.  In addition, the questions should be tested to make sure they are asking for the correct information.

The Census Bureau should use Census 1990 data (or other relevant data) for analysis and comparison purposes.  When analyzing data, other information resources should be studied (such as literature reviews) from inside and outside of the Census Bureau.

The Census Bureau should evaluate the response time between the request and receipt of in-language forms for Census participants.

The capabilities of the contractors should be evaluated more carefully to ensure credibility and breadth of languages.

The Committee would like to see multi-lingual advertising materials address the issue of trust to reach the hard-to-count communities.

The Census Bureau should find a way to put two forms (in different languages) in the same envelope so that a targeted mailing to specific ethnic communities can be done.

The Census Bureau should explore the use of more languages for the Census form.

The Census Bureau should establish quality control standards for language translations.  In addition, pre-testing of the Census form should occur with each language group after it is translated.

The Asian Advisory Committee would like to see targeted mailing of the in-language forms to the Asian community to replace the current two-step process.  The Committee thought that people should not have to rely on getting the advance letter to receive the in-language form.

# Appendix D – Hispanic Advisory Committee

REAC – Hispanic Advisory Committee

Partnership Debriefing

Tuesday, June 19, 2001, 1:05 p.m. – 2:35 p.m.

Facilitator and Recorder – James Green & Kristen Wagner

Participants

Dr. John Garcia – Professor, University of Arizona

Tony Chavez – Attorney

Dr. Aileen Lucero –  Associate Professor, The Metropolitan State College of Denver

Dr. Fernando Soriano – Associate Professor, California State University San Marcos

Dr. Jorge Chapa – Professor, Indiana University

Susana Gomez – Assistant Director, AFL-CIO (Civil Rights Department)

Ana Sol Gutierrez – Director, Computer Sciences Corporation

Resource Person:

Gustavo Paredes – Partnership and Data Services Branch, Field Division

Stan Rolark – Division Chief, Customer Liaison Office

Renee Jefferson-Copeland – Program Administrator, Customer Liaison Office

Committee Liaison:

Idabelle Hovland – Branch Chief, Decennial Management Division

Summary of Issues

Census 2000 Successful Areas

The Census Bureau, as well as Local governments, provided increased support and resources toward Partnership Program.

The use of a multi-lingual program (for staff and advertisements) increased the success of the Partnership Program.

The Partnership Program increased the relevance of Census 2000 at a local level.

Census 2000 Lessons Learned

The Hispanic Advisory Committee suggested that the Census Bureau use Partnership Programs better during the Non-Response Follow-Up (NRFU) procedures to create continuous awareness and advertising that the Census was not over.

Ideas to Improve Census 2010

The Committee suggested that a new acronym for the Non-Response Follow Up (NRFU) be used so that it can be more easily advertised.

The Committee suggested that the Census Bureau create a Census month or season instead of just a Census Day.

Issues in Detail

Census 2000 Successful Areas

The Hispanic Advisory Committee noted that improvement in attitude of the Census Bureau executive staff regarding the use of a Partnership Program improved the overall Census response rate. As more partners were involved, more people were reached.  The committee commented that this was one of the major successes of Census 2000.

The Partnership Program created a more inclusive environment than in past years. The lower income population was more engaged in Census 2000. The use of a cross-generation approach worked well in the Hispanic community. The use of different types of partners really brought the Census home and showed its relevance on many levels.

The Partnership Program worked well because individuals were not just getting information from Washington, D.C., but from people that lived and worked in their community. In addition, the information was coming not only from the Census Bureau, but other organizations and local leaders.

Using local partners increased the confidence local communities had in the Census and added to the success of the Census. The local leaders in the different communities were able to instill more trust in the Hispanic community (specifically in the immigrant populations).

Having a more diverse group sending the Census message seemed to build trust within the Hispanic community regarding personal privacy issues.

Local partners influenced the local media. Unsolicited articles were written across the country.  This helped spread the Census message at a local level.

Open houses in the local district offices seemed to be successful in engaging local officials in the Census process.

Census 2000 Lessons Learned

Communication from the Census Bureau to the local partners was not very good. The partners should be better informed on their roles, responsibilities, and how they should operate.

After Census Day it seemed like the Census process was completely over. The partners were not active in getting the word out regarding the Non-Response Follow-Up (NRFU) period. The Committee suggested that there needed to be better communication throughout the regions regarding the NRFU time period.

Ideas to Improve or Enhance Census 2010

The Committee recommended having a Census month or season rather than a Census Day. The thought behind this is that people will realize the Census is not just a one-day event.  As a result, participation should be more inclusive and will increase.

It was mentioned during the session that the use of the acronym "NRFU" was not optimal. The Census Bureau might want to look into a new acronym for the purpose of better advertising throughout the follow-up time period.

Other Relevant Issues

The Hispanic Advisory Committee had a discussion during this session to determine why the 2000 Census was better than previous Censuses. The Committee listed the following reasons—

- There was a mandate to find better way to operate

- There was support from the executive branch

- The economy was strong

- The more traditional use of funding

- Strong leadership

- The Census Bureau tried to learn from past experiences

- Non-traditional approach (grassroots vs. national campaign only)

- Regional office flexibility.

REAC – Hispanic Advisory Committee

Recruitment and Hiring Debriefing

Tuesday, June 19, 2001, 2:45 p.m. – 4:15 p.m.

Facilitator and Recorder – James Green & Kristen Wagner

Participants

Dr. John Garcia – Professor, University of Arizona

Tony Chavez – Attorney

Dr. Aileen Lucero –  Associate Professor, The Metropolitan State College of Denver

Dr. Fernando Soriano – Associate Professor, California State University San Marcos

Dr. Jorge Chapa – Professor, Indiana University

Susana Gomez – Assistant Director, AFL-CIO (Civil Rights Department)

Ana Sol Gutierrez – Director, Computer Sciences Corporation

Resource Person:

Gabe Sanchez – Field Division

Committee Liaison:

Idabelle Hovland – Branch Chief, Decennial Management Division

Summary of Issues

Census 2000 Successful Areas

The Hispanic Advisory Committee considered the fact that the Census Bureau removed the hiring priority for U.S. citizens a success. Because of this, the Census Bureau could hire local legal residents that were representative of their communities.

The ability to pay prevailing local wages allowed the Census Bureau to obtain and retain more qualified people.

The Welfare-to-Work program was a success in the Hispanic communities.

The multi-lingual staffing test enabled more people to apply for a job with the Census Bureau.

The advertising and promotion of available Census jobs was successful in informing the Hispanic community about employment opportunities.

Census 2000 Lessons Learned

Census Bureau staff at all levels did not and does not reflect the racial or ethnic diversity of the U.S. population. As a result of insufficient representation, decisions for Census 2000 were made that were not sensitive to the needs of the Hispanic population. In the few cases where Census Bureau staff reflects the diversity of the U.S. population, cultural sensitivities were taken into consideration and programs were generally effective.

There is a need for a dedicated position or a greater capability within the PIO to respond to the needs and concerns of the Latino community (English and Spanish-speaking).

The 1-800 number did not have a Spanish language capability.

The Census field offices did not reflect the diversity of the areas in which they were located.

Ideas to Improve Census 2010

A performance standard should be established to measure the success of having a diverse staff.  Measurement should take into consideration all aspects of the program, including the person responsible and senior management.

The Census Bureau and the Department of Commerce should build a larger pool of bilingual staff members (interns and regular staff) through recruitment and outreach strategies.

The Census Bureau can increase awareness of Census positions and hiring practices through local media and partnership programs.

The Census Bureau should add a Spanish language capability to the 1-800 number.

Issues in Detail

Census 2000 Successful Areas

The Hispanic Advisory Committee identified several Census 2000 recruitment and hiring areas of success. One of the biggest changes identified from the 1990 Census was the hiring of legal non-citizens for temporary Census positions. There were certain positions where the Census was able to hire legal residents even if the resident was not a citizen. This policy was a success because word got out quickly to other non-citizens that there were potential jobs available. The Census Bureau was able to hire local immigrants to better represent the Latino community. In certain cases, having non-citizens was advantageous because they could encourage other non-citizens to participate in Census 2000.

Another success mentioned by the Hispanic Advisory Committee was the Census Bureau's ability to pay a prevailing wage that was based on the local labor market. The ability to pay these wages allowed the Census Bureau to obtain and retain more qualified people.

The advertising and promotion of available Census jobs was excellent. Effective grass roots advertising resulted in a strong awareness that the Census Bureau was hiring. The Committee was also pleased with the multi-lingual materials available to potential Spanish-speaking employees. Job applicants were able to take competency tests in Spanish, giving them a better chance of receiving a job, as well as a better understanding of what they would be doing for the Census Bureau.

The Hispanic Advisory Committee was pleased to see the Census Bureau hired Welfare-to-Work recipients for available job positions. This program appeared to the Committee to be a success.

Census 2000 Lessons Learned

The Hispanic Advisory Committee expressed concerns with the Census Bureau's ability to hire a diverse staff, especially in positions of authority. It was thought that the Census Bureau staff at all levels did not and does not reflect the racial or ethnic diversity of the population. The Committee highlighted the PIO as an example. It was stated that the PIO office should have employees that are not just bilingual, but bicultural, to better respond to the concerns of the Latino community. There were individuals in positions that were bilingual, but they were not dedicated to the Hispanic population. The Hispanic Advisory Committee was concerned that when staff is not made up of bilingual and bicultural employees, decisions are made that are not sensitive to the Hispanic population. In a few cases where there was a diverse staff, it proved to be effective. At the Committee's suggestion, the Census Bureau should build on the capability of bilingual recruitment through internships for permanent and temporary staff.

The 1-800 number that was advertised for people to call for employment did not have Spanish capabilities. In most cases, the operator was not able to speak Spanish and was only able to pass the person's identification information on to the Local Census Office for follow-up. As a result, many prospective Latino job applicants were lost.

In some instances, the field offices did not reflect the diversity of the areas in which they were located. The Committee thought that to get the best participation in all communities, the field office staff should be representative of that community.

Ideas to Improve or Enhance Census 2010

The Hispanic Advisory Committee identified several areas for enhancement for the Recruitment and Hiring Program for Census 2010. Many of the areas identified are not new areas, but are simply areas that can be expanded for improvement.

Continue hiring a bilingual and bicultural staff. The Census Bureau can continue to have a large pool of potential applicants by focusing on the recruitment of interns through the Department of Commerce and through outreach and recruitment strategies. If more permanent bilingual and bicultural staff are hired, it will have a positive impact on the hiring of temporary staff for the Census.  As a result, the needs of the Hispanic population will be better addressed.

A performance standard should be established to be able to measure the success of having a diverse staff. Measurement should take into consideration all aspects of the program, including the person responsible and senior management.  Performance measures should be in place to show the correlation.

The 1-800 number provided so that people could obtain more information regarding Census jobs should have Spanish capabilities to assist and encourage more Spanish-speaking applicants.

The Census Bureau should continue to increase the awareness of hiring through the use of local media and partnership programs.

REAC - Hispanic Advisory Committee

MAF/TIGER Debriefing

Tuesday, June 19, 2001, 4:15 p.m. – 5:30 p.m.

Facilitator and Recorder – James Green and Kristen Wagner

Participants

Dr. John Garcia – Professor, University of Arizona

Tony Chavez – Attorney

Dr. Aileen Lucero –  Associate Professor, The Metropolitan State College of Denver

Dr. Fernando Soriano – Associate Professor, California State University San Marcos

Dr. Jorge Chapa – Professor, Indiana University

Susana Gomez – Assistant Director, AFL-CIO (Civil Rights Department)

Ana Sol Gutierrez – Director, Computer Sciences Corporation

Resource Person:

Cathy McCully – Assistant Chief, Redistricting Office

Linda Franz – Geography Division

Committee Liaison:

Idabelle Hovland – Branch Chief, Decennial Management Division

Summary of Issues

Census 2000 Successful Areas

There was much improvement and accuracy in the geographic information for Census 2000.

There was better cooperation from Local governments in Census 2000 than in past Censuses.

Census 2000 Lessons Learned

The maps provided on the Geography Division's Internet site were hard to print in black and white. The maps were in color, but many people only had black and white printers.

The Census Bureau needs a better understanding of local Hispanic populations.

Ideas to Improve Census 2010

The Census Bureau should create a map index by geography.

The Census Bureau should develop the ability to print maps from the Internet in black and white.

Please Note: The Hispanic Advisory Committee was not familiar with MAF/TIGER Program. The time spent during the MAF/TIGER debriefing session was used more as a question and answer period.  The Committee asked the Census Bureau resource person several questions to learn more about the program. The Census Bureau resource people recommended the Committee look at the home page of the Census Bureau's Geography Division to learn more about MAF/TIGER and how it operates.  The issues identified in this section arose from the questions answered by the Census Bureau resource person(s).

Issues in Detail

Census 2000 Successful Areas

The Committee thought there was improvement over the 1990 Census in available geographic information as a result of MAF/TIGER.

In addition, the Committee thought that Local governments were willing to help collect more accurate geographic information for the Census Bureau.

Census 2000 Lessons Learned

Maps that were available on the Internet worked well and provided good information, but they did not print well in black and white. Many of the people that would potentially use these maps do not have access to color printers.

The Census Bureau needed to have a better understanding of the local Hispanic population and how this community receives mail. There should be a distinction between those who receive mail at a Post Office box only and those who receive mail at a residence and a Post Office Box (this would help with those that need a physical address follow-up).

Ideas to Improve or Enhance Census 2010

The Geography Division should improve the ability to print in black in white by converting the maps to black and white or providing an option to print in black and white.

The Committee would like to see an enhanced ability to search Census geographic information. The MAF/TIGER has information that people may really want to use, but the organization of the information is difficult to understand.

REAC - Hispanic Advisory Committee

Advertising Campaign Debriefing

Wednesday, June 20, 2001, 8:30 a.m. – 10:00 a.m.

Facilitator and Recorder – James Green and Kristen Wagner

Participants

Dr. John Garcia – Professor, University of Arizona

Tony Chavez – Attorney

Dr. Aileen Lucero –  Associate Professor, The Metropolitan State College of Denver

Dr. Fernando Soriano – Associate Professor, California State University San Marcos

Dr. Jorge Chapa – Professor, Indiana University

Susana Gomez – Assistant Director, AFL-CIO (Civil Rights Department)

Resource Person:

Ken Meyer – Special Assistant to the Associate Director for Communications

Committee Liaison:

Idabelle Hovland – Branch Chief, Decennial Management Division

Other non-committee attendees

Wendy Glass – Young &Rubicam

Summary of Issues

Census 2000 Successful Areas

The Advertising Program gave tremendous exposure to the Census on both the national level and the local level.

The television commercials were realistic and helped people relate and understand the importance of filling out the Census forms.

The radio advertisements were effective in rural areas.

The Advertising campaigns were sensitive to several cultural groups throughout the campaign.

Newspaper and magazine coverage was extensive.

Funding for Census advertising increased the ability to successfully advertise Census 2000 to the population.

Feedback or input from the Hispanic Advisory Committee was well received throughout the advertising campaign.

Census 2000 Lessons Learned

The Census Bureau needed better quality control on translations to avoid conveying the wrong message to diverse groups.

In some respects, commercials may have promised too much in regard to what people will receive as a result of filling out the Census form.

Primetime coverage and awareness was more effective than off-hour advertising used in the 1990 Census.

Ideas to Improve Census 2010

Because this was a new joint effort for national awareness, the Census Bureau should capture the knowledge gained through the successes and failures of the advertising campaign.

The Census Bureau should hire permanent individuals for the Communication Office and ACS staff that are bilingual and bicultural (Spanish and English) with expertise in advertising and communications.

The Census Bureau should start the advertising process for Census 2010 two to three years earlier than what was done for the 2000 Census.

Focus groups should be created and used throughout the advertising campaign.

The Census Bureau should continue to consult with the Hispanic Advisory Committee (and other REAC Committees) regarding appropriate advertising campaigns.

The Census Bureau should explore ways to increase the opportunities for smaller Hispanic advertising agencies to address the concerns of the Hispanic community.

Issues in Detail

Census 2000 Successful Areas

The Census Bureau created tremendous exposure on both the national level and at the local level through the advertising campaign. The Committee thought it was effective that the national campaign was supplemented locally through Regional Offices. By having both campaigns, the Census Bureau was able to reach a more comprehensive group of people. The Committee believed that a national campaign would not have the ability to address certain topics and/or issues that are specific to specific diverse communities.

Both the television commercials and radio advertisements were successful for different markets. The Committee viewed the television commercials as realistic and effective for getting people to realize the importance of filling out the Census forms. The radio advertisements were particularly effective in rural areas.

For the most part, the Hispanic Advisory Committee agreed that the advertising campaigns used were sensitive to cultural groups, including the Latino population.

Newspaper and magazine coverage was extensive throughout the country. Even Latino magazines had unsolicited articles about Census 2000. The extensive newspaper and magazine coverage may have been the result of established partnerships. The Partnership Program and the advertising campaign complemented each other in several arenas.

Many of the 1990 Census television commercials were aired during the middle of the night or at odd hours. For Census 2000, the advertisements were placed on prime time, thereby creating more coverage and awareness.

Having funding available for both national and local advertising contributed to the overall success of the advertising campaign. In the past, advertising was not heavily budgeted for. The Committee agreed that it was useful to have funding for local level advertising campaigns. One Committee member mentioned that for a local campaign in Denver a Spanish comic book was created for children to read and learn more about Census 2000. It was noted that this kind of local and targeted advertising was effective.

The Hispanic Advisory Committee believed that its involvement in advertising campaigns contributed to the success of the campaign because the Committee had a strong understanding of local Latino issues and communities and helped ensure the right message was being conveyed.

Census 2000 Lessons Learned

It was stated that the Census Bureau needed better quality control over the translation of advertising materials. The Committee stated that it had seen translations that could be viewed as misleading. Better quality control could ensure that translations are consistent and convey the proper message.

The Committee thought that some of the television commercials were too strong or may have promised too much in regard to what people would receive as a result of completing and mailing the Census 2000 form. One of the commercials showed children going into a closet for class to illustrate to parents that if their children were not counted in the 2000 Census, their school district may not receive enough money for their children to have a classroom.

The topic of confidentiality was not heavily addressed throughout the advertising campaign. The Committee did not state that it should have been addressed more, but stated that confidentiality was a huge issue for the Latino community. The Committee expressed that advertising may be one venue for encouraging participation and eliminating fears of confidentiality for the Latino community.

Ideas to Improve or Enhance Census 2010

Because it was a new joint effort for national awareness, the Committee would like to see the Census Bureau capture and use the knowledge it gained about Census 2000 advertising campaign successes and failures. This was a new arena for many of the national media outlets to try to capture the national community and many lessons can be learned from what was done in 2000.

The Committee thought there was a need to capture the best ways to reach all populations, including the Latino community. A group of national advertisers should be established to decipher what was learned. The Committee suggested that focus groups should be conducted for viewers to discuss how certain advertisements captured their attention or helped to convince them to fill out their forms.

The Census Bureau should hire permanent individuals for the Communication Office and  ACS staff that are bilingual and bicultural (Spanish and English) with expertise in advertising and communications.

The Committee thought that the advertising process should start sooner and include more focus groups.

The REAC should continue to be involved throughout the advertising campaign. Feedback and input from the REAC should be incorporated into the advertising process for Census 2010.

The Census Bureau should explore ways to increase the opportunities for smaller Latino advertising agencies to participate in the advertising campaign. Smaller Latino advertising agencies may be able to better address the concerns of the Latino community. Bravo was used during Census 2000 to advertise to the Hispanic community, which is a start, but the Census Bureau should explore the use of more Latino advertising agencies in the future.

Future advertising campaigns should address the needs and concerns of not only the Spanish-speaking Hispanic population, but the English-speaking Hispanic population as well. It was mentioned that some of the Spanish advertisements were designed with the possibility of an English voice over, but the Committee was not sure if any of these actually took place. English is the primary language for much of the Hispanic population in the United States. The Committee thought that more research should be done to address the needs and concerns of the English-speaking Hispanic population.

REAC - Hispanic Advisory Committee

Data Collection Strategies Debriefing

Wednesday, June 20, 2001, 10:05 a.m. – 11:15 a.m.

Facilitator and Recorder – James Green and Kristen Wagner

Participants

Dr. John Garcia – Professor, University of Arizona

Tony Chavez – Attorney

Dr. Aileen Lucero –  Associate Professor, The Metropolitan State College of Denver

Dr. Fernando Soriano – Associate Professor, California State University San Marcos

Dr. Jorge Chapa – Professor, Indiana University

Susana Gomez – Assistant Director, AFL-CIO (Civil Rights Department)

Resource Person:

Samonica Green – Planning, Research, and Evaluation Division

Committee Liaison:

Idabelle Hovland – Branch Chief, Decennial Management Division

Summary of Issues

Census 2000 Successful Areas

The Non-Response Follow-Up (NRFU) strategy was a successful way to capture additional populations not reached through the regular Census process.

Census 2000 Lessons Learned

Potential respondents should be able to receive in-language questionnaires from the Telephone Questionnaire Assistance (TQA) Line.

The TQA line should be able to respond to the large volume of calls.

The Questionnaire Assistance Centers (QACs) should be more visible and in better locations.

The quantity of staff and/or volunteers working at the QACs should be increased.

A risk of duplication exists in the Be Counted Program with children from divorced households and college students.

The Be Counted Program should be more heavily advertised to be effective.

Ideas to Improve or Enhance Census 2010

In-language questionnaires should be provided through the TQA line.

QACs should be planned better and site selection criteria for QACs should be more strategic.

The Census Bureau should budget to rent or buy QAC space, if necessary.

The Census Bureau should budget for more QAC staff.

Issues in Detail

Census 2000 Successful Areas

The Non-Response Follow-Up (NRFU) process was a successful way to capture additional populations not reached through the regular Census process. The NRFU was completed on time and within budget. The Committee mentioned the majority of the Latino population responded well to the personal contact provided through the NRFU.

Census 2000 Lessons Learned

Potential respondents should be able to receive in-language questionnaires from the Telephone Questionnaire Assistance (TQA) line. Not only could callers not receive in-language questionnaires, but also the TQA line did not have the capacity to handle the volume of calls received. When the TQA line is being evaluated from Census 2000, the Committee would like to see the caller volume broken down by the number of Spanish-speaking calls.

The Committee agreed that the Questionnaire Assistance Centers (QACs) were not placed in the best locations. Because most of the QACs were staffed on a volunteer basis, it was difficult to dictate where the QAC would be set up. Several Committee members mentioned the difficulties they had finding the QACs after they entered the specified location.  Many times QACs were not staffed. The Committee suggested that the number of staff and/or volunteers working at the QACs should be increased. In addition, the Committee would like to see more strategic location planning and selection criteria for QACs. It might be worth paying for space to have more effective locations and to reach a broader audience.

The Committee commented that the Be Counted Program was not working very reliably throughout Census 2000 and created a risk of duplication, especially with children of divorced parents and college students. The Be Counted Program was not well advertised and often times the public did not know about the program until it was too late. To be effective, the program should be more heavily advertised.

Ideas to Improve or Enhance Census 2010

To enhance the data collection strategies for Census 2010, the Committee would like to see in-language questionnaires provided through the TQA line. In addition, the TQA line capacity should be expanded to handle a larger volume of callers.

The Committee also recommended that the Census Bureau examine strategies for better planning and site selection of QACs. A budget should be taken into consideration for QACs to improve locations and reach a broader audience. Additionally, the Committee would like to see increased staffing levels for the QACs.

REAC - Hispanic Advisory Committee

Language Programs Debriefing

Wednesday, June 20, 2001, 1:15 p.m. – 2:15 p.m.

Facilitator and Recorder – James Green and Kristen Wagner

Participants

Dr. John Garcia – Professor, University of Arizona

Tony Chavez – Attorney

Dr. Aileen Lucero –  Associate Professor, The Metropolitan State College of Denver

Dr. Fernando Soriano – Associate Professor, California State University San Marcos

Dr. Jorge Chapa – Professor, Indiana University

Susana Gomez – Assistant Director, AFL-CIO (Civil Rights Department)

Resource Person:

Jane Ingold – Decennial Management Division

Committee Liaison:

Idabelle Hovland – Branch Chief, Decennial Management Division

Summary of Issues

Census 2000 Successful Areas

The incorporation of the mail-back card increased the multi-lingual participation in Census 2000.

Census 2000 Lessons Learned

The Census Bureau should not promise more than it can deliver (i.e., direct mail language forms).

There was insufficient testing of direct mail procedures (amount and timing).

English and Spanish forms could not be produced and mailed at the same time.

The Census Bureau needs sufficient data regarding linguistically isolated populations to improve the enumeration accuracy.

The in-language forms should be used where clearly appropriate.

The advance letter should be multi-lingual.

Quality assurance should be tightened for all translated materials that are going to "final print."

Ideas to Improve or Enhance Census 2010

All Language Program processes and procedures should be tested early and often.

The Census Bureau should utilize U.S. Postal Service, ACS, Census and other data to locate linguistically isolated populations.

The Census Bureau should solicit REAC support on the Language Program as early as possible.

The Census Bureau should test for possible resistance to language specific materials prior to launching the Language Program for the next Census.

Create strong partnerships and develop a budget to help Questionnaire Assistance Centers (QACs) meet the needs of a multi-lingual community.

Integrate outreach efforts to speakers of languages other than English from the beginning of the Census 2010 process.

Plan for and hire Spanish-speaking staff in the early stages of the Language Program.

Issues in Detail

Census 2000 Successful Areas

Incorporation of the mail-back card increased multi-lingual participation in Census 2000.  Participants were able to mail these cards to request a Census form in a different language.

Census 2000 Lessons Learned

The Census Bureau should not promise more than it can deliver.  Direct mail language forms were promised to various communities, but were not followed through with.

The Census Bureau had difficulties with insufficient testing of direct mail procedures.  They were unable to produce and mail English and Spanish forms at the same time and did not plan enough time for linguistically isolated populations.  More time should be factored into the process for linguistically isolated populations.

The Census Bureau should avoid sending questionnaires in languages that are not appropriate for that particular community. In-language forms should be used where clearly appropriate.  The Census Bureau should use all available resources to determine where in-language forms should be sent. After the American Community Survey (ACS) is in place, Spanish-speaking populations should be easier to identify.  The advance letter should be multi-lingual to determine what type of form to send.

Quality assurance should be tightened for all translated materials that are going to "final print".  A committee member commented on a form that instructed a person that spoke a language other than English to do something in English, which they could not read.  Other committee members found translation errors in various Census Bureau tests, letters and advertisements.  The Census Bureau should institute quality assurance procedures in its Language Program.  The Committee added that it understood the difficulties of translating languages when there are multiple translators translating several different materials.

Ideas to Improve or Enhance Census 2010

All processes and procedures should be tested early and often to ensure they will work during the actual Census program.  The Census Bureau should also test for possible resistance to language materials prior to launching the program.

The Census Bureau should utilize U.S. Postal Service, ACS, Census and other data to locate linguistically isolated populations.

The Census Bureau should solicit REAC support on the Language Program as early as possible.

Create strong partnerships and develop a budget to help Questionnaire Assistance Centers (QACs) meet the needs of a multi-lingual community. The QACs are a great place to provide assistance to the Spanish-speaking population.  The Census Bureau should integrate outreach efforts to speakers of languages other than English at the beginning of the Census Language Program.

Plan for and hire Spanish-speaking staff in the early stages of the Language Program.

Other Relevant Issues

During this session, the Hispanic Advisory Committee had a discussion about literacy.  Printed forms do not help an illiterate person no matter what language it is in.  The Census Bureau may want to take literacy into account for Census 2010.

# Appendix E – Native Hawaiian and Other Pacific Islander Advisory Committee

REAC – Native Hawaiian and Other Pacific Islander (NHOPI) Advisory Committee

Partnership Debriefing

Tuesday, June 19, 2001, 1:05 p.m. – 2:35 p.m.

Facilitator and Recorder – Anshu Singhal & Chris Jimenez

Participants:

Clinton Helenihi – Vice-President, Pacific American Foundation

Dr. Faye Untalan – Associate Professor, University of Hawaii

William Emmsley – CEO, Samoan Service Providers Association (SSPA)

Mary Salas – President, Chamorro Community Council

Resource Person:

Brenda August – Branch Chief, Partnership and Data Services Branch, Field Division
Stan Rolank – Division Chief, Customer Liaison Office

Renee Jefferson-Copeland – Program Administrator, Customer Liaison Office

Committee Liaison:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Summary of Issues

Census 2000 Successful Areas

The fact that the Census Bureau initiated a Partnership Program in the NHOPI community was considered a success.

Staff at the Census Bureau headquarters provided strong support to State and Local governments.

The Partnership Specialist in the Los Angeles area was very effective because he was trusted and respected in that NHOPI community.

Census 2000 Lessons Learned

The Committee thought that there was no outreach to the Micronesians.

More time is needed to plan develop effective Partnerships with State and Local governments.

The Census Information Center (CIC) stopped accepting applications because of the Federal Register Notice deadline.

Ideas to Improve Census 2010

Provide incentives such as in-kind funds or grants for vendors to support community based organizations.

The Census Bureau should hire more Partnership Specialists who are local leaders and are trusted and respected in their communities.

The Census Bureau should get more state and local leaders involved in the Partnership Program.

Issues in Detail

Census 2000 Successful Areas

The Partnership Program did not occur in the NHOPI community in the previous Census because the NHOPI were included in the Asian and Pacific Islander racial grouping.  The Committee thought that the Partnership Program was a success because the Census Bureau recognized the Pacific Islander community and efforts were made to form partnerships with NHOPI local businesses and state and Local governments.

The Census Bureau supported and encouraged participation of the Governor of Hawaii, the Department of Business and Economics, and local businesses.  The Census Bureau staff received strong support from the Lieutenant Governor of Hawaii for the Census advertising campaign.  His influence was effective in getting corporate sponsorship for the promotion of Census 2000.  These businesses provided food, prizes, and incentives for Pacific Islanders to participate in the Census kick-off.  In addition, this event was held in a cultural palace that had significant meaning to the NHOPI community.  As a result, the Census kick-off was well attended.

The Los Angeles area hired a Partnership Specialist who is a Samoan minister and a civil servant.  Because of his dual role in the community, this Partnership Specialist was well respected and trusted by Pacific Islanders.  He had an established relationship with the community that allowed him to be "culturally sensitive" to the needs of Pacific Islanders.  As a result of this rapport, he was successful in making Pacific Islanders aware of Census 2000.

Census 2000 Lessons Learned

Micronesians were not included in the partnership outreach program.  The Committee thought that the Partnership Program needed to target all Pacific Islanders.  The Census Bureau should develop relationships with local leaders to understand who lives within the community, what the culture and languages are, and where the clusters of the Micronesian population are located.

The Committee thought that there was not enough notice in starting the outreach program.  The outreach program began in the year 2000 for the 2000 Census.  In addition, the NHOPI Advisory Committee was not established until October of 1999.  The Committee thought that if more time was available, proper planning was exercised, and the Committee's recognition was established earlier, the Census Bureau would have been successful in reaching more of the Pacific Islander communities.  The Committee suggested that the Census Bureau start its outreach efforts two to three years before Census 2010 begins.

Initially people did not understand the role of the Census Information Center (CIC), only later did people start understanding that the responsibility of the CIC was to provide a community-based component to reach undercounted populations that may not have access to Census data through existing channels.  A Federal Register Notice was published stating that the CIC would stop accepting applications for partnership.  The Committee thought that more interest would have been generated, if the CIC program had still accepted applications after the deadline.

Ideas to Improve or Enhance Census 2010

The Committee suggested re-structuring community based organizations so that those vendors who help support the census could apply for in-kind funds or grants.  For example, in-kind funds would be made available to a company that provides transportation to the Questionnaire Assistance Centers (QACs), sponsorship and advertising.

The Committee strongly believed that if more Partnership Specialists were hired, outreach to the NHOPI community would have been more successful.  These Partnership Specialists should be community leaders who have an established relationship with the community.  Furthermore, these Partnership Specialists should be respected, trusted, and culturally sensitive to Pacific Islander issues.

The Census Bureau must get more NHOPI community leaders involved with the Census process.  Community leaders can stress the importance of the Census and get Pacific Islanders involved.  For example, the Governor of California had a budget for the 2000 Census.  Congressional leaders from Carson, California supported Census events.  Census got the Governor of Hawaii involved and resulted in sponsorship in a very cultural and meaningful place.

REAC – Native Hawaiian and Other Pacific Islander (NHOPI) Advisory Committee

Recruitment and Hiring Debriefing

Tuesday, June 19, 2001, 2:45 p.m. – 4:15 p.m.

Facilitator and Recorder – Anshu Singhal & Chris Jimenez

Participants:

Clinton Helenihi – Vice-President, Pacific American Foundation

Dr. Faye Untalan – Associate Professor, University of Hawaii

William Emmsley – CEO, Samoan Service Providers Association (SSPA)

Mary Salas – President, Chamorro Community Council

Resource Person:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Committee Liaison:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Summary of Issues

Census 2000 Successful Areas

The Census Bureau provided preparation for the Census 2000 examination.

Census training occurred at civic organizations such as churches and schools.

Census 2000 Lessons Learned

The NHOPI Advisory Committee thought that Pacific Islanders were "appallingly absent" in the Workforce Report D-284, dated March 14, 2001.

A more defined process for applications and feedback to job applicants should be developed.

Advertisements and posters are needed in more specific Pacific Islander languages.

Ideas to Improve Census 2010

The Census Bureau should put more emphasis on hiring Native Hawaiians and Pacific Islanders locally and nationally.

The Census Bureau should form partnerships with Federal Government staff who perform job-training services.

Use Partnership Specialists to recruit NHOPI citizens in their native communities.

Develop an action plan to prepare qualified applicants to take the Census exam and prepare for job interviews.  The action plan must also include hiring Census takers.

Issues in Detail

Census 2000 Successful Areas

Preparation provided by the Census Bureau helped raise scores on the Census examination.  Members of the Committee knew people, from the NHOPI community, who successfully passed the Census exam because of the preparation program.

Training for the Census examination occurred in community based organizations (CBOs) such as churches and schools.

Churches were an effective place to advertise and train because they are important cultural centers where Pacific Islanders typically gather.

Census 2000 Lessons Learned

The NHOPI Advisory Committee thought that the Pacific Islanders were "appallingly absent" in the Workforce Report D-284 dated March 14, 2001.  The NHOPI Advisory Committee assumed that there were either no NHOPI Census employees or the NHOPI employees were included in the Asian statistics.  As a result, the NHOPI Advisory Committee thought there was a need to hire and recruit more Pacific Islanders, locally and nationally, so that the Census Bureau could be more aware of NHOPI issues.

There should be a more defined process for applications and feedback to job applicants.  People were confused about the notification and hiring process of preparing for and taking the Census exam and the selection of Census employees.  Members of the NHOPI Advisory Committee knew people who had scored excellent on the exam but never received a phone call for an interview or job offer.

Recruiting advertisements and posters should be in more Native Hawaiian and Pacific Islander languages.  Posters had an "Asian/Pacific Islander" focus, which insulted the NHOPI community.  For example, posters had Asian faces with Samoan languages; therefore the faces and words did not match and the translations were not correct.  It was very difficult for Pacific Islanders to relate to the posters, because the language was not translated properly.

Ideas to Improve or Enhance Census 2010

The Census Bureau should use cultural venues specific to targeted groups for its outreach efforts.  For instance the Census Bureau would be more effective in recruiting Pacific Islanders by using more community based organizations (CBOs) such as churches, schools, and community offices, for advertising jobs for Census enumerators, training and interviewing qualified candidates, and administrating the Census exams.

The Census Bureau should form partnerships with Federal Government staff who perform job-training services.  The Census Bureau does not necessarily need to tap into its budget for training, but other Federal organizations could be used to provide job-training services.  It was suggested this could be done under the Work Force Investment Act.

The Census Bureau could recruit more Census enumerators by hiring Partnership Specialists that reflect the make-up of the community.  The Census Bureau should also utilize all Census outreach staff (such as local and regional staff of Pacific Islander heritage) and use more "word-of-mouth" strategies.  "Word-of-mouth" strategies work well in the Pacific Islander community and can create synergy and generate interest in Census activities.  A Partnership Specialist who is trusted and respected by the Pacific Islander community can be effective in informing and recruiting Pacific Islanders.

More time is necessary to properly plan for hiring qualified applicants.  The Census Bureau should develop an action plan with the following milestones: preparing qualified applicants for the exam, preparing qualified applicants for job interviews, and hiring qualified applicants.

REAC – Native Hawaiian and Other Pacific Islander (NHOPI) Advisory Committee

MAF/Tiger Debriefing

Tuesday, June 19, 2001, 4:15 p.m. – 5:30 p.m.

Facilitator and Recorder – Anshu Singhal & Chris Jimenez

Participants:

Clinton Helenihi – Vice-President, Pacific American Foundation

Dr. Faye Untalan – Associate Professor, University of Hawaii

William Emmsley – CEO, Samoan Service Providers Association (SSPA)

Mary Salas – President, Chamorro Community Council

Resource Person:

Joe Marinucci – Branch Chief, Geography Division

Committee Liaison:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Summary of Issues

Census 2000 Successful Areas

The MAF/TIGER Hawaiian Homeland efforts went well.

Census Bureau experts assured the data collected was accurate and concise.

Census 2000 Lessons Learned

None of the NHOPI Advisory Committee members took part in any formal discussions on the MAF/Tiger initiatives.

The Census Bureau should track the mobility and immigration of Native Hawaiian and Other Pacific Islanders to the continental U.S.

The Census Bureau should communicate the enumeration of the Pacific Islands to the NHOPI Advisory Committee.

Ideas to Improve Census 2010

The Committee suggested that the Census Bureau establish a point of contact from the NHOPI Advisory Committee to participate in MAF/TIGER initiatives.

The Committee suggested that the Census Bureau construct a MAF for the Pacific Islands for Census 2010.

Issues in Detail

Census 2000 Successful Areas

The Hawaiian Homeland efforts went well.  There was a very specialized effort to identify unconventional neighborhoods in rough and sparse areas.  A format was developed for accounting for Homelands in America Samoan, Guam, and all other Pacific Islands.

The Committee also thought that Census Bureau experts assured the data collected was accurate and concise.  Experts verified the transfer of data from state and local boundary information to the TIGER database.  In addition, Hawaiian Homeland boundaries were checked for and errors corrected.

Census 2000 Lessons Learned

Although the Committee thought that the MAF/TIGER efforts were successful in the Hawaiian Homelands, they indicated that no NHOPI Advisory Committee member was part of the MAF/TIGER initiatives.  The late recognition of the NHOPI Advisory Committee by the Census Bureau was the cause of the lack of involvement.

The Census Bureau should track the mobility and immigration of Native Hawaiian and Other Pacific Islanders to the continental U.S.  By tracking the migration of Pacific Islanders to the continental U.S., the Census Bureau would have a better idea where Pacific Islanders are relocating and may have better indication of where the pockets of high-density Pacific Islanders are.

The Census Bureau should communicate the enumeration of the Pacific Islands to the NHOPI Advisory Committee.  MAF information may be useful for sampling communities, especially in American Samoa and Guam to verify if "the NHOPI numbers and statistics" are correct.

Ideas to Improve or Enhance Census 2010

The Committee suggested that the Census Bureau establish a point of contact from the NHOPI Advisory Committee.  Establishing a point of contact from the NHOPI Advisory Committee would help future MAF/TIGER initiatives on other Pacific Islands.  This point of contact could help focus or target pockets of high-density Pacific Islanders that the MAF/TIGER staff may be unaware.

The Committee suggested that the Census Bureau construct a MAF for the Pacific Islands for Census 2010.  The Census Bureau will adopt use of a short form of the American Community Survey (ACS) for Census 2010.  The Pacific Islander respondents were confused and apprehensive with the long form.  Pacific Islanders also thought that the long form was intrusive (e.g., how much money do you make).  The content of the ACS form is still being discussed with Local governments.  ACS will not be used for Guam and Samoa.

REAC – Native Hawaiian and Other Pacific Islander (NHOPI) Advisory Committee

Paid Advertising Campaign Debriefing

Wednesday, June 20, 2001, 8:30am – 10:00am

Facilitator and Recorder – Anshu Singhal & Chris Jimenez

Participants:

Clinton Helenihi – Vice-President, Pacific American Foundation

Dr. Faye Untalan – Associate Professor, University of Hawaii

William Emmsley – CEO, Samoan Service Providers Association (SSPA)

Mary Salas – President, Chamorro Community Council

Resource Person:

Jennifer Marks – Division Chief, Census 2000 Public Information Office

Committee Liaison:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Summary of Issues

Census 2000 Successful Areas

The advertising campaign was well received in Southern California.

Advertising contractors were open to suggestions by the NHOPI community.

The State Governments of California and Hawaii participated in the advertising campaign.  The California government provided funding for targeted advertising.

Census 2000 Lessons Learned

The advertising campaign was poorly planned and that there were budget constraints.

The Committee thought that its members could have provided value-added support to the advertising campaign.  However, the Census Bureau was late in recognizing the NHOPI Advisory Committee.

The Committee was disappointed with the Current Population Survey that did not identify the NHOPI community as a stand-alone demographic, thereby reducing the significance of the community.

Ideas to Improve Census 2010

The Committee thought that the advertising campaign should be a national effort, not a local one (i.e., think globally act locally).

The advertising campaign should target schools to educate people about the Census.

The Census Bureau should seek leaders in the community to identify culturally sensitive issues.

A NHOPI Advisory Committee member should participate in the planning of the Paid Advertising Program for Census 2010.

Issues in Detail

Census 2000 Successful Areas

The advertising campaign was effective in Southern California because it showed different Pacific Islander groups, used cultural artists (art), reflected the Pacific Islander community (photos), and motivated the community.  The advertising showed that it knew its audience and targeted the audience well.  One of the most effective advertisements was a poster of a grandmother and a baby.  This appealed to Pacific Islanders because they are very family-oriented.

The State governments of California and Hawaii participated in the advertising campaign.  The State government approached the Census Bureau to elicit ways in which they could help.  In addition, the State of California set aside a budget to help offset the cost of Census advertising.  Sponsorship from State governments generated interest from the community and local business.  In Hawaii, the Census kick-off was held in a cultural palace that was important to NHOPI.  Local businesses helped by sponsoring food, prizes, and other incentives.

An advertising campaign was initiated that separated Native Hawaiians and Pacific Islanders, from the Asian community.  This campaign included helping local communities create advertisements in their native languages that were used on local radio stations (using a trusted and familiar voice) and in local television ads.

Census 2000 Lessons Learned

Advertising campaign advertisements were uncoordinated, confusing, and in some cases misrepresented the NHOPI community.  One poster depicted Asians dressed in Pacific Islander clothing, using words that were poorly translated into Samoan.  This misrepresentation turned-off many Pacific Islanders and did very little to motivate their involvement.  The NHOPI Advisory Committee approached the Census Bureau in an effort to solicit recognition of the misrepresentation and lack of NHOPI advertising.  In response, the posters were changed to reflect the entire Pacific Islander population.  However, the posters were implemented only a month before the Census.

The Committee thought that its members could have provided value-added support to the national advertising campaign.  However, the Census Bureau was late to consult the NHOPI Advisory Committee.  The national advertising campaign did not start until six months before the Census was to begin.  The advertisers did not have enough time to develop advertising that was culturally sensitive to the NHOPI population.  Additionally, the advertising firms did not consult representatives from each of the NHOPI cultural groups that would be targeted in the advertising campaigns.

Enumerators were hired to conduct a Current Population Survey.  The committee thought the intent of the survey was to identify the ethnic diversity of the American population to accurately create targeted audiences.  As a result of the survey, NHOPI community members were considered part of the "Diverse American Campaign" initiative.  The Committee was disappointed with the results of the survey because the results did not identify the NHOPI community as a stand-alone demographic, thereby reducing the significance of the community.

Ideas to Improve or Enhance Census 2010

Advertising must be a national effort, not just a local one (think globally act locally).

Local cultural groups had very little involvement with the national advertising campaign.  The State of California took it upon itself to develop localized, more targeted campaigns that were very successful.  However, the same California advertisements were used in Hawaii with very little affect.  NHOPI advertisements should appear nationally.  The benefit is two-fold: (1) the advertisement will reach geographically dispersed NHOPI community members and (2) the advertisement will act as a global awareness to other ethnic groups that NHOPI is a distinct ethnicity, worthy of recognition.

Advertising should target schools and make the NHOPI community more aware of the Census.  The advertising campaign should do more than get people involved.  The campaign should be more educational; make people aware of the importance of the Census and what the Census may do for them or their community.  The Census in Schools programs should be expanded and more youth organizations should be solicited to become involved.

The Committee suggested that the Census Bureau seek leaders in the NHOPI community to identify culturally sensitive issues.  Community leaders can help advertisers identify pockets of high-density Pacific Islanders and the culturally sensitive issues affecting the community at large.  An alliance with these civic leaders could mitigate the risk of advertising misrepresentation.

California's Partnership Specialist was a pivotal catalyst in assuring that the NHOPI community was not only involved but also properly targeted in advertisements.

A NHOPI Advisory Committee member should participate in the planning of the Paid Advertising Program for Census 2010.  A representative from the NHOPI Advisory Committee can advise the advertising staff on translations, languages, cultural dress, and introduce the advertising representatives to the leaders of the NHOPI community.

REAC – Native Hawaiian and Other Pacific Islander (NHOPI) Advisory Committee

Data Collection Strategies Debriefing

Wednesday, June 20, 2001, 10:05am – 11:15am

Facilitator and Recorder – Anshu Singhal & Chris Jimenez

Participants:

Clinton Helenihi – Vice-President, Pacific American Foundation

William Emmsley – CEO, Samoan Service Providers Association (SSPA)

Mary Salas – President, Chamorro Community Council

Resource Person:

Dottie Douglas – Field Division

Committee Liaison:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Summary of Issues

Census 2000 Successful Areas

A Partnership Specialist, who was a minister and a civic leader, guided people to complete questionnaires.

The long form used for data gathering captured important information for the Census Bureau.

Census 2000 Lessons Learned

The Census Bureau had to enumerate in the Hawaiian Homelands.

Pacific Islanders did not respond well to the Census Bureau mailings because the questionnaire was too intrusive.

Ideas to Improve Census 2010

The Committee suggested that the Census Bureau use the NHOPI community's network to obtain relevant information on the community.

The Committee suggested the Census Bureau hire more Partnership Specialists who are trusted and respected by the NHOPI community.

The Committee suggested the Census Bureau's mail-outs should be specifically targeted to the NHOPI community to appeal more to the community.

Issues in Detail

Census 2000 Successful Areas

A Partnership Specialist, who was a minister and a civic leader, guided people to complete the Census questionnaire.  This Specialist held town hall meetings with community stakeholders to explain the importance of the long form questionnaire.  In addition, he instructed the community on how to complete the long form questionnaire.  Due to the success of this Partnership Specialist, the Committee thought the Census Bureau should use community leaders to motivate the community to fill out the questionnaires.

The long form used for data gathering captured important information for the Census Bureau.  The long form questionnaire had explanations and instructions to help the reader complete the form.  Complete Count Committees (CCC) also helped the reader complete the long form questionnaire.

Census 2000 Lessons Learned

The Census Bureau had to re-enumerate in the Hawaiian Homelands.  The mail-outs had low return because most Pacific Islanders did not trust the U.S. Government and threw the forms away.  The Committee cited the following example of Government mistrust: The response was sporadic due to political problems in the Rice vs. Cayetano election.  The community became angry because of the legal battle involved in this campaign, which led the community to not respond to the Census.  The Census Bureau also needed special efforts in enumerating people living in non-traditional housing including natives who lived on the beach.

Pacific Islanders did not respond well to the Census Bureau mailings because the questionnaire was too intrusive to this culture.  The Mailout/Mailback campaign was not effective because of language barriers, literacy problems, and cultural issues.  Many people did not trust the intent of the long form and thought that the form was linked to the Internal Revenue Service (IRS).  Others thought the questions were too intrusive because they concerned confidential information such as a household salary.

Ideas to Improve or Enhance Census 2010

The Committee suggested that the Census Bureau use the NHOPI community's network to gain information on this community.  The Census Bureau should use community centers, such as churches, schools, and other community based organizations (CBOs), to gather information.  Group interaction can help facilitate the data collection process by explaining the instructions and the intent of the long form.  A communication network could also help identify homeless and non-traditional housing in Hawaii.

The Committee suggested that the Census Bureau hire more Partnership Specialists who are trusted and respected by the NHOPI community.  The Census Bureau should recruit more culturally appropriate Partnership Specialists who can explain the long form used for data collection by hosting town hall meetings, attending organization meetings, and by initiating a Train-the-Trainer program.  These specialists should be trusted by the community.  The Census should hire a Partnership Specialist that is representative of each NHOPI group.

REAC – Native Hawaiian and Other Pacific Islander (NHOPI) Advisory Committee

Language Program Debriefing

Wednesday, June 20, 2001, 1:15 p.m. – 2:15 p.m.

Facilitator and Recorder – Anshu Singhal & Chris Jimenez

Participants:

Clinton Helenihi – Vice-President, Pacific American Foundation

William Emmsley – CEO, Samoan Service Providers Association (SSPA)

Mary Salas – President, Chamorro Community Council

Resource Person:

Manuel de la Puente – Assistant Chief, Statistical Research Division

Committee Liaison:

Bob Gabbard – Partnership and Data Services Branch, Field Division

Summary of Issues

Census 2000 Successful Areas

The Census Bureau was successful in recognizing the Samoan language and becoming more sensitive to other languages.

A Telephone Questionnaire Assistance (TQA) program was established so that respondents could call and request help in a variety of languages.

Census 2000 Lessons Learned

The Census Bureau could improve on translations and word usage in its advertising campaigns.

The Committee thought that they could have provided value-added support to the translations.  However, the Census Bureau was late in recognizing the NHOPI Advisory Committee.

Pacific Islander respondents called the Telephone Questionnaire Assistance (TQA), but were unable to receive assistance.

Ideas to Improve Census 2010

The Committee suggested that the Census Bureau should target desired languages for Census 2010.

The Committee suggested that the Census Bureau should establish a Translation Group with a representative from the NHOPI Advisory Committee.

The Committee suggested that the Census Bureau execute a better plan to allow time for proper translations.

Issues in Detail

Census 2000 Successful Areas

The Census Bureau was successful in recognizing the Samoan language and becoming more sensitive to other languages.  The Language Program was an excellent effort by the Census Bureau to reach out to the NHOPI community.

Telephone Questionnaire Assistance (TQA) was created so respondents could call and request help in a variety of languages.  The Census Bureau had established the TQA to assist respondents by providing instructions in a variety of languages.  Respondents could call this number and navigate through the phone system.  A Census Bureau representative would come to the line and help the respondent.  This area of the Language Program was a success.

Census 2000 Lessons Learned

The Census Bureau could improve on translations and word usage in its advertising campaign.  There were not many materials in NHOPI languages in Hawaii.  The materials that were available had poor translations in which entire meanings were misrepresented.  This confused respondents.  In addition, some posters had misspellings.  Consequently, the posters had to be returned and redone.  As a result of the poor translations, the Census Bureau could have captured bad or incomplete data.  The Committee suggested translations should be done and checked by more than one person.

The Committee thought that they could have provided support to ensure translations were correct and appropriate.  However, the Census Bureau was late in contacting the NHOPI Advisory Committee.  The Committee thought that if the NHOPI community was recognized earlier by the Census Bureau, problems with translations could have been mitigated.  The NHOPI Advisory Committee could have helped the Census Bureau target specific Pacific Islanders with correct languages, correct usage, and correct translations.

Pacific Islander respondents called the Telephone Questionnaire Assistance (TQA), but were unable to receive assistance.  Although the Committee recognized that the Census Bureau was trying to reach the Pacific Islanders through TQA, oftentimes the system did not work.  Respondents would wait for someone to help, but no one came to the line.

Ideas to Improve or Enhance Census 2010

The Census Bureau should expand the number of languages the Census questionnaire is available in beyond the current six.  The Committee suggested that the Census Bureau should do studies to determine what other languages are needed (based upon Census 2000 data) and add those to the Language Program in Census 2010.  The Census Bureau should ensure that a qualified group or committee translates the materials.

The Committee suggested that the Census Bureau should establish a Translation Group with a representative from the NHOPI Advisory Committee.  It is important to have a conceptual translation versus a literal translation.  The Committee used the term "Cognitive Acquiescence" to try to think like the targeted respondents.  The NHOPI Advisory Committee believed that misinterpretation resulted because only one person did the translations for Census 2000 materials.  Translation should be a group effort.  A review process should be instituted for translated material to ensure quality control.

The Committee suggested that the Census Bureau start the Language Program earlier to allow time for proper translations.  Planning early can help—

- Identify relevant languages

- Translate the materials

- Provide group translations

- Designate a committee

- Review

- Cognitive testing

- Ensure the Census questionnaire is reviewed for proper translation.

- Task the NHOPI Advisory Committee for consultation.

# Appendix F – Acronym List

| AAR | After Action Review |
| --- | --- |
| ACS | American Community Survey |
| AIAN | American Indian and Alaska Native |
| BA&H | Booz Allen & Hamilton |
| CBOs | Community Based Organizations |
| CCCs | Complete Count Committees |
| REACs | Race and Ethnic Advisory Committees |
| ESL | English as a Second Language |
| GPS | Global Positioning Systems |
| LCO | Local Census Office |
| LUCA | Local Update of Census Addresses |
| MAF/TIGER | Master Address File/TIGER Database |
| NHOPI | Native Hawaiian and Other Pacific Islander |
| NRFU | Non-Response Follow-Up |
| QAC | Questionnaire Assistance Center |
| RCC | Regional Census Center |
| SAP | Statistical Area Program |
| SES | Senior Executive Service |
| TQA | Telephone Questionnaire Assistance |
| USPS | United States Postal Service |

# Text boxes

June 19 – 20, 2001

Race and Ethnic Advisory Committees

Census 2000 Debriefing Report

U.S. Department of Commerce

U.S. Census Bureau

Census Advisory Committees and

Special Populations Liaison Office