North American Carbon Program

Linking Landscape-scale Carbon Monitoring with Forest Management

2007 Progress Report

(NASA proposal # CARBON/04-0225-0191)

Contents

1. Project History									page 3

2. Project Description									page 4

3. Progress Report and Plans								page 11

4. Synthesis Activities									page 14

5. Northern Forest Soil Carbon							page 15

6. Proposed Future Work								page 16

APPENDIX 1: Field Manual Summary 						page 17

APPENDIX 2: Data Management Plan						page 19

APPENDIX 3: Land Classification							page 24

APPENDIX 4: List of Products							page 27

Partial List of Participants in Landscape-scale Carbon Monitoring

Richard Birdsey, USDA Forest Service

Marie-Louise Smith, USDA Forest Service

Harry Valentine, USDA Forest Service

Michael Ryan, USDA Forest Service

Randall Kolka, USDA Forest Service

Steven McNulty, USDA Forest Service

John Hom, USDA Forest Service

Ken Clark, USDA Forest Service

Yude Pan, USDA Forest Service

Linda Heath, USDA Forest Service

Dave Hollinger,USDA Forest Service

Coeli Hoover, USDA Forest Service

John Bradford, USDA Forest Service

Chris Potter, NASA (Ames Research Center)

Steven Klooster, California State University

Vanessa Genovese, California State University

Michael Lefsky, Colorado State University

Peter Weishampel, University of Minnesota

Scott Ollinger, University of New Hampshire

Michael Gavazzi, North Carolina State University

1. Project History

In 2001 we initiated a series of research studies at NE and NC to enhance capacity in carbon cycle science.  We strengthened our scientific capability to contribute to the strategic priorities of the USGCRP.  We targeted the CCSP Strategic Plan’s “North American Carbon Program” (NACP) as the highest priority for future research.

In 2002 we proposed to initiate an improved forest carbon observation and monitoring system to augment existing capability at the Forest Service network of experimental forests and at intensive research and monitoring sites such as the LTER and AmeriFlux networks.  Three related activities comprise the improved observation system: (1) development and deployment of improved field measurement techniques to enhance ongoing monitoring activities, (2) implementation of an efficient and cost-effective forest carbon monitoring network based on the Forest Service experimental forest network, and (3) development of data analysis and integration methods.  Improved estimates of carbon stocks and flows will provide a strong scientific foundation for development and deployment of carbon sequestration technology to mitigate greenhouse gas emissions.  Anticipated products include key input data for predictive models and scenario analysis, comprehensive and timely analyses and reports that support an increasing interest in forest carbon management, improved monitoring and estimation methods, and customized studies of opportunities to protect and enhance America’s forest productivity.  Enhancing observations at experimental forests has additional benefits such as facilitating use of these sites for carbon management research and demonstration projects, and providing the basis for an “early warning” capability to detect the initial impacts of climate change.

A national planning workshop was held in June 2003 to devise a preliminary sampling strategy and determine the suite of appropriate measurements. The objective was to develop a common suite of measurements for application at condition sample sites (tier 3) associated with the North American Carbon Program (NACP).  At this workshop we identified a list of variables, developed guidelines for sample site selection, and discussed consistent sampling protocols for the proposed “tier 3” sites.  Two documents were developed: a generic field manual of recommended field measurements for intensive forest carbon monitoring, and a recommended sampling design for landscape-scale monitoring.

Three pilot studies were begun in 2004 in different areas of the U.S. to test methods and develop a consensus on specific protocols:

- Northeast pilot at Bartlett, NH with emphasis on remote sensing, foliar chemistry, data analysis, and integration methods.  Marie-Louise Smith (lead), Linda Heath, David Hollinger, Coeli Hoover, other FS scientists and University of New Hampshire.

- North Central pilot at Marcell, MN with emphasis on CO2 and CH4 fluxes and cooperation with Canada. Randy Kolka (lead), Christian Giardina, other FS scientists and University of Minnesota.

- Rocky Mountain pilot at 3 alpine sites featuring methods for mountain terrain and cooperation with Mexico.  Mike Ryan (lead), other FS scientists and University of Colorado.

2. Project Description

OVERVIEW

The USDA Global Climate Change Program has recently funded several pilot projects to examine the potential of sites with intensive ground-based measurements to aid in the development of landscape level carbon flux estimates.  The sites, termed “Tier 3” sites in the North American Carbon Program, are intended to tie the spatially extensive, but coarsely resolved, measurements made through remote sensing and forest inventory to the spatially intensive and highly resolved measurements made at AmeriFlux sites.  To more fully develop the potential of connecting intensive and extensive monitoring, and increase our ability to develop accurate terrestrial carbon budgets for various forest management and disturbance scenarios, we propose to expand upon this effort by extending our ground-based measurements across additional levels of forest management intensity, by adding Lidar measurements, by developing ecosystem process models at two distinct scales, and by linking landscape monitoring to carbon management at a scale relevant to land managers.

Our proposal consists of the following three linked objectives: (1) develop a consistent set of landscape-scale estimates of carbon stocks and productivity (NPP, NEP) for stands at various stages of succession following land management activities and natural disturbances, and evaluate their uncertainty; (2) develop and validate two compatible process models to simulate (a) effects of natural disturbances on carbon stocks and productivity at the ecoregion scale, and (b) effects of forest management activities on carbon stocks and productivity at the forest stand scale; and (3) develop and evaluate two decision support tools for estimating and reporting carbon stocks and changes in carbon stocks for use by forest carbon managers.  Achieving these objectives will constitute a significant advance in availability of relevant and useful ecosystem data for broad application by the scientific, policy, and land management community, and lead the way toward implementation of landscape monitoring on a much broader scale than currently possible.

A physiologically-based individual tree modeling component (AMORPHYS) will facilitate using the field data to estimate NPP and NEP for managed tree stands in various stages of development, and will provide the ability for land managers to update or project stand-level inventories of carbon stock for project evaluation and reporting to greenhouse gas registries.  We plan to strengthen our ability to map and characterize landscapes through remote sensing technologies, primarily MODIS and Lidar.  Finally, this suite of landscape-scale data will be used to parameterize decision support tools such as CASA-CQUEST for analysis of carbon cycle impacts of operational forest management and to implement carbon management programs.

The main products of this research include precise statistical estimates and maps of carbon stocks and productivity for a variety of forest landscape conditions; improved process models at ecoregion and stand scales; and decision-support tools for land managers interested in carbon management.

Total budget for 3 years: $1,074,716

Project period: March 1, 2005 through December 31, 2008

Landscape research and monitoring sites:

- Marcell Experimental Forest, Northern Minnesota

- Bartlett Experimental Forest, New Hampshire

- Fraser Experimental Forest, Colorado

- Niwot Ridge LTER, Colorado

- Glacier Lakes Ecosystem Experimental Site, Wyoming

- The Parker Tract (Weyerhauser land), North Carolina

- Silas Little Experimental Forest, New Jersey (added in 2006)

“ROADMAP” LINKING DATA, MODELS, AND DECISION SUPPORT

We envision a multi-component process to link data collection and process models with decision support needs (Figure 1).  Our roadmap consists of 3 broad activities as illustrated in Figure 1: (1) develop a consistent set of landscape-scale estimates of carbon stocks and productivity (NPP, NEP) for stands at various stages of succession following land management activities and natural disturbances, and evaluate their uncertainty; (2) develop and validate process models to simulate (a) effects of natural disturbances on carbon stocks and productivity at the ecoregion scale, and (b) effects of forest management activities on carbon stocks and productivity at the forest stand scale; and (3) develop and evaluate decision support tools for estimating and reporting carbon stocks and changes in carbon stocks for use by forest carbon managers.  Achieving these objectives will constitute a significant advance in availability of relevant and useful ecosystem data for broad application by the scientific, policy, and land management community, and lead the way toward implementation of landscape monitoring on a much broader scale than currently possible.

Six landscape monitoring sites began testing the field protocols in April 2004; a sixth (New Jersey) began in 2005.  The sites were selected to represent a variety of managed and unmanaged forest conditions in different physiographic regions, so that the protocols can be thoroughly tested using a realistic range of applications.  Figure 1 shows the locations of the pilot test landscapes along with a representation of existing and potential flux tower sites and other intensive monitoring sites without flux towers.  Except for the Southern site, these locations are on public lands and therefore protected from unanticipated human disturbances.

A summary list of variables is shown in Table 1.  Similar to intensive monitoring, important variables that define the ecosystem “state” such as vegetation type, foliage nitrogen concentration, and soil C:N ratio will be measured along with automated measurements of key “driving variables” such as light, temperature, and precipitation that control the rate of ecosystem carbon uptake and loss. These state and driving variables will be measured at different vegetation conditions within landscapes, allowing estimates of NPP and NEP to be derived as closely as possible from field measurements, supplemented by models of ecosystem C exchange that are parameterized for each landscape monitoring location.

Table 1. Selected land measurement variables and scale of measurement.

| Example Variable | Extensive Monitoring | Landscape Monitoring | Intensive Monitoring |
| --- | --- | --- | --- |
| Land cover | X | X | X |
| Leaf area | X | X | X |
| Disturbance | X | X | X |
| Live biomass | X | X | X |
| Litterfall |  | X | X |
| Soil CO2 flux |  | X | X |
| Methane flux |  | X | X |
| Dissolved Organic C |  | X | X |
| Net Ecosystem Exchange of CO2 |  |  | X |

TASK LIST FROM ORIGINAL PROPOSAL

Task 1. Harmonize classifications and definitions [PI and CO-PIs].

Task 1a. Develop crosswalk between Forest Inventory (FIA) forest types, MODIS land classes, and CASA land classes.

Task 1b. Agree on classification of natural disturbances and management activities.

Task 1c. Ensure all components adhere to definitions of ecosystem carbon pools used in greenhouse gas registries.

Task 2. Estimate and map carbon stocks and productivity for landscape sites.

Task 2a. Lidar.  Acquire Lidar imagery for the selected landscape monitoring sites – target is 3x3 km square at each site.  Produce maps of stand structure scaled up from biometric measurements; explore linkages with stand model; determine spatial and temporal characteristics of disturbances. [Co-PI Lefsky]

Task 2b. Biometrics.  Continue existing (pre-proposal) biometric measurements at the core 1x1 km square at each site.  Add (this proposal) biometric measurements to parameterize stand model. Add (this proposal) biometric measurements at Lidar validation sites in the 3x3 km square. [Co-PIs Kolka, Smith, Ryan, McNulty, Valentine]

Task 2c. Data compilation.  Combine intensive data, landscape data, and remote sensing to characterize the temporal and spatial variation in carbon stocks and productivity estimates. Develop and apply consistent forest classifications based on FIA forest types and selected natural disturbance and management classes [Co-PIs Kolka, Smith, Ryan, McNulty, Lefsky]

Task 3. Link models to multi-scale data sets.

Task 3a. Ecoregion model (CASA).  Use intensive field site tower and biometric measurements, of carbon fluxes and storage pools, and lidar–based maps, to evaluate the accuracy of our satellite data-driven model simulations for NASA-CASA [Co-PIs Potter, Klooster, Genovese]

Task 3b. Stand model (AMORPHYS).  Parameterize a process-based individual tree model for updating and projecting estimates of carbon stocks and NPP, and evaluate the accuracy of estimates using data from landscape monitoring sites. [Co-PI Valentine]

Task 4. Apply models and resource inventory data for carbon management needs.

Task 4a. CQUEST.  Validate model application for mapping natural disturbances, and estimating the magnitude of observed changes in carbon stocks attributable to natural disturbance events.  [Co-PIs Potter, Klooster, Genovese]

Task 4b. Entity Greenhouse Gas Inventory.  Demonstrate how entities can combine output from models and data from resource inventories to estimate and report greenhouse gas inventories (forest sector) to State and National registries.  [PI Birdsey]

Task 5. Evaluate methods, data, and approach.

Task 5a. Sponsor independent statistical review of network design, landscape monitoring protocols, sampling methods and data. [PI Birdsey – subcontract]

Task 5b. Certify that estimates meet greenhouse gas registry requirements for content and precision.  [PI Birdsey]

A preliminary timeline linked to the project tasks of this proposal, and also showing the associated pilot study (funded separately), is shown in the following table:

| Fiscal Year: | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- | --- |
| Quarter: | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Task - pilot study: | Ongoing biometrics pilot study and implementation |
| Workshop |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Field manual |  |  | x | x | x | x |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot study |  |  |  |  |  | x | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |
| Task – this proposal: | Remote sensing, modeling, and applications |
| 1.Classification |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |
| 2a. Lidar |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  |  |
| 2b. Biometrics |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x |  |  |  |  |
| 2c. Data comp. |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x |  |  |
| 3. Model dev. |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |
| 4. Applications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x |  |  |
| 5. Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x |

3. Progress Report and Plans

Task 1. Harmonize classifications and definitions. We have developed a crosswalk between Forest Inventory (FIA) forest types, MODIS land classes, and CASA land classes.  We continue to address this issue through cross-site comparison studies, and it is embedded into our data management strategy which requires consistent definitions and units, and compatible calculation procedures.

Task 2. Estimate and map carbon stocks and productivity for landscape sites.

- Lidar imagery acquired and processed for each site. Supporting biometric measurements made on schedule for each site, and analysis of data has begun. Integration of biometric data and Lidar imagery is underway.

- Frazer, Niwot Ridge, and Glacier Lakes – During FY06 we maintained the existing set of plots at 3 the Fraser Experimental Forest, the Glacier Lakes Ecosystem Experiment Station and the Niwot Ridge Ameriflux site.  This maintenance included measurement of soil respiration twice during the winter and monthly during the summer, as well as collection of litterfall in spring and fall.  We installed branchfall traps in summer 2006 in all plots.

- Marcell – We have collected all of our samples that required a one time sampling (e.g. soil and leaf samples).  Some of those samples still need to processed and analyzed.  We have begun to analyze and present our data as noted by the presentations listed below.  We continue to take our periodic gas measurement fluxes on our plots.  Our eddy covariance system starting collecting data on June 2, 2006 in an open (non-forested) peatland.  We hope to compare several years with our data with data collected in the early 1990s for NEE and gaseous fluxes of carbon dioxide and methane.

- Bartlett – Coordinated Hyperion imaging spectrometer data collection at NJ NACP sites. Collection of images pending; field sampling deferred until successful image acquisition. Coordinated and carried out foliar chemistry sampling in conjunction with Hyperion image acquisition at Bartlett and Marcel Experimental Forests. Continued plot-level measurements of C stocks and fluxes at Bartlett Experimental forest. Five (5) manuscripts submitted or in press. Worked up and shared plot level productivity data with C. Potter for use in CASA modelling.

- Parker Tract – Data collection for most aboveground carbon pools have been completed through 2006, with plans to complete remaining data collection and analysis by May 2007.  Two years of branchfall data should be analyzed by summer 2007, once we have obtained carbon estimates from samples collected in 2006 and 2007.  Data collection for a more complete estimate of belowground carbon (60 + cm) will be conducted when the water table is lower.

- Silas Little - We have made extensive measurements of forest structure and fuel loading at a total of ca. 150 sites thoughout upland forests in the Pine Barrens.  In conjunction with LIDAR measurements, these data are used to estimate aboveground biomass and C pools across the Pinelands. We have started to collaborate with Dr. Yude Pan to parameterize PnET CN specifically for our 3 eddy flux sites, in conjunction with Tier 3 activities.  To date we have provided formatted meterological files and forest structure data.

Task 3. Link models to multi-scale data sets. Completed several tasks with CASA: U.S. C sequestration inventory using MODIS; historical reconstruction of U.S. C pool baselines from 20 years of AVHRR; completed U.S. analysis of soil C changes from land use change.  For the stand model (AMORPHYS): Post-doc hired and has begun calibrating the model for carbon change estimation at the field sites.

Task 4. Apply models and resource inventory data for carbon management needs.  Not scheduled until 2007.

Task 5. Evaluate methods, data, and approach. Not scheduled until 2008.

FY 2007 Plans

Task 1. Harmonize classifications and definitions. This activity will continue as we develop cross-site synthesis products and a prototype data base for landscape-scale carbon monitoring.

Task 2. Estimate and map carbon stocks and productivity for landscape sites.

- Lidar imagery will be processed and preliminary maps developed.  Scheduled biometric measurements will be continued.

- Frazer, Niwot Ridge, and Glacier Lakes - For FY07 we intend to continue maintaining the plots at these three sites and begin measuring some experiments that were installed previously.  In summer 2005, we installed both root ingrowth bags and litter decomposition bags.  We plan to harvest and analyze the root ingrowth bags and one set of the litter bags in late summer 2007.

- Marcell - Over the next year we will continue to sample/measure the necessary variables for the pilot project and will be spending much more time analyzing data, developing outputs and publications.  Need to develop data compilation standards and data management plan.

- Bartlett - Ongoing activities field activities during fall (2006) and winter (2007) including litterfall collection, re-measurement (mid-Oct.) of stem DBH on all subplots. Early FY2007 will be devoted to summarization of FY2006 field measurements, and integration of field measurements with remote sensing (Hyperion, MODIS) and flux tower data.

- Parker Tract – will continue collecting data on the “tier-3” sampling grid; add measurements of tree height and dbh from a variety of stand structures within the Lidar footprint; and begin compiling data and comparing estimates with other sites.

- Silas Little – we will complete the collection of basic biometric data on the “tier 3” sampling grid; continue collecting data at the 3 tower sites; compile estimates of NPP, NEP, biomass, and age at multiple scales; and compare and analyze the results across spatial and temporal scales.

Task 3. Link models to multi-scale data sets. Generate CASA model products for NPP annual carbon flux and above-ground carbon pools at high spatial resolution for each study site.  Integrate CERES satellite products into CASA model results for ecosystem carbon budgets and begin benchmarking.  Compare top-down CASA model predictions with bottom-up estimates on approximately 50 x 50 km2 areas around the field sites.

Task 4. Apply models and resource inventory data for carbon management needs.

We are beginning to integrate the intensive biometric data with the FIA data sets surrounding each of the field sites.  Once we have harmonized the data (e.g., definitions, consistent estimates of NEP, accounting standards) we will evaluate whether the estimates are rigorous enough to comply with the standards set for greenhouse gas registries.

Task 5. Evaluate methods, data, and approach.

Not scheduled until 2008.

4. Synthesis Activities

DRAFT Common Products Table (11/20/06)

| Short title | Lead and contributors* | Brief description |
| --- | --- | --- |
| (1) Network database (see 2006 progress report for details) | Cole, Birdsey, all others | Prepare metadata form for each PI to fill out; design and populate a common summary database; ensure archiving by each PI |
| (2) Spatial variability and sampling design (outline available) | Bradford, others | Characterize spatial variability in stand structure, carbon stocks, and carbon fluxes; assess influence on plot layout and sample size. |
| (3) Importance of CWD and forest floor in carbon dynamics (outline available) | Bradford, others | Quantify C in CWD and FF; determine if amount of C is related to components that can be measured remotely; determine relationship with age. |
| (4) Belowground carbon allocation | Ryan, others | Use C balance approach and compare to above-ground C across and within sites. |
| (5) LIDAR comparison with plot data | Lefsky, Hom, others | Above-ground stand structure maps and biomass estimates (maps, statistics) |
| (6) Biomass and soil respiration comparison | Potter, others | Compare each site with CASA predictions |
| (7) Woody biomass increment | ? | Tree cores available at some sites. May need additional data collection to get recent years. Use AMORPHYS?? (see #12). |
| (8) Accuracy assessment – compare top-down & bottom up estimates | Birdsey, Potter, Van Tuyl, Pan, others | Prepare maps of stand age, biomass, NPP, and NEP for each site at scales of 1 km2, 9 km2, and 2500 km2. Compare with CASA and other model predictions. |
| (9) Comparison of flux measurements | Hom, others with flux towers |  |
| (10) Use of canopy N and LAI for scaling up | Smith, others |  |
| (11) Landscape-scale modeling: linking above- and below-ground processes | ? |  |
| (12) AMORPHYS stand dynamics model | Valentine, Ducey, Henning | Calibrate model with site data and LIDAR; estimate above-ground C and compare with other estimates. Link to below-ground??? (see item 11) |
| (13) Standardized land cover classifications | Potter, others | For each site (3 x 3 km area plus 50 x 50 km surrounding area for selected maps): land use/land cover; land cover change; present vegetation composition; derived products (e.g., biomass, NPP, NEP, etc.). |
| (14) Field manual | Hoover, others | This is a methods manual for landscape monitoring sites, based on initial workshop and modified with field experience. |
| (15) Do we need a network of landscape-scale monitoring sites for decision support? | Birdsey, others | These are final reports to NASA describing the effectiveness of the project for decision support. |

* “others” means that contributions will be made from someone at each site

5. NGCP Soil Carbon Initiative

NOTE: these are related studies under the NACP umbrella program.  They were begun in the summer of 2006.  We will begin reporting progress in the fall of 2007.

Objective: To improve accuracy and precision of soil carbon estimates, and estimates of the effects of management and disturbance on soil carbon, for regional and project analyses in the Northeastern and North Central U.S.

Key questions:

1. What are regional estimates of soil C, especially with respect to land use and land cover change?

2. How do we improve regional C estimates?

3. What are the driving factors (now and the future) at regional scales (e.g., soil texture, landscape position, temperature, moisture, land use, land cover, natural disturbance, vegetation cover, atmospheric chemistry, management / utilization, invasive species).

4. How will expected changes in driving variables (Temperature, Moisture, Land-use, Natural disturbance, Vegetation cover, Atmospheric chemistry, Management / Utilization) affect C storage, and our ability to predict over these changes?.

Selected Pre-proposals:

Modeling soil carbon at the landscape level by linking NRCS and FIA data

Charles Perry, Linda Heath, and Richard Pouyat (FS)

Jim Thompson (WVU)

Models of Northern forest C dynamics at a range of spatial scales

Paul Bolstad (U. MN)

R. Pouyat (FS)

R. Scheller (U. Wisc.)

M. Carreiro (U. Louisville)

Management effects on forest soil carbon: literature synthesis, meta-analysis, and assessment of implications for carbon management and accounting

Peter Curtis (Ohio State)

Alex Friend (FS)

Eric Vance (NCASI)

Soil carbon storage and accumulation in forests of Western New England and the Northern Great Lakes States

Art Johnson and Fred Scatena (U. Penn)

Coeli Hoover, Erik Lilleskov, Yude Pan, and Richard Pouyat (FS)

Paul Bolstad (U. MN)

6. Proposed Future Work

Landscape-scale monitoring provides a critical element for evaluating the causes and impacts of natural and human-induced disturbances (e.g. fire, harvesting), climate variability and atmospheric chemistry on forest carbon dynamics in the temperate and boreal forest zones of North America.  Two areas of research are fundamental to realize this opportunity:

- Develop a forest-age distribution map that reflects the history of disturbances

- Link ecosystem process models with landscape disturbance models to quantify the relative effects of different factors (climate, atmospheric chemistry, and disturbance) on forest carbon cycling

The work involves integrating satellite data, inventory data, and other statistical data sets across space and time; and strategic enhancement of modeling capability so that the unique characteristics of different regions can be effectively represented.

An example of a forest-age distribution map for Canada illustrates one of the main products of this proposed work.

APPENDIX 1: Field Measurements for Forest Carbon Monitoring at Research Sites (Manual in Review)

I. Overview –

A. Brief outline of North American Carbon Program

B. Objectives for land measurements and models

C. Heirarchical approach to biophysical measurements

D. Tier 3: Carbon process monitoring at medium-intensity sites

II. Proposed Tier 3 Network

A. Goals and objectives of network

1. Augment coverage of the land surface by Tier 4 sites

a. Natural disturbances and management

b. Edges/fragmented landscapes

c. Mountain terrain

2. Scaling from intensive sites to landscapes

3.Model parameterization or validation

B. Site Selection Criteria

1. Need for comprehensive representation of North America’s forests

2. Stratification and other general design issues

3. Choosing representative sites

4. Linkages with sites from other tiers (scaling)

C. Choosing Sample Plot Locations

1.  Random sampling, grids, and clusters

2.  Tradeoffs : cost/precision; consistency/flexibility

3.  Statistical rigor : power and independence; avoiding bias

4. Management and disturbance effects: chronosequences, experimental plots

5. Other factors (ownership, access, security, safety, georeferencing, etc.)

D.  Plot design considerations

1. Need to facilitate cross comparisons w/other Tiers and sites, Canada, Mexico

2. Need consistency and flexibility – use core + added design

3. Statistical rigor

4. Practicality and efficiency

III. Overview of Recommended Variables

A.  What guided choices

B.  Recommendations for core, added

C. Tables for each variable group, listing variable, frequency, use, ?

IV. Site Description –

A. Site history

1. Management

2. Natural disturbances

B. Stand ages, including appropriate indicator for mixed age stands

C. Other general stand description variables – geology, etc.

V. Meteorological Variables –

A. Air temperature

B. Soil temperature

C. Precipitation

D. Relative humidity

E. Soil moisture (litter moisture?)

F. Photon Flux Density

G. Net radiation

VI. Aboveground Pools and Properties-

A. Pools-

1. Aboveground biomass

2. Woody shrub biomass

3. CWD by size class

4. Forest floor mass

B. Properties –

1. Vegetation height

2. LAI

3. % canopy cover

4. Foliar N

5. Litter C:N ratio?

VII. Aboveground Fluxes –

A. Litterfall

B. Branchfall

C. Litter decomposition

D. Dead wood decomposition

1. Decomposition rates

2. Specific gravity – by species or decay class?  How to define decay classes?

VIII. Belowground Pools and Properties –

A. Pools

1. Soil C stocks (including concentration, bulk density, and calculation of Content)

2. Coarse root biomass

a. Total roots: live and dead

b. Discussion of root allometry

c. Explanation of why fine roots are not included

B. Properties

1. Soil C:N ratio

2. Soil C turnover rates (14C incubations)

IX.  Belowground Fluxes –

A. CO2

B. CH4

C. N2O

4. DOC

5. Suspended sediment

X. Synthesis

A. Use the variables to:

1. Estimate ANPP

2. Estimate NEP

3. Validate remote sensing imagery

B. Integrating Tier 3 measurements with flux tower data

C. Management and disturbance effects

D. Cross comparing and integrating with Canada and Mexico

E. Adapting design, measurements, and protocols to other land cover types: grasslands, etc.

APPENDIX 2: Data Management Plan (DRAFT – 02/23/06)

Purpose of Plan

This plan outlines a data management policy and plan for the landscape monitoring component of the North American Carbon Program (NACP).  The main objectives are to (1) document data collection procedures and QA/QC, (2) define standard data products, (3) state a policy for data sharing both internally and externally, and (4) plan for data archiving.  This plan follows the general guidance on data management developed for the NACP, and is consistent with the guidelines in the U.S. Government’s Data Quality Act.  For additional information about data and information management for the NACP, see the NACP Science Implementation Strategy at: http://www.nacarbon.org/nacp/documents.html

NACP Data Policy (from Science Implementation Strategy document)

A data policy for NACP needs to be developed and approved by the international partners based on data sharing and cooperation in support of the scientific goals of NACP. The NACP data policy should treat the following issues:

• Definition of the data that falls within the purview of the NACP data policy (e.g., primary observations, monitoring data compiled by U.S., Canadian, and Mexican agencies, site characterization, remotely sensed data, and ancillary data required by NACP);

• Timely release of data to NACP participants (e.g., no period of restricted access, within 6 months of collection, or other period);

• Timely release of data and documentation to the public (e.g., within 0, 1, or 2 years of collection);

• Timely documentation of data products;

• Protecting the intellectual property rights of data originators

- Data users should contact data originators before publishing data,

- Credit is given to data originators, through co-authorship, citation, or acknowledgement;

• Protecting the rights of students

- Some institutions require that key data cannot be published prior to submitting dissertation;

• Acknowledging NACP and its sponsors;

• Establishing a process and timeline for archiving key NACP data; and

• Resolving conflicts over data and the data policy.

Data Collection

- Field methods manual: draft nearly complete, will be circulated to all investigators for review.

- Remote sensing specifications: for “standard” products such as Landsat-TM, refer to original documentation.  For LIDAR and hyperspectral products specific to this study, investigators should provide documentation or links to documentation.

- QA/QC plans for each site: responsibility of each PI.

Data Processing and Products

- Standards for data processing (how computations are done): synthesis products (cross-site comparisons) should include evaluation of computation methods to ensure consistency among sites.

- Central vs. distributed processing.  All data processing is distributed to individual PIs unless separate agreement made to share processing.

- Summary data base of compiled field observations and basic calculations: For general use (internal and external), all PIs are expected to contribute data to a data base using a standard format and variable definitions.  PIs will agree on these data base attributes.  Example attached from Delaware River Basin study.

- Remote sensing data sets: responsible PIs will ensure that common remote sensing data products are available and that sufficient information about processing methods and data standards are documented.

- “Value-added” data products (e.g. estimates derived from models): if value-added data products are critical components of a research paper, then these data sets should be documented and archived in the same manner as primary data sets.

- Meta-data requirements following NACP protocols: specific requirements for NACP are not yet available.  Meanwhile, follow the meta-data protocol used by the DAAC for biogeochemical dynamics: http://www.daac.ornl.gov/PI/pi_info.html

- QA/QC plans for each data processor including error analysis: responsibility of each PI.

Data Sharing

- Sharing preliminary data among project scientists: open policy, data should be available for sharing as soon as QA/QC performed.

- Making data publicly available: follow guidelines for NACP (yet to be determined).

- Protecting the rights of project scientists and students: follow guidelines for NACP (yet to be determined).  Meanwhile, use reasonable judgment to ensure the rights of everyone involved in this projects.

Data Maintenance and Archiving

- What data sets to archive:

  - all primary data sets

  - secondary data sets used for cross-site studies (including the summary data base)

  - value-added data sets if basis for research or policy paper

- When and where to store and archive data: will follow NACP protocols, which are not yet available. A Task Force recommended a central data index linked to thematic data centers, but this is not yet implemented.  Meanwhile, we will follow a model that involves central archiving of meta-data and selected key data sets that are common among most sites, with all other data sets managed in a distributed way.

- Monitoring data use and citations: until data is made publicly available, appropriate acknowledgement among PIs and students involved in this project is required common courtesy.  For public release we will follow NACP guidelines when available.

ACTION ITEMS (03/02/06)

- Resources: NGCP will make staff time available for initiating central data archive for this project.  Interim location will be NGCP computing lab in Newtown Square; other options being explored according to FS and NCAP developments.

- Incentives for good data management:

  - Resources needed by anyone?

  - Will review data management status before allocating FY 2007 funds.

- Summary data base: will develop draft and circulate for review (example from another project attached).

- Field methods manual: will be circulated for review.

- Identify critical common data sets: draft will be circulated for review (see next section)

Plan for Developing a Common Data Base for Landscape-scale Monitoring in the NACP

Purpose: to develop a common framework for organizing, archiving, and retrieving the various kinds of measured biometric data and derived variables at landscape-scale research sites of the NACP.

Kinds of data: data sets include both measured variables and derived variables relevant to estimating carbon stocks and fluxes for above- and below-ground ecosystem components.  In-situ, remote sensing, and modeled estimates are included.  Data sets will include primary measurements (such as tree dbh); carbon stock and flux estimates of different ecosystem carbon pools (such as aboveground live biomass); and ancillary variables (such as time since disturbance) that help explain observations.  Attached is a prioritized list of the kinds of relevant variables compiled during a workshop held in 2002 to identify key variables and data sets.

Approach: request each landscape monitoring site to compile a list of key variables including name, description, and reporting units.  Attached is a second list of specific plot- and subplot-level variables compiled by Mike Ryan and John Bradford to link their site-level data with LIDAR data. This is a suggested format for the tables that should be developed for each landscape site.  These lists will be sent to Jason Cole (jcole@fs.fed.us) who will sort and combine the lists into a first draft of a framework.  This draft will be circulated back out, and then we will convene a conference call to discuss the progress and determine if there needs to be a small workshop to finish the process.  We also need to consider data formats, data base requirements, where to store the data, and when to make it available for general use.

EXAMPLE DATA BASE: Biometric Measurements Only

| Variable Name | Description | Units |
| --- | --- | --- |
| Site | Site: F, G, or N |  |
| Plot | Plot: 1 - 16 |  |
| Subplt | Subplot within the plot (1-4) |  |
| pla_sum | Sum of leaf area from trees | m2 |
| hght_mean | mean tree height | m |
| BincMgCha | mean biomass increment for 1994 - 2003 | MgC/ha/yr |
| ba_m2ha | basal area of all trees | m2/ha |
| baLP_m2ha | lodgepole basal area | m2/ha |
| baSF_m2ha | subalpine fir basal area | m2/ha |
| baES_m2ha | engelman spruce basal area | m2/ha |
| baTA_m2ha | aspen basal area | m2/ha |
| baLM_m2ha | limber pine basal area | m2/ha |
| treesha | tree density | trees/ha |
| agemean | mean age | years |
| agemax | maximum age | years |
| treeagl_MgCha | tree aboveground live biomass | MgC/ha |
| treebgl_MgCha | tree belowground live biomass | MgC/ha |
| treeagd_MgCha | tree aboveground dead biomass (standing snags) | MgC/ha |
| treebgd_MgCha | tree belowground biomass (from snags and stumps) | MgC/ha |
| pla_sum_sap | sum of sapling leaf area | m2 |
| sapba_m2ha | sapling basal area | m2/ha |
| saps/ha | sapling density | saps/ha |
| sapbio_Mg/ha | sapling (2.5-10cm dbh) total biomass | MgC/ha |
| sapagMgC/ha | sapling aboveground biomass | MgC/ha |
| sapbgMgC/ha | sapling belowground biomass | MgC/ha |
| pla_sum_seed | sum of seedling leaf area | m2 |
| seeds/ha | seedling density | seeds/ha |
| seedbio_Mg/ha | seedling total biomass | MgC/ha |
| seedagMgC/ha | seedling aboveground biomass | MgC/ha |
| seedbgMgC/ha | seedling belowground biomass | MgC/ha |
| stumpnum | number of stumps/plot | sumpts |
| stump_MgC/ha | aboveground stump biomass | MgC/ha |
| cwd_MgCha | coarse woody debris biomass | MgC/ha |
| ffMgCha | forest floor biomass | MgC/ha |
| soilcmassMgCha | soil carbon (top 10 cm) | MgC/ha |
| LF_MgChayr | litterfall (only 1 year) | MgC/ha/yr |
| veg_MgCha | understory productivity | MgC/ha/yr |

APPENDIX 3: Land Classification

# PRESENT LAND USE/LAND COVER

Current land use/cover should be recorded or mapped for each area using a national inventory protocol such as FIA or NRI, or a standard land cover classification such as NLCD 2001 (specify which classification schemes are used).  Recommended major land use/land cover categories and sub-categories include:

Water

Developed:

Residential

Industrial

Forest

Cropland

Grass/field

Wetland

Advanced land-use features that indicate management intensity may include:

Agricultural management:

no-till

fertilizer use

irrigation

herbicides

Forest management:

clearcut

partial cutting

thinning

site preparation

regeneration

fuels management

fertilization

Hydrologic management:

dams

reservoirs

canals

Suggested web sites:

FIA				http://fia.fs.fed.us/

NRI				http://www.nrcs.usda.gov/technical/NRI/

USGS Eros Data Center	http://edc.usgs.gov/products/landcover.html

LAND COVER CHANGE

All major historical land use changes and disturbances should be discussed in terms of their geographical distribution, the size of the area occupied by each, and the impact on land cover.  The dates of the changes or disturbances should be recorded.

Basic land cover change features should be characterized for all study sites, withprecise dating of events if possible.

Natural disturbances:

wildfire

drought

flood

weather damage (ice, wind)

pest outbreaks

Human disturbances:

fire

deforestation and/or afforestation

timber harvest

stand treatments (see “forest management” above)

grazing

agricultural treatments (see “agricultural management” above)

introduced species

Advanced land cover change features that may be characterized include tree ring chronologies, carbon dating, and isotope characterization.

Suggested web sites:

http://landcover.usgs.gov/landcovertrends.asp

# PRESENT VEGETATION COMPOSITION

A good characterization of vegetation composition is required for using site data in models, and for extrapolating results from individual sites or landscapes to larger or similar geographic areas.  Major species and/or species groups, using a common classification system or systems, should be recorded in terms of geographical distribution and the size of the area occupied by each.  In this section we present a few of the more common vegetation classification systems.  Sometime it is necessary to have the site classified according to more than one system, or to at least be aware of how to crosswalk from one system to another.

Forest Inventory and Analysis (FIA) – the FIA program uses a forest type classification that is relevant to land management.  The system is based on a set of rules that determine

forest type from the dominance or co-dominance of different tree species.  There is a two-level hierarchy comprised of forest type groups and forest types.  Details are available in the FIA field manual (see web site below).

Food and Agriculture Organization (FAO) – the United Nations FAO has developed a classification system that is commonly used for the world’s forests, and is the basis for reporting global forest statistics in periodic Forest Resource Assessments. The FAO classification system is primarily designed to determine how “natural” forests are by determining whether trees are planted or natural, and if natural, whether the forest is “primary” (or mostly undisturbed) or “secondary” (recovering from disturbance).

National Land Cover Data (NLCD) – National land cover data is derived from Landsat satellite imagery and is classified by vegetation types that are more detailed than the basic land cover classes.  Since this is a common product for mapping vegetation, it may be necessary to classify sites according to this scheme.

International Geosphere/Biosphere Program (IGBP) – MODIS and other satellite data products use the IGBP vegetation classification system, which includes 11 vegetation classes.

Advanced vegetation cover features that may be characterized include detailed descriptions of species including understory vegetation, which may also be used to construct biodiversity indices.

Suggested web sites:

FIA				http://fia.fs.fed.us/

FAO				http://www.fao.org/forestry/index.jsp

NLCD				http://landcover.usgs.gov/index.asp

IGBP				http://edcdaac.usgs.gov/main.asp

Table 1   Forest cover types, regrouped forest types, and MODIS classifications (from Pan et al. 2006)

| Forest Cover Types | Percent of forest area | Regrouped Types for PnET-CN | Percent of forest area | MODIS Class | Percent of forest area |
| --- | --- | --- | --- | --- | --- |
| Maple-beech-birch | 29 | N. Hardwoods | 29 | Deciduous | 82 |
| Elm-Ash -cottonwood | * |  |  |  |  |
| Oak-Hickory | 53 | Oak-hickory | 53 |  |  |
| Spruce-fir | 1 | Spruce-fir | 1 | Coniferous | 9 |
| White-red-jack pine | 3 | Pine Forests | 8 |  |  |
| Loblolly-shortleaf pine | 5 |  |  |  |  |
| Long-leaf-Slash Pine | * |  |  |  |  |
| Oak-Pine | 8 | Oak-Pine | 9 | Mixed | 9 |
| Oak-gum-cypress | 1 |  |  |  |  |

*  Less than 1 percent

APPENDIX 4: LIST OF PRODUCTS

Publications

Birdsey, R., R. Kolka, M.L. Smith, M. Ryan, D. Hollinger, L. Heath, and C. Hoover.  2004.  Landscape carbon monitoring and analysis at the experimental forest network.  Proceedings of the 3rd Annual Conference on Carbon Sequestration. (electronic only)  Alexandria, VA May 2004

Birdsey, Richard; Pregitzer, Kurt; Lucier, Alan.  2006. Forest carbon management in the United States 1600-2100.  Journal of Environmental Quality. 35: 1461-1469.

Birdsey, Richard A.  2006. Carbon accounting rules and guidelines for the United States forest sector. Journal of Environmental Quality.  35: 1518-1524.

DeForest, J., G. Sun, A. Noormets, J. Chen, S. McNulty, M. Gavazzi, D. Amatya, R. Skaggs.  2006.  Carbon and water fluxes in a drained coastal clearcut and a pine plantation in eastern North Carolina.  In: Williams, Thomas, eds. Hydrology and Management of Forested Wetlands:  Proceedings of the International Conference, St. Joseph, MI:  ASABE: 587-597.

Ollinger, Scott V.; Smith, Mary-Louise.  2005. Net primary production and canopy nitrogen in a temperate forest landscape: an analysis using imaging spectroscopy, modeling and field data. Ecosystems. 8: 760-778.

Pan, Yude; Birdsey, Richard; Hom, John; McCullough, Kevin; Clark, Kenneth.  2005. Improved estimates of net primary productivity from MODIS satellite data at regional and local scales. Ecological Applications.  16(1): 125-132.

Ryan MG and BE Law.  2005.  Interpreting, measuring and modeling soil respiration.  Biogeochemistry 73: 3-27

Potter, C., S. Klooster, S. Hiatt, M. Fladeland, V. Genovese, and P. Gross, 2006,

Satellite-derived estimates of potential carbon sequestration though afforestation of

agricultural lands in the United States, Climatic Change (In Press).

Potter, C., S. Klooster, R. Nemani, V. Genovese, S. Hiatt, M. Fladeland and P. Gross, 2006, Estimating Carbon Budgets for U.S. Ecosystems, Eos Transactions American Geophysical Union, 87(8), 85-96.

Presentations, posters

Birdsey, R., M. Ryan, M.L. Smith, R. Kolka, S. McNulty, J. Hom, C. Potter, M. Lefsky, J. Bradford, and P. Weishampel.  2006. Linking landscape-scale carbon monitoring with forest management. NASA Carbon Cycle and Ecosystems Joint Workshop on Biodiversity, Terrestrial Ecology and Related Applied Science.  Adelphi, MD.

Birdsey, Richard A. Biometric measurement pilot study for North American Carbon Program. AmeriFlux Annual Meeting, Boulder, CO. Oct. 19, 2005.

Bolstad, P.V., R. Anderson, B.D. Cook, J. Tang, N.Z. Saliendra, P. Weishampel, R.K. Kolka, J.G. Martin, and K.J. Davis.  2006. Landscape estimates of carbon pools and fluxes via LIDAR and high resolution spectral data. American Geophysical Union Annual Conference, San Franciso, CA.

Bradford, John and Mike Ryan.  2005. Generating large-scale forest NEP estimates: Can we escape site history?  Oral Presentation, Ecological Society of America Annual Meeting. Montreal, QC. August 2005

Bradford, J. B., Schimel D. S., Monson, R., Sacks, B., Ryan, M.G., and L.E Scott-Denton. (2006) Biometric versus eddy covariance estimates of net ecosystem carbon balance: a comparison in the subalpine Rocky Mountains.  Poster Presentation: Integrated Land-Ecosystem-Atmosphere Processes meeting, Boulder, CO.

Bradford, J.B. (2005) Biometric ecosystem production measurements for comparison with eddy covariance measurements.  Oral Presentation: Ameriflux annual meeting, Boulder, CO.

Bradford, J.B. and M. G. Ryan (2006) Forest Carbon Dynamics: consequences of spatial variability for landscape-scale estimation.  Oral Presentation: Ecological Society of America Meetings, Memphis, TN.

Gavazzi, M., S. McNulty, G. Sun, J. Chen, A. Noormets, J. DeForest, S. Strickland, J. Boggs.  2006.  Comparing carbon, water and energy fluxes in two coastal plain loblolly pine plantations. Critical Processes and Properties Regulating Carbon Cycling in Southern Forests, Asheville, NC.

Kolka, R. and D. Olson.  2006.  Introduction to the Marcell eddy covariance system.  USCCC Meeting, Beijing, China.

Kolka, R.K. and P. Weishampel.  2006.  Tier 3 measurements in the upscaling approach at the Chequamegon Ecosystem-Atmosphere Study (ChEAS).  Annual ChEAS Meeting.  Woodruff, WI.

McNulty, Steve.  Estimating evapotransiration in threee contrasting forest ecosystems using eddy covariance, sapflow and soil water balance methods.  American Geophysical Union Fall Meeting.  December 5-9, 2005, San Fransisco, CA

McNulty, Steve. Water cycles in a drained coastal clearcut and pine plantation in coastal North Carolina.  ASABE International Conference on Hydrology and Management of Forested Wetlands.  April 8-12, 2006, New Bern, NC

Christopher Potter and Matthew Fladeland, NASA Ames Research Center; Steven Klooster, Vanessa Genovese, Peggy Gross, Seth Hiatt, California State University. AGU 2005 and updated for NASA ecosystems and carbon meeting 2006: Terrestrial Carbon Sinks for the United States Predicted from MODIS Satellite Data and Ecosystem Modeling

Potter, Chris. Past Impacts and Future Scenarios of Climate on Ecosystem Carbon Balance for the Western United States. Invited Poster Presented at the Second Annual Conference on Climate Change in the Western States, Sacramento, CA, September, 2005.

Saliendra N.Z., M.E. Kubiske, R. Teclaw, R. Kolka, K. Davis, K. Cherrey, A. Desai, D. Ricciuto, B. Cook, F.A. Heinsch , and P. Bolstad.  2006.  Testing the flux tower upscaling hypothesis in a complex landscape in northern Wisconsin.  Annual AmeriFlux Meeting, Boulder, CO.

Valentine, HT and Annikki Makela. Bridging process-based and empirical approaches to modeling tree growth.  Colloquium and workshop on modeling wood quality.  Montreal May 2005

Valentine, HT and Annikki Makela. Cross-sectional area growth versus crown length: deductions from theory.  Meeting of the Northeastern Mensurationists’ Organization.  Freeport, Maine. Nov. 2005

Weishampel, P, J. King, and R. Kolka.  2006.  Scaling soil CO2 and CH4 fluxes in heterogeneous northern forest landscapes. NASA Carbon Cycle and Ecosystems Joint Workshop on Biodiversity, Terrestrial Ecology and Related Applied Science.  Adelphi, MD.

Weishampel, P, J. King, and R. Kolka.  2006.  Methane fluxes in forests and wetlands of northern Wisconsin and Minnesota. American Geophysical Union Annual Conference, San Francisco, CA

# Text boxes

Figure 1. Flow diagram (roadmap) of linkage between data, models, and decision support.