# OVERVIEW OF LIFE CYCLE MANAGEMENT

# 1.1  		Introduction

_____________________________________________________________

## 1.1.1	Purpose

This Life Cycle Management Manual establishes management policies, procedures, and practices governing the initiation, definition, design, development, deployment, operation, maintenance, enhancement, and retirement of automated information systems (AIS) at the United States Patent and Trademark Office (USPTO).

## 1.1.2	Objectives

The primary objective of life cycle management is to deliver quality systems when promised and within cost estimates using an identifiable, measurable, and repeatable process.

Life Cycle Management (LCM) emphasizes decision processes that influence system cost and usefulness efficiencies.  These decisions must be based on full consideration of business functional requirements and economic and technical feasibility in order to produce an effective system.  The objectives of the LCM approach are to:

- deliver quality systems which meet or exceed customer expectations when promised and within cost estimates.

- deliver systems that work effectively and efficiently within the current and planned information technology infrastructure.

- deliver systems that are cost-effective to enhance and maintain.

- develop quality systems using an identifiable, measurable, and repeatable processes.

- establish an organizational and project management structure with appropriate levels of authority to ensure that each AIS or infrastructure project is effectively managed throughout its life cycle.

- Identify and assign the roles and responsibilities of all affected parties including functional and technical managers throughout the AIS or infrastructure system life cycle.

- Ensure that AIS or infrastructure system requirements are well defined and subsequently satisfied.

- Provide visibility and comprehensive information to USPTO functional and technical managers for all AIS or infrastructure system resource requirements and expenditures.

- Establish appropriate levels of management authority to provide timely direction, coordination, control, review, and approval of the AIS or infrastructure system project.

- Ensure project management accountability.

- Identify project risks early and manage them before they become problems.

# 1.2  		Intended Audience

_____________________________________________________________

The primary audience for this Manual and the supporting Technical Standards and Guidelines (TSGs) are the functional and technical managers responsible for defining and delivering USPTO systems, their staff and their support contractors.

# 1.3  		Types of  Projects

_____________________________________________________________

AIS or infrastructure system projects vary in scope and diversity from simple to complex.  Examples of USPTO project types include:

AIS or infrastructure system projects vary in scope and diversity from simple to complex, from the installation of a COTS application software package to the development of a new AIS or infrastructure system.

- AIS Development – AIS Development involves the development and deployment of an AIS to support a new or changed business function, replace an existing AIS which can no longer fulfill business needs, or to automate functions being done manually.  Replacement of an existing AIS may include changing major components of the architecture.

- AIS Enhancement – AIS Enhancements involve significant changes to the AIS design specification or architecture to ensure that new or changing requirements are being met.

- AIS or Infrastructure Maintenance – AIS or Infrastructure maintenance are projects with new functionality changes or corrections (bug fixes) that do not impact the design or architecture of the AIS or infrastructure.

- Infrastructure Development or Enhancement – Infrastructure Development or Enhancement involves the installation of new or replacement hardware or system software products such as the installation of high-speed switches or the upgrade of the network operating system.  Infrastructure Development or Enhancement supports the evolution and adaptation of the USPTO Information Technology Infrastructure to support new systems and the increasing demands placed on it.

1.4  	Life Cycle Management Phases

_____________________________________________________________

Life Cycle Management includes six phases, during which defined AIS or infrastructure system work products are created or modified. The tasks and work products for each phase are described in subsequent chapters. The LCM phases may be tailored to accommodate the unique aspects of an AIS or infrastructure system project as long as the resulting approach remains consistent with the primary LCM objective to deliver a timely, quality system within cost. LCM phases may overlap and AIS or infrastructure system projects can follow an evolutionary development strategy that provides for incremental delivery of products and/or subsystems.  The tailoring process is described in the Automated Information System Life Cycle Process Tailoring Technical Standard and Guideline, IT-212.2-03.

The LCM phases may be tailored to accommodate the unique aspects of an AIS or infrastructure system project as long as the resulting approach will deliver a quality system.

## 1.4.1	Initiation Phase

The purposes of the Initiation Phase are to:

- identify and validate an opportunity to improve business accomplishments of the organization or a deficiency related to a business need,

- identify significant assumptions and constraints on solutions to that need, and

- recommend the exploration of alternative concepts and methods to satisfy the need.

This phase is completed upon agreement between the Program Sponsor and the Chief Information Officer (CIO) to initiate an AIS or infrastructure system project.

## 1.4.2	Concept Phase

This phase will determine whether an acceptable and cost-effective approach can be found to address the business need, with high confidence that technology can support it.  The purposes of this phase are to:

- identify system interfaces,

- identify basic functional and data requirements to satisfy the business need,

- identify basic electronic records management requirements and ensure that the AIS or infrastructure system is compliant with the Federal Records Act, Privacy Act, and Paperwork Reduction Act,

- establish system boundaries, identify goals, objectives, critical success factors, and performance measures,

- evaluate costs and benefits of alternative approaches to satisfy the basic functional requirements,

- assess project risks,

- identify and initiate risk mitigation actions, and

- develop high level architecture, process models, data models, a records schedule, and a concept of operations.

This phase may include several trade-off decisions such as the decision to use COTS software products as opposed to developing custom software or reusing software components, or the decision to use an incremental delivery versus a complete, one-time deployment. Construction of executable prototypes is encouraged to evaluate technology to support the business process.  The Program Sponsor approves requirements and the Technical Review Board verifies that the requirements are clearly defined.  This phase is completed upon approval by the Technical Review Board at the High Level Requirements Review and when the Program Sponsor and the CIO agree to the system boundary.

## 1.4.3	Detailed Analysis and Design Phase

The purposes of this phase are to:

- further define and refine the functional and data requirements,

- complete a retention schedule for records and obtain approval from the National Archives and Records Administration and ensure that electronic records management requirements are incorporated into the design,

- complete reuse component selection,

- complete business process reengineering of the functions to be supported,

- develop detailed data and process models,

- define functional and system requirements that are not easily expressed in data and process models,

- further refine the high level architecture and logical design to support the functional and technical requirements, and

- continue to identify and mitigate risks, coordinating with the business area to ensure that new technology can be phased in.

At the end of this phase, the system is described by a completed high level architecture and logical design.  This phase is completed upon Technical Review Board approval at the Technical Design Review.  The Technical Review Board records this approval in a record of agreement, as described in the Technical Review Board Charter.

## 1.4.4	Development Phase

The purposes of the Development Phase are to:

- design, develop, integrate, and test the AIS or infrastructure system,

- update and finalize plans to deploy the AIS or infrastructure system, and

- complete business transition planning, and identify and initiate business transition activities.

All components of the logical design are allocated to components of the detailed design and detailed design is completed and transformed into a physical design.  Risk identification and mitigation activities continue to be performed to address any remaining risk.  This phase is completed when the Technical Review Board conducts the Production Readiness Review confirming that the AIS is complete, correct, fully tested, and ready for the Deployment Phase to begin.

## 1.4.5	Deployment Phase

The purposes of the Deployment Phase are to:

a.  ensure that the AIS or infrastructure system is installed as planned and specified,

b.  ensure that the users are trained,

c.  ensure that the end users and supporting organizations are prepared to accept the

system.

In this phase, the system is installed to support the intended business functions.  Performance objectives have been identified, agreed to, and recorded in a Service Level Agreement contained in the Operational Support Plan prior to going into operation.  Deployment occurs incrementally when logistics do not permit all the intended end users to receive the system at the same time.  Deployment includes user notification, user training, installation of hardware, installation of software onto production computers, certification of data, and integration of the system into daily work processes.  The deployment phase ends when all the intended users are first processing all the intended workload with the system, and the Program Sponsor and the CIO agree that the AIS or infrastructure system is fully operational.

## 1.4.6	Operations Phase

The purposes of this phase are to:

- operate, maintain, and enhance the AIS or infrastructure system,

- certify that the AIS or infrastructure system can process sensitive information,

- conduct routine data base assessment to ensure data quality and optimal data base performance is maintained,

- conduct periodic assessments of the AIS or infrastructure system to ensure the functional requirements are being satisfied, and

- determine when the AIS or infrastructure system needs to be modernized, replaced, or retired.

# 1.5  		Tailoring the Life Cycle

_____________________________________________________________

The tailored life cycle will contain only that which is necessary for the delivery of a quality system on time and within budget.  Common sense should prevail.

The LCM can be tailored to fit the unique needs of an AIS or infrastructure system project.  The tailored process will be described in the AIS or infrastructure system Concept Brief and Quality Assurance Plan. The Concept Brief is an informational briefing presented to the Technical Review Board in the Concept Phase that provides the project description, life cycle tailoring agreement, schedule, and any project issues.

As a tailoring example, LCM tasks and products can be reduced for an AIS project to install a COTS software product on the existing USPTO information technology infrastructure.  The System Development Manager should consider the size, complexity, and scope of the AIS or infrastructure system project when preparing the AIS or infrastructure system Project Management Plan.  During this phase, the System Development Manager will identify a tailored life cycle for the AIS or infrastructure system and provide the tailoring information to the Office of System Product Assurance for consulting purposes.  The tailored process must include the Concept Phase which bases much of the information gathering on the information engineering planning and analysis approach.  Some of the Concept Phase tasks and work products may be omitted as long as the resulting approach provides for delivery of a timely, quality, system within costs.  There are a few essential tasks and work products that cannot be “tailored out” even when a COTS software product will be used:

- succinct functional requirements,

- USPTO standard data definitions,

- records management,

- adequate testing,

- configuration management,

- user training,

- user manuals, and

- operations, maintenance, and help desk documentation.

The AIS Life Cycle Process Tailoring TSG, IT-212.2-03, provides guidance for LCM tailoring.  The tailoring information will be presented in the Concept Brief to the Technical Review Board for approval.

# 1.6  		System Development Methodology

_____________________________________________________________

## 1.6.1	General

The system development methodology supports an integrated set of principles, procedures, practices, technical standards, and supporting tools.

The system development methodology supports an integrated set of principles, procedures, practices, technical standards, and supporting tools that the USPTO has adapted for use in developing, modifying, and managing AISs or infrastructure systems.

USPTO’s methodology is described in a series of technical standards and guidelines publications.  These technical publications describe methods and procedures as well as documentation requirements (format and content) associated with developing an AIS or infrastructure system within the USPTO information technology infrastructure.  The methodology defines the activities that are needed to build a system, the interfaces among those activities, and the products created as a result of those activities.  Much of the AIS or infrastructure system analysis and design-level documentation will be captured and maintained in the Computer Aided Software Engineering (CASE) tool repository, and reused where practicable.

## 1.6.2	System Development Methodology Criteria

In order for the USPTO to build upon business process reengineering activities, share data and processes, and develop and maintain responsive automated information systems on time and within budget, a rigorous and proven system development methodology is needed that:

- Supports an integrated set of formal techniques for the planning, analysis, design, and development of automated information systems on an enterprise-wide basis rather than on a project-wide basis.

- Is business-driven and firmly anchored in the strategic planning of the business enterprise.

- Supports business process reengineering and provides for storage of planning information relative to the business enterprise such as data and process models, critical success factors, process improvement, best practices, and business functions, goals, and objectives.

- Is supported by a set of commercially available automated tools that facilitate applying the methodology and provide for a rigorous enforcement of the methodology's techniques and standards.

- Is a data-centered design approach and provides techniques for formal data modeling and data administration.

- Imposes a rigorous discipline that enforces a good structuring of data and application program code.

- Supports techniques to identify processes and process improvements that are used many times in the enterprise so that designs and program code can be reused.

- Emphasizes top management involvement to provide strategic direction and active program sponsor/customer participation throughout the life cycle.

# 1.7  	Policies and Guidelines for the Management of Projects

_____________________________________________________________

Following these policies and guidelines will result in a high probability that a quality system will be successfully integrated with business processes and will continue to be used effectively.

The following policies and guidelines apply throughout the full AIS or infrastructure system life cycle, including maintenance, and enhancement of AISs or infrastructure systems.  Further information on these policies and guidelines is contained in Chapters 2 through 7 of this manual.

## Manage AIS Projects as Investments

Proposed AIS or infrastructure system projects will be clearly supported by detailed analyses of the project’s expected costs and benefits; alternative solutions considered; potential programmatic and technical risks; and the AIS’s or infrastructure systems’ overall contribution to the business area’s and USPTO’s mission, goals, and objectives.

## Emphasize Evolutionary Development and Incremental Delivery of Products

AISs or infrastructure systems will be developed emphasizing evolutionary development and incremental delivery of products and services.  AIS or infrastructure system project plans should focus on providing the end user with usable products as early as practical.

1.7.3	Improve End-User Productivity

AISs or infrastructure system will simplify and reduce the effort required to handle administrative activities so that more employees can focus on program-related workloads.  Each AIS should meet the following objectives:

- Emphasize user friendliness over ease of technical design and application software development.

- Provide easier, secure, reliable access to data.

- Tailor management information reports to customer needs.

- Provide automated tools to facilitate end user access to and use of data.

- Provide readily available help within the application software and provide for computer based training modules.

- Reduce the reliance on paper.

- Provide easier, secure access and management to electronic records.

## 1.7.4	Encourage End-User Involvement

End-user participation and involvement throughout life cycle activities is crucial to the success of each AIS or infrastructure system and must be encouraged.  For example, end users must participate early in the AIS project in order to obtain clear, validated functional requirements.  Due consideration must be given to ensure that all internal, external, and legal customer requirements are adequately reflected in the automated solution.

## 1.7.5	Ensure that Adequate End-User Training is Provided

End-user training is essential in order for the AIS or infrastructure system to be effectively used.  End-users must be provided with initial training to support a newly installed AIS or infrastructure system, and must receive all additional training necessary to effectively utilize AIS or infrastructure system modifications and enhancements.

## 1.7.6	Employ Matrix Management Techniques

Matrix management techniques should be used to recognize the complementary roles of functional users, AIS or infrastructure system developers, and other supporting organizations.  The Project Manager reports to the Program Sponsor, and is responsible for coordinating end-user participation and managing functional requirements. Generally, the System Development Manager reports to the CIO and is matrixed to the Project Manager.  The System Development Manager is responsible for coordinating development and technical support, and for managing technical requirements.

## Comply with USPTO Information Technology Standards and Guidelines

AIS or infrastructure system projects must follow the provisions of the USPTO Information Technology Standards and Guidelines (TSGs), which provides up-to-date technical guidance designed to aid the System Development Manager deliver a quality system and the System Maintenance Manager to maintain and enhance one.

## Use USPTO Information Technology Infrastructure and  Ensure Compatibility With USPTO Technical Reference  Model

AIS or infrastructure system projects must be developed within the bounds of current and planned information technology standards and capabilities as defined in the USPTO Strategic Information Technology Plan and USPTO Technical Reference Model.  An AIS or infrastructure system project's computer and network resource requirements must be satisfied by the USPTO information technology infrastructure capabilities whenever practicable. PTOnet and distributed processing platforms will be exploited to provide managers and staff with needed automated support.

A key information technology management objective is to transform the USPTO information technology infrastructure into a standards-based open system environment.  An open system environment will allow the USPTO to add new or replace existing products or infrastructure components as new technologies are introduced into the marketplace.  System Development Managers will select standards and products that conform to the Technical Reference Model in the detailed design and development of the technical architecture.  System Development Managers must adhere to approved standards and preferred products unless other standards or products can be clearly demonstrated to be cost-effective over the life of the application.

The System Architect is responsible for developing, maintaining and evolving the USPTO information technology infrastructure and the USPTO Technical Reference Model.

## 1.7.9	Use USPTO Standard Data Definitions

Standard definitions of data will be developed and maintained so that it will be easier for users to reliably and consistently interpret and use data.  AISs or infrastructure systems shall be developed using USPTO standard data models and data elements.  Guidance is contained in the USPTO Data Management Technical Standard and Guideline, IT-212.2-05, and Data Element Standardization Technical Standard and Guideline, IT-212.3-13.

## 1.7.10	Use USPTO Standard System Development Tools

The CIO has selected a standard suite of system development tools that support the system development life cycle.  The standard tools will reduce maintenance costs, make projects more predictable, reduce dependence on original developers, leverage the experience of in-house staff to work on different projects without retraining on system development tools, and facilitate reuse of software components.  System Development Managers will use the USPTO standard system development tools designated in the USPTO Technical Reference Model and refrain from using other system development tools unless it can be clearly demonstrated that other system development tools would be more cost effective over the life of the application.

## Cost and Schedule Performance Must Be Planned and Reported

USPTO has established a project management control system to provide visibility into actual progress of each project.  The project management control system provides for tracking actual cost and schedule performance against project plans.  This visibility will help both functional and technical managers identify problem areas and take corrective actions when actual results deviate significantly from plans. Project Managers and System Development Managers will ensure that the necessary information for each AIS or infrastructure system project is provided in a timely manner and entered into the project management control system.  Project planning specialists from the CIO’s Office of Technical Plans and Policy will assist the Project Manager and the System Development Manager in developing a project management plan and project schedule.  The USPTO Project Management Technical Standard and Guideline, IT-212.2.01 provides guidance on how to prepare project management plans and project schedules.

## Each Project Must Be Consistent with the USPTO Strategic Information Technology Plan

AIS or infrastructure system projects will be contained in the USPTO Strategic Information Technology Plan.  New projects must be consistent with the USPTO Strategic Information Technology Plan and be agreed to by both the business area Program Sponsor and the CIO, as described in paragraph 1.4.1.  The Program Sponsor and the CIO will identify and allocate project resources and the new project will be included in the next planning cycle.  Project Managers shall identify in the LCM documentation the specific key goals and objectives of the USPTO Strategic Plan that are supported by the AIS or infrastructure system project.

## 1.7.13	Use of COTS Software is Encouraged

Commercial-Off-The-Shelf application software products cover a broad spectrum of capabilities.  These products can satisfy USPTO business needs and can operate on USPTO’s Information Technology Infrastructure.  COTS application software products are preferred over developing new application software. USPTO unique requirements not provided by the COTS product will be satisfied through application program interfaces.

## 1.7.14    	Business Processing Reengineering Techniques May Be Applied

USPTO will employ reengineering and continuous quality improvement techniques as required to help ensure that processes are as effective and efficient as possible.  Information technology is a key enabler of process improvement.  No AIS or infrastructure system project will be undertaken before the supported process has been reviewed and, as necessary, redesigned to its greatest possible effectiveness.  If needed, formal business process reengineering will precede application software design and development.  The business area Program Sponsor, in consultation with the CIO, will designate AIS or infrastructure system projects that will apply business reengineering techniques.

## 1.7.15	Secure and Protect All Sensitive Information

Security of all sensitive information must be explicitly considered throughout the AIS or infrastructure system life cycle and documented in an AIS security and disaster recovery plan.  Program Sponsors, with the guidance and assistance of the CIO, must ensure that their AISs or infrastructure system and business procedures will process and handle sensitive information and deliver critical services in a manner compliant with all applicable laws and regulations. AISs or infrastructure systems will be controlled with respect to access, authority to modify, and ability to operate.  Security specialists from the CIO’s Office of Technical Support Services will maintain a USPTO Information Technology Infrastructure Security and Disaster Recovery Plan and assist the System Development Manager develop a security and disaster recovery plan that addresses the unique business requirements of an AIS or infrastructure system project.

## 1.7.16	Apply Risk Management Techniques

Risk management must be applied to all LCM-AIS projects throughout the life cycle. Risk, as used in the LCM, is associated with a lack of resources, information, and/or control.  Risk management is distinguished from "problem management" in that risk management is concerned with situations that may or may not occur, whereas problem management is concerned with known difficulties that are a result of a risk having occurred.  An analysis of risk and any strategy adopted to control risk should at least consider the effect of one or more of three factors: lack of resources (such as personnel or funding); lack of information (for example, completeness and confidence); or lack of control over the decision-making process (such as external project decisions affecting the project plans and assumptions).  Applying risk management to production AISs or infrastructure systems includes considering backup and recovery in service level agreements and plans.  Management responsibility for a risk must be assigned to individuals and organizations that can affect the risk's root causes.  The Project Manager shall be responsible for managing project risks over which the Project Manager can exert direct control.  Risks that affect the project, but are not under project control, shall be explicitly assigned to either the Program Sponsor or the CIO, as appropriate.  Situations external to the project that could be sources of risk to the project shall be coordinated through the Project Manager.  Risk shall be a consideration in Technical Review Board and management decisions.  Project risk situations, plans, and progress against risks must be considered at all project reviews. Guidance is contained in the USPTO Project Management Technical Standard and Guideline, IT-212.2-01.

## 1.7.17	Focus on Software Process Improvement

The USPTO is committed to a program of continuous software process improvement.  The USPTO’s software process improvement program will enhance the USPTO’s ability to deliver quality systems in a timely and cost-effective manner. Established in January 1994 to define and institutionalize a USPTO-standard system development life cycle management process, the Software Engineering Process Group (SEPG) is the CIO’s focus group for capturing best practices, presenting new technology and tools, reviewing draft guidelines and keeping the CIO staff aware of new software process improvement opportunities.  System Development and System Maintenance Managers must stay abreast of and contribute to process improvements in order to institutionalize LCM within USPTO and make it work.

## 1.7.18	Manage AIS or Infrastructure System Baselines

An AIS or infrastructure system baseline is an approved set of work products for a stage in the system life cycle.  Baselines are established at the completion of phases of the life cycle. The set of work products designated as a baseline is managed as a unit.  Changes to baselines are approved by their designated owners. System Development and System Maintenance Managers must establish and maintain baselines throughout the AIS or infrastructure system life cycle to: keep successive versions of the system synchronized with incremental service delivery promises; keep track of the current contents of the complete systems; and maintain complete technical data packages.  Properly managing baselines will prevent costly later rework and rediscovery, and aid reuse. Configuration management specialists will periodically audit established AIS or infrastructure system baselines to verify that they conform to the documentation that defines them. The Configuration Management Technical Standard and Guideline, IT-212.2-06, describes the baselines and their contents in more detail. Technical reviews decide completion, and each baseline type is described in Section 1.8.2, Conducting Technical Reviews.

## 1.7.19	Implement Key Software Management Processes

The following policies apply to phase-independent key software process areas that are necessary to support the definition, design, development, deployment, operation, maintenance, and enhancement of AISs or infrastructure systems.  These key process areas are configuration management, quality assurance, data management, and requirements management.  Other key process areas are discussed in the relevant chapters of this Manual.

- Requirements Management.  Requirements management controls the identification, definition and refinement of requirements as analysis proceeds from high level to detail definition, and allocation to system and subsystem components.  Requirements must be managed as they change and evolve throughout the AIS or infrastructure system life cycle. The System Development Manager will create and maintain a requirements database and a requirements traceability matrix to identify changes throughout the AIS or infrastructure system life cycle.  Requirements management specialists from the Office of System Product Assurance will help the System Development Manager develop the requirements traceability matrix.

- Data Management.  The System Development Manager will establish plans to manage the data, data models, and databases required by the AIS or infrastructure system.  Data management plans will be defined and updated to ensure that all data related issues are addressed throughout the life cycle and to ensure that the agency records management program is followed for compliance with records management laws and regulations.  Data management specialists from the CIO’s Office of Data Management will, in coordination with the System Development Manager, prepare data management plans and will review the data management plans and data models to ensure compliance with data administration policy and guidelines.  Data management specialists will also facilitate the processes for developing data models and standardizing data elements.  Records management staff from the CIO’s Office of Data Management will assist the System Development Manager in scheduling AIS or infrastructure system records and ensure that the AIS or infrastructure system is compliant with the Federal Records, Privacy Act, and Paperwork Reduction Act and meets basic electronic records management requirements.

- Quality Assurance.  The System Development Manager will establish plans to provide management with appropriate visibility into the process being used by the software project and the products being built. Quality assurance specialists from the Office of System Product Assurance will, in coordination with the System Development Manager, prepare Quality Assurance plans and will attend all major technical reviews.  Quality assurance specialists will review and audit the AIS or infrastructure system project work products and activities to help assure that the AIS or infrastructure system Project will deliver a quality system.

- Configuration Management.  Configuration management of all AIS or infrastructure system hardware, software, and accompanying documentation shall be performed throughout the AIS or infrastructure system life cycle.  The Office of System Product Assurance, in coordination with the System Development Manager, will establish plans and baselines to ensure configuration identification, configuration control, configuration status accounting, and configuration audits for all configuration documentation, physical media, and physical parts composing the system.  Configuration management shall also be applied to any resources such as compilers or CASE tools used to develop the AIS or infrastructure system.  The configuration management process shall provide a means for recording, reviewing, approving, and tracking change requests and problem reports for all configuration items/units. Configuration management methods will be compatible with and leverage the use of standard system development tools designated in USPTO’s Technical Reference Model.  Configuration management specialists from the Office of System Product Assurance will work with the System Development Manager in preparing configuration management plans and performing configuration management and will attend all major technical reviews.

## 1.7.20	Conduct Peer Reviews

Peer reviews will be conducted on designated critical AIS or infrastructure system projects to identify and remove defects from the project's work products early and efficiently.  The AIS or infrastructure system project's peer review process and the specific work products that will undergo peer review will be documented in the quality assurance plan.  Peer reviews should be led by trained peer review leaders, and each person attending a peer review will have a specific role that they are trained to perform.  Products that undergo peer review will have all actions identified as a result of the peer review tracked until they are resolved.  Checklists that guide the peer reviews will be maintained by the Office of System Product Assurance, and reviewed by the checklist's potential users.  Results of peer reviews will be collected and reported in a manner that leads to positive corrective actions taken and not to evaluate the performance of individuals.

## 1.7.21	Establish A Technical Training Program

A technical training program for the AIS or infrastructure system project must be established to help ensure that appropriate skills and knowledge of individuals assigned to the project are developed so that they can perform their project roles effectively and efficiently.  Each project will evaluate its current and future skill needs and determine how these skills will be obtained.  Technical training specialists from the CIO’s Office of Technical Plans and Policies will assist the System Development Manager in developing a training program.

## 1.7.22	Encourage Prototyping

The use of prototyping in the Concept and Detailed Analysis and Design Phases to help define and refine requirements is encouraged.  Prototypes can enhance user and developer understanding and interpretation of requirements or validate portions of the technical architecture against the functional requirements and technical specifications. Executable prototypes must be fully tested and documented and meet the minimum criteria established in section 1.5 prior to being placed in pilot or production status.  Additional information on prototyping and pilots is provided in chapters 3 and 4 of this document.

## 1.7.23	Reuse Software Whenever Practical

The reuse of existing system components will reduce cost and quicken system delivery.  System Development Managers will construct AISs or infrastructure systems from previously developed system components whenever practical.  The reusable components include data and process models, technical design specifications, plans, test suites, and program code.

## 1.7.24	Help Ensure Software Independence

AISs or infrastructure systems will be developed, documented, and maintained in such a manner as to reduce reliance on individuals or organizations that operate, maintain, or enhance the AIS or infrastructure system.  Initially, this will require additional cost and effort to collect, analyze, and enhance the life cycle documentation necessary to ensure software independence.  Once this technical knowledge base has been firmly established, however, AISs or infrastructure systems can be maintained and enhanced much more cost-effectively, much faster and with far less effort.

## 1.7.25	Using Contractor Support

For contractor-supported AIS or infrastructure system projects, System Development Managers will ensure that USPTO personnel work closely with the contractor to ensure that tasks are accomplished in a quality, timely, and cost-effective manner and that technology transfer occurs. Contractors are prohibited from preparing Project Manager Charters and related decision memoranda.  Contractors are also prohibited from assigning a role, responsibility or authority, which is documented in the Project Management Plan.

## 1.7.26	Maintain Complete Project Records

LCM documentation developed in support of AIS or infrastructure system projects will be retained in accordance with USPTO’s record management schedule.  LCM documentation developed in support of an AIS or infrastructure system project that is retired before successful fielding also will be retained in accordance with USPTO’s record management schedule.  All documentation related to a contract shall be retained after contract close-out in accordance with USPTO’s record management schedule.  Contract close-out is the last billing date and may be as long as 3 years after the end of the contract.

# 1.8  		AIS or Infrastructure System Project Reviews

_____________________________________________________________

Technical reviews provide a mechanism to help managers monitor the progress of an AIS or infrastructure system project and direct corrective actions to keep the project on schedule for delivering a quality system.

Diverse and rapidly developing opportunities to employ computers to improve mission performance have brought increased importance to the application and management of information technology. Technical reviews must be performed to ensure that an AIS or infrastructure system project is progressing on schedule and within budget and is satisfying functional requirements. The conduct of the reviews may be tailored to address the specific needs of each project consistent with the development plan.  The Technical Review Board conducts reviews of work products and plans for the next life cycle phase.  The CIO conducts in-progress reviews of cost, schedule and deliverables.  The Program Sponsor and the CIO jointly conduct a management review to decide to initiate an AIS or infrastructure system project.

## 1.8.1	Purpose of Technical Reviews

Technical reviews are performed to provide sufficient visibility into the AISs or infrastructure systems’ functional and technical characteristics, as well as establish management control points for assessing project cost, schedule, and quality.  The purposes of a technical review are to:

- Improve the quality of intermediate AIS or infrastructure system work products and to correct defects as early in the life cycle as possible in order to prevent problems over the long run.

- Ensure that the AIS or infrastructure system being produced can be supported by the current and planned USPTO information technology infrastructure.

- Ensure that the AIS or infrastructure system project conforms to USPTO system development methodology and supporting tools, uses USPTO standard data, and adheres to the USPTO Technical Reference Model.

- Monitor the impact of an AIS or infrastructure system project on other USPTO AISs, AIS projects, and the USPTO information technology infrastructure.

## 1.8.2	Conducting Technical Reviews

The Project Manager, System Development Manager, or Technical Review Board Chairperson may choose to convene technical reviews at any time during the life cycle to determine the state of work products.  Technical reviews may be held as one or more events as determined by the Technical Review Board Chairperson.  Reviews may be combined.  The conduct of the reviews may be tailored to address the specific needs of each project consistent with the AIS or infrastructure system development plan.  Tailoring guidance may be found in the Automated Information System Life Cycle Process Tailoring Technical Standard and Guideline, IT-212.2-03.  A typical project will not require all the reviews and baselines discussed below.  Guidance is contained in the USPTO Quality Assurance Technical Standard and Guideline, IT-212.2-04.

- High Level Requirements Review.  This review is conducted to confirm that a common understanding of the functional requirements for the AIS or infrastructure system is captured in the System Boundary Agreement or Requirements Specification, Part 1.  This review is conducted at the end of the Concept Phase.  This review approves the System Boundary Baseline, which includes the functional requirements and project related cost, schedule, and performance measures.  The System Boundary Baseline contains the System Boundary Agreement.  The developmental configuration is initiated after this review under the ownership of the System Development Manager.  The developmental configuration consists of the design and the associated technical data that defines the components of the system.

- Detailed Level Requirements Review.  This review is conducted to confirm that a common understanding of the functional requirements for the AIS or infrastructure system is captured in the Requirements Specification, Parts 1 and 2.  This review is conducted during the Detailed Analysis and Design Phase.  This review approves the Requirements Specification, Parts 1 and 2.

- Logical Design Review.  This review is conducted during the Detailed Analysis and Design Phase to confirm the functional, data and other requirements of the AIS, to verify the data and process models of the AIS or infrastructure system, to confirm the ability of the High Level Architecture to satisfy the functional, data and other requirements and to confirm the allocation of requirements to components of the technical architecture.  This review approves the logical design (allocated) baseline, which describes approved functional, data, interface, and other requirements allocated to the system or subsystem elements.

- Technical Design Review.  This review is conducted during the Detailed Analysis and Design Phase to evaluate the appropriateness of the technical design.  This review verifies that the system conforms to the infrastructure baseline.  The USPTO Information Technology Infrastructure is controlled separately from any individual AIS project.  This baseline is managed by the System Architect.

- Test Readiness Review.  This review is conducted at the end of the Development Phase to determine whether unit and integration testing has been conducted in accordance with the test procedures and that the tests are complete.  This review determines whether the system is ready for independent acceptance testing. The development configuration is created during the Development Phase and maintained under informal configuration management at the project level until the end of the Development Phase. The developmental configuration consists of the design and associated technical data that defines the components of the system. A version of the Developmental Configuration is placed under formal configuration management after Test Readiness Review and is used for acceptance testing.

- Beta Readiness Review.  This review is conducted during independent acceptance testing to determine whether formal testing is complete and the system is ready for user Beta testing.  The review is performed during the Development Phase.

- Production Readiness Review.  This review is conducted at the end of the Development Phase to determine whether the system is adequately tested, satisfies the boundary conditions, and is ready for production use.  The Program Sponsor participates in the Production Readiness Review.  This review establishes that appropriate operational and maintenance support is available.  This review establishes the product and operational baselines. The Product Baseline consists of the documentation describing all the necessary functional and physical characteristics of the elements that compose the system and the actual equipment and software. The Operational Baseline consists of the parameters and procedures needed to operate and to perform routine maintenance on the AIS or infrastructure system.  The Operational Baseline is established to record changes to those items for which a review by the Technical Review Board prior to making the change is not required.

- Post Installation Review.  This review assesses results during the production trial period. The TRB or the Project Manager may request that a Post Installation Review (PIR) be conducted.  The PIR is used to identify remaining discrepancy reports, deferred requirements for future maintenance releases, and any issues related to the system operation.  Based upon the results of this review, the Technical Review Board and the business area Program Sponsor give permission for the AIS or infrastructure system to remain in production if there are no serious problems.

- Functional Configuration Audit.  This audit may be conducted during the Deployment Phase to ensure that all functional requirements specified in the System Boundary Agreement are satisfied.

- Physical Configuration Audit.  This audit is conducted during the Deployment Phase to determine whether the delivered (“as built”) system is complete and consistent with its documentation.

## 1.8.3	In-Progress Reviews

The CIO and Program Sponsors conduct periodic in-progress reviews (IPR) to assess progress, adherence to schedule and budget, possible impact on other projects, and to direct corrective actions as needed.  Project Managers and System Development Managers should also hold regularly scheduled (e.g., biweekly) project status reviews that discuss progress against project plan as well as technical issues.

# 1.9    	Roles and Responsibilities for AIS or Infrastructure System Project Management

_____________________________________________________________

The successful development, deployment, and operation of an AIS or infrastructure system require close collaboration and partnership between the Program Sponsor and the CIO.

The successful development, deployment, and operation of an AIS or infrastructure system require close coordination and partnership between the Program Sponsor and the CIO.  Teamwork is essential to delivering a quality system on time and within budget.  The Program Sponsor identifies and prioritizes business needs.  The CIO determines how best to employ technology.  The Program Sponsor and the CIO provide resources and work together to determine the project schedule and cost estimates.

## 1.9.1	Program Sponsor

The Program Sponsor is responsible for defining and validating functional requirements, for making resources available to support information technology program initiatives, and for reviewing the progress of AIS or infrastructure system projects to ensure that functional requirements are being satisfied in a timely and cost-effective manner.  Program sponsors within their area of responsibility will:

- Ensure that the goals and objectives of all information technology related initiatives are consistent with the goals, objectives, and governing strategies of the USPTO Corporate Performance Plan and the Business Area’s Strategic Plan.

- Exercise management oversight of AIS or infrastructure system projects to ensure that business requirements are being satisfied in a cost-effective manner.

- Exercise management oversight of the evaluation and improvement of business processes as well as the development of business goals, objectives, critical success factors, and performance measures.

- Ensure that the necessary data for each AIS or infrastructure system project are provided in a timely manner and are entered into USPTO's project management control system and work with the CIO to ensure that corrective actions are taken when needed.

- Ensure, with the assistance of the CIO, that AISs or infrastructure systems processes handle sensitive information and deliver critical services in a manner compliant with all applicable laws and regulations.

- Ensure that business area transition planning and appropriate training are accomplished in a timely manner.

- Assign Project Managers to direct and coordinate the complete effort to achieve agency business objectives to be accomplished by the AIS or infrastructure system project.

- Assign Production Managers to direct and coordinate the maintenance and modifications of an operational AIS or infrastructure system required to keep up with changing business needs.

## 1.9.2	Chief Information Officer (CIO)

The CIO is the principal advisor to the Commissioner on the effective application of information technology and will:

- Ensure that all information technology initiatives are managed in accordance with sound life cycle management principles and practices and are consistent with the USPTO Strategic Information Technology Plan.

- Perform technical reviews to ensure that an AIS or infrastructure system project is progressing on schedule and within budget and is satisfying functional requirements.

- Establish service level agreements to promote organized and timely information technology support to customers.

- Use the results of periodic customer focus sessions to identify opportunities for improvement, to determine customer needs, and to determine whether an AIS or infrastructure system effectively serves its users and meets established performance measures.

- Establish and administer a project management control system to provide visibility into the actual progress of each AIS or infrastructure system project.

- Ensure that security is adequately considered in system design and issue an accreditation statement that authorizes operation of the AIS or infrastructure system based on evidence provided by the certification and verified by an accreditation audit.

- Assign a System Development Manager to develop and deploy an AIS or infrastructure system.

- Assign a System Maintenance Manager to perform system maintenance and develop and deploy system enhancements as identified and prioritized by the Production Manager.

- Operate the AIS or infrastructure system according to established Service Level Agreements contained in the Operational Support Plan.

## 1.9.3	Steering Committee

The Steering Committee may be created to perform the duties of or assist the Program Sponsor when an AIS or infrastructure system project crosses organizational boundaries.  The Steering Committee is composed of functional and technical representatives appointed by the Program Sponsor and the CIO.

## 1.9.4	Project Manager

Appointed by the Program Sponsor, the Project Manager oversees the complete effort to achieve agency business objectives to be accomplished by the AIS or infrastructure system project.  The Project Manager, in coordination with the Program Sponsor, the System Development Manager, and other managers, develops the project budget and schedule, and monitors cost and schedule performance for the project.  The Project Manager will:

- Provide daily direction and coordination for the business aspects of the design, development, and deployment of an AIS or infrastructure system subject to the technical direction of the CIO and the business direction of the Program Sponsor.

- Coordinate changes to the business environment brought on by the implementation of new business processes.  The changes to the business environment may require resolution of labor management issues, legal issues, employee relations issues, and/or changes to the physical workplace environment.

- Ensure that users: (1) actively participate in the AIS or infrastructure system project to help identify and refine requirements and to test the system; and (2) are adequately trained before the AIS or infrastructure system is fully deployed.

- Under matrix management, the Project Manager directs the activities of the project team.  The Project Management Technical Standard and Guideline, IT-212.2-01, describes the responsibilities of the Project Manager in more detail.

## 1.9.5	System Development Manager

Appointed by the CIO, the System Development Manager is responsible for designing, developing and deploying an AIS or infrastructure system. The System Development Manager ensures that the AIS or infrastructure system is consistent with the agency's strategic information technology plans and is managed according to sound life cycle management principles and practices.  The Project Management Technical Standard and Guideline, IT-212.2-01, describes the responsibilities of the System Development Manager in more detail.

## 1.9.6	System Architect

A senior manager in the Office of System Architecture and Engineering serves as the USPTO System Architect.  Appointed by the CIO, the System Architect is responsible for:

- Developing or approving the high level design for all USPTO AISs or infrastructure systems,

- Managing the evolution of USPTO’s information technology infrastructure, and

- Developing and maintaining the USPTO’s Technical Reference Model.

The Technical Reference Model provides a comprehensive set of information technology standards, services, protocols, and preferred products that define the target technical environment.  This model is used for the acquisition, development, and support of all USPTO AISs or infrastructure systems.

## 1.9.7	Production Manager

Appointed by the Program Sponsor, the Production Manager, directs and coordinates the maintenance and modification of an operational AIS or infrastructure system required to keep up with changing business needs.  Under matrix management, the Production Manager identifies and prioritizes functional requirements that will be incorporated into an operational AIS or infrastructure system by the System Maintenance Manager and coordinates the implementation of those changes in the business environment.  The Production Manager ensures that users participate in system testing and are adequately trained before the AIS or infrastructure system changes are fully deployed.  The Production Manager assures that the AIS or infrastructure system has been adequately secured.

## 1.9.8	System Maintenance Manager

Appointed by the CIO, the System Maintenance Manager performs system maintenance and develops and deploys system enhancements as identified and prioritized by the Production Manager.  The System Maintenance Manager ensures that the operational AIS or infrastructure system is managed according to sound life cycle management principles and practices.

## 1.9.9	Technical Review Board

Appointed by the CIO, the Technical Review Board evaluates the progress of each AIS or infrastructure system project by assessing the quality of its work products and recommends action to the CIO.  The Board ensures that USPTO’s Life Cycle Management methodology is followed in a coordinated, common-sense manner for all AIS or infrastructure system projects by conducting technical reviews described in section 1.8. Results of the technical reviews are provided to the Commissioner of Patents and Commissioner of Trademarks, as appropriate.  The Technical Review Board Charter defines the Board's authority and responsibility in more detail.

## 1.9.10	Software Engineering Process Group

Appointed by the CIO, the Software Engineering Process Group defines, introduces, monitors, and continuously improves system development life cycle processes.  The goal of the SEPG is to develop and institutionalize an identifiable, measurable, and repeatable life cycle management process that facilitates the delivery of quality systems when promised and within cost estimates.  The Software Engineering Group Charter defines the Group’s authority and responsibility in more detail.

# Footnotes

An automated information system (AIS) is a combination of functional users, information technology personnel, business processes and procedures, application software, system software, documentation, commercial off-the-shelf software, computer, networking and other information technology resources that collect, record, process, store, communicate, retrieve, display, and disseminate information.

Tailoring is the process of omitting or reducing tasks and work products from the AIS or infrastructure system project management plan.  In special cases, tailoring may add tasks or work products.

Service Level Agreements are contained in the Operational Support Plan and describe the services OCIO provides to another USPTO organization.  Each service description includes OCIO's commitments in regards to providing the service and the other organization's responsibilities in regards to obtaining the service.  The final document is approved by the CIO and his peer in the other USPTO organization.

The USPTO Technical Standards and Guidelines are downloadable and may be found at http://ptoweb/ptointranet/tsg/tsgindex.htm.

USPTO Technical Standards and Guidelines may be found at http://ptoweb/ptointranet/tsg/tsgindex.htm.

The USPTO Strategic Information Technology Plan documents the role that information technology plays in achieving the USPTO’s mission, vision, and goals.  The USPTO Technical Reference Model provides a comprehensive set of information technology standards, services, protocols, and products that define the target technical environment for the acquisition, development, and support of USPTO AISs.

Pilot - A limited scope application program that satisfies most, if not all of the user’s requirements.  It normally is targeted to a limited user group for evaluation with the understanding that it will be scaled up and integrated into a fully compatible production system.

The Requirements Specification organizes the requirements into high level (Part 1) and detailed requirements (Part 2).