## Change Request Number: 02-09	Date Received:  1/16/02

Title:  Investment Analysis Policy

# Name: David Woodson

Routing Symbol: ASU-120

Phone: 267 7601

Policy OR Guidance: Policy

Summary of Change: This change fleshes out the transformation to a two-phased investment analysis process that was introduced into AMS in late 2001. Detailed program planning is moved into final investment analysis from solution implementation; investment programs are baselined for variance tracking at the final investment decision after completion of detailed planning and solicitation for prime contractual needs; the determination of initial requirements is removed from investment analysis; the initial requirements document is completed before the mission need decision; and the JRC must approve planning, funding, and resources for both initial and final investment analysis before work can begin. This change also strengthens the requirement to develop and approve new investment opportunities within context of all existing and planned assets to provide a particular service or capability, and it focuses attention on the need to plan and manage every aspect of achieving value and benefits from investment dollars, particularly those outside the authority of n integrated product team or management unit.

Reason for Change: Current AMS policy for investment analysis is internally inconsistent and does not reflect current best practices now instituted within FAA.

Development, Review, and/or Concurrence: ASD-400 (IA organization) has reviewed and commented extensively. This draft reflects their recommendations. This draft is also consistent with recommendations of the IPLT Lifecycle Management Policy team sponsored by Marty Phillips and Steve Zaidman. This team has representation from AOP, ACP, APP, AST, ABU, ANS, AUA, ARN, AND, ACM, AIO, ASD, ATO, ABZ, ANI, and ASF.

Target Audience: Lifecycle management specialists and managers.

Potential Links within FAST for the Change: N/A

Attachments: Language of change

### Briefing Planned: Yes

ASAG Responsibilities: Review and Comment

2.4 Investment Analysis

Figure 2.4.1 illustrates the phases and decision points of investment analysis, which is conducted to ensure the critical needs of the agency are satisfied by practical and affordable solutions. Initial investment analysis rigorously evaluates alternative solutions to mission need and determines which offers the best value and most benefit to the agency and its customers within acceptable cost and risk. Final investment analysis develops detailed plans and final requirements for the proposed investment program, including a lifecycle program baseline that establishes cost, schedule, performance, benefits, and risk-management boundaries for program execution.

Figure 2.4.1 – The Phases and Decision Points of Investment Analysis

Investment analysis is conducted within a strategic context of all assets, capabilities, and resources planned or in-place to provide a specific capability or service, as well as within context of the current and planned architecture of the National Airspace System. Strong stakeholder involvement is mandatory throughout investment analysis, and all stakeholders must buy into and support the solution approved at the investment decision.

Investment analysis is a flexible process that is tailored for the specific analysis to be performed. Tailoring decisions are recorded in the appropriate action plan for initial or final investment analysis, as approved by the Joint Resources Council. The FAA Acquisition Executive may also approve tailoring of the investment analysis process.

A full-up investment analysis by a dedicated team is usually appropriate for major, complex investment opportunities. Tailoring, which infers lesser levels of analysis, may be most practical for smaller, less complex programs and for re-planning previously approved investment programs as a prelude to baseline changes. In all cases, rigorous standard processes and techniques shall be applied. These standards and techniques are resident in and the responsibility of the investment analysis organization.

The mission need statement establishes the mission need and its urgency , and states when an operational capability must be in place. This, in turn, establishes when investment analysis must be complete to allow sufficient time to acquire and deploy a suitable solution. The key is to balance the timeliness of the analysis with development of comprehensive, rigorous data needed by the Joint Resources Council to make an informed investment decision.

The following factors must be considered while conducting an investment analysis:

- Operationally suitable, low-risk commercial or nondevelopmental solutions are strongly preferred over complex developmental alternatives. The agency undertakes developmental programs only when necessary. For complex and developmental programs, the agency minimizes risk by applying such management techniques as evolutionary development, block upgrade, or pre-planned product improvement to satisfy requirements that cannot or need not be met today. If the best overall solution to mission need requires development, sufficient cost and schedule must be factored into the lifecycle program baseline of the proposed solution to accommodate the increased risk.

- Should a nonmaterial solution emerge during investment analysis that satisfies the need, can be achieved within approved budgets, and is operationally acceptable to the user, it may be implemented without proceeding further in the lifecycle management process. Upon making the decision to implement a nonmaterial solution, the Associate Administrator of the operating organization notifies the Joint Resources Council, which then terminates investment analysis activity.

- Affordability is a key factor in the decision to approve a new investment program. The Systems Engineering/Operational Analysis Team (SEOAT) maintains a relative priority listing of all existing and proposed agency investment programs, based on standard criteria approved by the Joint Resources Council. The SEOAT assesses the affordability of candidate solutions to mission need during initial investment analysis versus all other agency investment needs based on this priority listing. In the same manner, it assesses the affordability of a proposed new investment program during final investment analysis. The SEOAT is composed of representatives from each line of business and other appropriate functional disciplines, and is chaired by the Director, System Architecture and Investment Analysis.

- The FAA Work Breakdown Structure shall be used when developing cost and schedule estimates for investment programs. Where available, cost estimates must be based on historical data captured by the agency’s cost accounting system.

- The investment analysis team must consider the general direction and specific objectives of FAA strategic planning when considering alternative solutions to mission need. The emphasis during both mission and investment analysis is the overall strategic benefits that can be obtained toward achieving agency service objectives. Additionally, the results of investment analysis and subsequent decisions from that analysis feed back into the evolution of agency strategic planning.

Investment analysis processes and alternatives must conform with Federal laws, regulations, and guidelines such as those specified in OMB directives. For example, OMB Circular A-76, Performance of Commercial Activities, establishes government policy to rely on commercial sources to supply the products and services the government needs and to perform inherently governmental activities in-house. The FAA follows the policies of Circular A-76 to the extent such policies are consistent with FAA’s statutory authority. Potential A-76 issues are addressed during investment analysis and at other stages of lifecycle management, as appropriate.

2.4.1 Initial Investment Analysis - Analyze Alternatives and Determine Preferred Solution

The action plan for initial investment analysis specifies the resources (people and money), schedule, activities, documentation, and alternatives to be analyzed during initial investment analysis. The Joint Resources Council approves the action plan at the mission need decision and provides resources for its execution. Initial requirements should be defined in the initial requirements document before beginning investment analysis.

Figure 2.4.2 Principal activities of initial investment analysis

2.4.1.1 What Must Be Done

- Form investment analysis team. After approval of mission need, the investment analysis staff works with the sponsoring organization and the designated integrated product team or management unit to establish the investment analysis team, as specified in the action plan for initial investment analysis. Each team typically has operations analysts and requirements specialists from the organization with the need; acquisition, engineering, and market specialists from the integrated product team or management unit; investment analysis staff specialists with skills in such disciplines as risk assessment, cost and schedule estimating, and benefits estimation; and technical specialists from FAA staff elements or other sources for whatever support is needed. This team conducts the analysis and generates the information used by the Joint Resources Council at the initial investment decision. It is highly desirable for key members from mission analysis to participate on the investment analysis team, particularly the initial requirements team lead.

- Define evaluation factors. The investment analysis team determines the evaluation factors against which each alternative will be evaluated competitively and impartially. Evaluation factors address the most important issues confronting the Joint Resources Council as it makes decisions to allocate agency resources among investment opportunities. Typically, evaluation factors embrace such considerations as operational suitability, compatibility with the NAS architecture, lifecycle cost and benefits, risk, security, safety, human capabilities and limitations, physical infrastructure, regulatory and procedural impact, and environmental impact.

- Conduct market survey. The investment analysis team surveys the marketplace to determine the capability, state of development, risk, and cost of potential solutions to mission need. It uses the results of this survey to refine the requirements and alternatives it will evaluate. The preference is commercial or non-developmental items and services or nonmaterial solutions that are cost-effective and operationally suitable. Developmental alternatives are considered only if other choices are not cost-effective or operationally acceptable to users. Operational or factory capability demonstration of potential solutions is strongly encouraged to verify suitability for meeting mission need.

- Finalize investment analysis action plan. Changes to the investment analysis action plan at this point typically result from the addition of newly identified alternative solutions, a change in team membership, or a change in member roles and responsibilities. The addition of new alternatives may have a collateral impact on estimated resources and time necessary to complete the analysis. All team members sign the final action plan, signifying acceptance, resource commitment, and support by the participants and their parent organizations. The JRC Secretariat notifies the Joint Resources Council when alternatives are added or if additional resources are needed beyond those approved at the mission need decision.

- Analyze alternatives. The investment analysis team evaluates the alternative solutions in the final action plan by compiling and analyzing data against the evaluation factors. This process may involve multiple iterations and tradeoffs among the key evaluation factors to determine the most advantageous solution to core agency needs, not necessarily one that meets every initial requirement (See Figure 2.4.3). However, it is essential that user stakeholders support any substantive modifications to requirements. The analysis of alternatives must include the impact of complying with applicable federal regulations and requirements. Ideally, the alternatives should be qualitatively different from each other (e.g., different technologies, such as ground-based vs. airborne solutions). For complex and developmental alternatives, incremental delivery, evolutionary development, and pre-planned product improvement should always be evaluated as ways to reduce risk and satisfy important requirements at a future date that cannot or need not be met today. Alternatives undergo a comprehensive assessment of such risk facets as technical, operability, producibility, supportability, cost, benefit, schedule, management, funding, stakeholder, information security, human factors, and others as needed. The results of investment analysis are recorded in the investment analysis report, which contains comprehensive, quantitative data developed equally for each candidate solution.

Figure 2-4.3: Investment analysis involves trade-off among factors such as cost, schedule,

risk, and performance.

- Assess affordability. Affordability assessments actually begin in mission analysis with the development of a rough estimate of likely lifecycle cost, which is recorded in the mission need statement and placed in long-range agency planning documents upon approval of mission need by the Joint Resources Council. The investment analysis team develops these costs in more detail and fidelity for each candidate solution, and forwards them to the Systems Engineering / Operational Analysis Team. The SEOAT assesses the affordability of candidate solutions against each other and all other investment programs in the agency's financial baseline based on relative priority. When a candidate solution cannot be funded within agency planning and budgeting baselines, the SEOAT may propose offsets from lower priority programs. Preliminary affordability assessments by the SEOAT shape subsequent deliberations of the investment analysis team. The final affordability assessment is included in the investment analysis report.

- Develop initial lifecycle program baseline(s). The investment analysis team develops an initial lifecycle program baseline (i.e., performance, cost, schedule, benefits, and risk) for candidate solutions offering superior value and benefit to the agency and its customers. These baselines are derived from implementation strategies tailored to each specific alternative (e.g., COTS versus development, replacement versus upgrade, sole source versus competition), and are the primary basis for the initial investment decision. It is critically important for the implementation strategy to align with each proposed alternative, and for the initial baselines to be realistic and appropriately adjusted for risk. Integrated product team or management unit members of the investment analysis team lead the development of cost and schedule baselines using the FAA work breakdown structure and other applicable standards.

- Prepare for the initial investment decision. The investment analysis team records the results of the analysis in the investment analysis report, prepares briefing materials and documentation, and coordinates its findings and recommendations with all key stakeholders. The investment analysis report defines each candidate solution, and catalogs its relative strengths and weaknesses against the evaluation factors established early in investment analysis. The investment analysis report recommends an alternative for implementation based on user acceptance, satisfaction of agency requirements, and scoring against evaluation factors. It also contains the affordability assessment and initial lifecycle program baseline for recommended alternative(s), as attachments.

- Prepare action plan for final investment analysis. The investment analysis team prepares the action plan for final investment analysis. This plan defines the actions, resources, schedules, roles and responsibilities, documentation, exit criteria, and approach that will be used to mitigate risk, finalize requirements, and plan implementation and lifecycle support for the selected alternative. It includes the cost of soliciting and evaluating vendor offers for major contracts necessary to implement the proposed investment, as well as any risk-reduction effort such as modeling, analysis, simulation, or research.

2.4.1.2 Who Does It?

Investment analysis teams perform the investment analysis.

The sponsoring organization participates on the investment analysis team. Its primary responsibility is to define agency requirements and record them in the initial requirements document.

The investment analysis organization leads complex investment analyses, and is responsible for the investment analysis report. It also assists management units and integrated product teams in the conduct of less complex investment analyses, and confirms the investment analysis report is complete and consistent with agency standards. The investment analysis organization develops, sustains, and improves standard estimating tools and analytical techniques for use in all investment analyses, based on corporate history and best practices from government and industry.

Integrated product teams and management units conduct technology assessments, assist in the generation of cost and schedule estimates for alternative solutions, and work with operational team members to determine what performance and supportability can be achieved within these estimates. They may also conduct investment analysis for smaller needs and baseline changes, as directed by the Acquisition Executive, using standard agency investment analysis tools and techniques.

The SEOAT assesses affordability and identifies candidate offsets from lower priority programs when necessary.

Customers, users, unions, and stakeholders participate as team members throughout investment analysis, providing their perspective and endorsing the recommended solution(s).

2.4.1.3 Outputs / Products

The principal output of initial investment analysis is information and data that enables the Joint Resources Council to allocate agency resources to those investment opportunities offering greatest value and benefit to the agency and its customers with the least acceptable risk. A second output is the action plan for final investment analysis. The following are required products of initial investment analysis that enable and record these primary outputs:

- Initial investment analysis report, including the affordability assessment.

- Initial lifecycle program baseline for the most viable alternative(s).

- Updated initial requirements document.

- Action plan for final investment analysis.

# 2.4.1.4 Who Approves?

The Director, Investment Analysis staff, approves the initial investment analysis report and certifies that methodology and results are consistent with agency standards. The Associate Administrator of the sponsoring organization approves the updated initial requirements document. The Associate Administrator of the operating organization may implement a nonmaterial solution to mission need that emerges during investment analysis when it can be fully funded within existing approved resources. The Acquisition Executive and the Associate Administrator of the sponsoring organization approve the initial lifecycle program baseline. The Acquisition Executive approves tailoring of the investment analysis process.

# 2.4.2 Initial Investment Decision – JRC 2a

The Joint Resources Council selects the best overall solution for implementation at the initial investment decision, based on information in the investment analysis report. It makes the decision within context of all ongoing and planned agency activities associated with the proposed service or capability. The Joint Resources Council focuses on affordability of the proposed investment program, value or benefit that will accrue to the agency and its customers, risk associated with the proposed investment, and whether it is strategically aligned with agency goals and the NAS Architecture. The investment decision also defines what each organization will do to support final investment analysis. Commitments are recorded in the investment decision memorandum of record and action plan for final investment analysis. The Acquisition Execution is the chairperson of the Joint Resources Council at the initial investment decision.

2.4.2.1 Entrance Criteria

The following are required at the initial investment decision:

- Initial investment analysis report.

- Updated initial requirements document for each alternative under serious consideration.

- Initial lifecycle program baseline for each alternative under serious consideration.

- Action plan for final investment analysis.

- Acquisition strategy for each alternative under serious consideration.

2.4.2.2 Joint Resource Council Actions

The Joint Resources Council:

- Selects the alternative to be implemented or rejects the alternatives and specifies what action is needed.

- Approves an initial lifecycle program baseline for the alternative selected for implementation.

- Approves and funds the action plan for final investment analysis.

- Designates the integrated product team or management unit responsible for solution implementation.

2.4.3 Final Investment Analysis - Plan and Baseline the Investment

The Joint Resources Council approves the action plan for final investment analysis at the initial investment decision and provides resources for its execution. This plan specifies the resources (people and money), schedule, activities, and documentation for final investment analysis activity. Figure 2.4.4 identifies the principal activities of final investment analysis.

Figure 2.4.4 Principal activities of final investment analysis

2.4.3.1 What Must Be Done

- Identify key planning elements. The investment analysis team identifies all key actions and events that must be executed to obtain delivery within cost and schedule constraints and achieve projected value and benefits. Complex investment programs may require development of systems and equipment, modification or construction of facilities, additions to the physical infrastructure, development of regulations, purchase of real property, and integration with other complex activities or programs. They may also require planning and integration for a large number of functional disciplines such as systems engineering, logistics support, test and evaluation, risk management, system safety, human factors, configuration management, quality assurance, environmental factors, and security. If key planning elements are overlooked, the result will be sub-optimization of resources, cost growth, and schedule delay. Key stakeholders must be part of the planning process to ensure plans are realistic and complete. For example, if regional offices are to upgrade facilities or install new equipment, they must participate in planning so they can integrate their commitment to a specific program with the requirements of other programs and activities within their region.

- Finalize investment analysis action plan. Investment analysis team members resolve any remaining issues associated with the conduct of final investment analysis. These are recorded in the action plan for final investment analysis. Team members sign the final action plan, signifying acceptance and support by all participants and their parent organizations.

- Solicit and evaluate offers for prime contract(s). Requirements in the requirements document and work packages in the integrated program plan are allocated to various tasking and solicitation packages, as necessary to obtain the solution. Responses from offerors are used to finalize requirements, costs, schedules, and benefits in the lifecycle program baseline and tasking in the integrated program plan. Note that contract award shall not occur until AFTER the final investment decision even though offers are solicited during final investment analysis.

- Reduce risk and finalize requirements. Working with the designated integrated product team or management unit, the investment analysis team conducts a detailed risk assessment of the selected alternative to identify and plan for major risks that threaten achievement of performance, cost, schedule, and benefit objectives. This includes detailed assessments of safety, security, and human factors. Resultant risk mitigation strategies and necessary resources are recorded in the final lifecycle program baseline and integrated program plan. Risk mitigation actions are monitored and updated throughout solution implementation.

- Finalize strategy for implementation and lifecycle support. The integrated product team or management unit conducts a strategic assessment of the proposed investment program to identify key assumptions, constraints, interrelationships, actions, and events that must occur for successful implementation and realization of projected value and benefits. It then develops a detailed implementation strategy, which defines how the solution will be obtained and supported over its lifecycle. It also identifies responsible individuals and organizations and defines their roles and responsibilities. The implementation strategy is recorded in the acquisition strategy paper.

- Develop detailed program plan. The actions and activities necessary to implement the program and realize benefits are recorded in the integrated program plan. The integrated program plan is developed using the program work breakdown structure, which in turn is traceable to the standard FAA work breakdown structure. The integrated program plan must be as complete and mature as possible at the time of the final investment decision since the quality of the investment decision and the success of the program is crucially dependent on the adequacy of program planning. To accommodate any residual uncertainty, both the final lifecycle program baseline and integrated program plan are revalidated, and updated if necessary, after contract award to ensure they can continue to serve as the fundamental management constructs for program implementation. Screening information requests can and should be released and industry responses evaluated before final approval of the plan to ensure it reflects realistic program costs and schedules.

- Finalize the lifecycle program baseline. The investment analysis team develops the final lifecycle program baseline, which establishes parameters for cost, schedule, performance, and benefit within which the implementing organization is authorized to perform and against which the program is tracked. The cost baseline must embody all lifecycle costs, including resources for acquisition, deployment and commissioning, maintenance and repair, and lifecycle support. It also includes funding for removal and disposal of any assets being replaced by the program and restoration of vacated sites.  The cost baseline also includes the cost of pre-planned product improvements, technology refreshment, telecommunications, buildings / power, and other costs that are part of the overall lifecycle management strategy. The SEOAT assesses the affordability of the cost baseline and reports results in the final investment analysis report.

- Prepare for the final investment decision. The investment analysis team records the results of final investment analysis in the investment analysis report, prepares briefing materials and documentation, and coordinates findings and recommendations with all key stakeholders. The investment analysis report contains the affordability assessment of the SEOAT and the lifecycle program baseline for the selected alternative, as attachments.

2.4.3.2 Who Does It?

The investment analysis team plans and conducts final investment analysis, coordinates development of planning documents and the lifecycle program baseline, prepares the final investment analysis report and briefing materials, and briefs key stakeholders and Joint Resource Council members in preparation for the final investment decision.

The integrated product team or management unit participates on the investment analysis team, develops the acquisition strategy paper and integrated program plan, issues solicitation packages and evaluates responses, and conducts whatever analyses, research, modeling, or simulation is necessary to lower risk and finalize requirements. The sponsoring organization works with and assists the investment analysis team in all aspects of final investment analysis. It also completes the final requirements document and revalidates the mission need statement.

The investment analysis organization leads complex, high-value investment analyses and supports integrated product teams and management units in the conduct of any smaller, low-risk analyses directed by the Joint Resources Council or Acquisition Executive. The investment analysis organization also develops and sustains standard investment analysis tools and techniques.

Key stakeholders work on and assist the investment analysis team in all aspects of final investment analysis, particularly risk management and human factors. They also commit formally in the final investment analysis decision record and acquisition strategy paper what each will do to support the investment program throughout solution implementation and in-service management to achieve the value and benefits projected in the lifecycle program baseline.

The SEOAT performs the final affordability assessment.

2.4.3.3 Outputs / Products

The principle output of final investment analysis is detailed program planning for the alternative selected for implementation and a final lifecycle program baseline for variance tracking. Also critical are the agreements documented in the final investment analysis decision record and acquisition strategy paper concerning what each key stakeholder organization will do to realize value and benefits projected for the investment program. The following required products contribute to and record these outputs:

- Final requirements document.

- Revalidated mission need statement

- Final lifecycle program baseline

- Final acquisition strategy paper.

- Integrated program plan (including risk management planning).

- Screening information request(s) for prime contract(s).

- Final investment analysis report.

- Tailored ISR Checklist.

2.4.3.4 Who Approves?

The Director, Investment Analysis staff, approves the final investment analysis report and certifies that methodology and results are consistent with agency standards. The Associate Administrator of the sponsoring organization approves the final requirements document and revalidates the mission need statement. As applicable, the Strategic Support Group, Integrated Management Team, or equivalent Directors of the operating and performing organizations approve the acquisition strategy paper and integrated program plan. The Acquisition Executive and the Associate Administrator of the sponsoring organization approve the final lifecycle program baseline.

# 2.4.4 Final Investment Decision – JRC 2b

The final investment decision determines whether a program is approved for implementation based on cost, risk, alignment with the NAS Architecture, affordability, and value / benefit to the agency and aviation community. It also defines what each organization will do to implement the solution and achieve the value and benefits projected in the lifecycle program baseline. Decisions are recorded in the final investment decision of record. Organizational responsibilities are recorded in the acquisition strategy paper and tracked at all future program reviews. The Acquisition Execution is the chairperson of the Joint Resources Council chairperson at the final investment decision.

# 2.4.4.1 Entrance Criteria

The following are required at the final investment decision:

- Final requirements document.

- Final investment analysis report.

- Final lifecycle program baseline.

- Final Acquisition strategy paper.

- Integrated program plan

2.4.4.2 Joint Resources Council Actions

The Joint Resources Council approves, disapproves, or modifies the recommendations in the investment analysis package. If the Joint Resources Council disapproves the recommendations, it returns the investment package with specific instructions for further work or terminates the effort. If the Joint Resources Council accepts the investment analysis recommendations, it:

- Approves the investment program for implementation and verifies delegation to the appropriate integrated product team or management unit.

- Approves the lifecycle program baseline for program execution and variance tracking.

- Commits the agency to full lifecycle funding, as specified in the lifecycle program baseline.

- Ratifies and baselines the requirements document.

- Identifies future corporate decisions and levels of delegation.

- Approves adjustments to agency plans and budgets to reflect the investment decision.

- Designates the in-service decision authority.

- Ratifies the acquisition strategy paper and integrated program plan.

(add the following definition to Appendix C)

Management Units. Management units are accountable and responsible for delivering assigned services, as specified by and within the resources provided by the Joint Resources Council. Management units range from business units delivering service to a physical domain such as the terminal area, to product teams responsible for specific systems or facilities, to organizational units providing administrative, management, or technical support. Management units may deliver services directly to a customer, such as flight planning for general aviation, or to other management units that deliver end services to a customer, for example, telecommunications or power generators. Together, management units span the spectrum of agency activity and responsibility.

# Text boxes

Plan the entire solution, not just part of it

Refer to Appendix B for planning document details