DRAFT

VERSION 0.1

April 10, 1998

ATS Requirements Development and Investment Analysis

Standard Operating Procedures

| REVISION | DATE | DESCRIPTION |
| --- | --- | --- |
| Version 0.1 | 04/10/98 | Baseline document, for internal ARS review. |

PREFACE

The ATS Requirements Development and Investment Analysis Standard Operating Procedures (SOP) were developed to provide consistency in executing ATS Investment Analysis. These procedures, developed from interviews with subject matter experts throughout the FAA, represent the foundation for the methodologies and competencies required to develop program requirements and conduct investment analyses.  Several components of these SOPs are untried and will be improved based upon the experiences and feedback of the ARS Requirements Development Directorate (ARR) specialists and customers. Although these SOPs represent a significant step forward in conducting sound Investment Analysis, they are only the first of several iterations of the ATS Requirements Development and Investment Analysis process.  The success of the ATS Requirements Development and Investment Analysis is dependent on the people, processes and information resources used to accomplish its goals and objectives.

ARR-100 (Requirements Development and Investment Analysis Division) specialists play a critical role in executing and refining the ATS Investment Analysis process.  These specialists are accountable for understanding the methodologies, assumptions, data sources and conclusions of the analyses.  They are expected to brief senior FAA executive decision-makers on their conclusions about specific investment analysis outcomes, requirements trade-offs and potential offsets in ATS priorities.  In addition, specialists are expected to provide feedback to their management on the effectiveness of specific activities in order to continue to improve the effectiveness and efficiency of the ATS Requirements Development and Investment Analysis process.

Developing partnerships with the operating organizations, Air Traffic Service (AAT) and Airway Facilities Services (AAF), is as important as any of ARR’s internal initiatives.  The participation of ATS functional organizations and their commitment to the ATS requirements management process are essential to the Investment Analysis process.  ARR specialists and their Integrated Requirement Team (IRT) members must develop a common understanding of both technical and programmatic issues associated with requirements development and investment analysis.  This is necessary for the specialist to manage meaningful analysis and to be an effective advocate for the operating organizations.

Although these SOPs comply with the FAA Acquisition Management System, several concepts in this first version require further analysis and clarification.

Investment Analysis will be measured and improved through employee involvement, customer feedback and the analysis of process metrics.  These SOPs will be revised to incorporate lessons learned from those who use, execute, and manage the ATS Requirements Development and    Investment Analysis process.

We welcome your comments.

TABLE OF CONTENTS

1. 	ATS REQUIREMENTS MANAGEMENT DURING INVESTMENT ANALYSIS

1.1	PURPOSE ........................................................................................................

1.2	BACKGROUND ................................................................................................

1.3	PROCESS OVERVIEW.....................................................................................

2. 	PROCESS DESCRIPTIONS .............................................................................

2.1	PREPARE INITIAL RQUIREMENT DOCUMENT .............................................

2.2	SUPPORT IDENTIFICATION OF ALTERNATIVES .........................................

2.3	SUPPORT ANALYSIS OF ALTERNATIVES ....................................................	27

2.4	OBTAIN INVESTMENT DETERMINATION ......................................................	34

2.5	ASSESS REQUIREMENT TRADE-OFFS ........................................................	44

2.6	RESOLVE ATS REQUIREMENT ISSUES .......................................................	47

2.7	TRACE ATS REQUIREMENTS ........................................................................	53

# ATS REQUIREMENTS MANAGEMENT DURING INVESTMENT ANALYSIS

## PURPOSE

The purpose of this document is to describe the specific processes, activities and steps involved in accomplishing the ATS Requirements Management function and other related ATS responsibilities during investment analysis.

## BACKGROUND

The Air Traffic System Requirements Service (ARS) is a consolidated customer and user focused organization that develops comprehensive National Airspace System (NAS) requirements and manages a disciplined process to fulfill the operational needs of Air Traffic Services (ATS).  This process supports both the strategic and tactical needs of ATS.  ARS accomplishes its mission by collecting, validating, translating and advocating requirements that ensure operationally effective solutions.

ARS executes the ATS Requirements Management function with the following principles as guidelines:

- Focus on Customers and Users

The external input from the operational environment is a key input to the activities and decisions made by ARS personnel.  ARS personnel act as the advocate for customers and users.  In this role, they ensure the integrity of requirements throughout the acquisition process and work to optimize the solution in light of budgetary and schedule constraints

- Foster Open Communications

Open and honest communications are the key to a successful acquisition process.  ARS personnel will maintain open communications with team members, including union and field personnel, in order to develop a common understanding about technical issues and program status.

- Promote and Obtain Customer and User Input throughout the Process

ARS personnel will actively involve representatives from ATS functional organizations at critical review and decision points throughout the requirements and acquisition process to ensure that operational scenarios have been considered and to facilitate acceptance of deployed products.  The forum for involving stakeholders in investment analysis is the Integrated Requirements Team (IRT) which includes representatives from ATS functional organizations.

- Promote Effective and Efficient Operating Procedures

ARS representatives will actively define and critique work processes as a means of improving the effectiveness and efficiency of their activities.  Activities and accomplishments of the ARS personnel will be reviewed against specific process metrics in order to highlight process areas requiring improvement.

- Solicit Customer and User Feedback

Feedback regarding the success of ARS activities, from the perspective of the operational customer and user, will be actively solicited and used as a key input to the definition and refinement of work activities.  The feedback mechanisms developed by ARS-l will include a “report card” concept so that customers and users receive information on the status of their comments and recommendations.

## PROCESS OVERVIEW

The FAA Acquisition Management System (AMS) identifies three phases in acquisition management.  ATS requirements management during the first phase, Mission Needs Analysis, is led by the Plans and Performance Directorate (ARX).  During the Investment Analysis phase, the ATS requirements management function is led by the Requirements Development and Investment Analysis Division (ARR-100).  During Solution Implementation, leadership of the ATS requirements management function is provided by either ARN, ARU, or ARW.

During Investment Analysis, ARR-100:

- Manages the development of the Requirements Document (RD) by “harvesting” high level requirements from the ATS functional organizations through members of the IRT.  The RD evolves from a set of high level initial requirements as the basis for identifying candidate solutions to a final RD with a more comprehensive set of requirements which enable cost analysis within 10% of actual cost.

- Assigns personnel to participate on Investment Analysis Teams (IAT).  IATs are normally established by Office of System Architecture and Investment Analysis (ASD).

- Coordinates ATS participation on the IAT by identifying ATS subject matter experts (SMEs) relevant to the mission need under analysis and coordinating SME assignments with ATS functional organizations.

- Coordinates with ARR-200 (Financial Services Division) to complete affordability assessments of candidate solutions.

- Coordinates analysis of requirement trade-offs based on technical, schedule and cost analyses performed during assessment of alternative solutions.

- Traces the ATS requirements throughout the investment analysis phase.

- Manages the resolution of ATS requirements issues which arise during the investment analysis phase.

- Performs quality control over the RDs and the performance section of the Acquisition Program Baselines.

The objectives of the ATS Requirements Management function during the Investment Analysis phase of the acquisition process are:

- To ensure ATS requirements are comprehensive and realistic/reasonable

- To support ASD in the conduct of market analysis, and identification and analysis of candidate solutions to meet requirements represented in the RD

- To ensure that the recommended solution will meet ATS requirements

- To support resolution of ATS requirements issues

The activities conducted as part of ATS requirements management during Investment Analysis are highly interdependent.  ATS Requirements management during investment analysis involves the following sub-processes to achieve defined objectives:

- Prepare initial RD

- Support identification of alternatives

- Support analysis of alternatives

- Obtain investment determination

- Assess requirement trade-offs

- Resolve ATS requirement issues

- Trace ATS requirements

A summary of each of the ATS Investment Analysis sub-processes is provided in the paragraphs below.

1.3.1	Prepare Initial Requirements Document

Process Lead: ARR

Following the JRC mission need determination, the sponsoring line of business for the approved mission need is responsible for establishing initial requirements.  Within ATS, the requirements management responsibility is transferred from ARX to ARR, who will develop initial requirements with support from other ATS functional organizations, Integrated Product Teams (IPTs), and other organizations, as required.  ARR provides the ATS expertise to support sponsor organizations in the development of the initial RD.

The initial RD contains high level requirements and constraints which permit the conduct of market surveys and identification of candidate alternative solutions.  It establishes the criteria for identifying potential solutions, conducting market analyses, analyzing alternatives, and performing affordability assessments.  The initial RD addresses operational concept, physical integration, functional integration, in-service support, test and evaluation, implementation, quality assurance, configuration, human factors, and in-service management requirements. It also identifies Critical Operational Issues that potential solutions must address and resolve to ensure the operational capability specified in the Mission Need Statement is fully satisfied.  The initial RD must also record Congressional mandates, Executive Orders, and federal regulations that directly influence the requirement.

In order to accelerate the investment analysis process, ARR should begin development of the initial RD when a Mission Need Statement has been submitted for ATS review.  In preparing the initial RD, the ATS Integrated Requirement Team (IRT) is reconvened with ARR-100 as the IRT Lead.  The ARR representative serves as the IRT Lead throughout the Investment Analysis Phase.  The IRT completes an IRT Plan, analyzes the approved Mission Need Statement (MNS), and translates the MNS into an initial and final requirements documents.  These documents (IRD/FRD) are the products of the IRT during the Investment Analysis Phase.

Requirements incorporated in the initial RD are maintained in an ATS requirements database which traces each requirement to a “parent” need statement in the MNS.  (See Trace ATS Requirements sub-process).  The members of the IRT achieve consensus on the content of the IRD and document that consensus by signing a consensus agreement.  The initial RD is reviewed throughout ATS and other program stakeholders and submitted for approval to ARS-1.  It is then provided to ASD for use by the Investment Analysis Team (IAT) to identify candidate solutions through market analysis.  When the IRD is provided to ASD, it is also provided to the Radio Technical Commission for Aeronautics, Inc. (RTCA), who will coordinate industry review.

1.3.2	Support Identification of Alternatives

Process Lead: ASD

The IAT established by ASD identifies candidate solutions to meet requirements documented in the initial RD.  ARR coordinates with ASD to assure that there is appropriate representation of ATS functional organizations on the IAT and to coordinate assignment of SMEs to the team.  ASD prepares an Investment Analysis Plan (IAP) which defines the team composition, roles of team members, schedule and resource requirements for the alternatives analysis process.

The requirements contained in the initial RD are the basis for identifying all potential material and nonmaterial solutions to the mission need, using market surveys as well as input from industry and FAA organizations that have potential solutions ( e.g., IPTs, System Architecture and Investment Analysis organization, regulatory offices, research organizations, etc.).  The preference is to identify commercial-of-the-shelf, non-developmental items (COTS/NDI), or nonmaterial solutions that are cost-effective and operationally suitable as a first priority for satisfying the mission need and requirements.  Developmental alternatives should be considered only if other choices are not feasible.  Operational or factory capability demonstration of potential solutions is encouraged.

The IAT prepares life-cycle cost (LCC) rough order of magnitude (ROM) estimates for each candidate alternative and coordinates, through ARR-200, the identification of budget place-holders based on those estimates.  When candidate solutions have been identified, ARR-100 assesses whether solutions conform to the requirements identified in the initial RD.  If not all requirements can be met by candidate alternatives, the Assess Requirement Trade-Offs sub-process is engaged.  When a set of alternatives that can meet the initial requirements is identified, the analysis of alternatives begins.  If a viable non-material solution is identified, it may be implemented without proceeding further.

1.3.3	Support Analysis of Alternatives

Process Lead: ASD

The IAT, led by ASD, is responsible for performing analysis of candidate alternatives.  ARR and the IRT provide primary support to this process by further populating the RD template.  The RD template is populated to a level to support life-cycle cost estimation.  Each solution alternative is analyzed in relation to RD requirement domains.  Cost and feasibility assessments are performed by the IAT.  If identified alternatives cannot meet ATS specified requirements and thresholds defined in the initial RD, ARR initiates the Assess Requirement Trade-Offs sub-process to determine if modifications can be made to requirements while still meeting the mission need.  Considering the ATS priorities and budget baselines, ARR-100 and ARR-200 perform ATS affordability assessments for each alternative and determine what offsets in other ATS programs may be required to fund the program.  The results of the ATS affordability assessment are provided to the System Engineering Operational Analysis Team (SEOAT) for assessment of affordability in relation to agency-wide planning horizons.  If the SEOAT determines that one or more solutions are affordable, the IAT proceeds to the Obtain Investment Determination sub-process.

1.3.4	Obtain Investment Determination

Process Lead: ASD

From the affordable alternative solutions identified by the SEOAT, the IAT selects an alternative to be recommended to the Joint Resource Council (JRC).  Based on this decision, the IRT prepares the final RD for the alternative to be recommended to the JRC.  When IRT members reach consensus on the content of the final RD,  they document that consensus by signing a consensus agreement.  When the final RD has been signed off by IRT members, it is receives a quality assurance review within ARR prior to being coordinated within ARS.  When approved by ARS-1 it is distributed to ATS Service directors (AAT-1, AAF-1, ATQ-1) and the unions.  The IAT proceeds to develop the Investment Analysis Report by developing a Acquisition Program Baseline (APB) for each alternative.  The Investment Analysis Report (IAR) is coordinated by ASD and when approved, is provided to the JRC for consideration.  If the JRC selects and approves investment in one of the solution options, the APB for that option is provided to an IPT for implementation of the solution.  The RD for the selected option is used to update the ATS requirements database.

1.3.5	 Assess Requirement Trade-Offs

Process Lead:  ARR

After issuance of the initial RD and throughout the subsequent Investment Analysis activities, it may become apparent that available solutions cannot meet the entirety of requirements as documented in the RD.  When such a determination is made, ARR convenes the IRT to identify possible requirement trade-offs so that a viable solution can be selected.  When trade-offs are identified, ARR assures that the RD template(s) are revised and that the changes are traced in the requirements tracking database.  Life-cycle cost estimates for affected requirements elements are adjusted to reflect requirement changes.

1.3.6	Resolve ATS Requirement Issues

Process Lead: ARR

At any point during mission analysis, investment analysis and solution implementation, issues may arise regarding ATS requirements.  Issues may be internal to ATS in the form of conflicts or incompatibility of requirements submitted by ATS functional organizations.  Issues may arise due to the cost, schedule or technical feasibility of meeting the requirement.  The IRT Lead is responsible for documenting ATS requirement issues.  Information about the issue is distributed to IRT members and a meeting of the IRT is convened to establish the ATS position relative to the issue.

If the issue is internal to ATS, the IRT Lead coordinates resolution with the appropriate ATS functional organizations.  If the issue requires resolution of differences between ATS and the IAT, the IRT Lead coordinates resolution with the IAT.  If an issue cannot be resolved at the IAT level, the IRT Lead coordinates resolution of the issue through his/her management, documents the decisions, and verifies accomplishment of the resolution.

1.3.7	Trace ATS Requirements

Process Lead: ARR

As requirements are identified, modified, and the RD template is completely populated, it is the responsibility of the ARR Lead for the Investment Analysis to “track” requirement changes.  The ARR Lead assures that ATS requirements are documented and traced to the “parent” MNS.  Deleted requirements are documented and “warehoused.”  Part of the Trace ATS Requirements sub-process involves documenting ATS requirements in accordance with ARS standards.  Once provided to ASD, all ATS requirement statements (both original, derived and/or modified), along with their origin and rationale are added to the ATS requirements database and related to their parent requirement(s).  At the completion of the Investment Analysis phase, the requirement database is handed off to ARU/N/W for maintenance during the Solution Implementation phase.

# PROCESS DESCRIPTIONS

## PREPARE INITIAL RQUIREMENTS DOCUMENT

Investment analysis begins with the translation of broad statements of mission need into initial requirements.  All requirements in the initial RD originate and are coordinated within the ATS organization.  The initial requirements undergo detailed market, investment, and affordability analysis.  Statements in the MNS concerning urgency and criticality of the need determine when the investment analysis must be completed.

The sub-processes involved in preparation of the initial RD:

- Transition from Mission Need Analysis

- Prepare Initial RD

- Coordinate Initial RD

Figure 2.1-1

Preparation of Initial Requirements Document

2.1.1	Transition from Mission Need Analysis

| Description | This sub-process involves the start-up and hand-off activities required to transfer ATS Requirements Management leadership from ARX to ARR. The Mission Need Analysis phase precedes Investment Analysis and culminates in a corporate Mission Need Determination by the Joint Resource Council (JRC). The ATS Lead during Mission Need Analysis is a member of the ARX organization. The product of the Mission Need Analysis phase is the Mission Need Statement (MNS). When the JRC makes a Mission Need Determination, the AMS process moves to the Investment Analysis phase and ATS Requirements Management leadership responsibility is transferred to ARR. |  |
| --- | --- | --- |

| Activity #1 | Pre-transition Actions |  |
| --- | --- | --- |
| Purpose | Whenever possible, the ARR-100 specialist(s) participating in the Mission Analysis activities should prepare in advance for the ARR-100 initial requirements development activities. During the final stages of Mission Analysis, ARR-100 may begin some tasks that will result in an expeditious Investment Analysis phase. |  |
| Step #1 | Based on the subject MNS, the ARR-100 specialist reviews the RD template and determines an initial format for the IRD. Review RD template and determine IRD format |  |
| Step #2 | Using the initial format for the IRD and knowledge of functional organizations, devise a tentative plan for subject/topic area assignments. Determine subject/topic area assignments |  |
| Step #3 | Prepare drafts of the Customer Contract and the IRT plan. The Customer Contract documents the scope of the effort and the expected milestones. The IRT Plan defines the particulars on how the IRT intends to complete the expected milestones. Prepare a draft Customer Contract and a draft IRT Plan |  |

| Activity #2 | Transfer Project Case File Data from ARX to ARR |  |
| --- | --- | --- |
| Purpose | An ATS Case File, which was initiated in the Mission Analysis phase is maintained by the assigned ARS Mission Analysis lead. This activity describes the steps involved in transferring the Case File and status information from ARX to the assigned ARR Specialist. |  |
| Step #1 | The ARX-200 representative, acting as IRT lead during the Mission Analysis phase, will schedule a meeting of the IRT to review the contents of the MNS file, to provide a sense of agency or program direction in terms of the purpose and scope of the mission need, to describe the technical, financial, or political implications of the MNS and identify and discuss key issues (schedule, etc.) for the Investment Analysis Phase. Obtain debriefing from ARX Lead for ATS Mission Need Analysis |  |
| Step #2 | Part of the transfer of ATS requirements management from ARX to ARR involves transfer of database management responsibility, paperwork and completion of reports. Support Mission Need Analysis Close-out activities |  |
| Step #3 | The ATS Project Case File is physically transferred from the ARX representative to the newly assigned ARR representative. Obtain ATS Project Case File |  |
| Step #4 | The IRT leadership responsibility, along with IRT meeting records, membership lists and scheduling information is transferred from ARX representative to the assigned ARR representative. Transfer IRT Leadership to ARR Requirement Lead |  |

| Activity #3 | Reconvene/Convene the IRT |  |
| --- | --- | --- |
| Purpose | Provide stake holding organizations an opportunity to participate in the development of requirements to the mission need, and discuss responsibilities and commitments needed to perform activities throughout the Investment Analysis phase. |  |
| Step #1 | Request that all interested organizations in AAF, AAT, ATQ, ARS, and ASC, including the unions, provide a point of contact and/or an active participants in the IRT. Although an IRT may have existed during the mission analysis phase, this step provides all organizations an opportunity to participate in the investment analysis phase. It will also reaffirm or substitute the current membership for the Investment Analysis Phase and provide the IRT with a point of contact in all ATS organizations for resolution of issues that may arise during the development of requirements. Request ATS participation |  |
| Step #2 | The IRT reviews the approved MNS and determines which functional organizations within ATS are primary stakeholders for the solution to the need. If key stakeholder organizations are not currently members of the IRT, the membership should be augmented. Likewise, if there are current IRT representatives from organizations with limited stake in the solution, then those members may wish to adjust their level of participation on the IRT. Identify team member adjustments required |  |
| Step #3 | The IRT, reviews the MNS and identifies specific subject matter expertise which will be required to assist and/or provide input and review to the IRD development. Identify SME requirements |  |

| Activity #3 | Adjust IRT Membership |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to assure that appropriate representation from ATS functional organizations on the IRT. |  |
| Step #1 | Each IRT member serves as OPI for one or more of the IRD Sections and Appendices identified in the template for Requirement Documents. A specific IRT member is identified as having primary responsibility for the planning, development, and validation of the assigned Sections and Appendices . Confirm OPI assignments |  |
| Step # 2 | The IRT membership during Mission Analysis may not have included organizational representation from all the ATS functional organizations identified as OPIs for subject/topic areas. Discrepancies in membership and OPI responsibilities are identified and the IRT Lead contacts the managers of OPI organizations not yet represented on the IRT to obtain an IRT member from that organization. Obtain assignment of IRT members from OPI organization(s) not yet members of IRT |  |
| Step #3 | SMEs from non-ATS organizations will supplement the teams, as appropriate, to provide additional insight/support. Organizations providing SMEs may include Integrated Product Teams (IPTs), the FAA Logistics Center, ATC facilities, Systems Management Offices (SMOs), Investment Analysis Staff (ASD-400), or others as appropriate. The IRT Lead coordinates with non-ATS functional organizations to identify and obtain assignment of personnel with the subject matter expertise the IRT has identified . Obtain assignment of SMEs |  |

| Activity #4 | Prepare/Revise Customer Contract and IRT Plan |  |
| --- | --- | --- |
| Purpose | The Customer Contract should clarify and document scope and objectives of the effort, the expected milestones, and the organizational responsibilities. The IRT Plan defines the particulars on how the IRT intends to meet the objectives listed in the Customer Contract and develop the IRD/FRD. The plan should list the IRT membership, the activities that each member is responsible for, and the expected completion dates. |  |
| Step #1 | Statements in the Mission Need Statement concerning time-frame and urgency establish when a solution to a mission need must be in place. Using this information, and additional input from the sponsor, ARR establishes a boundary on when investment analysis must be completed. Establish schedule boundaries |  |
| Step #2 | The IRT lead drafts a Customer Contract and IRT plan. The IRT Plan includes a synopsis of the shortfalls/opportunities prompting the IRT activities, documents the team objectives, membership, roles and responsibilities, products (RDs), resources and schedule for accomplishing IRT activities during Investment Analysis. Draft Customer Contract and IRT Team Plan |  |
| Step #3 | The IRT Lead distributes the draft IRT Plan and Customer Contract to IRT members for review. Obtain IRT member review of draft IRT plan and Customer Contract |  |
| Step #4 | Use the IRT feedback on the plan to finish the Customer Contract. Review the document with the sponsor(s) and sign. Finalize and sign Customer Contract |  |
| Step #5 | The IRT Lead receives comments from IRT members on the draft Team Plan, adjudicates those comments and makes appropriate revisions to produce a final Team Plan. Obtain IRT sign-off on IRT Plan |  |
| Step #6 | The IRT schedule and OPI assignments of IRT members, based on the final IRT Team Plan is shared with the managers of ATS functional organizations so that IRT member workload can be reflected within the functional organizations’ planning. Distribute the team plan, under ARR-100 signature, to managers of functional organizations represented on the IRT |  |

2.1.2	Prepare Initial RD

| Description | Capability shortfalls or technological opportunities identified in the MNS are translated into requirements along with the functional requirements in (or derived from) the NAS Architecture (the Service Model) The initial RD is derived from the Mission Need Statement and contains initial requirements addressing operational concept, schedule, performance, benefits, physical integration, functional in-service support, test and evaluation, implementation, quality assurance, configuration, human factors, and in-service management. Care must be taken so that leasing, commercial, or non-developmental items are not precluded as potential solutions. During investment analysis, these initial requirements are evaluated against the costs, benefits, schedules, and risks of various candidate solutions, and brought into balance with an affordable solution, whenever possible. |  |
| --- | --- | --- |

| Activity #1 | Identify AMS Requirement Categories |  |
| --- | --- | --- |
| Purpose | Capability shortfalls or technological opportunities identified in the MNS are translated into requirements along with the functional requirements in (or derived from) the NAS Architecture (the Service Model) to develop an initial RD defining top-level, mission-critical requirements that the acquisition community must provide to the user community. |  |
| Step #1 | Once the IRT is reconvened, they should review the document to obtain familiarity with the mission need. Each IRT member needs to review the MNS and his/her the RD Template assignments to ensure they have the information and/or coordination points identified to enable them to complete their RD development assignment and on schedule. Analyze MNS, RD Template and IRT plan |  |
| Step #2 | The IRT validates which of the requirement RD template Chapters and Appendices are applicable based on analysis of the MNS. The IRT coordinates with IRT members to ensure coordination with appropriate organizations will be accomplished and by whom. Care will be taken to minimize duplication of effort or coordination. Translate MNS needs into requirements in the appropriate Chapters and Appendices defined in RD template |  |

| Activity #2 | Obtain Requirement Inputs from Functional Organizations |  |
| --- | --- | --- |
| Purpose | The ATS functional organizations are the primary source of ATS requirements. The purpose of this activity is to solicit requirements data from them for inclusion in the initial RD. |  |
| Step #1 | IRT members, based on OPI assignments established in the IRT Team Plan, establish mechanisms for obtaining organizational inputs. They solicit requirements and data inputs from the functional organizations with functions related to the MNS and incorporate into the appropriate assigned RD Chapter/Appendix. Solicit inputs from functional organizations |  |
| Step #2 | A rationale that supports the need for each requirement must be prepared. Information in the rationale will be useful when developing low-level requirements later in the process. Functional organizations are key providers in developing requirements rational and to identify validation criteria for the requirement. Obtain rationales for requirements |  |

| Activity #3 | Validate Requirements |  |
| --- | --- | --- |
| Purpose | All requirements derived from the MNS must be verifiable and able to be validated. Information obtained during this process should then be catalogued for future reference. |  |
| Step #1 | Requirement inputs gathered by IRT members are consolidated by the IRT Lead and distributed to the IRT membership for review. The IRT lead will coordinate the consolidation of IRT members development data into an initial draft RD for review. Consolidate candidate requirements |  |
| Step #2 | The IRT meets to review the draft RD The IRT resolves conflicts, gaps and overlaps in the draft and develops changes as necessary to successfully complete their assigned area of the RD. This is an iterative process until the IRT agrees they have a document ready for organizational review. a comprehensive set of requirement statements which address the contents specified in the initial RD template. Prepare integrated set of initial RD requirements |  |
| Step #3 | The IRT performs quality control assessments of the IRTs initial RD requirements to assure that statements are clear and concise. Resolution of the format of statements is coordinated through the IRT Lead. Verify requirement statement format |  |

| Activity #4 | Consolidate Requirements in RD Template |  |
| --- | --- | --- |
| Purpose | The AMS provides a specific template for the RD to assure that all the necessary information to proceed to alternatives identification and analysis is documented. |  |
| Step #1 | The IRT uses the IRT’s consolidated set of initial requirements and other information to populate the RD template. Prepare draft of initial RD |  |
| Step #2 | The IRT performs an internal review of the draft initial RD for conformance to AMS templates and division format. Conduct internal ARR review |  |

| Activity #5 | Obtain IRT Consensus |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to obtain Team consensus. Issues preventing consensus should documented and elevated to the appropriate level of management for resolution. |  |
| Step #1 | When all issues have been resolved and the team has indicated consensus, document team concurrence using the Consensus Agreement Form (Appendix TBD). Obtain consensus agreement |  |

- Coordinate Initial RD

| Description | The initial RD is the basis for the identification of potential solutions and must accurately represent the ATS functional organization’s high level requirements to meet theestablished mission need. The document must be reviewed by ARS and other ATS organizations to ensure the initial RD includes the requirements from all stakeholders. |  |
| --- | --- | --- |

| Activity #1 | Obtain Internal ARS Concurrence |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to reach internal ARS concurrence on the initial RD. |  |
| Step # 1 | IRT lead briefARR-100 & 200 on the initial RD and provides a copy of the initial RD to ARR-100 management for final review. Review by ARR-100 management and ARR-200. |  |
| Step #2 | IRT lead prepares a separate Clearance Record Form (1300-2) for each ARS director (ARN/U/W/X-1). A copy of the IRD and the signed consensus agreement are attached. Distribute review package to obtain comments/concurrence from internal ARS |  |
| Step #3 | If full concurrence does not occur, resolve the non-concurs. If necessary, meet with IRT to review changes. Resolve ARS non-concurs |  |

| Activity #2 | Obtain ATS/Stakeholder Concurrence |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to reach concurrence from those FAA organizations having an interest in the program. |  |
| Step #1 | IRT lead prepares a separate Clearance Record Form (1300-2) for each for each AAT director (ATO/X/A/Q-1); AAF director (AOS/ANS/AOP/ASR/ANI-1); ASC-1,and ATQ-1. In addition, IRT lead prepares a letter requesting comments from the ATS Unions (PASS, NAATS, NATCA);, and any other relevant stake holders on non-ATS organizations. Copies of the IRD and the signed consensus agreement are attached. Distribute review package to obtain comments/concurrence from Stakeholders |  |
| Step #2 | If full concurrence does not occur, resolve the non-concurs. If necessary, meet with IRT to review changes. Resolve ARS non-concurs |  |

| Activity #3 | Transmit IRD for ARS-1 Signature |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to prepare the initial RD containing internal ARS and stakeholder comments/concurrence for approval. |  |
| Step #1 | A copy of the clearance records, the initial RD, and a the consensus agreement are packaged for ARS-1 signature. IRT lead prepares a transmittal letter from ARR-100, through ARR-1, to ARS-1. Generate and transmit ARS-1 signature package |  |

| Activity #4 | Transmit IRD for Industry Review |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to obtain industry feedback on FAA requirements, to ensure that the final requirements document (FRD) incorporates industry’s comments and suggestions. |  |
| Step #1 | The IRT lead will prepare a letter, for ARS-1 signature, to the Radio Technical Commission for Aeronautics, Inc. (RTCA) and to any other relevant industry association. Attached will be a copy of the signed IRD. Transmit IRD for industry review Note: The IRT should exercise caution in that it should not make public any sensitive information that may compromise future procurement activities or the security of FAA’s infrastructure. |  |

- Solicit Customer Feedback

| Description | After the approval of the IRD, ARR-100 will solicit written feedback from the IRT membership organizations and program stakeholders. |  |
| --- | --- | --- |

Note: We are currently developing a customer feedback form. Specific guidance TBD.

## SUPPORT IDENTIFICATION OF ALTERNATIVES

In initiating the investment analysis process for a new MNS, ASD assembles a team to support its investment analysis staff in the investment analysis activities.  It is expected that the ARR-100 IRT will support the ASD Investment Analysis Team (IAT), andmust:

- Evaluate the current system capability within the problem domain and its role in the NAS in terms of functions and services

- Determine how a solution that fulfills the need will fit into the current operational environment

- Examine the operational/logistical concepts which will likely result and forecast their impact on NAS performance and FAA levels of services

- Break down the requirements to a level where trade-offs among them can be effectively considered.

Figure 2.2-1

Support Identification of Alternatives

Figure 2.2-1 summarizes the activities comprising support for identification of candidate solutions and depicts the decision processes leading to analysis of solutions alternatives.

ARR supports identification of candidate solutions by:

- Coordinating participation on IAT

- Identifying candidate alternatives

- Supporting development of the Investment Analysis Plan (IAP)

2.2.1	Coordinate Participation on IAT

| Description | An IAT consists of experts IPT(s), sponsor organizations, the investment analysis staff within ASD, and other organizations as necessary to conduct the detailed analysis of alternatives leading to the selection and recommendation of a preferred acquisition solution. ARR coordinates the selection and assignment of ATS personnel to the IAT. |  |
| --- | --- | --- |

| Activity #1 | Coordinate ATS Personnel Assignments |  |
| --- | --- | --- |
| Purpose | ARR supports ASD in identifying the appropriate skills from within ATS which will be required in the performance of alternatives identification and analysis processes. |  |
| Step #1 | The ATS skill requirements are assessed and a determination of those skills required as full time IAT members or as ad hoc SME is made. Assess IAT requirements |  |
| Step #2 | ARR contacts the appropriate ATS functional organization managers to identify individuals with the requisite skills and coordinates the temporary duty assignments to the IAT or ad hoc participation, as appropriate. Coordinate assignment of AT/AF members and SMEs to IAT |  |

2.2.2	Identify Candidate Alternatives

| Description | The alternative solution identification and analysis activity begins with a market analysis using the initial RD and other information that will assist in developing information about potential alternatives. A market analysis will solicit information on potential capabilities that may satisfy the mission need, initial requirements, and support the identification of alternatives. The magnitude and degree of formality of the market analysis will vary, but should always seek widest possible input from industry or others with potential solutions. The IAT may determine that a market analysis is not needed because they already have a good knowledge of available technology and products. |  |
| --- | --- | --- |

| Activity #1 | Support Market Analysis |  |
| --- | --- | --- |
| Purpose | Market surveys are performed to determine the availability of industry products, as well as other government vehicles that meet some or all of the initial requirements. Concurrent with the market analysis, and throughout the Investment Analysis process, the RD is continuously refined by the ARR-100 IRT for specificity and prioritization through performance of trade-off analyses. |  |
| Step #1 | Market analysis is initiated through a request from the FAA to industry, foreign sources, universities, and other agencies (as a minimum) for potential capabilities/alternatives that may satisfy the mission need. The request normally will consist of a letter, the initial RD, and other data as deemed appropriate. This activity supports the identification of alternatives. Support identification of market sources |  |
| Step#2 | Responses to the market survey are reviewed in relation to evaluation criteria and potential candidate solutions are identified. Review vendor capability statements |  |
| Step #3 | Products or vendor identified as potential solution alternatives may be physically inspected. Inspect potential products/vendor facilities |  |

| Activity #2 | Identify and assess candidate alternatives |  |
| --- | --- | --- |
| Purpose | Identifying alternatives is a process by which possible solutions for meeting the shortfalls stated in the MNS and satisfying the requirements in the initial RD are evaluated. Early interaction with the sponsor and IPT will help develop a thorough understanding of the problem and how closely the system and supportability characteristics can be satisfied with current technology or identified future technology. Depending on the type of problem, identifying alternatives should include: Nonmaterial solutions; Acquisition of COTS/NDI; Collaborative development programs/shared funding for “custom” system development with other countries, federal agencies or private sector entities; and Custom development for FAA. A compilation of alternatives that are different in approach, technology, user involvement, or other parameters will be developed. |  |
| Step #1 | A list of potential solution alternatives is developed by the IAT, along with documentation of the features of the potential solution which suggest its viability as a candidate solution. Identify and document candidate solutions |  |
| Step #2 | The items on the list of candidate solutions are each examined in relation to initial requirements contained in the initial RD. Review candidates in relation to initial requirements and thresholds |  |
| Step #3 | If none of the alternatives examined meet the requirements on the initial RD, the sponsoring organization, in coordination with ARR, initiates the Assess Requirement Trade-off process. Requirements Trade-Off |  |
| Step #4 | If a viable nonmaterial solution is identified that is achievable within approved budgets, it may be implemented without proceeding further in the acquisition management process. The organization sponsoring the mission need must notify the JRC of the selection of the nonmaterial solution. A nonmaterial solution could remain as a potential candidate for investment analysis if it is not clearly determined at this point to be more cost-effective than the material solutions under consideration. Prepare list of candidate solutions |  |

| Activity #3 | Assess ATS Budget Impacts |  |
| --- | --- | --- |
| Purpose | For each of the candidate solutions, ARR coordinates the development of a rough order of magnitude (ROM) assessment of the life-cycle costs associated with each requirement element defined in the RD template. This assessment provides the baseline for future requirement trade-off analyses. Budget place-holders are adjusted as necessary. |  |
| Step #1 | ARR-100 coordinates, with ARR-200 and ARX-200, the development of O&M cost estimates. Prepare O&M cost estimates |  |
| Step #2 | The IPT member to the IAT takes the lead in developing the F&E cost estimates associated with each solution alternative. ARR-100 coordinates ATS assistance, as required. Prepare F&E cost estimates |  |
| Step #3 | The IPT member to the IAT takes the lead in developing the RE&D cost estimates associated with each solution alternative. ARR-100 coordinates ATS assistance, as required. Obtain RE&D cost estimates |  |
| Step #4 | ARR-100 engages ARR-200 in comparing the aggregate life-cycle cost estimates (F&E, RE&D, and if possible, O&M) with current ATS budget profiles associated with the mission need. If the existing budget projections for F&E and R,E&D are breached, ARR-200 coordinates adjustment of the out-year budget profiles. Coordinate adjustment of budget place-holders |  |

2.2.3	Support Development of Investment Analysis Plan

| Description | The Investment Analysis Plan (IAP) provides the planning information necessary for conducting the particular investment analysis in a timely and efficient manner. It must be completed early in the investment analysis phase, normally immediately after identification of the alternatives. The IAP is developed by the IAT and signed and distributed by the Director, IAS (ASD-400). The IAP will provide the following: composition of the IAT (by name and organization), and schedule for completing the various activities within the investment analysis process, including expected date for the investment decision (JRC #2). the assignment of roles and responsibilities for accomplishing the activities consistent with the AMS guidelines and the defined investment analysis process tool(s) all alternatives identified and the end set chosen for further analysis as candidate solutions. The template for developing the Investment Analysis Plan is available at http://fast.faa.gov. |  |
| --- | --- | --- |

| Activity #1 | Provide Input to IAP |  |
| --- | --- | --- |
| Purpo¦se | ASD is responsible for developing a plan for analysis of alternatives. As a member of the IAT, ARR participates in the development of the plan. |  |
| Step #1 | To facilitate the Investment Analysis process, roles and responsibilities of individual IAT member organizations should be identified early on. This will allow for accountability, as well as minimize the risk of tasks not being addressed. A table should be provided identifying the roles and responsibilities for all activities (elements) within the investment analysis process. Determine IAT team roles and responsibilities |  |
| Step #2 | When developing a preliminary schedule, the following must be considered: The initial schedule requirement at the beginning of investment analysis is the time-frame in the Mission Need Statement when the new capability must be operational to satisfy mission responsibilities; and The schedule requirement at the investment decision is the time needed to deploy the solution selected for implementation by the JRC, plus the schedule requirement for resolution of any deferred requirements. Develop schedule |  |
| Step #3 | The IAT assesses resource requirements for conduct of market analysis and other activities associated with identification of solution alternatives and their analysis. (e.g., travel to vendor locations to view products with solution potential should be considered) Determine resource requirements |  |
| Step #4 | Of particular interest to ATS are the assumptions upon which the investment analysis will be based, and the criteria for evaluating the alternatives. The IAT will develop evaluation criteria to enable comparison of alternatives. The evaluation criteria must be clearly defined and the relative weight for each factor must be stated in the IAP. Life-cycle cost to the FAA and airspace users must be used as evaluation factors in every investment analysis. Evaluation criteria will vary according to the nature of the need and potential solutions, but typically should include such factors as time to field an operational capability, acquisition and life-cycle cost, schedule, system performance (to include human performance), benefits, risks, supportability, affordability, and infrastructure. Review assumptions and develop evaluation criteria |  |

| Activity #2 | Coordinate ATS review of IAP |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to assure that the IAP appropriately reflects the participation, schedule and understanding of the scope of the investment analysis from an ATS perspective. |  |
| Step #1 | The IRT Lead/ARR representative to the IAT briefs ARR management on the content of the IAP and highlights potential ATS concerns. Brief ARR management |  |
| Step #2 | The draft IAP is circulated to the IRT for their review and comment. Obtain IRT review |  |

2.3	SUPPORT ANALYSIS OF ALTERNATIVES

ATS participation in analysis of solution alternatives involves:

- Identifying  solution specific requirements

- Supporting analysis of solution alternatives

- Performing ATS affordability assessment

- Participating in SEOAT affordability assessment

Figure 2.3-1 summarizes the Analyze Alternatives process.

Figure 2.3-1

Analysis of Solution Alternatives

2.3.1	Identify Solution Specific Requirements

| Description | The analysis of solution alternatives is dependent upon a full understanding of the supportability, implementation and other requirement elements which were addressed at a high level in the alternatives identification process. ATS uses the template for the RD to identify requirements derived from the high-level requirements in the initial RD. |  |
| --- | --- | --- |

| Activity #1 | Populate RD template |  |
| --- | --- | --- |
| Purpose | This activity begins the decomposition of high-level requirements contained in the initial RD into more detailed requirements which will enable more detailed comparison of the costs and relative suitability of candidate options. |  |
| Step #1 | IRT members, based on OPI assignments established in the IRT Team plan use their internally established mechanisms for obtaining organizational requirement inputs for the RD. Obtain functional organization inputs |  |
| Step #2 | The requirement inputs from functional organizations are provided to the IRT Lead who consolidates them in the RD template format. Consolidate functional organization inputs |  |
| Step #3 | In a meeting of the IRT, the consolidated RD requirement inputs are reviewed and validated. The IRT resolves conflicts, gaps and/or overlaps in the candidate requirements and develops a comprehensive set of requirement statements that fully populate the RD template. Validate requirements |  |
| Step #4 | ARR performs an assessment of the IRT-approved set of RD requirement statements to assure that statements are clear and concise. Resolution of the format and content of statements is coordinated through the IRT Lead. Verify requirement statement format |  |

| Activity #2 | Tailor the RD to solution specific alternatives |  |
| --- | --- | --- |
| Purpose | Specific solution alternatives may require that some requirement elements be tailored to address the specific nature of the alternative. For example, a ground based surveillance alternative may have significantly different operation and maintenance requirements than a space-based alternative. |  |
| Step#1 | Each solution alternative is reviewed in relation to the RD template to identify requirement categories which are unique to that alternative. Identify solution-specific requirement categories |  |
| Step #2 | IRT members, based on OPI assignments established in the IRT Team Plan use their internally established mechanisms for obtaining organizational requirement inputs for the RD. Obtain solution-specific requirement inputs from ATS functional organizations |  |
| Step #3 | Conflicts, gaps or overlaps among solution-specific requirement inputs received from OPIs are resolved between the OPI and the IRT Lead Resolve requirement discrepancies |  |
| Step #4 | The IRT Lead coordinates quality assurance review of the solution-specific requirement statements. Validate requirement statement format |  |
| Step #5 | Solution-specific RDs are prepared, as necessary. Prepare solution-specific RDs |  |

- Support Analysis of Solution Alternatives

| Description | The IAT will undertake the analysis of the candidate solutions based on the evaluation criteria in the IAP. The evaluation criteria must be clearly defined and the relative weight for each factor must be stated by the IAT. An evaluation matrix will be constructed by the IAT to provide a value or ranking for each evaluation factor for each alternative, including life-cycle cost, benefits, schedule, performance, and risk. |  |
| --- | --- | --- |

| Activity #2 | Prepare Evaluation Matrix |  |
| --- | --- | --- |
| Purpose | The IAT will construct an evaluation matrix to provide a value or ranking for each evaluation factor for each alternative. The factors to be analyzed may include, as appropriate: Compatibility with NAS architecture, life-cycle cost (systems, equipment, facilities, support, etc), cost and benefit analysis (period to pay back investment), technical performance/functionality, schedule, human factors, environmental & health impacts, radio frequency spectrum availability, supportability, regulatory/procedural impact, operational suitability, interdependencies with other programs, and risk assessment (the likelihood of meeting stated performance, schedules, benefits, and cost). |  |
| Step #1 | The IAT will develop the evaluation matrix by determining which factors to include as criteria and their relative importance. ATS members of the IAT will provide input to the construction of the evaluation matrix. Provide input to development of the evaluation matrix |  |

| Activity #2 | Populate Evaluation Matrix |  |
| --- | --- | --- |
| Purpose | The evaluation matrix will provide an objective and quantified record of the strengths and weaknesses for each of the alternatives. |  |
| Step #1 | ATS SMEs will play a big role in assessing the attributes of each alternative. ARR-100 will participate in the process and coordinate the participation of ATS SMEs, as required. Populate evaluation matrix |  |

| Activity #3 | Assess Requirements Trade-Offs |  |
| --- | --- | --- |
| Purpose | Upon completion of the evaluation matrix, a trade-off analysis must be conducted against the requirements to ensure that a balancing of the criteria to the requirements can be attained effectively or that some trade-offs may be effected in order to solve any potential problem areas. |  |
| Step #1 | ARR-100 will reconvene the IRT and initiate the process to Assess Requirement Trade-Offs. Perform a requirements trade-off |  |

2.3.3	Develop preliminary Acquisition Program Baselines

| Description | Preliminary APBs are required prior to perform the affordability analyses. Based on the data gathered during evaluation of alternatives, the IPT representatives to the IAT will prepare preliminary APBs. The key parameters for the subsequent affordability assessments are the cost and schedule baselines. |  |
| --- | --- | --- |

| Activity #1 | Prepare APB templates |  |
| --- | --- | --- |
| Purpose | AMS has provided a template for the development of the APB. The IAT should use this template as guidance in developing the preliminary APBs for each alternative. |  |

| Activity #2 | Transfer evaluation matrix data into APBs. |  |
| --- | --- | --- |
| Purpose | For each of the candidate solutions, the IAT needs to populate schedule and cost profiles. |  |

2.3.4	Perform ATS Affordability Assessment

| Description | Affordability assessments are a determination of whether there are adequate financial and other resources available to funding the candidate alternatives under current agency funding plans (Capital Investment Plan [CIP] financial profile, operations and research, engineering and development profiles, and the LRRAP projections). If adequate funding is not available, offsets must be made from existing programs to provide for the solution undergoing affordability analysis if it is to be funded. Before proceeding to the SEOAT, ATS sponsored programs will undergo an internal affordability assessment. With very rare exceptions, offsets required to fund an ATS sponsored program will come from other ATS sponsored programs. Therefore, the internal assessment is performed in order to decide what offset recommendations will ATS present to the SEOAT. |  |
| --- | --- | --- |

| Activity #1 | Identify ATS priorities |  |
| --- | --- | --- |
| Purpose | ATS priorities must be reviewed to determine whether the mission need under analysis can be accommodated within the current priorities or if ATS program offsets may be required. |  |
|  | Note: Specific steps are TBD |  |

| Activity #2 | Identify offsets |  |
| --- | --- | --- |
| Purpose | Depending on the relative priority of the subject mission need compared to other program priorities, it may be necessary to eliminate, down-scope, or otherwise revise the baseline of other ATS sponsored programs. The purpose of this activity is to identify the proposed program offsets to be made. |  |
|  | Note: Specific steps are TBD |  |

| Activity #3 | Provide data for SEOAT assessment |  |
| --- | --- | --- |
| Purpose | Document the recommendations of the ATS affordability assessment for consideration by the SEOAT. The purpose of this activity is to package ATS input to the agency affordability assessment. |  |
|  | Note: Specific steps are TBD |  |

2.3.5	Participate in SEOAT Affordability Assessment

| Description | A new program is authorized only if the agency commits to full funding of it. The Systems Engineering/Operational Analysis Team (SEOAT) determines the priority of the proposed new program in relationship to all other programs competing for resources in the same year(s) and recommends offsets among programs to the JRC. This information is included in the Investment Analysis Report provided to the JRC at the investment decision point. The SEOAT performs an affordability assessment of all candidate solutions to a mission need, and maintains a relative priority listing of all agency programs based on standard evaluation criteria approved by the. This priority list supports the affordability assessment of new programs, reprogramming due to baseline changes on existing programs, and the annual budget process. The SEOAT is composed of representatives from each line of business and other appropriate functional disciplines, and is chaired by the Director, System Architecture and Investment Analysis. |  |
| --- | --- | --- |

| Activity #1 | Review package to be presented to SEOAT |  |
| --- | --- | --- |
| Purpose | Upon completion of the analysis of the candidate solution, the IAT will forward initial APBs and supporting data for all candidate solutions to the SEOAT. The information from the ATS affordability assessment is provided to the SEOAT. The IAT information that is provided includes a set of well-defined candidates along with a preliminary APB for each candidate, cost and benefit analysis, risk assessment, and other data as appropriate. Each alternative will be fully documented as to all data and factors considered. Key assumptions will be identified for each alternative. |  |
|  | Note: Specific steps are TBD |  |

2.4	OBTAIN INVESTMENT DETERMINATION

Obtaining an investment determination from the JRC involves:

- Determining solution(s) to be recommended

- Developing solution-specific RD(s)

- Supporting development of acquisition program baseline (APB) document(s)

- Supporting development of the Investment Analysis Report (IAR) document

- Preparing for JRC determination

- Transitioning to Solution Implementation

Figure 2.4-1

Obtain Investment Determination

2.4.1	Determine Solution(s) to be Recommended

| Description | The IAT is responsible to the JRC to provide an analysis of all viable solution alternatives and to recommend a solution for their approval. The selection of the solution to be recommended is determined by evaluating candidate solutions in relation to the relative risks, costs, and schedule considerations. |  |
| --- | --- | --- |

| Activity #1 | Evaluate relative costs vs. benefits of solution alternatives |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to perform a structured evaluation to compare alternatives as a means of identifying the solution to be recommended to the JRC. |  |
| Step #1 | Apply the IAT developed evaluation matrix to each candidate solution and provide input to the IAT Lead. Evaluate each solution |  |
| Step #2 | The composite of evaluations performed by IAT members is reviewed by ARR. Review the IAT’s composite evaluation |  |
| Step #3 | Participate on the IAT to determine a consensus solution to be recommended. Participate in selection of solution to be recommended |  |

| Activity #2 | Coordinate identification of optimum solution |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to inform ATS management of the IAT’s recommendations and to obtain management feedback. |  |
| Step #1 | The ARR member of the IAT briefs ARR management on the selection solution recommendation. Brief ARR management |  |
| Step #2 | The ARR representative to the IAT performs follow-up actions as directed by ARR management. Perform follow-up as directed by management. |  |

- Finalize Solution-Specific RD(s)

| Description | The Investment Analysis Report includes a draft Acquisition Program Baseline (APB) for each alternative considered during investment analysis. A fully populated RD, tailored to the specific solution, is one component of the APB. Provision of the RD is the responsibility of ARR. |  |
| --- | --- | --- |

| Activity #1 | Update/complete RD template(s) |  |
| --- | --- | --- |
| Purpose | As is the case for the Mission Need Statement, the Requirements Document may engender more than one acquisition program. In such situations, requirements in the Requirements Document are partitioned into the Acquisition Program Baselines of each proposed program, as appropriate. APBs do not describe a specific solution, and should not preclude leasing, commercial, or non-developmental items as potential solutions. |  |
| Step #1 | The RD template is reviewed in relation to the current evolution of the RD and incomplete or missing information is identified. Identify missing/incomplete information |  |
| Step #2 | IRT members who are the OPIs for requirement domains which are not yet complete coordinate provision of missing information with stakeholder functional organizations. Obtain missing/incomplete information |  |
| Step #3 | The ARR member of the IAT consolidates IRT supplied information into the RD template. Update RD |  |

| Activity #2 | Obtain IRT Consensus |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to obtain Team consensus. Issues preventing consensus should documented and elevated to the appropriate level of management for resolution. |  |
| Step #1 | When all issues have been resolved and the team has indicated consensus, document team concurrence using the Consensus Agreement Form (Appendix TBD). Obtain consensus agreement |  |

2.1.3	Coordinate Final RD

| Description | The RDs incorporated within APBs represent the ATS position relative to requirements to be met during solution implementation. They must accurately and comprehensively reflect ATS interests. The purpose of this activity is to obtain ATS commitment to the contents of the solution specific RDs because one of them will be selected for implementation. The documents must be reviewed by appropriate ARS and other ATS organizations to ensure the RD includes the requirements from all stakeholders. |  |
| --- | --- | --- |

| Activity #1 | Obtain Internal ARS Concurrence |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to reach internal ARS concurrence on the final RD. |  |
| Step # 1 | IRT lead briefs ARR-100&200 on the final RD and provides a copy of the final RD to ARR-100 management for final review. Review by ARR-100 management and ARR-200. |  |
| Step #2 | IRT lead prepares a separate Clearance Record Form (1300-2) for each ARS director (ARN/U/W/X-1). A copy of the RD and a copy of the signed consensus agreement is attached. Distribute review package to obtain comments/concurrence from internal ARS |  |
| Step #3 | If full concurrence does not occur, resolve the non-concurs. If necessary, meet with IRT to review changes. Resolve ARS non-concurs |  |

| Activity #2 | Obtain ATS/Stakeholder Concurrence |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to reach concurrence from those FAA organizations having an interest in the program. |  |
| Step #1 | IRT lead prepares a separate Clearance Record Form (1300-2) for each service under ATS (AAT-1, AAF-1, ASC-1, ATQ-1). In addition, IRT leads prepares a letter requesting comments from the ATS Union (PASS, NAATS, NATCA); and any other relevant stakeholders organizations. A copy of the RD and a copy of the signed IRT consensus agreement is attached. Distribute review package to obtain comments/concurrence from Stakeholders |  |
| Step #2 | If full concurrence does not occur, resolve the non-concurs. If necessary, meet with IRT to review changes. Resolve FAA non-concurs |  |

| Activity #3 | Transmit RD for ATS-1 Signature |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to prepare the final RD containing internal ARS and stakeholder comments/concurrence for approval. |  |
| Step #1 | A copy of the clearance records, the final RD, and a the consensus agreement are packaged for ARS-1 signature. IRT lead prepares a transmittal letter from ARR-1, through ARS-1, to ATS-1. Generate and transmit ATS-1 signature package |  |

- Support Development of IAR

| Description | The results of investment analysis are contained in the Investment Analysis Report. The report defines each candidate solution to the mission need, and compares the relative strengths and weaknesses against the evaluation factors considered during investment analysis. It also contains the SEOAT affordability assessment. The Acquisition Program Baseline for each candidate solution is attached to the report. The template for developing the Investment Analysis Report is available at http://fast.faa.gov. |  |
| --- | --- | --- |

| Activity #1 | Review/Populate APB Template |  |
| --- | --- | --- |
| Purpose | The APB represents the contract between the providing and user organizations concerning what the acquisition program will provide, how much it will cost, and when it will deliver products and services. It defines the performance, supportability, and benefit requirements the program must achieve, and sets the cost and schedule boundaries within which the program is authorized to proceed. It also establishes the performance metrics for assessing program success and for advancing it through the acquisition lifecycle. Development of the APB is the responsibility of the IPT. As a member of the IAT, the ARR representative supports the development of the APB, as required. |  |
| Step #1 | As the focal point on the IAT for ATS requirements, the ARR representative assures that performance parameters of the APB meet the requirements of the RD. Incorporate RD data |  |
| Step #2 | The ARR representative on the IAT performs data collection and writing tasks on the APB as appropriate. Draft APB content, as needed |  |

| Activity #2 | Coordinate ATS review |  |
| --- | --- | --- |
| Purpose | The APBs to be included in the IAR are reviewed with ASD and by ARR management to assure that they reflect the content and quality necessary for inclusion in the report to the JRC. |  |
| Step #1 | The ARR representative to the IAT provides draft APBs to the IRT and ARR management for review. Obtain IRT and ARR management review |  |
| Step #3 | IRT and ARR management comments are consolidated and provided to the IPT lead for incorporation in the final IAR. Provide ATS comments to the IAT |  |

2.4.4	Prepare for JRC

| Description | The investment decision is the formal venue for implementing a program. The investment decision process is initiated upon completion of the analysis of candidate solutions and the affordability assessment and delivery of the IAR to the JRC. The investment decision process is concluded with the JRC determination of which candidate solution, if any, the FAA will pursue and what resources (capital and operating) will be allocated. |  |
| --- | --- | --- |

| Activity #1 | Conduct JRC Pre-briefs to ATS management |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to prepare ATS management for participation in the JRC investment decision and to identify critical data which ATS recommends be tracked by the JRC during solution implementation |  |
| Step #1 | The IAT prepares a briefing summarizing the investment analysis process and the conclusions of the analysis. The briefing highlights issues, risks, and concerns relevant to the ATS functional organizations. Prepare JRC pre-brief |  |
| Step #2 | The ARR member of the IAT schedules and participates in ASD conducted JRC pre-briefs to affected ATS functional organization management. IRT members from the functional organization being briefed participate in the briefing. Schedule and conduct pre-brief(s) |  |
| Step #3 | Questions and issues raised during each JRC pre-briefs are documented and provided to ARR management. Document ATS management concerns |  |

| Activity #2 | Identify critical data for JRC tracking |  |
| --- | --- | --- |
| Purpose | When an investment decision is made by the JRC, critical data and milestones to be reviewed with the JRC during solution implementation are identified. ARS develops and recommends the list of critical data items which ATS wants reviewed by the JRC. |  |
| Step #1 | Based on ATS management comments and discussion during the JRC pre-briefs, the ARR representative drafts a list of critical data to be tracked by the JRC during solution implementation/ Draft list of critical data elements for JRC tracking |  |
| Step #2 | The list of proposed critical data elements is submitted to ARR management for coordination with ARS-1. Submit proposed critical data elements to ARR management |  |
| Step #3 | ARS-1 determines the critical data elements to be proposed to JRC for tracking. Obtain ARS-1 approval for JRC recommendations |  |

- Transition to Solution Implementation

| Description | An investment decision commits the FAA to full funding of the program and/or approves required offsets. The cost and schedule baselines in the APB at the investment decision and the corresponding funding commitment by the JRC are “not to exceed” agreements. When the JRC approves a solution, the Investment Analysis Staff updates the various documents affected by the decisions, including CIP, RE&D, and LRRAP. The IPT updates the APB to reflect JRC directions and the IRT updates the RD, as necessary. The JRC identifies an IPT to carry out solution implementation in accord with the approved APB. |  |
| --- | --- | --- |

| Activity #1 | Adjust ATS budget profiles |  |
| --- | --- | --- |
| Purpose | Depending on the solution approved by the JRC, ATS budget profiles may be impacted. The appropriate adjustments are coordinated and incorporated in ATS documentation. |  |
| Step #1 | ARR identifies any budget impacts which the JRC decision has on ATS. Identify budget impacts |  |
| Step #2 | Out-year budget profiles are adjusted to reflect the JRC decision and the approved APB. Adjust ATS budget profiles |  |

| Activity #2 | Adjust NAS architecture |  |
| --- | --- | --- |
| Purpose | Depending on the solution approved by the JRC, the NAS architecture may be impacted. The appropriate adjustments are coordinated and incorporated in ATS documentation. |  |
| Step #1 | ARR, in coordination with ARX, identifies NAS architecture impacts resulting from the JRC decision. Identify architecture impacts |  |
| Step #2 | ARR coordinates adjustments to the NAS architecture baseline documentation. Adjust NAS architecture documentation |  |

| Activity #3 | Transfer ATS requirements management leadership to ARU/N/W |  |
| --- | --- | --- |
| Purpose | The investment decision establishes a program and assigns it to an appropriate IPT. An ARU/N/W specialist is assigned to each IPT to support solution implementation and to serve as the focal point for ATS requirements. The purpose of this activity is to transition ATS requirement management from ARR to ARU/N/W. |  |
| Step #1 | The newly assigned ARU/N/W representative to the IPT meets with the ARR representative who represented ARS during Investment Analysis. The meeting is an opportunity for the ARR representative to describe activities, decisions, problems and provide advice to the ARU/N/W representative during Solution Implementation. Briefing the ARU/N/W specialist |  |
| Step #2 | Part of the transfer of ATS requirements management from ARR to ARU/N/W involves transfer of database management responsibility, paperwork and completion of reports. Transfer database control and documentation to ARU/N/W |  |
| Step #3 | The ATS Project Case File is physically transferred from the ARR representative to the newly assigned ARU/N/W representative. Deliver ATS Project Case File |  |
| Step #4 | The IRT leadership responsibility, along with IRT meeting records, membership lists and scheduling information is transferred from ARR representative to the assigned ARU/N/W representative. Transfer IRT leadership to ARU/N/W lead |  |

2.5	ASSESS REQUIREMENT TRADE-OFFS

The Assess Requirement Trade-Offs process may be initiated at any time during Investment Analysis when analyses indicate that ATS requirements may not be achievable due to technical limitations or cost and/or schedule constraints.  The current ATS requirements are reviewed to identify possible requirement trade-offs which can be agreed to by the ATS functional organizations in order to permit identification of an acceptable solution alternative.  As depicted in Figure 2.5-1, assessment of requirement trade-offs involves:

1. 	Reviewing solution trade-offs

2. 	Modifying RD templates to reflect trade-offs

Figure 2.5-1

Assess Trade-Offs

- Review Solution Trade-Offs

| Description | If a solution does not meet all requirements stated in the RD, it must be evaluated for trade-offs. Such trade-offs may be in reference to any of the requirement domains defined by the RD template. |  |
| --- | --- | --- |

| Activity #1 | Assess requirement element trade-offs |  |
| --- | --- | --- |
| Purpose | The ARR Lead coordinates an assessment of requirement trade-offs through the IRT. |  |
| Step #1 | In advance of an IRT meeting, the ARR staff performs an assessment of potential technological, cost and/or schedule trade-offs for consideration by the IRT membership. Identify potential requirement trade-offs |  |
| Step #2 | The IRT is convened to review proposed requirement trade-offs and develops an IRT consensus. Convene IRT to determine viable requirement adjustments |  |

| Activity #2 | Coordinate trade-offs with affected functional organizations |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to coordinate adjustments to ATS requirements with affected functional organizations prior to providing the information to the IAT |  |
| Step #1 | Members of the IRT, as OPIs for particular requirement domains, obtain review of proposed requirement adjustments from the affected stakeholder organizations. Obtain functional organization review |  |
| Step #2 | Based on functional organization review, the IRT members confirm or modify the preliminary position relative to requirement adjustments and approve a position to be delivered to the IAT. Obtain IRT member commitment to trade-offs |  |
| Step #3 | The IRT Lead documents the IRT trade-off decisions and provides the information to the IAT Lead. Inform IAT of requirement adjustments |  |

2.5.2	Modify RD and Life-Cycle cost estimates

| Description | Any requirement trade-offs are incorporated into the RD and life-cycle cost projections are adjusted and coordinated with ATS budget planners. |  |
| --- | --- | --- |

| Activity #1 | Adjust LCC ROM, if necessary |  |
| --- | --- | --- |
| Purpose | The life-cycle cost adjustments associated with warehoused/modified requirements need to be reflected in the life-cycle cost estimate. |  |
| Step #1 | The life-cycle cost impact of requirement trade-offs are assessed. Assess changes to life-cycle costs |  |
| Step #2 | The life-cycle cost estimates are provided to ARR-100 for incorporation in ATS budget profiles. Coordinate ATS budget profile adjustments |  |

| Activity #2 | Document Requirement Trade-Offs |  |
| --- | --- | --- |
| Purpose | If requirement trade-offs occur, such actions must be warehoused as either an appendix or attachment to the final RD This information is necessary to show that requirements have not been omitted, but set-aside as non-critical. Warehoused requirements may be addressed at a later time, when funding, schedule, or other criteria permit. |  |
| Step #1 | The ARR representative to the IAT summarizes decisions relative to requirement trade-offs and identifies the list of warehoused requirements. Prepare summary of warehoused requirements |  |
| Step #2 | Warehoused requirements are incorporated as an attachment to the RD. Prepare RD attachment |  |
| Step #3 | The RD is revised to reflect requirement trade-offs. Revise RD template |  |

2.6	RESOLVE ATS REQUIREMENT ISSUES

The Resolve ATS Requirement Issues process is an ongoing from the start of Mission Analysis and continues into In-Service Management.  Some issues may be internal to ATS due to conflicts or incompatibilities among requirements identified by ATS functional organizations.  These issues are managed within ATS, usually through IRT deliberations.  Issues external to the ATS are usually due to either disagreement with or misinterpretation of ATS requirements by the IAT or other organization managed outside of the ATS Directorate.  The ARR representative on the IAT facilitates understanding and interpretation of ATS requirements so that potential issues are solved and the Resolve ATS Requirements process can be avoided.

Resolve ATS Requirement Issues process involves:

- Coordinating Issue Internally

- Coordinating Resolution with IAT

- Elevating issue (as necessary)

Figure 2.6-1 depicts the Resolve ATS Requirement Issues process.

Figure 2.6-1

Resolve ATS Requirement Issues

- Coordinate Issue Internally

| Description: | When an ATS requirements issue is identified, the representative to the IAT coordinates development of a clear and succinct statement of the issue and its potential impact. Based on understanding of the issue, a determination is made as to whether the issue is one internal to ATS or one that requires involvement of the IAT. |  |
| --- | --- | --- |

| Activity #1 _ | Identify and Document Issue |  |
| --- | --- | --- |
| Purpose: | The purpose of this activity is to assure that the requirement issue is fully understood and clearly documented so that deliberations about resolution can be conducted. |  |
| Step #1 | The ARR member of the IAT is the recipient and focal point for all identified ATS requirement issues. Upon notification or awareness of a requirement issue the ARR representative contacts the issue identifier to obtain clarification of this issue and to determine what, if any, actions have been attempted to obtain resolution. Obtain information about the issue from issue identifier |  |
| Step #2 | Based on information obtained in Step #1, the ARR representative drafts a statement of the issue and provides a summary of potential impacts on achieving ATS requirements if the issue is not resolved. Prepare a statement of the issue and its relationship to ATS requirements |  |

| Activity #2 | Coordinate Issue with OPIs |  |
| --- | --- | --- |
| Purpose | Identified issues will be related to one or more ATS requirement elements. This activity assures that the OPI(s) on the IRT who have responsibility for the associated requirement elements are informed of the issue. |  |
| Step #1 | The issue statement prepared by ARR is reviewed with the issue source and the OPIs on the IRT. Review Issue Statement with issue source and representatives of ATS functional organizations |  |
| Step # 2 | Comments and input from the issue identifier and OPIs are used to revise and refine the issue statement. Finalize Issue Statement |  |
| Step # 3 | The IRT Lead sends the finalized issue statement to all IRT members. Distribute Issue Statement to IRT members |  |
| Step #4 | Based on the input from the issue identifier and discussion with the associated OPIs, the IRT Lead determines if the issues can be resolved internal to ATS. Determine if issue can be resolved at IRT level or if IAT involvement is required |  |
| Step #5 | Issues internal to ATS are discussed at an IRT meeting and an appropriate solution is identified. When a resolution involves modification of ATS requirements, the Trace Requirements process is engaged. Convene IRT to resolve internal issues |  |

2.6.2	Coordinate Issue Resolution with IAT

| Description | When the ARR representative determines that an issue must be resolved with IAT involvement, the IRT is convened to determine an ATS corporate position relative to the issue. This position is coordinated with ARS management prior to presentation to the IAT for their action. |  |
| --- | --- | --- |

| Activity #1 | Establish ATS Position Relative to Issue |  |
| --- | --- | --- |
| Purpose | Before an issue is presented to the IAT, the IRT Lead coordinates development of a corporate position relative to the issue to avoid conflicting viewpoints being communicated to the IAT by ATS functional organizations. |  |
| Step #1 | Convene IRT to review issue |  |
| Step #2 | The IRT identifies options, evaluates those options and selects one to recommend as the ATS position relative to the issue. Identify and evaluate alternative options to resolve issues |  |
| Step #2 | Based on the outcomes of the IRT meeting, the IRT Lead prepares a briefing to present the issue and the IRT’s recommended ATS position. Brief ARR management |  |
| Step #3 | The IRT Lead obtains ARR management concurrence with a proposed position. This may involve elevating the issue to ARR-1 or to the ATS Management Team. Obtain management decision relative to preferred approach |  |

| Activity #2 | Support Development of Resolution |  |
| --- | --- | --- |
| Purpose | Once the ATS position has been coordinated with ATS management, the requirements issue is presented to the IAT for consideration of an appropriate resolution and the approach recommended by ATS management. |  |
| Step # 1 | The ARR representative notifies the IAT Lead of the need to address the issue at an IAT meeting. Schedule and brief IAT on issue and ATS position |  |
| Step # 2 | In discussion with IAT members, an action plan is identified to resolve the issue. The ARR member of the IAT assures that specific action steps, responsible parties and schedule are developed to accomplish the resolution. Develop action plan for resolution of the issue |  |
| Step # 3 | The ARR representative to the IAT provides the resolution action plan to the IAT and obtains commitment to its execution. Confirm IAT concurrence with resolution strategy |  |
| Step # 4 | The ARR member of the IAT monitors accomplishment of action plans to resolve ATS requirements issues. Monitor progress toward resolution |  |
| Step # 5 | When the action plan has been completed, the ARR representative confirms that the issue identifier and OPIs concur that the issue has been resolved. Verify completion of resolution |  |

- Elevate Issue

| Description | The Acquisition Management System (AMS) is based on an Integrated Product Development System (IPDS) approach. The IPDS provides for a hierarchy of teams within teams. Each team has defined empowerment boundaries and decisions are made at the lowest level of the teaming hierarchy. IPDS process guidelines provide mechanisms for resolution of problems and issues throughout the acquisition process. When problems cannot be resolved at the IAT level, the problem is elevated to the next higher team, the Integrated Product Leadership Team (IPLT). When problems cannot be resolved at that level, the next level is the Integrated Management Team. |  |
| --- | --- | --- |

| Activity #1 | Coordinate Briefing to IPLT/IMT |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to plan for presentation of the issue to the IPLT/IMT. |  |
| Step #1 | Each IPDS team has a team plan which outlines its empowerment boundaries. The IRT Lead will review the team plans to determine the appropriate team level empowered to resolve the issue. Review IPDS empowerment boundaries |  |
| Step #2 | In preparation for IMT/IPLT briefing, the IRT Lead reviews team membership. Review core IMT/IPLT membership |  |
| Step #3 | The IRT Lead prepares a briefing which describes the issue and efforts at the IRT and IAT level to resolve the issue. The IRT Lead coordinates the draft briefing with ATS members of the IPLT/IMT. Brief ATS members |  |

| Activity #2 | Support Development of Resolution |  |
| --- | --- | --- |
| Purpose | The purpose of this activity is to formally present the issue to the IPLT/IMT and coordinate execution of the decision made at that level. |  |
| Step #1 | The IRT Lead presents the briefing on the issue(s) which could not be resolved at the IAT level. Brief IPLT/IMT |  |
| Step #2 | The IRT Lead responds to IPLT/IMT questions and provides back up information as required. Provide supporting information |  |
| Step #3 | Based on the decision of the IPLT/IMT, the IRT Lead prepares an action plan to execute the IPLT/IMT decision. Develop resolution action plan |  |
| Step #4 | The resolution action plan is presented to the IPLT/IMT for concurrence prior to its execution. Obtain IPLT/IMT commitment to plan |  |
| Step #5 | The IRT Lead monitors the execution of the resolution action plan and verifies that the resolution is obtained.. Verify resolution of the issue |  |

2.7	TRACE ATS REQUIREMENTS

The Trace ATS Requirements process extends from Mission Analysis through In-Service Management of a product or service.  Once an ATS requirement is included in any AMS required document (e.g., RD, APB, Acquisition Strategy Plan , Integrated Program Plan, and solicitation documentation), it is entered into an ATS tracking data base.  Whenever a change occurs, all “parent” and “child” requirements related to that change must be adjusted and entered in the ATS tracking database.  ARS is developing and will define processes for the management of requirements tracking when selection of the needed tools is complete.

Execution of the Trace Requirements Process involves:

- Editing and formatting requirements statements

- Maintaining the ARS requirements data base

- Preparing and distributing ATS Requirements Status Reports

Figure 2.7-1 depicts the Trace ATS Requirements process.

Figure 2.7-1

Trace ATS Requirements

2.7.1	Edit and Format ATS Requirements Statements

Note:  completion of this section is contingent upon the data base tool and procedures implemented by ARS

| Description: | ARS will develop and issue standards for the documentation of requirements to assure that all ATS requirement statements are concise, positively stated, validated and minimize misinterpretation. Prior to providing any ATS requirement as an input to AMS documents, ARS will review and edit statement in accord with its established standards and criteria. |  |
| --- | --- | --- |

2.7.2	Update ATS Requirements Data Base

Note:  completion of this section is contingent upon the data base tool and procedures implemented by ARS

| Description: | ATS requirements are tracked from their origin in the Mission Need Analysis, through Investment Analysis as documented in the APB. Decomposition of these requirements occurs throughout Solution Implementation through identification of strategies, actions and procurement tasking. During Investment Analysis it is the responsibility of the ARR to assure that the data base is maintained and updated whenever ATS requirements are modified or when a decomposition occurs. The data base tracking assures that every ATS requirement statement is linked to a “parent” requirement in higher order documents or to a “child” requirement(s). Child requirements are translations/decomposition of a requirement in a higher-level planning document. |  |
| --- | --- | --- |

2.7.3	Issue ATS Requirements Status Reports

Note:  completion of this section is contingent upon the data base tool and procedures implemented by ARS

| Description: | The ARS Directorates inform the ATS functional organizations of the status of ATS requirements through periodic ATS Requirements Status Reports. The content, format, frequency, and process for their issuance are not yet determined. |  |
| --- | --- | --- |