U.S. Department of Transportation

Federal Aviation Administration

GUIDE FOR PREPARING THE

FEDERAL AVIATION ADMINISTRATION

OMB EXHIBIT 300s

Final

Version 3.2

February 2007

| Version Number | Version Date | Changes |
| --- | --- | --- |
| Version 1.0 Final | 01/25/2005 | Exhibit 300 guidance (FY2006). |
| Version 2.2 Preliminary Draft | 11/04/2005 | Initial draft with updates to Exhibit 300 guidance (FY2007). |
| Version 2.3 Draft | 11/09/2005 | Complete draft with updates to Exhibit 300 guidance (FY2007). |
| Version 2.4 Draft | 11/09/2005 | Completed draft with updates to Exhibit 300 guidance (FY2007) and highlighted comments |
| Version 2.5.1 Draft | 11/30/2005 | FAA comments from 11/22/05 meeting and inputs were incorporated. |
| Version 2.5.2 Advanced Draft – for ASAG meeting on 12/07/05 | 12/5/2005 | Added comments from K. Kepchar, T. Burke and Terminal. |
| Version 2.5.3 Draft for ASAG review | 12/9/2005 | Incorporated additional comments received after ASAG meeting on 12/7/05. |
| Version 2.5.4 Draft | 1/6/2006 | Incorporates additional comments from Brandi Ingargiola, Darren Ash and Dave Woodson and some editorial clarifications. |
| Version 2.5.4 Final Draft | 2/7/2006 | Incorporates SoS revisions from Sue Fedor and corrected URLs. |
| Version 3.0 | 01/2007 | Revised based on OMB BY08 A-11 Guidance. |
| Version 3.1 | 02/2007 | Incorporates comments from the VMO Office (G. Carnaroli, V. Viets, C. Bumblis, D. Milano). |
| Version 3.2 | 02/2007 | BAE QA Review – A. Evans. |

Note:  This guide is a living document.  Several sections of this guide are subject to change prior to the end of the fiscal year due to OMB and other government wide guidance changes as well as any changes in FAA guidelines and processes.

Table of Contents

1.   Exhibit 300 Preparation Overview	1

1.1   Introduction	1

1.2   Purpose	1

1.3   Acquisition Management System	2

1.4   Exhibit 300 Submission Process	3

1.5   Organization of the Guide	4

1.6   Scoring Criteria	4

1.7   General Writing Rules	14

1.8   Lifecycle Terminology	15

2.  Part I: Summary Information and Justification	1

2.1   Introduction	1

2.2   Section A: Overview	1

2.3   Section B: Summary of Spending	7

2.4   Section C: Acquisition/Contract Strategy	9

2.5   Section D: Performance Information	13

2.6   Section E: Security and Privacy	16

2.7   Section F:  Enterprise Architecture (EA)	20

3.  Part II: Planning, Acquisition and Performance Information	1

3.1   Introduction	1

3.2   Section A: Alternative Analysis	1

3.3   Section B: Risk Management	3

3.4   Section C: Cost and Schedule Performance	5

4.  Part III: Operation and Maintenance Investments	1

4.1   Introduction	1

4.2   Section A: Risk Management	1

4.3   Section B:  Cost and Schedule Performance	2

APPENDIX A - CROSSWALK OF THE EXHIBIT 300 SECTIONS	A-1

APPENDIX B – OPERATIONAL ANALYSIS AND PIRs	B-1

APPENDIX C – USEFUL WEB LOCATIONS	C-1

APPENDIX D – GLOSSARY OF ESSENTIAL TERMS	D-1

APPENDIX E – EVM TERMS	E-1

APPENDIX F – FEDERAL ACQUISITION REGULATION	F-1

APPENDIX G – AMS PERFORMANCE BASED PAYMENT CLAUSES	G-1

# 1.   Exhibit 300 Preparation Overview

## 1.1   Introduction

The purpose of the Exhibit 300 to help agencies plan, budget, procure, and manage their capital assets and report this information to the Office of Management and Budget (OMB).  Per OMB’s Capital Programming Guide dated June 2006, “capital assets include but are not limited to, land, (including parklands), structures, equipment including fleet, and intellectual property (including software) that are used by the Federal Government and have an estimated useful life of two years or more.”

As stated in OMB’s Circular A-11, Federal agencies must annually submit to OMB and Congress the Exhibit 300 as an appendix to their budgets.  In order to receive Congressional program funding each year, the Federal Aviation Administration (FAA) must show through the Exhibit 300’s that investments are managed using the best available practices and that they contribute to the achievement of FAA’s strategic goals and objectives.  The Exhibit 300 serves as FAA’s opportunity to demonstrate to budget decision makers why FAA’s investments are critical to the air traffic community.  It is important to remember that the primary purpose of the Exhibit 300 is to effectively convey accurate information about the investment, including its impact on the business, its status, and the management processes used to execute it and monitor its performance.  Understanding and complying with the information requirements of the Exhibit 300 are key not only to ensuring that the correct information is reported, but also to ensuring that lifecycle management and investment selection, control and evaluation processes are performed correctly to enable the best investment decisions.

The FAA Acquisition Management System (AMS) calls for the use of Exhibit 300 as the approval document for agency investments.  Each Exhibit 300 that is submitted to OMB must be consistent with the most recently approved Joint Resource Council (JRC) baseline.

## 1.2   Purpose

The purpose of this guide is to provide guidance for preparing the Exhibit 300.  As the cornerstone of key investment decisions, the Exhibit 300s must be filled out completely, clearly, and concisely.  In the past FAA has risked reduced funding for major NAS F&E investments by as much as $300 million because of poor or not so compelling business cases.  In referring to this, Administrator Marion Blakey stated in the BY2005 Exhibit 300 kickoff meeting, “the inability to tell the story of why these investments are important cost us dearly."

This guide addresses common issues that arise during both the writing and scoring process of the Exhibit 300.  In addition to general guidance, detailed information is provided for each section of the Exhibit 300.  If additional information or clarification is needed, the FAA Value Management Office (VMO) maintains an updated list with contact information for the Subject Matter Experts (SMEs) which can be found in the Exhibit 300 portal:  https://nase.amc.faa.gov.

Note: This URL will not work from outside the FAA intranet without a valid FAA user id and password.  To obtain access to this URL contact Anona Day at Anona.Day@faa.gov.

## 1.3   Acquisition Management System

The Acquisition Management System (AMS) establishes policy and guidance for all aspects of lifecycle acquisition management for the FAA.  It defines how the FAA manages its resources - money / people / assets - to fulfill its mission. The objectives of the policies are to increase the quality, reduce the time, manage the risk, and minimize the cost of delivering safe and secure services to the aviation community and flying public.  AMS policies promote these objectives through partnerships among service providers and customers to ensure FAA plans, programs, and budgets address priority aviation needs.

The AMS consists of numerous policies and guidelines that describe investment management and lifecycle management requirements, responsibilities, processes, and documentation, including those for investment analysis and decisions.  Electronic copies of the AMS policies and guidelines are available on http://fast.faa.gov.

OMB uses the terms “Planning, Acquisition, and Maintenance” to define life-cycle funding phases in the Summary of Spending (SoS) Table and other sections of the Exhibit 300.  The table below maps OMB CPIC and Funding Phases to FAA AMS Lifecycle Phases.

| OMB CPIC Phase | Summary of Spending Funding Phase | FAA AMS Lifecycle Phase |
| --- | --- | --- |
| Select | Planning | Mission Analysis Investment Analysis |
| Control | Acquisition (DME) | Solution Implementation |
| Evaluate | Maintenance (Steady-State) | In-Service |

Table 1: CPIC/AMS Mapping

All sections of the Exhibit 300 must be completed prior to submittal to OMB.  It is very important that investments in the planning phases that have not completed an initial investment analysis or obtained a final investment decision by the JRC clearly state throughout the Exhibit 300 that the information is preliminary.  For new investments it’s important that the funding for the phase or segment that covers that budget year be approved by the JRC prior to the OMB Exhibit 300 being submitted to OMB; otherwise the funding may not be approved.

The Exhibit 300 is also used at JRC investment decision meetings.  The JRC is the FAA executive investment review board that makes all the investment decisions for investments that are required to submit Exhibit 300s to OMB and for other investments designated for JRC review based on agency specific criteria.

The Exhibit 300 becomes the official baseline document for an investment once it is approved by the JRC.  This baseline cannot be changed without JRC approval.  The JRC has several investment review responsibilities, depending on the lifecycle phase of the project.  Figure 1 illustrates the investment analysis phases and decision points which are conducted to ensure FAA's critical needs, are satisfied by practical and affordable solutions.

Figure 1: JRC Decisions during the FAA Lifecycle Management Process

The AMS guidance found in the FAST web site provides detailed guidance on investment analysis processes, decisions, and documentation.   The AMS also explains who is responsible for the different investment decisions.

The cover sheet that includes a list of required signatures for the Exhibit 300 PB is included in Appendix B of the AMS policy which can be found on the FAST web page at:  http://fast.faa.gov/docs/exhibit300.doc.

## 1.4   Exhibit 300 Submission Process

As part of the annual budget process FAA submits to OMB and Congress an annual OMB Exhibit 300 for each of its major investments.  The list of which specific FAA investments must submit an Exhibit 300 is coordinated with, and agreed to, annually with OMB.  As part of the annual submission process FAA, in coordination with DOT, has implemented a process to assist FAA investment programs in preparing Exhibit 300s that provide comprehensive and up-to-date information about their investments.  The FAA Value Management Office (VMO) and Subject Matter Experts (SMEs) are available to provide guidance in specific areas of the Exhibit 300.  The VMO maintains an updated list of Exhibit 300 SMEs and other contacts on the FAA Exhibit 300 portal located at https://nase.amc.faa.gov.  The VMO also provides annual training and internal independent scoring of the completed Exhibit 300s.  Prior to being submitted to OMB Exhibit 300s are submitted for internal FAA scoring, review, and approval.

- The OMB Exhibit 300 must be updated at least annually to depict upcoming near term activities identified in the program baseline and report the status of these activities prior to submission of the Exhibit 300 to OMB.

- The baseline information documented in the OMB Exhibit 300 must be consistent with the latest JRC approved baseline.  Changes cannot be made to the OMB Exhibit 300 baseline information without first having rebaseline approval from the JRC.

- The OMB Exhibit 300 would need to be updated to incorporate the results of any JRC decision that has taken place since the last annual or official submission to OMB.

## 1.5   Organization of the Guide

The Exhibit 300 consists of four parts:

Part I: Summary Information and Justification

Part II: Planning, Acquisition and Performance Information

Part III: Operation and Maintenance Investments

Part IV: Planning for E-Gov and Lines of Business Oversight

Part I includes Overview, Summary of Spending, Acquisition/Contract Strategy, Performance, Security and Privacy and EA information for all investments.  Part II includes Alternative Analysis, Risk Management and Cost/Schedule information for investments in the planning, full acquisition or mixed lifecycle phases.  Part III includes information on investments that are completely steady state.  No FAA investments meet the criteria for Part IV.

This guide covers the topics of the Exhibit 300 in the same order as the OMB Exhibit 300 template.  The appendices at the end of this guide include a table that summarizes the relationships between the sections and a list of useful web sites and references as well as more detailed information and guidance on various Exhibit 300 topics.

## 1.6   Scoring Criteria

As part of their evaluation process, DOT and OMB score all Exhibit 300s.  These scores are critical, as they play a large part in agency funding decisions.  Business cases are scored on a scale of one to five, with five being the highest score.  The scores are factored into funding decisions as follows:

- Investments scoring 5 and meeting program requirements are automatically recommended for funding.

- Investments scoring an overall 4, meeting performance goals, and scoring a 4 on the performance based management criteria and security, will be recommended for funding, but will be instructed to continue improvements in the areas identified as needing work.

- Investments scoring 3 or below have the opportunity to improve to a 4 or degrade to a 2 rather easily.

- Investments scoring a 2 or below are not recommended for funding.

In order to develop the overall scores, scores are assigned to each of ten distinct scoring areas.  For the BY09 budget process, those scoring areas are:

- Supports the President’s Management Agenda (PMA)

- Project Management (PM)

- Acquisition Strategy (AS)

- Performance Information (PI)

- Security (SE)

- Privacy (PR)

- Enterprise Architecture (EA)

- Alternatives Analysis (AA)

- Risk Management (RM)

- Performance-Based Management (PB)

The following figure illustrates how the overall scores are computed.

Note: While OMB has identified these ten areas, they have not provided scoring guidance.  Therefore, this document provides scoring guidelines to be used at FAA.  These guidelines are based on a combination of the BY07 guidance and experience with the BY08 OMB Passback.

    - Overall Emphasis Areas

While the business case does receive scores for each of the individual sections, the scores also reflect OMB’s review of the document from a holistic perspective.  The information provided in all the sections must be consistent and complete.  In addition, the most successful business cases clearly demonstrate that the investment is fully aligned with OMB’s goals and objectives.  The following emphasis areas should be clearly addressed throughout the business case.

- Strategic View

  - There should be a clear tie into FAA and DOT strategic goals – this starts with the investment description, and continues with performance goals clearly related to overall mission accomplishment

- Focus on Results

  - Performance Goals and Measure must be clear, measurable, attainable, and address order of magnitude improvements

- Strong Project Management

  - PM must be qualified at the level of the investment

  - Earned Value Management, with variances < 10%

  - Solid corrective action plans if needed

  - Individual PM cannot lead multiple, major investments

- Modernization plans are key for Steady State investments

  - The description should include future plans for meeting the business need

  - Provide details on operational analysis

  - The Alternatives Analysis should describe future plans, and not the decision to make the original investment

- Security is critical

  - Need dates for Security Plan, C&A, and any periodic updates – including planned dates for new modifications/enhancements

  - Security and Privacy information must be consistent

- Risk Management

  - Must demonstrate active risk management

  - Risk Management Plan and Risk Register must be current

- Enterprise Architecture

  - This is tied to the EA assessments

  - Ensure the investment is in the Agency target architecture

  - Investments must be approved by the EA committee

  - Increasing emphasis on component reuse, as shown in SRM and TRM tables

- OMB scores can reflect more than what’s in the Exhibit 300

  - Must ensure consistency with IG Reports, FISMA reports, program documentation, etc.

    - Supports the President’s Management Agenda (PMA)

Scoring Criteria:

5 - This is a collaborative investment that includes industry, multiple agencies, state, local, or tribal governments, uses e-business technologies, and is governed by citizen needs.  If the investment is a steady state investment, then operational analysis is being conducted to identify any need/opportunities for modernization, consolidation, and related e-Gov strategy issues.  If appropriate, this investment is fully aligned with one or more of the President's e-Gov initiatives.

4 - This is a collaborative investment that includes industry, multiple agencies, state, local, or tribal governments, uses e-business technologies though work remains to solidify these relationships.  If investment is in steady state, then operational analysis is being conducted to identify any need/opportunity for modernization, consolidation, and related e-Gov strategy issues but needs work in order to strengthen the analysis.  If appropriate, investment supports one or more of the President's e-Gov initiatives, but is not yet fully aligned.

3 - This is not a collaborative investment though it could be and much work remains to strengthen the ties to the President's Management Agenda.  If this is a steady state investment and no operational analysis is evident, this investment will have a difficult time securing continued or new funding from OMB.  If appropriate, this investment supports one or more of the President's e-Gov initiatives but alignment is not demonstrated.

2 - This is not a collaborative investment and it is difficult to ascertain support for the Agenda Items (AI).  If this is a steady state investment, then no operational analysis is being performed or is planned.

1 - There seems to be no link to the AI and e-Gov strategy.

Critical Success Factors:

- Collaboration – investment should include multiple agencies, state, local, or tribal governments

- Supports the President’s Management Agenda by addressing redundancy or reuse

- Investment is governed by citizen needs

- Clearly supports the Federal Enterprise Architecture, as demonstrated in both the description and the EA tables

- If appropriate, this investment is fully aligned with one or more of the President's e-Gov initiatives

Common Pitfalls:

- No discussion of collaboration or eliminating redundancy

- Doesn’t give context or clearly describe what investment is

- No clear boundaries on investment – the investment seems to have an “identity crisis”

    - Project Management (PM)

Scoring Criteria:

5 - Project is very strong and has resources in place to manage it.

4 - Project has few weak points in the area of PM and agency is working to strengthen PM.

3 - Much work remains in order for PM to manage the risks of this project.

2 - There is some understanding of PM for this project but understanding is rudimentary.

1 - There is no evidence of PM.

Critical Success Factors:

- Project is very strong and has resources in place to manage it.

- Qualified Project Managers are in place and successfully managing the project

- Risk is being managed, and milestones are within acceptable variance

Common Pitfalls:

- The same individual is managing multiple major investments

- The Project Manager is not qualified at the level of the investment

- Contact information is not provided for the project managers

- No clear consistency among the different sections for project management, especially lifecycle costs shown in the Alternatives Analysis, discussion in the Risk Assessment, and the Cost and Schedule Performance sections

- Missing or inadequate EVM information

- Missing or inadequate Operational Analysis information

- Investment has unacceptable cost, schedule, and/or performance variances

- Project managers appear to rebaseline rather than report variances

    - Acquisition Strategy (AS)

Scoring Criteria:

5 - Strong Acquisition Strategy that mitigates risk to the Federal government, accommodates Section 508 as needed, and uses contracts and statements of work (SOWs) that are performance based.  Implementation of the Acquisition Strategy is clearly defined.

4 - Strong Acquisition Strategy that mitigates risk to the Federal government accommodates Section 508 as needed, uses contracts and SOWs that are performance based.  Acquisition strategy has very few weak points which agency is working to strengthen, and the implementation of AS is clearly defined.

3 - Acquisition strategy does not appear to successfully mitigate risk to the Federal government, accommodates Section 508 as needed, much work remains to solidify and quantify the AS, and contracts and SOWs do not appear to be performance based.

2 - Acquisition strategy does not appear to successfully mitigate risk to the Federal government, does not accommodate Section 508, does not appear to use performance based contracts and SOWs, and there is no clear implementation of the acquisition strategy.

1 - There is no evidence of an acquisition strategy.

Critical Success Factors:

- The Acquisition Strategy table is consistent with the Summary of Spending – it identifies contracts over the same period of time, and the dollar amounts are consistent

- There is a clear mapping between contract and project milestones/costs, with project milestones appropriately attributed to the various contracts

- The Acquisition Strategy table is consistent with the project milestones, alternatives analysis, and performance goals, as appropriate

- There is a strong Acquisition Strategy that mitigates risk to the Federal government

- The investment accommodates Section 508

- Contracts and statements of work (SOWs) are performance based

- Implementation of the Acquisition Strategy is clearly defined

Common Pitfalls:

- There is no single, clear acquisition strategy for the investment

- Performance-based contracts are not used, and:

  - There is no plan for transitioning to performance-based contracts

  - There is no adequate justification for retaining current contract type

- Government risk associated with using T&M contracts is not fully addressed

- Contracts/contract types are not tied to the Summary of Spending or Cost and Schedule Performance tables

- Qualification levels are not shown for Contracting Officers, or CO’s are not qualified for the investment

    - Performance Information (PI)

Scoring Criteria:

5 - Performance goals are provided for the agency and are linked to the annual performance plan. The investment discusses the agency’s mission and strategic goals, and performance measures are provided.

4 - Performance goals are provided for the agency and are linked to the annual performance plan. The investment discusses the agency’s mission and strategic goals, and performance measures are provided. Some work remains to strengthen the performance goals.

3 - Performance goals exist but the linkage to the agency’s mission and strategic goals is weak.

2 - Performance goals are in their initial stages and are not appropriate for the type of investment. Much work remains to strengthen the performance goals.

1 - There is no evidence of performance goals for this investment.

Critical Success Factors:

- Performance Goals are:

  - provided for the agency,

  - linked to the annual performance plan, and

  - included in the project discussion of the agency mission and strategic goals

- Performance measures/actual results are tracked across the life of the project.

- There is consistency between all sections of the business case, regarding the performance gap the investment is addressing, how the investment is supposed to close the gap, and how business is actually improving once the investment has been fielded

- The investment will provide/is providing order of magnitude improvements

Common Pitfalls:

- No clear tie to agency strategic goals

- “Goals” are either project milestones or technology measures

- Measures focus on “Outputs” rather than “Outcomes”

- Metrics are vague

  - Avoid terms such as “significant, better, improved”

  - Quantify everything that can be quantified

- “Planned Improvement Goal” isn’t a real improvement

  - OMB is looking for significant, order-of-magnitude improvements

- Investment uses non-performance-based contracts

  - This can limit possibility of real change and improvement

- Metrics aren’t meaningful

- Benefits are not clearly attributable to the specific investment

- Actual results are not provided

    - Security (SE)

Scoring Criteria:

5 - Security issues for the investment are addressed, all questions are answered.  Security detail is provided about the individual investment throughout the lifecycle to include budgeting for SE.

4 - Security information for the investment is provided but there are weaknesses in the information that need to be addressed.

3 - Security information for the investment is provided but fails to address the minimum requirements.

2 - Security information points to an overall Agency Security Process with little or no detail at the investment level.

1 - There is no security information provided for the investment.

Critical Success Factors:

- Security issues for the project are addressed and all questions are answered

- Security controls are tested annually

- Continuity of Operations Plans (COOPs) are tested annually

- For systems in planning, the certification and accreditation (C&A) will be completed prior to putting the system into production

- For operational systems, the C&A was completed using NIST 800-37 guidelines

- For operational systems, the C&A was completed within the last three years, or when the last major modification was fielded, whichever is later

- Security detail is provided about the individual project throughout the lifecycle to include budgeting for IT Security

- Ensure security is planned from the outset and throughout the investment lifecycle

Common Pitfalls:

- Not answering the question about what weaknesses additional funding is needed for

- Not providing dates for when the security plans, C&A and other security activities and controls were completed or descriptions of plans for completing them

- Security and maintenance costs are underestimated:

  - Security costs should include software, government labor, C&A costs for implementation and maintenance of the system, intrusion detection

  - Maintenance costs should not be straight-lined, but should account for increasing costs of maintaining and securing older technologies and interfaces

- Not including or at least describing security costs paid by other organizations that are attributable to this system – for example for C&A processes or periodic testing

- Having C&As that are over 3 years old

    - Privacy (PR)

Scoring Criteria:

5 - Privacy issues for the investment are addressed, all questions are answered, and a privacy impact assessment is provided in appropriate circumstances.  Privacy detail is provided about the individual investment throughout the lifecycle to include budgeting.

4 - Privacy information for the investment is provided but there are weaknesses in the information that need to be addressed.

3 - Privacy information for the investment is provided but fails to address the minimum requirements.

2 - Privacy information points to an overall Agency Process with little or no detail at the investment level.

1 - There is no privacy information provided for the investment.

Critical Success Factors:

- Privacy issues for the project are addressed, and all questions are answered

- The business case identifies a point of contact for Privacy for the investment; this is typically someone who participated in the privacy impact assessment, rather than an agency-level Privacy office

- A privacy impact assessment is provided if the system is new

- The systems listed in the Privacy table are identical to the systems listed in the two Security tables

Common Pitfalls:

- Not providing contact information for the Privacy point of contact

- Using different system names in the Security and Privacy tables, or not including all of the systems that are shown in the two Security tables

- Not providing a PIA if required

    - Enterprise Architecture (EA)

Scoring Criteria:

5 - This investment is included in the Agency EA and CPIC process. Project is mapped to and supports the Federal Enterprise Architecture and is clearly linked to the FEA Reference Models (BRM, PRM, SRM, and TRM). BC demonstrates the relationship of the investment to the business, data, application, and technology layers of the EA.

4 - This investment is included in the agency’s EA and CPIC process. Investment is mapped to and supports the Federal Enterprise Architecture. Investment is clearly linked to the BRM but work is continuing to map the investment to the PRM, SRM, and TRM. BC is weak in demonstrating the relationship of the investment to the business, data, and application, and technology layers of the EA.

3 - This investment is not included in the agency’s EA and CPIC process, was not approved by the agency EA committee, or does not link to the FEA. The business case demonstrates a lack of understanding on the layers of the EA (business, data, application, and technology).

2 - While the agency has an EA framework, it is not implemented in the agency and does not include this investment.

1 - There is no evidence of a comprehensive EA in the agency.

Critical Success Factors:

- The investment is mapped to and supports the Federal Enterprise Architecture and clearly links to the FEA Reference Models (BRM, PRM, SRM, and TRM).

- The SRM table includes all components, and appropriately identifies reuse, names of reused components, and overall percentages

- The TRM table shows the technology used for every component identified in the SRM table, and does not include any items that are not listed in the SRM table

- The investment is not duplicative

- The investment is an agency priority, and is in the transition strategy, if appropriate

Common Pitfalls:

- No clear tie between the investment and the EA

- Investment is Steady State but not included in the Transition Strategy

- No clear mapping to the BRM; performance gap is not clear

- PRM metrics are vague or trivial

- SRM and TRM mappings are incomplete or inconsistent with other Agency investments and/or the Department models

- SRM table does not include percentages allocated to each component

    - Alternatives Analysis (AA)

Scoring Criteria:

5 - AA includes three viable alternatives; alternatives were compared consistently; and reasons and benefits were provided for the alternative chosen.

4 - AA includes three viable alternatives, however work needs to continue to show alternatives comparison, and support must be provided for the chosen alternative.

3 - AA includes fewer than three alternatives and overall analysis needs strengthening.

2 - AA includes weak AA information and significant weaknesses exist.

1 - There is no evidence that an AA was performed.

Critical Success Factors:

- For systems in planning or mixed lifecycle, Alternatives Analysis must demonstrate:

  - Three viable alternatives were considered

  - Alternatives were compared consistently against one another and against the current baseline

  - Alternative chosen provides benefits and reasons

  - The viable alternative does not include status quo

- Measurable benefits—financial and non-financial— are analyzed such as improved mission performance, increased customer satisfaction, reduced costs

- The project appears to be planned well enough to come in on budget

- Alternatives Analysis section provides clear, detailed information on all costs associated with the investment

- The formulation of lifecycle costs include all of the required resources

- All costs should be consistent in Summary of Spending, Alternatives Analysis section, and Cost and Schedule Information section

Common Pitfalls:

- Includes fewer than 3 viable alternatives to closing the performance gap

- Information on baseline is not included

- The selected alternative’s costs do not match the SoS

- A vendor analysis is documented instead of an AA; i.e. comparing the costs of the same new system but with 3 different software vendors

  - A vendor analysis may be appropriate after a more extensive AA has been completed

- Benefits of each alternative, performance gaps cited, and discussion of why a particular alternative was chosen are vague

- Costs in AA are inconsistent with costs in the Summary or Spending, Acquisition Strategy, and/or project milestones

- Alternative Analysis is older than 5 years

    - Risk Management (RM)

Scoring Criteria:

5 - Risk assessment was performed for all mandatory elements and risk is managed throughout the investment.

4 - Risk assessment addresses some of the risk, but not all that should be addressed for this investment.

3 - Risk management is very weak and does not seem to address or manage most of the risk associated with the investment.

2 - Risk assessment was performed at the outset of the investment but does not seem to be part of the program management.

1 - There is no evidence of a risk assessment plan or strategy.

Critical Success Factors:

- Risk assessment was performed during the early planning and initial concept phase of this investment’s life-cycle

- The PM developed a risk-adjusted life-cycle cost estimate and a plan to eliminate,

- mitigate or manage risk

- Risk is being actively managed throughout the investment’s life-cycle

- Risks and risk mitigation strategies and costs are apparent in the project milestones and in the risk database/register as appropriate

Common Pitfalls:

- Risk plan was not done, or is dated

- No description of how costs are risk-adjusted

- No risk assessment against the EA ((EA is not being used to minimize risks of duplication, obsolete or bleeding edge technology, lack of interoperability, etc.)

- Risk register/database is not up to date or does not reflect security or other significant risks identified in IG or other audits/reviews.

    - Performance-Based Management (PB)

Scoring Criteria:

5 - Agency will use, or uses Earned Value Management System (EVMS) that meets ANSI/EIA Standard 748 and investment is earning the value as planned for costs, schedule, and performance goals.

4 - Agency uses the required EVMS and is within the variance levels for two of the three criteria.  Work is needed on the third issue.

3 - Agency uses the required EVMS but the process within the agency is either very new, not fully implemented, or there are weaknesses in this investment’s EVMS information.

2 - Agency seems to re-baseline rather than report variances.

1 - There is no evidence of PB.

Critical Success Factors:

- Agency uses an Earned Value Management System (EVMS) that meets ANSI/EIA Standard 748A

- Project is earning the value as planned for costs, schedule, and performance goals

- Data is consistent across the project milestones, in type, level, etc.

- For Steady State investments, operational analysis (OA) is conducted, and the business case describes how the OA was done, the results of the OA, and how these results are being used in decision-making

- EVM data is being reported periodically as required during the year and the Exhibit 300 data is consistent with the information in the EVM reports.

Common Pitfalls:

- Milestones/costs in sections II.C.9 and III.B.2 are at too high a level and/or cover more than one year at a time

- Milestones in sections II.C.9 do not clearly break out Planning, DME, and O&M milestones though it is clear that the investment is mixed

- It is not clear what portions of the milestones and costs shown in II.C.9 are attributable to which contract and which are being tracked using EVMS

- It appears that the agency is only using the prime contractor’s EVMS data, though there are several contractors involved; there should be a master schedule that is centrally managed by the Project Manager and includes and tracks all activities and costs

- Government FTE costs are not being included in the EVM calculations or the Section II.C milestones.

- The relationship between the costs in section II.C.9/III.B.2, the Summary of Spending, the Acquisition Strategy, and the Alternatives Analysis is not clear

- Totals and subtotals (DME and O&M) are not consistent with the respective Planning and Acquisition and O&M funding plus FTE costs shown in the SoS table (Section II.C)

- Table II.C current baseline planned schedule or cost figures are not consistent with the most recent JRC baseline decision and the related Exhibit 300 Program Baseline document.

## 1.7   General Writing Rules

The best investment may score lower if the reviewer cannot understand the text in its Exhibit 300.  The following are simple grammar and format rules that need to be followed to produce an effective business case.

- Remember Your Audience – The FAA may get a new OMB examiner each year.  At times the examiner may be from outside the FAA (and possibly outside DOT) so it’s important to ensure that the Exhibit 300s are clear, concise and easy to read.  Remember to use guidelines as set forth in the FAA’s Plain Language website.  You can find this guidance at  www.plainlanguage.gov.  Other tips include:

  - Avoid FAA jargon and overly technical explanations - Reviewers main focus is to determine how well projects are being managed.  Limit the amount of technical explanations, and when you do need to go into further details – try to translate technical jargon into common, everyday language.

  - Limit use of multiple acronyms - Reviewers will be familiar with common government acronyms such as FAA, DOT, DoD, and OMB.  For all other acronyms always spell the word out the first time it’s used followed by the acronym in parenthesis.  After the first occurrence just the acronym may be used.

- Keep it simple – Like any government document, the Exhibit 300 must follow the rules of Plain Language.  The goal of Plain Language is to make documents clear and concise.  These guidelines include:

  - Avoid repetition - When repetition occurs, there is a chance that the repeated information is used inappropriately or in a different context.

  - Use active verbs- Reduce the use of passive verbs.

  - Keep sentences short – For clarity keep sentences short.  The longer a sentence, the more likely there will be grammatical errors.  Long sentences can be split into lists or bullets.

  - Use an editing program - Using an editing program such as StyleWriter can help with Plain Language.

- Only answer the question - When answering questions, provide a brief, concise response.  Before providing additional information, check to make sure it is not requested in a later section of the Exhibit 300.

- Ensure your Exhibit 300 includes current information - Programs who have submitted the Exhibit 300 in the past often use the previous years version as a jumping off point.  If this is done, double check each response to make sure you update all of it appropriately (i.e. use current year where appropriate).   In some cases, questions have been broken into smaller parts – so make sure your previous answer has been broken down appropriately.

- Keep section answers consistent - Often times the responses in one section will refer to responses in others.  Make sure that these responses are consistent with one another.  Appendix A includes a crosswalk that compares the various sections.  The answers in the Exhibit 300 must also be consistent with what is reported in the Agency’s Exhibit 53, IT Portfolio.

- Avoid using “Not Applicable”, “Not Available”, or leaving questions blank - If a question cannot be answered because data is not available, explain why the data is not available and provide a date when it will be available.

- Do not “cut-and-paste” answers between different questions - Although many questions are related to another, the same answer will not satisfy two different questions.

## 1.8   Lifecycle Terminology

It is very important to clearly identify the investment phase for which funding is being requested.  Investments need to briefly, but concisely, describe the phase, useful segment(s), duration and scope for which funding is being requested.

Lifecycle:  An investment’s total lifecycle is the duration of the investment encompassing the planning, acquisition, and maintenance phases until the investment is discontinued, disposed of, and/or replaced.

Phase:  A part of the investment that usually reflects its current status such as Planning, Full Acquisition, Operations and Maintenance or Mixed Lifecycle.

Useful Segment:  A useful segment is an economically and programmatically separate component of an investment, as narrow in scope and brief in duration as practicable.  It provides a measurable performance outcome for which the benefits are derived independently and separately of other useful segments.  An investment can consist of just one useful segment or can include several useful segments.

Milestones:  Milestones are specific activities, deliverables or tasks that have a beginning and an end and are part of a useful segment.

Below is a depiction of the relationship between an investment’s total lifecycle, its phases, useful segments, and milestones.

| Investment’s Complete Lifecycle |
| --- |
| Planning Phase | Acquisition (DME) Phase | Maintenance (Steady-State) Phase |
| Planning Useful Segment #1A: 10/01/2004-05/30/2005 | Acquisition/Development Useful Segment #1B: 06/01/2005-09/30/2008 Milestone 1 Milestone 2 Milestone 3 Milestone 4 | Steady-State Useful Segment #1C: 01/15/2007-09/30/2012 |
| Planning Useful Segment #2A: 04/01/2004-09/30/2005 | Acquisition/Development Useful Segment # 2B: 10/01/2005-05/30/2007 Milestone 1 Milestone 2 | Steady-State Useful Segment #2C: 06/01/2007-12/30/2010 |
| Planning Useful Segment #3A: 10/01/2005- 06/30/2006 | Acquisition/Development Useful Segment #3B, 07/01/2006-09/30/2010 Milestone 1 Milestone 2 Milestone 3 | Steady-State Useful Segment #3C, 10/01/2010-09/30/2012 |

Table 2: Sample Life-Cycle Phase, Segment, and Phase Relationships

# 2.  Part I: Summary Information and Justification

## 2.1   Introduction

This section includes the investment’s overview, total estimated lifecycle costs, acquisition and contract strategies, performance goals, security, and enterprise architecture information for the business case.  Programs are required to provide information for all these sections for all capital asset investments.

## 2.2   Section A: Overview

1.  Date of Submission:

This field is updated each year.  Enter the date the business case will be submitted to OMB.

2.  Agency:

Enter “Department of Transportation (DOT)”

3.  Bureau:

Enter “Federal Aviation Administration (FAA)”

4.  Name of this Capital Asset:

Use the full name of the investment followed by its acronym in parentheses.  Please note that if this investment was submitted as part of the previous budget year’s portfolio, the name of the investment should NOT change, per OMB direction.

5.  Unique Project (Investment) Identifier (UPI):

For IT investments enter the UPI.  The UPI depends on the investment’s primary strategic goal mapping, the type of IT investment (i.e., financial, infrastructure, grants management, enterprise architecture, or other), and the primary line of business and sub-function.  The code is based on, and must be consistent with, the responses to several specific Exhibit 300 sections.  The Department's eCPIC tool automatically generates the UPI code.  If you have questions regarding the UPI code or need additional information, contact the Value Management Office.

6.  What kind of investment will this be in <budget year>?

The status is based on the investment’s status for the current budget year for which funding is being requested.  For example, if the investment will be fully steady state in budget year 2009 but still has development, modernization and enhancement (DME) activities in fiscal year 2008 the program would select mixed lifecycle as the answer.

Ensure your response is consistent with the funding request documented in the Budget Year (BY) column of the Summary of Spending (SoS) table as well as the rest of the business case.  For example, if Operations and Maintenance has been selected as the response to this question OMB would not expect to see an Acquisition funding request in the SoS table for the current budget year.

The following is an explanation of the terms.

- Planning: Funds are being expended for preparing, developing or acquiring the information to design and evaluate the project (e.g., market research, engineering or design studies, prototypes, full cost-benefit studies, accessibility studies, security studies). Planning can be considered a useful segment and depending on the nature of the project, one or more planning segments may be necessary.

- Full Acquisition: Funds are being expended on acquiring hardware, software or DME activities.

- Operations and Maintenance: Funds are being expended for the maintenance of an operational system or module (system has been through at least one full budget cycle).

- Mixed Lifecycle: Mixed lifecycle investment means an investment that has development, modernization, and/or enhancement (DME) aspects as well as steady-state aspects. For example, a mixed lifecycle investment could include a prototype or module of a system that is operational with other modules still in development.

- E-Gov/LoB Oversight:  FAA does not have any investments that fall within this category.

7.  What was the first budget year this investment was submitted to OMB?

If an Exhibit 300 went to OMB and was approved for the previous budget year, then enter the first year the business case was submitted to OMB.  If the project did not submit an Exhibit 300 to OMB last year, then enter the current budget year.

8. Provide a brief summary and justification for this investment, including a brief description of how this closes in part or in whole and identified agency performance gap.

Start with a brief, concise description of the program and the performance gap it addresses.  This includes a succinct and clear description of what the investment is, why it is needed (performance gap it is addressing) and its status (select, control, evaluate).  If the investment is mixed lifecycle state the status of each segment or module.

Subsequent paragraphs should briefly describe the DOT and FAA missions that are supported by the investment.  Be sure to explain the relationship between the performance gap and the DOT and FAA missions.

Briefly describe the various investment segments including the CPIC and lifecycle phase of each segment.  Identify which segments are covered by this year’s funding request.  Ensure that information included in this response is consistent with responses in other sections of the business case.

9.  Did the Agency’s Executive/Investment committee approve this request?

The answer is ‘yes’ for all projects that have JRC or JRC subordinate board approval (if delegated by the JRC), and were given authorization to proceed to the next phase.	  This would include both the JRC Initial and Final Investment Decisions.

9. a.  If yes, what was the date of this approval?

Enter the date of the JRC decision.  Since this question is only asking for the program to provide a date, make sure the response to question 8 includes a brief sentence stating whether the JRC approval date was for the Initial or Final investment decision.

10.  Did the Project Manager review this Exhibit?

The response to this question should always be ‘yes’.  The Project Manager (PM) must review the Exhibit 300 business case and is responsible for fully understanding the content of the Exhibit 300.

11.  Contact information of Project Manager?

Each project must have a project manager; enter the name and contract information here.

12.  Has the agency developed and/or promoted cost effective, energy-efficient and environmentally sustainable techniques or practices for this project?

Select ‘yes’ or ‘no’.  Both IT and non-IT investments are required to answer this question.

12.a.  Will this investment include electronic assets (including computers)?

Select ‘yes’ or ‘no’.  Both IT and non-IT investments are required to answer this question.

12.b.  Is this investment for a new construction or major retrofit of a Federal building or facility?

Select ‘yes’ or ‘no’.  Both IT and non-IT investments are required to answer this question.

12.b.1.  If “yes”, is an ESPC or UESC being used to help fund this investment?

If the response to Question 12.b is ‘yes’ then answer this question.

12.b.2.  If “yes”, will this investment meet sustainable design principles?

If the response to Question 12.b is ‘yes’ then answer this question.

12.b.3.  If “yes”, is it designed to be 30% more energy efficient tan relevant code?

If the response to Question 12.b is ‘yes’ then answer this question.

13.  Does this investment directly support one of the PMA initiatives?

VMO guidance states that most FAA investments do not support PMA initiatives therefore the standard response for this question would be ‘no’.  If a program thinks their investment does support an E-Government initiative, please contact your VMO representative to discuss.

13.a.  Briefly describe how this asset directly supports the identified initiative(s)?

VMO guidance states that most FAA investments do not support PMA initiatives therefore this question should be left blank.

14.  Does this investment support a program assessed using the Program Assessment Rating Tool (PART)?

On July 16, 2002, OMB issued a memo to the heads of federal department and agencies describing a new approach being used by OMB to assess program performance.   OMB is now using a Program Assessment Rating Tool (PART) to complete a formal evaluation of federal programs and plans to apply this detailed analysis to a percentage of federal programs every year.  The OMB memo describes the purposes of the PART as:

“The program assessment effort presents an opportunity to inform and improve agency GPRA plans and reports, and establish a meaningful systematic link between GPRA and the budget process.  The memo defines the PART approach as follows, “The PART is a diagnostic tool that relies on objective data to inform evidence-based judgments to assess and evaluate programs across the wide range of issues related to performance.”

Use the most recent review that applies to the investment.  If you are unsure whether your investment supports a program reviewed under PART, contact the Value Management Office.

The following reviews have been completed to date:

1)  The RED account – in 2003

2)  The Airport Improvement Grants – in 2002

3)  Air Traffic Services Operations (OPS funded only) – in 2003

4)  Facilities and Equipment (F&E) – in 2004

5)  Aviation Safety

14.a. If “yes”, does this investment address a weakness found during a PART review?

Use the most recent review information that applies to the investment.

14.b.  If “yes”, what is the name of the PARTed program?

Use the most recent review information that applies to the investment.

14.c.  If “yes”, what rating did the PART receive?

Use the most recent review information that applies to the investment.

15.  Is this investment for information technology?

Information Technology, as defined by the Clinger-Cohen Act of 1996, Sections 5002, 5141, and 5142, means any equipment or interconnected system or subsystem of equipment that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange transmission, or reception of data or information.  For purposes of this definition, equipment is “used” by an agency whether the agency uses the equipment directly or it is used by a contractor under a contract with the agency that (1) requires the use of such equipment or (2) requires the use, to a significant extent, of such equipment in the performance of a service of the furnishing of a product.  Information Technology includes computers, ancillary equipment, software, firmware and similar procedures, services (including support services), and related resources.  It does not include any equipment that is acquired by a Federal contractor incidental to a Federal contract.  An FAA investment that is part of the NAS is usually considered IT.  For example, the En Route Automation Program (ERAM) is categorized as an IT investment, whereas the Power Systems Sustained Support (PSSS) is not.

16.  What is the level of the IT Project?

The level of an investment is determined by the project's scope and dollar threshold.

| Level | Project Type | Dollar Threshold |
| --- | --- | --- |
| 1 | A division, bureau or agency project | Up to $20 M |
| 2 | A cross-cutting project or agency-wide system integration project across the Department | Up to $100M |
| 3 | Large, inter-governmental or government-wide complex, high risk IT project (e.g., e-Gov or President’s Management Agenda initiative, mission critical function, or high interest project) | Greater than $100M |

17.  What project management qualifications does the Project Manager have?

The PM must be validated at the same level as the investment.  Select the most appropriate response from the list:

- Project manager has been validated as qualified for this investment.

- Project manager qualification is under review for this investment.

- Project manager assigned to investment, but does not meet requirements.

- Project manager assigned but qualification status review has not yet started.

- No project manager has yet been assigned to this investment.

18.  Is this investment identified as “high risk” on the Q4 – FY 2007 agency high risk report?

Each year the Office of Management and Budget compiles a list of high-priority IT projects.  The intent is for agencies to focus on the execution and performance of their projects.  If your program is on this list please select ‘yes’ as the response to this question.  If you are not sure your program is on the list, contact your VMO representative.

19.  Is this a financial management system?

Select ‘yes’ or ‘no’.

Financial management systems are subject to additional regulation and scrutiny.  Financial Management Systems are financial systems and the financial portion of mixed systems that support the interrelationships and interdependencies between budget, cost and management functions, and the information associated with business activities.  Financial systems are comprised of one or more applications that are used for any of the following:

- Collecting, processing, maintaining, transmitting, and reporting data about financial events;

- Supporting financial planning or budgeting activities;

- Accumulating and reporting cost information; or

- Supporting the preparation of financial statements.

Note: Ensure consistency between the responses for questions 19, 19.a, 19.a.1, 19.a.2, 19.b and the information that has been included in the Exhibits 52 and 53

19.a.  If “yes”, does this investment address a FFMIA compliance area?

Select ‘yes’ or ‘no’.

The Federal Managers Financial Integrity Act of 1982, Chief Financial Officers Act of 1990 and Federal Financial Management Improvement Act of 1996 require accountability of financial and program managers for financial results of actions taken, control over the Federal government's financial resources, and protection of Federal assets.  The Office of the CFO prepares the FFMIA compliance reporting for financial management systems.  Contact the VMO regarding questions.

19.a.1.  If “yes”, which compliance area?

Enter the compliance area.

19.a.2.  If “no”, what does it address?

Enter the requested information.

19.b.  If “yes”, please identify the system name(s) and system acronym(s) as reported in the most recent financial systems inventory update required by Circular A-11, Section 52.

Enter the requested information.

20.  What is the percentage breakout for the total <budget year> funding request for the following?  (Hardware, Software, Services, Other)

This question is asking the program to breakout the funding request for the budget year for which funding is being requested.  The percent should be whole numbers and total 100%.

21.  If this project produces information dissemination products for the public, are these products published to the Internet in conformance with OMB Memorandum 05-04 and included in your agency inventory, schedules and priorities?

The management of agencies' public websites should be in compliance with Federal information resource management law and policy and is part of promoting more citizen centered government.  OMB Memo 05-04 provides the policies for Federal Agency Public Websites and can be located at: http://www.whitehouse.gov/omb/memoranda/fy2005/m05-04.pdf.

22.  Contact information of individual responsible for privacy related questions?

Enter the name and contract information for the FAA individual that is responsible for privacy related questions.

23.  Are the records produced by this investment appropriately scheduled with the National Archives and Records Administration’s approval?

A “records schedule” identifies records as either temporary or permanent.  All records schedules must be approved by NARA.

- A records schedule provides mandatory instructions for the disposition of the records (including the transfer of permanent records and disposal of temporary records) when they are no longer needed by the agency.  As part of the ongoing records lifecycle, disposition should occur in the normal course of agency business.

- All Federal records must be scheduled (44 U.S.C. 3303) either by an agency schedule or a General Records Schedule (GRS).

- The GRS include records relating to civilian personnel, fiscal accounting, procurement, communications, printing, and other common functions.

## 2.3   Section B: Summary of Spending

The term Total Lifecycle Costs refers to the overall estimated cost, both government and contractor, for an alternative over the time period corresponding to the life of the program, including direct and indirect initial costs plus any periodic or continuing costs of operation and maintenance.  Lifecycle costs include:

- Planning costs include costs for mission analysis and investment analysis.  At FAA, planning comprises all efforts leading up to the final investment decision by the JRC.  It generally includes all activity that occurs prior to the contract award for development.

- Acquisition costs include costs for solution implementation (acquisition, development, testing and deployment).

- Operations and Maintenance costs are steady-state costs, which include costs for routine maintenance and technology refresh.

- Government FTE costs include both program and field personnel.

The funding requests documented in this table reflect the current CIP funding with out-years adjusted to match the current JRC approved program baseline total.  Although the estimated annual funding amounts may change in the Summary of Spending (SoS) table, the total estimated program funding must agree with the latest JRC approved cost baseline.

The top half of the SoS table does not include government FTEs and should reconcile with the ATO-F parameter sheets in SPIRE.  Government FTE (PCB&T) costs are provided separately at the bottom of the SoS table and should include both program and field support.

1.  Provide the total estimated lifecycle cost for this investment by completing the following table.  All amounts represent budget authority in millions and are rounded to three decimal places.  Federal personnel costs should be included only in the row designated “Government FTE Cost”, and should be excluded from the amounts shown for Planning, Full Acquisition, and Operations/Maintenance.  For Federal buildings and facilities, lifecycle costs should include long term energy, environmental, decommissioning, and/or restoration costs.  The costs associated with the entire lifecycle of the investment should be included in this report.

The SoS table represents the total cost of ownership for the selected alternative, regardless of source of funding or budget account.  Summary program costs are to be provided by year and phase (planning, acquisition, and maintenance), and must be risk adjusted.  Government FTE costs should NOT be included in the costs shown in the “TOTAL” row or in the rows above it.  FTE costs and numbers are shown in separate rows at the bottom of the SOS table.

| Column 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Life-Cycle Stage | PY-1 and Earlier | Prior Year (PY) 20XX-2 (Op Plan) | Current Year (CY) 20XX-1 (Pres Bud) | Budget Year (BY) 20XX OMB Sub | BY+1 20XX+1 | BY+2 20XX+2 | BY+3 20XX+3 | BY+4 & Beyond | Total |
| Planning: |  |  |  |  |  |  |  |  |  |
| Acquisition: |  |  |  |  |  |  |  |  |  |
| Subtotal Planning & Acquisition: |  |  |  |  |  |  |  |  |  |
| Operations & Maintenance: |  |  |  |  |  |  |  |  |  |
| TOTAL: |  |  |  |  |  |  |  |  |  |
| Government FTE Costs should not be included in the amounts provided above. |
| Government FTE Costs: |  |  |  |  |  |  |  |  |  |
| Number of FTE represented by Costs: |  |  |  |  |  |  |  |  |  |

Table 3: Summary of Spending Table

Budgetary Resources

In the SoS table, "Budgetary Resources" means the amount available to enter into new obligations and to liquidate them; including direct spending and obligation limitations (see OMB A-11 or contact Budget Office if the project line item is subject to statutory limitations on obligations).

For the Past Year and Prior always refer to the appropriated amounts received by the program. During the period the Exhibit 300 is being developed for OMB, the Current Year will equal the President's Budget request until an appropriations bill is enacted and signed by the President.  Past year F&E appropriation amounts by project can be found in the Capital Investment Plan.

The Budget Year amount should be consistent with the budget request FAA makes to the Department and OMB.  ATO Finance develops the F&E budget within the framework of the Capital Investment Plan (CIP).  Programs should keep in touch with ATO Finance and the CFO Budget Office to ensure they have the latest figures.

F&E resources beyond the Budget Year should be consistent with amounts found in the CIP, which should adjust out year amounts for current or past year resource changes in order to maintain consistency with the JRC approved baseline.

The Operations budget is developed within each line of business.  Operations funding should be also be consistent with request levels to OMB.

Any project collaborating with another agency or agencies (such as E-Gov projects) should include the funding from those collaborators.  See OMB A-11 Section 300 for more guidance on collaborative projects.

Government FTE Costs:

For the Government FTE costs, use a cost-per-FTE commensurate with the grade level of the government employee(s) performing the work. The budget office has cost per FTE for each Line of Business organization and other inflation rates for formulating payroll resources.  Multi-agency initiatives must include FTE costs for all partnering agencies.  Government FTE Costs in the Summary of Spending include:

- All government personnel considered direct and indirect labor in support of the investment.

- The investment management IPT (service team) and any other government effort (e.g., programming effort for part of the overall investment, development effort) that contributes to the success of the investment.

- Salary costs plus the fringe benefit rate of 32.8%.

- Costs of internal FTEs supporting the IT investment.  At a minimum include the costs of those FTEs that spend more than 50% of their time supporting the investment. Persons working on more than one investment, whose contributions for all investments would exceed 50% of their overall time, should have their specific time allocated to each investment.

# Note:  The totals for Planning, Acquisition, O&M and FTE costs in the SOS table should match the subtotals and totals in Part II.C and III.B and be consistent with the JRC APB and SPIRE data.

2.  Will this project require the agency to hire additional FTE’s?

Select ‘yes’ or ‘no’.

Indicate whether the investment will require additional government FTEs.

2.a.  If “yes”, how many and in what year?

If the response to question 2 is ‘yes’, then enter the number of additional FTEs the investment plans to hire and in what year(s).

3.  If the Summary of Spending has changed from the FY2007 President’s budget request, briefly explain those changes.

Describe any changes since the previous budget year request (rescissions, rebaseline, etc).  Describe any requirements or issues that cause spikes or lumpiness in the spending curve.

## 2.4   Section C: Acquisition/Contract Strategy

Per OMB’s Capital Program Guide dated June 2006, the use of competition, performance-based specifications, financial incentives and earned value are tools to reduce the risk to the government.  Of particular important is the use of performance-based contracts.  These contracts focus on results, mitigate risk to the government and are the required standard for major acquisitions.

The Acquisition Strategy, which is part of the Integrated Strategy and Planning (ISP) document, should also make sure that earned value requirements are incorporated into all FAA contracts that are equal to, or greater then, $10M.  Additionally, OMB wants to see programs accommodate Section 508 as needed.

If an investment is not using performance-based contracts and Statements of Works (SOWs), the Acquisition Strategy should clearly state the reasons that prompted use of other than performance-based contracts and SOWs and how the risk to the government will be mitigated.  Implementation of the Acquisition Strategy must also be clearly defined.

Note:  Ensure the information in this section is consistent with the ISP document.

1.  Complete the table for all (including all non-Federal) contracts and/or task orders currently in place or planned for this investment.  Total Value should include all option years for each contract.  Contracts and/or task orders that are completed do not need to be included.

In the Contracts/Task Orders table OMB is requiring that investments include both F&E and O&M contracts that are currently being executed or will be executed sometime in the future.  This includes any contracts or task orders that are in the planning phase but have not yet been awarded.  There is no need to list past/expired contracts however the total F&E and O&M contract dollars documented in this table should be consistent with the SoS and II.C.9 tables.  Similar contracts can be rolled up or consolidated (i.e. support contracts, field contracts) however contracts over 10% of the program value should be reported as separate lines.

Performance-Based Contracts:

Performance-based acquisition is a collective responsibility that involves representatives from budget, technical, contracting, logistics, legal, and program offices [Source: Seven Steps to Performance Based Services Acquisition].  This means that contracts are integrally tied to cost, schedule and technical performance and have documented, systematic processes for program management, including:

- Integrating program scope, schedule and cost objectives,

- Establishing a baseline plan for accomplishing program objectives, and

- Using earned value techniques for performance measurement during program execution.

Performance based contracts are required for both F&E and O&M activities.  The intent is for agencies to describe their needs in terms of what is to be achieved, not how it is to be done.

Competitively Awarded Contracts:

“Performance-based contracting" means structuring all aspects of an acquisition around the purpose of the work to be performed with the contract requirements set forth in clear, specific, and objective terms with measurable outcomes as opposed to either the manner by which the work is to be performed or broad and imprecise statements of work [Source: FAR 2.101].

If a contract was competitively awarded but some of subordinate task orders were not (such as SETA II), then the program should answer ‘yes’ in the “Competitively Awarded” column of the Contracts/Task Orders table and  provide a brief explanation in Section I.C.2

Table 5: Contracts/Task Orders Table

Ensure that the contracts listed in this table meet the following criteria:

- OMB expects that contracts awarded in 2006 and later will be performance-based, include Earned Value Management (EVM) requirements (when applicable), be competitively awarded, and be Firm Fixed Price (FFP).

- If the program states the investment is in the planning phase, OMB would expect to see a list of contracts that the program plans to award.

- For future DME contracts indicate that the program is planning to use performance-based, FFP contracts with EVM requirements.

- For future O&M contracts indicate that the program is planning to use performance-based and FFP contracts.

- Include planned future contracts for the rest of the investment.  At a minimum include one line for future DME contracts and one line for future O&M contracts.

2.  If earned value is not required or will not be a contract requirement for any of the contracts or task orders above, explain why.

If any of the contracts listed in the Contracts/Task Orders table do not meet the OMB criteria the following information should be included in the response:

- If the program states the investment is in the planning phase and the planned contracts have been listed in the Contracts/Task Orders table, briefly explain what those contracts are for (i.e., planning activities, analyses, program management support, etc.)

- If some contracts are partly performance-based or have performance-based characteristics, brief explanations should be provided in I.C.2.  For example, if a contract does not contain performance-based language but the payments are tied to deliverables and milestones this should be noted in I.C.2.

- If some contracts do not include EVM requirements briefly explain why.  For example, the contract is less then or equal to the $10M FAA threshold for including EVM as a contract requirement OR the contract is for operational activities that do not require EVM.

- For those contracts that don’t include EVM requirements explain how the program is monitoring cost, schedule and performance at the program level.  It is not sufficient to just state the program is monitoring cost, schedule and performance.  The program must briefly explain how.  Briefly describe the procedures and management processes that are in place for mitigating the risks.

- If some of the contracts are not performance based and using FFP briefly explain why.  Indicate that the program is planning to maximize the use of FFP contracts instead of just stating that they are one of the contract types that will be considered.

- If any of the contracts are not competitive briefly explain why and describe any plans to increase the use of competition in future contracts.

- Describe any progress made to date in becoming EVM compliant.

OMB expects that an Earned Value Management System (EVMS) will be used for all DME activities and that earned value will be applied to both government (FTE) and contractor efforts.  This includes:

- Prototypes during the planning phase

- DME activities during the acquisition phase, and

- DME activities during the steady state phase including tech refreshes

Note:  Ensure the information in this response is consistent with the information provided in Section II.C.

3.  Do the contracts ensure Section 508 compliance?

Indicate whether the contracts comply with Section 508.

- Yes – the investment complies with all Section 508 standards

- No - the investment does not comply with all Section 508 standards

- N/A - the 508 standards are not applicable to the investment

Per the 508 SME the program determines whether to select ‘No’ or ‘N/A’.  Ensure the response has been approved by the Section 508 SME.

3.a.  Explain why?

OMB is requiring investments to clarify the answer to question 3.  If the answer is ‘yes’ to question 3, ensure the appropriate standard text is used and that the response has been approved by the Section 508 SME.

4.  Is there an Acquisition Plan which has been approved in accordance with agency requirements?

The Acquisition Plan is part of the FAA’s ISP document.  Ensure that the information in the Acquisition Plan is consistent with the responses to questions I.C.1 and I.C.2.

4.a.  If “yes”, what is the date?

Enter the date.

4.b.  If “no”, will an Acquisition Plan be developed?

Select ‘yes’ or ‘no’.

4.b.1.  If “no”, briefly explain why.

Provide the required explanation.

## 2.5   Section D: Performance Information

Developing annual performance goals for investments based on the agency mission allows management and OMB to clearly see that the investment has achieved its intended goals.  The FAA, as a whole, needs to improve its performance measurement indicators and the linkage between IT investments and a program’s performance goals.  For future years, programs are encouraged to develop performance goals and measures that demonstrate support for the agency’s mission and including strategic outcomes.  In cases where more than one investment contributes to an outcome (such as increased safety or reduced delays), it is important to attribute the appropriate portion of the outcome improvement to each contributing investment.

At a minimum the Exhibit 300 should include performance goals up to and including one year beyond the budget year.  Programs may provide goals for the entire phase or useful segments for which JRC funding has been approved.

In general, performance goals previously reported to OMB must be included in subsequent Exhibit 300 submissions and not eliminated or changed unless such changes are part of a JRC-approved rebaseline.  If they are approved as part of a rebaseline, the reasons (such as risk adjustments) for the change and the fact that the change is part of an approved rebaseline need to be clearly reported in appropriate Exhibit 300 sections.  Goals from past years should not be deleted until the actual performance results have been reported to OMB at least once in the Exhibit 300 officially submitted in September.

Helpful Tip:  The Baseline indicates “where you are today” (for new investments) or “where you were when you first began” (for steady-state investments).  This is the basis for determining increases or decreases in performance.  Planned is the targeted performance level expressed in a metric that can be measured and compared to the actual performance.  Actual is tangible performance results that occurred as the system was used.

Table 1

Most FAA investments can drop this table from their Exhibit 300.  However, if the program decides to keep the table in their business case the goals and objectives should demonstrate incremental progress toward the long term goals and objectives described in the FAA and DOT strategic plans through at least FY 2005.

Table 6: Performance Goals – Table 1

- Column #1 Fiscal Year: Develop and report performance goals through at least FY 2005.  Performance goals should not be dropped from the table unless the actual performance has been reported to OMB for one full year after the goal was first submitted to OMB.

- Column #2 Strategic Goal(s) Supported: Indicate which DOT Strategic Plan and FAA’s Flight Plan goals the investment supports.  Ensure that the goals are consistent with the information provided in other sections of the business case.

- Column #3 Performance Measure:  Enter the metric the program will use to measure performance.  This metric will measure planned versus actual performance for each performance goal.  To the maximum extent practicable, this should be a quantitative metric for the units that are being measured (for example: the number of delays per year, the number of accidents per year, the number of errors per year, customer complaints per year, hours required to complete an activity/task, or cost of something in dollars, etc).  The metric must be consistent with the information documented in columns 4, 5 and 6.

- Column #4 Actual Baseline (from previous year): Enter the baseline for each performance goal.  This is the base metric the program will use to measure progress.

- Column #5 Planned Performance Metric (target): Enter the improvement metric.  This is the improvement the investment expects to gain in a fiscal year.

- Column #6 Performance Metric Results (actual): For the current year, state the mid-year progress (if available), progress projected to the end-of-year, or state when performance will be measured.  For future years, when the information is not known, provide an estimated date when it will be available.

Table 2

All IT investments that include DME activities for 2005 and beyond must use Table 2 and are required to map to the Federal Enterprise Architecture (FEA) Performance Reference Model (PRM).

The purpose of the table is to measure the success of IT investments and their impact on an agency’s strategic mission and objectives.  The PRM includes detailed guidance about how to develop realistic performance goals and incorporate measurement indicators into this table.  Use Table 2 and the PRM to identify and link the internal business components and the achievement of business and customer-centric outputs.  The PRM structure is designed to clearly express the cause–and-effect relationship between inputs and outputs. This “line of sight” is articulated through the use of the Measurement Area, Category, Grouping, and Indicator hierarchy.

Mission goals listed in the DOT Strategic Plan and FAA Flight Plan are the ultimate strategic outcomes that FAA investments support, yet it may be appropriate to name some subsidiary or lesser mission objective or sub-objective that the investment supports.  Build on what you have from last year and review the DOT Strategic Plan and FAA Flight Plan for the appropriate outcomes your investment supports.  The “Baseline,” “Planned Improvement to Baseline,” and “Actual Results” columns should contain numerical data showing the status of the measurement indicator at the beginning of the fiscal year, the desired target level, and the indicator at the end of the fiscal year, respectively.  If there is no data for the measurement, indicate in the data field why the data is not yet collected, explain how the data will be collected over the course of the upcoming fiscal year, and provide an estimated date by which the required data will be available.  It is expected that in many cases, benefits and their related performance goals will not be realized until an investment is at least partly operational.

Please note that new investments that have not yet completed a final JRC investment decision need only provide estimated goals.  In most cases it will be difficult during the preliminary planning phases of these new initiatives to quantify these goals.  Therefore, Table 2 should show the types of performance improvements that are expected and provide an estimated date for when the information to quantify baselines and performance improvements will become available.

Note:  Ensure there is consistency between these goals and strategic goals and objectives described in other sections of the business case.

Table 7: Performance Goals – Table 2

- Column #1 Fiscal Year: Develop and report performance goals starting with FY05 through at least the BY+1.  Table 2 should include all goals that were reported in last year’s submission, plus goals for future years up through one year beyond the budget year.  Performance goals should not be dropped from the table unless the actual performance has been reported to OMB for one full year after the goal was first submitted to OMB.

- Column #2 Measurement Area: This is the highest level of the PRM framework capturing aspects of performance at the output levels. This column is directly linked to the performance objectives established at the agency and program levels. All major IT investments requesting new DME funding for 2005 and beyond must identify at least one goal in each of the four Measurement Areas: Mission and Business Results, Customer Results, Processes and Activities, and Technology.  Table 2 must include at least one performance goal for each measurement area for each fiscal year.  Use the same goals each year to demonstrate the intended value of the investment over time.

- Column #3 Measurement Grouping: There are categories within each measurement area that describes the attribute or characteristic to be measured.  Within each Category there are further subcategories call Groupings.  Enter the correct Grouping for the performance goal.

- Column #4 Measurement Indicator: The specific metric that will be used to track successful performance (e.g., number and/or percentage of customers satisfied) tailored for a specific BRM Line of Business or Sub-function, agency, program, or IT initiative.

- Column #5 Baseline:   If there is an existing system what is the current baseline metric for the performance goal.  If there is no current baseline enter zero.

- Column #6 Planned Improvement to the Baseline: What improvement to the baseline metric does the investment expect to gain?   Additionally, to demonstrate linkage of specific performance improvement goals to the DOT Strategic Plan and FAA Flight Plan goals, the names of the appropriate DOT/FAA goals that are supported by a performance improvement may be included in the “Planned Improvement to the Baseline” Column.

- Column #7 Actual Results: Enter the actual results of the performance goal.  If there are no actual results enter the date the investment expects to have the actual results.

## 2.6   Section E: Security and Privacy

In order to successfully address this area of the Exhibit 300, each question below must be answered at the investment (system/application) level, not at a program or agency level.  Simply referring to security plans or other documents is not an acceptable response.  For IT investments under development, security planning must proceed in parallel with the development of the system to ensure that IT security requirements and life-cycle costs for the investment are identified and validated.  All IT investments must have up-to-date security plans and be fully certified and accredited prior to becoming operational.  Anything short of a full certification and accreditation indicates that IT security weaknesses remain, need to be remedied and is therefore not adequate to ensure funding for the investment.  Additionally, to ensure that requests for increased IT security funding are appropriately addressed and prioritized, the agency must identify: 1) current costs; 2) current IT security performance gaps; and 3) how the funding request will close the performance gaps.  This information must be provided to OMB through the system’s security Plans of Action and Milestones (POA&M) and tied to the IT Exhibit 300 through the unique project identifier.

Programs must ensure their Federal Information Security Management Act (FISMA) review, POAM information and the Exhibit 300 are consistent.  Programs need to clearly state that there is adequate funding to implement corrective actions.  Certification and Authorization (C&As) must be completed in a timely manner and wherever possible identified in table II.C.9 as a planned milestone.

New initiatives that have not received a final investment decision by the JRC should address each question by providing information about future plans to complete security activities and documentation, which regulations will be complied with, and which methodologies will be used as appropriate.  If exact dates for completion of security activities or documentation cannot be provided, an estimated date for when the information will be available should be provided.

The information presented in Table 3 (Systems in Planning) and Table 4 (Operational Systems) should match the information provided in the Privacy Table.  Systems included in Table 4 must be included on the FAA’s FISMA system inventory and should be easily referenced in the inventory.

1.  Have the IT security costs for the system(s) been identified and integrated into the overall costs of the investment?

Select ‘yes’ or ‘no’.

Security costs are referenced in terms of a percent of a program’s funding request for the budget year as documented in the Summary of Spending table.

IT security includes such costs as:

- Development of the security architecture

- Development, review and testing of security plans, disaster recovery plans, contingency plans

- Deployment of security-related hardware and software

- Vulnerability assessments and penetration testing

- Development of security policies, security training; security program assessments

- Physical security

- Background checks for Federal and contract IT personnel

1.a.  If “yes”, provide the “Percentage IT Security” for the budget year.

Provide a percentage using whole numbers plus two decimal places.  This percentage includes the contractor’s security costs being charged to the investment.

2.  Is identifying and assessing security and privacy risks a part of the overall risk management effort for each system supporting or part of this investment?

Select ‘yes’ or ‘no’.

For IT investments security risks must be included in the Risk Management Plan and Risk Matrix.

3.  Security table for planned systems.

If a program is still in the planning phase, this section should describe plans for completing a full C&A prior to becoming operational and provide an approximate date for SCAP approval.

Completion of a SCAP or SCAP update should be included as a milestone in table II.C.9.

Note:  Mixed lifecycle investments must complete both the Systems in Planning and Operational Systems tables.

Table 8:  Systems in Planning – Security Table

4.  Security table for operational systems.

Enter the name of each investment system, whether the system is operated by FAA or contractor personnel and the risk impact level.

For the FAA a C&A consists of the Security Certification and Accreditation Plan (SCAP) process. Indicate whether or not the C&A was completed using NIST 800-37 guidelines and enter the date it was completed.

It is up to the ATO ISSM to decide which standard should be selected for security control testing.  In previous years the decision was made to follow the NIST 800-53 standard, instead of the 800-26.  Identify the standards that were used for the Security Control testing.  Enter the dates that the Security Control and Contingency Plan testing were completed.

Note:  Mixed lifecycle investments must complete both the Systems in Planning and Operational Systems tables.  Additionally, the security information documented in this section must be consistent with the information in the DOT ESP system.

Table 9:  Operational Systems – Security Table

5.  Have any weaknesses, not yet remediated, related to any of the systems part of or supporting this investment been identified by the agency or IG?

Select ‘yes’ or ‘no’.

For increased IT Security funding please give the dollar amount and clearly mark it as “increased IT security funding”.  You must also describe the weakness, using the same phraseology as the POA&Ms, that the increased funding is slated to address and the corrective measures for which the funding is being requested.  It is a good idea in this section to describe any additional security controls and studies that are being funded.   If there are security weaknesses - regardless of whether additional funding is being requested – a brief explanation should be provided of how the weaknesses are being addressed and/or what additional controls have been or are being implemented.  This should be consistent with responses in the risk assessment section (I.F) and the FISMA screening question.

5.a.  If “yes”, have those weaknesses been incorporated into the agency’s plan of action and milestone process?

Briefly describe the identified weaknesses and how the program plans to mitigate them.

6.  Indicate whether an increase in IT security funding is requested to remediate IT security weaknesses.

Select ‘yes’ or ‘no’.

Indicate if the program has requested additional funds for remediating identified security weakness(es) be selecting “yes’ or ‘no’.

6.a.  If “yes”, specify the amount, provide a general description of the weakness, and explain how the funding request will remediate the weakness.

OMB is asking the program to state the amount, describe the security weakness(es) and how the funding request will remediate this weakness(es).

7.  How are contractor security procedures monitored, verified, and validated by the agency for the contractor systems above?

This question is asking the program to describe the security processes and procedures that are being used to validate and monitor contractors.  Things to consider when answering this question are:

- Do contractors receive security training?  Does this training include rules of behavior?

- Are contractor facilities inspected periodically?

- When was the last inspection?

- Are security requirements for contractors, including background investigations, security training participation, and protection of sensitive government information included in SOWs and contracts?

- Are there any specific contract clauses that clearly state all of the security requirements?

- How the program monitors, verifies, and validates the contractor security procedures (i.e., periodic reviews, independent third party assessments, scheduled and unscheduled site visits, etc.)

8.  Privacy Table.

Select the appropriate responses from the answer key.  For a listing of government policies applicable to safe handling of personal information, see Order 1600.75, Appendices B, C and F.  For clarification on DOT or FAA security policies, contact your security servicing organization.

The E-Government Act require agencies to conduct, and submit to OMB, privacy impact assessments (PIAs) for all new IT investments administering information in identifiable form collected from, or about, members of the public.  PIA’s should be updated on a regular basis and the date of the latest PIA should be included.

Table 10: Privacy Table

## 2.7   Section F:  Enterprise Architecture (EA)

The Clinger-Cohen Act requires agencies to have an enterprise architecture.  OMB Circular A-130 requires the enterprise architecture to include As-is (current) and To-be (future) views and defines EA as:

“A strategic information asset base, which defines the mission, the business processes necessary to perform the mission, the data required to perform the processes, the applications required to manage the data, the technologies required to manage the applications, and transitional processes for modernizing.”

1.  Is this investment included in your agency’s target enterprise architecture?

The answer to this question should always be ‘yes’.  Investments should be in the FAA EA prior to being developed as a business case.

1.a.  If “no”, please explain why?

If, for some reason, the investment is not in the FAA EA explain why.

2.  Is this investment included in the agency’s EA Transition Strategy?

Review DOT’s Transition Strategy and FAA Modernization Blueprint.  If the investment is listed  in one of the documents, select ‘yes’; otherwise select ‘no’.

2.a.  If “yes”, provide the investment name as identified in the Transition Strategy provided in the agency’s most recent annual EA Assessment.

Provide the required information.

2.b.  If “no”, please explain why.

Contact the EA SME for guidance.

Because most FAA investments are not specifically identified in the DOT Transition

3.  Service Component Reference Model (SRM) Table

Per the Consolidated Reference Model, the SRM is a business-driven, functional framework classifying Service Components according to how they support business and performance objectives.  It serves to identify and classify horizontal and vertical Service Components supporting federal agencies and their IT investments and assets. The model aids in recommending service capabilities to support the reuse of business components and services across the federal government.  The SRM is organized across horizontal service areas, independent of the business functions, providing a leverage-able foundation for reuse of applications, application capabilities, components, and business services.

The goal of Table 3 is to identify 3 to 5 MAJOR functions (components) performed by the investment.  The basis is still the FEA Consolidated Reference Model which provides the full list of Service Components from which to choose.  OMB recognizes the fact that agencies may use different terminology for their components and now provides a mapping.

Note: The FAA NAS investments must map to both the NAS and FEA SRM components

Table 11: Service Component Reference Model Table

- Agency Component Name – Enter the NAS or FEA SRM component name.

- When entering a NAS component in this table, enter the NAS Component Name in column 1, the NAS Component Description in column 2 and either map to a FEA SRM Component in column 4, or enter NEW in column 4.

- If entering a FEA SRM Component Name in column 1, enter the FEA SRM Component Description in column 2 and enter the FEA SRM Name again in column 4.

- Agency Component Description – Enter the NAS or FEA SRM component description.

- FEA SRM Service Type – Service Domains are classified into one or more Service Types that group similar capabilities in support of the domain. Service Types provide an additional layer of categorization that defines the business context of a specific component within a given domain.  Using the FEA SRM enter the Service Type.

- FEA SRM Component – Each Service Type includes one or more Service Components that provide the “building blocks’ to deliver the Component capability to the business. A Component is defined as "a self contained business process or service with predetermined functionality that may be exposed through a business or technology interface."  Using the FEA SRM enter the Component.

- FEA Service Component Reused – A component already exists and the investment is transferring money to another FAA program or government organization in order to use the component.  This DOES NOT include a transfer of money from one program/organization to another for development efforts.

  - Component Name – Enter the component name of the other investment that uses the same component.  This demonstrates information sharing and reuse.

  - UPI – Enter the UPI code of the investment from which the component is shared.

- Internal or External Reuse

  - Internal – Component reuse within DOT

  - External – Component reuse outside DOT

- BY Funding Percentage – NOT tied to reuse!

  - A percentage breakdown/allocation of costs across each of the service components included in the TRM table.

  - If External, the percentage of funding would be the percentage transferred to the other organization.

  - Total percentage of all SRM table components should add up to 100%

4.  Technical Reference Model (TRM) Table

Per the Consolidated Reference Model, The TRM is a component-driven, technical framework categorizing the standards and technologies to support and enable the delivery of Service Components and capabilities. It also unifies existing agency TRMs and E-Gov guidance by providing a foundation to advance the reuse and standardization of technology and Service Components from a government-wide perspective.  Aligning agency capital investments to the TRM leverages a common, standardized vocabulary, allowing interagency discovery, collaboration, and interoperability. Agencies and the federal government will benefit from economies of scale by identifying and reusing the best solutions and technologies to support their business functions, mission, and target architecture.

The goal of Table 4 is to demonstrate how an IT investment aligns with the FEA Technical Reference Model (TRM).  Each SRM Component listed in Question 3 will have at least one TRM line in this table.

Table 12: Technical Reference Model Table

- FEA SRM Component – This is the same FEA SRM component name that was entered in the Service Component Reference Model table.  List all the components identified in the SRM table in the left-most column of the TRM table.  Complete the TRM table ensuring at least one TRM row is filled in for each component listed in the SRM table.

- FEA TRM Service Area – Service Areas represent a technical tier supporting the secure construction, exchange, and delivery of Service Components. Each Service Area aggregates the standards and technologies into lower-level functional areas. Each Service Area consists of multiple Service Categories and Service Standards. This hierarchy provides the framework to group standards and technologies that directly support the Service Area.  Using the FEA TRM enter the Service Area.

- FEA TRM Service Category – Service Categories classify lower levels of technologies and standards with respect to the business or technology function they serve. In turn, each Service Category is comprised of one or more Service Standards.  Using the FEA TRM enter the Service Category.

- FEA TRM Service Standard – Service Standards define the standards and technologies that support a Service Category. To support agency mapping into the TRM, many of the Service Standards provide illustrative specifications or technologies as examples.  Using the FEA TRM enter the Service Standard.

- Service Specification – Enter the vendor and product information for each SRM Component.

5.  Will the application leverage existing components and/or applications across the Government (i.e., FirstGov, Pay.Gov, etc)?

Select ‘yes’ or ‘no’.

5.a.  If “yes”, please describe.

Briefly describe how the investment will leverage government wide components/applications.

6.  Does this investment provide the public with access to a government automated information system?

Select ‘yes’ or ‘no’.

6.a.  If “yes”, does customer access require specific software (e.g., a specific web browser version)?

Select ‘yes’ or ‘no’.

6.a.1.  If “yes”, provide the specific product name(s) and version number(s) of the required software and the date when the public will be able to access this investment by any software (i.e. to ensure equitable and timely access of government information and services).

Enter the required information.

# 3.  Part II: Planning, Acquisition and Performance Information

## 3.1   Introduction

This section is to be completed for all capital asset investments identified as Planning, Full Acquisition or Mixed Lifecycle.  The information included in this section should provide FAA management and OMB with accurate information on acquisition and life-cycle costs.  The full life-cycle costs for an investment include all direct and indirect costs for planning, procurement, operations and maintenance, including service contracts, and disposal.  It is critical that the cost estimates are realistic estimates of the final costs and adjusted to consider risk in order to fully account for all costs and to solidly justify expenditure for the investment.

## 3.2   Section A: Alternative Analysis

Once a decision is made that an investment is needed a comparison of the various alternatives is required to ensure that the correct solution or product is acquired.  OMB expects the program to identify alternatives that have been evaluated using the same criteria, then select and report details on the top three alternatives as well as the status quo. The Clinger Cohen Act and OMB Circular A-94 include minimum criteria to be applied when considering whether to undertake a particular investment, including criteria related to the quantitatively expressed projected net, risk-adjusted return on investment and specific quantitative and qualitative criteria for comparing and prioritizing alternative investments.  For IT investments, agencies should use the Federal Enterprise Architecture (FEA) to identify potential partnerships or joint solutions that may be used to close the identified performance gap.

Information in this section should be consistent with the Business Case Analysis Report (BCAR).  If the investment alternative analysis is more than 5 years old it is considered outdated and must be updated.  This usually means that JRC approval will be needed for new segments of an existing investment or for changes to previously approved program baselines.

For investments that are past the original alternative analysis and/or didn’t have three viable alternatives, the program must schedule a new alternatives analysis (which includes a Cost Benefit Analysis) and show this as a milestone in Table II.C.9.

1.  Did you conduct an alternatives analysis for this project?

Select ‘yes’ or ‘no’.

1.a.  If “yes”, provide the date the analysis was completed.

Enter the date the AA was completed.

1.b.  If “no”, what is the anticipated date this analysis will be completed?

Enter the planned completion date.

1.c.  If no analysis is planned, please briefly explain why.

Provide the required information.

2.  Results of the alternatives analysis.

Briefly describe the analysis results for three viable alternatives as well as the status quo including the risk adjusted lifecycle cost and benefit estimates.

Ensure the alternatives are all viable.  Do not include an alternative if the analysis showed it was not a feasible or viable alternative.  Enter a very short title for the alternative in the first column, and provide summary information in the description column.  Column 3 should reflect the total lifecycle costs and, for the selected alternative, match the funding requests documented in the Summary of Spending table.

- Planning/Beginning of Full Acquisition: At this point in the lifecycle the program should describe the alternatives the program considered that would meet a mission need or close a performance gap.

- Full Acquisition/Mixed Lifecycle:  At this point in the lifecycle the program should be validating that the selected alternative is still the best alternative versus other possible alternatives, and continues to meet the specified cost, schedule, and performance goals.

Table 13: Alternative Analysis Results

For new initiatives and/or when the AA cannot be completed before submission of the business case, include a discussion of alternatives that will be, or are being, considered and some rough order magnitude (ROM) estimates of alternative costs, and benefits.

3.  Which alternative was selected by the agency’s Executive/Investment Committee and why was it chosen?

Identify the alternative from the above analysis that was selected and explain why.  Describe the criteria used to select the alternative and briefly explain how closing any FAA performance gap was part of the analysis and decision-making process.  This response should also include a summary comparison of the total ROI and NPV of the alternatives and other considerations such as differences in costs, benefits, and risks that explain why one alternative is preferred over the others.  If agency funding decisions/constraints have resulted in the selection or implementation of an alternative that was not the preferred one, this should be explained in this section as well.

For Mixed Lifecycle investments, be sure to include Operational Analysis information.  OAs demonstrates that an operational asset is delivering expected value efficiently and effectively, contributing to performance goals of the agency, and meeting the service needs of its customers.  This type of analysis should include cost to maintain, failure rates, and outages information and address the following questions:

- Asset performance: Is the asset meeting performance goals established during investment analysis? Are operating and maintenance costs within baseline values? Are support or operational problems emerging that could impact asset performance or adversely affect ownership costs?

- Customer satisfaction: Is the asset fully meeting customer/user needs? Is it delivering the services it was designed to deliver? Is it meeting stakeholder needs (e.g., safety, information security, human factors)?

- Strategic and business results: What strategic goal does this investment address? Is it helping to achieve that goal? How is it contributing to agency business needs?

- Financial performance: Are actual in-service costs and benefits within baseline values in the Exhibit 300 Program Baseline? If not, what corrective action is needed? Are operational costs as low as they can be for the results delivered?

- Innovation: Are there smarter or lower cost ways to satisfy customer needs and achieve benefits. Can this investment asset be combined with others to better meet organizational goals? Can we use technology to deliver better service at lower cost? Is there another way to do this work better, more efficiently, or at lower cost?

It is important to have consistency between the lifecycle costs for the selected alternative in this section, the SoS table and table II.C.9.  In some cases there may be reasons why the costs for the selected alternative will not match the costs shown in the SoS table or table II.C.9 but this would be the exception not the rule.  Listed below are some reasons why these costs may not match that can be included, as appropriate, in this response:

- The SoS table documents the investment’s total lifecycle costs, from the beginning until it is discontinued or replaced.  This includes risk adjust and inflated dollars.

- The AA table documents the total lifecycle costs of all three alternatives.   Normally the analysis should be based on constant/real dollars instead of inflated and would not normally include sunk costs.

- The costs shown in the SoS table includes government labor (FTE) costs, however FTE costs were not included in the alternative analysis.

For new initiatives and/or when the AA cannot be completed before submission of the business case, include a discussion of alternatives that will be, or are being, considered and some rough order magnitude (ROM) estimates of alternative costs, and benefits.  Include the planned completion date for the Alternative Analysis, Cost-Benefit Analysis, etc. and include these as milestones in Table II.C.9.

4.  What specific qualitative benefits will be realized?

Describe the intangible benefits that this investment will realize.  If there are no qualitative benefits then state this.  Do not include quantitative benefits as these have been included in the Cost Benefit Analysis.

## 3.3   Section B: Risk Management

In order to successfully address this section of the Exhibit 300 the program must have performed a Risk Assessment and developed a Risk Management Plan at initial concept, and demonstrated active risk management throughout the life-cycle of the investment.  For all investments, both IT and non-IT, the programs Risk Management Plan must discuss how the program will identify, manage and mitigate risks.  This documentation should also include a Risk Matrix that would, at a minimum, list the risks, probability of occurrence, and mitigation strategies.

Indicate whether any costs for mitigating risks have been included in the table II.C.9 milestones, regardless of whether they are shown as individual milestones or included as part of other milestones.

Note:  The Risk Matrix should be updated at least once a year.  The Risk Management Plan should be updated as needed.

1.  Does the investment have a Risk Management Plan?

Select ‘yes’ or ‘no’.  This response includes both the Risk Management Plan and the associated Risk Matrix.

1.a.  If “yes”, what is the date of the plan?

In many cases the Risk Management Plan which documents the risk processes will not need to be updated, however risks are continuously monitored and updated. The risk matrix should be updated as risks are mitigated and closed, and new risks are identified. This can be monthly quarterly, semi-annually and annually.

1.b.  Has the Risk Management Plan been significantly changed since last year’s submission to OMB?

Select ‘yes’ or ‘no’.

Again, the Risk Management Plan which documents the risk processes may not have changed, however risks are constantly changing from year to year.  Risks become obsolete, some are mitigated and new risks are identified.

1.c.  If “yes”, describe any significant changes.

Describe any changes to the RMP or Risk Matrix.  Additionally, briefly describe the processes the program is using to continuously monitor and update risks.

2.  If there currently is no plan, will a plan be developed?

Select ‘yes’ or ‘no’.

2.a.  If “yes”, what is the planned completion date?

Enter the planned completion date.

2.b.  If “no”, what is the strategy for managing the risks?

Briefly describe how the program will review and manage the risks.

3.  Briefly describe how investment risks are reflected in the lifecycle cost estimate and investment schedule.

Describe how the costs and completion dates for the milestones shown in table II.C.9 have been risk adjusted.  This would include the incorporation of costs for risk mitigation activities, as well as the existence of a management reserve and use of methods/tools for estimating risk adjusted cost and completion date values.

## 3.4   Section C: Cost and Schedule Performance

The government’s emphasis on managing program cost and schedule performance is increasing.  OMB requirement for managing all major investments:

- Agencies must use a performance-based acquisition management system based on Earned Value Management to obtain timely cost and schedule performance data

  - Required on contractor and Government program efforts

  - Required for fixed price and cost type contracts

- The system must also measure milestone progress in terms of cost, capability of the investment to meet specified requirements, timeliness, and quality

The success or failure of investments to achieve cost, schedule, and performance goals can significantly affect the FAA’s ability to maintain budget discipline and achieve its strategic plan.  Program managers need early visibility into a contract’s progress to immediately identify any problems.  This allows time for contractors and the government to implement corrective actions before significant variances can occur.

OMB and AMS policies require programs with DME activities to use EVM based on ANSI/EIA-748 guidelines.  Therefore, programs must fill out this section for investments that are in the Planning, Full Acquisition, and Mixed Lifecycle phases.  The information documented in this section includes both contractor and government FTEs and must be consistent with the Summary of Spending table.

Table II.C.9 includes three sections:

- The Initial Baseline (original program baseline) will include milestones as approved by the JRC at either the Initial Investment or the original Final Investment Decision.  Whether the program includes the initial or final baseline depends on what CPIC phase the investment is in (planning, acquisition or mixed lifecycle).  If the baseline is based on the Final Investment Decision, this baseline must be included in all subsequent Exhibit 300s and cannot be revised.

- The Current Baseline reflects the most current JRC approved Program Baseline and requires identification of DME Useful Segments.  The current approved baseline must be reconciled through the Parameter Sheets in SPIRE to the CIP.   This baseline would include:

  - Useful Segments (or phases within a useful segment) that have received the Authorization to Proceed (ATP) by the JRC

  - Useful Segments (or phases within a useful segment) that have not received the ATP by the JRC

- For the Current Baseline Variance FAA programs will use “at-completion baseline and forecast dates” to determine the current baseline schedule variance in days.

Note: Mixed lifecycle investments are required to report all milestones and costs (DME and O&M) in Section II.C and do not have to complete III.B.  Additionally mixed lifecycle investments should complete an Operational Analysis for the steady state portion even if they do not need to complete Part III.

1.  Does the earned value management system meet the criteria in ANSI/EIA Standard 748?

ANSI/EIA 748 is a government standard that requires integrated project management. The processes include integration of program scope, schedule, and cost objectives, establishment of a baseline plan for accomplishment of program objectives, and use of earned value techniques for performance measurement during the execution of a program.

In order to be compliant an investment must meet all 32 guidelines.  Only FAA programs that have been rated ‘green’ for ANSI/EIA 748 compliance should answer ‘yes’ to this question.  All other programs should answer ‘no’.

2.  Answer the following questions about current cumulative cost and schedule performance.  The numbers reported below should reflect current actual information.

2.a.  What is the Planned Value (PV)?

Planned Value is the time phased BAC budgeted costs for the scheduled work. It’s also known as BCWS (Budgeted Cost for Work Scheduled).

2.b.  What is the Earned Value (EV)?

Earned Value is the budget value of the work that has been accomplished. It’s also known as BCWP (Budgeted Cost for Work Performed).

2.c.  What is the Actual Cost of work performed (AC)?

Actual Cost is the cost for the work that has been accomplished. It’s also known as ACWP (Actual Cost of Work Performed).

2.d.  What costs are included in the reported Cost/Schedule Performance information (Government Only/Contractor Only/Both)?

Programs should incorporate both contract and government costs in table II.C.9.  At the government level both program and field FAA FTE costs should be includes in the milestones costs.

- The use of FTEs by most of programs is for Program Management and sustaining Engineering support.  In these instances, the FAA FTE effort will be included as Level of Effort (LOE) in the EVM Control Accounts and OMB-300 reporting Milestones for PM or SE.

- Some FAA programs use FAA FTE resources for measurable activities, such as, deployment.  In these instances, the FAA FTE effort will be included as a measurable activity in the EVM Control Accounts and the OMB-300 reporting Milestones that provide a measure of schedule progress.

Programs having problems determining how to incorporate FAA FTEs into the EVM Control Accounts or the OMB-300 reporting milestones should contact a member of the VMO or EVM team for additional guidance.

2.e.  “As of” date.

Enter the required date.

3.  What is the calculated Schedule Performance Index (SPI=EV/PV)?

The Schedule Performance Index is the schedule efficiency factor. Measures the value of work performed (EV) against work scheduled (budget).

4.  What is the schedule variance (SV=EV-PV)?

The Schedule Variance is the difference between the value of work performed (EV) less value of work scheduled (budget).

5.  What is the calculated Cost Performance Index (CPI=EV/AC)?

The Cost Performance Index is the cost efficiency factor.  Measures the value of work accomplished against actual cost.

6.  What is the cost variance (CV=EV-AC)?

The Cost Variance is the difference between the earned value and the actual cost of work completed.

7.  Is the CV% or SV% greater than + or – 10%?

Select ‘yes’ or ‘no’.

7.a.  If “yes”, was it the CV, SV or Both?

Select the appropriate response.

7.b.  If “yes”, explain the variance.

If any of the cost, schedule or performance variances are not within 10% of current baseline provide complete analysis of the variance.  This would include the cause, corrective actions, and the most likely EAC.  This information is required for both positive and negative variances.  Use the EVM system to identify the specific work packages where problems are occurring.

7.c.  If “yes” what corrective actions are being taken?

Describe the corrective actions to be taken in order to correct the variance.

7.d.  What is the most current “Estimate at Completion”?

Based on the corrective actions provide the most current EAC.  Do NOT include O&M costs in this calculation.

8.  Have any significant changes been made to the baseline during the past fiscal year?

Select ‘yes’ or ‘no’.

Proposed baseline changes must be submitted to OMB prior to budget request; proposed changes should not be assumed approved.  Investments that re-baseline are expected to provide the following information to DOT and OMB before submitting the Exhibit 300 in September:

- Background:  Include Information about the most recent previous baseline decision, the events leading up to the need to re-baseline, and the methods used to determine the new cost and/or schedule baseline.

- Impact/New Program Baseline:  Compare the revised baseline to the old, address the impact on project schedule, costs, benefits/ROI, and other investments.

- JRC/IRB Concerns:  Address any special conditions or constraints placed by the JRC.

8.a.  If “yes”, when was it approved by OMB?

Enter the OMB approval date.

9.  Initial baseline and current approved baseline comparison.

The foundation of this table is the Work Breakdown Structure (WBS) which organizes and defines the project scope and includes both current Work Packages and future Planning Packages.

Table 14: Approved Program Baseline Table

Table II.C.9 Guidelines

- Milestones should be broken out by lifecycle phase.  Mixed lifecycle investments would include milestones in multiple phases (planning, acquisition, O&M).

- Include security milestones such as the completion of security plans, risk assessments, SCAPS and C&As.

- Prototypes and pilots must be treated and reported as full acquisition and their development is subject to EVM requirements.

- If the Initial and Current Milestones/Baselines are the same (there have been no changes to the original JRC approved baseline), then the planned dates and estimated costs from the “Initial Baseline” should be repeated in the planned completion dates and costs of the “Current Baseline” columns.

- If initial baselines are not part of the current milestones (unable to map between the two), list the initial milestones information and leave the current baseline blank for that same row.  List the current milestones and their completion dates and costs in the rows below the initial baseline.

- The totals in Section II.C and the SOS should include all risk adjustments and management reserve.  If the management reserve or other risk-related costs are not included in the milestone costs include them as a separate milestone.

- AMS standard level 1 milestones must be included in the baseline however level 2 milestones should be included as appropriate.  Milestone descriptions should be clear and concise and should be consistent with the Blue Sheet and RPD activities.  Coordinate with EVM team to ensure the milestones in table II.C.9 have been adequately documented.

- Complete and Future milestones beyond the current budget year may be rolled-up or consolidated.

- Make sure the initial and current baselines agree with what ATO-F has on record.  Reconcile any differences.

- F&E and O&M milestones should be grouped together in separate sections of the table and have associated subtotals.

- O&M milestones/costs should be broken out by fiscal year.

- The estimated total costs should be consistent with the total lifecycle costs for the selected alternative and the lifecycle costs documented in the Summary of Spending.

- Consistent with OMB and FAA EVM guidance FTE costs must be included in the table.  F&E FTE costs should be incorporated in the milestone costs instead of being listed separately.  O&M FTE costs also must be included in the table either as part of the annual O&M costs or as a separate annual O&M FTE cost row.

- For mixed lifecycle investments include O&M milestones separately at the bottom of the table - but do NOT include O&M milestones and their costs in the EVM calculations (including BAC or EAC).

# 4.  Part III: Operation and Maintenance Investments

## 4.1   Introduction

Poorly performing assets detract from mission effectiveness by deflecting resources that could be used more effectively to support an agency’s core mission.  If not properly managed, an investment’s useful life can be shortened dramatically or prolonged beyond the planned termination date at high cost and risk, thereby reducing the return on the taxpayers’ investment.    Once an investment is operational the focus should be placed on analyzing it’s ability to support the organizational mission.  By continuously monitoring performance the FAA can diagnose and mitigate potential problems before they become crises.

OMB expects investments to use Operational Analysis (OA), Post-Implementation Review (PIRs) and Service Level Reviews (SLRs) to monitor performance.

- The OA process consists primarily of capturing and tracking operational cost and performance information in the steady state phase and measuring that performance against the established cost, schedule, and performance goals.  Operational analysis can reveal: (1) previously undetected faults in the design, construction, or installation: (2) if operational or maintenance costs are higher than anticipated; or (3) if the asset fails to meet program requirements.  Operational analysis allows management to make decisions which can minimize the total cost of ownership.

- PIRs  are a subset of the OA process that allow program managers to evaluate stakeholder and customer/user satisfaction with the end product, mission/program impact, and technical capability.

- SLRs are used to periodically report on PIR and OA activities, findings, and status of recommended actions

## 4.2   Section A: Risk Management

In order to successfully address this section of the Exhibit 300 the program must have performed a Risk Assessment and developed a Risk Management Plan at initial concept, and demonstrated active risk management throughout the life-cycle of the investment.  For all investments, both IT and non-IT, the programs Risk Management Plan must discuss how the program will identify, manage and mitigate risks.  This documentation should also include a Risk Matrix that would, at a minimum, list the risks, probability of occurrence, and mitigation strategies.

Indicate whether any costs for mitigating risks have been included in the table II.C.9 milestones, regardless of whether they are shown as individual milestones or included as part of other milestones.  Please note that the Risk Management Plan and Risk Matrix should be updated at least once a year.

1.  Does the investment have a Risk Management Plan?

Select ‘yes’ or ‘no’.  This response includes both the Risk Management Plan and the associated Risk Matrix.

1.a.  If “yes”, what is the date of the plan?

In many cases the Risk Management Plan which documents the risk processes will not need to be updated, however risks are continuously monitored and updated. The risk matrix should be updated as risks are mitigated and closed, and new risks are identified. This can be monthly quarterly, semi-annually and annually.

1.b.  Has the Risk Management Plan been significantly changes since last year’s submission to OMB?

Again, the Risk Management Plan which documents the risk processes may not have changed, however risks are constantly changing from year to year.  Risks become obsolete, some are mitigated and new risks are identified.

1.c.  If “yes”, describe any significant changes.

Describe any changes to the RMP or Risk Matrix.  Additionally, briefly describe the processes the program is using to continuously monitor and update risks.

2.  If there currently is no plan, will a plan be developed?

Select ‘yes’ or ‘no’.

2.a.  If “yes”, what is the planned completion date?

Enter the planned completion date.

2.b.  If “no”, what is the strategy for managing the risks?

Briefly describe how the program will review and manage the risks.

## 4.3   Section B:  Cost and Schedule Performance

Operational Analysis demonstrates that an operational asset is delivering expected value efficiently and effectively, contributing to performance goals of the agency, and meeting the service needs of its customers.  This type of analysis should include cost to maintain, failure rates, and outages information and address the following questions:

- Asset performance: Is the asset meeting performance goals established during investment analysis? Are operating and maintenance costs within baseline values? Are support or operational problems emerging that could impact asset performance or adversely affect ownership costs?

- Customer satisfaction: Is the asset fully meeting customer/user needs? Is it delivering the services it was designed to deliver? Is it meeting stakeholder needs (e.g., safety, information security, human factors)?

- Strategic and business results: What strategic goal does this investment address? Is it helping to achieve that goal? How is it contributing to agency business needs?

- Financial performance: Are actual in-service costs and benefits within baseline values in the Exhibit 300 Program Baseline? If not, what corrective action is needed? Are operational costs as low as they can be for the results delivered?

- Innovation: Are there smarter or lower cost ways to satisfy customer needs and achieve benefits. Can this investment asset be combined with others to better meet organizational goals? Can we use technology to deliver better service at lower cost? Is there another way to do this work better, more efficiently, or at lower cost?

1.  Was an Operational Analysis conducted?

Select ‘yes’ or ‘no’.

1.a.  If “yes”, provide the date the analysis was completed.

Enter the date the analysis was completed.

1.b.  If “yes”, what were the results?

Describe the OA, PIR, and SLA activities that have been planned, completed, or are ongoing.  Include the results as well as any actions that are being taken.

1.c.  If “no”, please explain why it was not conducted and if there are any plans to conduct and Operational Analysis in the future.

Briefly explain why OA, PIR, and SLA activities have not been conducted and when the program plans to schedule these activies.

2.  Complete the following table to compare actual cost performance against the planned cost performance baseline.  Milestones reported may include specific individual scheduled preventative and predictable corrective maintenance activities, or may be the total of planned annual operations and maintenance efforts.

2.a.  What costs are included in the reported Cost/Schedule Performance information (Government Only/Contractor Only/Both)?

Programs should incorporate both contract and government costs in table III.B.2.  At the government level both program and field FAA FTE costs should be included in the yearly maintenance milestones.

2.b.  Plan vs. Actual Performance Table

Table 15: Steady State Plan vs. Actual Performance Table

Table III.C.2.b Guidelines

- A one line rollup of completed DME total costs should be included at the top of the table so that the total planned baseline at the bottom is consistent with the SOS total (including FTE costs).

- Dates and costs shown in “Planned” Columns should be consistent with the Current JRC Approved Baseline

- O&M milestones must be shown for each year for the previous year through the budget year or the last year of the current segment that the JRC has approved for funding and execution (whichever is the later date).

- Operational FTE costs must be included either as part of the milestones/annual cost line or as a separate line.

# APPENDIX A - CROSSWALK OF THE EXHIBIT 300 SECTIONS

| CROSSWALK OF EXHIBIT 300 SECTIONS (With each other and other Exhibit 300 related documents) |
| --- |
| Question | What to Check |
| Exhibit 300 | The information provided in the Exhibit 300 should be consistent with the investment’s lifecycle documentation. Lifecycle documents that are referenced in the business case are: Acquisition Plan (Section I.C) Security Plan (Section I.E) Privacy Impact Assessment (Section I.E) Alternatives Analysis and Benefit-Cost Analysis (Section II.A) Risk Management Plan (Section II.B, III.A) Operational Analysis and PIR reports |
| I.A.5 | Guidance for this number is found in OMB Circular A-11 Exhibit 53. The UPI shown for this project/investment on the Exhibit 300 should be consistent with the UPI shown in the Exhibit 53. |
| I.A.6 | Ensure your response is consistent with the funding request documented in the Budget Year (BY) column of the Summary of Spending (SoS) table and the Contracts/Task Orders table. For example: If Operations and Maintenance has been selected as the response to this question OMB would not expect to see an Acquisition funding request in the SoS table for the current budget year. If Planning has been selected as the response to this question OMB would only expect to seen planning contracts being executed. Other contracts would most likely be future contracts that are being planned. |
| I.A.8 | Ensure the information included in this response is consistent with the responses provided in I.A.6, Section I.D, Section II.A and II.C. For example, OMB expects the program to describe how the program will address the performance gap as well as the FAA and DOT strategic goals and objectives the investment supports. This information should be consistent with the performance goals documented in Tables 1 and 2. |
| I.A.9.a | Ensure this date is consistent with any JRC dates that have been included in the response to I.A.8 and table II.C.9. |
| I.A.15 | Ensure the response to this question is consistent with Section I.E. For example, if the program answers ‘yes’ to this question OMB would expect to see the Security section filled in. |
| I.A.19 | Ensure that the response to this question is consistent with the information provided on Exhibits 52 and 53. |
| I.B.1 | The total lifecycle costs documented in the Summary of Spending table should match the total lifecycle costs documented in Sections II.C and III.B and should be consistent with the current JRC approved baseline totals. The total lifecycle costs in the SoS should also be consistent with the total lifecycle costs for the selected alternative (Section II.A.2) and SPIRE data. |
| I.C.1 | The total value of the contracts listed in the Contracts/Task Orders table should be a logical representation of the total lifecycle costs documented in the Summary of Spending table. For example, OMB would not expect to see a total contract value greater than the total lifecycle costs (without FTE costs). Significant differences should be explained in Section I.C.2. |
| I.C.2 | The response to this question should be consistent with information provided in Section II.C. |
| I.D | The performance goals documented in Tables 1 and 2 should be consistent with the FAA and DOT strategic goals and objectives described in the response to question I.A.8 and linked to any benefits that were described in the alternative analysis section. |
| I.E. | The information in the Security section should be consistent with information provided in the responses to I.A.6 and I.A.15. For example if the program selected Mixed Lifecycle as the response to question I.A.6 then OMB would expect to see both the Planning and Operational tables filled in. Security Plan and C&A dates may be included as milestones in table II.C.9. Section II.C dates should then be consistent with Section I.E. Ensure that any responses regarding security risks and required mitigation actions are consistent with risk information provided in Sections II.B and III.A. Ensure security risks are documented in the project’s Risk Register/Matrix or provide an explanation if they are documented elsewhere. |
| I.E.8 | The systems that are included in the Privacy table should be the same systems that appear in the Planning and Operational tables. |
| II.A. | Any benefits described in this section should be consistent with the FAA and DOT strategic goals and objectives described in the response to I.A.8 and the performance goals in Section I.D. |
| II.A.2 | The total lifecycle costs for the selected alternative, including FTE costs, should be consistent with the total lifecycle costs documented in the SoS and II.C.9 tables. |
| II.C. | The information documented in this section should be consistent with the response to question I.A.6. |
| II.C.1 | The response to this question should be consistent with the information provided in the response to question I.C.2. The response should be “No” if an investment has not scored “green” in its EVM assessment. |
| II.C. 3, 4, 5, 6, 7 | Any large cost or schedule variances, especially negative variances > 10% and related mitigation actions should be clearly documented in the risk register/database. |
| III.B | The information documented in this section should be consistent with the response to question I.A.6. The information documented in this section should be consistent with the response to question I.A.6. Total costs in the table should be consistent with total costs in the SOS table (including FTE costs). Also, descriptions of completed, ongoing, or planned operational analysis (OA) and/or Post Implementation Review (PIR) activities should be consistent with PIR and OA information in the FAA PIR plan and in the investment's Investment Strategy Planning (ISP) document. The ISP is part of the documentation required for JRC investment decisions and it should include information about PIRs and OA activities consistent with AMS guidance. |

# APPENDIX B – OPERATIONAL ANALYSIS AND PIRs

Template for Operational Analysis Report

This template guides the service organization when preparing an Operational Analysis Report. It includes information that is the basis for the summarized performance information presented in the Exhibit 300 and at service level reviews. The template is used to document and report an investment’s operational analysis procedures, results, and future plans including scheduled activities and corrective actions. The types of information, methods for collecting and analyzing the information and the level of detail will depend on the size, complexity, and requirements of each investment. Some specific performance information needs to be included that is critical to determining if the investment is meeting its mission and functional objectives. The template can be augmented with charts/graphs to illustrate results and trends. Operational analysis documentation must be available for the Joint Resources Council, the Operational Quality Council, and the Office of Management and Budget (OMB).

For those investments using this template or completing the operational analysis process for the first time not all information requested in this template may be available.  In such chases Operational Analysis teams should provide the information that is being collected and available and complete as much information as possible in each section of the template.  Questions about this template should go to the Operational Quality Council, Post Implementation Review Quality Officer.

Operational Analysis Report

(Program Name)

Version #

Approved by:                  Signature                   Date: 
Vice President or Director of the performing service organization

Approved by:                  Signature                   Date:
Vice President or Director of the operating service organization(s) (if different from the performing service organization)

Submitted by:                  Signature                   Date: 
Appropriate preparing organization

| Service Organization Focal Point | Operating Organization Focal Point |
| --- | --- |
| Name | Name |
| Code and organization | Code and organization |
| Phone Number | Phone Number |
| FAX Number | FAX Number |
| Email Address | Email Address |

Federal Aviation Administration
800 Independence Avenue
Washington, D.C. 20591

| 1: IDENTIFYING INFORMATION |
| --- |
| 1.1: Investment Title |  |
| 1.2: Program Office |  |
| 1.3: Date of Operational Analysis |  |
| 1.4 : Investment (Project) Manager |  |
| 1.5: Investment Owner |  |
| 1.6: Submission Date |  |
| 1.7: Revision Number |  |
| 1.8: Revision Date |  |
| 2: OPERATIONAL ANALYSIS DESCRIPTION |
| Refer to FAST for guidance on conducting an operational analysis, including responsibilities. Provide a brief summary of the operational analysis, including: The period of the analysis, Its scope (investment segments/subsystems, any specific locations, etc), Operational analysis team composition The overall process Assumptions related to the strategic/business, customer, technical or financial analyses conducted as part of the operational analysis. |
| 3: STRATEGIC AND BUSINESS/MISSION ANALYSIS |
| For each Department of Transportation Strategic plan and FAA Flight Plan goal that the investment supports, explain if and how the investment is continuing to meet FAA and Department mission or strategic goals. Clearly identify any impacts on performance that are caused by sources external to the investment or asset, such as infrastructure (facilities, environmental, telecommunications) environment, or events outside the control of the investment and those responsible for it. Include the information listed below. |
| 3.1: Summary of Goals Supported by the Investment Summarize the specific DOT and FAA investment supported by this investment. Use appropriate goals from the DOT Strategic Plan, the FAA Flight Plan, and Line of Business (LOB) business plans. For those investments that complete Exhibits 300, include performance metrics/indicators in the areas of “mission and business results” and “processes and activities” being used to monitor performance and ensure DOT and Flight Plan mappings are consistent with those in the Exhibit 300. 3.2: Data Collection and Analysis Methods, Procedures, and/or Tools Describe methods, procedures, and/or tools used to collect and analyze performance goal data. 3.3: Performance Results Describe overall results including any instances of exceeding performance goals as well as failures to meet them. Describe the causes and impact of positive or negative performance results. 3.4: Planned Actions Describe activities and actions planned as a result of exceeding performance expectations or to mitigate the impact in areas where performance goals are not being met. |
| 4: Customer, User, Stakeholder Analysis/Assessment |
| Identify investment users, customers, and stakeholders and the processes used to measure the effectiveness of the investment in supporting user and/or customer functions and to measure user and/or customer satisfaction. (Note: objective quantitative measures are preferred for effectiveness/efficiency, whereas, surveys, user group meetings, customer focus groups, etc. are typically used to assess user and/or customer satisfaction and to elicit potential improvements). Summarize the results of data collection and survey efforts or other user or customer inputs and usage trends. Questions to be answered are: Does the existing asset provide customers with needed functionality and performance? Is it helping users perform their functions more easily or efficiently? For guidance in selecting appropriate performance measure, refer to OMB guidance that can be found at www.whitehouse.gov/omb/part/2004_program_eval.pdf. Regardless of which “customer results” performance indicators and goals are reported in the Exhibit 300, customer/user/stakeholder indicators/metrics should address: Does the investment reflect current user or customer functional or performance requirements? Has the investment exceeded expectations? How does the investment address the following operational indicators in relation to customer and stakeholder requirements/expectations and their ability to perform their functions: Efficiency Effectiveness Maintainability/supportability Productivity Usability Suitability Security Availability Reliability Energy usage Costs and cost savings Clearly identify any impacts on performance that are caused by sources external to the investment or asset, such as infrastructure (facilities, environmental, telecommunications) environment, or events outside the control of the investment and those responsible for it. Include the information listed below. |
| : Customers, Users, Stakeholders, and Related Performance Goals and Metrics Identify primary customers/users and stakeholders related to this investment and summarize customer/user/stakeholder requirements, performance and satisfaction goals, and related metrics supported by this investment including related Exhibit 300 performance metrics/indicators in the area of “Customer Results” or “Processes and Activities” (e.g., productivity, efficiency, errors, complaints, and timeliness). 4.2: Data Collection and Analysis Methods, Procedures, and/or Tools Describe methods, procedures, and/or tools used to collect and assess customer/user efficiency, system usability and suitability, and customer/user satisfaction and other data (e.g., performance data, including error data, surveys, user group meetings, customer focus groups, system data, etc.) 4.3: Performance Results Describe overall results on actual performance and the results of surveys or other user or customer inputs, and usage analysis/trends, including any instances of exceeding performance goals as well as failures to meet performance goals. Describe the causes and impact of positive or negative performance results. 4.4: Planned Actions Describe activities and actions planned as a result of exceeding performance expectations or to mitigate the impact in areas where performance goals have not been met. |
| 5: Technical Performance Analysis |
| Briefly describe the methods, and/or tools used to collect and analyze technical performance and the results of the analysis. The Program Requirements attachment to the Exhibit 300 Program Baseline defines technical performance for the investment program. Regardless of which “technical” performance indicators and goals are reported in the Exhibit 300, technical performance indicators/metrics should include: Functional performance/effectiveness Unscheduled outages Maintenance and equipment outages Mean Time Between Outages/Failures Replaced component count for the reporting period Mean Time to Restore Corrective maintenance actions labor hours Operational availability Impact on interfacing technology/downstream users Functional performance/effectiveness (in relation to functional requirements/objectives) The following technical performance goals should also be addressed either in this area or in the user/customer areas where most appropriate: Operational productivity measures (e.g., mean time to perform tasks/functions, human-system throughput Human-system error rates Training time to proficiency Staffing support requirements (including technical skills, aptitudes, and related numbers) Clearly identify any impacts on performance that are caused by sources external to the investment or asset, such as infrastructure (facilities, environmental, telecommunications) environment, or events outside the control of the investment and those responsible for it. |
| 5.1: Technical Goals and Metrics Summarize the technical goals and related metrics supported by this investment, including related Exhibit 300 performance metrics/indicators in the area of “Technology”. 5.2: Data Collection and Analysis Methods, Procedures, and/or Tools Describe methods, procedures, and/or tools used to collect and assess technical performance data (e.g. system reports, change order requests, etc.) 5.3: Performance Results Describe overall results including any instances of exceeding performance goals as well as failures to meet them. Describe the causes and impact of positive or negative performance results. 5.4: Planned Actions Describe activities and actions planned as a result of exceeding performance expectations or to mitigate the impact in areas where performance goals have not been met. |
| 6: Financial Performance Analysis |
| Explain if this investment is meeting financial/cost and schedule goals. Discuss actual cost performance to date and any expected changes to annual estimates as well as total baseline costs. In addition to the costs of the investment, this financial section should address performance in relation to cost saving/avoidance goals and metrics (e.g., cost avoidance or savings goals and indicators/metrics in the processes and activities or technology areas of the Exhibit 300) and the return-on-investment and payback-period estimates of the cost/benefit analyses that were part of investment analysis. Clearly identify any impacts on performance that are caused by sources external to the investment or asset, such as infrastructure (facilities, environmental, telecommunications) environment, or events outside the control of the investment and those responsible for it. Include the information listed below. |
| 6.1: Financial Goals and Metrics 6.1.1 Cost elements/metrics Explain the elements that are part of the investment’s operations and maintenance costs being tracked. Some financial/cost metrics that should be considered by all programs include: Costs of maintenance per system/box Repair costs Replacement parts/component costs Training costs Staffing costs Software license/maintenance Application hosting environment (infrastructure) Application support (to meet new/changing requirements) 6.1.2: Cost and benefits goals Summarize financial goals and related metrics supported by this investment including related Exhibit 300 saving/avoidance performance goals and metrics (for example, cost avoidance or savings goals and indicators in the areas of processes and activities or technology or integrated logistics support) and the return on investment and payback period estimates of the cost/benefit analyses that were part of the investment analysis. Include information about the alternatives analysis. Include the following information where available. If it is too soon (insufficient portions of the investment are operational) to make determinations, provide a planned date when sufficient operational information will be available to validate benefit expectations including, where applicable, financial performance goals from Section I.D of the Exhibit 300): What is the date of the program’s most current alternatives-cost/benefit analysis (AA-CBA) document? What is the value of the quantifiable benefits reported in the AA-CBA for the selected alternative? Is that still a valid projection? If not, do you have a current projection of the quantifiable lifecycle benefits for your program? If yes, please describe. In the AA-CBA document, assumptions were made to estimate the end-of-life date for the program. What is the end-of-life date and is that date still valid? If not, what is the revised end-of-life date? Please describe how the program is measuring and recording the value of accumulated benefits (including financial performance goals from Section I.D of the exhibit 300). Please detail the estimated benefits accumulation schedule (by FY) for the program consistent with your alternatives-cost/benefit analysis: Previous Year-1 and earlier: $ Previous Year: $ Current Year: $ Budget Year: $ Budget Year + 1: $ Budget Year +2: $ Budget Year +3: $ Budget Year +4 and Beyond: $ 6.2: Data Collection and Analysis Methods, Procedures, and/or Tools Describe methods, procedures, and/or tools used to collect and analyze cost, benefit, and schedule performance data. 6.3: Cost Drivers Identify major cost drivers related to this investment and how they impact costs 6.4: Performance Results Describe overall results including any instances of exceeding cost performance goals as well as failures to meet them. Describe the causes and impact of positive or negative performance results. 6.5: Planned Actions Describe activities and actions planned as a result of exceeding performance expectations or to mitigate the impact in areas where performance goals have not been met. |
| 7: Actual Performance in Relation to Established Exhibit 300 Baseline Performance Goals (Note: This section should only be completed by investments that complete Exhibit 300s and the information should be consistent with that reported in the Exhibit 300.) |
| For past and current fiscal years, provide the Performance Goals and Measures table(s) with prior-year actual results and current-year interim results, if known. Complete Table 1 and/or Table 2 below. If the project collects, manages, or reports to other performance goals and measures, add rows to record those goals and measures. |
| 7.1: Table 1 (Optional) Use of Table 1 is optional. It should only be used for investments that report in an OMB Exhibit 300 if either 1) not all actual performance results have been reported yet, or 2) the investment team wants to include Table 1 information for historical purposes. OMB guidance indicates that information technology (IT) investments initiated prior to FY2005 and non-IT investments must use Table 1, while IT investments initiated in FY2005 or beyond must use Table 2. Consequently, if Table 1 is included, consistent with the Exhibit 300, it should normally not include goals for periods beyond FY 2005. If in the OMB Exhibit 300, Table 1 includes goals past FY 2005, then this table need only cover performance goals reported in the Exhibit 300 up through the current fiscal year. Clearly identify any impacts on performance that are caused by sources external to the investment or asset, such as infrastructure (facilities, environmental, telecommunications) environment, or events outside the control of the investment and those responsible for it. |
| Past and Current Fiscal Years | Strategic Goal(s) Supported | Existing Baseline | Planned Performance Improvement Goal | Actual Performance Improvement Results | Planned Performance Metric | Actual Performance Metric Results |
| Last fiscal year |  |  |  |  |  |  |
| Current fiscal year |  |  |  |  |  |  |
| 7.2: Table 2 This table need only cover performance goals reported in the Exhibit 300 up through the current fiscal year. |
| Past and Current Fiscal Year | DOT Strategic and FAA Flight Plan Goals Supported | Measurement Area | Measurement grouping | Measurement Indicator | Baseline | Planned Improvements to the Baseline | Actual Results |
| Past fiscal year(s) |  | Mission and Business Results |  |  |  |  |  |
| Past fiscal year(s) |  | Customer Results |  |  |  |  |  |
| Past fiscal year(s) |  | Processes and Activities |  |  |  |  |  |
| Past fiscal year(s) |  | Technology |  |  |  |  |  |
| Current fiscal year |  | Mission and Business Results |  |  |  |  |  |
| Current fiscal year |  | Customer Results |  |  |  |  |  |
| Current fiscal year |  | Processes and Activities |  |  |  |  |  |
| Current fiscal year |  | Technology |  |  |  |  |  |

8: Table for Operations and Maintenance (O&M) Activities/Milestones This table should include only operations and maintenance milestones/activities that are part of an investment’s steady-state or AMS in-service management phase. This table compares the actual cost and schedule performance in relation to current baseline cost and schedule goals. For investments that report in the Exhibit 300 and have a completed Exhibit 300 Program Baseline approved by the Joint Resources Council or other designated Investment Review Board, the baseline information in these tables should be consistent with that in the approved Exhibit 300 Baseline document. The level of detail should be the same or greater than in the Exhibit 300. At a minimum, provide one “milestone” line for each fiscal year that shows the total costs and completion date of the O&M activities for that fiscal year. Milestones/activities may also be broken out in sufficient detail for each year to show operations activities that are supposed to take place consistent with service-level agreements or plans. Investments that do not submit Exhibit 300s to OMB may tailor or streamline this table based on the requirements of the JRC or the appropriate subordinate Investment Review Board. The cost estimates would include maintenance, training, repair, disposition, and other operational costs, including FTE costs. The milestones listed on the table may consist of a rollup of past fiscal year costs, one line for annual costs at least up through the budget year, and a roll up of future out year costs beyond the budget year. They may also include sub-milestones with a breakout of the activities and related costs during each fiscal year (such as equipment repair costs, replacements or parts, technical documentation updates, training activities, and related FTE costs). Investments without a baseline that has been officially approved by the Joint Resources Council or Subordinate Investment Review Board should still fill in the “Planned” schedule and cost column and provide a brief explanation at the bottom of the table about the source or basis of the planned cost and schedule data. Questions about this table should be referred to the Value Management Office or the PIR Quality Officer.

Description of Milestone (Milestone costs include FTE costs) Current Baseline/Planned Schedule Current Baseline/Planned Costs Actual Completion Date Actual Costs Planned Completion Date Planned $M costs at milestone comp Comp Date - Blank if not complete $ M costs to date TOTALS Current Schedule B/L Completion Date Current total O&M Cost baseline Actual Completion Date (when completed) (Actual Cost to date) *Note: Prior to NAS handoff, programs will be using F&E funds to cover O&M costs. These costs are subject to EVM and will therefore be included in the EVM reporting process. When NAS handoff is complete, the investment or the operational segment/milestones will become subject to Operational Analysis.

9: ANALYSIS OF RISK

Briefly describe how risks and related mitigation activities are monitored and any significant changes to the risk environment/status or risk mitigation actions.

10: INNOVATION ANALYSIS

Addressing innovation in the operational analysis demonstrates that investment managers are monitoring the current state of and availability in the marketplace of cost-saving and performance-enhancing technologies and are communicating with investment customers and stakeholders to address questions such as: How can we better meet customer needs? Could we meet these same customer needs at lower cost? How could this investment be combined with others to better meet our organization’s strategic goals? Is the current investment implementation going to meet its life expectancy targets? Are the customer’s most recent performance standards projections capable of being met with the current investment implementation?

10.1: Methods used for Innovation Analysis and Related Results Briefly describe methods used to periodically assess if this investment adheres to the current Departmental and FAA Enterprise Architecture and whether alternatives are available to this investment, including new technical solutions and other systems developed by other agencies. Include the results of E-Gov strategy reviews and updated analysis of alternatives, market research, benchmarking and other methods used to ensure innovative approaches and technical solutions are being sought and considered. Briefly describe the results of these analyses/studies/market research, etc., and any need to start considering alternatives to this investment. Also address steps taken to ensure workforce competency and training in relation to this investment. 10.2: What was the plan and schedule for performing technical refreshes in the current and next fiscal year? What are the associated costs to complete technical refreshes? 10.3: Are you planning a major systems upgrade at any time over the next four (4) years? If yes, during which fiscal year will this occur? Briefly describe why the upgrade is needed and the estimated cost of the upgrade.

11: SUMMARY OF FINDINGS AND RECOMMENDATIONS

If any cost, schedule, or performance variance is 10 percent or more, in the sections that follow provide a complete analysis of the reasons for the cost overrun or performance gap with planned actions to correct the variance and information on techniques that generated the savings.

11.1: Summary Gap Analyses

For each area of the operational analysis (Mission and business, customer/user/stakeholder, technical, and financial goals), describe significant performance gaps and their root cause, and what, if any, additional functionality, capacity, or performance is required. Include information about any gap in the investment’s ability to adhere to the current DOT and FAA Enterprise Architectures and to satisfy or comply with current customer, strategic, technical, and security requirements and standards. If any cost, schedule, or performance variance is plus/minus 10 percent or more, summarize the reasons for the cost overrun or performance gap with planned actions to correct the variance and share techniques that generated savings. Address lessons-learned, why the problems occurred (root cause), or how savings were realized. Explain if further analysis is planned to better determine variance causes and how to address them.

11.2: Opportunities/Alternatives for Improvements

Based on the gap analysis, identify opportunities or alternatives to address the gap by improving functionality or performance (effectiveness and or efficiency). These opportunities may include investing in technology compliant with the FAA and Departmental Enterprise Architectures, business process reengineering, or collaboration with another project. Discuss whether E-Gov initiatives can be leveraged. Describe if/how the project could deliver services more efficiently in a web-based environment.

| 11.3: Conclusions and Recommendations |
| --- |
| State if current benefits continue to justify the operational costs of the investment or whether it should be enhanced or terminated. Specifically recommend if existing asset should be 1) continued with no additional investment, 2) enhanced, 3) terminated, or 4) migrated to a similar asset and retired. If the asset is to be enhanced or terminated, summarize the actions to be taken this fiscal year. |
| 11.4: Program/Investment Owner Recommendation/Concurrence |
| 12 : ACTION PLAN |
| (If applicable) In the table below, list actions planned for each performance area analyzed and the status of these actions. Uncompleted In Service Decision (ISD) action plan activities should also be included. Actions may include plans to conduct analyses for alternate technologies or obtain more information, as well as corrective actions to address positive or negative cost or performance variances. |
| Action Planned | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Current Status/Progress made |
| Strategic and Business/Mission Support |
| Customer, User, Stakeholder Analysis |
| Technical Performance |
| Financial Performance |
| Other Related Actions (e.g., Integrated Logistics Support, Innovation, Risk, etc.) |

# APPENDIX C – USEFUL WEB LOCATIONS

FAA’s Exhibit 300 portal - https://nase.amc.faa.gov

FAA Acquisition Management System FAST URL - http://fast.faa.gov/index.htm

FAA Contract Writing Toolbox URL -   http://204.108.10.60/conwrite/

FAA Policies, Regulations, and Guidelines -   http://www.faa.gov/regulations/

FAA Flight Plan - http://www.faa.gov/AboutFAA/Plans.cfm

DOT Strategic Plan -  http://www.dot.gov/insdtdot/geninfo.htm?pg=stratplan

DOT Publications -  http://www.dot.gov/business/manuals_publications.htm

DOT Departmental Information Resource Management Manual (DIRMM -   http://cio.ost.dot.gov/policy/dirmm.html

DOT Capital Planning and Investment Control Guidelines - http://cio.ost.dot.gov/capital_programming/index.html

Department of Homeland Security (DHS) Strategic Plan -   http://www.dhs.gov/dhspublic/theme_home1.jsp

OMB URLs important for Capital Planning processes and documentation:

- OMB Circular A-11, Section 300, Planning, Budgeting, acquisition, and management of Capital Assets, The most recent official and final version of the Exhibit 300 reporting instructions and format document are on OMB’s website.  Section 300 includes OMB’s 5-Point Scoring Criteria for IT Investments (also used by FAA):  OMB Circulars are located on OMB’s website at: http://www.whitehouse.gov/omb/circulars/index.html.  Please note again that scoring is based on OMB’s perception of the strength of the IT project management, rather than simply the writing of the Exhibit 300.

- OMB Circular A-11, Section 53, Information Technology and E-Government.  This section or exhibit shows all of an agency’s IT and e-Gov spending, and lists major as well as non-major projects individually and using a unique project identifier (UPI).  This section of Circular A-11 is also found at:  http://www.whitehouse.gov/omb/circulars/index.html.

- OMB Circular A-94: Guidelines and Discount Rates for Benefit-Cost Analysis of Federal Programs:  This circular provides general guidance for conducting benefit-cost and cost-effectiveness analyses. It also provides specific guidance on the discount rates to be used in evaluating Federal programs whose benefits and costs are distributed over time. Located on OMB’s website: 
http://www.whitehouse.gov/omb/circulars/a094/a094.html#1

- The OMB Circular A-11, Part 7, Capital Programming Guide:  The document’s purpose is to provide guidance for a disciplined capital programming process for capital assets.  Located on OMB’s website: http://www.whitehouse.gov/omb/circulars/a11/cpgtoc.html

- Implementing the President’s Management Agenda for E-Government:  This document describes the E-Government achievements since February 2002, the challenges facing E-Government leaders in 2003 and 2004, and the strategy to address these challenges. Located on OMB’s website: http://www.whitehouse.gov/omb/egov/2003egov_strat.pdf

- The President’s Management Agenda is located at:  http://www.whitehouse.gov/omb/budget/fy2002/mgmt.pdf.

- The FEA reference models can be found on www.egov.gov, This URL includes the PRM with detailed guidance about how to incorporate PRM Indicators into the performance goals and measures in Table 2 of the Exhibit 300 and on how to incorporate the PRM into agencies’ performance goals and measures.

- The Federal Architecture Management System (FEAMS) is a web-based management system designed to provide agencies with access to initiatives aligned to the FEA and the associated reference models.  FEAMS should be checked to help identify other government initiatives that might be alternatives to addressing a performance gap.   FEAMS is located on:  https://www.feams.gov

- Information on EVMS is available at http://www.acq.osd.mil/pm.

# APPENDIX D – GLOSSARY OF ESSENTIAL TERMS

Appropriation

An appropriation is an act of Congress that enables Federal agencies to spend money for specific purposes. Congress must then pass appropriations bills to provide money to carry out government programs for that year. Appropriations bills divided up by type of program and agency into thirteen separate bills: Agriculture; Commerce/Justice/State; Defense; District of Columbia; Energy and Water; Foreign Operations; Interior; Labor/Health and Human Services/Education; Legislative Branch; Military Construction; Transportation; Treasury/Postal Service; and Veterans Affairs/Housing and Urban Development.

Authorization

An authorization is an act of Congress that establishes or continues a federal program or agency, and sets forth the guidelines to which it must adhere.

Balanced Budget

A balanced budget occurs when total receipts equal total outlays for a fiscal year.

Budget Authority (BA): The authority provided by law to incur financial obligations that will result in outlays.  Specific forms of budget authority include appropriations, borrowing authority, contract authority, and spending authority from offsetting collections.

Budget Resolution

The budget resolution is the annual framework within which Congress makes its decisions about spending and taxes. This framework includes targets for total spending, total revenues, and the deficit, as well as allocations, within the spending target, for discretionary and mandatory spending.

“Cap”

A “cap” is a legal limit on annual discretionary spending.

Capital Planning and Investment Control

A decision-making process for ensuring that information technology (IT) investments integrate strategic planning, budgeting, procurement, and the management of IT in support of agency missions and business needs. A Capital Planning and Investment Control cycle typically includes three major strategies: Select (investments are selected), Control (investments are controlled and monitored as they are implemented), and Evaluate (investments are evaluated after they have reached full operating capacity).

Clinger-Cohen Act

The Clinger-Cohen Act is also known as the Information Technology Management Reform Act of 1996. The act supplements the Paperwork Reduction Act of 1980 by establishing a comprehensive approach for executive agencies to improve the acquisition and management of their information resources (IT).

Cost Benefit Analysis

A systematic, quantitative method to assess the desirability of government projects or policies when it is important to take a long view of future effects and a broad view of possible side-effects.

Deficit

The deficit is the difference produced when spending exceeds revenues within a fiscal year.

Discount Factor

The factor that translates expected benefits or costs in any given future year into present value terms. The discount factor is equal to

1/(1 + i)t

where i is the interest rate and t is the number of years from the date of initiation for the program or policy until the given future year.

Discretionary Spending

Discretionary spending is what the President and Congress decide to spend through the 13 annual appropriations bills. Examples include money for such activities as the FBI and the Coast Guard, housing and education, space exploration and highway construction, and defense and foreign aid. See Mandatory Spending.

E-Government

E-Government (electronic government) refers to the federal government’s use of information technologies (such as Wide Area Networks, the Internet, and mobile computing) to exchange information and services with citizens, businesses, and other arms of government. Refers to the use by the Government of web-based Internet applications and other information technologies, combined with processes that implement these technologies, to enhance the access to and delivery of Government information and services to the public, other agencies, and other Government entities; or to bring about improvements in Government operations that may include effectiveness, efficiency, service quality, or transformation.

Entitlement

An entitlement program is one in which the federal government is legally obligated to make payments or provide aid to any person who meets the legal criteria for eligibility. Examples include Social Security, Medicare, Medicaid, and Food Stamps.

Fiscal year

The fiscal year is the federal government’s accounting period. It begins on October 1 and ends up September 30. For example, fiscal year 2003 began on October 1, 2002 and will end on September 30, 2003.

Full-time Equivalents (FTEs)

Civilian employment in the Executive Branch is measured on the basis of full-time equivalents. One FTE is equal to one work year or 2,080 non-overtime hours. For example, one full-time employee counts as one FTE, and two half-time employees also count as one FTE.

Lifecycle Costs

The overall estimated cost, both government and contractor, for a particular program alternative over the time period corresponding to the life of the program, including direct and indirect initial costs plus any periodic or continuing costs of operation and maintenance.

Major IT Investment (Investments that are required to be reported to OMB):  A Major IT investment means a system or investment that requires special management attention because of its importance to an agency’s mission; was a major investment in the FY 2005 submission and is continuing; is for financial management and spends more than $500,000; is directly tied to the top two layers of the Federal Enterprise Architecture (Services to Citizens and Mode of Delivery); is an integral part of the agency’s modernization blueprint (EA); has significant program or policy implications; has high executive visibility; and is defined as major by the agency’s capital planning and investment control process. OMB may work with the agency to declare other investments as major investments. Investments that are E-Government in nature or use e-business technologies must be identified as major investments regardless of the costs.

Mandatory Spending

Mandatory spending is authorized by permanent law rather than annual appropriations. An example is Social Security. The President and the Congress can change the law to change the eligibility criteria and thus the level of spending on mandatory programs, but they do not have to take annual action to ensure the continuation of spending.

Mixed Lifecycle Investment

An investment that has both development/modernization/enhancement (DME) and steady-state aspects. For example, a mixed lifecycle investment could include a prototype or module of a system that is operational with the remainder of the system in DME stages; or, a service contract for steady-state on the current system with a DME requirement for system upgrade or replacement.

Net Present Value/NPV

The difference between the discounted present value of benefits and the discounted present value of costs

Obligations: A binding agreement that will result in outlays, immediately or in the future.  Budgetary resources must be available before obligations can be incurred legally.

“Off-Budget”

By law, the Government must distinguish “off-budget” programs separate from the budget totals. Social Security and the Postal Service are “off-budget.”

“On-Budget”

Those programs not legally designated as off-budget.

Outlays: A payment to liquidate an obligation (other than the repayment of debt principal).  Outlays generally equal to cash disbursements, but also are recorded for cash-equivalent transactions, such as the subsidy cost of direct loans and loan guarantees, and interest accrued on public issues of the public debt.  Outlays are the measure of Government spending.

ROI

Return on Investment

Risk Adjusted Lifecycle Costs

The overall estimated cost for a particular investment alternative over the time period corresponding to the life of the investment, including direct and indirect initial costs plus any periodic or continuing costs of operation and maintenance that has been adjusted to accommodate any risk identified in the risk management plans.

Sunk Cost

A cost incurred in the past that will not be affected by any present or future decision. Sunk costs should be ignored in determining whether a new investment is worthwhile.

Useful Segment/Module

An economically and programmatically separate component of a capital investment that provides a measurable performance outcome for which the benefits exceed the costs, even if no further funding is appropriated.

Budget Authority and Outlays

Spending levels in the President’s Budget and in congressional budget resolutions are measured in dollars in two ways: budget authority and outlays. Outlays represent actual disbursements by the Treasury. When the Treasury issues a check in fiscal year 1998, that is a fiscal year 1998 outlay. Budget authority, on the other hand, is the legal authority for an agency to enter into obligations of dollars in a certain amount that will result in outlays. When Congress appropriates (appropriations bills) funds for a particular program, it is enacting budget authority – not outlays.

# APPENDIX E – EVM TERMS

- Planned Value (PV) = Budgeted Cost of Work Scheduled (BCWS): The sum of the budgets for all work packages, planning packages, etc., scheduled to be accomplished (including in-process work packages), plus the amount of level of effort and apportioned effort scheduled to be accomplished within a given time period.

- Earned Value (EV) = Budgeted Cost for Work Performed (BCWP): The sum of the budgets for completed work packages and completed portions of open work packages, plus the applicable portion of the budgets for level of effort and apportioned effort.  This is value earned to date.

- Actual Cost (AC) = Actual Cost of Work Performed (ACWP):  The costs actually incurred and recorded in accomplishing the work performed within a given time period.

- Variance – The difference (in $$) between your plan and your actuals

  - Cost Variance – the numerical difference between value earned (BCWP) and actual cost (ACWP)

  - Schedule Variance – The numerical difference between value earned (BCWP) and the planned budget (BCWS)

- Either one may be positive or negative

  - A negative value normally denotes either having accomplished less than scheduled or spent more than planned for the work accomplished.

  - A positive value normally denotes having accomplished more than what had been scheduled or spent less than planned for the amount of work that was accomplished.

- Performance Index – A measure of the efficiency of work performed to date

  - Cost Performance Index – cost efficiency factor achieved by relating value earned (BCWP) to the dollars actually spent (ACWP):  CPI = BCWP/ACWP

  - Schedule Performance Index – schedule efficiency factor achieved by relating value earned (BCWP) to the scheduled work (BCWS):  SPI = BCWP/BCWS

- Budget at Completion (BAC) – The sum of all budgets (BCWS) on the project.

- Estimate at Completion (EAC) – The sum of all actual costs to date plus the estimate of costs for authorized work remaining: EAC = ACWP + Estimate To Complete

  - This should be updated periodically

- Estimate to Complete (ETC) – That portion of the EAC that addresses total expected costs for all work remaining

# APPENDIX F – FEDERAL ACQUISITION REGULATION

FAR Performance Based Contracting Definition

Subpart 37.6—Performance-Based Acquisition

This subpart prescribes policies and procedures for acquiring services using performance-based acquisition methods.

37.601  General. 
(a) Solicitations may use either a performance work statement or a statement of objectives (see 37.602). 
(b) Performance-based contracts for services shall include— 
(1) A performance work statement (PWS); 
(2) Measurable performance standards (i.e., in terms of quality, timeliness, quantity, etc.) and the method of assessing contractor performance against performance standards; and 
(3) Performance incentives where appropriate. When used, the performance incentives shall correspond to the performance standards set forth in the contract (see 16.402-2). 
(c) See 12.102(g) for the use of Part 12 procedures for performance-based acquisitions.

37.602  Performance work statement. 
(a) A Performance work statement (PWS) may be prepared by the Government or result from a Statement of objectives (SOO) prepared by the Government where the offeror proposes the PWS. 
(b) Agencies shall, to the maximum extent practicable— 
(1) Describe the work in terms of the required results rather than either “how” the work is to be accomplished or the number of hours to be provided (see 11.002(a)(2) and 11.101); 
(2) Enable assessment of work performance against measurable performance standards; 
(3) Rely on the use of measurable performance standards and financial incentives in a competitive environment to encourage competitors to develop and institute innovative and cost-effective methods of performing the work. 
(c) Offerors use the SOO to develop the PWS; however, the SOO does not become part of the contract. The SOO shall, at a minimum, include— 
(1) Purpose; 
(2) Scope or mission; 
(3) Period and place of performance; 
(4) Background; 
(5) Performance objectives, i.e., required results; and 
(6) Any operating constraints.

37.603  Performance standards. 
(a) Performance standards establish the performance level required by the Government to meet the contract requirements. The standards shall be measurable and structured to permit an assessment of the contractor’s performance. 
(b) When offerors propose performance standards in response to a SOO, agencies shall evaluate the proposed standards to determine if they meet agency needs.

37.604  Quality assurance surveillance plans. 
Requirements for quality assurance and quality assurance surveillance plans are in Subpart 46.4. The Government may either prepare the quality assurance surveillance plan or require the offerors to submit a proposed quality assurance surveillance plan for the Government’s consideration in development of the Government’s plan.

# APPENDIX G – AMS PERFORMANCE BASED PAYMENT CLAUSES

3.3.1-32  Performance Based Payments (November 2000)

(a) Amount of payments and limitations on payments. Subject to such other limitations and conditions as are specified in this contract and this clause, the amount of payments and limitations on payments shall be specified in the contract's description of the basis for payment.

(b) Contractor request for performance-based payment. The Contractor may submit requests for payment of performance-based payments not more frequently than monthly, in a form and manner acceptable to the Contracting Officer. Unless otherwise authorized by the Contracting Officer, all performance-based payments in any period for which payment is being requested shall be included in a single request, appropriately itemized and totaled. The Contractor's request shall contain the information and certification detailed in paragraphs (l) and (m) of this clause.

(c) Approval and payment of requests. (1) The Contractor shall not be entitled to payment of a request for performance-based payment prior to successful accomplishment of the event or performance criterion for which payment is requested. The Contracting Officer shall determine whether the event or performance criterion for which payment is requested has been successfully accomplished in accordance with the terms of the contract. The Contracting Officer may, at any time, require the Contractor to substantiate the successful performance of any event or performance criterion which has been or is represented as being payable.

(2) A payment under this performance-based payment clause is a contract financing payment under the Prompt Payment clause of this contract, and approved requests shall be paid in accordance with the prompt payment period and provisions specified for contract financing payments by that clause. However, if the Contracting Officer requires substantiation as provided in paragraph (c)(1) of this clause, or inquires into the status of an event or performance criterion, or into any of the conditions listed in paragraph (e) of this clause, or into the Contractor certification, payment is not required, and the prompt payment period shall not begin until the Contracting Officer approves the request.

(3) The approval by the Contracting Officer of a request for performance-based payment does not constitute an acceptance by the Government and does not excuse the Contractor from performance of obligations under this contract.

(d) Liquidation of performance-based payments. (1) Performance-based finance amounts paid prior to payment for delivery of an item shall be liquidated by deducting a percentage or a designated dollar amount from the delivery payment. If the performance-based finance payments are on a delivery item basis, the liquidation amount for each such line item shall be the percent of that delivery item price that was previously paid under performance-based finance payments or the designated dollar amount. If the performance-based finance payments are on a whole contract basis, liquidation shall be by either pre-designated liquidation amounts or a liquidation percentage.

(2) If at any time the amount of payments under this contract exceeds any limitation in this contract, the Contractor shall repay to the Government the excess. Unless otherwise determined by the Contracting Officer, such excess shall be credited as a reduction in the unliquidated performance-based payment balance(s), after adjustment of invoice payments and balances for any retroactive price adjustments.

(e) Reduction or suspension of performance-based payments. The Contracting Officer may reduce or suspend performance-based payments, liquidate performance-based payments by deduction from any payment under the contract, or take a combination of these actions after finding upon substantial evidence any of the following conditions:

(1) The Contractor failed to comply with any material requirement of this contract (which includes paragraphs (h) and (i) of this clause).

(2) Performance of this contract is endangered by the Contractor's—

(i) Failure to make progress; or

(ii) Unsatisfactory financial condition.

(3) The Contractor is delinquent in payment of any subcontractor or supplier under this contract in the ordinary course of business.

(f) Title. (1) Title to the property described in this paragraph (f) shall vest in the Government. Vestiture shall be immediately upon the date of the first performance-based payment under this contract, for property acquired or produced before that date. Otherwise, vestiture shall occur when the property is or should have been allocable or properly chargeable to this contract

(2) "Property," as used in this clause, includes all of the following described items acquired or produced by the Contractor that are or should be allocable or properly chargeable to this contract under sound and generally accepted accounting principles and practices:

(i) Parts, materials, inventories, and work in process;

(ii) Special tooling and special test equipment to which the Government is to acquire title under any other clause of this contract;

(iii) Nondurable (i.e., non-capital) tools, jigs, dies, fixtures, molds, patterns, taps, gauges, test equipment and other similar manufacturing aids, title to which would not be obtained as special tooling under subparagraph (f)(2)(ii) of this clause; and

(iv) Drawings and technical data, to the extent the Contractor or subcontractors are required to deliver them to the Government by other clauses of this contract.

(3) Although title to property is in the Government under this clause, other applicable clauses of this contract (e.g., the termination or special tooling clauses) shall determine the handling and disposition of the property.

(4) The Contractor may sell any scrap resulting from production under this contract, without requesting the Contracting Officer's approval, provided that any significant reduction in the value of the property to which the Government has title under this clause is reported in writing to the Contracting Officer. The contractor shall credit the proceeds against the cost of performance.

(5) In order to acquire for its own use or dispose of property to which title is vested in the Government under this clause, the Contractor must obtain the Contracting Officer's advance approval of the action and the terms. If approved, the contractor shall exclude the allocable costs of the property from the costs of contract performance, and repay to the Government any amount of unliquidated payments allocable to the property.

(6) When the Contractor completes all of the obligations under this contract, including liquidation of all performance-based payments, title shall vest in the Contractor for all property (or the proceeds thereof) not—

(i) Delivered to, and accepted by, the Government under this contract; or

(ii) Incorporated in supplies delivered to, and accepted by, the Government under this contract and to which title is vested in the Government under this clause.

(7) The terms of this contract concerning liability for Government-furnished property shall not apply to property to which the Government acquired title solely under this clause.

(g) Risk of loss. Before delivery to and acceptance by the Government, the Contractor shall bear the risk of loss for property, the title to which vests in the Government under this clause, except to the extent the Government expressly assumes the risk. If any property is damaged, lost, stolen, or destroyed, the basis of payment (the events or performance criteria) to which the property is related shall be deemed to be not in compliance with the terms of the contract and not payable (if the property is part of or needed for performance), and the Contractor shall refund the related performance-based payments in accordance with paragraph (d) of this clause.

(h) Records and controls. The Contractor shall maintain records and controls adequate for administration of this clause. The Contractor shall have no entitlement to performance-based payments during any time the Contractor's records or controls are determined by the Contracting Officer to be inadequate for administration of this clause.

(i) Reports and Government access. The Contractor shall promptly furnish reports, certificates, financial statements, and other pertinent information requested by the Contracting Officer for the administration of this clause and to determine that an event or other criterion prompting a financing payment has been successfully accomplished. The Contractor shall give the Government reasonable opportunity to examine and verify the Contractor's records and to examine and verify the Contractor's performance of this contract for administration of this clause.

(j) Special terms regarding default. If this contract is terminated under the default provisions of any termination clause, (1) the Contractor shall, on demand, repay to the Government the amount of unliquidated performance-based payments, and (2) title shall vest in the Contractor, on full liquidation of all performance-based payments, for all property for which the Government elects not to require delivery under the Default clause of this contract. The Government shall be liable for no payment except as provided by the Default clause.

(k) Reservation of rights. (1) No payment or vesting of title under this clause shall—

(i) Excuse the Contractor from performance of obligations under this contract; or

(ii) Constitute a waiver of any of the rights or remedies of the parties under the contract.

(2) The Government's rights and remedies under this clause—

(i) Shall not be exclusive, but rather shall be in addition to any other rights and remedies provided by law or this contract; and

(ii) Shall not be affected by delayed, partial, or omitted exercise of any right, remedy, power, or privilege, nor shall such exercise or any single exercise preclude or impair any further exercise under this clause or the exercise of any other right, power, or privilege of the Government.

(l) Content of Contractor's request for performance-based payment. The Contractor's request for performance-based payment shall contain the following:

(1) The name and address of the Contractor;

(2) The date of the request for performance-based payment;

(3) The contract number and/or other identifier of the contract or order under which the request is made;

(4) Such information and documentation as is required by the contract's description of the basis for payment; and

(5) A certification by a Contractor official authorized to bind the Contractor, as specified in paragraph (m) of this clause.

(m) Content of Contractor's certification. As required in paragraph (l)(5) of this clause, the Contractor shall make the following certification in each request for performance-based payment:

I certify to the best of my knowledge and belief that—

(1) This request for performance-based payment is true and correct; this request (and attachments) has been prepared from the books and records of the Contractor, in accordance with the contract and the instructions of the Contracting Officer;

(2) (Except as reported in writing on __________), all payments to subcontractors and suppliers under this contract have been paid, or will be paid, currently, when due in the ordinary course of business;

(3) There are no encumbrances (except as reported in writing on _________) against the property acquired or produced for, and allocated or properly chargeable to, the contract which would affect or impair the Government's title;

(4) There has been no materially adverse change in the financial condition of the Contractor since the submission by the Contractor to the Government of the most recent written information dated _____________; and

(5) After the making of this requested performance-based payment, the amount of all payments for each deliverable item for which performance-based payments have been requested will not exceed any limitation in the contract, and the amount of all payments under the contract will not exceed any limitation in the contract.