# Last Date Saved:  8/17/2007

| Project Name: | Project Task Number: | Prepared by: (Project Manager) | Date: |
| --- | --- | --- | --- |
| MTA beam line installation | 20.11.8.1 | Fernanda G. Garcia | 8/17/2007 |

| Project Completion Date: 09/27/2007 | Report Date | 8/17/2007 |
| --- | --- | --- |
| Project Status | Status Report Summary |
| Project in jeopardy | If this box is checked, explain why the project is in jeopardy. |
| Project late | Catching up the lost time due to the strike |
| Project on time | If this box is checked, highlight the main activities. |

| Project Main Tasks | Notes |
| --- | --- |
| Shielding Work |  | Good progress with the shielding blocks. Many of the blocks were removed. Iron workers will continue removing the final layer on Monday. |
| Magnet inst. |  | Schedule to receive first truck on Monday (08/20) |
| Alignment |  | As soon the bottom layer is removed, alignment needs to tie both network and also do some chaulk line demarcations. |
| Vacuum inst. |  | Not started yet. |
| LCW Work |  | Task was supposed to start 3rd week of the shutdown. |
| Electrical Work |  | Catching up. Good progress with the cable trays installation. |

| Issues / Exceptions | Description of Issues / Exceptions |
| --- | --- |
| Scope change Resources not available Performance error Other | Dump line is under vacuum since 10:30 A.M. on Friday. Not clear what happened. Needs to be investigated further. |

Next Milestone :

Complete remove the shielding blocks and complete the alignment work.

Next 2 days tentative schedule:

- Finish the removal of the shielding blocks

- Complete alignment work

- Lower auxiliary equipment to aid the installation

- Start lowering the magnets, building the line from the linac end.