National Aeronautics and

Space Administration

George C. Marshall Space Flight Center

Marshall Space Flight Center, Alabama 35812

MICROGRAVITY CRYSTAL GROWTH

DEMONSTRATION (MCGD)

Project Plan

SCIENCE

DIRECTORATE

MSFC - Form 454 (Rev. October 1992)

Microgravity Crystal Growth

Demonstration (MCGD)

Project Plan

Approval Signatures:

_________________________________________________		_____________

Dr. Frank Rose, Director							Date

Science Directorate

_________________________________________________		_____________

Robin Henderson, Program Manager						Date

Microgravity Research Program Office

_________________________________________________		______________

Fred Sanders, Project Manager						Date

Microgravity Crystal Growth Demonstration

REVISION LIST

MSFC PROJECT PLAN for the MICRO-GRAVITY CRYSTAL GROWTH DEMONSTRATION (MCGD)

ORIGINAL DOCUMENT RELEASE DATE:

REVISION LETTER                       DATE                         APPROVAL

--------------------------                  ----------------                --------------------

### TABLE OF CONTENTS

1.  Introduction…………………………………………………………….	6

2.  Objectives………………………………………………………………	6

3.  Customer Definition and Advocacy……………………………………	7

4.  Project Authority……………………………………………………….	8

5.  Management……………………………………………………………	8

6.  Technical Summary…………………………………………………….	10

7.  Schedules………………………………………………………………..	11

8.  Resources………………………………………………………………..	11

9.  Controls…………………………………………………………………	12

10.  Implementation Approach……………………………………………..	13

11.  Acquisition Summary…………………………………………………	17

12.  Program/Project Dependencies………………………………………..	17

13.  Agreements……………………………………………………………	17

14.  Performance Assurance………………………………………………..	17

15.  Risk Management……………………………………………………..	19

16.  Environmental Impact…………………………………………………	21

17.  Safety………………………………………………………………….	21

18.  Technology Assessment……………………………………………….	22

19.  Commercialization…………………………………………………….	22

20.  Reviews………………………………………………………………..	22

TABLE OF CONTENTS (cont’d)

21.  Export Control…………………………………………………………	23

22.  Tailoring………………………………………………………………	23

23.  Documentation Retention……………………………………………..	24

# MCGD PROJECT PLAN

1.  INTRODUCTION

The Marshall Space Flight Center (MSFC) Science Directorate (SD) has authorized its Science Systems Department (SSD) to complete the Micro-gravity Crystal Growth Demonstration (MCGD). It will constitute the payload for the MSFC Future X Small Payload Access to Space Experiment (SPASE), authorized under contract NAS8-00111. The MCGD will be non-retrievable and will function as a proof of concept payload for the AeroAstro, Inc. (AA), SPASE (aka: “Bitsy”) spacecraft kernel. The primary goal of this mission is to demonstrate the capability of the “Bitsy” as a resource for low cost, rapid access to space.  The MCGD will consist of a single fluid cell for sucrose crystal growth and will be launched, attached to the SPASE spacecraft kernel as a Hitchhiker payload.

To be consistent with the SPASE spacecraft kernel, MCGD will demonstrate a streamlined, innovative, yet safe process, by which to design, fabricate and assemble a small flight project. The minimalist approach will be reflected in every aspect of this project plan. This plan, while not all-inclusive, will broadly address most facets of MCGD design, development, fabrication and delivery.  Further supporting plans will be minimized. Note that some typical flight payload requirements for the MCGD payload (eg debris analysis, hazard analysis) are being completed by AeroAstro at the SPASE mission level  under funding and direction of the SPASE contract and are not within the scope of the MCGD Project Plan.

2.  OBJECTIVES

The key word in understanding the primary objective of the MCGD is the word “demonstration”. The MCGD is being provided to allow the SPASE spacecraft kernel to functionally demonstrate the essence of low cost access to space. MCGD will provide data to be fed through the SPASE spacecraft kernel and down-linked as it demonstrates its on-orbit capabilities. MCGD is designed as a demonstration and is not intended for scientific community peer review.

The primary MCGD goal is scientific and straightforward, ultimately intended to provide data transfer throughout the mission and to provide some insight into the mechanism of sucrose crystal growth in a prolonged and undisturbed microgravity environment. A secondary MCGD goal is to employ extensive thermal instrumentation to quantify thermal design data for future experiments. Various thermal models have been employed to characterize the internal thermal environment of the MCGD canister. Verification of some or all of these models (through the use of MCGD orbital thermal data) would be both useful and valuable for similar follow-on flights. Accomplishment of either MCGD goal will require successful transmittal of data through Bitsy to the ground station and would thus constitute proof of the Bitsy’s mission support capabilities.

The mechanism of sucrose crystal growth is expected to be demonstrated as follows. The face growth rate of a sucrose crystal will be measured as a function of the solute super-saturation, as defined by the growth temperature, in a pure microgravity environment.  Due to the microgravity, the transport of the solute will be purely by diffusion. The measured rate of diffusive flux will thus be a function of the interfacial solute super-saturation. The measured rate of diffusive flux will be utilized to determine the super-saturation based upon prior ground based experimentation. The obtained data will be video down-linked through the SPASE spacecraft kernel and will then be modeled to characterize the solute concentration gradient profile about the crystal. Although one downlinked sucrose crystal growth cycle would constitute mission success, it is hoped that this on-orbit technology demonstration will be run repeatedly by manipulation of the growth solution temperature. If so, the sucrose crystal could be grown, dissolved and re-grown, repeatedly.

Innovation will be attempted in several aspects of the MCGD process. Specifically, in an effort to demonstrate simplified and cost-effective acquisition/fabrication, the MCGD will intentionally utilize Commercial, Off the Shelf (COTS) items in the broadest practical sense. Regardless of this stated objective, no hardware/component compromises will be made that would impact mission safety. The Future X SPASE spacecraft kernel is not designed for on-orbit or post-flight recapture. All MCGD crystal growth data will be recorded via an on-board, digital, video camera and down-linked to a ground station. One successful cycle of MCGD video data transfer would represent the first video data capture of orbital free-flyer crystal growth. Also, it would reveal the results from the first crystal growth ever completed in an absolute microgravity environment. In summary, the MCGD is intended to provide scientific data to exercise the Future X SPASE spacecraft kernel, and likewise is striving to achieve modest scientific goals, innovative processes, reduced costs and prompt delivery.

3.  CUSTOMER DEFINITION AND ADVOCACY

The MCGD has two customers. The MSFC Micro-gravity Research Project Office (MRPO) is funding the MCGD and constitutes the primary MCGD customer. However, the delivery of the MCGD flight hardware will be directly to the AA SPASE Mission Project Manager.  MCGD is to be the payload for the initial proof of concept flight for the Future X SPASE (aka: “bitsy”) spacecraft kernel. The MCGD Project Manager will provide regular project status to the funding customer, MRPO. The MSFC MCGD Project Manager will maintain a close and regular technical working relationship with AA personnel. The MCGD Project Team will communicate regularly with the AA engineering staff throughout the MCGD development and fabrication process to ensure customer advocacy and satisfaction with the end product.

4.  PROJECT AUTHORITY

The MSFC Science Systems Department (SSD) and MRPO have signed a letter of intent and commitment of funding for the MCGD. MSFC/SD has also provided a letter of commitment to AA, declaring that MSFC/SD will design, fabricate, test and deliver the MCGD for flight on the Future X SPASE Mission, mounted to the AA Bitsy kernel. MCGD Project Manager authority/responsibilities will cease after on-orbit release and payload checkout except for the provision of mission support as required and post flight data analysis and the final report.

5.  MANAGEMENT

The managerial approach to achieve completion of the MCGD will follow the latest revision of MPD-1280.1, but will be tailored as a small project per guidance and flexibility provided by NASA Procedures and Guidelines 7120.5A.

Management Responsibilities:  The MCGD PM will ensure that the MCGD and mission support tasking assigned to MSFC/SD is completed in an expedient, quality conscious and cost effective manner. MSFC/SD will coordinate with the AA SPASE Project Manager and his engineering staff, to assure that the MCGD and the Future X SPASE Bitsy kernel are compatible in fit, function, performance, safety and schedule. AA, MSFC/Science Directorate, MSFC/Pathfinder Program Office (TD14) and the Goddard Space Flight Center (GSFC) will respectively perform the following roles and responsibilities:

AeroAstro, Inc., will provide:

Future X SPASE Mission PI

Future X SPASE mission oversight and engineering

SPASE spacecraft kernel

Future X SPASE mission EGSE

Future X SPASE mission software

Integrated SPASE analysis, including MCGD

SPASE Spacecraft environmental test parameters

Shipping of the Bitsy kernel to MSFC for integrated systems tests

SPASE integration direction/support

Spacecraft kernel environmental test reviewers/approvers

Provide for a ground control station (may be contracted)

Payload integration into the Hitchhiker Ejection System

MSFC/SD will provide:

MCGD Funding and Program oversight

MCGD Project Manager

MCGD Systems/ Lead Engineer and support engineering

MCGD design support/engineering

MCGD flight crystal growth hardware/canister

MCGD integration with the Bitsy kernel

Integrated systems environmental testing and test coordination

Shipping crate, as required, for return shipment of integrated MCGD/SPASE

Shipping of the integrated SPASE to AA, post systems test

MSFC/QS (S&MA office) will provide:

Support to major MCGD reviews held at MSFC

#### Representation on MCGD CCB

Provide inspections as defined in this Project Plan

MSFC/TD will provide:

MSFC SPASE Project Manager

File form 1628 to NASA headquarters Code R for SPASE manifest

Representation of MCGD at all flight and ground safety reviews

GSFC/Shuttle Small Payloads Projects Office (SSPPO) will provide:

SPASE Mission Manager

Payload vibration test Marmon clamp (loaned from GSFC) per memo TD14 (00-15) 5/25/2000

Payload integration into the Hitchhiker canister

Payload safety and hazard analysis oversight

Payload presentation before the JSC STS Flight Safety Review Panel and KSC Ground Safety Review Panel

All MSFC/SSD efforts for the MCGD will be directly managed by the MCGD Project Manager in SD21. Technology demonstration objectives for MCGD will be documented in the Technology Demonstration Requirements Document (TDRD).  Engineering, technical and fabrication support for MCGD will be provided by SD22.  In-house fabrication will be provided through the SD support contract with Sverdrup, NAS 8-40-836. Technical information will be forwarded through the MCGD Systems Engineer to the AA SPASE Project Manager or through the designated AA engineering representative.  All S&MA tasks for MCGD will be conducted by the SD MCGD team, with the exception being: (1) inspection of those items specifically identified as safety critical including fasteners and their installation, (2) inspection of packaging prior to shipment, (3) inspection for sharp edges, and (4) MSFC S&MA support to the MCGD Configuration Control Board.  S&MA will provide quality requirements for procurement of critical fasteners as defined by the MCGD team.  All safety critical fasteners procured by MSFC will be procured as quality sensitive and will be routed through S&MA for receiving inspection.  Safety critical items will be inspected by the appropriate S&MA office. Managerial support for the MCGD efforts at MSFC may also be provided by the Science Systems Department (SD20), however, MCGD project funds will be under the direction of the MCGD Project Manager in SD21.

6.  TECHNICAL SUMMARY

MCGD requirements will flow down from the SPASE Requirements Document (2210-0002, AA-RQMT-TBD, and will be documented in the MCGD Systems Requirements Document and the Bitsy to MCGD Interface Control Document that will be produced in conjunction and cooperation with AeroAstro personnel. MCGD Level 2 demonstration requirements will be documented in the MCGD Technology Demonstration Requirements Document (TDRD). This information that follows in this section provides a general technical overview of the mission and a general description of the MCGD.

The Future X SPASE on-orbit mission lifetime is expected to be at least 6 months. The spacecraft kernel’s design and orbital parameters are intended to support low earth orbit (LEO). The prolonged microgravity environmental conditions are expected to deliver optimal sucrose crystal growth. The spacecraft kernel will have two general operational systems: the spacecraft kernel system and a sucrose crystal growth demonstration system. The primary goal of this mission (and the MCGD payload) is to provide AA with the opportunity to demonstrate its miniature SPASE spacecraft kernel. The MCGD will constitute the sole payload for this demonstration flight, along with spacecraft kernel-to-payload interface hardware.

The Future X SPASE spacecraft kernel will be launched as a STS HitchHiker payload while integrated into a “top opening” Hitchhiker canister. While on orbit the entire, sealed SPASE payload (to include MCGD) will be released from the Hitchhiker canister as a free flyer spacecraft. The Future X SPASE spacecraft kernel can accommodate launch upon either the GAS beam, GAS bridge or other similar Hitchhiker mounting platforms. The SPASE miniature spacecraft kernel (w/o payload) measures approximately twelve (12.0 ) inches long, by twelve (12.0) inches wide by three and one-half (3.5) inches high. The fully (double) enclosed, MCGD sucrose crystal growth canister will have one end permanently mounted to the SPASE spacecraft kernel. The other end of the MCGD canister will be open, and may carry an extra solar panel. Orbital deployment of the SPASE payload will be provided by the Hitchhiker Ejection System (HES). The SPASE system will interface with a Marmon clamp release mechanism and payload interface plate. (Refer to GSFC Hitchhiker CARS 740-SPEC-008, 1999, pgs. 2-127-129).  Note, that after orbital release the Future X SPASE payload is not intended to be recovered or retrieved.

After successful deployment, the Future X SPASE spacecraft will achieve a stable LEO and will function as a self sustaining, free flyer at the disposal of the MCGD team. The spacecraft kernel will be capable of executing up link commands and will down link scientific video and low-bandwidth data concerning crystal growth status and limited spacecraft kernel parameters, such as power generation and solar panel sun exposure. The MCGD will provide in-flight on-board video that will closely view the process/progress of sucrose crystallization and then transmit these images back to the MCGD Ground Station at the University of Alabama in Huntsville (UAH) for dissemination to the science community via the internet. The MCGD Ground Station will be a simplistic arrangement, and will be accomplished/established with the cooperation of UAH staff and students. The MCGD team will disclose and distribute data pertaining to sucrose crystal growth rate on a monthly basis throughout the duration of the mission. This monthly status will include a report on the performance of the technology demonstration, a brief synopsis of spacecraft kernel health and a discussion of accomplishment/determination of scientific milestones.

MSFC/SD will have no role in the SPASE spacecraft kernel design, fabrication or management.  To the extent that the technology demonstration requirements can still be met, the MSFC/SD MCGD project will be responsive to the direction of the AA SPASE Project Manager.

7.  SCHEDULES

The MCGD project schedule is maintained by the MCGD PM and is done in Primavera software. The MCGD schedule is a stand-alone, detailed entity and is not included in this project plan to avoid continuous revisions to this document. A copy of the current schedule is readily available from the MCGD PM upon request.   MCGD milestone target dates are as follows:

MCGD SRR/PDR – May 2000

MCGD CDR – Aug 2000

MCGD pre-delivery FRR – Feb 2001

MCGD delivery to AA – Feb 2001

8.  RESOURCES

MCGD is funded by MRPO for $156K and 4 FTE’s, for a development and fabrication effort that is expected to take a few months less than two calendar years from the Authority to Proceed (ATP) of the AA contract for SPASE.  The $156K is consistent with MSFC/SD in house estimates for this project. The original cost estimates are valid and are available upon request from the MCGD PM. The specific man-loading for this project meets the current requirements of the MSFC Collaborative Work Commitments (CWC) budgeting process.

Resource allocation is expected to require $56K during the remainder of FY00 (development), with the remaining $100K to be expended during FY01 (fabrication, testing and delivery). The funds provided do not include any resources for mission operations and data analysis (MO&DA), which is to be funded by MRPO. Mission Operations (to include data collection and posting on a SPASE web site) are being conducted by the University of Alabama in Huntsville (UAH), under the SPASE mission contract and are not within the scope of this effort. It is estimated that the MO&DA effort will be supported by 1/3 FTE of a graduate students time for 6 months (approx. $8K). FTE allocation for MCGD development is not expected to exceed the level of 4 civil service FTE’s at any given time throughout the development, fabrication and delivery of the MCGD. The usage rate of the 4 FTE allocation is expected to require 2 FTE’s in FY00 and 2 FTE’s in  FY01. MCGD completion and delivery is expected to require approximately 18 months.

9.  CONTROLS

For the MSFC/SD effort to support the Future X SPASE mission, technical (design) control is only applicable to those flight components of the mission that are to be designed, modified, and/or fabricated by MSFC/SD.

Design Control:  All such design work is intended to be completed “in house”, tailored in accordance with the latest revision of MPG 8060.1 and should be accomplished by Science Directorate (SD) personnel. Typical stand-alone control plans (e.g. a configuration management plan, a quality plan) will not be produced.  As such, documentation will be provided within the body and contents of this Project Plan (Note: test plans will be produced separately).  A Risk Identification Matrix has been produced which identifies project risks and mitigation procedures. The MCGD team will produce a MCGD Systems Requirements Document (SRD). The MCGD SRD will be a living document and will serve as the quality record for requirements, defining verification methodology and the documentation of compliance verification for each requirement. The Bitsy to MCGD Interface Control Document will be produced by TD with MCGD input.

The MCGD Configuration Control Board (CCB) will ensure the baselining of the MCGD design and will be responsible for MCGD configuration control in accordance with this plan. The MCGD CCB will approve the issue of standard drawing numbers. Any MCGD document or drawing that is issued a number will then be considered to be a MCGD “controlled document/drawing” and will thereafter be subject to change/redline approval and signature of the MCGD CCB. MCGD working drawings will be held by the responsible engineer, but paper copies of all final MCGD fabrication drawings will be held by the MCGD PM, who will serve as the project repository for all controlled drawings and documents.   The MCGD CCB will sign and date all controlled document/drawing baselines/redlines. Should any drawing require a redline change, the latest date of CCB signature will always indicate the controlling iteration of that drawing. The MCGD CCB will also review the project Engineering Parts List (EPL) which will document all flight materials and all flight parts (COTS and otherwise). As a minimum, the MCGD CCB will consist of the following members from within MSFC/SD and S&MA, and will sign all controlled drawings and documents.

Chair: MCGD Project Manager: MSFC/SD20

MCGD Systems/Lead Engineer: MSFC/SD SD22

MCGD Design Engineer (for subject component): MSFC/SD SD22

S&MA Representative: MSFC/QS

Technical nonconformance reporting and disposition will be conducted within the MCGD team and will be resolved by the members of the MCGD CCB, as described above. The MCGD team will evaluate and the CCB members will resolve all issues of potential impact upon mission safety and performance. Should the circumstance require it, experts from outside the MCGD team would be sought for further comment and opinion on a gratis basis.  A safety, interface, or AA requirement related nonconformance would be reported to the SPASE PM at Aeroastro and resolved according to the oversight and direction of the NASA center responsible for the integration and acceptance of the SPASE/MCGD Hitchhiker payload (GSFC). Final disposition for any and all such changes, alterations, modifications, to include any required changes to this plan, must be approved and documented by the MCGD CCB. Final release of MCGD controlled drawings/documents will be derived from the redline drawings/documents and will be signed/dated by the MCGD CCB. The MCGD Project Manager will serve as the sole MCGD documentation repository and will maintain copies of all quality records.  Test nonconformances will be documented on MSFC Form (3473) Discrepancy Record (DR) and  controlled and dispositioned by the MCGD CCB.  Test discrepancies upgraded to a DR will be dispositioned by a Material Review Board (MRB) consisting of S&MA (chair), the MCGD Project Manager, and the MCGD Systems/Lead Engineer. The CCB Chairman has final approval authority for CCB actions.

Control of customer-supplied product will be implemented per the Customer-Supplied Product Arrangement (CSPA), TD14-003.

10.  IMPLEMENTATION APPROACH

The MCGD will be developed “in-house” within MSFC/SD, utilizing a team approach to provide civil service management and civil service engineering/design support. MSFC civil service design support, engineering support and civil service environmental test support will be sought outside of SD, while existing (on-site) SD support contractor technicians will be used to perform MCGD flight hardware production/fabrication work, as required. Collaborative Work Commitments (CWC’s) will be implemented where required, per the MCGD Work Breakdown Structure (WBS).

The MCGD does not constitute program critical hardware. This is verified by the 29FEB00 letter from TD14/SPASE Project Office to SD21/MCGD Project Office. As such, MWI 6410.1 Packaging, Handling and Moving Program Critical Hardware (PCH), para 5.15, does not apply. SD is not required to follow the PCH transportation requirements for SPASE, MCGD or parts thereof.

This project plan will not circumvent or reduce those procedures that are consistent with good engineering practice for the production of flight hardware. However, it is essential that all steps taken represent the best value to the MCGD project. Therefore, certain MSFC support organizations may not be called upon to perform tasks they traditionally complete for larger, more complex, fully funded, projects. This does not mean that those tasks will go undone. However, SD MCGD team personnel will perform most of the quality inspection tasks required by this plan, with the exception being inspection of those items determined to be safety critical. Safety criticality for the SPASE hardware is being determined by AA in conjunction with GSFC (the payload to spacecraft integrator). Inspection of any MCGD items identified as safety critical will be performed by the MSFC S&MA Office.  MSFC S&MA will also approve of fasteners and their installation and inspect for sharp edges.  The MSFC S&MA office is requested to support the MCGD Project as an independent reviewer through their attendance and support of major MCGD reviews held at MSFC as well as providing representation to the MCGD Configuration Control Board.

The MSFC/SD MCGD tasking will require mechanical design, electrical design and fabrication.  There is no MCGD flight software. Each design engineer will provide inputs and comments through the MCGD Systems Engineer to ensure that all requirements are defined before designs are finalized and fabrication is begun. Mission level design reviews (e.g. PDR, CDR) are coordinated with the AA SPASE Project Manager.  MSFC/SD team personnel will participate in these reviews by telecon and/or in person, as directed by the MCGD PM, and to the extent that travel funding is available. The MCGD PM will also conduct in-house, weekly MCGD/AA project team telecons.  The weekly telecon between MSFC/SD and AeroAstro, Inc., will ensure that MCGD design work is meeting system, interface, and operational requirements and progressing as scheduled. As a minimum, the MCGD Project Manager, the MCGD Systems Engineer and MCGD design engineers will participate in these weekly telecons, along with other MSFC support engineers/personnel, as appropriate. With regards to the MCGD work package, MSFC/SD is essentially functioning as the sub-contractor for delivery of this simple scientific payload. Definition and design of the payload to Hitchhiker interface structure lies with the AA SPASE Project Manager .

The MCGD Project Manager will utilize redline drawings throughout the MCGD design and layout processes as necessary. MSFC/SD MCGD CCB (see section 9) will maintain the baselined and redlined MCGD configuration/design drawings within SD. The MSFC/SD CCB will not release finished drawings until the time for fabrication. MCGD drawings will be baselined thru the MSFC release desk prior to shipment of the MCGD to AA.  A full set of MCGD as-built drawings and MCGD controlled documents will be delivered to the AA SPASE Project Manager at the time of hardware delivery. A second full (paper copy) set of MCGD as-built drawings and controlled documents will be also held by the MCGD PM per Section 23.

The MCGD Project Manager, working with an SD engineer serving as the MCGD project purchasing agent, will have complete oversight for the purchase, certification, locked storage, use and documentation of all MCGD flight components (COTS or otherwise). All electrical parts will be stored in anti-static bags. Vendor certification, receipts and component traceability will be maintained as appropriate for all MCGD flight materials and components. This team approach to the acquisition, locked security and utilization of flight hardware components provides a continual audit trail for MCGD flight hardware. This procedure equivocates more stringent flight hardware acquisition approaches at a greatly reduced cost, commensurate with the very limited funding for this demonstration.

MSFC SD contractor personnel will be requested to inspect all MCGD flight drawings prior to final flight hardware fabrication in order to ensure that the provided MCGD drawings and notations conform with industry drawing standards established for produceability. Given the simplicity of and low funding for MCGD hardware, quality inspections for MCGD drawings will not be conducted at every drawing level. This project management plan will not request the quality organization to conduct “build to print” inspections of MCGD piece parts. All parts, fabricated or purchased, will be closely inspected by the MCGD CCB and MCGD design engineers who have already built bench models of several MCGD components.  All parts inspections will be documented with the date and CCB acceptance signatures verifying that all parts have been fitted and tested. The MCGD project will not build an engineering model. All components will be fabricated from flight material stock and flight parts. The first “proto-flight” part produced may eventually be designated by the MCGD CCB as the flight part if form, fit, function and testing permits (as described below).

Wherever possible, MCGD system verification will be done by testing instead of analysis. Separate test plans will be written and are not included in this project management plan. Analysis may be utilized on a limited basis, particularly to characterize the MCGD canister thermal environment. All verification, validation and functional testing will be conducted and documented by MCGD team personnel and MCGD CCB, with the exception of vibration testing as described below. MCGD team personnel are well equipped and experienced in verification testing for flight hardware and software. The MCGD team is situated such that many iterations of pertinent tests can be run to characterize/verify hardware performance and response. Integrated environmental testing (to include EMI/EMC testing, as required) on MCGD and the SPASE (aka “bitsy”) spacecraft kernel will be done within MSFC. MSFC/SD expects AA to deliver the Future-X spacecraft kernel to MSFC for combined environmental testing. Combined MCGD/bitsy (integrated payload) testing is being done in an effort to save the overall mission the expense of conducting separate tests for MCGD and for SPASE, then having to retest upon integration. Therefore, the MCGD will conduct one extensive series of combined, integrated payload environmental testing. The integrated test requirements for SPASE/MCGD will be jointly developed by AA/MSFC SD22 and documented in test plans separate from this document. The combined Environmental Test Plans for the SPASE/MCGD will then be compiled, written and produced by SD22 personnel and reviewed by/concurred with by AA. AA will further provide to MSFC, in writing, all Future-X SPASE pre-test/post-test functional testing requirements. Integrated payload thermal-vac testing will be conducted within SD and the results will be documented by the MSFC/SD MCGD team. Vibration testing will be conducted and documented by MSFC/ED personnel. MSFC/ED will provide the post-test summary report to the AA SPASE PM and the MCGD PM for the vibration testing.

When environmental and functional testing are successfully completed, the MCGD hardware (still integrated with the Future-X SPASE spacecraft kernel) will be delivered (without exchange of title) by MSFC/SD personnel, directly to the SPASE Project Manager at AeroAstro, Inc.  A Form 57 will be prepared and the MCGD will go thru MSFC shipping for packaging.  MSFC Quality shall approve packaging only.  AA will be required to provide a letter to the MCGD PM of acknowledgement and acceptance, upon delivery. AA will implement delivery of the integrated SPASE payload to GSFC and will observe Hitchhiker integration at GSFC and observe payload integration into the STS launch vehicle at KSC. MCGD will not require any KSC on-pad access prior to STS cargo bay closure.  The following provides the Level 2 MCGD Work Break Down Structure.

11.  ACQUISITION SUMMARY

The MCGD will be accomplished “in-house” and the procurement of significant off-site support is not anticipated or expected. The most likely off-site procurement would be minor machine shop work.

MCGD will use COTS flight hardware wherever possible. However, it is not possible to use COTS hardware on components that are deemed to be safety critical (e.g. per GSFC,  all fasteners). All MGCD safety critical flight certified parts and COTS components (that are within acceptable cost parameters according to the FAR) will be procured by US Government Credit Card. A partial list of typical MCGD COTS items for flight includes aluminum stock, electronic parts, wiring, seals, insulation, mylar, glass tubing and shrink tubing. Documentation of all parts purchased, to include receipts and flight certifications (as appropriate), will be maintained by the MCGD PM.  All flight hardware purchased with credit cards will be in accordance with MWI 5113.1.

- PROGRAM/PROJECT DEPENDENCIES

MCGD and the SPASE mission has no external project dependencies other than launch services which is being secured by AA.

13.  AGREEMENTS

(1) MCGD funding letter signed by MRPO

(2) MSFC/SD letter of commitment to AA to provide the MCGD

(3) MSFC Future-X SPASE contract w/AA, released late July 14, 2000.

(4) Customer-Supplied Product Agreement w/AA

14.  PERFORMANCE ASSURANCE

(a) GENERAL: The primary objective of the MCGD is to achieve a successful  technology demonstration while minimizing every aspect of overhead costs, employing process innovations and not compromising safety. Extensive quality control expenditures are not budgeted, nor desirable given the limited scope and funding for this project. It is the responsibility of the entire MCGD team, and the ultimate responsibility of the MCGD project manager, to ensure the best possible quality for this payload.

(b) RELIABILITY: Reliability will be demonstrated by repeated testing wherever possible. Active systems will be minimized in the design phase and all components and systems will be thoroughly tested in the lab.  MCGD will have no mechanisms and will be of robust structural design. Final acceptance of product reliability will lie with the MCGD CCB. The MCGD team will be responsible for all aspects of Reliability except as specifically noted in this Plan

(c) QUALITY ASSURANCE: Determination of the quality of workmanship lies with the MCGD team and especially with the MCGD CCB. The MCGD team will perform post fabrication inspections on all piece parts to ensure that they conform to the intended design specifications. The final determination for quality of workmanship and function will be demonstrated by an array of environmental and operational testing. Final acceptance of the components and release of the MCGD product will be the responsibility of the MCGD CCB. The MSFC S&MA Office responsibilities for Quality Assurance are described in detail in other sections of this document.

(d) PARTS: The MCGD is intended to demonstrate that selected COTS parts can perform safely and acceptably in limited space flight applications. This aspect of MCGD is a major facet of the rationale for the low funding of the project. All selected COTS parts will be inspected and tested to determine their suitability. Wherever allowed within US Govt. costing regulations, government credit cards will be utilized for parts/components purchases in an effort to streamline the parts acquisition process. All parts will be inspected upon delivery, labeled according to the MCGD Engineering Parts List (EPL) and stored in a locked parts cabinet within a secure SD storage area. Anti-static bagging will be provided for electrical parts. The parts will be held in secure storage until required for use and the storage area key will be held by a MCGD team member. The keeper of the key will also maintain a parts log book for notation of parts received and removed. The MCGD PM will be ultimately responsible to maintain all purchasing documentation and component certifications per Section 23.

(e) MATERIALS and PROCESS CONTROL: MCGD materials will be tracked by the MCGD team, throughout the fabrication process to ensure that only approved/purchased project materials are used. Records of materials and process will be maintained by the MCGD PM per Section 23. The MCGD PM will conduct impromptu visits to the fabrication areas to observe ongoing MCGD work. If testing, observation and/or analysis reveals that changes in materials or components are required, then the MCGD CCB will adhere to the change process as described in the Controls section of this document.

(f) PERFORMANCE VERIFICATION: Pre-launch performance of the MCGD will be verified by test, where practical, on all functional/operational parameters. However, some aspects of performance cannot be fully verified outside of the orbital and micro-gravity environments. It will be particularly difficult to absolutely assure the performance of the MCGD thermal stabilization system in other than orbital conditions since the attitude control system is completely passive and the spacecraft orbital attitude is inexact, although predictable. Likewise, the performance of the growth cell could be somewhat altered by launch dynamics, time delays and micro-gravity itself. For example, it is not assured that the sucrose crystal will grow at the desired growth location (i.e. the tip of the sting). Further, it is not assured that the attitude control system (two magnetized steel stabilization bars) will totally damp out all the extraneous effects (motion) due to gravity. In any case, operational efforts will be taken to meet all the scientific requirements, even if certain systems function at less than an optimal or anticipated level.

Instrumentation will be provided (e.g. thermal sensors) to return orbital engineering feedback that might influence future designs for similar payloads. On-orbit performance will be monitored and down-linked in order to determine micro-gravity conditions, temperature oscillations and crystal growth/quality. Solar cell performance will be monitored by instrumentation internal to Bitsy and provided by AA.  All crystal growth information will be gathered and transmitted by video observation (visual inspection). Regardless of the success or failure to grow sucrose crystals, the availability of this on-orbit information from MCGD will serve to broaden the knowledge base in design and fabrication of future low budget, free flyer experiments.

(g) CONTAMINATION CONTROL: MCGD does not pose an external contamination threat (e.g. to ground crews, the STS crew or to the STS itself). MCGD will employ a simple, straightforward design and will minimize and control the few possible sources for internal contamination. Internal contamination mitigation can be anticipated in three primary areas. For example, crystal growth data is to be captured and transmitted by a miniature digital video camera. The lens of this camera might be subject to coating and clouding if certain materials (e.g. plastics) out-gas during the mission. The thermal vacuum environment could precipitate out-gassing of hydrocarbons from undesirable plastics which could cloud the lens over a short time. Secondly, the field of view is subject to simply being obscured by floating debris (e.g. loose insulation) that might drift toward and lodge between the camera lens and the growth cell. The design will shroud the lens in such a manner so as to preclude contact with floating debris from any source. Contamination from leaking crystal growth medium (4 mls of sugar water, or approximately 1/7 oz.) is not considered to be a contamination risk although any such leakage would result in scientific failure. Regardless, design steps will be taken to adequately seal and contain the growth medium, as growth medium leakage constitutes a single point failure.

(h) SOFTWARE ASSURANCE: MCGD has no flight software.  Data handling as well as all command and control functions are provided by the Bitsy spacecraft kernel.

(i) MAINTAINABILITY:  The MCGD will not be retrieved or serviced during its operational life. As such, maintainability is not applicable to this project/product. .

- RISK MANAGEMENT

Risk, within this section, addresses technical risk only. Risk analysis will be an on-going process and will be the general responsibility of the MCGD CCB and the ultimate responsibility of the MCGD PM.

Technical risk has been numerically evaluated by subsystem comparison, considering past engineering experience, flight history and technology maturity. An assigned values risk map was built. The consensus result is that the primary risk of MCGD lies in the limited ability of the MCGD thermal control system to maintain the relatively narrow temperature range required by the MCGD team in order to properly grow sucrose crystals. MCGD can be heated, but no cooling loop can be provided due to costs and complexity. Recognizing this risk, the crystal growth support structure can be variably biased to provide an optimal rate of heat transfer from the growth cell to the canister exterior. In addition, thermal modeling and analysis is being iterated by multiple sources to closely determine MCGD thermal profiles. Extensive laboratory testing is planned to ensure that the final design delivers the best thermal stability available within the budget of MCGD. However, since thermal control is acknowledged to be difficult, it has been determined to capture actual on-orbit thermal data, regardless of the crystal growth success or failure.  This will permit engineers to further refine thermal models for future flights of similar experiment canisters. The MCGD thermal data also serves to provide a secondary data source for downlinking whereby “bitsy” can demonstrate proof of orbital functionality.

The assigned values risk map (matrix) revealed that the second greatest technical risk to MCGD came from the COTS solar panels. There is no orbital flight history for “off the shelf” solar panels. Bids were requested for typical “flight” solar panels and the cheapest of those were far too costly for the MCGD budget. However, it is within the charter of MCGD to seek out those opportunities to fly COTS hardware that might result in future savings. There is no doubt that one of the largest cost drivers to small free flyer missions relates directly to solar panel costs. A successful flight of COTS solar panels could result in significant future savings. In an effort to mitigate the perceived technical risks of COTS solar panels, early environmental testing of the selected terrestrial solar panels has been conducted at MSFC. That series of tests, which was conducted entirely separate from and in addition to the environmental testing of the actual flight COTS solar panels, characterized the performance and true technical risks posed by those COTS panels.  The tests consisted of a rigorous series of thermal vacuum tests, vibration tests and flash tests to determine efficiency following each test sequence.  The results of these tests were such that the decision to fly COTS solar panels on this mission was made based on the demonstrated capability of the COTS panels to withstand the rigors of launch and repeated thermal cycling with no apparent loss of efficiency.

The risk values map revealed that the third greatest technical risk to MCGD was the potential for leakage of the crystal growth medium (sugar water) primarily due to freezing during the interim period between launch and full power availability (approx. one week). While the leakage of such a small volume (4 mls or approximately 1/7 oz.) of sugar water poses no safety risk, such leakage would represent technical failure of the crystal growth demonstration. The fluid growth medium leakage is a single point failure and the limited MCGD budget cannot provide redundancy. Extensive testing will be done, including freezer tests. Design efforts will focus on the shape and mounting of the growth cell to provide a strong acceptable design.

The other MCGD subsystems and components were determined to pose a relatively low level of technical risk. The risk analysis for the Future-X SPASE “bitsy” spacecraft kernel is the responsibility of AA.

16.  ENVIRONMENTAL IMPACT

MCGD is designed to completely burn up in the earth’s atmosphere during re-entry and it is built entirely of light weight, non-hazardous materials. Given its benign nature, it qualifies for a Categorical Exclusion from any EPA requirement to submit an Environmental Assessment or an Environmental Impact Statement. It poses no threat to the environment either assembled or in part. The growth medium is organic (sugar water) and could be safely ingested.

17.  SAFETY

MCGD is a non-mission critical Hitchhiker payload and will be entirely double contained within its structural canister, in addition to being fully contained within a Hitchhiker payload canister.  The MCGD is a benign payload and poses no injury or illness hazard to ground support personnel, ground support systems, the STS, the overall STS mission or the flight crew.  It has no mechanisms, no hazardous chemicals and generates no significant levels of electrical charge.  AeroAstro will perform all hazard analyses required to verify MCGD conformance to Agency safety requirements.  MCGD will provide inputs to AeroAstro who will inturn provide the appropriate safety data input into the SPASE mission safety data package.  MCGD safety data will be reviewed at all SPASE and internal MCGD milestone design reviews.  MCGD personnel will support all SPASE flight and ground safety reviews.  The SPASE Project will represent MCGD in all flight and ground safety reviews in accordance with the plan presented in FXP-EXP-SPASE-PLAN-001, Figure 13, “Flight Safety Process”.  This representation will extend to Flight Readiness Reviews, Prelaunch Assessment Reviews, and the MSFC Payload Safety Readiness Review Board process.  No System Safety support from MSFC S&MA is requested, with the exception of support to major MCGD design reviews to be held at MSFC.

MCGD Safety compliance data will be included in the SPASE Mission Safety Data Packages.  MCGD will support all SPASE flight and ground safety reviews.  SPASE Project Manager will represent MCGD in all flight and ground safety reviews in accordance with the plan presented in FXP-EXP-SPASE-PLAN-001, Figure 13, “Flight Safety Process”.

18.  TECHNOLOGY ASSESSMENT

MCGD does not represent a technology push from a science perspective, but it does advance space flight technology in several ways. As the sole payload for the SPASE spacecraft kernel (“bitsy”), the MCGD will provide the means by which SPASE can prove itself as an orbital resource for rapid and relatively inexpensive access to space. If data downlink is successful, MCGD will constitute the first instance wherein a flight crystal growth apparatus was designed and flown such that all data was gathered in an microgravity environment of long duration without payload recovery.

MCGD is intended to maximize the use of COTS items and should expand the list of low cost items that could be safely and reliably used in subsequent flight systems of similar design and mission. MCGD will also seek to expand the knowledge base of thermal modeling for small free flyer spacecraft by providing on-orbit thermal data for direct comparison to the thermal models developed by AA and/or MSFC. While the mission life goal is only six months, MCGD will also be watched closely to ascertain which COTS items fail to complete or perhaps surpass their expected mission life. The largest contribution to future missions would seem to lie in the ability of MCGD to obtain adequate performance and power generation from the size limited COTS solar panels.

19.  COMMERCIALIZATION

While the MCGD does not constitute a commercially appealing entity, a successful flight may indirectly lead to greater interest in space flight by commercial interests. The SPASE/MCGD demonstration of a streamlined process and cheaper access to space could serve to encourage space flight by small businesses and commercial entities that heretofore had felt it was simply too cumbersome and too expensive to attempt R&D in space. As a pathfinder for low cost entry into space, MCGD could have a significant impact as an educational outreach tool, serving to encourage low budget space flight by universities and other educational organizations. For this reason, it is imperative to seek all opportunities to reduce the MCGD hardware/mission preparation process while not jeopardizing safety. The more straightforward the process, the more follow-on interest it may create.

20.  REVIEWS

As travel funds permit, the MCGD Project Manager will attend all major reviews scheduled by the AA SPASE Project Manager.  Technical Interchange Meetings (TIM) required by the Goddard Space Flight Center (GSFC) Hitchhiker Payload Office will be attended. GSFC has held only one such TIM thus far, and GSFC has agreed to limit the number of such required meetings in a cooperative effort to hold down project costs. The schedule and content of these GSFC reviews are yet to be determined. In addition, the MCGD PM will conduct three major internal reviews; a project level System Requirements Review/ Preliminary Design Review (May 2000), a project level Critical Design Review (September 2000), and a project level pre-delivery/post test Flight Readiness Review (February 2001). These internal reviews will be conducted in accordance with MPG 8060.1. In addition, weekly intra-team product reviews will be conducted to ascertain/coordinate team progress. There will also be formal monthly project reviews with SD20. MCGD team reviews, in conjunction with the MCGD CCB, will cover all applicable aspects of design progress, fabrication status, assembly, test readiness and test results. Design review minutes/results will be maintained by the MCGD PM as a quality record per Section 23. The MCGD PM and the entire project team will be available to provide MSFC/SD management with further information, as requested. Given that the MCGD is funded as a demonstration, no science community peer reviews, non-advocate reviews, Independent Assessments (IA) or Independent Annual Reviews (IAR) will be required for MCGD.

The FRR Board will include the SD20 Manager (chairman), SD21 Group Lead, SD22 Group Lead, a SMO representative, a S&MA representative, and a MRPO representative.  The SD20 Manager will author the certificate of flight readiness to be provided to the SPASE Project Office.

## 21.  EXPORT CONTROL

MCGD will follow all US laws and regulations regarding export control per MSFC procedures. There are no expected Export Control issues since SPASE involves only US participants.

22.  TAILORING

All tailored items listed below are discussed in greater detail in the appropriate section of this document.

The stated objective of MCGD is to provide a demonstrative payload for the SPASE (“bitsy”) spacecraft kernel. MCGD is striving for cost/schedule/process innovation in several areas, while intending to achieve the self-appointed science objectives in a safe manner. To succeed within the limitations of the present MCGD budget and schedule it is necessary to limit, delegate and modify certain typical aspects of project management/oversight/support process that would be nominal in a larger space flight project with a larger budget.

All supporting activities and services have been judged in the light of whether they constitute a faster schedule, a better product or a cheaper way to accomplish the stated goals of this project. This approach does not seek to eliminate required tasking or control, but reserves the right of the MCGD PM to determine who will accomplish this tasking. Generally, the MSFC/SD MCGD team will conduct all manner of design, control, purchasing, testing, inspection and transportation.  Otherwise, the team will complete the entire flight task and meet all requirements in conjunction with the customer (the AA SPASE Project Manager). The only absolute exception to this internal approach will be with regards to flight safety requirements, which will be dictated by safety personnel at the integrating NASA facility (GSFC) and observed by safety personnel at MSFC.

This project will minimize cost and overhead while maintaining quality/safety and meeting the technology demonstration objectives of the MCGD.

This project will conduct internal quality inspections and establish internal metrics to assure that a quality/safe product is being produced and delivered.

MCGD flight hardware will utilize both certified flight hardware and “off the shelf” commercial components as a special demonstration. The MCGD Project Team and CCB will determine which components will be purchased as “commercial” items and which will be “flight” certified items. SD certified flight spares from former missions, which are not in secure storage, may be utilized as form, fit, function, shelf life and costs permit/dictate. Regardless, all MCGD safety critical items will be from flight certified and controlled stocks.

All flight hardware, commercial or otherwise will be purchased directly on US Government Credit Cards, where the dollar value of the purchase falls within existing US government purchasing regulations and if the purchasing of these items in this manner is in the best interest of the government. Credit cards enable timely purchases of materials for US government use. MCGD intends to maximize the flexibility and capability for rapid acquisition that is provided by having such a credit card. It should be noted that the expedience with which an item is purchased is in no way a reflection upon the quality of the item itself. All components that are used to assemble the flight MCGD will be certified and documented to be of the desired level of quality. All the necessary documentation will be maintained by the MCGD PM to provide an audit trail of purchase/source.

Flight hardware drawings will be released through/to the MSFC Drawing Repository before delivery. MCGD is a unique product and AA will simultaneously take delivery of the MCGD hardware and a full set of drawings/documents. The MCGD PM will serve as the MSFC drawing repository for MCGD drawings and documentation per Section 23.

The MCGD will be delivered to AA without an exchange of title. It will be built as and remain a NASA owned flight project throughout the duration of the SPASE integration, launch and mission operations phase.

23.  DOCUMENTATION RETENTION

The MCGD Project Manager is responsible for maintaining a complete and current file of Quality Records in accordance with MPG 1440.2, MSFC Records Management Program.  Quality Records will be retained for a period of 2 years after project or task completion.  At the conclusion of the 2 year retention period, the Project Manager shall disposition the Quality Records in accordance with NPG 1441.1.

# Text boxes

NOT MEASUREMENT

SENSITIVE