## Cost and Labor Summary
RSVP AGS Infrastructure Labor FTE's #
| Management | Admin | Eng'r | Physicist | Design | Tech | C-AD Total | DTS | Shops
AGS/Booster |  |  | 16.2382 | 3.5943 | 2.1943 | 20.7806 | 42.8074 | 0.97379 | 4.6091
Switchyard |  |  | 2.1083 | 0.34758 | 0.87749 | 15.0154 | 18.3487 | 2.9402 | 1.2479
K0PI0 |  |  | 4.7134 | 3.4587 | 2.5972 | 15.3766 | 26.1459 | 4.5641 | 0.17664
MECO |  |  | 1.7994 | 0.19145 | 0.97436 | 12.0832 | 15.0484 | 7.2957 | 0.70655
AGS Project Office | 5.0006 | 1.2501
Total | 5.0006 | 1.2501 | 24.8593 | 7.592 | 6.6433 | 63.2558 | 108.6011 | 15.7738 | 6.7402
# does not include FTE's for beam development
RSVP AGS Infrastructure Cost Summary
| Materials | C-AD Labor | DTS/Shops | Sub-Total | Contingency | Total
AGS/Booster | 9308336.1972 | 6400837.8987 | 991420.6634 | 16700594.7593 | 3311347.9275 | 20011942.6868
Switchyard | 1505162.6826 | 2461536.9595 | 602699.8063 | 4569399.4485 | 891809.2149 | 5461208.6633
K0PI0 | 3832572.8126 | 3849145.9609 | 607918.5351 | 8289637.3087 | 1908031.9442 | 10197669.2529
MECO | 1838054.7728 | 2015149.837 | 1050713.3327 | 4903917.9425 | 1095281.825 | 5999199.7675
AGS Project Office | 62580.6625 | 1443788.1882 |  | 1506368.8507 |  | 1506368.8507
TOTAL | 16546707.1277 | 16170458.8443 | 3252752.3376 | 35969918.3097 | 7206470.9115 | 43176389.2212
Beam Development* | 16721161.6878 | 13838281.2053 |  | 30559442.8932 |  | 30559442.8932
RSVP AGS WBS Total | 33267868.8156 | 30008740.0497 | 3252752.3376 | 66529361.2028 | 7206470.9115 | 73735832.1144
* includes DTS and Power Costs, assumes Jan 04 plan, FY06-FY10 running with RHIC for 14 weeks, balance outside RHIC
What's Missing from this
1. RSVP Project Office
2. AGS/Booster Shield CAPS, several incomplete WBS items
3. AGS/Booster/Switchyard Collimators
4. MECO Magnet and Refrigerator Infrastructure Support
5. Meco - experiment area (detectors, cosmic shield, target, counting house etc)
6. K0PI0 - experiment area, counting house, fast electronics etc..
7. Beam Development costs (AGS running)

## WBS 1.4.1 Booster-AGS
RSVP - Booster/AGS Modifications
| 9/2/04 (K. Brown v2.2 with AGS CAPs added 9/16/04 and Booster CAPS 10/4/04) |  |  |  |  | Labor Rates
| 10/4/04 - added CFI work and support & 100 MHz Cavity, revised contingency |  |  |  |  | 66.86 | 89.23 | 55.96 | 52.25 | 78.35 | 92.83
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total | Direct Total | Direct Total
Number | Description | <$25000 | >$25000 | >$600000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | w/ Cont | w/ Cont | Comments
[23 empty] | (level 5) | (level 4)
1.4.1 | BOOSTER/AGS MODIFICATIONS |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.1.1 | Project Support |  |  |  | 0 | 1764 | 882 | 0 |  |  |  | 196641.9 | 196641.9 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 31462.704 | 228104.604 | 228104.604 | 228104.604 | 1.0 LE, .5 LP
1.4.1.1.1 | installation supervision |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 5% 0f Tech labor
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.1.2 | Booster |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 3454488.9994
1.4.1.2.1 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 947320.748
| Project Support |  |  |  | 0 | 120 | 0 | 20 | 340 |  |  | 26907.4 | 26907.4 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 4305.184 | 31212.584 |  |  | 10 % eng management, 20% technical management
| Cable Repair/Replacement | 12000 | 0 |  | 12000 | 120 | 0 | 0 | 160 | 0 | 0 | 16383.2 | 28383.2 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 5108.976 | 33492.176
| Cable Trays | 1500 |  |  | 1500 | 80 | 0 | 0 | 80 | 0 | 0 | 9528.8 | 11028.8 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 1985.184 | 13013.984
| Upgrade of PFN's | 119400 | 129500 |  | 248900 | 800 | 0 | 120 | 960 | 160 | 40 | 126612.4 | 375512.4 | 3 | 2 | 8 | 1 | 2 | 8 | 24% | 90122.976 | 465635.376
| Magnet Coils - Mechanical | 0 | 312000 |  | 312000 | 110 | 0 | 0 | 440 | 0 | 0 | 30344.6 | 342344.6 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 61622.028 | 403966.628
1.4.1.2.2 | Mechanical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 559832.659
| Project Support |  |  |  | 0 | 40 | 0 | 80 | 500 |  |  | 33276.2 | 33276.2 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 5324.192 | 38600.392 |  |  | 10 % eng management, 20% technical management
| Spare Booster F6 | 0 | 28000 |  | 28000 | 220 | 0 | 0 | 1320 | 0 | 875 | 164905.45 | 192905.45 | 2 | 2 | 4 | 1 | 2 | 4 | 14% | 27006.763 | 219912.213
| Booster Injection | 0 | 85000 |  | 85000 | 220 | 110 | 440 | 1210 | 0 | 450 | 154142.9 | 239142.9 | 4 | 2 | 8 | 1 | 2 | 8 | 26% | 62177.154 | 301320.054
Collimators
1.4.1.2.3 | RF System modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 763501.712
| Project Support |  |  |  | 0 | 80 | 0 | 0 | 400 |  |  | 26248.8 | 26248.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 4199.808 | 30448.608 |  |  | 10 % eng management, 20% technical management
| RF Feedback | 120000 | 240000 |  | 360000 | 1040 | 520 | 0 | 2080 | 160 | 40 | 240863.2 | 600863.2 | 2 | 2 | 8 | 1 | 2 | 8 | 22% | 132189.904 | 733053.104
1.4.1.2.4 | Instrumentation | [21 empty] | 482107.432
| Project Support | 0 | 0 | 0 | 0 | 240 | 120 | 40 | 440 | 0 | 0 | 51982.4 | 51982.4 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 8317.184 | 60299.584
| Loss Monitors | 51000 | 0 | 0 | 51000 | 400 | 0 | 120 | 800 | 0 | 0 | 75259.2 | 126259.2 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 25251.84 | 151511.04
| WCM Upgrade (D6) | 5000 | 0 | 0 | 5000 | 880 | 80 | 80 | 880 | 0 | 40 | 120145.2 | 125145.2 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 32537.752 | 157682.952
| Inflector protection (C3) | 5000 | 0 | 0 | 5000 | 80 | 0 | 40 | 160 | 0 | 0 | 15947.2 | 20947.2 | 1 | 2 | 12 | 4 | 2 | 8 | 30% | 6284.16 | 27231.36
| Cables | 10000 | 0 | 0 | 10000 | 160 | 0 | 0 | 320 | 0 | 0 | 27417.6 | 37417.6 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 5986.816 | 43404.416
| BTA | 13000 | 0 | 0 | 13000 | 80 | 0 | 20 | 320 | 0 | 0 | 23188 | 36188 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 5790.08 | 41978.08
1.4.1.2.5 | Controls | [21 empty] | 93326.4484
| Project Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0
| Instrumentation Interfaces | 4000 | 18454 | 0 | 22454 | 96 | 0 | 0 | 114 | 0 | 0 | 12375.06 | 34829.06 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 7662.3932 | 42491.4532
| Software & Database | 0 | 0 | 0 | 0 | 594 | 0 | 0 | 0 | 0 | 0 | 39714.84 | 39714.84 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 11120.1552 | 50834.9952
1.4.1.2.6 | Safety | [21 empty] | 608400
| Project Support |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 10 % eng management, 20% technical management
| Shield Caps |  |  | 520000 | 520000 | [6 empty] | 0 | 520000 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 88400 | 608400
1.4.1.3 | AGS |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 7898884.7478
1.4.1.3.1 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 2039271.804
| Project Support |  |  |  | 0 | 120 | 0 | 0 | 560 |  |  | 37283.2 | 37283.2 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 5965.312 | 43248.512 |  |  | 10 % eng management, 20% technical management
| Cable Repair/Replacement | 0 | 120000 |  | 120000 | 120 | 0 | 0 | 320 | 0 | 0 | 24743.2 | 144743.2 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 26053.776 | 170796.976
| Cable Trays | 1500 |  |  | 1500 | 80 | 0 | 0 | 80 | 0 | 0 | 9528.8 | 11028.8 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 1985.184 | 13013.984
| Active Filter | 0 | 110000 |  | 110000 | 120 | 0 | 0 | 120 | 0 | 0 | 14293.2 | 124293.2 | 4 | 2 | 8 | 1 | 2 | 4 | 22% | 27344.504 | 151637.704
| F5 Power Supply | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 0 | 0
| F10 Power Supply | 0 | 250000 |  | 250000 | 120 | 0 | 0 | 120 | 0 | 0 | 14293.2 | 264293.2 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 52858.64 | 317151.84
| H20 Power Supply | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 1 | 2 | 4 | 14% | 0 | 0
| Upgrade of PFN's | 143500 | 180000 |  | 323500 | 640 | 0 | 120 | 1600 | 160 | 80 | 153068 | 476568 | 3 | 2 | 8 | 1 | 2 | 8 | 24% | 114376.32 | 590944.32
| Magnet Coils - Mechanical | 0 | 364000 |  | 364000 | 110 | 0 | 0 | 440 | 0 | 0 | 30344.6 | 394344.6 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 70982.028 | 465326.628
| J10 Bump; Low ripple P.S. | 0 | 225000 |  | 225000 | 120 | 0 | 0 | 120 | 0 | 0 | 14293.2 | 239293.2 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 47858.64 | 287151.84
1.4.1.3.2 | Mechanical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 1585610.263
| Project Support |  |  |  | 0 | 100 | 0 | 280 | 1000 |  |  | 74604.8 | 74604.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 11936.768 | 86541.568 |  |  | 10 % eng management, 20% technical management
| AGS RC Networks | 16000 | 0 |  | 16000 | 55 | 0 | 55 | 220 | 0 | 0 | 18250.1 | 34250.1 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 6850.02 | 41100.12
| New F5 (2) | 0 | 30000 |  | 30000 | 220 | 0 | 440 | 1760 | 0 | 1500 | 270536.6 | 300536.6 | 2 | 2 | 4 | 2 | 2 | 4 | 16% | 48085.856 | 348622.456
| New F10 (2) | 0 | 26000 |  | 26000 | 220 | 80 | 440 | 1320 | 0 | 1600 | 263968 | 289968 | 2 | 2 | 4 | 2 | 2 | 4 | 16% | 46394.88 | 336362.88
| New H20 (2) | 0 | 40000 |  | 40000 | 440 | 110 | 440 | 1760 | 0 | 2400 | 378608.1 | 418608.1 | 4 | 2 | 15 | 2 | 2 | 4 | 31% | 129768.511 | 548376.611
Collimators
| Sextupole Coils** | 0 | 160000 |  | 160000 | 110 | 0 | 0 | 440 | 0 | 0 | 30344.6 | 190344.6 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 34262.028 | 224606.628
1.4.1.3.3 | Instrumentation | [21 empty] | 561643.182
| Project Support | 0 | 0 | 0 | 0 | 240 | 120 | 80 | 440 | 0 | 0 | 54220.8 | 54220.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 8675.328 | 62896.128
| Loss Monitors | 20000 | 0 | 0 | 20000 | 180 | 0 | 20 | 640 | 0 | 0 | 46594 | 66594 | 2 | 4 | 15 | 2 | 4 | 8 | 39% | 25971.66 | 92565.66
| Wall Current Monitor | 10000 | 0 | 0 | 10000 | 880 | 20 | 20 | 880 | 0 | 0 | 107720.6 | 117720.6 | 1 | 2 | 10 | 1 | 3 | 8 | 23% | 27075.738 | 144796.338
| IPM Servo | 2000 | 0 | 0 | 2000 | 40 | 0 | 0 | 80 | 0 | 0 | 6854.4 | 8854.4 | 1 | 2 | 2 | 1 | 2 | 2 | 8% | 708.352 | 9562.752
| Motion Systems | 40000 | 0 | 0 | 40000 | 80 | 0 | 20 | 160 | 0 | 0 | 14828 | 54828 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 6579.36 | 61407.36
| Video | 37000 | 0 | 0 | 37000 | 80 | 0 | 20 | 160 | 840 | 0 | 80642 | 117642 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 14117.04 | 131759.04
| Ring Grounds | 25000 | 0 | 0 | 25000 | 40 | 0 | 0 | 240 | 0 | 0 | 15214.4 | 40214.4 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 4825.728 | 45040.128
| Cables | 5000 | 0 | 0 | 5000 | 20 | 0 | 0 | 120 | 0 | 0 | 7607.2 | 12607.2 | 1 | 2 | 2 | 1 | 2 | 2 | 8% | 1008.576 | 13615.776
1.4.1.3.4 | Controls | [21 empty] | 140056.9988
| Project Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | Scope defined by instrumentation needs
| Instrumentation Interfaces | 21350 | 36124 | 0 | 57474 | 68 | 0 | 0 | 180 | 0 | 0 | 13951.48 | 71425.48 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 15713.6056 | 87139.0856 |  |  | Scope defined by instrumentation needs
| Software & Database | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 10162.72 | 10162.72 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 2845.5616 | 13008.2816
| Ring Ground Interface | 8100 | 0 | 0 | 8100 | 15 | 0 | 0 | 60 | 0 | 0 | 4137.9 | 12237.9 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 1713.306 | 13951.206 |  |  | Needed to help detect shorts caused by hign intensity rf effects
| Software & DB | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 3343 | 3343 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 568.31 | 3911.31
| Power Supply Interfaces | 6310 | 5000 | 0 | 11310 | 20 | 0 | 0 | 34 | 0 | 0 | 3113.7 | 14423.7 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 3173.214 | 17596.914 |  |  | Need to replace obsolete extraction element controls
| Software & Database | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 3476.72 | 3476.72 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 973.4816 | 4450.2016
1.4.1.3.5 | Safety |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 3572302.5
| Project Support |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 10 % eng management, 20% technical management
| Shield Caps (PE Subcontract) |  |  | 3053250 | 3053250 | [6 empty] | 0 | 3053250 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 519052.5 | 3572302.5
1.4.1.4 | MECO AGS Modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 1099948.452
1.4.1.4.1 | AC-Dipole | [21 empty] | 278236.488
| Project Support | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 200 | 0 | 0 | 15798.8 | 15798.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2527.808 | 18326.608
| Magnet Design, Fabracation, Installation | 0 | 45000 | 0 | 45000 | 200 | 80 | 0 | 440 | 0 | 0 | 43500.4 | 88500.4 | 4 | 2 | 8 | 2 | 2 | 4 | 24% | 21240.096 | 109740.496
| Magnet Water Cooling | 5000 | 0 | 0 | 5000 | 80 | 0 | 0 | 200 | 0 | 0 | 15798.8 | 20798.8 | 2 | 2 | 4 | 2 | 2 | 4 | 16% | 3327.808 | 24126.608
| Power Supply | 0 | 50000 | 0 | 50000 | 400 | 80 | 0 | 340 | 0 | 0 | 51647.4 | 101647.4 | 4 | 2 | 8 | 2 | 2 | 4 | 24% | 24395.376 | 126042.776
1.4.1.4.2 | Strip-line Kickers | [21 empty] | 630117.308
| Project Support | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 160 | 0 | 0 | 13708.8 | 13708.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2193.408 | 15902.208
| Strip-lines | 0 | 200000 | 0 | 200000 | 160 | 80 | 0 | 240 | 0 | 0 | 30376 | 230376 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 50682.72 | 281058.72
| Power Supply/Pulsers | 0 | 125000 | 0 | 125000 | 120 | 80 | 0 | 120 | 0 | 0 | 21431.6 | 146431.6 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 32214.952 | 178646.552
| Low Level Controls | 0 | 75000 | 0 | 75000 | 400 | 80 | 0 | 340 | 0 | 0 | 51647.4 | 126647.4 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 27862.428 | 154509.828
1.4.1.4.3 | Simulations | [21 empty] | 191594.656
| Mini-bunched extraction | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 157044.8 | 157044.8 | 1 | 2 | 8 | 2 | 2 | 8 | 22% | 34549.856 | 191594.656
1.4.1.5 | KOPIO AGS Modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 3568756.7462
1.4.1.5.1 | Booster To AGS Kickers | [21 empty] | 837082.2026
| Project Support |  |  |  | 0 | 240 | 346 | 90 | 300 |  |  | 67631.38 | 67631.38 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 10821.0208 | 78452.4008 |  |  | 10 % eng management, 20% technical management
| Interface/Installation | 0 | 61600 | 0 | 61600 | 1386 | 0 | 520 | 1213 | 216 | 0 | 202070.01 | 263670.01 | 2 | 2 | 4 | 2 | 2 | 4 | 16% | 42187.2016 | 305857.2116
| Controls | 28600 | 0 | 0 | 28600 | 433 | 0 | 173 | 346 | 173 | 0 | 70264.51 | 98864.51 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 21750.1922 | 120614.7022
| Conventional | 0 | 192500 | 0 | 192500 | 606 | 0 | 173 | 0 | 0 | 0 | 50198.24 | 242698.24 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 48539.648 | 291237.888
| Tunnel Penetration | 0 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 2 | 2 | 8 | 2 | 2 | 8 | 24% | 7920 | 40920
1.4.1.5.2 | 25 MHz RF cavity (C-AD Part) | [21 empty] | 330145.368
| Project Support |  |  |  | 0 | 140 | 0 | 0 | 625 |  |  | 42016.65 | 42016.65 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 6722.664 | 48739.314 |  |  | 10 % eng management, 20% technical management
| Cavity * |  | 832000 |  |  | 1010 |  |  | 670
| Tuner * | 15625 |  |  |  | 675 |  |  | 335 |  | 768
| Vacuum * | 21250 | [6 empty] | 96
| Power Amplifier * |  | 26250 |  |  | 1010 |  |  | 2356
| Damper * | 21250 |  |  |  | 3040 |  |  | 2022 |  | 768
| Driver | 21250 | 0 | 0 | 21250 | 0 | 0 | 0 | 325 | 0 | 0 | 16981.25 | 38231.25 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 8410.875 | 46642.125
| Low Level Control | 21250 | 0 | 0 | 21250 | 680 | 0 | 0 | 325 | 0 | 0 | 62446.05 | 83696.05 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 18413.131 | 102109.181
| Controls | 0 | 31250 | 0 | 31250 | 690 | 0 | 0 | 600 | 0 | 0 | 77483.4 | 108733.4 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 23921.348 | 132654.748
| Access Controls | 20000
| Shipping * | 25000
1.4.1.5.3 | 100 MHz RF Cavity | [21 empty] | 2209934.5196
| Project Support |  |  |  | 0 | 1017 | 0 | 0 | 1200 |  |  | 130696.62 | 130696.62 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 20911.4592 | 151608.0792 |  |  | 10 % eng management, 20% technical management
| Cavity | 0 | 416250 | 0 | 416250 | 3038 | 0 | 0 | 1687 | 0 | 0 | 291266.43 | 707516.43 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 155653.6146 | 863170.0446
| Tuner | 21250 | 0 | 0 | 21250 | 682 | 0 | 0 | 325 | 0 | 532 | 111965.33 | 133215.33 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 29307.3726 | 162522.7026
| Vacuum | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 96 | 0 | 0 | 5016 | 20016 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 4403.52 | 24419.52
| Power Amplifier | 0 | 41250 | 0 | 41250 | 1700 | 0 | 0 | 2020 | 0 | 0 | 219207 | 260457 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 57300.54 | 317757.54
| Damper | 21250 | 0 | 0 | 21250 | 3048 | 0 | 0 | 1018 | 0 | 532 | 306365.34 | 327615.34 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 72075.3748 | 399690.7148
| Driver | 21250 | 0 | 0 | 21250 | 0 | 0 | 0 | 324 | 0 | 0 | 16929 | 38179 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 8399.38 | 46578.38
| Low Level Control | 21250 | 0 | 0 | 21250 | 1020 | 0 | 0 | 324 | 0 | 0 | 85126.2 | 106376.2 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 23402.764 | 129778.964
| Controls | 31250 | 0 | 0 | 31250 | 682 | 0 | 0 | 324 | 0 | 0 | 62527.52 | 93777.52 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 20631.0544 | 114408.5744
| Access Controls | 20000
1.4.1.5.4 | Simulations | [21 empty] | 191594.656
| Micro-bunched extraction | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 157044.8 | 157044.8 | 1 | 2 | 8 | 2 | 2 | 8 | 22% | 34549.856 | 191594.656
1.4.1.6 | Beam Development |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Project Support |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 10 % eng management, 20% technical management
| Labor Hours |  |  |  |  | 28498 | 6308 | 3851 | 36470 | 1709 | 8089 | [8 empty] | 0%
| FTE |  |  |  |  | 16.2382 | 3.5943 | 2.1943 | 20.7806 | 0.97379 | 4.6091
| TOTALS - DIRECT | 924010 | 3629928 | 3573250 | 8087188 | 1905376.28 | 562862.84 | 215501.96 | 1905557.5 | 133900.15 | 750901.87 | 5474100.6 | 13561288.6 | [6 empty] | 19.83% | 2688894.9494 | 16250183.5494 | 16250183.5494 | 16250183.5494
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 24.98% | 13.19% | 13.19% |  | 39.47% | 39.47% | 39.47% | 39.47% | 12.05% | 12.05% | [7 empty] | 18.8% | 23.15% | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 3194341.8869 | 19894936.6462
| TOTAL | 1154806.9078 | 4108842.5507 | 4044686.7387 | 9308336.1972 | 2657487.7384 | 785042.3622 | 300567.3065 | 2657740.4916 | 150035.1181 | 841385.5453 | 7392258.5621 | 16700594.7593 | [6 empty] | 19.83% | 3311347.9275 | 20011942.6868
* Off Project - CFI TRIUMF Work,
not included in totals
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## WBS 1.4.2 Switchyard
RSVP - Switchyard Modifications with instrumentation and security included 8/5/04
6/29/04 - AP with security and instrumentation, wbs dictionary (partial) 9/29/04 | [5 empty] | Labor Rates
[6 empty] | 66.86 | 89.23 | 55.96 | 52.25 | 64.07 | 94.65
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total
Number | Description | <$25,000 | >$25,000 | >$600,000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | Comments/WBS Dictionary
1.4.2 | Switchyard modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.1 | project support and integration |  |  |  | 0 | 900 | 450 | 450 |  |  |  | 125509.5 | 125509.5 | 3 | 2 | 8 | 1 | 1 | 2 | 17% | 21336.615 | 146846.115 | .5 LE, .25 LP
1.4.2.1.1 | installation supervision |  |  |  | 0 |  |  |  | 1000 |  |  | 52250 | 52250 | 3 | 2 | 8 | 1 | 1 | 2 | 17% | 8882.5 | 61132.5 | Provides for Design, Trades & Technician labor supervision @ 5%
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.2 | shielding modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.2.1 | modify shielding at AD2 | 2000 |  |  | 2000 |  |  | 10 | 40 | 200 | 40 | 19249.6 | 21249.6 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 4249.92 | 25499.52 | Provides a 10' long radiation shield between the AGS ring and the SEB
1.4.2.2.2 | rebuild d/s labyrinth | 5000 |  |  | 5000 |  |  | 10 | 40 | 160 | 40 | 16686.8 | 21686.8 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 4337.36 | 26024.16 | Adds an extra turn on the existing labyrinth to decrease radiation leakage
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.3 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.3.1 | modify Royals (9) |  | 135000 |  | 135000 | 10 |  |  | 40 | 160 |  | 13009.8 | 148009.8 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 32562.156 | 180571.956 | Provides electrical breakers for AC power to power supplies
1.4.2.3.2 | remove power | [8 empty] | 80 |  | 5125.6 | 5125.6 | 1 | 2 | 8 | 1 | 1 | 4 | 15% |  |  | Removes the existing power distribution in the SYG cave
1.4.2.3.3 | provide power in cave | 5000 |  |  | 5000 |  |  | 4 |  | 160 |  | 10475.04 | 15475.04 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 2630.7568 | 18105.7968 | Provides new power distribution in the SYG cave
1.4.2.3.4 | provide power @VME stations | 5000 |  |  | 5000 |  |  | 4 |  | 160 |  | 10475.04 | 15475.04 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 2630.7568 | 18105.7968 | Provides power & distribution in the VME controls enclosures
1.4.2.3.5 | modify PS's for new controls (20) |  | 187500 |  | 150000 | 200 |  | 160 | 12000 |  | 40 | 653111.6 | 803111.6 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 160622.32 | 963733.92 | PSI type controls with SLC's, includes testing but no contactors or tap switches
1.4.2.3.6 | power supply maintenance |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | no cost if we do controls mods
1.4.2.3.7 | reconfigure interlock racks | 2000 |  |  | 2000 |  |  | 8 | 120 |  |  | 6717.68 | 8717.68 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 1482.0056 | 10199.6856 | This reconfigures the existing PLC rack for the new magnet interlock layout
1.4.2.4 | Mechanical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.4.1 | fabricate beam plugs (3) | 48500 |  |  | 48500 | 40 |  |  | 300 |  | 900 | 103534.4 | 152034.4 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 30406.88 | 182441.28 | Provides a remote beam plug capable of intercepting ~1% of beam,copy of NSRL stop
1.4.2.4.2 | modify PS water cooling | 5000 |  |  | 5000 | 16 |  | 16 | 160 |  |  | 10325.12 | 15325.12 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 2605.2704 | 17930.3904 | Removes rad water cooling & provides open tower cooling water for PS's
1.4.2.4.3 | prepare magnets (4) | 4000 |  |  | 4000 | 16 |  |  | 320 |  | 10 | 18736.26 | 22736.26 | 2 | 2 | 8 | 1 | 1 | 8 | 21% | 4774.6146 | 27510.8746 | Provides for refurbishing of 4 existing magnets, including bus, interlocks and stands
1.4.2.4.4 | replace CT1 piping |  | 30000 |  | 30000 | 16 |  | 16 |  |  |  | 1965.12 | 31965.12 | 2 | 2 | 15 | 2 | 2 | 4 | 27% | 8630.5824 | 40595.7024 | Replaces CT1 piping that is or was leaking with S/S pipe (for PS cooling)
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.5 | Installation
1.4.2.5.1 | remove equipment in ring |  |  |  | 0 |  |  |  | 460 | 256 |  | 40436.92 | 40436.92 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 7278.6456 | 47715.5656 | Removes 8 of the 14 elements in the AGS ring
1.4.2.5.2 | remove equipment in "A" |  |  |  | 0 |  |  |  | 1200 | 840 |  | 116518.8 | 116518.8 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 20973.384 | 137492.184 | Removes all 15 existing elements in the A transport section of the SYG
1.4.2.5.3 | remove equipment in "B" |  |  |  | 0 |  |  |  | 720 | 620 |  | 77343.4 | 77343.4 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 13921.812 | 91265.212 | Removes 6 of the 12 transport elements in the C & B lines of the SYG
1.4.2.5.4 | rad waste removal (100cu ft) |  | 40000 |  | 40000 |  |  |  | 200 | 60 |  | 14294.2 | 54294.2 | 1 | 2 | 8 | 4 | 2 | 2 | 20% | 10858.84 | 65153.04 | Provides for sorting, packing, shipping and burial of rad waste
1.4.2.5.5 | install magnets in ring (2) | 4000 |  |  | 4000 |  |  |  | 400 | 112 |  | 28075.84 | 32075.84 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 6415.168 | 38491.008 | Provides for installation labor, materials, & testing for 2 new magnets in the AGS
1.4.2.5.6 | install magnets in "A" line (5) | 20000 |  |  | 20000 |  |  |  | 1360 | 560 |  | 106939.2 | 126939.2 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 25387.84 | 152327.04 | Provides for installation labor, materials, & testing for 5 new magnets in the A line
1.4.2.5.7 | install magnets in "B" line (3) | 12000 |  |  | 12000 |  |  |  | 816 | 336 |  | 64163.52 | 76163.52 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 15232.704 | 91396.224 | Provides for installation labor, materials, & testing for 3 new magnets in the B line
1.4.2.5.8 | install beam plugs (3) | 5000 |  |  | 5000 |  |  |  | 340 | 40 |  | 20327.8 | 25327.8 | 2 | 2 | 8 | 4 | 1 | 4 | 20% |  | 25327.8 | Provides for installation labor, materials & testing of the beam plugs
1.4.2.5.9 | clear cave & paint | 1000 |  |  | 1000 |  |  |  | 100 | 100 |  | 11632 | 12632 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 3031.68 | 15663.68 | Provides for preparation & painting of the SYG floor
1.4.2.5.10 | install roof |  |  |  | 0 |  |  |  |  | 480 |  | 30753.6 | 30753.6 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 6150.72 | 36904.32 | Re-installs the existing SYG roof taken off for beam line modifications
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.6 | Vacuum |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.6.1 | install vacuum in ring (100') | 8500 | 25000 |  | 33500 | 40 |  | 40 | 100 |  | 140 | 23388.8 | 56888.8 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 13653.312 | 70542.112 | Provides for a new welded vacuum d/s of CQ4. assumes rough vacuum
1.4.2.6.2 | install vacuum in "A" line (100') | 14000 | 50000 |  | 64000 | 80 |  | 120 | 160 |  | 440 | 62070 | 126070 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 30256.8 | 156326.8 | Provides for a new "A" line vacuum system in the SYG.assumes rough vacuum
1.4.2.6.3 | install vacuum in "B" line (120') | 20000 | 50000 |  | 70000 | 80 |  | 120 | 240 |  | 540 | 75715 | 145715 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 34971.6 | 180686.6 | Provides for labor, materials for vacuum in C&B lines.assumes rough vacuum
1.4.2.6.4 | plc modifications |  |  |  | 0 | 80 |  | 40 | 160 |  |  | 15947.2 | 15947.2 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 3827.328 | 19774.528 | This re-configures the existing vacuum PLC rack for the new vacuum system
[12 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.7 | Conventional |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.7.1 | cable fire protection | 5000 |  |  | 5000 |  |  |  | 80 |  |  | 4180 | 9180 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 2203.2 | 11383.2 | Provides for labor & materials for tray cable fire protection
1.4.2.7.2 | controls enclosure | 20000 |  |  | 20000 |  |  |  |  | 280 |  | 17939.6 | 37939.6 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 9105.504 | 47045.104 | Provides for a air conditioned enclosure for controls and instrumentation
1.4.2.7.3 | cave dehumidification | 18000 |  |  | 18000 | 20 |  | 10 | 10 | 120 |  | 10107.7 | 28107.7 | 2 | 2 | 8 | 2 | 2 | 2 | 18% | 5059.386 | 33167.086 | Keeps the SYG cave below 85% RH
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8 | Switchyard Instrumentation |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.1 | project support |  |  |  | 0 | 220 |  | 120 |  |  |  | 21424.4 | 21424.4 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 4284.88 | 25709.28
1.4.2.8.1.1 | installation supervision |  |  |  | 0 |  |  |  | 440 |  |  | 22990 | 22990 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 4598 | 27588
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.2 | Loss Monitor System |  |  |  | 0 |  |  | 80 |  |  |  | 4476.8 | 4476.8 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 895.36 | 5372.16 | Only long loss mons & OLD 4ch NIM elec, will I/F to Controls V102 & ADC's
1.4.2.8.2.1 | Gas system distributed. | 1000 |  |  | 1000 | 20 |  |  | 80 |  |  | 5517.2 | 6517.2 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 912.408 | 7429.608 | Upgrade and routing of supply & return gas dist.
1.4.2.8.2.2 | New & repair Long loss Mons (Cables) | 5000 |  |  | 5000 | 20 |  |  | 100 |  |  | 6562.2 | 11562.2 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2312.44 | 13874.64 | Repair, replace, relocate as needed.
1.4.2.8.2.3 | LM Inhibit system & I/F | 5000 |  |  | 5000 | 40 |  |  | 80 |  |  | 6854.4 | 11854.4 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2370.88 | 14225.28 | Similar to H20 type.
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3 | Profile Monitors |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.1 | EPM's |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.1.1 | SWYD (2) Mechanical | 30000 |  |  | 30000 | 80 | 40 | 20 | 160 | 40 |  | 20960 | 50960 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 13249.6 | 64209.6
| Electronics | 50000 |  |  | 50000 | 80 |  | 20 | 160 |  |  | 14828 | 64828 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 12965.6 | 77793.6
1.4.2.8.3.1.2 | A line (2) Mechanical | 30000 |  |  | 30000 | 80 | 40 | 20 | 160 | 40 |  | 20960 | 50960 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 13249.6 | 64209.6
| Electronics | 50000 |  |  | 50000 | 80 |  | 20 | 160 |  |  | 14828 | 64828 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 12965.6 | 77793.6
1.4.2.8.3.1.3 | B Line (2) Mechanical | 30000 |  |  | 30000 | 80 | 40 | 20 | 160 | 40 |  | 20960 | 50960 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 13249.6 | 64209.6
| Electronics | 50000 |  |  | 50000 | 80 |  | 20 | 160 |  |  | 14828 | 64828 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 12965.6 | 77793.6
1.4.2.8.3.1.4 | Biasing for all | 12000 |  |  | 12000 | 20 |  |  | 40 |  |  | 3427.2 | 15427.2 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 1851.264 | 17278.464
1.4.2.8.3.1.5 | Cabling (round to flat) | 6000 |  |  | 6000 | 40 |  |  | 160 |  |  | 11034.4 | 17034.4 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 2384.816 | 19419.216
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.2 | Scanning Target |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.2.1 | Installation/Survey | 1000 |  |  | 1000 | 40 |  |  | 80 |  |  | 6854.4 | 7854.4 | 1 | 2 | 6 | 1 | 2 | 6 | 16% | 1256.704 | 9111.104
1.4.2.8.3.2.2 | Detectors | 1000 |  |  | 1000 | 20 |  |  | 40 |  |  | 3427.2 | 4427.2 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 885.44 | 5312.64
1.4.2.8.3.2.3 | Electronics (use existing) | 0 |  |  | 0 |  |  |  | 20 |  |  | 1045 | 1045 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 146.3 | 1191.3
1.4.2.8.3.2.4 | Bias (use existing) | 0 |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.2.5 | Device motion upgrade | 10000 |  |  | 10000 | 20 |  |  | 40 |  |  | 3427.2 | 13427.2 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2685.44 | 16112.64
1.4.2.8.3.2.6 | New targets | 2000 |  |  | 2000 | 40 |  |  | 40 |  |  | 4764.4 | 6764.4 | 1 | 2 | 10 | 1 | 4 | 8 | 24% | 1623.456 | 8387.856
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.3.3 | C011 Plunging SWIC |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.3.3.1 | SWIC Head | 15000 |  |  | 15000 | 40 |  |  | 80 |  |  | 6854.4 | 21854.4 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 4370.88 | 26225.28
1.4.2.8.3.3.2 | Motion upgrade | 5000 |  |  | 5000 | 20 |  |  | 40 |  |  | 3427.2 | 8427.2 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 1011.264 | 9438.464
1.4.2.8.3.3.3 | Electronics | 1000 |  |  | 1000 | 80 |  | 20 | 160 |  |  | 14828 | 15828 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 3165.6 | 18993.6 | Use CF100 SWIC Electronics, minor modifications.
1.4.2.8.4 | Motion Control |  |  |  | 0
1.4.2.8.4.1 | Beam Plugs (3) A, B, & C. | 9000 |  |  | 9000 | 80 |  |  | 160 |  |  | 13708.8 | 22708.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3633.408 | 26342.208 | connectors and I/F to Controls. New axis includes cables and J-box.
1.4.2.8.4.2 | X & Y Collimator, 4 jaws = 4 axis | 12000 |  |  | 12000 | 80 |  |  | 160 |  |  | 13708.8 | 25708.8 | [6 empty] | 0% | 0 | 25708.8
1.4.2.8.5 | Current Transformer |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.5.1 | CT at C036 | 10000 |  |  | 10000 | 80 | 40 | 20 | 160 |  |  | 18397.2 | 28397.2 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 3407.664 | 31804.864
1.4.2.8.5.2 | Electronics | 25000 |  |  | 25000 | 80 |  |  | 120 |  |  | 11618.8 | 36618.8 | 1 | 2 | 12 | 1 | 2 | 8 | 24% | 8788.512 | 45407.312
1.4.2.8.5.3 | VME | 4000 |  |  | 4000
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6 | Secondary Emission Chamber |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6.1 | C10 SEC |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6.2 | Plunge capability | 30000 |  |  | 30000 | 80 |  |  | 160 |  |  | 13708.8 | 43708.8 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 6993.408 | 50702.208
1.4.2.8.6.3 | Device |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6.4 | Electronics | 5000 |  |  | 5000 | 40 |  | 20 | 100 |  |  | 9018.6 | 14018.6 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2803.72 | 16822.32
1.4.2.8.6.5 | Vacuum controls | 10000 |  |  | 10000 | 20 |  |  | 40 |  |  | 3427.2 | 13427.2 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2148.352 | 15575.552
1.4.2.8.6.6 | Cabling | 500 |  |  | 500 |  |  |  | 20 |  |  | 1045 | 1545 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 216.3 | 1761.3
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% |  | 0
1.4.2.8.7 | Cable & Racks |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.7.1 | Rad-Damaged & old replaced | 15000 |  |  | 15000 | 40 |  |  | 600 |  |  | 34024.4 | 49024.4 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 6863.416 | 55887.816
1.4.2.8.7.2 | Relocation | 10000 |  |  | 10000 | 40 |  |  | 160 | 40 |  | 13597.2 | 23597.2 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 3303.608 | 26900.808
1.4.2.9 | Switchyard Security modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.1 | project support |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 0 | 0
1.4.2.9.1.1 | installation supervision |  |  |  | 0 |  |  |  | 600 |  |  | 31350 | 31350 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 3135 | 34485
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.2 | PLC Systems |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | PLC will be located in 911A cage. Some modules will resides locally.
1.4.2.9.2.1 | Programming | 0 |  |  | 0 | 320 |  | 0 | 0 | 0 | 0 | 21395.2 | 21395.2 | 2 | 2 | 3 | 2 | 2 | 8 | 19% | 4065.088 | 25460.288
1.4.2.9.2.2 | PLC & Racks | 17000 |  |  | 17000 | 32 |  | 40 | 240 | 16 | 0 | 17943.04 | 34943.04 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 5241.456 | 40184.496
1.4.2.9.2.3 | I/O modules | 11000 |  |  | 11000 | 16 |  | 0 | 40 | 0 | 0 | 3159.76 | 14159.76 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 2123.964 | 16283.724
1.4.2.9.2.4 | R/IO Blocks | 10000 |  |  | 10000 |  |  | 0 | 40 | 0 | 0 | 2090 | 12090 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1813.5 | 13903.5
1.4.2.9.2.5 | UPS and Phoenix connectors | 4000 |  |  | 4000 |  |  | 0 | 40 | 40 | 0 | 4652.8 | 8652.8 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1297.92 | 9950.72
1.4.2.9.2.6 | Fiber converters (R/IO & DH+ comm)(6) | 7200 |  |  | 7200 | 16 |  | 0 | 40 | 0 | 0 | 3159.76 | 10359.76 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1553.964 | 11913.724
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.3 | Gates (Incl. 3 gates) |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.3.1 | Gates | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 0 | 0 | The existing gates will be used.
1.4.2.9.3.2 | Gates Boxes | 1800 |  |  |  | 40 |  | 40 | 240 | 0 |  | 17452.8 | 17452.8 | 1 | 2 | 3 | 2 | 1 | 4 | 11%
1.4.2.9.3.3 | Limit switches (10) | 600 |  |  | 600 |  |  | 0 | 24 | 0 |  | 1254 | 1854 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 203.94 | 2057.94
1.4.2.9.3.4 | Electric strikes (2) | 240 |  |  | 240 |  |  | 0 | 24 | 0 |  | 1254 | 1494 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 164.34 | 1658.34
1.4.2.9.3.5 | Card Readers (2) | 400 | 0 |  | 400 | 8 |  | 0 | 40 | 0 | 0 | 2624.88 | 3024.88 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 332.7368 | 3357.6168
1.4.2.9.3.6 | Key Tree & Iris Scanner | 9000 |  |  | 9000 |  |  |  | 40 | 40 |  | 4652.8 |  | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1774.864 | 15427.664
1.4.2.9.4 | Cables |  |  |  | 0 |  |  |  | 80 | 40 | 0 | 6742.8 | [7 empty] | 0% | 0 | 6742.8
1.4.2.9.4.1 | Cables 18/c (3000ft) | 1500 |  |  | 1500 | 0 |  |  | 0 |  | 0 | 0 | 1500 | 0 | 2 | 3 | 2 | 2 | 4 | 11% | 165 | 1665
1.4.2.9.4.2 | Cables 12/c (3000ft) | 1500 |  |  | 1500 | 0 |  | 0 | 0 |  |  | 0 | 1500 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 135 | 1635
1.4.2.9.4.3 | Cables 8/c (3000ft) | 1350 |  |  | 1350 | 0 |  |  | 0 |  | 0 | 0 | 1350 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 121.5 | 1471.5
1.4.2.9.4.4 | Cables 4/c (3000ft) | 1050 | 0 |  | 1050 | 0 |  | 0 |  |  |  | 0 | 1050 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 94.5 | 1144.5
1.4.2.9.4.5 | Crash cables (1000ft) | 750 | 0 |  | 750 | 0 |  | 0 |  |  |  | 0 | 750 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 67.5 | 817.5
1.4.2.9.4.6 | DH+ Comm cables (1000ft) | 450 | 0 |  | 450 | 0 |  | 0 |  |  |  | 0 | 450 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 40.5 | 490.5
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.5 | CATV
1.4.2.9.5.1 | Bobcat switch 16*2 mux (2) | 1200 |  |  | 1200 | 40 |  | 24 | 80 | 0 |  | 8197.44 | 9397.44 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1409.616 | 10807.056
1.4.2.9.5.2 | Lee Data 1*1 Fiber Optics Transmitter (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1254 | 1754 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 263.1 | 2017.1
1.4.2.9.5.3 | Lee Data 1*1 Fiber Optics Receiver (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1254 | 1754 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 263.1 | 2017.1
1.4.2.9.5.4 | Digital Cameras (6) | 1800 | 0 |  | 1800 |  |  |  | 40 | 0 |  | 2090 | 3890 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 583.5 | 4473.5
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.6 | Chipmunks | [21 empty] | Will use existing chipmunks and DAQ hardware.
1.4.2.9.6.1 | Chipmunks (0 units) | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
1.4.2.9.6.2 | VME SIS Scaler board | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
1.4.2.9.6.3 | Weather proof enclusure | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
1.4.2.9.6.4 | Coaxial cables (1000 ft) | 0 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.7 | Crash, Sweep & Alarms
1.4.2.9.7.1 | Check station boxes | 300 |  |  | 300 | 80 |  | 40 | 80 | 0 |  | 11767.2 | 12067.2 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1568.736 | 13635.936
1.4.2.9.7.2 | Crash Actuators | 500 |  |  | 500 |  |  |  | 80 | 0 |  | 4180 | 4680 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 608.4 | 5288.4
1.4.2.9.7.3 | Crash Stations and Alarms | 1500 |  |  | 1500 |  |  |  | 160 | 0 |  | 8360 | 9860 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1281.8 | 11141.8
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.5.2.10 | NASA relocation |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | location?
1.5.2.10.1 | vacuum valves & windows | 12000 |  |  | 12000 | 10 |  | 8 | 10 |  | 40 | 5424.78 | 17424.78 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 3833.4516 | 21258.2316 | Provides for a removable section of B vacuum system for NASA running
1.5.2.10.2 | enclosure | 10000 |  |  | 10000 |  |  |  |  | 120 |  | 7688.4 | 17688.4 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 3891.448 | 21579.848 | Builds an enclosure in the SYG for NASA experiments
1.5.2.10.3 | air conditioning | 1000 |  |  | 1000 |  |  |  |  | 20 |  | 1281.4 | 2281.4 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 501.908 | 2783.308 | Provides AC in the enclosure for NASA
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Labor Hours |  |  |  |  | 3700 | 610 | 1540 | 26352 | 5160 | 2190 | [8 empty] | 0%
| FTE |  |  |  |  | 2.1083 | 0.34758 | 0.87749 | 15.0154 | 2.9402 | 1.2479
| TOTALS - DIRECT | 735640 | 517500 | 0 | 1213840 | 247382 | 54430.3 | 86178.4 | 1376892 | 330601.2 | 207283.5 | 2302767.4 | 3492211.8 | [6 empty] | 19.52% | 681574.6136 | 4171603.6136
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 24.98% | 13.19% |  |  | 39.47% | 39.47% | 39.47% | 39.47% | 12.05% | 12.05% | [9 empty] | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 919386.3201 | 585776.3625 |  | 1505162.6826 | 345031.3928 | 75915.6374 | 120195.7029 | 1920394.2263 | 370438.6446 | 232261.1617 | 3064236.7659 | 4569399.4485 | [6 empty] | 19.52% | 891809.2149 | 5461208.6633
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## WBS 1.4.3 K0PI0 B-Line
RSVP - KOPIO, AGS
2004-06-30 | pearson with instrumentation, security, experiment area and neutral beam |  |  |  |  | Labor Rates
[6 empty] | 66.86 | 89.23 | 55.96 | 52.25 | 64.07 | 94.65
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total
Number | Description | <$25000 | >$25000 | >$600000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont |  | Comments
1.4.3 | K0PI0 BEAMS
1.4.3.1 | Project support and Integration |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.1.1 | Engr & Design Supervision |  |  |  | 0 | 5830 | [5 empty] | 389793.8 | 389793.8 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 62367.008 | 452160.808
1.4.3.1.2 | Physicist Supervision |  |  |  | 0 |  | 5830 |  |  |  |  | 520210.9 | 520210.9 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 83233.744 | 603444.644
1.4.3.1.3 | Design |  |  |  | 0 |  |  | 3150 |  |  |  | 176274 | 176274 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 28203.84 | 204477.84
1.4.3.1.4 | Construction Supervision |  |  |  | 0 |  |  |  | 6250 |  |  | 326562.5 | 326562.5 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 52250 | 378812.5
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2 | Primary Beam |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.1 | B1,B2,B5 Removal |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.1.1 | Remove equipment |  |  |  | 0 |  |  |  | 760 | 120 |  | 47398.4 | 47398.4 | 1 | 2 | 4 | 6 | 1 | 4 | 16% | 7583.744 | 54982.144
1.4.3.2.1.2 | Remove power & tray |  |  |  | 0 |  |  |  |  | 80 |  | 5125.6 | 5125.6 | 1 | 2 | 4 | 6 | 1 | 4 | 16% | 820.096 | 5945.696
1.4.3.2.1.3 | Modify shielding |  |  |  | 0 |  |  |  |  | 2160 |  | 138391.2 | 138391.2 | 1 | 2 | 4 | 6 | 1 | 4 | 16% | 22142.592 | 160533.792
1.4.3.2.1.4 | Rad disposal | 60000 |  |  | 60000 |  |  |  | 300 |  |  | 15675 | 75675 | [6 empty] | 0% | 0 | 75675
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.2 | C1,C3,C7 Removal |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Remove equipment |  |  |  | 0 |  |  |  | 168 |  |  | 8778 | 8778 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 1228.92 | 10006.92
| Remove power & tray |  |  |  | 0 |  |  |  |  | 80 |  | 5125.6 | 5125.6 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 717.584 | 5843.184
| Modify shielding |  |  |  | 0 |  |  |  |  | 1440 |  | 92260.8 | 92260.8 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 12916.512 | 105177.312
| Rad disposal | 20000 |  |  | 20000 |  |  |  | 100 |  |  | 5225 | 25225 | [6 empty] | 0% | 0 | 25225
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.3 | Additional Shielding |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Floor blocks (200 tons) |  | 30000 |  | 30000 | 60 | [5 empty] | 4011.6 | 34011.6 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 6122.088 | 40133.688
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.4 | Transport Magnets (9) |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Refurbish 8Q32 | 1000 |  |  | 1000 | 10 |  |  | 160 | 12 | 10 | 10743.94 | 11743.94 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 2113.9092 | 13857.8492
| Refurbish 3-5Q36 | 3000 |  |  | 3000 | 30 |  |  | 480 | 24 | 30 | 31462.98 | 34462.98 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 6203.3364 | 40666.3164
| Refurbish 4-Trims | 2000 |  |  | 2000 | 20 |  |  | 320 | 12 | 20 | 20719.04 | 22719.04 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 4089.4272 | 26808.4672
| Refurbish N3Q48 | 1000 |  |  | 1000 | 10 |  |  | 160 | 12 | 10 | 10743.94 | 11743.94 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 2113.9092 | 13857.8492
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.5 | Power Supplies |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify PSs for new controls (9) |  | 75000 |  | 75000 | 100 |  | 80 | 5400 |  |  | 293312.8 | 368312.8 | 4 | 4 | 4 | 4 | 2 | 8 | 36% | 132592.608 | 500905.408
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.6 | Electrical Modifications |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify Royals (4) |  | 60000 |  | 60000 |  |  |  |  | 80 |  | 5125.6 | 65125.6 | 4 | 2 | 8 | 10 | 2 | 8 | 44% | 28655.264 | 93780.864
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% |  | 0
1.4.3.2.7 | Instrumentation/Controls |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.1 | project support |  |  |  | 0 | 240 | 120 | 80 |  |  |  | 31230.8 | 31230.8 | [6 empty] | 0% | 0 | 31230.8
| installation supervision |  |  |  | 0 |  |  |  | 440 |  |  | 22990 | 22990 | [6 empty] | 0% | 0 | 22990
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2 | B Transport Devices | [10 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.1 | EPM's/Plunging SWIC's (4) | 240000 |  |  | 240000 | 240 | 80 | 80 | 480 |  |  | 52741.6 | 292741.6 | 3 | 2 | 10 | 4 | 2 | 8 | 32% | 93677.312 | 386418.912
Includes device & electronics
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.2 | Loss Monitors |  |  |  | 0 | 120 |  |  | 240 |  |  | 20563.2 | 20563.2 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3290.112 | 23853.312
| Long LM's | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 960 | 6960
| LM's, IC's(4 in picture frame config.) | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
| 1 Detector per magnet | 24000 |  |  | 24000 | [6 empty] | 0 | 24000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 3360 | 27360
| HV Bias | 7500 |  |  | 7500 | [6 empty] | 0 | 7500 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 1050 | 8550
| Electronics | 8000 |  |  | 8000 | [6 empty] | 0 | 8000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 1120 | 9120
| Special chassis | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3 | New B Target Devices |  |  |  | 0 | 240 | 40 | 80 | 480 |  | 40 | 52958.4 | 52958.4 | 1 | 2 | 10 | 4 | 2 | 8 | 28% | 14828.352 | 67786.752
1.4.3.2.7.2.3.1 | B-SEC |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Device, with vacuum pump. | 20000 |  |  | 20000 | [6 empty] | 0 | 20000 | 3 | 2 | 8 | 1 | 2 | 8 | 24% | 4800 | 24800
| Electronics (I/V, I/F, HV Bias, & counter) | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 10 | 4 | 2 | 8 | 28% | 1680 | 7680
| Translation Table & Controls | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3.2 | Target Temperature Monitor | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3.3 | B Target Flag |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Mount, Lamps | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 280 | 2280
| Rad-Hard video camera | 25000 |  |  | 25000 | [6 empty] | 0 | 25000 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 5000 | 30000
| Camera Lens, ND Filter, driver. | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 840 | 6840
1.4.3.2.7.2.3.4 | 90 deg telescope |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| 90 Target Tel (Scint/PMT assy & mount) | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 960 | 6960
| Tel Elec & Bias (amps, discr counter) | 12500 |  |  | 12500 | [6 empty] | 0 | 12500 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2000 | 14500
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3.5 | Loss Monitors |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| IC's (4 in picture frame config.) | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 700 | 5700
| LM VME FE electronics, Controls I/F | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 700 | 5700
| HV Bias | 2500 |  |  | 2500 | [6 empty] | 0 | 2500 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 350 | 2850
| Interface to machine protect system | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
1.4.3.2.7.2.3.6 | Cables and Racks |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Cables, connectors, patch panels | 3000 |  |  | 3000 |  |  |  | 240 |  |  | 12540 | 15540 | 1 | 2 | 4 | 2 | 2 | 8 | 18% | 2797.2 | 18337.2
| All Rack H/W and misc. items | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 280 | 2280
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.4 | B Target Instrumentation Station |  |  |  | 0 | 160 |  |  | 320 |  |  | 27417.6 | 27417.6 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 3838.464 | 31256.064
| Racks (5) installed at Instru Elec. Support location | 7500 |  |  | 7500 | [6 empty] | 0 | 7500 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 1050 | 8550
1.4.3.2.8 | Environmental Enclosures |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| New Instru enclosed room with AC | 15000 |  |  | 15000 | [6 empty] | 0 | 15000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2400 | 17400
| Control/Instru enclosure | 10000 |  |  | 10000 |  |  |  |  | 140 |  | 8969.8 | 18969.8 | 4 | 2 | 4 | 4 | 2 | 2 | 22% | 4173.356 | 23143.156
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.9 | Vacuum |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Pipe, flanges, bellows, valves | 42000 |  |  | 42000 | 80 |  |  | 120 |  | 120 | 22976.8 | 64976.8 | 3 | 2 | 8 | 4 | 2 | 2 | 24% | 15594.432 | 80571.232
| Vacuum pumps (2) |  | 48000 |  | 48000 | 40 | [5 empty] | 2674.4 | 50674.4 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 8107.904 | 58782.304
| Monitors | 5000 |  |  | 5000 | 8 |  |  | 80 |  |  | 4714.88 | 9714.88 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 1554.3808 | 11269.2608
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.10 | Installation |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Install magnets (9) | 18000 |  |  | 18000 | 36 |  |  | 2448 | 1008 |  | 194897.52 | 212897.52 | 3 | 2 | 8 | 4 | 2 | 2 | 24% | 51095.4048 | 263992.9248
| Survey beam components |  |  |  | 0 |  |  |  | 240 |  |  | 12540 | 12540 | 1 | 2 | 4 | 4 | 1 | 2 | 12% | 1504.8 | 14044.8
| Install vacuum |  |  |  | 0 |  |  |  | 160 |  | 80 | 15932 | 15932 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 2549.12 | 18481.12
| Install victualic & manifolds | 15500 |  |  | 15500 |  |  |  | 120 | 90 |  | 12036.3 | 27536.3 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4405.808 | 31942.108
| Install power & lights | 5000 |  |  | 5000 |  |  |  |  | 320 |  | 20502.4 | 25502.4 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 4080.384 | 29582.784
| Clean cave & paint | 1000 |  |  | 1000 |  |  |  | 80 | 80 |  | 9305.6 | 10305.6 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 1648.896 | 11954.496
| Close roof |  |  |  | 0 |  |  |  |  | 1440 |  | 92260.8 | 92260.8 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 14761.728 | 107022.528
| Fire Detection | 5000 |  |  | 5000 |  |  |  |  | 160 |  | 10251.2 | 15251.2 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 2440.192 | 17691.392
| Cave dehumidification | 15000 |  |  | 15000 |  |  |  |  | 40 |  | 2562.8 | 17562.8 | 4 | 2 | 4 | 4 | 2 | 2 | 22% | 3863.816 | 21426.616
| Shielding seismic restraints | 15000 |  |  | 15000 |  |  |  |  | 240 |  | 15376.8 | 30376.8 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 7897.968 | 38274.768
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.3 | Common Equipment/Facilities |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Magnet Interlock System | 35214 |  |  | 35214 | 72 |  | 96 | 608 |  |  | 41954.08 | 77168.08 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 16976.9776 | 94145.0576
| Bldg 912 Facility Upgrade | 40000 |  |  | 40000 | [6 empty] | 0 | 40000 | 3 | 2 | 8 | 4 | 2 | 2 | 24% | 9600 | 49600
1.4.3.4 | B-line Security System modifications |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| project support |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 0 | 0 | What is this?
| installation supervision |  |  |  | 0 |  |  |  | 600 |  |  | 31350 | 31350 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 3135 | 34485
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.1 | PLC Systems |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | PLC will be located in 911A cage. Some modules will resides locally.
| Programming | 0 |  |  | 0 | 320 |  | 0 | 0 | 0 | 0 | 21395.2 | 21395.2 | 2 | 2 | 3 | 2 | 2 | 8 | 19% | 4065.088 | 25460.288
| PLC & Racks | 8000 |  |  | 8000 | 32 |  | 40 | 240 | 16 | 0 | 17943.04 | 25943.04 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 3891.456 | 29834.496
| I/O modules | 6300 |  |  | 6300 | 16 |  | 0 | 40 | 0 | 0 | 3159.76 | 9459.76 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1418.964 | 10878.724
| R/IO Blocks | 8000 |  |  | 8000 |  |  | 0 | 40 | 0 | 0 | 2090 | 10090 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1513.5 | 11603.5
| UPS and Phoenix connectors | 4000 |  |  | 4000 |  |  | 0 | 40 | 40 | 0 | 4652.8 | 8652.8 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1297.92 | 9950.72
| Fiber converters (R/IO & DH+ comm)(6) | 4800 |  |  | 4800 | 16 |  | 0 | 40 | 0 | 0 | 3159.76 | 7959.76 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1193.964 | 9153.724
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.2 | Gates (Incl. 3 gates) |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Gates | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0 | The existing gates will be used.
| Gates Boxes | 1800 |  |  |  | 40 |  | 40 | 240 | 0 |  | 17452.8 | 17452.8 | 1 | 2 | 3 | 2 | 1 | 4 | 11%
| Limit switches (10) | 600 |  |  | 600 |  |  | 0 | 24 | 0 |  | 1254 | 1854 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 203.94 | 2057.94
| Electric strikes (2) | 240 |  |  | 240 |  |  | 0 | 24 | 0 |  | 1254 | 1494 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 164.34 | 1658.34
| Card Readers (2) | 400 | 0 |  | 400 | 8 |  | 0 | 40 | 0 | 0 | 2624.88 | 3024.88 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 332.7368 | 3357.6168
| Key Tree & Iris Scanner | 9000 |  |  | 9000 |  |  |  | 40 | 40 |  | 4652.8 | [7 empty] | 0% | 0 | 13652.8
1.4.3.4.3 | Cables |  |  |  | 0 |  |  |  | 80 | 40 | 0 | 6742.8 | [7 empty] | 0% | 0 | 6742.8
| Cables 18/c (3000ft) | 1500 |  |  | 1500 | 0 |  |  | 0 |  | 0 | 0 | 1500 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 225 | 1725
| Cables 12/c (3000ft) | 1500 |  |  | 1500 | 0 |  | 0 | 0 |  |  | 0 | 1500 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 165 | 1665
| Cables 8/c (3000ft) | 1350 |  |  | 1350 | 0 |  |  | 0 |  | 0 | 0 | 1350 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 148.5 | 1498.5
| Cables 4/c (3000ft) | 1050 | 0 |  | 1050 | 0 |  | 0 |  |  |  | 0 | 1050 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 115.5 | 1165.5
| Crash cables (1000ft) | 750 | 0 |  | 750 | 0 |  | 0 |  |  |  | 0 | 750 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 82.5 | 832.5
| DH+ Comm cables (1000ft) | 450 | 0 |  | 450 | 0 |  | 0 |  |  |  | 0 | 450 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 49.5 | 499.5
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.4 | CATV
| Bobcat switch 16*2 mux (2) | 1200 |  |  | 1200 | 40 |  | 24 | 80 | 0 |  | 8197.44 | 9397.44 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1221.6672 | 10619.1072
| Lee Data 1*1 Fiber Optics Transmitter (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1254 | 1754 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 228.02 | 1982.02
| Lee Data 1*1 Fiber Optics Receiver (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1254 | 1754 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 228.02 | 1982.02
| Digital Cameras (6) | 1800 | 0 |  | 1800 |  |  |  | 40 | 0 |  | 2090 | 3890 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 505.7 | 4395.7
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.5 | Chipmunks | [21 empty] | Will use existing chipmunks and DAQ hardware. If required additional units purchase later.
| Chipmunks (0 units) | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
| VME SIS Scaler board | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
| Weather proof enclusure | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
| Coaxial cables (1000 ft) | 0 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.6 | Crash, Sweep & Alarms
| Check station boxes | 300 |  |  | 300 | 80 |  | 40 | 80 | 0 |  | 11767.2 | 12067.2 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1568.736 | 13635.936
| Crash Actuators | 500 |  |  | 500 |  |  |  | 80 | 0 |  | 4180 | 4680 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 608.4 | 5288.4
| Crash Stations and Alarms | 1500 |  |  | 1500 |  |  |  | 160 | 0 |  | 8360 | 9860 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1281.8 | 11141.8
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.5 | Neutral beam |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.5.1 | Target Station |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Installation |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.5.2 | D1 sweeper | 12000 | 99225 |  | 111225 | 40 |  | 120 | 680 |  |  | 44919.6 | 156144.6 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 40597.596 | 196742.196
| Hookup | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 21922.72 | 25922.72 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 3888.408 | 29811.128
1.4.3.5.3 | D2 sweeper | 7000 | 202250 |  | 209250 | 40 |  | 120 | 160 |  |  | 17749.6 | 226999.6 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 59019.896 | 286019.496
| Hookup | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 21922.72 | 25922.72 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 3888.408 | 29811.128
1.4.3.5.4 | D3 sweeper | 7000 | 471500 |  | 478500 | 40 |  | 120 |  |  |  | 9389.6 | 487889.6 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 126851.296 | 614740.896
| Hookup | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 21922.72 | 25922.72 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 3888.408 | 29811.128
1.4.3.5.5 | Collimator |  |  |  | 0 | 160 |  | 320 |  |  |  | 28604.8 | 28604.8 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 7437.248 | 36042.048
| Vacuum box |  | 40000 |  | 40000 | [6 empty] | 0 | 40000 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 10400 | 50400
| Heavy met liner |  | 76000 |  | 76000 | [6 empty] | 0 | 76000 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 19760 | 95760
| Steel shielding |  | 650000 |  | 650000 | [6 empty] | 0 | 650000 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 169000 | 819000
| Installation |  |  |  | 0 | [6 empty] | 0 | 0 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.6 | D4 sweeper | 7000 | 338750 |  | 345750 | 40 |  | 120 |  |  |  | 9389.6 | 355139.6 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 92336.296 | 447475.896
| Installation |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Hoookup |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.7 | Power supplies |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify PSs for new controls (6) | 45000 |  |  | 45000 | 80 |  | 48 | 3240 |  |  | 177324.88 | 222324.88 | 4 | 4 | 4 | 4 | 2 | 8 | 36% | 80036.9568 | 302361.8368
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.8 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify Royals (4) |  | 60000 |  | 60000 | [6 empty] | 0 | 60000 | 4 | 4 | 4 | 4 | 2 | 8 | 36% | 21600 | 81600
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.9 | Experimental area |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Detector pit |  | 266000 |  | 266000 | [6 empty] | 0 | 266000 | 4 | 4 | 4 | 4 | 2 | 8 | 36% | 95760 | 361760
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| shielding |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| power and tray |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| counting house |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Fast electronics area |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Labor Hours |  |  |  |  | 8272 | 6070 | 4558 | 26986 | 8010 | 310 | [8 empty] | 0%
| FTE |  |  |  |  | 4.7134 | 3.4587 | 2.5972 | 15.3766 | 4.5641 | 0.17664
| TOTALS - DIRECT | 877754 | 2416725 | 0 | 834500 | 553065.92 | 541626.1 | 255065.68 | 1410018.5 | 513200.7 | 29341.5 | 3302318.4 | 6574601.8 | [6 empty] | 23.02% | 1513280.954 | 8090825.554
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 24.98% | 13.19% |  |  | 39.47% | 39.47% | 39.47% | 39.47% | 12.05% | 12.05% | [9 empty] | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 1096997.1997 | 2735575.6129 |  | 3832572.8126 | 771378.2922 | 755422.8184 | 355748.061 | 1966596.7893 | 575041.3843 | 32877.1508 | 4457064.496 | 8289637.3087 | [6 empty] | 23.02% | 1908031.9442 | 10197669.2529
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## WBS 1.4.4 MECO A-Line
RSVP - MECO with instrumentatiuon and security included 8/5/04
2004-06-23 | [5 empty] | Labor Rates
[6 empty] | 66.86 | 89.23 | 55.96 | 52.25 | 64.07 | 94.65
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total
Number | Description | <$25000 | >$25000 | >$600000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont |  | Comments
1.4.4.1 | Project Support |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | MECO has LE & LP under project management
| Construction Supervision |  |  |  | 0 |  |  |  | 800 |  |  | 41800 | 41800 | 1 | 2 | 10 | 2 | 1 | 2 | 16% | 6688 | 48488 |  | 5% of tech labor
Engr & Design Supervision
Physicist Supervision
Design
1.4.4.2 | Primary Beam |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.2.1 | Lambertson Magnets |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Thin Lambertson | 1000 |  |  | 1000 | 20 | 16 | 40 | 160 | 24 | 40 | 18686.96 | 19686.96 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3937.392 | 23624.352 |  | Refurbish an exixting magnet
| Thick lambertson | 6000 |  |  | 6000 | 20 | 40 | 120 | 580 | 48 | 400 | 82861.96 | 88861.96 | 1 | 2 | 12 | 4 | 1 | 4 | 22% | 19549.6312 | 108411.5912 |  | Refurbish an exixting magnet, fab new pole piece
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.2.2 | Equipment Removal |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| A-Line (AQ7 to A-Target) |  |  |  | 0 |  |  |  | 192 | 88 |  | 15670.16 | 15670.16 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 2820.6288 | 18490.7888
| A1-Line |  |  |  | 0 |  |  |  | 480 | 256 |  | 41481.92 | 41481.92 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 7466.7456 | 48948.6656
| A2-Line |  |  |  | 0 |  |  |  | 64 | 216 |  | 17183.12 | 17183.12 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 3092.9616 | 20276.0816
| A3-Line |  |  |  | 0 |  |  |  | 496 | 256 |  | 42317.92 | 42317.92 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 7617.2256 | 49935.1456
| Rad material Disposal |  | 48000 |  | 48000 |  |  |  | 800 |  |  | 41800 | 89800 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 14368 | 104168
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Power Supplies |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| AC Power Distribution |  | 90000 |  | 90000 |  |  |  |  | 168 |  | 10763.76 | 100763.76 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 26198.5776 | 126962.3376 |  | Refurbish Royals
| PSI Control Upgrades | 27000 | 81000 |  | 108000 |  |  |  | 4000 | 96 |  | 215150.72 | 323150.72 | 3 | 2 | 10 | 4 | 2 | 4 | 28% | 90482.2016 | 413632.9216 |  | Upgrade to PSI control system
| Refurbish Power Supplies |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | No cost if we do controls mods
| PS Installation & Hook-up | 15000 | 26000 |  | 41000 |  |  |  | 512 | 1232 |  | 105686.24 | 146686.24 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 29337.248 | 176023.488
| Magnet Monitor System |  | 15200 |  | 15200 | 48 | 80 |  | 448 |  |  | 33755.68 | 48955.68 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 9791.136 | 58746.816 |  | SLC based, Klixon mag temp measurements
| Run & Test Power Supplies |  |  |  | 0 |  |  |  | 560 |  |  | 29260 | 29260 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 5852 | 35112
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Magnets |  |  |  | 0 | [6 empty] | 0 | 0 | [7 empty] | 0 | 0
| Refurbish Magnets | 18000 |  |  | 18000 |  |  |  | 3384 | 432 | 120 | 215850.24 | 233850.24 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 46770.048 | 280620.288
| Magnet Installation |  |  |  | 0 |  |  |  | 720 | 288 |  | 56072.16 | 56072.16 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 11214.432 | 67286.592
| Magnet DC Hook-up | 12000 | 46000 |  | 58000 |  |  |  | 1600 | 640 |  | 124604.8 | 182604.8 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 43825.152 | 226429.952 |  | New 535mcm & WCB to magnets
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Shielding |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Build for Beam Tests |  | 296900 |  | 296900 |  |  | 600 |  | 4920 | 440 | 390446.4 | 687346.4 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 164963.136 | 852309.536 |  | Build up-stream beam & temporary beam stop
| Mod for Solenoid Install |  |  |  | 0 |  |  |  |  | 1624 |  | 104049.68 | 104049.68 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 24971.9232 | 129021.6032 |  | Install shielding around solenoids & beam stop
| Seismic Anchoring | 20000 |  |  | 20000 |  |  |  |  | 800 |  | 51256 | 71256 | 2 | 2 | 10 | 10 | 2 | 2 | 36% | 25652.16 | 96908.16
| Seal Floor | 20000 |  |  | 20000 | [6 empty] | 0 | 20000 | 4 | 2 | 10 | 10 | 2 | 4 | 42% | 8400 | 28400 |  | Seal floor area near target water
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Electric & Tray | 10000 | 10000 |  | 20000 |  |  |  |  | 800 |  | 51256 | 71256 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 17101.44 | 88357.44
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Cooling Water | 3000 |  |  | 3000 |  |  |  | 240 |  |  | 12540 | 15540 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 3729.6 | 19269.6 |  | Hook-ups to SEM system
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Vacuum | 100790 | 45000 |  | 145790 | 878 |  | 366 | 1464 |  | 160 | 170822.44 | 316612.44 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 75986.9856 | 392599.4256 |  | 10**-6, no windows
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.3 | Instrumentation
| project support |  |  |  | 0 | 240 | 120 | 80 |  |  |  | 31230.8 | 31230.8 | [6 empty] | 0% | 0 | 31230.8
| installation supervision |  |  |  | 0 |  |  |  | 440 |  |  | 22990 | 22990 | [6 empty] | 0% | 0 | 22990
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| A Transport Devices | [10 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
0
| SWIC's (4 locations) |  |  |  | 0 | 240 | 40 |  | 400 |  |  | 40515.6 | 40515.6 | [6 empty] | 0% | 0 | 40515.6
| Plunging Vac SWIC (32x32) (4" pipe) | 120000 |  |  | 120000 | [6 empty] | 0 | 120000 | 3 | 2 | 9 | 4 | 2 | 8 | 31% | 37200 | 157200
| SWIC Electronics (32x32) | 90000 |  |  | 90000 | [6 empty] | 0 | 90000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 14400 | 104400
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Servo SWIC (32x32) (Air) | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600
| Servo electronics | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 6 | 2 | 2 | 8 | 20% | 400 | 2400
| Bias | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 840 | 6840
| Cables/connectors | 4000 |  |  | 4000 | [6 empty] | 0 | 4000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 560 | 4560
| Gas Distribution (Argon-C02) | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 280 | 2280
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Current Transformers |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Bergoz | 70000 |  |  | 70000 | 240 | 40 |  | 240 |  |  | 32155.6 | 102155.6 | 1 | 2 | 10 | 4 | 2 | 8 | 28% | 28603.568 | 130759.168
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Beam Position Monitors |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Includes BPM, cables, electronics | 75000 |  |  | 75000 | 400 |  | 120 | 650 |  | 40 | 71207.7 | 146207.7 | 2 | 2 | 10 | 4 | 2 | 8 | 30% | 43862.31 | 190070.01
|  | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | [6 empty] | 0% | 0 | 5000
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Loss Monitors (various locations) |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Loss Monitors w/ mounts | 16000 |  |  | 16000 | 160 |  |  | 320 |  |  | 27417.6 | 43417.6 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 8683.52 | 52101.12
| Loss monitor Electronics |  |  |  | 0 | [6 empty] | 0 | 0 | 1 | 2 | 10 | 4 | 2 | 8 | 28% | 0 | 0
| HV Bias | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 840 | 6840
| RHIC Style VME | 15000 |  |  | 15000 | [6 empty] | 0 | 15000 | 1 | 2 | 6 | 1 | 2 | 8 | 18% | 2700 | 17700
| Cables (Sig and HV) | 1600 |  |  | 1600 | [6 empty] | 0 | 1600 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 224 | 1824
| Interface to machine protect system | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 1000 | 6000
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Target Instrumentation |  |  |  | 0 | 240 |  | 120 | 480 |  | 40 | 51627.6 | 51627.6 | [6 empty] | 0% | 0 | 51627.6
| Pin Diodes |  |  |  | 0 | [6 empty] | 0 | 0 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 0 | 0
| Pin Diodes & Mounts | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2000 | 12000
| Control Chassis & DCps | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 280 | 2280
| SIS scalar | 1500 |  |  | 1500 | [6 empty] | 0 | 1500 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 210 | 1710
| Cables & Connectors | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 140 | 1140
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| 90 Degree Telescope |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Detector - PMT/Base/Scint/mount | 4500 |  |  | 4500 | [6 empty] | 0 | 4500 | 1 | 2 | 10 | 2 | 2 | 8 | 24% | 1080 | 5580
| HV Bias | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 700 | 5700
| Phillips counting electronics | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 840 | 6840
| SIS Scalar counter | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 280 | 2280
| NIM chassis | 3000 |  |  | 3000 | [6 empty] | 0 | 3000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 420 | 3420
| Cables & Connectors | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 140 | 1140
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Flags & Video |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| (2 screens, front & back of Target) |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Camera Pan, remote cntrl | 2500 |  |  | 2500 | [6 empty] | 0 | 2500 | 1 | 2 | 3 | 1 | 2 | 8 | 15% | 375 | 2875
| Flag & holder & mount | 1500 |  |  | 1500 | [6 empty] | 0 | 1500 | 1 | 2 | 3 | 1 | 2 | 8 | 15% | 225 | 1725
| Video Camera | 20000 |  |  | 20000 | [6 empty] | 0 | 20000 | 1 | 2 | 3 | 1 | 2 | 8 | 15% | 3000 | 23000
| ND Filter Assy & Controls | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 3 | 1 | 2 | 8 | 15% | 150 | 1150
| Lens & Lamps | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 3 | 1 | 2 | 8 | 15% | 150 | 1150
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Controls | 10000 |  |  | 10000 |  |  |  |  | 140 |  | 8969.8 | 18969.8 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 4552.752 | 23522.552 |  | VME Counting House
1.4.4.4 | A-Line Security modifications |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.4.1 | project support |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 0 | 0 | What is this?
| installation supervision |  |  |  | 0 |  |  |  | 600 |  |  | 31350 | 31350 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 3135 | 34485
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.4.4.2 | PLC Systems |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | PLC will be located in 911A cage. Some modules will resides locally.
| Programming | 0 |  |  | 0 | 320 |  | 0 | 0 | 0 | 0 | 21395.2 | 21395.2 | 2 | 2 | 3 | 2 | 2 | 8 | 19% | 4065.088 | 25460.288
| PLC & Racks | 8000 |  |  | 8000 | 32 |  | 40 | 240 | 16 | 0 | 17943.04 | 25943.04 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 3891.456 | 29834.496
| I/O modules | 6300 |  |  | 6300 | 16 |  | 0 | 40 | 0 | 0 | 3159.76 | 9459.76 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1418.964 | 10878.724
| R/IO Blocks | 8000 |  |  | 8000 |  |  | 0 | 40 | 0 | 0 | 2090 | 10090 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1513.5 | 11603.5
| UPS and Phoenix connectors | 4000 |  |  | 4000 |  |  | 0 | 40 | 40 | 0 | 4652.8 | 8652.8 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1297.92 | 9950.72
| Fiber converters (R/IO & DH+ comm)(6) | 4800 |  |  | 4800 | 16 |  | 0 | 40 | 0 | 0 | 3159.76 | 7959.76 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1193.964 | 9153.724
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.4.4.3 | Gates (Incl. 3 gates) |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Gates | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0 | The existing gates will be used.
| Gates Boxes | 1800 |  |  |  | 40 |  | 40 | 240 | 0 |  | 17452.8 | 17452.8 | 1 | 2 | 3 | 2 | 1 | 4 | 11%
| Limit switches (10) | 600 |  |  | 600 |  |  | 0 | 24 | 0 |  | 1254 | 1854 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 203.94 | 2057.94
| Electric strikes (2) | 240 |  |  | 240 |  |  | 0 | 24 | 0 |  | 1254 | 1494 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 164.34 | 1658.34
| Card Readers (2) | 400 | 0 |  | 400 | 8 |  | 0 | 40 | 0 | 0 | 2624.88 | 3024.88 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 332.7368 | 3357.6168
| Key Tree & Iris Scanner | 9000 |  |  | 9000 |  |  |  | 40 | 40 |  | 4652.8 | [7 empty] | 0% | 0 | 13652.8
1.4.4.4.4 | Cables |  |  |  | 0 |  |  |  | 80 | 40 | 0 | 6742.8 | [7 empty] | 0% | 0 | 6742.8
| Cables 18/c (3000ft) | 1500 |  |  | 1500 | 0 |  |  | 0 |  | 0 | 0 | 1500 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 285 | 1785
| Cables 12/c (3000ft) | 1500 |  |  | 1500 | 0 |  | 0 | 0 |  |  | 0 | 1500 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 165 | 1665
| Cables 8/c (3000ft) | 1350 |  |  | 1350 | 0 |  |  | 0 |  | 0 | 0 | 1350 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 148.5 | 1498.5
| Cables 4/c (3000ft) | 1050 | 0 |  | 1050 | 0 |  | 0 |  |  |  | 0 | 1050 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 115.5 | 1165.5
| Crash cables (1000ft) | 750 | 0 |  | 750 | 0 |  | 0 |  |  |  | 0 | 750 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 82.5 | 832.5
| DH+ Comm cables (1000ft) | 450 | 0 |  | 450 | 0 |  | 0 |  |  |  | 0 | 450 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 49.5 | 499.5
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.4.4.5 | CATV
| Bobcat switch 16*2 mux (2) | 1200 |  |  | 1200 | 40 |  | 24 | 80 | 0 |  | 8197.44 | 9397.44 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1221.6672 | 10619.1072
| Lee Data 1*1 Fiber Optics Transmitter (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1254 | 1754 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 228.02 | 1982.02
| Lee Data 1*1 Fiber Optics Receiver (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1254 | 1754 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 228.02 | 1982.02
| Digital Cameras (6) | 1800 | 0 |  | 1800 |  |  |  | 40 | 0 |  | 2090 | 3890 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 505.7 | 4395.7
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.4.4.6 | Chipmunks | [21 empty] | Will use existing chipmunks and DAQ hardware. If required additional units purchase later.
| Chipmunks (0 units) | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
| VME SIS Scaler board | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
| Weather proof enclusure | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
| Coaxial cables (1000 ft) | 0 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.4.4.7 | Crash, Sweep & Alarms
| Check station boxes | 300 |  |  | 300 | 80 |  | 40 | 80 | 0 |  | 11767.2 | 12067.2 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1568.736 | 13635.936
| Crash Actuators | 500 |  |  | 500 |  |  |  | 80 | 0 |  | 4180 | 4680 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 608.4 | 5288.4
| Crash Stations and Alarms | 1500 |  |  | 1500 |  |  |  | 160 | 0 |  | 8360 | 9860 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1281.8 | 11141.8
| Safety & Facilities |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.5 | Common Equipment and Facilities
| ODH | 5000 |  |  | 5000 | 80 |  | 80 | 240 | 240 |  | 37742.4 | 42742.4 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 11967.872 | 54710.272
| Dehumidification |  | 40000 |  | 40000 | 40 |  | 40 |  | 160 |  | 15164 | 55164 | 2 | 2 | 10 | 6 | 2 | 2 | 28% | 15445.92 | 70609.92
| Fire Detection | 5000 |  |  | 5000 |  |  |  |  | 240 |  | 15376.8 | 20376.8 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 4890.432 | 25267.232
| Bldg 912 Facility Upgrade | 40000 |  |  | 40000 | [6 empty] | 0 | 40000 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 8800 | 48800 |  | Roof Repairs
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.6 | Cryo Support Facilities |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.7 | Experimental Area |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Labor Hours |  |  |  |  | 3158 | 336 | 1710 | 21206 | 12804 | 1240 | [8 empty] | 0% | 0 | 0
| FTE |  |  |  |  | 1.7994 | 0.19145 | 0.97436 | 12.0832 | 7.2957 | 0.70655
| TOTALS - DIRECT | 838430 | 698100 | 0 | 1449730 | 211143.88 | 29981.28 | 95691.6 | 1108013.5 | 820352.28 | 117366 | 2382548.54 | 3896882.94 | [6 empty] | 22.33% | 870362.2508 | 4770187.9908
[5 empty] | 0 | [15 empty] | 0 | 0
| indirect % | 24.98% | 13.19% |  |  | 39.47% | 39.47% | 39.47% | 39.47% | 12.05% | 12.05% | [9 empty] | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 1047850.9493 | 790203.8235 |  | 1838054.7728 | 294488.9563 | 41815.8265 | 133464.0597 | 1545380.9944 | 919204.7297 | 131508.603 | 3065863.1697 | 4903917.9425 | [6 empty] | 22.33% | 1095281.825 | 5999199.7675

## WBS 1.4.5 Project Office
RSVP - AGS Project Office
10/05/04 - | [8 empty] | Labor Rates
[7 empty] | 106.07 | 47.54 | 66.86 | 89.23 | 55.96 | 52.25 | 64.07 | 94.65
Total
WBS |  | Materials |  |  | Travel | Total |  |  | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total
Number | Description | <$25,000 | >$25,000 | >$600,000 |  | Mat'ls | Management | Administrative | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | Comments/WBS Dictionary
1.4.5 | RSVP AGS Project Office |  |  |  |  | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.5.1 | Project Head |  |  |  |  | 0 | 4388 | [7 empty] | 465435.16 | 465435.16 | [6 empty] | 0% | 0 | 465435.16 | 0.5 FTE per year x 5 years
1.4.5.2 | Deputy Project Head |  |  |  |  | 0 | 4388 | [7 empty] | 465435.16 | 465435.16 | [6 empty] | 0% | 0 | 465435.16 | 0.5 FTE per year x 5 years
1.4.5.3 | Fiscal |  |  |  |  | 0 |  | 2194 | [6 empty] | 104302.76 | 104302.76 | [6 empty] | 0% | 0 | 104302.76 | 0.25 FTE per year x 5 years
1.4.5.4 | MSTC | 15000 |  |  | 35000 | 50000 | [8 empty] | 0 | 50000 | [6 empty] | 0% | 0 | 50000 | $10,000 per year x 5 years
| Labor Hours | [5 empty] | 8776 | 2194 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0%
| FTE | [5 empty] | 5.0006 | 1.2501 | 0 | 0 | 0 | 0 | 0 | 0
| TOTALS - DIRECT | 15000 | 0 | 0 | 35000 | 50000 | 930870.32 | 104302.76 | 0 | 0 | 0 | 0 | 0 | 0 | 1035173.08 | 1085173.08 | [6 empty] | 0% | 0 | 1085173.08
[6 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 24.98% | 13.19% |  | 25.24% |  | 39.47% | 39.47% | 39.47% | 39.47% | 39.47% | 39.47% | 12.05% | 12.05% | [9 empty] | 0% | 0%
[6 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 18746.6625 | 0 |  | 43834 | 62580.6625 | 1298313.875 | 145474.3132 | 0 | 0 | 0 | 0 | 0 | 0 | 1443788.1882 | 1506368.8507 | [6 empty] | 0% | 0 | 1506368.8507
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## RSVP ops cost Summary Sheet
RSVP Operations Costs per week, FY 2005 $'s with reduced NSF Indirects
The present NYPA contract expires in July 2005 and energy costs are expected to increase
Only valid for construction period
Assumed Energy Cost | 85 | per MWhr | FY2006 and beyond
Fixed Personnel Costs | FTE's
Base FTE | 12 | 1883503.2898 | (shared)
E940 FTE | 6 | 884152.9513 | (shared)
E926 FTE | 4 | 0 | (shared)
Total Personnel Cost | 18 | 2767656.2411
Costs Common to RSVP
Booster and AGS Accelerators |  | w/o RHIC | w/RHIC HI | w/RHIC pp
DTS |  | 24012.5167 | 12006.2583 | 12006.2583
MSTC |  | 68283.2809 | 34141.6405 | 34141.6405
SP |  | 22264.1269 | 11132.0634 | 11132.0634
Shift Differential (5 seats) |  | 10722.7158 | 0 | 0
Booster and AGS sub-total |  | 125282.6402 | 57279.9622 | 57279.9622
On time% (determined by RHIC needs) |  | 100% | 80% | 80%
Booster & AGS cost per week |  | 125282.6402 | 45823.9698 | 45823.9698
Linac
DTS |  | 5705.9446 | 5705.9446 | 2852.9723
MSTC |  | 10872.2894 | 10872.2894 | 5436.1447
SP |  | 47434.3587 | 47434.3587 | 23717.1794
Linac Sub-Total |  | 64012.5927 | 64012.5927 | 32006.2963
On time% |  | 100% | 100% | 80%
Linac cost per week |  | 64012.5927 | 64012.5927 | 25605.0371
AGS SEB Experimental area MSTC |  | 21044 | 21044 | 21044
Total Common Costs/week |  | 210339.2329 | 130880.5625 | 92473.0069
MECO MSTC |  | 29699.9125 | 29699.9125 | 29699.9125
Power (MW)
Base (Experiment power that's always on) |  | 1 | 1 | 1
Accelerators |  | 8 | 3 | 3
Linac (always on) |  | 2 | 2 | 0
Experiment (that can be turned off) |  | 0 | 0 | 0
Total |  | 11 | 6 | 4
Power Cost
Cost/MWhr |  | 85 | 85 | 85
On time |  | 100% | 80% | 80%
Sub-Total |  | 157080 | 77112 | 48552
0% FCR |  | 0 | 0 | 0
MECO Power Total |  | 157080 | 77112 | 48552
E940 Experiment Specific Costs/week |  | 186779.9125 | 106811.9125 | 78251.9125
K0PI0 MSTC |  | 14849.9562 | 14849.9562 | 14849.9562
Power (MW)
Base (Experiment power that's always on) |  | 0.5 | 0.5 | 0.5
Accelerators |  | 12 | 7 | 7
Linac (always on) |  | 2 | 2 | 0
Experiment (that can be turned off) |  | 0.5 | 0.5 | 0.5
Total |  | 15 | 10 | 8
Power Cost
Cost/MWhr |  | 85 | 85 | 85
On time |  | 100% | 80% | 80%
Sub-Total |  | 214200 | 121380 | 92820
0% FCR |  | 0 | 0 | 0
K0PI0 Power Total |  | 214200 | 121380 | 92820
E926 Experiment Specific Costs/week |  | 229049.9562 | 136229.9562 | 107669.9562
Example Total Cost
Accelerator Weeks | 11 | 2313731.5619 | 1439686.1872 | 1017203.0755 | 36
E926 Weeks | 7 | 1603349.6937 | 953609.6937 | 753689.6937 | 72
E940 Weeks | 4 | 747119.6499 | 427247.6499 | 313007.6499 | 54
Personnel FTE's | 18 | 2767656.2411 | 2767656.2411 | 2767656.2411
Total RSVP Cost |  | 7431857.1466 | 5588199.7718 | 4851556.6601
Example (Jan 04 plan) | FY06 | FY07 | FY08 | FY09 | FY10
K0PI0 | 7 | 9 | 6 | 7 | 9.5
MECO | 4 | 6 | 7 | 7 | 9.5
Outside RHIC
K0PI0 | 0 | 0.5 | 0 | 0 | 2.5
MECO | 0 | 0.5 | 0 | 0 | 2.5
W/RHIC HI
K0PI0 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
MECO | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
W/RHIC pp
K0PI0 | 2 | 3.5 | 2 | 3.5 | 3.5
MECO | 2 | 3.5 | 2 | 3.5 | 3.5
Total
Personnel | 2767656.2411 | 2767656.2411 | 2767656.2411 | 2767656.2411 | 2767656.2411 | 13838281.2053
Other | 2508546.2427 | 3483102.2336 | 2508546.2427 | 3064848.0663 | 5156118.9026 | 16721161.6878
Total | 5276202.4837 | 6250758.4746 | 5276202.4837 | 5832504.3074 | 7923775.1437 | 30559442.8932

## WBS 1.4.1 Dictionary
RSVP - Booster/AGS Modifications
9/2/04 (K. Brown v2.2 with CAPs added 9/16/04)
WBS | WBS
Number | Description | WBS Dictionary Entry
1.4.1 | BOOSTER/AGS MODIFICATIONS | Booster and AGS modifications section to the AGS RSVP Project
1.4.1.1 | Project Support
1.4.1.1.1 | installation supervision
1.4.1.2 | Booster | Booster Modifications
1.4.1.2.1 | Electrical modifications | Booster Electrical Systems Modifications, include cable repairs, upgrade of extraction kicker capicitor banks, and main magnet coil replacments.
Project Support
| Cable Repair/Replacement | Radiation or other environmentally damaged cables to be replaced or repaired
| Cable Trays | Old and damaged cable trays to be repaired or replaced.
| Upgrade of PFN's | Pulse forming network capacitor banks for the extraction kicker to be modified to reducing radiation damage during RSVP operations
| Magnet Coils - Mechanical | Costs for replacement of 6 Booster dipole coils. Replace 1 per year during RSVP operations.
1.4.1.2.2 | Mechanical modifications | Mechanical modifications of the Booster, include two spare extraction septa, projection C5 and C7 main magnet coils during H- injection, and collimators to allow higher throughput.
Project Support
| Spare Booster F6 | Currently no Spare extraction septum for Booster. This includes costs for having two spare septum magnets.
| Booster Injection | Booster C5 (location of H- injection point) and C7 (just after H- stripping foil) magnet coils have failed once each. This covers protection of these magnets during H- injection.
| Collimators | Beam loss limits currently keep the intensity in the Booster to < 30 TP/sec. Cost of multistage collimation to allow higher beam throughput.
1.4.1.2.3 | RF System modifications | Bosoter RF System modifications for RSVP, include RF feedback to gain stability for high intensity acceleration.
Project Support
| RF Feedback | Cost of adding RF feedback for high intensity operation to Band II and Band III rf sytems.
1.4.1.2.4 | Instrumentation | Instrumentation modifications for RSVP, includes upgrade to loss monitor system, new wall current monitor, heavy ion inflector protection,
Project Support
| Loss Monitors | Booster Loss monitor system upgrade. Critical for monitoring beam losses and keeping within preset limits.
| WCM Upgrade (D6) | A new wall current monitor for high beam currents
| Inflector protection (C3) | Protection of Heavy ion injection inflector from high intensity protons.
| Cables | Radiation or other environmentally damaged cables to be replaced or repaired
| BTA | Remote gain control for BTA instrumentation.
1.4.1.2.5 | Controls | Hardware and software controls support for Booster Modifciations.
Project Support
| Instrumentation Interfaces | Hardware Controls interface support for instrumention
| Software & Database | Software and database support for instrumentation.
1.4.1.2.6 | Safety | Safety system considerations, includes shield cap for the Booster
Project Support
| Shield Caps | Cost of capping the Booster to prevent ground-water contamination.
1.4.1.3 | AGS
1.4.1.3.1 | Electrical modifications | Electrical systems modifications for the AGS, includes ripple improvement for slow extraction, new extraction devices power supplies, main magnet coil replacements, and modifications to injection kicker capicitor bank to reduce radiation damage.
Project Support
| Cable Repair/Replacement | Radiation or other environmentally damaged cables to be replaced or repaired
| Cable Trays | Old and damaged cable trays to be repaired or replaced.
| Active Filter | New active filter for improved (reduced) main magnet power supply ripple during extraction
| F5 Power Supply | new thin septum power supply for new thin septum magnet
| F10 Power Supply | new thick septum power supply for new thick septum magnet
| H20 Power Supply | new electrostatic septum power supply for new electrostatic septum
| Upgrade of PFN's | Pulse forming network capacitor banks for the injection kicker to be modified to reducing radiation damage during RSVP operations
| Magnet Coils - Mechanical | Pre-emptive replacement of magnet coils in slow extraction region.
| J10 Bump; Low ripple P.S. | New J10 bump power supply with low ripple, to improve slow extracted beam spill structure.
1.4.1.3.2 | Mechanical modifications | Mechanical modifications to AGS equipment, includes upgrade to Vacuum chamber impedence, new extraction magnets, new sextupole coils, and collimators.
Project Support
| AGS RC Networks | Reduce overall AGS impedence (avoid high intensity instabilities) and RC networks that can take the higher power image currents from high intensity beams
| New F5 (2) | new thin magnet septum and spare for slow extraction
| New F10 (2) | new thick magnetic septum and spare for slow extraction
| New H20 (2) | new electrostatic septum and spare for slow extraction
| Collimators | Beam loss limits currently limit the intensity. Cost of multistage collimation to allow higher beam throughput.
| Sextupole Coils** | replace 16 AGS sextupole coils with new coils (current coils are very old and damaged is evident)
1.4.1.3.3 | Instrumentation | Instrumentation modifications in the AGS for RSVP, includes beam loss monitoring, new device positioning interfaces, ring grounds monitoring, and beam instabilities monitoring.
Project Support
| Loss Monitors | Upgrade AGS long loss montitor system used to monitor beam efficiencies.
| Wall Current Monitor | Segmented wall current monitor for monitoring beam instabilites
| IPM Servo | move controled leak hardware to low radiation area
| Motion Systems | upgrade position controls for septa and AGS instrumentation to new controls and motors
| Video | radiation hardened cameras for instrumentation in extraction systems
| Ring Grounds | upgrade ring grounds monitoring system
| Cables | Radiation or other environmentally damaged cables to be replaced or repaired
1.4.1.3.4 | Controls | Hardware and software support for AGS Modifications
Project Support
| Instrumentation Interfaces | hardware controls interfaces for instrumentation
| Software & Database | software and database support for instrumentation
| Ring Ground Interface | hardware controls support for ring grounds monitoring system
| Software & DB | software and database support for ring grounds system
| Power Supply Interfaces | hardware controls interfaces for new power supplies
| Software & Database | hardware and software support for new power supplies
1.4.1.3.5 | Safety | Safety system considerations, includes capping the AGS ring shielding.
Project Support
| Shield Caps (PE Subcontract) | Cost of capping the AGS to prevent ground-water contamination.
1.4.1.4 | MECO AGS Modifications
1.4.1.4.1 | AC-Dipole | Dipole magnet in which the field oscillates at the vertical betatron resonance frequency, rapidly pushing protons outside the RF buckets of interest out of the aperture of the machine.
Project Support
Magnet
Power Supply
Installation
1.4.1.4.2 | Strip-line Kickers | These cancel the sinusoidal activation of the AC dipole magnet for protons within the nominal beam buckets
Project Support
Strip-lines
Power Supply/Pulsers
Low Level Controls
Installation
1.4.1.4.3 | Simulations | Tracking simulations of mini-bunched slow extraction.
Mini-bunched extraction
1.4.1.5 | KOPIO AGS Modifications
1.4.1.5.1 | Booster To AGS Kickers | CFI project to upgrade the injection kickers to stabilized proton injection
Project Support
1.4.1.5.2 | 25 MHz RF cavity | CFI project to build the 25 MHz RF cavity which will microbunch the slow extracted beam into <300 psec bunches.
Project Support
1.4.1.5.3 | 100 MHz RF Cavity | Additional RF cavity to get even shorter bunches (<250 psec).
Project Support
1.4.1.5.4 | Simulations | Microbunching tracking simulations of slow extraction.
1.4.1.6 | Beam Development | AGS studies required to achieve the beam characteristics needed for MECO
Project Support
Labor Hours
FTE
TOTALS - DIRECT
indirect %
TOTAL
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
0%

## AGS R&D (Plan)
KOPIO R&D -- 2004 (C. Pearson)
| 64.13 | 85.61 | 53.69 | 50.13 | 89.7
| Eng'r | Physicist | Design | Tech | Shops
Work Description | Hours | Hours | Hours | Hours | Hours |  | Comments
Liaison engineer | 520 |  |  |  |  | 46510.938 | .25 time -- Liaison services & neutral beam concept
Liaison physicist |  | 520 |  |  |  | 62089.5276 | .25 time
General layout |  |  | 320 |  |  | 23962.5977 | 1 man - 2 months
Baseline support | 240 | 240 | 160 | 80 |  | 67698.0207 | Support for bottoms up estimate
0
primary beam design | 160 | 160 | 80 | 80 |  | 44999.6073
Shielding design | 80 | 160 |  |  |  | 26259.999 | primary beam dump, target area, neutral beam, exp area
Target thermal analysis | 80 | 80 | 40 | 80 | 80 | 33337.2267 | mechanical prototype -- testing in D-line ?
Instrumentation | 80 | 80 | 40 |  | 80 | 27743.7967 | EPM, intensity meas, target monitoring development
Electrical layout | 80 |  | 40 |  |  | 10150.8536 | Royal replacement development
Controls R&D | 80 | 80 | 40 |  |  | 19703.0887 | PS and Inst controls analysis and development
Safety system R&D | 80 |  | 40 |  |  | 10150.8536 | PASS analysis and development
Switchyard collimator R&D | 80 | 80 | 40 | 80 |  | 25296.5187 | extraction and primary beam lines
Total hours | 1480 | 1400 | 800 | 320 | 160
Total direct cost | 94912.4 | 119854 | 42952 | 16041.6 | 14352
Burdened cost | 133570.2205 | 168670.5342 | 60446.3496 | 22575.3437 | 16124.472 | 397903.0283
|  |  |  | Total | 401386.92
KOPIO CFI Support Related -- 2004 (K. Brown)
| 64.13 | 85.61 | 53.69 | 50.13
| Eng'r | Physicist | Design | Tech | MSTC
Work Description | Hours | Hours | Hours | Hours |  |  | Comments
Support for 25 MHz Cavity Development | 1316 |  |  |  | 10000 | 130206.4509
93 MHz cavity relocation estimate | 173 | 173 |  |  |  | 36130.5395 | priority of this is TBD
AGS beam extraction simulation |  | 265 |  |  |  | 31641.7785 | priority of this is TBD
AGS Collimator R&D | [6 empty] | priority of this is TBD
Kicker R&D | [6 empty] | priority of this is TBD
Total hours | 1489 | 438 | 0 | 0
Total direct cost | 95489.57 | 37497.18 | 0 | 0 | 10000
Burdened cost | 134382.4719 | 52769.7814 | 0 | 0 | 12498 | 197978.7689
|  |  |  | Total | 199650.2533
MECO R&D -- 2004 (adapted from draft SOW/Hebert guidance)
| 64.13 | 85.61 | 53.69 | 50.13 | 89.7
| Eng'r | Physicist | Design | Tech | Shops
Work Description | Hours | Hours | Hours | Hours | Hours |  | Comments
Liaison engineer | 310 |  |  |  |  | 27727.6746
Liaison physicist |  | 310 |  |  |  | 37014.9107
General layout | [5 empty] | 0
Baseline support | [5 empty] | 0
primary beam design | 160 | 160 | 80 |  |  | 39406.1773
Shielding design | 48 | 96 |  |  |  | 15755.9994
MGMD Support | 79 | 107 |  |  |  | 19842.1992
Total hours | 597 | 673 | 80 | 0 | 0
Total direct cost | 38285.61 | 57615.53 | 4295.2 | 0 | 0
Burdened cost | 53879.339 | 81082.3354 | 6044.635 | 0 | 0 | 139746.9612
AGS RSVP Grand Total 2005 R&D | [5 empty] | 735628.7584

## AGS R&D (Revised Plan)
AGS RSVP Project Office -- 2004 (P.Pile)
AGS Project Office - part not covered in either MECO or K0PI0 Plan
FTE
Project Manager, P. Pile | 0.25
Asst Project Manager, A. Pendzick | 0.25
AGS/Booster sub-project manager, K. Brown | 0.25
Fiscal, D. Sappo | 0.25
Subtotal | 1 | 175000
Other Labor (physicist/engineers) |  | 25000
MSTC |  | 10000
Total |  | 210000
KOPIO R&D -- 2004 (C. Pearson)
| 64.13 | 85.61 | 53.69 | 50.13 | 89.7
| Eng'r | Physicist | Design | Tech | Shops
Work Description | Hours | Hours | Hours | Hours | Hours |  | Comments
Liaison engineer# | 440 |  |  |  |  | 39355.4091 | .25 time -- Liaison services & neutral beam concept
Liaison physicist# |  | 440 |  |  |  | 52537.2926 | .25 time
General layout# |  |  | 200 |  |  | 14976.6236 | 1 man - 2 months
Baseline support# | 100 | 100 | 50 |  |  | 24628.8608 | Support for bottoms up estimate
0
primary beam design# | 100 | 100 | 50 |  |  | 24628.8608
Shielding design# | 40 | 80 |  |  |  | 13129.9995 | primary beam dump, target area, neutral beam, exp area
Target thermal analysis* | [5 empty] | 0 | mechanical prototype -- testing in D-line ?
Instrumentation* | [5 empty] | 0 | EPM, intensity meas, target monitoring development
Electrical layout* | [5 empty] | 0 | Royal replacement development
Controls R&D* | [5 empty] | 0 | PS and Inst controls analysis and development
Safety system R&D* | [5 empty] | 0 | PASS analysis and development
Switchyard collimator R&D* | [5 empty] | 0 | extraction and primary beam lines
Total hours | 680 | 720 | 300 | 0 | 0
Total direct cost | 43608.4 | 61639.2 | 16107 | 0 | 0
Burdened cost | 61370.1013 | 86744.8462 | 22667.3811 | 0 | 0 | 169257.0464
|  |  |  | Total | 170782.3286
KOPIO CFI Support Related -- 2004 (K. Brown)
| 64.13 | 85.61 | 53.69 | 50.13
| Eng'r | Physicist | Design | Tech | MSTC
Work Description | Hours | Hours | Hours | Hours |  |  | Comments
Support for 25 MHz Cavity Development | 1316 |  |  |  | 10000 | 130206.4509
93 MHz cavity relocation estimate* | [5 empty] | 0 | priority of this is TBD
AGS beam extraction simulation* | [5 empty] | 0 | priority of this is TBD
Total hours | 1316 | 0 | 0 | 0
Total direct cost | 84395.08 | 0 | 0 | 0 | 10000
Burdened cost | 118769.1961 | 0 | 0 | 0 | 12498 | 130206.4509
|  |  |  | Total | 131267.1961
MECO R&D -- 2004 (adapted from draft SOW/Hebert guidance)
| 64.13 | 85.61 | 53.69 | 50.13 | 89.7
| Eng'r | Physicist | Design | Tech | Shops
Work Description | Hours | Hours | Hours | Hours | Hours |  | Comments
Liaison engineer** | 440 |  |  |  |  | 39355.4091
Liaison physicist** |  | 440 |  |  |  | 52537.2926
General layout** |  |  | 200 |  |  | 14976.6236
Baseline support** | 100 | 100 | 50 |  |  | 24628.8608
primary beam design# | 100 | 100 | 50 |  |  | 24628.8608
Shielding design# | 40 | 80 |  |  |  | 13129.9995
MGMD Support | 79 | 107 |  |  |  | 19842.1992
Total hours | 759 | 827 | 300 | 0 | 0
Total direct cost | 48674.67 | 70799.47 | 16107 | 0 | 0
Burdened cost | 68499.8631 | 99636.0941 | 22667.3811 | 0 | 0 | 189099.2456
# Reduced Effort
* Eliminated
** Enhanced Effort
AGS RSVP Grand Total 2005 R&D | [5 empty] | 698562.7429

## AGS WBS R&D Summary (proposed)
FY2005 R$D Budget for C-AD |  |  | 2005-08-25
Available Funds - note the $250K for "other high priority work at the AGS" is not available
Source | Total C-AD Amount | Remarks
MECO | 141000 | includes $20,000 for MDMG support (Magnet Division)
K0PI0 | 601000
Total | 742000
Essential Requirements
AGS Project Office |  | FTE
| Project Manager, P. Pile | 0.5
| Asst Project Manager, A. Pendzick | 0.5
| AGS/Booster sub-project manager, K. Brown | 0.5
| Fiscal, D. Sappo | 0.25
| Subtotal | 1.75 | 325000
| Other Labor (physicist/engineers) |  | 50000
| MSTC |  | 20000
| Total |  | 395000
CFI Support
| 25 MHz Cavity, 1/4 *3 FTE Engineering | 0.75 | 119000
| MSTC |  | 10000
| Total | 0.75 | 129000
MECO Support
| Liaision Engineer, D. Phillips | 0.5
| Liaision Physicist, W. Meng | 0.5
| MGDM Support, P. Wanderer | 0.25
| Total | 1 | 238000
K0PI0 Support
| Liaision Engineer, C. Pearson | 0.5
| Liaision Physicist, D. Lazarus | 0.5
| Total | 1 | 185000
Essential Requirements Total |  |  | 947000
Net funds remaining |  |  | -205000

## AGS WBS R&D Summary (revised)
FY2005 Proposed R&D Budget for C-AD |  |  | 2005-08-26
Available Funds - note the $250K for "other high priority work at the AGS" is not available
Source | Total C-AD Amount | Remarks
MECO | 141000 | includes $20,000 for MDMG support (Magnet Division)
K0PI0 | 601000
Total | 742000
Essential Requirements (revised)
AGS Project Office |  | FTE
| Project Manager, P. Pile | 0.33
| Asst Project Manager, A. Pendzick | 0.33
| AGS/Booster sub-project manager, K. Brown | 0.33
| Fiscal, D. Sappo | 0.25
| Subtotal | 1.24 | 240000
| Other Labor (physicist/engineers) |  | 52000
| MSTC |  | 20000
| Total |  | 312000
CFI Support
| 25 MHz Cavity, 1/4 *3 FTE Engineering | 0.75
| Subtotal | 0.75 | 120000
| MSTC |  | 10000
| Total |  | 130000
MECO Support
| Liaision Engineer, D. Phillips | 0.33
| Liaision Physicist, W. Meng | 0.33
| MGDM Support, P. Wanderer | 0.25
| Total | 0.91 | 175000
K0PI0 Support
| Liaision Engineer, C. Pearson | 0.33
| Liaision Physicist, D. Lazarus | 0.33
| Total | 0.66 | 125000
Essential Requirements Total |  |  | 742000
Net funds remaining |  |  | 0

## Sheet1
System | WBS | Description
Project Office | 1.1
KOPIO | 1.2
AGS | 1.2.1 | AGS Modifications
AGS | 1.2.2 | Beam
| 1.2.3 | Vacuum System
| 1.2.4 | Preradiator
| 1.2.5 | Calorimeter
| 1.2.6 | Charged Particle Veto
| 1.2.7 | Photon Veto
| 1.2.8 | Catcher
| 1.2.9 | Trigger
| 1.2.10 | DAQ
| 1.2.11 | Front End Electronics (FEE)
MECO | 1.3
AGS | 1.3.1 | AGS Modifications & Studies
AGS | 1.3.2 | Proton Beamline | RFMM
AGS (tgt) | 1.3.3 | Production Target and Shield | Contentious
| 1.3.4 | Solenoids
| 1.3.5 | Muon Beamline
| 1.3.6 | Tracker
| 1.3.7 | Calorimeter
| 1.3.8 | Cosmic Ray Shield
| 1.3.9 | DAQ & Online Computing
| 1.3.10 | Infrastructure
AGS | 1.4
| 1.4.1 | AGS/Booster
| 1.4.2 | Switchyard
| 1.4.3 | KOPIO
| 1.4.4 | MECO
| 1.4.5 | AGS Beam Development | For Now
| 1.4.6 | Admin

## Resource Categories
RSVP Resource Categories
FY05 (D. Sappo, 9/30/04)
Category |  | Code | Rate | O/H Rate
Labor
| Physicist | PH | 89.23 | 39.47%
| Mechanical Engineer | ME | 66.86 | 39.47%
| Electrical Engineer | EE | 66.86 | 39.47%
| Mechanical Designer | MD | 55.96 | 39.47%
| Electrical Designer | ED | 55.96 | 39.47%
| IT Professional | IT | 69.28 | 39.47%
| Administrative | ADM | 47.54 | 39.47%
| Management | MGT | 106.07 | 39.47%
| Supervisor | SPV | 88.86 | 39.47%
| Electrical Technician | ET | 52.25 | 39.47%
| Mechanical Technician | MT | 52.25 | 39.47%
| Pulsed Power Technician | PPT | 52.25 | 39.47%
| Access Controls Technician | ACT | 52.25 | 39.47%
| PS Systems Technician | PST | 52.25 | 39.47%
| Coordinators | MCC | 66.86 | 39.47%
| Operators | MCO | 69.28 | 39.47%
| Vacuum Technician | VT | 52.25 | 39.47%
| RF Technician | RFT | 52.25 | 39.47%
| Instrumentation Beam Technician | IBT | 52.25 | 39.47%
| Cryogenic Technician | CT | 52.25 | 39.47%
| Controls Technician | CNT | 52.25 | 39.47%
| Beam Service Technician | BST | 52.25 | 39.47%
| Collider Accelerator Support Technician | CAS | 52.25 | 39.47%
| Mechanical Service Technician (FES) | MST | 52.25 | 39.47%
| Survey | S | 52.25 | 39.47%
| Electronics Service Technician (FES) | EST | 52.25 | 39.47%
| Water Systems Technician (FES) | WST | 52.25 | 39.47%
| Post Docs | PD | 42.25 | 39.47%
Other Labor
| Scientific Distributed Labor | SD | 131.05 | 17.05%
| Contract Labor | CL | Per Contract | 17.05%
| Consultants/Collaborators | CC | Per Contract | 17.05%
Support Labor
| Central Shops | CS | 92.83 | 12.05%
| Building Trades (Standard) | BTS | 78.35 | 12.05%
| Building Trades Engineer | BTE | 94.65 | 12.05%
| Building Trades Carpenter | BTC | 78.35 | 12.05%
| Building Trades Electrician | BTE | 78.35 | 12.05%
| Building Trades Rigger | BTR | 78.35 | 12.05%
Materials
| Low Value (Less Than $25K) | LV | Per PO | 25.24%
| High Value (Over $25K) | HV | Per PO | 13.19%
| Large Procurement (Over $600K) | LP | Per PO | 13.19% | Only First $600K
| Capital Equipment | CE | Per PO | 8.19%
Other | Travel | TV | Per Trip | 25.24%

## Labor and Indirect Rates (NSF)
For non-DOE projects - includes safeguards tax (adds 2.7% to G&A) and Full Cost Recovery fee (3%)
| FY05 |  |  |  | 2004-09-16
Indirect for Capital Projects
Direct Salary and Wage
Rate
| Direct Cost |  |  |  | 60406.72
| Paid Absence Burden(PAB) |  |  | 18.5% | 11175.2432
| Fringe on DC and PAB |  |  | 41% | 29348.6049
| Nominal Salary Base (Direct Cost) |  |  |  |  | 100930.5681 | 1 |  | 59.85%
| Space Charge (SC) on DC,PAB and Fringe |  |  | 2.21% | 2230.5656
| Fuel Charge on Space Charge |  |  | 16.6% | 370.2739
| Organizational Burden(OB) on DC,PAB and Fr |  |  | 8.86% | 8942.4483
| Power(Pwr) on DC, PAB and Fr |  |  | 2.54% | 2563.6364
| Communications on DC, PAB and Fr (incl. in OB) |  |  | 0% | 0
| ITD Contribution on DC, PAB and Fr |  |  | 1.59% | 1604.796
| Auto on DC, PAB and Fr |  |  | 0.79% | 797.3515
| ESH on DC, PAB and Fr |  |  | 3.17% | 3199.499
| Department Burden Total |  |  |  |  | 19708.5707 | 19.53%
| G&A on DC |  |  | 17.05% | 10299.3458
| G&A on PAB |  |  | 17.05% | 1905.379
| G&A on Fr |  |  | 17.05% | 5003.9371
| G&A on SC |  |  | 17.05% | 380.3114
| G&A on Fuel |  |  | 17.05% | 63.1317
| G&A on OB |  |  | 17.05% | 1524.6874
| G&A on All else except power |  |  | 17.05% | 955.0807
| G&A on Pwr |  |  | 0% | 0
| BNL G&A Total |  |  |  |  | 20131.8732 | 19.95%
| Department plus G&A |  |  |  |  | 39840.4439 | 39.47%
| Sub-Total |  |  |  | 140771.012
| FCR (direct to DOE) |  |  | 0% | 0 | 0 | 0%
| Department plus G&A plus FCR |  |  |  |  | 39840.4439 | 39.47%
| Total |  |  |  | 140771.012 | 140771.012
| Indirect on Direct+PAB+Fringe ($100,000) |  |  |  | 39.47%
Consultants/Jobshoppers | [5 empty] | Dept | Lab | DOE | Total
| Direct Costs (DC) |  |  |  | 100000
| G&A on DC |  |  | 17.05% | 17050
| Sub-Total |  |  |  | 117050 | 0% | 17.05% |  | 17.05%
| FCR |  |  | 0% | 0
| Total |  |  |  | 117050
| Indirect |  |  |  | 17.05% | 0% | 17.05% | 0%
DTS (Central Shops/Plant Engineering)
| Direct Costs (DC) |  |  |  | 100000
| G&A on DC |  |  | 12.05% | 12050
| Sub-Total |  |  |  | 112050 | 0% | 12.05% |  | 12.05%
| FCR |  |  | 0% | 0
| Total |  |  |  | 112050
| Indirect |  |  |  | 12.05% | 0% | 12.05% | 0
MSTC (purchases)
| Direct Cost (DC) |  |  |  | 100000
| Material Handling (MH) |  |  | 6.5% | 6500
| G&A on DC |  |  | 17.35% | 17350
| G&A on MH |  |  | 17.35% | 1127.75
| Sub-Total |  |  |  | 124977.75 | 6.5% | 18.48% |  | 24.98%
| FCR |  |  | 0% | 0
| Total |  |  |  | 124977.75
| Indirect |  |  |  | 24.98% |  |  | 0%
Subcontracts (Purchases > 25K)
| Direct Cost (DC) |  |  |  | 100000
| Material Handling (MH) |  |  | 7% | 7000
| G&A on DC ("Traditional" only) |  |  | 5% | 5000
| G&A on MH |  |  | 17.05% | 1193.5
| Total |  |  |  | 113193.5 | 7% | 6.193% |  | 13.19%
| FCR |  |  | 0% | 0
113193.5
| Indirect |  |  |  | 13.19% | 7% | 6.193% | 0%
Subcontracts (Purchases > 600K) on the first $600k only
| Direct Cost (DC) |  |  |  | 600000
| Material Handling (MH) on DC-6.5% of $600K |  |  | FIXED | 39000
| G&A on DC-8% of $600K |  |  | FIXED | 48000
| G&A on MH |  |  | 17.05% | 6649.5
| Sub-Total |  |  |  | 693649.5
| FCR |  |  | 0% | 0
| Total |  |  |  | 693649.5
| Indirect (Only on first $600K, prior approval required) |  |  |  | 15.61%
Purchase Equipment (Turn-key Purchases > 25K Gen CAP/HEEP)
| Direct Cost (DC) |  |  |  | 100000
| Material Handling (MH) |  |  | 7% | 7000
| G&A on MH |  |  | 17.05% | 1193.5
| Sub-Total |  |  |  | 108193.5
| FCR |  |  | 0% | 0
| Total |  |  |  | 108193.5
| Indirect |  |  |  | 8.194%
Purchase Equipment (Turn-Key, Purchases > 600K) on first $600K only
| Direct Cost (DC) |  |  |  | 600000
| Material Handling 7% of $600K (MH) |  |  | FIXED | 42000
| G&A on MH |  |  | 17.05% | 7161
| Sub-Total |  |  |  | 649161
| FCR |  |  | 0% | 0
| Total |  |  |  | 649161
| Indirect (Only on first $600K, prior approval required) |  |  |  | 8.194%
| Labor Rates (direct, includes PAB and fringe) |  |  |  | With Indirects | With Indirects
|  | $/hr |  |  | $/hr | $/year (FTE) | 0.25 FTE
| techs | 52.25 | PER PRODUCTIVE HOUR |  | 72.8747 | 127895.1073 | 31973.7768
| engineers | 66.86 | PER PRODUCTIVE HOUR |  | 93.2517 | 163656.7823 | 40914.1956
| designers | 55.96 | PER PRODUCTIVE HOUR |  | 78.0492 | 136976.2718 | 34244.068
| physicist | 89.23 | PER PRODUCTIVE HOUR |  | 124.4519 | 218413.0225 | 54603.2556 | LE/LP | 191034.9024
| BNL Administrative* | 47.54 | PER PRODUCTIVE HOUR |  | 66.3055 | 116366.1895 | 29091.5474
| BNL Management* | 106.07 | PER PRODUCTIVE HOUR |  | 147.9391 | 259633.1872 | 64908.2968
* pp estimate
DISTRIBUTED TECHNICAL SERVICES (DTS):
| CENTRAL SHOPS | 92.83 | PER PRODUCTIVE HOUR |  | 104.016 | 182548.1063
| BLDG. TRADES | 78.35 | PER PRODUCTIVE HOUR |  | 87.7912 | 154073.5121
| CNST ENGR SERVICES | 94.65 |  |  | 106.0553 | 186127.0954
| DIRECT ASSIGNED | 64.07 | PER PRODUCTIVE HOUR |  | 71.7904 | 125992.2134
| GENERAL LABOR | 52.37 | PER PRODUCTIVE HOUR |  | 58.6806 | 102984.4267
| PRODUCTIVE HOURS FOR 1 FTE |  | 1755

## K0PI0 manpower - NSF
Personnel Costs assuming construction project indirect costs.
The base manpower estimate is comprised of the following: | [6 empty] | Direct |  | BNL indirects
[5 empty] | FTE | Base | w/Fringe & PAB | C-AD Org Burd | w/3% Safeguards | Subtotal | FCR | TOTAL
[7 empty] | 59.85% | 19.53% | 19.95% |  | 0%
Physicist |  |  |  |  | 1 | 93723.9429 | 156598.65 | 30578.7991 | 31235.5733 | 218413.0225 | 0 | 218413.0225
Engineering (mechanical, electrical) |  |  |  |  | 1 | 70227.3095 | 117339.3 | 22912.6808 | 23404.8014 | 163656.7823 | 0 | 163656.7823
Controls |  |  |  |  | 0.5 | 37151.3601 | 62074.35 | 12121.1714 | 12381.511 | 86577.0324 | 0 | 86577.0324
Instrumentation |  |  |  |  | 1 | 62554.4034 | 104519.025 | 20409.2837 | 20847.6361 | 145775.9448 | 0 | 145775.9448
Vacuum systems |  |  |  |  | 0.5 | 31277.2017 | 52259.5125 | 10204.6418 | 10423.818 | 72887.9724 | 0 | 72887.9724
Magnet systems |  |  |  |  | 1.5 | 93831.6052 | 156778.5375 | 30613.9255 | 31271.4541 | 218663.9172 | 0 | 218663.9172
Power supplies |  |  |  |  | 1.5 | 93831.6052 | 156778.5375 | 30613.9255 | 31271.4541 | 218663.9172 | 0 | 218663.9172
Utilities (power, water, AC) |  |  |  |  | 2 | 125108.8069 | 209038.05 | 40818.5674 | 41695.2722 | 291551.8895 | 0 | 291551.8895
Extraction systems |  |  |  |  | 1 | 74302.7202 | 124148.7 | 24242.3428 | 24763.022 | 173154.0649 | 0 | 173154.0649
ES&H, QA, Admin, training (org. burden) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shift operations |  |  |  |  | 2 | 126227.4441 | 210907.125 | 41183.539 | 42068.0827 | 294158.7468 | 0 | 294158.7468
|  |  | Subtotal |  | 12 | 808236.3991 | 1350441.7875 | 263698.8772 | 269362.6251 | 1883503.2898 | 0 | 1883503.2898
E926 manpower support
Physicist, engineering |  |  |  |  | 1 | 81975.6262 | 136968.975 | 26745.74 | 27320.1874 | 191034.9024 | 0 | 191034.9024
RF systems engineering, technicians |  |  |  |  | 1 | 62554.4034 | 104519.025 | 20409.2837 | 20847.6361 | 145775.9448 | 0 | 145775.9448
Technicians (instr., vacuum, magnet etc.) |  |  |  |  | 2 | 109762.9949 | 183397.5 | 35811.7731 | 36580.9415 | 255790.2146 | 0 | 255790.2146
|  |  | Subtotal |  | 4 | 254293.0245 | 424885.5 | 82966.7967 | 84748.765 | 592601.0617 | 0 | 592601.0617
|  |  | TOTAL |  | 16 | 1062529.4236 | 1775327.2875 | 346665.674 | 354111.39 | 2476104.3515 | 0 | 2476104.3515
Accel Oprs (15% shift differential only) - 1 week
PERSONNEL (all shift work)
3 MCR |  |  |  |  | 3 |  | 5054.616 | 987.0078 | 1008.2068 | 7049.8306 | 0 | 7049.8306
1 Scientific |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
1 SIEMENS |  |  |  |  | 1 |  | 1316.7 | 257.1102 | 262.6324 | 1836.4426 | 0 | 1836.4426
1 HP |  |  |  |  | 1 |  | 1316.7 | 257.1102 | 262.6324 | 1836.4426 | 0 | 1836.4426
Total | [6 empty] | 7688.016 | 1501.2281 | 1533.4716 | 10722.7158 | 0 | 10722.7158
Labor Rates (direct, includes PAB and fringe)
FY 05 | $/hr
techs | 52.25 | PER PRODUCTIVE HOUR
engineers | 66.86 | PER PRODUCTIVE HOUR
designers | 55.96 | PER PRODUCTIVE HOUR
physicist | 89.23 | PER PRODUCTIVE HOUR
PRODUCTIVE HOURS FOR 1 FTE |  |  |  | 1755

## K0PI0 alacart Operations
K0PI0 (E926) - DRAFT
DEDICATED tests - no HEP or RHIC base support (pre/post-ops not included)
One Week - beam to B-target for tests
In FY05 Dollars and reduced NSF indirects, FY2006 Power Costs (estimate for new NYPA Contract)
Cost for 1 week of operatons |  |  | Power Cost | Clock time in hours
9/21/04 - escalated 3%/year FY03-FY05 |  |  | 85 | 168
per MWhr
| Direct | Dept Charges | G&A
Accel Oprs |  |  |  | TOTAL
PERSONNEL (all shift work)
3 MCR | 38752.056 | 7567.0597 | 2986.9545 | 49306.0703
1 Scientific/Professional (1/2 time) | 6555.78 | 1280.138 | 505.3104 | 8341.2284 | 89.23 | SCIENTIFIC
1 SIEMENS | 10094.7 | 1971.1779 | 778.0854 | 12843.9634 | 66.86 | PROFESSIONAL
1 HP | 10094.7 | 1971.1779 | 778.0854 | 12843.9634 | 52.25 | TECHNICAL
DTS | 21430.18 | 0 | 2582.3367 | 24012.5167 | PRODUCTIVE HOURS FOR 1 FTE |  | 1755
MSTC | 54636.35 | 3551.3628 | 10095.5682 | 68283.2809
SPEC PROC | 19669.086 | 1376.836 | 1218.2048 | 22264.1269
ES&F
2 Shift Personnel (CAS watch) | 20189.4 | 3942.3559 | 1556.1708 | 25687.9267
2 Tech Support (75% time) | 15142.05 | 2956.7669 | 1167.1281 | 19265.945
2 Prof Support (20 hrs per week each) | 2674.4 | 522.2263 | 206.139 | 3402.7654
MSTC Experimental Area | 11882.08 | 772.3352 | 2195.541 | 14849.9562
LINAC
Tech Support (1/4 time) | 2523.675 | 492.7945 | 194.5214 | 3210.9908
DTS | 5092.32 | 0 | 613.6246 | 5705.9446
MSTC | 8699.38 | 565.4597 | 1607.4497 | 10872.2894
SPEC PROC | 41905.55 | 2933.3885 | 2595.4202 | 47434.3587
TOTAL COST | 269341.707 | 29903.0794 | 29080.5404 | 328325.3267
ELECTRICITY COSTS (Est. Only)
Based on 12 MW above 3 MW base X $85 Mwhr | 171360 | 0 | 0 | 171360
Sub-TOTAL WEEKLY OPERATING COSTS | 440701.707 | 29903.0794 | 29080.5404 | 499685.3267
TOTAL DIRECT COSTS |  |  |  | 470604.7864
| HOURLY RATE |  |  | 19608.5328
3 (8HR) SHIFTS
| Full Cost Recovery |  |  | 26471.5192
Rate
Full Cost Recovery Fee (0%) |  |  |  | 0
TOTAL WEEKLY OPERATING COSTS |  |  |  | 499685.3267
Cost for 1 shift of operation |  |  |  | 23794.5394

## MECO alacart Operations
MECO (E940) - DRAFT
DEDICATED tests - no HEP or RHIC base support (pre/post-ops not included)
One Week - beam to A-target for tests
In FY05 Dollars and reduced NSF indirects, FY2006 Power Costs (estimate for new NYPA Contract)
Cost for 1 week of operatons |  |  | Power Cost | Clock time in hours
9/21/04 - escalated 3%/year FY03-FY05 |  |  | 85 | 168
per MWhr
| Direct | Dept Charges | G&A
Accel Oprs |  |  |  | TOTAL
PERSONNEL (all shift work)
3 MCR | 38752.056 | 7567.0597 | 2986.9545 | 49306.0703
1 Scientific/Professional (1/2 time) | 6555.78 | 1280.138 | 505.3104 | 8341.2284 | 89.23 | SCIENTIFIC
1 SIEMENS | 10094.7 | 1971.1779 | 778.0854 | 12843.9634 | 66.86 | PROFESSIONAL
1 HP | 10094.7 | 1971.1779 | 778.0854 | 12843.9634 | 52.25 | TECHNICAL
DTS | 21430.18 | 0 | 2582.3367 | 24012.5167 | PRODUCTIVE HOURS FOR 1 FTE |  | 1755
MSTC | 54636.35 | 3551.3628 | 10095.5682 | 68283.2809
SPEC PROC | 19669.086 | 1376.836 | 1218.2048 | 22264.1269
ES&F
2 Shift Personnel (CAS watch) | 20189.4 | 3942.3559 | 1556.1708 | 25687.9267
2 Tech Support (separator 75% time) | 15142.05 | 2956.7669 | 1167.1281 | 19265.945
2 Prof Support (20 hrs per week each) | 2674.4 | 522.2263 | 206.139 | 3402.7654
MSTC Experimental Area | 23764.16 | 1544.6704 | 4391.0821 | 29699.9125
LINAC
Tech Support (1/4 time) | 2523.675 | 492.7945 | 194.5214 | 3210.9908
DTS | 5092.32 | 0 | 613.6246 | 5705.9446
MSTC | 8699.38 | 565.4597 | 1607.4497 | 10872.2894
SPEC PROC | 41905.55 | 2933.3885 | 2595.4202 | 47434.3587
TOTAL COST | 281223.787 | 30675.4146 | 31276.0814 | 343175.283
ELECTRICITY COSTS (Est. Only)
Based on 12 MW above 3 MW base X $85 Mwhr | 171360 | 0 | 0 | 171360
Sub-TOTAL WEEKLY OPERATING COSTS | 452583.787 | 30675.4146 | 31276.0814 | 514535.283
TOTAL DIRECT COSTS |  |  |  | 483259.2016
| HOURLY RATE |  |  | 20135.8001
3 (8HR) SHIFTS
| Full Cost Recovery |  |  | 27183.3301
Rate
Full Cost Recovery Fee (0%) |  |  |  | 0
TOTAL WEEKLY OPERATING COSTS |  |  |  | 514535.283
Cost for 1 shift of operation |  |  |  | 24501.6801

## K0PI0 D6 Operations Cost
K0PI0 (E926) - DRAFT
DEDICATED tests - no HEP or RHIC base support (pre/post-ops not included)
One Week - including tune-up - LOW INTENSITY to D6-line
In FY05 Dollars and reduced NSF indirects, FY2006 Power Costs (estimate for new NYPA Contract)
Cost for 1 week of operatons |  |  | Power Cost | Clock time in hours
9/21/04 - escalated 3%/year FY03-FY05 |  |  | 85 | 168
per MWhr
| Direct | Dept Charges | G&A
Accel Oprs |  |  |  | TOTAL
PERSONNEL (all shift work)
3 MCR | 38752.056 | 7567.0597 | 2986.9545 | 49306.0703
1 Scientific/Professional (1/2 time) | 6555.78 | 1280.138 | 505.3104 | 8341.2284 | 89.23 | SCIENTIFIC
1 SIEMENS | 10094.7 | 1971.1779 | 778.0854 | 12843.9634 | 66.86 | PROFESSIONAL
1 HP | 10094.7 | 1971.1779 | 778.0854 | 12843.9634 | 52.25 | TECHNICAL
DTS | 21430.18 | 0 | 2582.3367 | 24012.5167 | PRODUCTIVE HOURS FOR 1 FTE |  | 1755
MSTC | 54636.35 | 3551.3628 | 10095.5682 | 68283.2809
SPEC PROC | 19669.086 | 1376.836 | 1218.2048 | 22264.1269
ES&F
2 Shift Personnel (CAS watch) | 20189.4 | 3942.3559 | 1556.1708 | 25687.9267
2 Tech Support (separator and other, 75% time) | 15142.05 | 2956.7669 | 1167.1281 | 19265.945
2 Prof Support (20 hrs per week each) | 2674.4 | 522.2263 | 206.139 | 3402.7654
MSTC | 11882.08 | 772.3352 | 2195.541 | 14849.9562
MSTC (D6) | 11882.08 | 772.3352 | 2195.541 | 14849.9562
LINAC
Tech Support (1/4 time) | 2523.675 | 492.7945 | 194.5214 | 3210.9908
DTS | 5092.32 | 0 | 613.6246 | 5705.9446
MSTC | 8699.38 | 565.4597 | 1607.4497 | 10872.2894
SPEC PROC | 41905.55 | 2933.3885 | 2595.4202 | 47434.3587
TOTAL COST | 281223.787 | 30675.4146 | 31276.0814 | 343175.283
ELECTRICITY COSTS (Est. Only)
Based on 12 MW above 3 MW base X $85 Mwhr | 171360 | 0 | 0 | 171360
Sub-TOTAL WEEKLY OPERATING COSTS | 452583.787 | 30675.4146 | 31276.0814 | 514535.283
TOTAL DIRECT COSTS |  |  |  | 483259.2016
| HOURLY RATE |  |  | 20135.8001
3 (8HR) SHIFTS
| Full Cost Recovery |  |  | 27183.3301
Rate
Full Cost Recovery Fee (0%) |  |  |  | 0
TOTAL WEEKLY OPERATING COSTS |  |  |  | 514535.283
Cost for 1 shift of operation |  |  |  | 24501.6801

## MECO manpower - NSF
Personnel Costs assuming construction project indirect costs.
The base manpower estimate is comprised of the following: | [6 empty] | Direct |  | BNL indirects
[5 empty] | FTE | Base | w/Fringe & PAB | C-AD Org Burd | w/3% Safeguards | Subtotal | FCR | TOTAL
[7 empty] | 59.85% | 19.53% | 19.95% |  | 0%
Physicist |  |  |  |  | 1 | 93723.9429 | 156598.65 | 30578.7991 | 31235.5733 | 218413.0225 | 0 | 218413.0225
Engineering (mechanical, electrical) |  |  |  |  | 1 | 70227.3095 | 117339.3 | 22912.6808 | 23404.8014 | 163656.7823 | 0 | 163656.7823
Controls |  |  |  |  | 0.5 | 37151.3601 | 62074.35 | 12121.1714 | 12381.511 | 86577.0324 | 0 | 86577.0324
Instrumentation |  |  |  |  | 1 | 62554.4034 | 104519.025 | 20409.2837 | 20847.6361 | 145775.9448 | 0 | 145775.9448
Vacuum systems |  |  |  |  | 0.5 | 31277.2017 | 52259.5125 | 10204.6418 | 10423.818 | 72887.9724 | 0 | 72887.9724
Magnet systems |  |  |  |  | 1.5 | 93831.6052 | 156778.5375 | 30613.9255 | 31271.4541 | 218663.9172 | 0 | 218663.9172
Power supplies |  |  |  |  | 1.5 | 93831.6052 | 156778.5375 | 30613.9255 | 31271.4541 | 218663.9172 | 0 | 218663.9172
Utilities (power, water, AC) |  |  |  |  | 2 | 125108.8069 | 209038.05 | 40818.5674 | 41695.2722 | 291551.8895 | 0 | 291551.8895
Extraction systems |  |  |  |  | 1 | 74302.7202 | 124148.7 | 24242.3428 | 24763.022 | 173154.0649 | 0 | 173154.0649
ES&H, QA, Admin, training (org. burden) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shift operations |  |  |  |  | 2 | 126227.4441 | 210907.125 | 41183.539 | 42068.0827 | 294158.7468 | 0 | 294158.7468
|  |  | Subtotal |  | 12 | 808236.3991 | 1350441.7875 | 263698.8772 | 269362.6251 | 1883503.2898 | 0 | 1883503.2898
E940 manpower support
Physicist, engineering |  |  |  |  | 1 | 81975.6262 | 136968.975 | 26745.74 | 27320.1874 | 191034.9024 | 0 | 191034.9024
Cryo systems engineering, technicians |  |  |  |  | 3 | 187663.2103 | 313557.075 | 61227.8511 | 62542.9083 | 437327.8343 | 0 | 437327.8343
Technicians (instr., vacuum, magnet etc.) |  |  |  |  | 2 | 109762.9949 | 183397.5 | 35811.7731 | 36580.9415 | 255790.2146 | 0 | 255790.2146
|  |  | Subtotal |  | 6 | 379401.8314 | 633923.55 | 123785.3641 | 126444.0371 | 884152.9513 | 0 | 884152.9513
|  |  | TOTAL |  | 18 | 1187638.2305 | 1984365.3375 | 387484.2413 | 395806.6622 | 2767656.2411 | 0 | 2767656.2411
Accel Oprs (15% shift differential only) - 1 week
PERSONNEL (all shift work)
3 MCR |  |  |  |  | 3 |  | 5054.616 | 987.0078 | 1008.2068 | 7049.8306 | 0 | 7049.8306
1 Scientific |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
1 SIEMENS |  |  |  |  | 1 |  | 1316.7 | 257.1102 | 262.6324 | 1836.4426 | 0 | 1836.4426
1 HP |  |  |  |  | 1 |  | 1316.7 | 257.1102 | 262.6324 | 1836.4426 | 0 | 1836.4426
Total | [6 empty] | 7688.016 | 1501.2281 | 1533.4716 | 10722.7158 | 0 | 10722.7158
Labor Rates (direct, includes PAB and fringe)
FY 03 | $/hr
techs | 52.25 | PER PRODUCTIVE HOUR
engineers | 66.86 | PER PRODUCTIVE HOUR
designers | 55.96 | PER PRODUCTIVE HOUR
physicist | 89.23 | PER PRODUCTIVE HOUR
PRODUCTIVE HOURS FOR 1 FTE |  |  |  | 1755