## Cost and Labor Summary
last revision | 2004-11-02
RSVP AGS Infrastructure Labor FTE's # (without Contingency or beam development personnel)
|  | Management | Admin | Eng'r | Physicist | Design | Tech | C-AD Total | DTS | Shops
AGS/Booster |  |  |  | 11.7755 | 3.743 | 12.253 | 23.9111 | 51.6826 | 2.7789 | 6.1595
Switchyard |  |  |  | 2.3647 | 0.34758 | 0.87749 | 10.6906 | 14.2803 | 2.9835 | 1.2821
K0PI0 |  |  |  | 5.2376 | 3.4724 | 2.0125 | 11.0291 | 21.7516 | 5.5607 | 0.45869
MECO |  |  |  | 7.7379 | 4.9521 | 2.5544 | 14.6211 | 29.8655 | 8.4085 | 1.8593
AGS Project Office |  | 5.0006 | 1.2501 |  |  |  |  | 6.2507
Total |  | 5.0006 | 1.2501 | 27.1157 | 12.5151 | 17.6974 | 60.2519 | 123.8308 | 19.7316 | 9.7595
# does not include FTE's for beam development
RSVP AGS Infrastructure Cost Summary (fully burdened)
|  | Materials | C-AD Labor | DTS/Shops | Sub-Total | Contingency | Total
AGS/Booster |  | 9679154.5872 | 7557051.0354 | 1658187.16 | 18894392.7826 | 3693466.2314 | 22587859.014
Switchyard |  | 1564617.585 | 1970105.4599 | 647722.656 | 4182445.7009 | 823232.283 | 5005677.9839
K0PI0 |  | 4508503.6353 | 3335092.0061 | 823923.464 | 8667519.1053 | 2065291.9434 | 10732811.0487
MECO |  | 3583556.5137 | 4613818.2466 | 1477302.232 | 9674676.9924 | 2261959.1701 | 11936636.1625
AGS Project Office |  | 62692.75 | 1451541.7109 |  | 1514234.4609 | 302846.8922 | 1817081.3531
TOTAL |  | 19398525.0712 | 18927608.4589 | 4607135.512 | 42933269.0422 | 9146796.5201 | 52080065.5623
Beam Development* |  | 14305738.0003 | 12190675.0965 |  | 26496413.0968 | 5632907.7909 | 32129320.8877
RSVP AGS WBS Total |  | 33704263.0715 | 31118283.5554 | 4607135.512 | 69429682.139 | 14779704.311 | 84209386.45
* includes Personnel, M&S, DTS and Power Costs, assumes Jan 04 plan, FY06-FY10 running with RHIC
and 1 year contingency with 10 weeks running outside RHIC
What's Missing from this
1. RSVP Project Office
2. AGS/Booster Shield CAPS, several incomplete WBS items
3. AGS/Booster/Switchyard Collimators
4. MECO Magnet and Refrigerator Infrastructure Support, controls
5. MECO - experiment area (detectors, cosmic shield, target, counting house etc)
6. K0PI0 - experiment area, counting house, fast electronics, controls etc..
7. Beam Development costs (AGS running)
8. MECO DS cosmic and TS shield

## WBS 1.4.1 Booster-AGS
RSVP - Booster/AGS Modifications
| 10/15/04 - corrected tech weight factors for F5 and F10 Power Supplies (1-->2), 10/4 controls update |  |  |  |  | Labor Rates
[6 empty] | 67.15 | 89.65 | 56.25 | 52.5 | 83.25 | 99.4
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total | Direct Total | Direct Total
Number | Description | <$25000 | >$25000 | >$600000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | w/ Cont | w/ Cont | Comments
[23 empty] | (level 5) | (level 4)
1.4.1 | BOOSTER/AGS MODIFICATIONS |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.1.1 | Project Support |  |  |  | 0 | 1764 | 882 | 0 |  |  |  | 197523.9 | 197523.9 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 31603.824 | 229127.724 | 229127.724 | 229127.724 | 1.0 LE, .5 LP
1.4.1.1.1 | installation supervision |  |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 5% 0f Tech labor | AGS/Booster (Common) | Direct w/o Contingency | Contingency | Direct Total
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  |  |  | Safety | 3573250 | 14.53% | 4092302.5
1.4.1.2 | Booster |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 4439009.8235 |  | Mechanical modifications | 3042726.99 | 17.06%
1.4.1.2.1 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 884544.912 |  |  | Electrical modifications | 2807345.65
| Project Support |  |  |  | 0 | 70 | 0 | 104 | 340 | 0 | 0 | 28400.5 | 28400.5 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 4544.08 | 32944.58 |  |  | 10 % eng management, 20% technical management | Instrumentation | 877659
| Cable Repair/Replacement | 12000 | 0 |  | 12000 | 120 | 0 | 0 | 160 | 0 | 0 | 16458 | 28458 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 5122.44 | 33580.44 |  |  |  | RF System modifications | 629322
| Cable Trays | 1500 |  |  | 1500 | 80 | 0 | 0 | 80 | 0 | 0 | 9572 | 11072 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 1992.96 | 13064.96 |  |  |  | Controls | 224178.95
| Upgrade of PFN's | 119400 | 129500 |  | 248900 | 400 | 0 | 598 | 960 | 160 | 40 | 128193.5 | 377093.5 | 3 | 2 | 8 | 1 | 2 | 8 | 24% | 90502.44 | 467595.94 |  |  |  | Project Support | 197523.9
| Magnet Coils - Mechanical | 7680 | 204012 |  | 211692 | 328 | 0 | 80 | 1068 | 288 | 0 | 106571.2 | 318263.2 | 1 | 2 | 0 | 2 | 1 | 2 | 6% | 19095.792 | 337358.992
1.4.1.2.2 | Mechanical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 1543994.302 |  |  | Sub-Total | 11352006.49
| Project Support | 5000 |  |  | 5000 | 198 | 0 | 477 | 486 | 0 | 0 | 65641.95 | 70641.95 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 11302.712 | 81944.662 |  |  | 10 % eng management, 20% technical management
| Spare Booster F6 | 38991 | 0 |  | 38991 | 220 | 0 | 0 | 1268 | 376 | 1181 | 230036.4 | 269027.4 | 2 | 4 | 4 | 4 | 1 | 4 | 20% | 53805.48 | 322832.88 |  |  |  | AGS/Booster (Experiment Specific)
| Booster Injection | 54700 | 0 |  | 54700 | 645 | 108 | 1820 | 1536 | 248 | 1020 | 358042.95 | 412742.95 | 2 | 4 | 4 | 4 | 1 | 4 | 20% | 82548.59 | 495291.54 |  |  |  | MECO Specific | 936045.75
| Collimator, LTB | 85700 | 0 |  | 85700 | 1100 | 179 | 2824 | 2056 | 248 | 740 | 450904.35 | 536604.35 | 4 | 2 | 4 | 4 | 1 | 4 | 20% | 107320.87 | 643925.22 |  |  |  | K0PI0 Specific | 2908164.95
Collimators, Booster (?)
1.4.1.2.3 | RF System modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 766190.52
| Project Support |  |  |  | 0 | 80 | 0 | 0 | 400 |  |  | 26372 | 26372 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 4219.52 | 30591.52 |  |  | 10 % eng management, 20% technical management | Sub-Total | 3844210.7
| RF Feedback | 120000 | 240000 |  | 360000 | 1040 | 520 | 0 | 2080 | 160 | 40 | 242950 | 602950 | 2 | 2 | 8 | 1 | 2 | 8 | 22% | 132649 | 735599
1.4.1.2.4 | Instrumentation | [21 empty] | 497865.1975 |  |  | AGS/Booster TOTAL | 15196217.19
| Project Support | 0 | 0 | 0 | 0 | 120 | 120 | 183 | 440 | 0 | 0 | 52209.75 | 52209.75 | 1 | 2 | 8 | 1 | 1 | 4 | 15% | 7831.4625 | 60041.2125
| Loss Monitors | 51000 | 0 | 0 | 51000 | 200 | 0 | 359 | 800 | 0 | 0 | 75623.75 | 126623.75 | 6 | 2 | 8 | 4 | 2 | 8 | 36% | 45584.55 | 172208.3
| WCM Upgrade (D6) | 5000 | 0 | 0 | 5000 | 440 | 80 | 605 | 880 | 0 | 40 | 120925.25 | 125925.25 | 2 | 2 | 8 | 1 | 2 | 8 | 22% | 27703.555 | 153628.805
| Inflector protection (C3) | 5000 | 0 | 0 | 5000 | 40 | 0 | 88 | 160 | 0 | 0 | 16036 | 21036 | 4 | 2 | 8 | 4 | 2 | 8 | 32% | 6731.52 | 27767.52
| Cables | 10000 | 0 | 0 | 10000 | 160 | 0 | 0 | 320 | 0 | 0 | 27544 | 37544 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 6007.04 | 43551.04
| BTA | 13000 | 0 | 0 | 13000 | 40 | 0 | 68 | 320 | 0 | 0 | 23311 | 36311 | 2 | 2 | 4 | 1 | 2 | 2 | 12% | 4357.32 | 40668.32
1.4.1.2.5 | Controls | [21 empty] | 138014.892
| Project Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0
| Instrumentation Interfaces | 7500 | 38454 |  | 45954 | 96 | 0 | 0 | 114 | 0 |  | 12431.4 | 58385.4 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 12844.788 | 71230.188 |  |  | Scope defined by instrumentation needs (mainly obsolete Loss Mon system)
| Software & Database | 0 | 0 | 0 | 0 | 777 | [5 empty] | 52175.55 | 52175.55 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 14609.154 | 66784.704
1.4.1.2.6 | Safety | [21 empty] | 608400
| Project Support |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 10 % eng management, 20% technical management
| Shield Caps |  |  | 520000 | 520000 | [6 empty] | 0 | 520000 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 88400 | 608400
1.4.1.3 | AGS |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 8828154.7915
1.4.1.3.1 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 2371527.955
| Project Support |  |  |  | 0 | 60 | 0 | 72 | 560 | 0 | 0 | 37479 | 37479 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 5996.64 | 43475.64 |  |  | 10 % eng management, 20% technical management
| Cable Repair/Replacement | 0 | 120000 |  | 120000 | 60 | 0 | 72 | 320 | 0 | 0 | 24879 | 144879 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 26078.22 | 170957.22
| Cable Trays | 1500 |  |  | 1500 | 80 | 0 | 0 | 80 | 0 | 0 | 9572 | 11072 | 2 | 2 | 8 | 1 | 2 | 4 | 18% | 1992.96 | 13064.96
| Active Filter | 0 | 110000 |  | 110000 | 120 | 0 | 0 | 120 | 0 | 0 | 14358 | 124358 | 4 | 2 | 8 | 1 | 2 | 4 | 22% | 27358.76 | 151716.76
| F5 Power Supply | 5910 | 59100 |  | 65010 | 170 | 0 | 203 | 340 | 74 | 0 | 46844.75 | 111854.75 | 3 | 2 | 4 | 4 | 1 | 4 | 18% | 20133.855 | 131988.605
| F10 Power Supply | 22930 | 179300 |  | 202230 | 346 | 0 | 413 | 692 | 150 | 0 | 95282.65 | 297512.65 | 3 | 2 | 4 | 4 | 1 | 4 | 18% | 53552.277 | 351064.927
| Upgrade of PFN's | 143500 | 180000 |  | 323500 | 320 | 0 | 502 | 1600 | 160 | 80 | 154997.5 | 478497.5 | 3 | 2 | 8 | 1 | 2 | 8 | 24% | 114839.4 | 593336.9
| Magnet Coils - Mechanical | 8960 | 390992 |  | 399952 | 116 | 0 | 219 | 2828 | 840 | 56 | 244074.55 | 644026.55 | 1 | 2 | 0 | 2 | 1 | 2 | 6% | 38641.593 | 682668.143
| J10 Bump; Low ripple P.S. | 0 | 180000 |  | 180000 | 60 | 0 | 72 | 120 | 0 | 0 | 14379 | 194379 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 38875.8 | 233254.8 |  |  | reduced from 225K to 180 K 10/28/04 (JS Email)
1.4.1.3.2 | Mechanical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 2174995.518
| Project Support | 5000 |  |  | 5000 | 105 | 0 | 125 | 0 | 0 | 0 | 14082 | 19082 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3053.12 | 22135.12 |  |  | 10 % eng management, 20% technical management
| AGS RC Networks | 16000 | 0 |  | 16000 | 55 | 0 | 55 | 220 | 0 | 0 | 18337 | 34337 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 6867.4 | 41204.4
| New F5 (2) | 206000 | 0 |  | 206000 | 348 | 164 | 1006 | 2178 | 352 | 2480 | 484819.3 | 690819.3 | 4 | 2 | 4 | 4 | 1 | 4 | 20% | 138163.86 | 828983.16
| New F10 (1) | 21958 | 0 |  | 21958 | 220 | 0 | 0 | 1268 | 376 | 849 | 197035.6 | 218993.6 | 4 | 4 | 4 | 4 | 1 | 4 | 28% | 61318.208 | 280311.808
| New H20 (2) | 90560 | 0 |  | 90560 | 275 | 110 | 968 | 1470 | 216 | 3220 | 498002.75 | 588562.75 | 6 | 4 | 4 | 4 | 1 | 4 | 36% | 211882.59 | 800445.34
Collimators, AGS (?)
| Sextupole Coils** | 0 | 160000 |  | 160000 | 110 | 0 | 0 | 440 | 0 | 0 | 30486.5 | 190486.5 | 1 | 2 | 0 | 2 | 1 | 2 | 6% | 11429.19 | 201915.69
1.4.1.3.3 | Instrumentation | [21 empty] | 571041.3975
| Project Support | 0 | 0 | 0 | 0 | 120 | 120 | 223 | 440 | 0 | 0 | 54459.75 | 54459.75 | 1 | 2 | 8 | 1 | 1 | 4 | 15% | 8168.9625 | 62628.7125
| Loss Monitors | 20000 | 0 | 0 | 20000 | 90 | 0 | 127 | 640 | 0 | 0 | 46787.25 | 66787.25 | 3 | 4 | 8 | 3 | 2 | 8 | 34% | 22707.665 | 89494.915
| Wall Current Monitor | 10000 | 0 | 0 | 10000 | 440 | 20 | 545 | 880 | 0 | 0 | 108195.25 | 118195.25 | 2 | 4 | 8 | 2 | 2 | 8 | 28% | 33094.67 | 151289.92
| IPM Servo | 2000 | 0 | 0 | 2000 | 40 | 0 | 0 | 80 | 0 | 0 | 6886 | 8886 | 1 | 2 | 0 | 1 | 1 | 2 | 5% | 444.3 | 9330.3
| Motion Systems | 40000 | 0 | 0 | 40000 | 40 | 0 | 68 | 160 | 0 | 0 | 14911 | 54911 | 2 | 2 | 4 | 1 | 1 | 4 | 13% | 7138.43 | 62049.43
| Video | 37000 | 0 | 0 | 37000 | 40 | 0 | 68 | 160 | 840 | 0 | 84841 | 121841 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 14620.92 | 136461.92
| Ring Grounds | 25000 | 0 | 0 | 25000 | 40 | 0 | 0 | 240 | 0 | 0 | 15286 | 40286 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 4834.32 | 45120.32
| Cables | 5000 | 0 | 0 | 5000 | 20 | 0 | 0 | 120 | 0 | 0 | 7643 | 12643 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2022.88 | 14665.88
1.4.1.3.4 | Controls | [21 empty] | 138287.421
| Project Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | Scope defined by instrumentation needs
| Instrumentation Interfaces | 21350 | 36124 | 0 | 57474 | 68 | 0 | 0 | 180 | 0 | 0 | 14016.2 | 71490.2 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 15727.844 | 87218.044 |  |  | Scope defined by instrumentation needs
| Software & Database | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 10206.8 | 10206.8 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 2857.904 | 13064.704
| Ring Ground Interface | 8100 | 0 | 0 | 8100 | 15 | 0 | 0 | 60 | 0 | 0 | 4157.25 | 12257.25 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 1716.015 | 13973.265 |  |  | Needed to help detect shorts caused by hign intensity rf effects
| Software & DB | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 3357.5 | 3357.5 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 570.775 | 3928.275
| Power Supply Interfaces | 4750 | 4000 |  | 8750 | 23 |  |  | 48 | 0 |  | 4064.45 | 12814.45 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 2819.179 | 15633.629 |  |  | Need to replace obsolete extraction element controls
| Software & Database |  |  |  | 0 | 52 | [5 empty] | 3491.8 | 3491.8 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 977.704 | 4469.504
1.4.1.3.5 | Safety |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 3572302.5
| Project Support |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 10 % eng management, 20% technical management
| Shield Caps (PE Subcontract) |  |  | 3053250 | 3053250 | [6 empty] | 0 | 3053250 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 519052.5 | 3572302.5
1.4.1.4 | MECO AGS Modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 1143417.29
1.4.1.4.1 | AC-Dipole | [21 empty] | 320102.73
| Project Support | 0 | 0 | 0 | 0 | 40 | 0 | 48 | 200 | 0 | 0 | 15886 | 15886 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2541.76 | 18427.76
| Magnet Design, Fabracation, Installation | 0 | 45000 | 0 | 45000 | 200 | 80 | 440 | 600 | 0 | 0 | 76852 | 121852 | 4 | 2 | 8 | 2 | 2 | 4 | 24% | 29244.48 | 151096.48
| Magnet Water Cooling | 5000 | 0 | 0 | 5000 | 40 | 0 | 48 | 200 | 0 | 0 | 15886 | 20886 | 2 | 2 | 4 | 2 | 2 | 4 | 16% | 3341.76 | 24227.76
| Power Supply | 0 | 50000 | 0 | 50000 | 200 | 80 | 239 | 340 | 0 | 0 | 51895.75 | 101895.75 | 4 | 2 | 8 | 2 | 2 | 4 | 24% | 24454.98 | 126350.73
1.4.1.4.2 | Strip-line Kickers | [21 empty] | 630818.08
| Project Support | 0 | 0 | 0 | 0 | 40 | 0 | 48 | 160 | 0 | 0 | 13786 | 13786 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2205.76 | 15991.76
| Strip-lines | 0 | 200000 | 0 | 200000 | 80 | 80 | 96 | 240 | 0 | 0 | 30544 | 230544 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 50719.68 | 281263.68
| Power Supply/Pulsers | 0 | 125000 | 0 | 125000 | 120 | 80 | 0 | 120 | 0 | 0 | 21530 | 146530 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 32236.6 | 178766.6
| Low Level Controls | 0 | 75000 | 0 | 75000 | 400 | 80 | 0 | 340 | 0 | 0 | 51882 | 126882 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 27914.04 | 154796.04
1.4.1.4.3 | Simulations | [21 empty] | 192496.48
| Mini-bunched extraction | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 157784 | 157784 | 1 | 2 | 8 | 2 | 2 | 8 | 22% | 34712.48 | 192496.48
1.4.1.5 | KOPIO AGS Modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | 3513392.958
1.4.1.5.1 | Booster To AGS Kickers | [21 empty] | 837380.165
| Project Support |  |  |  | 0 | 240 | 346 | 90 | 300 |  |  | 67947.4 | 67947.4 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 10871.584 | 78818.984 |  |  | 10 % eng management, 20% technical management
| Interface/Installation | 0 | 61600 | 0 | 61600 | 693 | 0 | 1347 | 1213 | 216 | 0 | 203968.2 | 265568.2 | 2 | 2 | 4 | 2 | 2 | 4 | 16% | 42490.912 | 308059.112
| Controls | 28600 | 0 | 0 | 28600 | 433 | 0 | 173 | 346 | 173 | 0 | 71374.45 | 99974.45 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 21994.379 | 121968.829
| Conventional | 0 | 192500 | 0 | 192500 | 303 | 0 | 477 | 0 | 0 | 0 | 47177.7 | 239677.7 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 47935.54 | 287613.24
| Tunnel Penetration | 0 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 2 | 2 | 8 | 2 | 2 | 8 | 24% | 7920 | 40920
1.4.1.5.2 | 25 MHz RF cavity (C-AD Part) | [21 empty] | 331416.585
| Project Support |  |  |  | 0 | 70 | 0 | 86 | 625 |  |  | 42350.5 | 42350.5 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 6776.08 | 49126.58 |  |  | 10 % eng management, 20% technical management
| Cavity * |  | 832000 |  |  | 1010 |  |  | 670
| Tuner * | 15625 |  |  |  | 675 |  |  | 335 |  | 768
| Vacuum * | 21250 | [6 empty] | 96
| Power Amplifier * |  | 26250 |  |  | 1010 |  |  | 2356
| Damper * | 21250 |  |  |  | 3040 |  |  | 2022 |  | 768
| Driver | 21250 | 0 | 0 | 21250 | 0 | 0 | 0 | 325 | 0 | 0 | 17062.5 | 38312.5 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 8428.75 | 46741.25
| Low Level Control | 21250 | 0 | 0 | 21250 | 340 | 0 | 406 | 325 | 0 | 0 | 62731 | 83981 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 18475.82 | 102456.82
| Controls | 0 | 31250 | 0 | 31250 | 345 | 0 | 412 | 600 | 0 | 0 | 77841.75 | 109091.75 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 24000.185 | 133091.935
| Access Controls | 20000
| Shipping * | 25000
1.4.1.5.3 | 100 MHz RF Cavity | [21 empty] | 2152099.728
| Project Support |  |  |  | 0 | 509 | 0 | 608 | 1200 |  |  | 131379.35 | 131379.35 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 21020.696 | 152400.046 |  |  | 10 % eng management, 20% technical management
| Cavity | 0 | 416250 | 0 | 416250 | 1519 | 0 | 814 | 1687 | 0 | 0 | 236355.85 | 652605.85 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 143573.287 | 796179.137
| Tuner | 21250 | 0 | 0 | 21250 | 341 | 0 | 407 | 325 | 0 | 532 | 115735.2 | 136985.2 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 30136.744 | 167121.944
| Vacuum | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 96 | 0 | 0 | 5040 | 20040 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 4408.8 | 24448.8
| Power Amplifier | 0 | 41250 | 0 | 41250 | 850 | 0 | 1015 | 2020 | 0 | 0 | 220221.25 | 261471.25 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 57523.675 | 318994.925
| Damper | 21250 | 0 | 0 | 21250 | 1524 | 0 | 1820 | 1018 | 0 | 532 | 311037.4 | 332287.4 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 73103.228 | 405390.628
| Driver | 21250 | 0 | 0 | 21250 | 0 | 0 | 0 | 324 | 0 | 0 | 17010 | 38260 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 8417.2 | 46677.2
| Low Level Control | 21250 | 0 | 0 | 21250 | 510 | 0 | 609 | 324 | 0 | 0 | 85512.75 | 106762.75 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 23487.805 | 130250.555
| Controls | 31250 | 0 | 0 | 31250 | 316 | 0 | 377 | 324 | 0 | 0 | 59435.65 | 90685.65 | 4 | 2 | 6 | 2 | 2 | 4 | 22% | 19950.843 | 110636.493
| Access Controls | 20000
1.4.1.5.4 | Simulations | [21 empty] | 192496.48
| Micro-bunched extraction | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 157784 | 157784 | 1 | 2 | 8 | 2 | 2 | 8 | 22% | 34712.48 | 192496.48
1.4.1.6 | Beam Development |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Project Support |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 0 | 0 |  |  | 10 % eng management, 20% technical management
| Labor Hours |  |  |  |  | 20666 | 6569 | 21504 | 41964 | 4877 | 10810 | [8 empty] | 0%
| FTE |  |  |  |  | 11.7755 | 3.743 | 12.253 | 23.9111 | 2.7789 | 6.1595
| TOTALS - DIRECT | 1479339 | 3302332 | 3573250 | 8314921 | 1387721.9 | 588910.85 | 1209600 | 2203110 | 406010.25 | 1074514 | 6869867 | 15184788 | [6 empty] | 19.55% | 2968314.587 | 18153102.587 | 18153102.587 | 18153102.587
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 25.72% | 13.73% | 13.73% |  | 40.22% | 40.22% | 40.22% | 40.22% | 12% | 12% | [7 empty] | 19.63% | 24.43% | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 3551094.5744 | 22445487.357
| TOTAL | 1859898.9578 | 3755577.067 | 4063678.5625 | 9679154.5872 | 1945893.165 | 825783.32 | 1696126.8482 | 3089247.7021 | 454731.48 | 1203455.68 | 9215238.1954 | 18894392.7826 | [6 empty] | 19.55% | 3693466.2314 | 22587859.014
| * Off Project - CFI TRIUMF Work, | [23 empty] | 15184788
not included in totals
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## WBS 1.4.1 Dictionary
RSVP - Booster/AGS Modifications
9/2/04 (K. Brown v2.2 with CAPs added 9/16/04)
WBS | WBS
Number | Description | WBS Dictionary Entry
1.4.1 | BOOSTER/AGS MODIFICATIONS | Booster and AGS modifications section to the AGS RSVP Project
1.4.1.1 | Project Support
1.4.1.1.1 | installation supervision
1.4.1.2 | Booster | Booster Modifications
1.4.1.2.1 | Electrical modifications | Booster Electrical Systems Modifications, include cable repairs, upgrade of extraction kicker capicitor banks, and main magnet coil replacments.
Project Support
| Cable Repair/Replacement | Radiation or other environmentally damaged cables to be replaced or repaired
| Cable Trays | Old and damaged cable trays to be repaired or replaced.
| Upgrade of PFN's | Pulse forming network capacitor banks for the extraction kicker to be modified to reducing radiation damage during RSVP operations
| Magnet Coils - Mechanical | Costs for replacement of 6 Booster dipole coils. Replace 1 per year during RSVP operations.
1.4.1.2.2 | Mechanical modifications | Mechanical modifications of the Booster, include two spare extraction septa, projection C5 and C7 main magnet coils during H- injection, and collimators to allow higher throughput.
Project Support
| Spare Booster F6 | Currently no Spare extraction septum for Booster. This includes costs for having two spare septum magnets.
| Booster Injection | Booster C5 (location of H- injection point) and C7 (just after H- stripping foil) magnet coils have failed once each. This covers protection of these magnets during H- injection.
| Collimators | Beam loss limits currently keep the intensity in the Booster to < 30 TP/sec. Cost of multistage collimation to allow higher beam throughput.
1.4.1.2.3 | RF System modifications | Bosoter RF System modifications for RSVP, include RF feedback to gain stability for high intensity acceleration.
Project Support
| RF Feedback | Cost of adding RF feedback for high intensity operation to Band II and Band III rf sytems.
1.4.1.2.4 | Instrumentation | Instrumentation modifications for RSVP, includes upgrade to loss monitor system, new wall current monitor, heavy ion inflector protection,
Project Support
| Loss Monitors | Booster Loss monitor system upgrade. Critical for monitoring beam losses and keeping within preset limits.
| WCM Upgrade (D6) | A new wall current monitor for high beam currents
| Inflector protection (C3) | Protection of Heavy ion injection inflector from high intensity protons.
| Cables | Radiation or other environmentally damaged cables to be replaced or repaired
| BTA | Remote gain control for BTA instrumentation.
1.4.1.2.5 | Controls | Hardware and software controls support for Booster Modifciations.
Project Support
| Instrumentation Interfaces | Hardware Controls interface support for instrumention
| Software & Database | Software and database support for instrumentation.
1.4.1.2.6 | Safety | Safety system considerations, includes shield cap for the Booster
Project Support
| Shield Caps | Cost of capping the Booster to prevent ground-water contamination.
1.4.1.3 | AGS
1.4.1.3.1 | Electrical modifications | Electrical systems modifications for the AGS, includes ripple improvement for slow extraction, new extraction devices power supplies, main magnet coil replacements, and modifications to injection kicker capicitor bank to reduce radiation damage.
Project Support
| Cable Repair/Replacement | Radiation or other environmentally damaged cables to be replaced or repaired
| Cable Trays | Old and damaged cable trays to be repaired or replaced.
| Active Filter | New active filter for improved (reduced) main magnet power supply ripple during extraction
| F5 Power Supply | new thin septum power supply for new thin septum magnet
| F10 Power Supply | new thick septum power supply for new thick septum magnet
| H20 Power Supply | new electrostatic septum power supply for new electrostatic septum
| Upgrade of PFN's | Pulse forming network capacitor banks for the injection kicker to be modified to reducing radiation damage during RSVP operations
| Magnet Coils - Mechanical | Pre-emptive replacement of magnet coils in slow extraction region.
| J10 Bump; Low ripple P.S. | New J10 bump power supply with low ripple, to improve slow extracted beam spill structure.
1.4.1.3.2 | Mechanical modifications | Mechanical modifications to AGS equipment, includes upgrade to Vacuum chamber impedence, new extraction magnets, new sextupole coils, and collimators.
Project Support
| AGS RC Networks | Reduce overall AGS impedence (avoid high intensity instabilities) and RC networks that can take the higher power image currents from high intensity beams
| New F5 (2) | new thin magnet septum and spare for slow extraction
| New F10 (2) | new thick magnetic septum and spare for slow extraction
| New H20 (2) | new electrostatic septum and spare for slow extraction
| Collimators | Beam loss limits currently limit the intensity. Cost of multistage collimation to allow higher beam throughput.
| Sextupole Coils** | replace 16 AGS sextupole coils with new coils (current coils are very old and damaged is evident)
1.4.1.3.3 | Instrumentation | Instrumentation modifications in the AGS for RSVP, includes beam loss monitoring, new device positioning interfaces, ring grounds monitoring, and beam instabilities monitoring.
Project Support
| Loss Monitors | Upgrade AGS long loss montitor system used to monitor beam efficiencies.
| Wall Current Monitor | Segmented wall current monitor for monitoring beam instabilites
| IPM Servo | move controled leak hardware to low radiation area
| Motion Systems | upgrade position controls for septa and AGS instrumentation to new controls and motors
| Video | radiation hardened cameras for instrumentation in extraction systems
| Ring Grounds | upgrade ring grounds monitoring system
| Cables | Radiation or other environmentally damaged cables to be replaced or repaired
1.4.1.3.4 | Controls | Hardware and software support for AGS Modifications
Project Support
| Instrumentation Interfaces | hardware controls interfaces for instrumentation
| Software & Database | software and database support for instrumentation
| Ring Ground Interface | hardware controls support for ring grounds monitoring system
| Software & DB | software and database support for ring grounds system
| Power Supply Interfaces | hardware controls interfaces for new power supplies
| Software & Database | hardware and software support for new power supplies
1.4.1.3.5 | Safety | Safety system considerations, includes capping the AGS ring shielding.
Project Support
| Shield Caps (PE Subcontract) | Cost of capping the AGS to prevent ground-water contamination.
1.4.1.4 | MECO AGS Modifications
1.4.1.4.1 | AC-Dipole | Dipole magnet in which the field oscillates at the vertical betatron resonance frequency, rapidly pushing protons outside the RF buckets of interest out of the aperture of the machine.
Project Support
Magnet
Power Supply
Installation
1.4.1.4.2 | Strip-line Kickers | These cancel the sinusoidal activation of the AC dipole magnet for protons within the nominal beam buckets
Project Support
Strip-lines
Power Supply/Pulsers
Low Level Controls
Installation
1.4.1.4.3 | Simulations | Tracking simulations of mini-bunched slow extraction.
Mini-bunched extraction
1.4.1.5 | KOPIO AGS Modifications
1.4.1.5.1 | Booster To AGS Kickers | CFI project to upgrade the injection kickers to stabilized proton injection
Project Support
1.4.1.5.2 | 25 MHz RF cavity | CFI project to build the 25 MHz RF cavity which will microbunch the slow extracted beam into <300 psec bunches.
Project Support
1.4.1.5.3 | 100 MHz RF Cavity | Additional RF cavity to get even shorter bunches (<250 psec).
Project Support
1.4.1.5.4 | Simulations | Microbunching tracking simulations of slow extraction.
1.4.1.6 | Beam Development | AGS studies required to achieve the beam characteristics needed for MECO
Project Support
Labor Hours
FTE
TOTALS - DIRECT
indirect %
TOTAL
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
|  |  | 0 | 0 | 0% | 0 | 0
0%

## WBS 1.4.2 Switchyard
RSVP - Switchyard Modifications with instrumentation and security included 8/5/04
6/29/04 - AP with security and instrumentation, wbs dictionary (partial) 9/29/04 | [5 empty] | Labor Rates
10/4 controls update | [5 empty] | 67.15 | 89.65 | 56.25 | 52.5 | 67.05 | 101
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total | WBS Level 4
Number | Description | <$25,000 | >$25,000 | >$600,000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | Total (Direct w/cont') | Comments/WBS Dictionary
1.4.2 | Switchyard modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.1 | project support and integration |  |  |  | 0 | 900 | 450 | 450 |  |  |  | 126090 | 126090 | 3 | 2 | 8 | 1 | 1 | 2 | 17% | 21435.3 | 147525.3 | 208950.3 | .5 LE, .25 LP
1.4.2.1.1 | installation supervision |  |  |  | 0 |  |  |  | 1000 |  |  | 52500 | 52500 | 3 | 2 | 8 | 1 | 1 | 2 | 17% | 8925 | 61425 |  | Provides for Design, Trades & Technician labor supervision @ 5%
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.2 | shielding modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 53451.6
1.4.2.2.1 | modify shielding at AD2 | 2000 |  |  | 2000 |  |  | 10 | 40 | 200 | 40 | 20112.5 | 22112.5 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 4422.5 | 26535 |  | Provides a 10' long radiation shield between the AGS ring and the SEB
1.4.2.2.2 | rebuild d/s labyrinth | 5000 |  |  | 5000 |  |  | 10 | 40 | 160 | 40 | 17430.5 | 22430.5 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 4486.1 | 26916.6 |  | Adds an extra turn on the existing labyrinth to decrease radiation leakage
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.3 | Electrical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 628160.51
1.4.2.3.1 | modify Royals (9) |  | 135000 |  | 135000 | 10 |  |  | 40 | 160 |  | 13499.5 | 148499.5 | 3 | 2 | 8 | 2 | 2 | 4 | 22% | 32669.89 | 181169.39 |  | Provides electrical breakers for AC power to power supplies
1.4.2.3.2 | remove power | [8 empty] | 80 |  | 5364 | 5364 | 1 | 2 | 8 | 1 | 1 | 4 | 15% |  |  |  | Removes the existing power distribution in the SYG cave
1.4.2.3.3 | provide power in cave | 5000 |  |  | 5000 |  |  | 4 |  | 160 |  | 10953 | 15953 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 2712.01 | 18665.01 |  | Provides new power distribution in the SYG cave
1.4.2.3.4 | provide power @VME stations | 5000 |  |  | 5000 |  |  | 4 |  | 160 |  | 10953 | 15953 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 2712.01 | 18665.01 |  | Provides power & distribution in the VME controls enclosures
1.4.2.3.5 | modify PS's for new controls (20) | 34500 | 43400 |  | 77900 | 200 |  | 160 | 4160 | 60 | 100 | 254953 | 332853 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 66570.6 | 399423.6 |  | PSI type controls with SLC's, includes testing but no contactors or tap switches
1.4.2.3.6 | power supply maintenance |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | no cost if we do controls mods
1.4.2.3.7 | reconfigure interlock racks | 2000 |  |  | 2000 |  |  | 8 | 120 |  |  | 6750 | 8750 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 1487.5 | 10237.5 |  | This reconfigures the existing PLC rack for the new magnet interlock layout
1.4.2.4 | Mechanical modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 275688.86
1.4.2.4.1 | fabricate beam plugs (3) | 48500 |  |  | 48500 | 40 |  |  | 300 |  | 900 | 109336 | 157836 | 2 | 2 | 8 | 2 | 2 | 4 | 20% | 31567.2 | 189403.2 |  | Provides a remote beam plug capable of intercepting ~1% of beam,copy of NSRL stop
1.4.2.4.2 | modify PS water cooling | 5000 |  |  | 5000 | 16 |  | 16 | 160 |  |  | 10374.4 | 15374.4 | 2 | 2 | 8 | 1 | 1 | 4 | 17% | 2613.648 | 17988.048 |  | Removes rad water cooling & provides open tower cooling water for PS's
1.4.2.4.3 | prepare magnets (4) | 4000 |  |  | 4000 | 16 |  |  | 320 |  | 10 | 18884.4 | 22884.4 | 2 | 2 | 8 | 1 | 1 | 8 | 21% | 4805.724 | 27690.124 |  | Provides for refurbishing of 4 existing magnets, including bus, interlocks and stands
1.4.2.4.4 | replace CT1 piping |  | 30000 |  | 30000 | 16 |  | 16 |  |  |  | 1974.4 | 31974.4 | 2 | 2 | 15 | 2 | 2 | 4 | 27% | 8633.088 | 40607.488 |  | Replaces CT1 piping that is or was leaking with S/S pipe (for PS cooling)
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.5 | Installation | [21 empty] | 715445.484
1.4.2.5.1 | remove equipment in ring |  |  |  | 0 |  |  |  | 460 | 256 |  | 41314.8 | 41314.8 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 7436.664 | 48751.464 |  | Removes 8 of the 14 elements in the AGS ring | Switchyard modifications | Direct w/o Contingency
1.4.2.5.2 | remove equipment in "A" |  |  |  | 0 |  |  |  | 1200 | 840 |  | 119322 | 119322 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 21477.96 | 140799.96 |  | Removes all 15 existing elements in the A transport section of the SYG
1.4.2.5.3 | remove equipment in "B" |  |  |  | 0 |  |  |  | 720 | 620 |  | 79371 | 79371 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 14286.78 | 93657.78 |  | Removes 6 of the 12 transport elements in the C & B lines of the SYG | Electrical modifications | 522008.5
1.4.2.5.4 | rad waste removal (100cu ft) |  | 40000 |  | 40000 |  |  |  | 200 | 60 |  | 14523 | 54523 | 1 | 2 | 8 | 4 | 2 | 2 | 20% | 10904.6 | 65427.6 |  | Provides for sorting, packing, shipping and burial of rad waste | Switchyard Instrumentation | 799173
1.4.2.5.5 | install magnets in ring (2) | 4000 |  |  | 4000 |  |  |  | 400 | 112 |  | 28509.6 | 32509.6 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 6501.92 | 39011.52 |  | Provides for installation labor, materials, & testing for 2 new magnets in the AGS | Installation | 604028.2
1.4.2.5.6 | install magnets in "A" line (5) | 20000 |  |  | 20000 |  |  |  | 1360 | 560 |  | 108948 | 128948 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 25789.6 | 154737.6 |  | Provides for installation labor, materials, & testing for 5 new magnets in the A line | Vacuum | 352072
1.4.2.5.7 | install magnets in "B" line (3) | 12000 |  |  | 12000 |  |  |  | 816 | 336 |  | 65368.8 | 77368.8 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 15473.76 | 92842.56 |  | Provides for installation labor, materials, & testing for 3 new magnets in the B line | Mechanical modifications | 228069.2
1.4.2.5.8 | install beam plugs (3) | 5000 |  |  | 5000 |  |  |  | 340 | 40 |  | 20532 | 25532 | 2 | 2 | 8 | 4 | 1 | 4 | 20% |  | 25532 |  | Provides for installation labor, materials & testing of the beam plugs | Switchyard Security modifications | 210729.6
1.4.2.5.9 | clear cave & paint | 1000 |  |  | 1000 |  |  |  | 100 | 100 |  | 11955 | 12955 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 3109.2 | 16064.2 |  | Provides for preparation & painting of the SYG floor | Computer Controls | 190335.3
1.4.2.5.10 | install roof |  |  |  | 0 |  |  |  |  | 480 |  | 32184 | 32184 | 2 | 2 | 8 | 4 | 1 | 4 | 20% | 6436.8 | 38620.8 |  | Re-installs the existing SYG roof taken off for beam line modifications | project support and integration | 178590
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  |  | Conventional | 76450.5
1.4.2.6 | Vacuum |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 436569.28 |  | shielding modifications | 44543
1.4.2.6.1 | install vacuum in ring (100') | 8500 | 25000 |  | 33500 | 40 |  | 40 | 100 |  | 140 | 24326 | 57826 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 13878.24 | 71704.24 |  | Provides for a new welded vacuum d/s of CQ4. assumes rough vacuum | NASA relocation | 38073.5
1.4.2.6.2 | install vacuum in "A" line (100') | 14000 | 50000 |  | 64000 | 80 |  | 120 | 160 |  | 440 | 64962 | 128962 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 30950.88 | 159912.88 |  | Provides for a new "A" line vacuum system in the SYG.assumes rough vacuum
1.4.2.6.3 | install vacuum in "B" line (120') | 20000 | 50000 |  | 70000 | 80 |  | 120 | 240 |  | 540 | 79262 | 149262 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 35822.88 | 185084.88 |  | Provides for labor, materials for vacuum in C&B lines.assumes rough vacuum | TOTAL | 3244072.8
1.4.2.6.4 | plc modifications |  |  |  | 0 | 80 |  | 40 | 160 |  |  | 16022 | 16022 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 3845.28 | 19867.28 |  | This re-configures the existing vacuum PLC rack for the new vacuum system
[12 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.7 | Conventional |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 93090.03
1.4.2.7.1 | cable fire protection | 5000 |  |  | 5000 |  |  |  | 80 |  |  | 4200 | 9200 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 2208 | 11408 |  | Provides for labor & materials for tray cable fire protection
1.4.2.7.2 | controls enclosure | 20000 |  |  | 20000 |  |  |  |  | 280 |  | 18774 | 38774 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 9305.76 | 48079.76 |  | Provides for a air conditioned enclosure for controls and instrumentation
1.4.2.7.3 | cave dehumidification | 18000 |  |  | 18000 | 20 |  | 10 | 10 | 120 |  | 10476.5 | 28476.5 | 2 | 2 | 8 | 2 | 2 | 2 | 18% | 5125.77 | 33602.27 |  | Keeps the SYG cave below 85% RH
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8 | Switchyard Instrumentation |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 951145.8
1.4.2.8.1 | project support |  |  |  | 0 | 220 |  | 120 |  |  |  | 21523 | 21523 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 4304.6 | 25827.6
1.4.2.8.1.1 | installation supervision |  |  |  | 0 |  |  |  | 440 |  |  | 23100 | 23100 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 4620 | 27720
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.2 | Loss Monitor System |  |  |  | 0 |  |  | 80 |  |  |  | 4500 | 4500 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 900 | 5400 |  | Only long loss mons & OLD 4ch NIM elec, will I/F to Controls V102 & ADC's
1.4.2.8.2.1 | Gas system distributed. | 1000 |  |  | 1000 | 20 |  |  | 80 |  |  | 5543 | 6543 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 916.02 | 7459.02 |  | Upgrade and routing of supply & return gas dist.
1.4.2.8.2.2 | New & repair Long loss Mons (Cables) | 5000 |  |  | 5000 | 20 |  |  | 100 |  |  | 6593 | 11593 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2318.6 | 13911.6 |  | Repair, replace, relocate as needed.
1.4.2.8.2.3 | LM Inhibit system & I/F | 5000 |  |  | 5000 | 40 |  |  | 80 |  |  | 6886 | 11886 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2377.2 | 14263.2 |  | Similar to H20 type.
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3 | Profile Monitors |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.1 | EPM's |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.1.1 | SWYD (2) Mechanical | 30000 |  |  | 30000 | 80 | 40 | 20 | 160 | 40 |  | 21165 | 51165 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 13302.9 | 64467.9
| Electronics | 50000 |  |  | 50000 | 80 |  | 20 | 160 |  |  | 14897 | 64897 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 12979.4 | 77876.4
1.4.2.8.3.1.2 | A line (2) Mechanical | 30000 |  |  | 30000 | 80 | 40 | 20 | 160 | 40 |  | 21165 | 51165 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 13302.9 | 64467.9
| Electronics | 50000 |  |  | 50000 | 80 |  | 20 | 160 |  |  | 14897 | 64897 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 12979.4 | 77876.4
1.4.2.8.3.1.3 | B Line (2) Mechanical | 30000 |  |  | 30000 | 80 | 40 | 20 | 160 | 40 |  | 21165 | 51165 | 1 | 2 | 12 | 1 | 4 | 8 | 26% | 13302.9 | 64467.9
| Electronics | 50000 |  |  | 50000 | 80 |  | 20 | 160 |  |  | 14897 | 64897 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 12979.4 | 77876.4
1.4.2.8.3.1.4 | Biasing for all | 12000 |  |  | 12000 | 20 |  |  | 40 |  |  | 3443 | 15443 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 1853.16 | 17296.16
1.4.2.8.3.1.5 | Cabling (round to flat) | 6000 |  |  | 6000 | 40 |  |  | 160 |  |  | 11086 | 17086 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 2392.04 | 19478.04
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.2 | Scanning Target |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.2.1 | Installation/Survey | 1000 |  |  | 1000 | 40 |  |  | 80 |  |  | 6886 | 7886 | 1 | 2 | 6 | 1 | 2 | 6 | 16% | 1261.76 | 9147.76
1.4.2.8.3.2.2 | Detectors | 1000 |  |  | 1000 | 20 |  |  | 40 |  |  | 3443 | 4443 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 888.6 | 5331.6
1.4.2.8.3.2.3 | Electronics (use existing) | 0 |  |  | 0 |  |  |  | 20 |  |  | 1050 | 1050 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 147 | 1197
1.4.2.8.3.2.4 | Bias (use existing) | 0 |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.3.2.5 | Device motion upgrade | 10000 |  |  | 10000 | 20 |  |  | 40 |  |  | 3443 | 13443 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2688.6 | 16131.6
1.4.2.8.3.2.6 | New targets | 2000 |  |  | 2000 | 40 |  |  | 40 |  |  | 4786 | 6786 | 1 | 2 | 10 | 1 | 4 | 8 | 24% | 1628.64 | 8414.64
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.3.3 | C011 Plunging SWIC |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.8.3.3.1 | SWIC Head | 15000 |  |  | 15000 | 40 |  |  | 80 |  |  | 6886 | 21886 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 4377.2 | 26263.2
1.4.2.8.3.3.2 | Motion upgrade | 5000 |  |  | 5000 | 20 |  |  | 40 |  |  | 3443 | 8443 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 1013.16 | 9456.16
1.4.2.8.3.3.3 | Electronics | 1000 |  |  | 1000 | 80 |  | 20 | 160 |  |  | 14897 | 15897 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 3179.4 | 19076.4 |  | Use CF100 SWIC Electronics, minor modifications.
1.4.2.8.4 | Motion Control |  |  |  | 0
1.4.2.8.4.1 | Beam Plugs (3) A, B, & C. | 9000 |  |  | 9000 | 80 |  |  | 160 |  |  | 13772 | 22772 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3643.52 | 26415.52 |  | connectors and I/F to Controls. New axis includes cables and J-box.
1.4.2.8.4.2 | X & Y Collimator, 4 jaws = 4 axis | 12000 |  |  | 12000 | 80 |  |  | 160 |  |  | 13772 | 25772 | [6 empty] | 0% | 0 | 25772
1.4.2.8.5 | Current Transformer |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.5.1 | CT at C036 | 10000 |  |  | 10000 | 80 | 40 | 20 | 160 |  |  | 18483 | 28483 | 1 | 2 | 4 | 1 | 2 | 4 | 12% | 3417.96 | 31900.96
1.4.2.8.5.2 | Electronics | 25000 |  |  | 25000 | 80 |  |  | 120 |  |  | 11672 | 36672 | 1 | 2 | 12 | 1 | 2 | 8 | 24% | 8801.28 | 45473.28
1.4.2.8.5.3 | VME | 4000 |  |  | 4000
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6 | Secondary Emission Chamber |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6.1 | C10 SEC |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6.2 | Plunge capability | 30000 |  |  | 30000 | 80 |  |  | 160 |  |  | 13772 | 43772 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 7003.52 | 50775.52
1.4.2.8.6.3 | Device |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.6.4 | Electronics | 5000 |  |  | 5000 | 40 |  | 20 | 100 |  |  | 9061 | 14061 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 2812.2 | 16873.2
1.4.2.8.6.5 | Vacuum controls | 10000 |  |  | 10000 | 20 |  |  | 40 |  |  | 3443 | 13443 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2150.88 | 15593.88
1.4.2.8.6.6 | Cabling | 500 |  |  | 500 |  |  |  | 20 |  |  | 1050 | 1550 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 217 | 1767
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% |  | 0
1.4.2.8.7 | Cable & Racks |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.2.8.7.1 | Rad-Damaged & old replaced | 15000 |  |  | 15000 | 40 |  |  | 600 |  |  | 34186 | 49186 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 6886.04 | 56072.04
1.4.2.8.7.2 | Relocation | 10000 |  |  | 10000 | 40 |  |  | 160 | 40 |  | 13768 | 23768 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 3327.52 | 27095.52
1.4.2.9 | Switchyard Security modifications |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 239159.292
1.4.2.9.1 | project support |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 0 | 0
1.4.2.9.1.1 | installation supervision |  |  |  | 0 |  |  |  | 600 |  |  | 31500 | 31500 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 3150 | 34650
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.2 | PLC Systems |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  | PLC will be located in 911A cage. Some modules will resides locally.
1.4.2.9.2.1 | Programming | 0 |  |  | 0 | 320 |  | 0 | 0 | 0 | 0 | 21488 | 21488 | 2 | 2 | 3 | 2 | 2 | 8 | 19% | 4082.72 | 25570.72
1.4.2.9.2.2 | PLC & Racks | 17000 |  |  | 17000 | 32 |  | 40 | 240 | 16 | 0 | 18071.6 | 35071.6 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 5260.74 | 40332.34
1.4.2.9.2.3 | I/O modules | 11000 |  |  | 11000 | 16 |  | 0 | 40 | 0 | 0 | 3174.4 | 14174.4 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 2126.16 | 16300.56
1.4.2.9.2.4 | R/IO Blocks | 10000 |  |  | 10000 |  |  | 0 | 40 | 0 | 0 | 2100 | 12100 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1815 | 13915
1.4.2.9.2.5 | UPS and Phoenix connectors | 4000 |  |  | 4000 |  |  | 0 | 40 | 40 | 0 | 4782 | 8782 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1317.3 | 10099.3
1.4.2.9.2.6 | Fiber converters (R/IO & DH+ comm)(6) | 7200 |  |  | 7200 | 16 |  | 0 | 40 | 0 | 0 | 3174.4 | 10374.4 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1556.16 | 11930.56
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.3 | Gates (Incl. 3 gates) |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.3.1 | Gates | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 0 | 0 |  | The existing gates will be used.
1.4.2.9.3.2 | Gates Boxes | 1800 |  |  |  | 40 |  | 40 | 240 | 0 |  | 17536 | 17536 | 1 | 2 | 3 | 2 | 1 | 4 | 11%
1.4.2.9.3.3 | Limit switches (10) | 600 |  |  | 600 |  |  | 0 | 24 | 0 |  | 1260 | 1860 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 204.6 | 2064.6
1.4.2.9.3.4 | Electric strikes (2) | 240 |  |  | 240 |  |  | 0 | 24 | 0 |  | 1260 | 1500 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 165 | 1665
1.4.2.9.3.5 | Card Readers (2) | 400 | 0 |  | 400 | 8 |  | 0 | 40 | 0 | 0 | 2637.2 | 3037.2 | 1 | 2 | 3 | 2 | 1 | 4 | 11% | 334.092 | 3371.292
1.4.2.9.3.6 | Key Tree & Iris Scanner | 9000 |  |  | 9000 |  |  |  | 40 | 40 |  | 4782 |  | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1791.66 | 15573.66
1.4.2.9.4 | Cables |  |  |  | 0 |  |  |  | 80 | 40 | 0 | 6882 | [7 empty] | 0% | 0 | 6882
1.4.2.9.4.1 | Cables 18/c (3000ft) | 1500 |  |  | 1500 | 0 |  |  | 0 |  | 0 | 0 | 1500 | 0 | 2 | 3 | 2 | 2 | 4 | 11% | 165 | 1665
1.4.2.9.4.2 | Cables 12/c (3000ft) | 1500 |  |  | 1500 | 0 |  | 0 | 0 |  |  | 0 | 1500 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 135 | 1635
1.4.2.9.4.3 | Cables 8/c (3000ft) | 1350 |  |  | 1350 | 0 |  |  | 0 |  | 0 | 0 | 1350 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 121.5 | 1471.5
1.4.2.9.4.4 | Cables 4/c (3000ft) | 1050 | 0 |  | 1050 | 0 |  | 0 |  |  |  | 0 | 1050 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 94.5 | 1144.5
1.4.2.9.4.5 | Crash cables (1000ft) | 750 | 0 |  | 750 | 0 |  | 0 |  |  |  | 0 | 750 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 67.5 | 817.5
1.4.2.9.4.6 | DH+ Comm cables (1000ft) | 450 | 0 |  | 450 | 0 |  | 0 |  |  |  | 0 | 450 | 0 | 2 | 3 | 2 | 1 | 4 | 9% | 40.5 | 490.5
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.5 | CATV
1.4.2.9.5.1 | Bobcat switch 16*2 mux (2) | 1200 |  |  | 1200 | 40 |  | 24 | 80 | 0 |  | 8236 | 9436 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 1415.4 | 10851.4
1.4.2.9.5.2 | Lee Data 1*1 Fiber Optics Transmitter (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1260 | 1760 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 264 | 2024
1.4.2.9.5.3 | Lee Data 1*1 Fiber Optics Receiver (2) | 500 |  |  | 500 |  |  |  | 24 | 0 |  | 1260 | 1760 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 264 | 2024
1.4.2.9.5.4 | Digital Cameras (6) | 1800 | 0 |  | 1800 |  |  |  | 40 | 0 |  | 2100 | 3900 | 2 | 2 | 3 | 2 | 2 | 4 | 15% | 585 | 4485
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.6 | Chipmunks | [22 empty] | Will use existing chipmunks and DAQ hardware.
1.4.2.9.6.1 | Chipmunks (0 units) | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
1.4.2.9.6.2 | VME SIS Scaler board | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
1.4.2.9.6.3 | Weather proof enclusure | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
1.4.2.9.6.4 | Coaxial cables (1000 ft) | 0 | 0 |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.2.9.7 | Crash, Sweep & Alarms
1.4.2.9.7.1 | Check station boxes | 300 |  |  | 300 | 80 |  | 40 | 80 | 0 |  | 11822 | 12122 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1575.86 | 13697.86
1.4.2.9.7.2 | Crash Actuators | 500 |  |  | 500 |  |  |  | 80 | 0 |  | 4200 | 4700 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 611 | 5311
1.4.2.9.7.3 | Crash Stations and Alarms | 1500 |  |  | 1500 |  |  |  | 160 | 0 |  | 8400 | 9900 | 1 | 2 | 3 | 2 | 2 | 4 | 13% | 1287 | 11187
1.4.2.10 | Computer Controls | [21 empty] | 234934.096
| Instrumentation Interface Hardware | 19020 | 56540 |  | 75560 | 150 |  |  | 120 | 0 |  | 16372.5 | 91932.5 | 2 | 2 | 8 | 4 | 1 | 8 | 24% | 22063.8 | 113996.3 |  | Scope set by instrumentation needs
| Instrumentation Software & DB |  |  |  | 0 | 168 | [5 empty] | 11281.2 | 11281.2 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 3158.736 | 14439.936
| Power Supply Interface Hardware | 29000 | 41360 |  | 70360 | 80 |  |  | 130 | 16 |  | 13269.8 | 83629.8 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 18398.556 | 102028.356 |  | Need to replace obsolete Datacon controls
| Power Supply Software & DB |  |  |  | 0 | 52 | [5 empty] | 3491.8 | 3491.8 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 977.704 | 4469.504
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.5.2.10 | NASA relocation |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 | 46449.67 | location?
1.5.2.10.1 | vacuum valves & windows | 12000 |  |  | 12000 | 10 |  | 8 | 10 |  | 40 | 5686.5 | 17686.5 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 3891.03 | 21577.53 |  | Provides for a removable section of B vacuum system for NASA running
1.5.2.10.2 | enclosure | 10000 |  |  | 10000 |  |  |  |  | 120 |  | 8046 | 18046 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 3970.12 | 22016.12 |  | Builds an enclosure in the SYG for NASA experiments
1.5.2.10.3 | air conditioning | 1000 |  |  | 1000 |  |  |  |  | 20 |  | 1341 | 2341 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 515.02 | 2856.02 |  | Provides AC in the enclosure for NASA
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Labor Hours |  |  |  |  | 4150 | 610 | 1540 | 18762 | 5236 | 2250 | [8 empty] | 0%
| FTE |  |  |  |  | 2.3647 | 0.34758 | 0.87749 | 10.6906 | 2.9835 | 1.2821
| TOTALS - DIRECT | 818160 | 471300 | 0 | 1287660 | 278672.5 | 54686.5 | 86625 | 985005 | 351073.8 | 227250 | 1983312.8 | 3246308.8 | [6 empty] | 19.68% | 638972.122 | 3883044.922
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 25.72% | 13.73% |  |  | 40.22% | 40.22% | 40.22% | 40.22% | 12% | 12% | [9 empty] | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 1028631.66 | 535985.925 |  | 1564617.585 | 390760.5069 | 76682.5735 | 121467.4175 | 1381194.9621 | 393202.656 | 254520 | 2617828.1159 | 4182445.7009 | [6 empty] | 19.68% | 823232.283 | 5005677.9839
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## WBS 1.4.3 K0PI0 B-Line
RSVP - 1.4.3 KOPIO, AGS
2004-10-29 | pearson withneutral beam and chipmunk changesexperiment area and neutral beam |  |  |  |  | Labor Rates
[6 empty] | 67.15 | 89.65 | 56.25 | 52.5 | 67.05 | 101
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total | WBS Level 4 | WBS Level 4
Number | Description | <$25000 | >$25000 | >$600000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | Total (Direct w/o cont') | Total (Direct w/cont') | Comments
1.4.3.1 | Project support and Integration |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 1153994 | 1338633.04
| Engr & Design Supervision |  |  |  | 0 | 5830 | [5 empty] | 391484.5 | 391484.5 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 62637.52 | 454122.02 |  |  |  | K0PI0 | Direct w/o Contingency
| Physicist Supervision |  |  |  | 0 |  | 5830 |  |  |  |  | 522659.5 | 522659.5 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 83625.52 | 606285.02
| Design |  |  |  | 0 |  |  | 1800 |  |  |  | 101250 | 101250 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 16200 | 117450 |  |  |  | Primary Beam | 2034107.5
| Construction Supervision |  |  |  | 0 |  |  |  | 2640 |  |  | 138600 | 138600 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 22176 | 160776 |  |  |  | Neutral Beam | 2112664
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  |  |  | Project Support and Integration | 1153994
1.4.3.2 | Primary Beam |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 2034107.5 | 2449176.294 |  | Experimental Areas | 1120716.45
1.4.3.2.1 | B1,B2,B5 Removal |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  |  |  | Common Equipment & Facilities | 311576.3
| Remove equipment |  |  |  | 0 |  |  |  | 760 | 120 |  | 47946 | 47946 | 1 | 2 | 4 | 6 | 1 | 4 | 16% | 7671.36 | 55617.36 |  |  |  | Security | 227551.6
| Remove power & tray |  |  |  | 0 |  |  |  |  | 80 |  | 5364 | 5364 | 1 | 2 | 4 | 6 | 1 | 4 | 16% | 858.24 | 6222.24
| Modify shielding |  |  |  | 0 |  |  |  |  | 2160 |  | 144828 | 144828 | 1 | 2 | 4 | 6 | 1 | 4 | 16% | 23172.48 | 168000.48
| Rad disposal | 60000 |  |  | 60000 |  |  |  | 300 |  |  | 15750 | 75750 | [6 empty] | 0% | 0 | 75750 |  |  |  | K0PI0 TOTAL | 6960609.85
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.2 | C1,C3,C7 Removal |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Remove equipment |  |  |  | 0 |  |  |  | 168 |  |  | 8820 | 8820 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 1234.8 | 10054.8
| Remove power & tray |  |  |  | 0 |  |  |  |  | 80 |  | 5364 | 5364 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 750.96 | 6114.96
| Modify shielding |  |  |  | 0 |  |  |  |  | 1440 |  | 96552 | 96552 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 13517.28 | 110069.28
| Rad disposal | 20000 |  |  | 20000 |  |  |  | 100 |  |  | 5250 | 25250 | [6 empty] | 0% | 0 | 25250
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.3 | Additional Shielding |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Floor blocks (200 tons) |  | 30000 |  | 30000 | 60 | [5 empty] | 4029 | 34029 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 6125.22 | 40154.22
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.4 | Transport Magnets (9) |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Refurbish 8Q32 | 1000 |  |  | 1000 | 10 |  |  | 160 | 12 | 10 | 10886.1 | 11886.1 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 2139.498 | 14025.598
| Refurbish 3-5Q36 | 3000 |  |  | 3000 | 30 |  |  | 480 | 24 | 30 | 31853.7 | 34853.7 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 6273.666 | 41127.366
| Refurbish 4-Trims | 2000 |  |  | 2000 | 20 |  |  | 320 | 12 | 20 | 20967.6 | 22967.6 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 4134.168 | 27101.768
| Refurbish N3Q48 | 1000 |  |  | 1000 | 10 |  |  | 160 | 12 | 10 | 10886.1 | 11886.1 | 2 | 2 | 4 | 4 | 2 | 2 | 18% | 2139.498 | 14025.598
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.5 | Power Supplies |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify PSs for new controls (10) | 17250 | 21700 |  | 38950 | 100 |  | 80 | 2080 | 30 | 50 | 127476.5 | 166426.5 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 33285.3 | 199711.8
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.6 | Electrical Modifications |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify Royals (4) |  | 60000 |  | 60000 |  |  |  |  | 80 |  | 5364 | 65364 | 4 | 2 | 8 | 6 | 2 | 2 | 30% | 19609.2 | 84973.2
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% |  | 0
1.4.3.2.7 | Instrumentation/Controls |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.1 | project support |  |  |  | 0 | 240 | 120 | 80 |  |  |  | 31374 | 31374 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 5019.84 | 36393.84
| installation supervision |  |  |  | 0 |  |  |  | 440 |  |  | 23100 | 23100 | 1 | 2 | 4 | 4 | 1 | 2 | 12% | 2772 | 25872
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2 | B Transport Devices | [10 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.1 | EPM's/Plunging SWIC's (4) | 240000 |  |  | 240000 | 240 | 80 | 80 | 480 |  |  | 52988 | 292988 | 3 | 4 | 4 | 6 | 2 | 8 | 36% | 105475.68 | 398463.68
Includes device & electronics
1.4.3.2.7.2.2 | Loss Monitors |  |  |  | 0 | 120 |  |  | 240 |  |  | 20658 | 20658 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3305.28 | 23963.28
| Long LM's | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 960 | 6960
| LM's, IC's(4 in picture frame config.) | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
| 1 Detector per magnet | 24000 |  |  | 24000 | [6 empty] | 0 | 24000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3840 | 27840
| HV Bias | 7500 |  |  | 7500 | [6 empty] | 0 | 7500 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 900 | 8400
| Electronics | 8000 |  |  | 8000 | [6 empty] | 0 | 8000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 960 | 8960
| Special chassis | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3 | New B Target Devices |  |  |  | 0 | 240 | 40 | 80 | 480 |  | 40 | 53442 | 53442 | 1 | 2 | 4 | 4 | 2 | 8 | 22% | 11757.24 | 65199.24
1.4.3.2.7.2.3.1 | B-SEC |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Device, with vacuum pump. | 20000 |  |  | 20000 | [6 empty] | 0 | 20000 | 3 | 4 | 4 | 2 | 2 | 8 | 28% | 5600 | 25600
| Electronics (I/V, I/F, HV Bias, & counter) | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 4 | 4 | 2 | 8 | 22% | 1320 | 7320
| Translation Table & Controls | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600
1.4.3.2.7.2.3.2 | Target Temperature Monitor | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3.3 | B Target Flag |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Mount, Lamps | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 240 | 2240
| Rad-Hard video camera | 25000 |  |  | 25000 | [6 empty] | 0 | 25000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 4000 | 29000
| Camera Lens, ND Filter, driver. | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 960 | 6960
1.4.3.2.7.2.3.4 | 90 deg telescope |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| 90 Target Tel (Scint/PMT assy & mount) | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 960 | 6960
| Tel Elec & Bias (amps, discr counter) | 12500 |  |  | 12500 | [6 empty] | 0 | 12500 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2000 | 14500
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7.2.3.5 | Loss Monitors |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| IC's (4 in picture frame config.) | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
| LM VME FE electronics, Controls I/F | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
| HV Bias | 2500 |  |  | 2500 | [6 empty] | 0 | 2500 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 300 | 2800
| Interface to machine protect system | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 800 | 5800
1.4.3.2.7.2.3.6 | Cables and Racks |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Cables, connectors, patch panels | 3000 |  |  | 3000 |  |  |  | 240 |  |  | 12600 | 15600 | 1 | 2 | 4 | 2 | 2 | 8 | 18% | 2808 | 18408
| All Rack H/W and misc. items | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 320 | 2320
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.7 | B Target Instrumentation Station |  |  |  | 0 | 160 |  |  | 320 |  |  | 27544 | 27544 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 3856.16 | 31400.16
| Racks (5) installed at Instru Elec. Support location | 7500 |  |  | 7500 | [6 empty] | 0 | 7500 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 1050 | 8550
1.4.3.2.8 | Environmental Enclosures |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| New Instru enclosed room with AC | 15000 |  |  | 15000 | [6 empty] | 0 | 15000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2400 | 17400
| Control/Instru enclosure | 10000 |  |  | 10000 |  |  |  |  | 140 |  | 9387 | 19387 | 4 | 2 | 4 | 4 | 2 | 2 | 22% | 4265.14 | 23652.14
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.9 | Vacuum |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Pipe, flanges, bellows, valves | 42000 |  |  | 42000 | 80 |  |  | 120 |  | 120 | 23792 | 65792 | 3 | 2 | 8 | 4 | 2 | 2 | 24% | 15790.08 | 81582.08
| Vacuum pumps (2) |  | 48000 |  | 48000 | 40 | [5 empty] | 2686 | 50686 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 8109.76 | 58795.76
| Monitors | 5000 |  |  | 5000 | 8 |  |  | 80 |  |  | 4737.2 | 9737.2 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 1557.952 | 11295.152
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.2.10 | Installation |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Install magnets (9) | 18000 |  |  | 18000 | 36 |  |  | 2448 | 1008 |  | 198523.8 | 216523.8 | 3 | 2 | 8 | 4 | 2 | 2 | 24% | 51965.712 | 268489.512
| Survey beam components |  |  |  | 0 |  |  |  | 240 |  |  | 12600 | 12600 | 1 | 2 | 4 | 4 | 1 | 2 | 12% | 1512 | 14112
| Install vacuum |  |  |  | 0 |  |  |  | 160 |  | 80 | 16480 | 16480 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 2636.8 | 19116.8
| Install victualic & manifolds | 15500 |  |  | 15500 |  |  |  | 120 | 90 |  | 12334.5 | 27834.5 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4453.52 | 32288.02
| Install power & lights | 5000 |  |  | 5000 |  |  |  |  | 320 |  | 21456 | 26456 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 4232.96 | 30688.96
| Clean cave & paint | 1000 |  |  | 1000 |  |  |  | 80 | 80 |  | 9564 | 10564 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 1690.24 | 12254.24
| Close roof |  |  |  | 0 |  |  |  |  | 1440 |  | 96552 | 96552 | 3 | 2 | 4 | 4 | 1 | 2 | 16% | 15448.32 | 112000.32
| Fire Detection | 5000 |  |  | 5000 |  |  |  |  | 160 |  | 10728 | 15728 | 1 | 2 | 4 | 4 | 2 | 2 | 16% | 2516.48 | 18244.48
| Cave dehumidification | 15000 |  |  | 15000 |  |  |  |  | 40 |  | 2682 | 17682 | 4 | 2 | 4 | 4 | 2 | 2 | 22% | 3890.04 | 21572.04
| Shielding seismic restraints | 15000 |  |  | 15000 |  |  |  |  | 240 |  | 16092 | 31092 | 6 | 2 | 4 | 4 | 2 | 2 | 26% | 8083.92 | 39175.92
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.3 | Common Equipment/Facilities |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 311576.3 | 379494.644
| Magnet Interlock System | 35214 |  |  | 35214 | 72 |  | 96 | 608 |  |  | 42154.8 | 77368.8 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 17021.136 | 94389.936
| Bldg 912 Facility Upgrade | 40000 |  |  | 40000 | [6 empty] | 0 | 40000 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 8800 | 48800
| Radio remote -- EEBA crane |  | 35000 |  | 35000 | 24 |  |  |  | 40 |  | 4293.6 | 39293.6 | 1 | 2 | 0 | 4 | 2 | 4 | 14% | 5501.104 | 44794.704 |  |  | Required for experiment assembly
| Controls |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Instrumentation Interface Hardware | 9300 | 49180 |  | 58480 | 180 |  |  | 230 | 0 |  | 24162 | 82642 | 2 | 2 | 8 | 4 | 1 | 8 | 24% | 19834.08 | 102476.08 |  |  | Scope set by instrumentation needs
| Instrumentation Software & DB |  |  |  | 0 | 174 | [5 empty] | 11684.1 | 11684.1 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 3271.548 | 14955.648
| Power Supply Interface Hardware | 18000 | 25000 |  | 43000 | 80 |  |  | 110 | 56 |  | 14901.8 | 57901.8 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 12738.396 | 70640.196 |  |  | Need to replace obsolete Datacon controls
| Power Supply Software & DB |  |  |  | 0 | 40 | [5 empty] | 2686 | 2686 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 752.08 | 3438.08
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4 | B-line Security System modifications |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 227551.6 | 267224.62
| project support |  |  |  | 0 | 40 | [5 empty] | 2686 | 2686 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 268.6 | 2954.6
| installation supervision |  |  |  | 0 |  |  |  | 600 |  |  | 31500 | 31500 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 3150 | 34650
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.1 | PLC Systems |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0 |  |  | PLC will be located in 911A cage. Some modules will resides locally.
| Programming | 0 |  |  | 0 | 320 | [5 empty] | 21488 | 21488 | 2 | 2 | 3 | 4 | 2 | 8 | 23% | 4942.24 | 26430.24
| PLC & Racks | 8000 |  |  | 8000 | 32 |  | 40 | 240 | 16 |  | 18071.6 | 26071.6 | 2 | 2 | 3 | 4 | 2 | 8 | 23% | 5996.468 | 32068.068
| I/O modules | 6300 |  |  | 6300 | 16 |  | 0 | 40 | 0 |  | 3174.4 | 9474.4 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1800.136 | 11274.536
| R/IO Blocks | 8000 |  |  | 8000 |  |  | 0 | 40 | 0 |  | 2100 | 10100 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1919 | 12019
| UPS and Phoenix connectors | 4000 |  |  | 4000 |  |  | 0 | 40 | 40 |  | 4782 | 8782 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1668.58 | 10450.58
| Fiber converters (R/IO & DH+ comm)(6) | 4800 |  |  | 4800 | 16 |  | 0 | 40 | 0 |  | 3174.4 | 7974.4 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1515.136 | 9489.536
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.2 | Gates (Incl. 3 gates) |  |  |  | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
| Gates | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 0 | 0 |  |  | The existing gates will be used.
| Gates Boxes | 1800 |  |  |  | 40 |  | 40 | 240 | 0 |  | 17536 | 17536 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 2630.4 | 20166.4
| Limit switches (10) | 600 |  |  | 600 |  |  | 0 | 24 | 0 |  | 1260 | 1860 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 279 | 2139
| Electric strikes (2) | 240 |  |  | 240 |  |  | 0 | 24 | 0 |  | 1260 | 1500 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 225 | 1725
| Card Readers (2) | 400 |  |  | 400 | 8 |  | 0 | 40 | 0 | 0 | 2637.2 | 3037.2 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 455.58 | 3492.78
| Key Tree & Iris Scanner | 9000 |  |  | 9000 |  |  |  | 40 | 40 |  | 4782 | 13782 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 2067.3 | 15849.3
1.4.3.4.3 | Cables |  |  |  | 0 |  |  |  | 80 | 40 | 0 | 6882 | 6882 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 894.66 | 7776.66
| Cables 18/c (3000ft) | 1500 |  |  | 1500 | 0 |  |  | 0 |  | 0 | 0 | 1500 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 195 | 1695
| Cables 12/c (3000ft) | 1500 |  |  | 1500 | 0 |  | 0 | 0 |  |  | 0 | 1500 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 195 | 1695
| Cables 8/c (3000ft) | 1350 |  |  | 1350 | 0 |  |  | 0 |  | 0 | 0 | 1350 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 175.5 | 1525.5
| Cables 4/c (3000ft) | 1050 |  |  | 1050 | 0 |  | 0 |  |  |  | 0 | 1050 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 136.5 | 1186.5
| Crash cables (1000ft) | 750 |  |  | 750 | 0 |  | 0 |  |  |  | 0 | 750 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 97.5 | 847.5
| DH+ Comm cables (1000ft) | 450 |  |  | 450 | 0 |  | 0 |  |  |  | 0 | 450 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 58.5 | 508.5
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.4 | CATV
| Bobcat switch 16*2 mux (2) | 1200 |  |  | 1200 | 40 |  | 24 | 80 |  |  | 8236 | 9436 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 1604.12 | 11040.12
| Lee Data 1*1 Fiber Optics Transmitter (2) | 500 |  |  | 500 |  |  |  | 24 |  |  | 1260 | 1760 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 299.2 | 2059.2
| Lee Data 1*1 Fiber Optics Receiver (2) | 500 |  |  | 500 |  |  |  | 24 |  |  | 1260 | 1760 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 299.2 | 2059.2
| Digital Cameras (6) | 1800 |  |  | 1800 |  |  |  | 40 |  |  | 2100 | 3900 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 663 | 4563
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.5 | Chipmunks | [23 empty] | Will use existing chipmunks and DAQ hardware. If required
| Chipmunks (0 units) | 10000 |  |  | 10000 |  |  |  | 40 |  |  | 2100 | 12100 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 2299 | 14399 |  |  | additional units purchase later.
| VME SIS Scaler board |  |  |  | 0 | [6 empty] | 0 | 0 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 0 | 0
| Weather proof enclusure |  |  |  | 0 | [6 empty] | 0 | 0 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 0 | 0
| Coaxial cables (1000 ft) | 500 |  |  | 500 |  |  |  | 40 |  |  | 2100 | 2600 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 494 | 3094
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.3.4.6 | Crash, Sweep & Alarms
| Check station boxes | 300 |  |  | 300 | 80 |  | 40 | 80 | 0 |  | 11822 | 12122 | 2 | 2 | 4 | 4 | 2 | 4 | 20% | 2424.4 | 14546.4
| Crash Actuators | 500 |  |  | 500 |  |  |  | 80 | 0 |  | 4200 | 4700 | 2 | 2 | 4 | 4 | 2 | 4 | 20% | 940 | 5640
| Crash Stations and Alarms | 1500 |  |  | 1500 |  |  |  | 160 | 0 |  | 8400 | 9900 | 2 | 2 | 4 | 4 | 2 | 4 | 20% | 1980 | 11880
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.5 | Neutral beam |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 2112664 | 2714738.408
1.4.3.5.1 | Target Station | 5000 |  |  | 5000 | 80 | 24 | 80 | 40 |  | 100 | 24223.6 | 29223.6 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 8767.08 | 37990.68
1.4.3.5.2 | D1 sweeper | 12000 | 99225 |  | 111225 | 60 |  | 120 | 680 |  |  | 46479 | 157704 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 47311.2 | 205015.2
1.4.3.5.3 | D2 sweeper | 7000 | 202250 |  | 209250 | 60 |  | 120 | 160 |  |  | 19179 | 228429 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 68528.7 | 296957.7
1.4.3.5.4 | D3 sweeper | 7000 | 471500 |  | 478500 | 60 |  | 120 |  |  |  | 10779 | 489279 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 146783.7 | 636062.7
1.4.3.5.5 | Power supplies
| Modify PSs for new controls (4) | 6900 | 8680 |  | 15580 | 40 |  | 32 | 832 | 12 | 20 | 50990.6 | 66570.6 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 13314.12 | 79884.72
1.4.3.5.6 | Collimator |  |  |  | 0 | 160 |  | 320 |  |  |  | 28744 | 28744 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 8623.2 | 37367.2
| Vacuum box |  | 40000 |  | 40000 | [6 empty] | 0 | 40000 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 12000 | 52000
| Heavy met liner |  | 76000 |  | 76000 | [6 empty] | 0 | 76000 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 22800 | 98800
| Steel shielding |  | 650000 |  | 650000 | [6 empty] | 0 | 650000 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 195000 | 845000
1.4.3.5.7 | Pump Skids |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Target, D1, D2 Pump Skid | 48000 |  |  | 48000 | 40 |  | 140 | 200 | 300 | 100 | 51276 | 99276 | 4 | 2 | 8 | 4 | 2 | 2 | 26% | 25811.76 | 125087.76
| D3, D4 , Exp Pump Skid | 75000 |  |  | 75000 | 40 |  | 112 | 200 | 400 | 140 | 60446 | 135446 | 4 | 2 | 8 | 4 | 2 | 2 | 26% | 35215.96 | 170661.96
1.4.3.5.8 | Temporary Window | 5000 |  |  | 5000 | 40 |  |  |  |  | 80 | 10766 | 15766 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 2522.56 | 18288.56
1.4.3.5.9 | Installation |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Target station | 5000 |  |  | 5000 | 8 |  |  | 48 | 24 |  | 4666.4 | 9666.4 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 1546.624 | 11213.024
| D1 magnet | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 22326.8 | 26326.8 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4212.288 | 30539.088
| D2 magnet | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 22326.8 | 26326.8 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4212.288 | 30539.088
| D3 magnet | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 22326.8 | 26326.8 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4212.288 | 30539.088
| Collimator & shielding | 1000 |  |  | 1000 | 8 | [5 empty] | 537.2 | 1537.2 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 245.952 | 1783.152
| Temporary Window | 500 |  |  | 500 | 8 |  |  | 80 | 12 |  | 5541.8 | 6041.8 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 966.688 | 7008.488
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.6 | Experimental Area |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 1120716.45 | 1469913.338
1.4.3.6.1 | MPS Removal |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Remove magnet |  |  |  | 0 |  |  |  | 240 | 360 |  | 36738 | 36738 | 1 | 2 | 4 | 4 | 1 | 2 | 12% | 4408.56 | 41146.56
| Fill pit | 15000 |  |  | 15000 | 40 | [5 empty] | 2686 | 17686 | 1 | 2 | 4 | 4 | 1 | 2 | 12% | 2122.32 | 19808.32
1.4.3.6.2 | Detector pit |  | 470945 |  | 470945 | 80 | [5 empty] | 5372 | 476317 | 6 | 2 | 15 | 4 | 2 | 4 | 39% | 185763.63 | 662080.63
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.3.6.3 | D4 Sweeper | 7000 | 338750 |  | 345750 | 40 |  | 120 |  |  |  | 9436 | 355186 | 6 | 2 | 8 | 4 | 2 | 2 | 30% | 106555.8 | 461741.8
| Installation | 4000 |  |  | 4000 | 8 |  |  | 272 | 112 |  | 22326.8 | 26326.8 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4212.288 | 30539.088
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Power supplies |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify PSs for new controls (1) | 1725 | 2170 |  | 3895 | 10 |  | 8 | 208 | 3 | 5 | 12747.65 | 16642.65 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 3328.53 | 19971.18
1.4.3.6.3 | shielding | 10000 |  |  | 10000 |  |  |  |  | 240 |  | 16092 | 26092 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 4174.72 | 30266.72
1.4.3.6.4 | Experimental power |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Modify royals |  | 60000 |  | 60000 | [6 empty] | 0 | 60000 | 4 | 2 | 8 | 6 | 2 | 2 | 30% | 18000 | 78000
| 480V power & tray | 15000 |  |  | 15000 |  |  |  |  | 160 |  | 10728 | 25728 | 2 | 2 | 8 | 4 | 1 | 2 | 18% | 4631.04 | 30359.04
1.4.3.6.5 | counting house | 20000 |  |  | 20000 | [6 empty] | 0 | 20000 | 1 | 2 | 8 | 4 | 2 | 2 | 20% | 4000 | 24000 |  |  | Use existing E802 counting house with minor changes
1.4.3.6.6 | Fast electronics area |  | 60000 |  | 60000 | [6 empty] | 0 | 60000 | 1 | 2 | 8 | 4 | 2 | 2 | 20% | 12000 | 72000 |  |  | Use modular system 20' X 60'
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Labor Hours |  |  |  |  | 9192 | 6094 | 3532 | 19356 | 9759 | 805 | [8 empty] | 0%
| FTE |  |  |  |  | 5.2376 | 3.4724 | 2.0125 | 11.0291 | 5.5607 | 0.45869
| TOTALS - DIRECT | 1099929 | 2748400 | 0 | 3846529 | 617242.8 | 546327.1 | 198675 | 1016190 | 654340.95 | 81305 | 3114080.85 | 6960609.85 | [6 empty] | 23.83% | 1658570.494 | 8619180.344 | 6960609.85 | 8619180.344 | 6960609.85
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 25.72% | 13.73% |  |  | 40.22% | 40.22% | 40.22% | 40.22% | 12% | 12% | [9 empty] | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 1382885.7352 | 3125617.9 |  | 4508503.6353 | 865510.9829 | 766071.48 | 278586.3108 | 1424923.2324 | 732861.864 | 91061.6 | 4159015.4701 | 8667519.1053 | [6 empty] | 23.83% | 2065291.9434 | 10732811.0487
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
[5 empty] | 0 | [6 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## WBS 1.4.4 MECO A-Line
RSVP - MECO
2004-10-18 | 10/4 controls update |  |  |  |  | Labor Rates
[6 empty] | 67.15 | 89.65 | 56.25 | 52.5 | 67.05 | 101
Total
WBS |  | Materials |  |  | Total | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total | WBS Level 4
Number | Description | <$25000 | >$25000 | >$600000 | Mat'ls | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | Total (Direct w/cont') | Comments
1.4.4 | MECO A-Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.1 | Project Support and Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1198265.152 | Liaison Physicist and Engineer for the design, fabrication and installation of the MECO Proton Beamline and Experiment at CA.
1.4.4.1.1 | Liaison Physicist | 0 | 0 | 0 | 0 | 0 | 5704 | 0 | 0 | 0 | 0 | 511363.6 | 511363.6 | 1 | 2 | 10 | 2 | 1 | 2 | 16% | 81818.176 | 593181.776
1.4.4.1.2 | Liaison Engineer | 0 | 0 | 0 | 0 | 5704 | 0 | 0 | 0 | 0 | 0 | 383023.6 | 383023.6 | 1 | 2 | 10 | 2 | 1 | 2 | 16% | 61283.776 | 444307.376
1.4.4.1.3 | Technical Supervision | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2640 | 0 | 0 | 138600 | 138600 | 1 | 2 | 10 | 2 | 1 | 2 | 16% | 22176 | 160776 |  | Supervision of technicians for the fabrication and installation of the MECO Proton Beamline and Experiment at CA.
1.4.4.2 | MECO Proton Beam Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 5036411.598 | Delivers the Proton Beam from the AGS Switchyard to the entrance to the PS. Includes the Proton Beam Dump.
1.4.4.2.1 | Beamline Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Physics design of the Proton Beam integrated with existing and new beam line components.
1.4.4.2.1.1 | Physics Design | 0 | 0 | 0 | 0 | 0 | 1755 | 0 | 0 | 0 | 0 | 157335.75 | 157335.75 | 1 | 2 | 10 | 2 | 1 | 2 | 16% | 25173.72 | 182509.47
1.4.4.2.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 1755 | 0 | 0 | 0 | 98718.75 | 98718.75 | 1 | 2 | 10 | 2 | 1 | 2 | 16% | 15795 | 114513.75
1.4.4.2.2 | Lambertson Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Separate the "empty buckets" from the Proton Beam.
1.4.4.2.2.1 | Thin Lambertson | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | The upstream Lambertson with a very thin separation between the field and non-field region.
1.4.4.2.2.1.1 | Engineering | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 1343 | 1343 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 241.74 | 1584.74
1.4.4.2.2.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 810 | 5310
1.4.4.2.2.1.3 | Refurbish | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 200 | 0 | 0 | 10500 | 11500 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 2300 | 13800
1.4.4.2.2.1.4 | Rigging | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 3218.4 | 3218.4 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 579.312 | 3797.712
1.4.4.2.2.1.5 | Pre-survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 420 | 420 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 84 | 504
1.4.4.2.2.2 | Thick Lambertson | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | The downstream Lambertson with a thick separation between the field and non-field region.
1.4.4.2.2.2.1 | Engineering | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 5372 | 5372 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 966.96 | 6338.96
1.4.4.2.2.2.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 6750 | 6750 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 1215 | 7965
1.4.4.2.2.2.3 | Pole Piece Fabrication | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 400 | 40400 | 45400 | 4 | 4 | 10 | 4 | 1 | 4 | 34% | 15436 | 60836
1.4.4.2.2.2.4 | Assembly - Mechanical | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 400 | 0 | 0 | 21000 | 22000 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4400 | 26400
1.4.4.2.2.2.5 | Assembly - Interlocks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 2100 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 378 | 2478
1.4.4.2.2.2.6 | Rigging | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 3218.4 | 3218.4 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 579.312 | 3797.712
1.4.4.2.2.2.7 | Pre-survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 420 | 420 | 1 | 2 | 10 | 2 | 1 | 4 | 18% | 75.6 | 495.6
1.4.4.2.2.2.8 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 8400 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1680 | 10080
1.4.4.2.3 | Beam Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Delivers the Proton Beam from the AGS Switchyard to the entrance to the PS. Includes the Proton Beam Dump.
1.4.4.2.3.1 | Equipment Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Clearing the A-Line area of existing equipment.
1.4.4.2.3.1.1 | A-Line (AQ7-A Targ Inst) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.1.1.1 | Disc 4 Mags etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1680 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 302.4 | 1982.4
1.4.4.2.3.1.1.2 | Remove DC Cables etc | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 96 | 0 | 0 | 5040 | 5540 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 997.2 | 6537.2
1.4.4.2.3.1.1.3 | Remove Components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 289.656 | 1898.856 |  |  | MECO | Direct w/o Contingency
1.4.4.2.3.1.1.4 | Disc PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 3360 | 3360 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 604.8 | 3964.8
1.4.4.2.3.1.1.5 | Remove PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 289.656 | 1898.856 |  |  | Primary Beam | 4086794.25
1.4.4.2.3.1.1.6 | Remove PS Decking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 536.4 | 536.4 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 96.552 | 632.952 |  |  | Experimental Area | 1345623.4
1.4.4.2.3.1.1.7 | Cable Tray Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 2145.6 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 386.208 | 2531.808 |  |  | Project Support | 1032987.2
1.4.4.2.3.1.2 | A1-Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  |  | Instrumentation | 763503
1.4.4.2.3.1.2.1 | Disc 9 Mags etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 4200 | 4200 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 756 | 4956 |  |  | Security | 222675.6
1.4.4.2.3.1.2.2 | Remove DC Cables etc | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 240 | 0 | 0 | 12600 | 13100 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 2358 | 15458 |  |  | Controls | 183395.3
1.4.4.2.3.1.2.3 | Remove Components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 4827.6 | 4827.6 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 868.968 | 5696.568
1.4.4.2.3.1.2.4 | Disc PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 8400 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 1512 | 9912
1.4.4.2.3.1.2.5 | Remove PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 4827.6 | 4827.6 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 868.968 | 5696.568
1.4.4.2.3.1.2.6 | Remove PS Decking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 2145.6 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 386.208 | 2531.808 |  |  | MECO TOTAL | 7634978.75
1.4.4.2.3.1.2.7 | Cable Tray Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5364 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 965.52 | 6329.52
1.4.4.2.3.1.2.8 | Remove A-Line Roof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 64368 | 64368 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 12873.6 | 77241.6
1.4.4.2.3.1.3 | A2-Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.1.3.1 | Disc 16 Mags etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 151.2 | 991.2
1.4.4.2.3.1.3.2 | Remove DC Cables etc | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 48 | 0 | 0 | 2520 | 3020 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 543.6 | 3563.6
1.4.4.2.3.1.3.3 | Remove Components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 8046 | 8046 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 1448.28 | 9494.28
1.4.4.2.3.1.3.4 | Remove PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 3218.4 | 3218.4 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 579.312 | 3797.712
1.4.4.2.3.1.3.5 | Cable Tray Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 3218.4 | 3218.4 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 579.312 | 3797.712
1.4.4.2.3.1.4 | A3-Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.1.4.1 | Disc 13 Mags etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 5040 | 5040 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 907.2 | 5947.2
1.4.4.2.3.1.4.2 | Remove DC Cables etc | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 240 | 0 | 0 | 12600 | 13100 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 2358 | 15458
1.4.4.2.3.1.4.3 | Remove Components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 4827.6 | 4827.6 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 868.968 | 5696.568
1.4.4.2.3.1.4.4 | Disc PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 8400 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 1512 | 9912
1.4.4.2.3.1.4.5 | Remove PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 3218.4 | 3218.4 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 579.312 | 3797.712
1.4.4.2.3.1.4.6 | Remove PS Decking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 2145.6 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 386.208 | 2531.808
1.4.4.2.3.1.4.7 | Cable Tray Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5364 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 965.52 | 6329.52
1.4.4.2.3.1.4.8 | Remove NASA Trailer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 1 | 2 | 8 | 4 | 1 | 4 | 18% | 289.656 | 1898.856
1.4.4.2.3.1.4.9 | Remove A3 Beam Dump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 16092 | 16092 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3218.4 | 19310.4
1.4.4.2.3.1.4.10 | Remove A3 Roof by door | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 37548 | 37548 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 7509.6 | 45057.6
1.4.4.2.3.1.4.11 | Remove D6 Dump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 32184 | 32184 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 6436.8 | 38620.8
1.4.4.2.3.1.5 | Rad Material Disposal | 48000 | 0 | 0 | 48000 | 0 | 0 | 0 | 800 | 0 | 0 | 42000 | 90000 | 1 | 2 | 8 | 4 | 1 | 2 | 16% | 14400 | 104400
1.4.4.2.3.2 | Shielding Procurements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Purchases of new shielding to meet needs not filled by existing CA inventory.
1.4.4.2.3.2.1 | Lt Concrete Side Wall | 0 | 56700 | 0 | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56700 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 13608 | 70308 |  | "Light" concrete blocks used to reduce background radiation in hagh activation areas.
1.4.4.2.3.2.2 | Heavy Concrete for Target Area | 13200 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 3168 | 16368 |  | "Heavy" concrete used to shield the target area.
1.4.4.2.3.2.3 | Custom Port Blocks | 33000 | 0 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 7920 | 40920 |  | Shield blocks with penetrations for electrical & cooling water services.
1.4.4.2.3.2.4 | Borated Blocks | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 4800 | 24800 |  | Concrete with boron added to stop neutrons around the TSu.
1.4.4.2.3.2.5 | Floor Blocks | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 7200 | 37200 |  | Blocks used to reduce activation of the building floor and to make working at beam height easier.
1.4.4.2.3.2.6 | Wall Blocks to Raise Roof | 0 | 144000 | 0 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144000 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 34560 | 178560 |  | Blocks to raise the cave roof height due to increased beam height.
1.4.4.2.3.2.7 | TSu Zinc Shielding | 0 | 39200 | 0 | 39200 | 0 | 0 | 0 | 0 | 0 | 40 | 4040 | 43240 | 4 | 2 | 10 | 6 | 2 | 4 | 34% | 14701.6 | 57941.6 |  | Non-magnetic shielding to protect the TSu from primary beam loses.
1.4.4.2.3.2.8 | Cosmic Ray Zinc | 0 | 161000 | 0 | 161000 | 0 | 0 | 0 | 0 | 0 | 120 | 12120 | 173120 | 4 | 2 | 10 | 6 | 2 | 4 | 34% | 58860.8 | 231980.8 |  | Non-magnetic shielding to close the downstream end of the DS.
1.4.4.2.3.2.9 | Cosmic Ray Heavy Conc Blk | 0 | 248400 | 0 | 248400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 248400 | 1 | 2 | 15 | 4 | 2 | 4 | 29% | 72036 | 320436 |  | New (non-activated) sidewall shielding to enclose the DS.
1.4.4.2.3.2.10 | Cosmic Ray Hvy Conc Beams | 0 | 226700 | 0 | 226700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226700 | 1 | 2 | 15 | 4 | 2 | 4 | 29% | 65743 | 292443 |  | New (non-activated) roof shielding to enclose the DS.
1.4.4.2.3.3 | Power Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | AC to DC power supplies for beamline magnets.
1.4.4.2.3.3.1 | AC Power Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | AC power distribution from sub-stations to disconnect switches for magnet power supplies.
1.4.4.2.3.3.1.1 | Refurbish 6 ea Royals |  | 90000 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 23400 | 113400 |  | Refurbishment of existing AC disconnect switches (Royals) by an outside vendor.
1.4.4.2.3.3.1.2 | Disconnect & Reconnect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 6436.8 | 6436.8 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 1673.568 | 8110.368
1.4.4.2.3.3.1.3 | Rig Royals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 4827.6 | 4827.6 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 1255.176 | 6082.776
1.4.4.2.3.3.2 | PS Controls to PSI (19 supplies) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Updating power supply controls from Datacon to PSI and adding PLC interlock control.
1.4.4.2.3.3.2.1 | Engineering | 0 | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 12758.5 | 12758.5 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 2551.7 | 15310.2
1.4.4.2.3.3.2.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 8550 | 8550 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 1710 | 10260
1.4.4.2.3.3.2.3 | Materials | 32775 | 41230 | 0 | 74005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74005 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 14801 | 88806
1.4.4.2.3.3.2.4 | Modifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3952 | 0 | 0 | 207480 | 207480 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 41496 | 248976
1.4.4.2.3.3.2.5 | Fabricate Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 9595 | 9595 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 1919 | 11514
1.4.4.2.3.3.2.6 | Rigging | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 3821.85 | 3821.85 | 3 | 2 | 8 | 1 | 2 | 4 | 20% | 764.37 | 4586.22
1.4.4.2.3.3.3 | Refurbish Power Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Checking power supply internal parts and cleaning, tightening, repairing & replacing as necessary.
1.4.4.2.3.3.3.1 | Refurbish PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | 0 | 19950 | 19950 | 2 | 2 | 10 | 4 | 2 | 2 | 24% | 4788 | 24738
1.4.4.2.3.3.3.2 | PS Materials | 19000 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 2 | 2 | 10 | 4 | 2 | 2 | 24% | 4560 | 23560
1.4.4.2.3.3.4 | Magnet Monitor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | PLC for monitoring magnet and miscellaneous interlocks, includes assembly & programming but not connections to magnets.
1.4.4.2.3.3.4.1 | Engineering | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 3223.2 | 3223.2 | 2 | 2 | 10 | 4 | 1 | 2 | 20% | 644.64 | 3867.84
1.4.4.2.3.3.4.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 2 | 2 | 10 | 4 | 1 | 2 | 20% | 900 | 5400
1.4.4.2.3.3.4.3 | Hardware | 15200 | 0 | 0 | 15200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15200 | 2 | 2 | 10 | 4 | 1 | 2 | 20% | 3040 | 18240
1.4.4.2.3.3.4.4 | Programming | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 10500 | 10500 | 2 | 2 | 10 | 4 | 1 | 2 | 20% | 2100 | 12600
1.4.4.2.3.3.4.5 | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 6300 | 6300 | 2 | 2 | 10 | 4 | 1 | 2 | 20% | 1260 | 7560
1.4.4.2.3.4 | Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Beamline magnets for focusing, bending & pitching the beam.
1.4.4.2.3.4.1 | Refurbish Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Refurbish existing magnets in preparation for installation in the beamline.
1.4.4.2.3.4.1.1 | Refurbish Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2240 | 0 | 0 | 117600 | 117600 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 23520 | 141120
1.4.4.2.3.4.1.2 | Misc Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 11312 | 11312 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 2262.4 | 13574.4
1.4.4.2.3.4.1.3 | Rig Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 11264.4 | 11264.4 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 2252.88 | 13517.28
1.4.4.2.3.4.1.4 | Magnet Materials | 14000 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 2800 | 16800
1.4.4.2.3.4.1.5 | Pre-Survey Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 5880 | 5880 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1176 | 7056
1.4.4.2.3.4.2 | Pole Tip Vacuum Boxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Vacuum boxes with magnet steel pole tips for AD4 & AD5 (18D72's) to achieve the required bend from the magnets.
1.4.4.2.3.4.2.1 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.2.1.1 | Magnetic Design | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 2151.6 | 2151.6 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 473.352 | 2624.952
1.4.4.2.3.4.2.1.2 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 590.92 | 3276.92
1.4.4.2.3.4.2.1.3 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 990 | 5490
1.4.4.2.3.4.2.2 | Fabrication & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.2.2.1 | Fab Vacuum Box Pieces | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 240 | 24240 | 25240 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 5552.8 | 30792.8
1.4.4.2.3.4.2.2.2 | Weld Assembly | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 160 | 16160 | 16360 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 3599.2 | 19959.2
1.4.4.2.3.4.2.2.3 | Fab Shims | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 80 | 8080 | 8580 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1887.6 | 10467.6
1.4.4.2.3.4.2.2.4 | Leak Check Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.2.2.5 | Rigging | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 536.4 | 536.4 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 118.008 | 654.408
1.4.4.2.3.4.3 | New Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | New magnets to be made where existing CA magnets do meet meet requirements.
1.4.4.2.3.4.3.1 | AP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Pitching magnet for final alignment on the Production Target. Integral field of 4kG-M.
1.4.4.2.3.4.3.1.1 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.1.1.1 | Magnetic Design | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 3586 | 3586 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 788.92 | 4374.92
1.4.4.2.3.4.3.1.1.2 | Engineering | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 5372 | 5372 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1181.84 | 6553.84
1.4.4.2.3.4.3.1.1.3 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 6750 | 6750 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1485 | 8235
1.4.4.2.3.4.3.1.2 | Fabrication & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.1.2.1 | Fab Core | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 120 | 12120 | 15120 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 4233.6 | 19353.6
1.4.4.2.3.4.3.1.2.2 | Fab Stand | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 40 | 4040 | 4540 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 1271.2 | 5811.2
1.4.4.2.3.4.3.1.2.3 | Fab Coil Tooling | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 40 | 4040 | 4540 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 1271.2 | 5811.2
1.4.4.2.3.4.3.1.2.4 | Fab Coils | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 10400 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 2912 | 13312
1.4.4.2.3.4.3.1.3 | Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.1.3.1 | Assemble Magnet | 800 | 0 | 0 | 800 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 9200 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 2024 | 11224
1.4.4.2.3.4.3.1.3.2 | Pre-Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.3.1.3.3 | Wire Magnet | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1880 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 413.6 | 2293.6
1.4.4.2.3.4.3.1.3.4 | Rig Magnet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 536.4 | 536.4 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 118.008 | 654.408
1.4.4.2.3.4.3.1.4 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.1.4.1 | Rig Magnet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 536.4 | 536.4 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 118.008 | 654.408
1.4.4.2.3.4.3.1.4.2 | Hook-up Magnet Power | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.3.1.4.3 | Hook-up Magnet Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 420 | 420 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 92.4 | 512.4
1.4.4.2.3.4.3.1.4.4 | Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.3.1.4.5 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 2151.6 | 2151.6 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 473.352 | 2624.952
1.4.4.2.3.4.3.1.4.6 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 1260 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 277.2 | 1537.2
1.4.4.2.3.4.3.2 | AP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Pitching magnet for final alignment on the Production Target. Integral field of 8kG-M.
1.4.4.2.3.4.3.2.1 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.2.1.1 | Magnetic Design | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 3586 | 3586 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 788.92 | 4374.92
1.4.4.2.3.4.3.2.1.2 | Engineering | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 5372 | 5372 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1181.84 | 6553.84
1.4.4.2.3.4.3.2.1.3 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 6750 | 6750 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1485 | 8235
1.4.4.2.3.4.3.2.2 | Fabrication & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.2.2.1 | Fab Core | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 120 | 12120 | 15120 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 4233.6 | 19353.6
1.4.4.2.3.4.3.2.2.2 | Fab Stand | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 40 | 4040 | 4540 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 1271.2 | 5811.2
1.4.4.2.3.4.3.2.2.3 | Fab Coil Tooling | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 40 | 4040 | 4540 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 1271.2 | 5811.2
1.4.4.2.3.4.3.2.2.4 | Fab Coils | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 10400 | 2 | 2 | 10 | 10 | 1 | 4 | 28% | 2912 | 13312
1.4.4.2.3.4.3.2.3 | Assembly and Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.2.3.1 | Assemble Magnet | 800 | 0 | 0 | 800 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 9200 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 2024 | 11224
1.4.4.2.3.4.3.2.3.2 | Pre-Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.3.2.3.3 | Wire Magnet | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1880 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 413.6 | 2293.6
1.4.4.2.3.4.3.2.3.4 | Rig Magnet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 536.4 | 536.4 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 118.008 | 654.408
1.4.4.2.3.4.3.2.4 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.4.3.2.4.1 | Rig Magnet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 536.4 | 536.4 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 118.008 | 654.408
1.4.4.2.3.4.3.2.4.2 | Hook-up Magnet Power | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.3.2.4.3 | Hook-up Magnet Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 420 | 420 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 92.4 | 512.4
1.4.4.2.3.4.3.2.4.4 | Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 184.8 | 1024.8
1.4.4.2.3.4.3.2.4.5 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 2151.6 | 2151.6 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 473.352 | 2624.952
1.4.4.2.3.4.3.2.4.6 | Magnet Measurements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 1260 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 277.2 | 1537.2
1.4.4.2.3.5 | Vacuum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Encloses primary proton beam from the Switchyard to the PS. Also includes PS downstream vacuum closure and Helium Box to beam dump.
1.4.4.2.3.5.1 | RFMM Vacuum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Vacuum through RFMM, 10**-6 Torr.
1.4.4.2.3.5.1.1 | Vacuum Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.1.1.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 590.92 | 3276.92
1.4.4.2.3.5.1.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 6750 | 6750 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1485 | 8235
1.4.4.2.3.5.1.2 | Vacuum Inst & Controls Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.1.2.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 590.92 | 3276.92
1.4.4.2.3.5.1.2.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 990 | 5490
1.4.4.2.3.5.1.3 | Vacuum - Fabrication & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.1.3.1 | Purchase | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 5500 | 30500
1.4.4.2.3.5.1.3.2 | Fabrications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 8080 | 8080 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1777.6 | 9857.6
1.4.4.2.3.5.1.4 | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.1.4.1 | Mechanical Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 2100 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 462 | 2562
1.4.4.2.3.5.1.4.2 | Welding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 808 | 808 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 177.76 | 985.76
1.4.4.2.3.5.1.4.3 | Electrical Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1680 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 369.6 | 2049.6
1.4.4.2.3.5.2 | Beamline Vacuum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 10**-2 Torr.
1.4.4.2.3.5.2.1 | Vacuum Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.2.1.1 | Engineering | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 8058 | 8058 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1772.76 | 9830.76
1.4.4.2.3.5.2.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 13500 | 13500 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 2970 | 16470
1.4.4.2.3.5.2.2 | Vacuum Inst & Controls Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.2.2.1 | Engineering | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 5372 | 5372 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1181.84 | 6553.84
1.4.4.2.3.5.2.2.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 9000 | 9000 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1980 | 10980
1.4.4.2.3.5.2.3 | Vacuum - Fab & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.2.3.1 | Purchase | 40000 | 50000 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 19800 | 109800
1.4.4.2.3.5.2.3.2 | Fabrications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 16160 | 16160 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 3555.2 | 19715.2
1.4.4.2.3.5.2.4 | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.2.4.1 | Mechanical Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 8400 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1848 | 10248
1.4.4.2.3.5.2.4.2 | Welding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 8080 | 8080 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 1777.6 | 9857.6
1.4.4.2.3.5.2.4.3 | Electrical Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 4200 | 4200 | 2 | 2 | 10 | 4 | 1 | 4 | 22% | 924 | 5124
1.4.4.2.3.5.3 | PS Vacuum End Cap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Closes downstream end of DS warm bore. With provisions for proton beam exit, beam instrumentation and target replacement.
1.4.4.2.3.5.3.1 | Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.3.1.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 725.22 | 3411.22
1.4.4.2.3.5.3.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 1215 | 5715
1.4.4.2.3.5.3.2 | Fabrication & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.3.2.1 | Purchase | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 1350 | 6350
1.4.4.2.3.5.3.2.2 | Fabrications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 24240 | 24240 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 6544.8 | 30784.8
1.4.4.2.3.5.4 | PS to Dump Helium Box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.4.1 | Mechanical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.2.3.5.4.1.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 725.22 | 3411.22
1.4.4.2.3.5.4.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 1215 | 5715
1.4.4.2.3.5.4.2 | Vacuum - Fab & Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1.4.4.2.3.5.4.2.1 | Purchase | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 540 | 2540
1.4.4.2.3.5.4.2.2 | Fabrications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 12120 | 12120 | 2 | 2 | 15 | 4 | 1 | 4 | 27% | 3272.4 | 15392.4
1.4.4.2.3.6 | Cooling Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Beamline magnet cooling water.
1.4.4.2.3.6.1 | Install Manifold Stations | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 240 | 0 | 0 | 12600 | 15600 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3120 | 18720
1.4.4.2.3.7 | Beamline Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installing shielding and beamline on experimental floor.
1.4.4.2.3.7.1 | Shielding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installation of shielding for proton beam and solenoid magnets.
1.4.4.2.3.7.1.1 | Build for Beam Tests | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Initial installation with a temporary beam stop to allow RFMM beam tests while the solenoid magnets are being installed.
1.4.4.2.3.7.1.1.1 | Rebuild Side Walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 80460 | 80460 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 16092 | 96552
1.4.4.2.3.7.1.1.2 | Rebuild Roof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120 | 0 | 75096 | 75096 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 15019.2 | 90115.2
1.4.4.2.3.7.1.1.3 | Build beam Dump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 24138 | 24138 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4827.6 | 28965.6
1.4.4.2.3.7.1.1.4 | Steel modifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 36360 | 36360 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 7272 | 43632
1.4.4.2.3.7.1.1.5 | Drill tap steel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 8080 | 8080 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1616 | 9696
1.4.4.2.3.7.1.2 | Build Final Layout | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Final shielding installation with solenoid magnets installed.
1.4.4.2.3.7.1.2.1 | Remove Temp Dump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 0 | 15019.2 | 15019.2 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3003.84 | 18023.04
1.4.4.2.3.7.1.2.2 | Remove Roof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 18774 | 18774 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3754.8 | 22528.8
1.4.4.2.3.7.1.2.3 | Modify Side Wall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 32184 | 32184 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 6436.8 | 38620.8
1.4.4.2.3.7.1.2.4 | Replace Roof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 21456 | 21456 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4291.2 | 25747.2
1.4.4.2.3.7.1.2.5 | Re-Install Beam Dump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 21456 | 21456 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4291.2 | 25747.2
1.4.4.2.3.7.1.2.6 | Install Cosmic Ray Shield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 0 | 42912 | 42912 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 8582.4 | 51494.4
1.4.4.2.3.7.1.3 | Seismic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installation of anchors to restrain shield blocks during a seismic event.
1.4.4.2.3.7.1.3.1 | Brackets | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 2 | 2 | 10 | 10 | 2 | 2 | 36% | 7200 | 27200
1.4.4.2.3.7.1.3.2 | Anchor Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 53640 | 53640 | 2 | 2 | 10 | 10 | 2 | 2 | 36% | 19310.4 | 72950.4
1.4.4.2.3.7.1.4 | Seal Floor | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 2 | 2 | 10 | 10 | 2 | 2 | 36% | 7200 | 27200
1.4.4.2.3.7.2 | Electric & Tray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installation of utility and instrumentation tray in primary beam cave.
1.4.4.2.3.7.2.1 | New Cable Tray | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4000 | 24000
1.4.4.2.3.7.2.2 | Misc Lights & Power Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 53640 | 53640 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 10728 | 64368
1.4.4.2.3.7.3 | Installation & Hook-up of Power Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Providing platforms, placing power supplies and hooking up AC power from the disconnect switch.
1.4.4.2.3.7.3.1 | Modify PS Platforms | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 400 | 0 | 26820 | 41820 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 8364 | 50184
1.4.4.2.3.7.3.2 | AC 262MCM | 1000 | 8400 | 0 | 9400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9400 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1880 | 11280
1.4.4.2.3.7.3.3 | AC 535MCM | 500 | 7000 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1500 | 9000
1.4.4.2.3.7.3.4 | AC Cable Tray Installation | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 400 | 0 | 26820 | 36820 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 7364 | 44184
1.4.4.2.3.7.3.5 | Rig Power Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 12873.6 | 12873.6 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 2574.72 | 15448.32
1.4.4.2.3.7.3.6 | AC Cable Pull | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 15120 | 15120 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3024 | 18144
1.4.4.2.3.7.3.7 | AC Hook-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 15120 | 15120 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3024 | 18144
1.4.4.2.3.7.4 | Beam Line Layout | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Survey prior to the start of installation.
1.4.4.2.3.7.4.1 | Establish Survey Controls | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 80 | 0 | 0 | 4200 | 4700 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 940 | 5640
1.4.4.2.3.7.4.2 | Survey Layout of Beam | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 8400 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1680 | 10080
1.4.4.2.3.7.5 | Magnet Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Place magnets in beamline.
1.4.4.2.3.7.5.1 | Install New Magnets, etc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 19310.4 | 19310.4 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 3862.08 | 23172.48
1.4.4.2.3.7.5.2 | Survey Magnets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 0 | 0 | 22680 | 22680 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4536 | 27216
1.4.4.2.3.7.5.3 | Install Magnet Stands | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5664 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1132.8 | 6796.8
1.4.4.2.3.7.6 | Magnet DC Hook-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installation of DC power cables/ water cooled buss to magnets.
1.4.4.2.3.7.6.1 | DC 535MCM | 2000 | 48000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 10000 | 60000
1.4.4.2.3.7.6.2 | DC Tray Installation | 8000 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 640 | 0 | 42912 | 50912 | 1 | 2 | 10 | 10 | 1 | 4 | 26% | 13237.12 | 64149.12
1.4.4.2.3.7.6.3 | Magnet Hook-up | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 1584 | 0 | 0 | 83160 | 87160 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 17432 | 104592
1.4.4.2.3.7.7 | Magnet Monitor Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0 | 0 |  | Installation of PLC system for monitoring magnet temperatures and other miscellaneous alarms.
1.4.4.2.3.7.7.1 | Pull Magnet Monitor Cable | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 96 | 0 | 0 | 5040 | 20040 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 4008 | 24048
1.4.4.2.3.7.7.2 | Terminate Mag Mon Cables | 0 | 0 | 0 | 0 |  |  |  | 160 | 0 |  | 8400 | 8400 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 1680 | 10080
1.4.4.2.3.7.8 | Vacuum Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installation and check-out of beamline vacuum.
1.4.4.2.3.7.8.1 | Install Vacuum Stands | 300 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1909.2 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 381.84 | 2291.04
1.4.4.2.3.7.8.2 | Survey Vacuum Stands | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1680 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 336 | 2016
1.4.4.2.3.7.8.3 | Install Vacuum Pipe | 0 | 0 | 0 | 0 |  |  |  | 80 | 0 |  | 4200 | 4200 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 840 | 5040
1.4.4.2.3.7.8.4 | Weld Vacuum Pipe | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 808 | 808 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 161.6 | 969.6
1.4.4.2.3.7.8.5 | Leak Check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 168 | 1008
1.4.4.2.3.7.8.6 | Rig PS End Cap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 804.6 | 804.6 | 1 | 2 | 15 | 4 | 1 | 4 | 25% | 201.15 | 1005.75
1.4.4.2.3.7.8.7 | Install PS End Cap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1680 | 1 | 2 | 15 | 4 | 1 | 4 | 25% | 420 | 2100
1.4.4.2.3.7.8.8 | Install Helium Box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 1260 | 1 | 2 | 15 | 4 | 1 | 4 | 25% | 315 | 1575
1.4.4.2.3.7.9 | Run & Test Power Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Testing all power supply & magnet interlocks, and power supply operation (regulation , ripple, etc).
1.4.4.2.3.7.9.1 | Run & Test PS's | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576 | 0 | 0 | 30240 | 30240 | 1 | 2 | 10 | 4 | 1 | 4 | 20% | 6048 | 36288
1.4.4.2.3.8 | Safety & Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Installation of beamline safety systems and facilities.
1.4.4.2.3.8.1 | Oxygen Deficiency Hazard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Oxygen deficiency hazard protection due to large amounts of cryogenic Helium in the DS.
1.4.4.2.3.8.1.1 | ODH Classification | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 5372 | 5372 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 1504.16 | 6876.16
1.4.4.2.3.8.1.2 | ODH System Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 1260 | 5760
1.4.4.2.3.8.1.3 | ODH - Materials | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 1400 | 6400
1.4.4.2.3.8.1.4 | ODH - Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 12600 | 12600 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 3528 | 16128
1.4.4.2.3.8.1.5 | ODH - Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5364 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 1501.92 | 6865.92
1.4.4.2.3.8.1.6 | Install Exhaust Fans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 10728 | 10728 | 1 | 2 | 10 | 6 | 2 | 4 | 28% | 3003.84 | 13731.84
1.4.4.2.3.8.2 | Dehumidification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Dehumidification of primary beamline to increase reliability of beamline components.
1.4.4.2.3.8.2.1 | Dehumid Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 10 | 6 | 2 | 2 | 28% | 752.08 | 3438.08
1.4.4.2.3.8.2.2 | Dehumid Design | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 2250 | 2250 | 2 | 2 | 10 | 6 | 2 | 2 | 28% | 630 | 2880
1.4.4.2.3.8.2.3 | Dehumid Procurement | 40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 2 | 2 | 10 | 6 | 2 | 2 | 28% | 11200 | 51200
1.4.4.2.3.8.2.4 | Dehumid Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 10728 | 10728 | 2 | 2 | 10 | 6 | 2 | 2 | 28% | 3003.84 | 13731.84
1.4.4.2.3.8.3 | Fire Detection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Primary beamline fire detection system.
1.4.4.2.3.8.3.1 | Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5364 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 1287.36 | 6651.36
1.4.4.2.3.8.3.2 | Materials | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 1200 | 6200
1.4.4.2.3.8.3.3 | Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 10728 | 10728 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 2574.72 | 13302.72
1.4.4.2.3.8.4 | Roof Repair | 40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 1 | 2 | 10 | 4 | 2 | 4 | 24% | 9600 | 49600
1.4.4.2.3.8.5 | Controls Hut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Air-conditioned space for beamline controls and instrumentation. Cost split with KOPIO.
1.4.4.2.3.8.5.1 | Install Controls Hut | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 12 | 0 | 804.6 | 10804.6 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 2593.104 | 13397.704
1.4.4.2.3.8.5.2 | Install Controls Hut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 7241.4 | 7241.4 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 1737.936 | 8979.336
1.4.4.2.3.8.5.3 | Controls Hut Fire Alarm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1341 | 1341 | 2 | 2 | 8 | 4 | 2 | 4 | 24% | 321.84 | 1662.84
1.4.4.2.3.8.6 | RFMM Hut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Air-conditioned space for RFMM controls.
1.4.4.2.3.8.6.1 | Install RFMM Hut | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 21609.2 | 2 | 2 | 15 | 4 | 2 | 4 | 31% | 6698.852 | 28308.052
1.4.4.2.3.8.6.2 | Install RFMM Hut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | 14482.8 | 14482.8 | 2 | 2 | 15 | 4 | 2 | 4 | 31% | 4489.668 | 18972.468
1.4.4.2.3.8.6.3 | RFMM Hut Fire Alarm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 2682 | 2682 | 2 | 2 | 15 | 4 | 2 | 4 | 31% | 831.42 | 3513.42
1.4.4.3 | Instrumentation |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.3.1 | Project Support |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 955109.36
| Project Support |  |  |  | 0 | 240 | 120 | 80 |  |  |  | 31374 | 31374 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 4392.36 | 35766.36
| Installation supervision |  |  |  | 0 |  |  |  | 440 |  |  | 23100 | 23100 | 1 | 2 | 4 | 4 | 1 | 4 | 14% | 3234 | 26334
1.4.4.3.2 | A Transport Devices |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.3.2.1 | SWIC's |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| SWIC's (4 locations) |  |  |  | 0 | 240 | 40 |  | 400 |  |  | 40702 | 40702 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 6512.32 | 47214.32 |  | Segmented Wire Ionization Chamber (SWIC). Semi-destructive measurement of H & V beam profiles.
| Plunging Vac SWIC (32x32) (4" pipe) | 120000 |  |  | 120000 | [6 empty] | 0 | 120000 | 3 | 2 | 8 | 4 | 2 | 8 | 30% | 36000 | 156000 |  | Horizontal & vertical array of 32 wires sandwiched between high volatge planes, with gas flowing thru chamber. Remote control plunging capability.
| SWIC Electronics (32x32) | 40000 | 50000 |  | 90000 | [6 empty] | 0 | 90000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 14400 | 104400 |  | Eight - 8 channel integrator eurocard modules in a Eurocrate with additional control & multiplexer modules.
| Servo SWIC (32x32) (Air) | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600 |  | Modified standard SWIC, signals from wires ganged such that beam position offset can be determined.
| Servo electronics | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 4 | 2 | 2 | 8 | 18% | 360 | 2360 |  | Signal processing electronics which provide reference for upstream steering dipole.
| Bias | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 2 | 1 | 1 | 8 | 13% | 780 | 6780 |  | High Voltage power supply with full remote control
| Cables/connectors | 4000 |  |  | 4000 | [6 empty] | 0 | 4000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 560 | 4560
| Gas Distribution (Argon-C02) | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 2 | 1 | 2 | 8 | 14% | 280 | 2280
1.4.4.3.2.2 | Current Transformers |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Non-destructive beam current measurement via a toroidal transformer & specialized signal processing electronics.
| Bergoz | 10000 | 60000 |  | 70000 | 240 | 40 |  | 240 |  |  | 32302 | 102302 | 1 | 2 | 10 | 4 | 2 | 8 | 28% | 28644.56 | 130946.56
1.4.4.3.2.3 | Beam Position Monitors |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Non-destructiove center of mass position measurement via E-M induced signal from bunched beam.
| Includes BPM, cables, electronics | 75000 |  |  | 75000 | 400 |  | 120 | 650 |  | 40 | 71775 | 146775 | 6 | 4 | 8 | 4 | 2 | 4 | 44% | 64581 | 211356
1.4.4.3.2.4 | Loss Monitors (various locations) |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Loss Monitors w/ mounts | 16000 |  |  | 16000 | 160 |  |  | 320 |  |  | 27544 | 43544 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 6967.04 | 50511.04 |  | Calibrated Ionization chambers generate current signal proportional to beam loss.
| Loss monitor Electronics |  |  |  | 0 | [6 empty] | 0 | 0 | 1 | 2 | 4 | 4 | 2 | 8 | 22% | 0 | 0 |  | VME based electronics which process the signal from the ionization loss monitors.
| HV Bias | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 720 | 6720 |  | High Voltage power supply with full remote control
| RHIC Style VME | 5000 | 10000 |  | 15000 | [6 empty] | 0 | 15000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 2400 | 17400 |  | Standard VME chassis modified with linear dc power supplies to reduce noise.
| Cables (Sig and HV) | 1600 |  |  | 1600 | [6 empty] | 0 | 1600 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 256 | 1856
| Interface to machine protect system | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 8 | 1 | 2 | 8 | 20% | 1000 | 6000
1.4.4.3.3 | Target Instrumentation |  |  |  | 0 | 240 |  | 120 | 480 |  | 40 | 52106 | 52106 | 1 | 2 | 4 | 4 | 2 | 4 | 18% | 9379.08 | 61485.08
1.4.4.3.3.1 | Pin Diodes |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Solid state device that detects direction specific single passes of minimum ionizing particles.
| Pin Diodes & Mounts | 10000 |  |  | 10000 | [6 empty] | 0 | 10000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 1600 | 11600 |  | Used to measure secondaries from beam interaction with beampipe and target.
| Control Chassis & DCps | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 320 | 2320 |  | DC power for pin diode system, and test mode control.
| SIS scalar | 1500 |  |  | 1500 | [6 empty] | 0 | 1500 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 180 | 1680 |  | VME based TTL counter 200mHz, 16ch, 32 bits.
| Cables & Connectors | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 160 | 1160
1.4.4.3.3.2 | 90 Degree Telescope |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Three Scintillator/PMT assemblies mounted in array so only secondaries from target will pass through all three.
| Detector - PMT/Base/Scint/mount | 4500 |  |  | 4500 | [6 empty] | 0 | 4500 | 4 | 2 | 4 | 2 | 2 | 8 | 24% | 1080 | 5580 |  | Electron Tubes Photo-multiplier, BNL designed voltage divider base, plastic scintillator from Saint-Gobain.
| HV Bias | 5000 |  |  | 5000 | [6 empty] | 0 | 5000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 600 | 5600 |  | High Voltage power supply with full remote control
| Phillips counting electronics | 6000 |  |  | 6000 | [6 empty] | 0 | 6000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 720 | 6720 |  | Standard NIM amplifiers, discriminators, majority logic, & level translators to provide signal when coincident partical passes through all 3 detectors.
| SIS Scalar counter | 2000 |  |  | 2000 | [6 empty] | 0 | 2000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 240 | 2240 |  | VME based TTL counter 200mHz, 16ch, 32 bits.
| NIM chassis | 3000 |  |  | 3000 | [6 empty] | 0 | 3000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 360 | 3360 |  | Standard 19" rack mount chassis to house signal processing electronics.
| Cables & Connectors | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 160 | 1160
1.4.4.3.3.3 | Flags & Video |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Thin phosphor (AlOx-Cr) screen placed in the beam path which illuminates when beam passes through.
| Camera Pan, remote cntrl | 2500 |  |  | 2500 | [6 empty] | 0 | 2500 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 400 | 2900
| Flag & holder & mount | 1500 |  |  | 1500 | [6 empty] | 0 | 1500 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 240 | 1740
| Video Camera | 20000 |  |  | 20000 | [6 empty] | 0 | 20000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 3200 | 23200
| ND Filter Assy & Controls | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 0 | 1 | 2 | 8 | 12% | 120 | 1120 |  | Neutral density (ND) filters are used to avoid saturating video camera, extend dynamic range.
| Lens & Lamps | 1000 |  |  | 1000 | [6 empty] | 0 | 1000 | 1 | 2 | 4 | 1 | 2 | 8 | 16% | 160 | 1160
1.4.4.4 | A-Line Security modifications |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 0 | 0 | 263748.62 | Personnel Access System to beam caves.
1.4.4.4.1 | Installation Supervision |  |  |  | 0 |  |  |  | 140 |  |  | 7350 | 7350 | 2 | 2 | 3 | 1 | 1 | 2 | 10% | 735 | 8085
1.4.4.4.2 | PLC Systems |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | PLC will be located in 911A cage. Some modules will resides locally.
| Programming | 0 |  |  | 0 | 320 |  | 0 | 0 | 0 | 0 | 21488 | 21488 | 2 | 2 | 3 | 4 | 2 | 8 | 23% | 4942.24 | 26430.24 |  | Software programs written in Allen Bradley native ladder logic development system by two independent programmers.
| PLC & Racks | 8000 |  |  | 8000 | 32 |  | 40 | 320 | 16 | 0 | 22271.6 | 30271.6 | 2 | 2 | 3 | 4 | 2 | 8 | 23% | 6962.468 | 37234.068 |  | Allen Bradley processors of difference architecture (PLC5 and SLC)
| I/O modules | 6300 |  |  | 6300 | 16 |  | 0 | 40 | 0 | 0 | 3174.4 | 9474.4 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1800.136 | 11274.536 |  | Allen Bradley local plug-in I/O units (16 inputs/outputs).
| R/IO Blocks | 8000 |  |  | 8000 |  |  | 0 | 40 | 0 | 0 | 2100 | 10100 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1919 | 12019 |  | Allen Bradley Remote I/O blocks(16 I/O)
| UPS and Phoenix connectors | 4000 |  |  | 4000 |  |  | 0 | 40 | 40 | 0 | 4782 | 8782 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1668.58 | 10450.58 |  | Best 3KVA online UPS and pheonix connectors.
| Fiber converters (R/IO & DH+ comm)(6) | 4800 |  |  | 4800 | 16 |  | 0 | 40 | 0 | 0 | 3174.4 | 7974.4 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 1515.136 | 9489.536 |  | Pheonix Fiber converter module for remote I/O and DH+ communication.
1.4.4.4.3 | Gates (Incl. 3 gates) |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Gates Boxes | 1800 |  |  | 1800 | 40 |  | 40 | 320 | 0 |  | 21736 | 23536 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 3530.4 | 27066.4 |  | Standard PASS style gates boxes with gate/area status information and access control key switches.
| Limit switches (10) | 600 |  |  | 600 |  |  | 0 | 40 | 0 |  | 2100 | 2700 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 405 | 3105 |  | Standard Onron 24VDC limit switches used in all ACS systems.
| Electric strikes (2) | 240 |  |  | 240 |  |  | 0 | 40 | 0 |  | 2100 | 2340 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 351 | 2691 |  | Standard 24VDC electric strike lock with status information used in all ACS systems.
| Card Readers (2) | 400 | 0 |  | 400 | 8 |  | 0 | 40 | 0 | 0 | 2637.2 | 3037.2 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 455.58 | 3492.78 |  | Secura Key Entracomp card readers compatible with C-AD PASS access cards.
| Key Tree & Iris Scanner | 9000 |  |  | 9000 |  |  |  | 40 | 40 |  | 4782 | 13782 | 2 | 2 | 3 | 4 | 1 | 4 | 15% | 2067.3 | 15849.3 |  | LG Iris Scanners for training verification and Castell industrial style key system with key capture monitoring.
1.4.4.4.4 | Cables |  |  |  | 0 |  |  |  | 80 | 40 | 0 | 6882 | 6882 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 894.66 | 7776.66 |  | All data cables are 18 gauge twisted pair types. The powers cables are 24VDC rated with low loss.
| Cables 18/c (3000ft) | 1500 |  |  | 1500 | 0 |  |  | 0 |  | 0 | 0 | 1500 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 195 | 1695
| Cables 12/c (3000ft) | 1500 |  |  | 1500 | 0 |  | 0 | 0 |  |  | 0 | 1500 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 195 | 1695
| Cables 8/c (3000ft) | 1350 |  |  | 1350 | 0 |  |  | 0 |  | 0 | 0 | 1350 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 175.5 | 1525.5
| Cables 4/c (3000ft) | 1050 | 0 |  | 1050 | 0 |  | 0 |  |  |  | 0 | 1050 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 136.5 | 1186.5
| Crash cables (1000ft) | 750 | 0 |  | 750 | 0 |  | 0 |  |  |  | 0 | 750 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 97.5 | 847.5
| DH+ Comm cables (1000ft) | 450 | 0 |  | 450 | 0 |  | 0 |  |  |  | 0 | 450 | 1 | 2 | 3 | 4 | 1 | 4 | 13% | 58.5 | 508.5 |  | These are three conductor cables used in Allen Bradley system for communication.
1.4.4.4.5 | CATV |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Bobcat switch 16*2 mux (2) | 1200 |  |  | 1200 | 40 |  | 24 | 80 | 0 |  | 8236 | 9436 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 1604.12 | 11040.12 |  | Video multiplexers use in routing gate camera video, used during controlled access, to MCR.
| Lee Data 1*1 Fiber Optics Transmitter (2) | 500 |  |  | 500 |  |  |  | 40 | 0 |  | 2100 | 2600 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 442 | 3042 |  | Fiber converter modules use for PLC communication.
| Lee Data 1*1 Fiber Optics Receiver (2) | 500 |  |  | 500 |  |  |  | 40 | 0 |  | 2100 | 2600 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 442 | 3042 |  | Fiber converter modules use for PLC communication.
| Digital Cameras (6) | 1800 | 0 |  | 1800 |  |  |  | 40 | 0 |  | 2100 | 3900 | 1 | 2 | 3 | 4 | 2 | 4 | 17% | 663 | 4563 |  | Cameras for video system use during controlled access in beam enclosures.
1.4.4.4.6 | Chipmunks |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 |  | Will use existing chipmunks and DAQ hardware. If required additional units purchase later.
| Chipmunks (2 units) | 10000 |  |  | 10000 |  |  |  | 40 | 0 |  | 2100 | 12100 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 2299 | 14399
| VME SIS Scaler board | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0% | 0 | 0
| Weather proof enclusure | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | 0% | 0 | 0
| Coaxial cables (1000 ft) | 500 |  |  | 500 |  |  |  | 40 | 0 |  | 2100 | 2600 | 2 | 2 | 3 | 4 | 2 | 4 | 19% | 494 | 3094
1.4.4.4.7 | Crash, Sweep & Alarms |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Check station boxes | 300 |  |  | 300 | 80 |  | 40 | 160 | 0 |  | 16022 | 16322 | 2 | 2 | 4 | 4 | 2 | 4 | 20% | 3264.4 | 19586.4 |  | Custom hardware use for securing area of personnel prior to beam and showing sweep status information.
| Crash Actuators | 500 |  |  | 500 |  |  |  | 160 | 0 |  | 8400 | 8900 | 2 | 2 | 4 | 4 | 2 | 4 | 20% | 1780 | 10680 |  | Industrial style switches with wire pull plunges and reset arm.
| Crash Stations and Alarms | 1500 |  |  | 1500 |  |  |  | 160 | 0 |  | 8400 | 9900 | 2 | 2 | 4 | 4 | 2 | 4 | 20% | 1980 | 11880 |  | Custom hardware which shows crash and alarm status.
| Safety & Facilities |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
1.4.4.5 | Controls |  |  |  | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0 | 227698.736
| Instrumentation Interface Hardware | 30560 | 58810 |  | 89370 | 110 |  |  | 160 | 0 |  | 15786.5 | 105156.5 | 2 | 2 | 8 | 4 | 1 | 8 | 24% | 25237.56 | 130394.06 |  | Scope set by instrumentation needs
| Instrumentation Software & DB |  |  |  | 0 | 420 | [5 empty] | 28203 | 28203 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 7896.84 | 36099.84
| Power Supply Interface Hardware | 10080 | 24000 |  | 34080 | 80 |  |  | 130 | 16 |  | 13269.8 | 47349.8 | 1 | 2 | 8 | 4 | 1 | 8 | 22% | 10416.956 | 57766.756 |  | Need to replace obsolete Datacon controls
| Power Supply Software & DB |  |  |  | 0 | 40 | [5 empty] | 2686 | 2686 | 2 | 2 | 15 | 1 | 1 | 8 | 28% | 752.08 | 3438.08
1.4.4.6 | MECO Experiment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1738818.854 | Items of CA Responsibility for MECO Experiment.
1.4.4.6.1 | Target Systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | The Production Target and it's mounting, handling, storage and cooling.
1.4.4.6.1.1 | Production Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | The primary proton beam target and it's cooling (cooling at the target only, not the cooling system).
1.4.4.6.1.1.1 | Verify Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.1.1.1.1 | Engineering Design | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 1181.84 | 3867.84
1.4.4.6.1.1.1.2 | Finite Element Analysis | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 5372 | 5372 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 2363.68 | 7735.68
1.4.4.6.1.1.1.3 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 4500 | 4500 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 1980 | 6480
1.4.4.6.1.1.2 | Target tests in A-Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Target tests with the proton beam.
1.4.4.6.1.1.2.1 | Fab Test Beam Target | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 80 | 8080 | 9080 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 3995.2 | 13075.2
1.4.4.6.1.1.2.2 | Assemble Beam Test Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 1260 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 554.4 | 1814.4
1.4.4.6.1.1.2.3 | Install Test Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.1.1.2.3.1 | Install Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 1260 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 554.4 | 1814.4
1.4.4.6.1.1.2.3.2 | Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 369.6 | 1209.6
1.4.4.6.1.1.2.4 | Evaluate Tests & Adjust Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Based on results from target beam test, reevaluate target design as necessary.
1.4.4.6.1.1.2.4.1 | Finite Element Analysis | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 2148.8 | 2148.8 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 945.472 | 3094.272
1.4.4.6.1.1.2.4.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 900 | 900 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 396 | 1296
1.4.4.6.1.1.3 | Fabricate Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Fabrication of final Target (does not include a spare Target).
1.4.4.6.1.1.3.1 | Fab Target & Housing | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 80 | 8080 | 10080 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 4435.2 | 14515.2
1.4.4.6.1.1.3.2 | Assemble Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 2100 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 924 | 3024
1.4.4.6.1.1.3.3 | Survey Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 1260 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 554.4 | 1814.4
1.4.4.6.1.1.3.4 | Bench Test Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 369.6 | 1209.6
1.4.4.6.1.2 | Mounting, Handling & Storage System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | System for positioning, installing, removing and storing the production target.
1.4.4.6.1.2.1 | Interface with Heat & Rad Shield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Design of the interface of the target mounting system with the Heat and Radiation Shield.
1.4.4.6.1.2.1.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 1181.84 | 3867.84
1.4.4.6.1.2.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 2250 | 2250 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 990 | 3240
1.4.4.6.1.2.2 | Target Trolley & Motion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Design and test of a "trolley" and drive system for installing and removing the target.
1.4.4.6.1.2.2.1 | Engineering | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 8058 | 8058 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 3545.52 | 11603.52
1.4.4.6.1.2.2.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 6750 | 6750 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 2970 | 9720
1.4.4.6.1.2.2.3 | Motion Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Test of trolley and motion system.
1.4.4.6.1.2.2.3.1 | Fab Set-up | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 40 | 4040 | 4540 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 1997.6 | 6537.6
1.4.4.6.1.2.2.3.2 | Fab Set-up | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 80 | 0 | 0 | 4200 | 4700 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 2068 | 6768
1.4.4.6.1.2.2.3.3 | Fab Set-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 2100 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 924 | 3024
1.4.4.6.1.2.2.3.4 | Test Motion | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1611.6 | 1611.6 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 709.104 | 2320.704
1.4.4.6.1.2.2.3.5 | Survey Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 840 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 369.6 | 1209.6
1.4.4.6.1.2.3 | Target Storage System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Design and fabrication of a storage pig for used targets.
1.4.4.6.1.2.3.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 1181.84 | 3867.84
1.4.4.6.1.2.3.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 2250 | 2250 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 990 | 3240
1.4.4.6.1.2.3.3 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.1.2.3.3.1 | Central Shops | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 120 | 12120 | 17120 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 7532.8 | 24652.8
1.4.4.6.1.2.3.3.2 | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 2100 | 10 | 2 | 8 | 6 | 2 | 4 | 44% | 924 | 3024
1.4.4.6.1.3 | Target Cooling System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | System to provide cooling water for the Target and Heat & Radiation Shield.
1.4.4.6.1.3.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 590.92 | 3276.92
1.4.4.6.1.3.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 8100 | 8100 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 1782 | 9882
1.4.4.6.1.3.3 | Fabrication & Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.1.3.3.1 | Fab Frame | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 32 | 3232 | 3732 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 821.04 | 4553.04
1.4.4.6.1.3.3.2 | Purchase Components | 38000 | 0 | 0 | 38000 | 0 | 0 | 0 | 24 | 0 | 0 | 1260 | 39260 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 8637.2 | 47897.2
1.4.4.6.1.3.3.3 | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 6300 | 6300 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 1386 | 7686
1.4.4.6.1.3.3.4 | Weld Pipes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 3232 | 3232 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 711.04 | 3943.04
1.4.4.6.1.3.4 | Install Skid at Beamline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.1.3.4.1 | Rigging | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 804.6 | 804.6 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 177.012 | 981.612
1.4.4.6.1.3.4.2 | Electric Hook-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 354.024 | 1963.224
1.4.4.6.1.3.4.3 | Tower Connection | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 3100 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 682 | 3782
1.4.4.6.1.3.4.4 | Instrumentation Set-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1680 | 1680 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 369.6 | 2049.6
1.4.4.6.1.3.4.5 | Set-up & Check-out | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 48 | 0 | 0 | 2520 | 3020 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 664.4 | 3684.4
1.4.4.6.1.3.4.6 | Piping to Target | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 2600 | 2 | 2 | 8 | 4 | 2 | 2 | 22% | 572 | 3172
1.4.4.6.2 | 1.4 Solenoids | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Area of CA responsibility for Solenoid Magnets
1.4.4.6.2.1 | MDMG Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Physicist support for the Magnet & Cryo Systems, Engineering Support for the Cryo System.
1.4.4.6.2.1.1 | Physics Support | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 78892 | 78892 | 1 | 2 | 15 | 2 | 1 | 2 | 21% | 16567.32 | 95459.32
1.4.4.6.2.1.2 | Engineering Support | 0 | 0 | 0 | 0 | 3520 | 0 | 0 | 0 | 0 | 0 | 236368 | 236368 | 1 | 2 | 15 | 2 | 1 | 2 | 21% | 49637.28 | 286005.28
1.4.4.6.2.2 | Solenoid Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Preparing Building 912 Infrastructure for Solenoid and Cryo installation.
1.4.4.6.2.2.1 | Building Space | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Prepare building space for Solenoid and Cryo Installation.
1.4.4.6.2.2.1.1 | Compressor Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.2.2.1.1.1 | Sound Proofing | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 160 | 0 | 10728 | 20728 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 7254.8 | 27982.8
1.4.4.6.2.2.1.1.2 | Painting | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 2345.6 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 820.96 | 3166.56
1.4.4.6.2.2.1.2 | 912 Floor Space | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.2.2.1.2.1 | Solid Steel Trench Covers | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 12 | 0 | 804.6 | 5804.6 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 2031.61 | 7836.21
1.4.4.6.2.2.1.2.2 | Paint Floor | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 16 | 0 | 1072.8 | 1272.8 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 445.48 | 1718.28
1.4.4.6.2.2.1.3 | Areas for Cryo Pipe Runs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
1.4.4.6.2.2.1.3.1 | Install Supports | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5864 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 2052.4 | 7916.4
1.4.4.6.2.2.1.3.2 | Install Supports | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 16 | 1616 | 1816 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 635.6 | 2451.6
1.4.4.6.2.2.2 | Compressor Power | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 480 Vac power for cryo system compressors.
1.4.4.6.2.2.2.1 | Spec Power Layout | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 940.1 | 3626.1
1.4.4.6.2.2.2.2 | Purchase Motor Starter | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 5250 | 20250
1.4.4.6.2.2.2.3 | Install Motor Starter | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 160 | 0 | 10728 | 11228 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 3929.8 | 15157.8
1.4.4.6.2.2.2.4 | Hook-up Compressor AC | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 6364 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 2227.4 | 8591.4
1.4.4.6.2.2.3 | Cooling Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Cooling water for compressors.
1.4.4.6.2.2.3.1 | Install Manifolds | 2000 | 0 | 0 | 2000 | 0 | 0 | 0 | 40 | 0 | 0 | 2100 | 4100 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 1435 | 5535
1.4.4.6.2.2.3.2 | Hook-up Compressor | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 1340 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 469 | 1809
1.4.4.6.2.2.4 | Compressed Air | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Compressed air for valves and instrumentation.
1.4.4.6.2.2.4.1 | Install Comp Air Manifolds | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 2340 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 819 | 3159
1.4.4.6.2.2.4.2 | Hook-up to Instrument Air | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 16 | 0 | 0 | 840 | 1040 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 364 | 1404
1.4.4.6.2.2.5 | LN2 Supply Tank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Liquid Nitrogen Storage Tank and piping supports.
1.4.4.6.2.2.5.1 | Layout Design | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 2250 | 2250 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 787.5 | 3037.5
1.4.4.6.2.2.5.2 | Digging Permit for Footings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1072.8 | 1072.8 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 375.48 | 1448.28
1.4.4.6.2.2.5.3 | Install Tank & Piping Footings | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 5250 | 20250
1.4.4.6.2.2.5.4 | Purchase LN2 Tank | 0 | 155000 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 54250 | 209250
1.4.4.6.2.2.5.5 | Install LN2 Tank | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 2145.6 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 750.96 | 2896.56
1.4.4.6.2.2.6 | Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Establishment of survey controls for magnet vendor. Verification of magnet locations.
1.4.4.6.2.2.6.1 | Establish Survey Controls | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 64 | 0 | 0 | 3360 | 3860 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 1351 | 5211
1.4.4.6.2.2.6.2 | Verify Magnet Location | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 2520 | 2520 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 882 | 3402
1.4.4.6.2.2.7 | Remote Operations Tie-in | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Cryo controls installation in RHIC Cryo Control Room.
1.4.4.6.2.2.7.1 | Connection with Cryo Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 4200 | 4200 | 8 | 2 | 15 | 4 | 2 | 4 | 43% | 1806 | 6006
1.4.4.6.2.2.8 | Cryogenic Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Support for installation and acceptance of cryogenic system.
1.4.4.6.2.2.8.1 | Installation Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 0 | 0 | 37800 | 37800 | 4 | 2 | 15 | 4 | 1 | 8 | 35% | 13230 | 51030
1.4.4.6.2.2.8.2 | Acceptance Test Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 0 | 0 | 37800 | 37800 | 4 | 2 | 15 | 4 | 1 | 8 | 35% | 13230 | 51030
1.4.4.6.2.3 | Power Supply Hook-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Install Solenoid Magnet Power Supplies and their AC and DC power.
1.4.4.6.2.3.1 | AC Power Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | AC power distribution from sub-stations to disconnect switches for magnet power supplies.
1.4.4.6.2.3.1.1 | Refurbish 1 ea Royal | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 3900 | 18900 |  | Refurbishment of existing AC disconnect switches (Royals) by an outside vendor.
1.4.4.6.2.3.1.2 | Disconnect & Reconnect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1072.8 | 1072.8 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 278.928 | 1351.728
1.4.4.6.2.3.1.3 | Rig Royals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 804.6 | 804.6 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 209.196 | 1013.796
1.4.4.6.2.3.2 | Install Power Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 563.22 | 2172.42
1.4.4.6.2.3.3 | Install Cable AC & DC Tray | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 8364 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 2927.4 | 11291.4
1.4.4.6.2.3.4 | Power Supply AC Hook-up | 500 | 9000 | 0 | 9500 | 0 | 0 | 0 | 160 | 0 | 0 | 8400 | 17900 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 6265 | 24165
1.4.4.6.2.3.5 | Pwr Sup/Magnet DC Hook-up | 2000 | 24000 | 0 | 26000 | 0 | 0 | 0 | 240 | 0 | 0 | 12600 | 38600 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 13510 | 52110
1.4.4.6.3 | Experimental Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Infrastructure for support of the MECO Experiment
1.4.4.6.3.1 | Electric Power and Tray | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Power and Cable Tray for electronics and signal cables.
1.4.4.6.3.1.1 | Engineering | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 940.1 | 3626.1
1.4.4.6.3.1.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 6750 | 6750 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 2362.5 | 9112.5
1.4.4.6.3.1.3 | Purchase Parts | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 5250 | 20250
1.4.4.6.3.1.4 | Power & Tray Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 21456 | 21456 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 7509.6 | 28965.6
1.4.4.6.3.2 | Electronics Hut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Rolling Electronics Hut which moves with MECO Detectors when they are removed from the DS.
1.4.4.6.3.2.1 | Spec Building | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 698.36 | 3384.36
1.4.4.6.3.2.2 | Purchase Building | 0 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 10400 | 50400
1.4.4.6.3.2.3 | Install Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1072.8 | 1072.8 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 278.928 | 1351.728
1.4.4.6.3.2.4 | Install Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 418.392 | 2027.592
1.4.4.6.3.2.5 | Fire Alarm Hook-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 2145.6 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 557.856 | 2703.456
1.4.4.6.3.2.6 | Rolling Frame & Access Way | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 2600 | 12600
1.4.4.6.3.2.7 | Cooling Water Installation | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 80 | 0 | 0 | 4200 | 5200 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 1352 | 6552
1.4.4.6.3.3 | New Counting House | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Counting house for experimenters and computers, located outside Building 912.
1.4.4.6.3.3.1 | Spec Building | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 2686 | 2686 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 698.36 | 3384.36
1.4.4.6.3.3.2 | Purchase Building | 0 | 240000 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 62400 | 302400
1.4.4.6.3.3.3 | Pour Footings | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 7800 | 37800
1.4.4.6.3.3.4 | Purchase Landings | 5600 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 1456 | 7056
1.4.4.6.3.3.5 | Install Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 2682 | 2682 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 697.32 | 3379.32
1.4.4.6.3.3.6 | Install Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1609.2 | 1609.2 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 418.392 | 2027.592
1.4.4.6.3.3.7 | Fire Detection Hook-up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 5364 | 5364 | 2 | 2 | 10 | 4 | 2 | 4 | 26% | 1394.64 | 6758.64
1.4.4.6.3.4 | Experimental Safety System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | "Fire wire" monitoring system for electronics racks in Electronics Hut, which will trip power if a high temperature is detected.
1.4.4.6.3.4.1 | Engineering | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1074.4 | 1074.4 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 376.04 | 1450.44
1.4.4.6.3.4.2 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 1800 | 1800 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 630 | 2430
1.4.4.6.3.4.3 | Assemble & Install System | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 64 | 0 | 0 | 3360 | 4360 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 1526 | 5886
1.4.4.6.3.4.4 | Hook-up Power Trip | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1072.8 | 1072.8 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 375.48 | 1448.28
1.4.4.6.3.5 | Clean Room | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | Clean room for working on detectors on the Building 912 Floor.
1.4.4.6.3.5.1 | Spec Clean Room | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 1611.6 | 1611.6 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 564.06 | 2175.66
1.4.4.6.3.5.2 | Purchase Clean Room | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 5250 | 20250
1.4.4.6.3.5.3 | Install Clean Room | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 2682 | 2682 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 938.7 | 3620.7
1.4.4.6.3.5.4 | Fire Alarm Hook-up | 1000 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 32 | 0 | 2145.6 | 3145.6 | 4 | 2 | 15 | 4 | 2 | 4 | 35% | 1100.96 | 4246.56
[5 empty] | 0 | [6 empty] | 0 | 0 | [6 empty] | 0% | 0 | 0
| Labor Hours |  |  |  |  | 13580 | 8691 | 4483 | 25660 | 14757 | 3263 | [8 empty] | 0% | 0 | 0
| FTE |  |  |  |  | 7.7379 | 4.9521 | 2.5544 | 14.6211 | 8.4085 | 1.8593
| TOTALS - DIRECT | 1189155 | 1836440 | 0 | 3025595 | 911897 | 779148.15 | 252168.75 | 1347150 | 989456.85 | 329563 | 4609383.75 | 7634978.75 | [6 empty] | 23.38% | 1785073.57 | 9420052.32
[5 empty] | 0 | [15 empty] | 0 | 0
| indirect % | 25.72% | 13.73% |  |  | 40.22% | 40.22% | 40.22% | 40.22% | 12% | 12% | [9 empty] | 0% | 0%
[5 empty] | 0 | [6 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 1495065.1238 | 2088491.39 |  | 3583556.5137 | 1278681.3694 | 1092538.1084 | 353596.3849 | 1889002.3839 | 1108191.672 | 369110.56 | 6091120.4786 | 9674676.9924 | [6 empty] | 23.38% | 2261959.1701 | 11936636.1625

## WBS 1.4.5 Project Office
RSVP - AGS Project Office
10/05/04 - | [8 empty] | Labor Rates
[7 empty] | 106.07 | 47.54 | 67.15 | 89.65 | 56.25 | 52.5 | 67.05 | 101
Total
WBS |  | Materials |  |  | Travel | Total |  |  | Labor Hours | [5 empty] | Labor | Total | Contingency Risk Factors | [7 empty] | Total
Number | Description | <$25,000 | >$25,000 | >$600,000 |  | Mat'ls | Management | Administrative | Eng'r | Physicist | Design | Tech | DTS | Shops | Cost | w/o Cont | Tech | WF | Design | Cost | WF | Sched | Cont | Cont $ | w/ Cont | Comments/WBS Dictionary
1.4.5 | RSVP AGS Project Office |  |  |  |  | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
1.4.5.1 | Project Head |  |  |  |  | 0 | 4388 | [7 empty] | 465435.16 | 465435.16 | [6 empty] | 20% | 93087.032 | 558522.192 | 0.5 FTE per year x 5 years
1.4.5.2 | Deputy Project Head |  |  |  |  | 0 | 4388 | [7 empty] | 465435.16 | 465435.16 | [6 empty] | 20% | 93087.032 | 558522.192 | 0.5 FTE per year x 5 years
1.4.5.3 | Fiscal |  |  |  |  | 0 |  | 2194 | [6 empty] | 104302.76 | 104302.76 | [6 empty] | 20% | 20860.552 | 125163.312 | 0.25 FTE per year x 5 years
1.4.5.4 | MSTC | 15000 |  |  | 35000 | 50000 | [8 empty] | 0 | 50000 | [6 empty] | 20% | 10000 | 60000 | $10,000 per year x 5 years
| Labor Hours | [5 empty] | 8776 | 2194 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0%
| FTE | [5 empty] | 5.0006 | 1.2501 | 0 | 0 | 0 | 0 | 0 | 0
| TOTALS - DIRECT | 15000 | 0 | 0 | 35000 | 50000 | 930870.32 | 104302.76 | 0 | 0 | 0 | 0 | 0 | 0 | 1035173.08 | 1085173.08 | [6 empty] | 20% | 217034.616 | 1302207.696
[6 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | 0
| indirect % | 25.72% | 13.73% |  | 25.24% |  | 40.22% | 40.22% | 40.22% | 40.22% | 40.22% | 40.22% | 12% | 12% | [9 empty] | 0% | 0%
[6 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | 0
| TOTAL | 18858.75 | 0 |  | 43834 | 62692.75 | 1305286.1623 | 146255.5486 | 0 | 0 | 0 | 0 | 0 | 0 | 1451541.7109 | 1514234.4609 | [6 empty] | 20% | 302846.8922 | 1817081.3531
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
[6 empty] | 0 | [8 empty] | 0 | [7 empty] | 0% | 0 | 0
0%

## RSVP pre-ops Summary Sheet
RSVP pre-operations costs per week, FY 2005 $'s with reduced NSF Indirects
The present NYPA contract expires in July 2005 and energy costs are expected to increase
Valid for operation during construction period, C-line costs
Assumed Energy Cost | 85 | per MWhr | FY2006 and beyond
2004-10-26
Fixed Personnel Costs (per-ops only) | FTE's
Base FTE | 12 | 1902335.9307 | (shared)
E940 FTE | 2 | 297666.1604 | (shared)
E926 FTE | 2 | 0 | (shared)
Total Personnel Cost | 14 | 2200002.091
Costs Common to RSVP
Booster and AGS Accelerators |  | w/o RHIC | w/RHIC HI | w/RHIC pp
DTS |  | 24001.8016 | 12000.9008 | 12000.9008
MSTC |  | 68691.551 | 34345.7755 | 34345.7755
SP |  | 22368.6681 | 11184.334 | 11184.334
Shift Differential (5 seats) |  | 10828.7098 | 0 | 0
Booster and AGS sub-total |  | 125890.7305 | 57531.0103 | 57531.0103
On time% (determined by RHIC needs) |  | 100% | 80% | 80%
Booster & AGS cost per week |  | 125890.7305 | 46024.8083 | 46024.8083
Linac
DTS |  | 5703.3984 | 5703.3984 | 2851.6992
MSTC |  | 10937.2955 | 10937.2955 | 5468.6478
SP |  | 47657.0867 | 47657.0867 | 23828.5434
Linac Sub-Total |  | 64297.7806 | 64297.7806 | 32148.8903
On time% |  | 100% | 100% | 80%
Linac cost per week |  | 64297.7806 | 64297.7806 | 25719.1123
AGS SEB Experimental area MSTC (50% of Operations Cost) |  | 10522 | 10522 | 10522
Total Common Costs/week |  | 200710.5112 | 120844.5889 | 82265.9205
Common Costs 0% FCR |  | 0 | 0 | 0
MECO MSTC (50% of Operations Cost) |  | 14938.7451 | 14938.7451 | 14938.7451
Power (MW)
Base (Experiment power that's always on, water, electronics etc) |  | 0.5 | 0.5 | 0.5
Accelerators (AGS and Booster) |  | 4.8 | 0.3 | 0.3
Linac |  | 2 | 2 | 0
Primary Beam (can be off, includes switchyard) |  | 0.1 | 0.1 | 0.1
Experiment (can be off) |  | 0 | 0 | 0
Total |  | 7.4 | 2.9 | 0.9
Power Cost
Cost/MWhr |  | 85 | 85 | 85
On time |  | 100% | 80% | 80%
MECO Power Total |  | 105672 | 40269.6 | 11709.6
Experiment Costs 0% FCR |  | 0 | 0 | 0
MECO Experiment Specific Costs/week |  | 120610.7451 | 55208.3451 | 26648.3451
K0PI0 MSTC (50% of Operations Cost) |  | 7469.3725 | 7469.3725 | 7469.3725
Power (MW)
Base (Experiment power that's always on, water, electronics etc) |  | 0.5 | 0.5 | 0.5
Accelerators (AGS and Booster) |  | 8.3 | 3.8 | 3.8
Linac |  | 2 | 2 | 0
Primary Beam (can be off, includes switchyard) |  | 0.2 | 0.5 | 0.5
Experiment (can be off) |  | 0 | 0 | 0
Total |  | 11 | 6.8 | 4.8
Power Cost
Cost/MWhr |  | 85 | 85 | 85
On time |  | 100% | 80% | 80%
K0PI0 Power Total |  | 157080 | 84823.2 | 56263.2
Experiment Costs 0% FCR |  | 0 | 0 | 0
E926 Experiment Specific Costs/week |  | 164549.3725 | 92292.5725 | 63732.5725
Example Total Cost
Accelerator Weeks | 20 | 4014210.2236 | 2416891.7784 | 1645318.4107
E926 Weeks | 10 | 1645493.7254 | 922925.7254 | 637325.7254
E940 Weeks | 10 | 1206107.4508 | 552083.4508 | 266483.4508
Personnel FTE's | 14 | 2200002.091 | 2200002.091 | 2200002.091
Total RSVP Cost |  | 9065813.4908 | 6091903.0456 | 4749129.6779
Example RSVP Beam Development Plan
Assumptions
(1) AGS not available for RSVP during 1st 7 weeks of RHIC operations and for 4 weeks/additional beam during a given year
(2) Last week of RHIC operations is considered running outside RHIC operations since this is cryo warm-up week (injectors not running)
(3) AGS is available for RSVP the balance of the time after reserving 15 weeks for shutdown work
(4) 80 hours/week are available for RSVP experiments during RHIC Operations
(5) 120 hours/week are available for RSVP experiments outside RHIC Operations
(6) RHIC Cryo Operations based on "Constant Effort" budget - 27 weeks per year
(7) Assumes RSVP Commissioning with neutral and muon beams in FY2009 and RSVP construction ends in FY2010 with an engineering run
Example (Nov 04 plan) | FY06 | FY07 | FY08 | FY09* | FY10** |  | Contingency***
RHIC Cryo Weeks | 27 | 27 | 27 | 27 | 27 |  | 27
HI-HI Phys. Wks. | 19 | 0 | 19 | 0 | 19 |  | 5
pp, pHI Phys. Wks. | 0 | 19 | 0 | 19 | 0 |  | 10
Available Outside RHIC | 10 | 10 | 10 | 10 | 10 |  | 10
TOTAL RSVP Weeks Available | 29 | 29 | 29 | 29 | 29 |  | 25
K0PI0 | 7 | 9 | 6 | 7 | 9.5 |  | 5
MECO | 4 | 6 | 7 | 7 | 9.5 |  | 5
Outside RHIC
K0PI0 | 0 | 0 | 0 | 0 | 0 |  | 5
MECO | 0 | 0 | 0 | 0 | 0 |  | 5
W/RHIC HI
K0PI0 | 7 | 0 | 6 | 0 | 9.5 |  | 0
MECO | 4 | 0 | 7 | 0 | 9.5 |  | 0
W/RHIC pp
K0PI0 | 0 | 9 | 0 | 7 | 0 |  | 0
MECO | 0 | 6 | 0 | 7 | 0 |  | 0
[6 empty] | Total |  | Total W/Cont
Personnel | 2200002.091 | 2200002.091 | 2200002.091 | 2795334.4117 | 2795334.4117 | 12190675.0965 | 2200002.091 | 14390677.1876
Other | 2196171.8662 | 1967472.0313 | 2511193.5067 | 2671314.563 | 4959586.0329 | 14305738.0003 | 3432905.6999 | 17738643.7002
Total | 4396173.9572 | 4167474.1224 | 4711195.5978 | 5466648.9748 | 7754920.4447 | 26496413.0968 | 5632907.7909 | 32129320.8877
* Commissioning with neutral beam (K0PI0) and muon beam (K0PI0), full operations cost with reduced indirects
** Engineering Run, full operations costs with reduced indirects
*** Contingency (with FY2006-2008 cost basis)

## RSVP ops cost (construction)
RSVP Operations Costs per week, FY 2005 $'s with reduced NSF Indirects
The present NYPA contract expires in July 2005 and energy costs are expected to increase
Valid for construction experiment operations period - experiment commissioning
Assumed Energy Cost | 85 | per MWhr | FY2006 and beyond
2004-10-26
Fixed Personnel Costs | FTE's
Base FTE | 12 | 1902335.9307 | (shared)
E940 FTE | 6 | 892998.4811 | (shared)
E926 FTE | 4 | 0 | (shared)
Total Personnel Cost | 18 | 2795334.4117 | (included 0% FCR)
Costs Common to RSVP
Booster and AGS Accelerators |  | w/o RHIC | w/RHIC HI | w/RHIC pp
DTS |  | 24001.8016 | 12000.9008 | 12000.9008
MSTC |  | 68691.551 | 34345.7755 | 34345.7755
SP |  | 22368.6681 | 11184.334 | 11184.334
Shift Differential (5 seats) |  | 10828.7098 | 0 | 0
Booster and AGS sub-total |  | 125890.7305 | 57531.0103 | 57531.0103
On time% (determined by RHIC needs) |  | 100% | 80% | 80%
Booster & AGS cost per week |  | 125890.7305 | 46024.8083 | 46024.8083
Linac
DTS |  | 5703.3984 | 6833.8934 | 3416.9467
MSTC |  | 10937.2955 | 13174.6021 | 6587.301
SP |  | 47657.0867 | 49429.2724 | 24714.6362
Linac Sub-Total |  | 64297.7806 | 69437.7679 | 34718.884
On time% |  | 100% | 100% | 80%
Linac cost per week |  | 64297.7806 | 69437.7679 | 27775.1072
AGS SEB Experimental area MSTC |  | 21044 | 21044 | 21044
Total Common Costs/week |  | 211232.5112 | 136506.5762 | 94843.9155
MECO MSTC |  | 35989 | 35989.1568 | 35989.1568
Power (MW)
Base (always on, refrigerator, water, electronics etc) |  | 1 | 1 | 1
Accelerators (AGS and Booster) |  | 4.8 | 0.3 | 0.3
Linac |  | 2 | 2 | 0
Primary Beam (can be off, includes switchyard) |  | 2.5 | 2.4 | 2.4
Experiment (can be off) |  | 0 | 0 | 0
Total |  | 10.3 | 5.7 | 3.7
Power Cost
Cost/MWhr |  | 85 | 85 | 85
On time |  | 100% | 80% | 80%
MECO Power Total |  | 147084 | 73684.8 | 45124.8
Experiment Costs 0% FCR |  | 0 | 0 | 0
MECO Experiment Specific Costs/week |  | 183073 | 109673.9568 | 81113.9568
K0PI0 MSTC |  | 17995 | 17994.5784 | 17994.5784
Power (MW)
Base (Experiment power that's always on, water, electronics etc) |  | 0.5 | 0.5 | 0.5
Accelerators (AGS and Booster) |  | 8.3 | 3.8 | 3.8
Linac |  | 2 | 2 | 0
Primary Beam (can be off, includes switchyard) |  | 0.5 | 0.5 | 0.5
Experiment (neutral beam and D4 can be off) |  | 3.2 | 3.2 | 3.2
Total |  | 14.5 | 10 | 8
Power Cost
Cost/MWhr |  | 85 | 85 | 85
On time |  | 100% | 80% | 80%
K0PI0 Power Total |  | 207060 | 121380 | 92820
Experiment Costs 0% FCR |  | 0 | 0 | 0
K0PI0 Experiment Specific Costs/week |  | 225055 | 139374.5784 | 110814.5784
Example Total Cost
Accelerator Weeks | 20 | 4224650.2236 | 2730131.5243 | 1896878.3091
E926 Weeks | 10 | 2250550 | 1393745.7841 | 1108145.7841
E940 Weeks | 10 | 1830730 | 1096739.5683 | 811139.5683
Personnel FTE's | 18 | 2795334.4117 | 2795334.4117 | 2795334.4117
Total RSVP Cost |  | 11101264.6353 | 8015951.2885 | 6611498.0732
Example RSVP Operations Plan (with reduced indirects applicable for construction period only)
Assumptions
(1) AGS not available for RSVP during 1st 7 weeks of RHIC operations and for 4 weeks/additional beam during a given year
(2) Last week of RHIC operations is considered running outside RHIC operations since this is cryo warm-up week (injectors not running)
(3) AGS is available for RSVP the balance of the time after reserving 15 weeks for shutdown work
(4) 80 full intensity hours/week are available for RSVP experiments during RHIC Operations
(5) 120 full intensity hours/week are available for RSVP experiments outside RHIC Operations
(6) RHIC Cryo Operations based on "Constant Effort" budget - 27 weeks per year
(7) Assumes RSVP construction ends in FY2010 with an engineering run and accounting for integrated protons begins in first physics production year (FY2011)
| FY09* | FY10* | FY11**
RHIC Cryo Weeks | 27 | 27 | 27
HI-HI Phys. Wks. | 0 | 19 | 5
pp, pHI Phys. Wks. | 19 | 0 | 10
Available Outside RHIC | 10 | 10 | 10
TOTAL RSVP Weeks Available | 29 | 29 | 25
K0PI0 (weeks) | 7 | 9.5 | 7.5
MECO (weeks) | 7 | 9.5 | 7.5
Outside RHIC
K0PI0 | 0 | 0 | 0
MECO | 0 | 0 | 0
W/RHIC HI
K0PI0 | 0 | 9.5 | 5
MECO | 0 | 9.5 | 0
W/RHIC pp
K0PI0 | 7 | 0 | 2.5
MECO | 7 | 0 | 7.5
Total
Personnel | 2795334.4117 | 2795334.4117 | 2795334.4117 | 8386003.2352
Power | 994582.008 | 1908709.068 | 1212707.58 | 4115998.656
Other | 1676732.555 | 3050876.9649 | 2000528.4699 | 6728137.9899
Total | 5466648.9748 | 7754920.4447 | 6008570.4617 | 19230139.8811
* Commissioning with neutral beam (K0PI0) and muon beam (K0PI0)
** Engineering Run
*** Contingency year

## Labor and Indirect Rates (NSF)
For non-DOE projects - includes safeguards tax (adds 2.7% to G&A) and Full Cost Recovery fee (3%)
| FY05 |  |  |  | 10/18/04 from Darlene
Indirect for Capital Projects
Direct Salary and Wage
Rate
| Direct Cost |  |  |  | 60406.72
| Paid Absence Burden(PAB) |  |  | 18.5% | 11175.2432
| Fringe on DC and PAB |  |  | 41% | 29348.6049
| Nominal Salary Base (Direct Cost) |  |  |  |  | 100930.5681 | 1 |  | 59.85%
| Space Charge (SC) on DC,PAB and Fringe |  |  | 1.54% | 1554.3307
| Fuel Charge on Space Charge |  |  | 16.6% | 258.0189
| Organizational Burden(OB) on DC,PAB and Fr |  |  | 8.05% | 8124.9107
| Power(Pwr) on DC, PAB and Fr |  |  | 2.67% | 2694.8462
| Communications on DC, PAB and Fr (incl. in OB) |  |  | 1.04% | 1049.6779
| ITD Contribution on DC, PAB and Fr |  |  | 2.05% | 2069.0766
| Auto on DC, PAB and Fr |  |  | 0.82% | 827.6307
| ESH on DC, PAB and Fr |  |  | 3.31% | 3340.8018
| Department Burden Total |  |  |  |  | 19919.2936 | 19.74%
| G&A on DC |  |  | 17.5% | 10571.176
| G&A on PAB |  |  | 17.5% | 1955.6676
| G&A on Fr |  |  | 17.5% | 5136.0059
| G&A on SC |  |  | 17.5% | 272.0079
| G&A on Fuel |  |  | 17.5% | 45.1533
| G&A on OB |  |  | 17.5% | 1421.8594
| G&A on All else except power |  |  | 17.5% | 1275.2577
| G&A on Pwr |  |  | 0% | 0
| BNL G&A Total |  |  |  |  | 20677.1277 | 20.49%
| Department plus G&A |  |  |  |  | 40596.4213 | 40.22%
| Sub-Total |  |  |  | 141526.9894
| FCR (direct to DOE) |  |  | 0% | 0 | 0 | 0%
| Department plus G&A plus FCR |  |  |  |  | 40596.4213 | 40.22%
| Total |  |  |  | 141526.9894 | 141526.9894
| Indirect on Direct+PAB+Fringe ($100,000) |  |  |  | 40.22%
Consultants/Jobshoppers | [5 empty] | Dept | Lab | DOE | Total
| Direct Costs (DC) |  |  |  | 100000
| G&A on DC |  |  | 17.5% | 17500
| Sub-Total |  |  |  | 117500 | 0% | 17.5% |  | 17.5%
| FCR |  |  | 0% | 0
| Total |  |  |  | 117500
| Indirect |  |  |  | 17.5% | 0% | 17.5% | 0%
DTS (Central Shops/Plant Engineering)
| Direct Costs (DC) |  |  |  | 100000
| G&A on DC |  |  | 12% | 12000
| Sub-Total |  |  |  | 112000 | 0% | 12% |  | 12%
| FCR |  |  | 0% | 0
| Total |  |  |  | 112000
| Indirect |  |  |  | 12% | 0% | 12% | 0
MSTC (purchases)
| Direct Cost (DC) |  |  |  | 100000
| Material Handling (MH) |  |  | 7% | 7000
| G&A on DC |  |  | 17.5% | 17500
| G&A on MH |  |  | 17.5% | 1225
| Sub-Total |  |  |  | 125725 | 7% | 18.73% |  | 25.72%
| FCR |  |  | 0% | 0
| Total |  |  |  | 125725
| Indirect |  |  |  | 25.72% |  |  | 0%
Subcontracts (Purchases > 25K)
| Direct Cost (DC) |  |  |  | 100000
| Material Handling (MH) |  |  | 7% | 7000
| G&A on DC ("Traditional" only) |  |  | 5.5% | 5500
| G&A on MH |  |  | 17.5% | 1225
| Total |  |  |  | 113725 | 7% | 6.725% |  | 13.73%
| FCR |  |  | 0% | 0
113725
| Indirect |  |  |  | 13.73% | 7% | 6.725% | 0%
Subcontracts (Purchases > 600K) on the first $600k only
| Direct Cost (DC) |  |  |  | 600000
| Material Handling (MH) on DC-6.5% of $600K |  |  | FIXED | 39000
| G&A on DC-8% of $600K |  |  | FIXED | 48000
| G&A on MH |  |  | 17.5% | 6825
| Sub-Total |  |  |  | 693825
| FCR |  |  | 0% | 0
| Total |  |  |  | 693825
| Indirect (Only on first $600K, prior approval required) |  |  |  | 15.64%
Purchase Equipment (Turn-key Purchases > 25K Gen CAP/HEEP)
| Direct Cost (DC) |  |  |  | 100000
| Material Handling (MH) |  |  | 7% | 7000
| G&A on MH |  |  | 17.5% | 1225
| Sub-Total |  |  |  | 108225
| FCR |  |  | 0% | 0
| Total |  |  |  | 108225
| Indirect |  |  |  | 8.225%
Purchase Equipment (Turn-Key, Purchases > 600K) on first $600K only
| Direct Cost (DC) |  |  |  | 600000
| Material Handling 7% of $600K (MH) |  |  | FIXED | 42000
| G&A on MH |  |  | 17.5% | 7350
| Sub-Total |  |  |  | 649350
| FCR |  |  | 0% | 0
| Total |  |  |  | 649350
| Indirect (Only on first $600K, prior approval required) |  |  |  | 8.225%
| Labor Rates (direct, includes PAB and fringe) |  |  |  | With Indirects | With Indirects
|  | $/hr |  |  | $/hr | $/year (FTE) | 0.25 FTE
| techs | 52.5 | PER PRODUCTIVE HOUR |  | 73.6166 | 129197.1623 | 32299.2906
| engineers | 67.15 | PER PRODUCTIVE HOUR |  | 94.1592 | 165249.3228 | 41312.3307
| designers | 56.25 | PER PRODUCTIVE HOUR |  | 78.8749 | 138425.531 | 34606.3827
| physicist | 89.65 | PER PRODUCTIVE HOUR |  | 125.7091 | 220619.5352 | 55154.8838 | LE/LP | 192934.429
| BNL Administrative* | 47.76 | PER PRODUCTIVE HOUR |  | 66.9701 | 117532.5042 | 29383.126
| BNL Management* | 106.58 | PER PRODUCTIVE HOUR |  | 149.4487 | 262282.5439 | 65570.636
* pp estimate
DISTRIBUTED TECHNICAL SERVICES (DTS):
| CENTRAL SHOPS | 99.4 | PER PRODUCTIVE HOUR |  | 111.328 | 195380.64
| BLDG. TRADES | 83.25 | PER PRODUCTIVE HOUR |  | 93.24 | 163636.2
| CNST ENGR SERVICES | 101 |  |  | 113.12 | 198525.6
| DIRECT ASSIGNED | 67.05 | PER PRODUCTIVE HOUR |  | 75.096 | 131793.48
| GENERAL LABOR | 55 | PER PRODUCTIVE HOUR |  | 61.6 | 108108
| PRODUCTIVE HOURS FOR 1 FTE |  | 1755

## Resource Categories
RSVP Resource Categories
FY05 (D. Sappo, 9/30/04)
Category |  | Code | Rate | O/H Rate
Labor
| Physicist | PH | 89.23 | 39.47%
| Mechanical Engineer | ME | 66.86 | 39.47%
| Electrical Engineer | EE | 66.86 | 39.47%
| Mechanical Designer | MD | 55.96 | 39.47%
| Electrical Designer | ED | 55.96 | 39.47%
| IT Professional | IT | 69.28 | 39.47%
| Administrative | ADM | 47.54 | 39.47%
| Management | MGT | 106.07 | 39.47%
| Supervisor | SPV | 88.86 | 39.47%
| Electrical Technician | ET | 52.25 | 39.47%
| Mechanical Technician | MT | 52.25 | 39.47%
| Pulsed Power Technician | PPT | 52.25 | 39.47%
| Access Controls Technician | ACT | 52.25 | 39.47%
| PS Systems Technician | PST | 52.25 | 39.47%
| Coordinators | MCC | 66.86 | 39.47%
| Operators | MCO | 69.28 | 39.47%
| Vacuum Technician | VT | 52.25 | 39.47%
| RF Technician | RFT | 52.25 | 39.47%
| Instrumentation Beam Technician | IBT | 52.25 | 39.47%
| Cryogenic Technician | CT | 52.25 | 39.47%
| Controls Technician | CNT | 52.25 | 39.47%
| Beam Service Technician | BST | 52.25 | 39.47%
| Collider Accelerator Support Technician | CAS | 52.25 | 39.47%
| Mechanical Service Technician (FES) | MST | 52.25 | 39.47%
| Survey | S | 52.25 | 39.47%
| Electronics Service Technician (FES) | EST | 52.25 | 39.47%
| Water Systems Technician (FES) | WST | 52.25 | 39.47%
| Post Docs | PD | 42.25 | 39.47%
Other Labor
| Scientific Distributed Labor | SD | 131.05 | 17.05%
| Contract Labor | CL | Per Contract | 17.05%
| Consultants/Collaborators | CC | Per Contract | 17.05%
Support Labor
| Central Shops | CS | 92.83 | 12.05%
| Building Trades (Standard) | BTS | 78.35 | 12.05%
| Building Trades Engineer | BTE | 94.65 | 12.05%
| Building Trades Carpenter | BTC | 78.35 | 12.05%
| Building Trades Electrician | BTE | 78.35 | 12.05%
| Building Trades Rigger | BTR | 78.35 | 12.05%
Materials
| Low Value (Less Than $25K) | LV | Per PO | 25.24%
| High Value (Over $25K) | HV | Per PO | 13.19%
| Large Procurement (Over $600K) | LP | Per PO | 13.19% | Only First $600K
| Capital Equipment | CE | Per PO | 8.19%
Other | Travel | TV | Per Trip | 25.24%

## K0PI0 manpower - NSF
Personnel Costs assuming construction project indirect costs.
The base manpower estimate is comprised of the following: | [6 empty] | Direct |  | BNL indirects
[5 empty] | FTE | Base | w/Fringe & PAB | C-AD Org Burd | w/3% Safeguards | Subtotal | FCR | TOTAL
[7 empty] | 59.85% | 19.74% | 20.49% |  | 0%
Physicist |  |  |  |  | 1 | 94165.0956 | 157335.75 | 31051.2172 | 32232.568 | 220619.5352 | 0 | 220619.5352
Engineering (mechanical, electrical) |  |  |  |  | 1 | 70531.9149 | 117848.25 | 23258.1064 | 24142.9664 | 165249.3228 | 0 | 165249.3228
Controls |  |  |  |  | 0.5 | 37327.296 | 62368.3125 | 12308.7856 | 12777.0762 | 87454.1744 | 0 | 87454.1744
Instrumentation |  |  |  |  | 1 | 62838.0016 | 104992.875 | 20721.0158 | 21509.3517 | 147223.2425 | 0 | 147223.2425
Vacuum systems |  |  |  |  | 0.5 | 31419.0008 | 52496.4375 | 10360.5079 | 10754.6758 | 73611.6213 | 0 | 73611.6213
Magnet systems |  |  |  |  | 1.5 | 94257.0024 | 157489.3125 | 31081.5238 | 32264.0275 | 220834.8638 | 0 | 220834.8638
Power supplies |  |  |  |  | 1.5 | 94257.0024 | 157489.3125 | 31081.5238 | 32264.0275 | 220834.8638 | 0 | 220834.8638
Utilities (power, water, AC) |  |  |  |  | 2 | 125676.0032 | 209985.75 | 41442.0317 | 43018.7034 | 294446.485 | 0 | 294446.485
Extraction systems |  |  |  |  | 1 | 74654.592 | 124736.625 | 24617.5713 | 25554.1525 | 174908.3487 | 0 | 174908.3487
ES&H, QA, Admin, training (org. burden) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shift operations |  |  |  |  | 2 | 126831.4032 | 211916.25 | 41823.0282 | 43414.195 | 297153.4732 | 0 | 297153.4732
|  |  | Subtotal |  | 12 | 811957.3121 | 1356658.875 | 267745.3116 | 277931.7441 | 1902335.9307 | 0 | 1902335.9307
E926 manpower support
Physicist, engineering |  |  |  |  | 1 | 82348.5053 | 137592 | 27154.6618 | 28187.7672 | 192934.429 | 0 | 192934.429
RF systems engineering, technicians |  |  |  |  | 1 | 62838.0016 | 104992.875 | 20721.0158 | 21509.3517 | 147223.2425 | 0 | 147223.2425
Technicians (instr., vacuum, magnet etc.) |  |  |  |  | 2 | 110288.1767 | 184275 | 36367.8506 | 37751.4739 | 258394.3245 | 0 | 258394.3245
|  |  | Subtotal |  | 4 | 255474.6835 | 426859.875 | 84243.5282 | 87448.5928 | 598551.996 | 0 | 598551.996
|  |  | TOTAL |  | 16 | 1067431.9957 | 1783518.75 | 351988.8398 | 365380.3369 | 2500887.9267 | 0 | 2500887.9267
Accel Oprs (15% shift differential only) - 1 week
PERSONNEL (all shift work)
3 MCR |  |  |  |  | 3 |  | 5076.54 | 1001.8877 | 1040.0047 | 7118.4324 | 0 | 7118.4324
1 Scientific |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
1 SIEMENS |  |  |  |  | 1 |  | 1323 | 261.1025 | 271.0362 | 1855.1387 | 0 | 1855.1387
1 HP |  |  |  |  | 1 |  | 1323 | 261.1025 | 271.0362 | 1855.1387 | 0 | 1855.1387
Total | [6 empty] | 7722.54 | 1524.0927 | 1582.0772 | 10828.7098 | 0 | 10828.7098
Labor Rates (direct, includes PAB and fringe)
FY 05 | $/hr
techs | 52.5 | PER PRODUCTIVE HOUR
engineers | 67.15 | PER PRODUCTIVE HOUR
designers | 56.25 | PER PRODUCTIVE HOUR
physicist | 89.65 | PER PRODUCTIVE HOUR
PRODUCTIVE HOURS FOR 1 FTE |  |  |  | 1755

## MECO manpower - NSF
Personnel Costs assuming construction project indirect costs.
The base manpower estimate is comprised of the following: | [6 empty] | Direct |  | BNL indirects
[5 empty] | FTE | Base | w/Fringe & PAB | C-AD Org Burd | w/3% Safeguards | Subtotal | FCR | TOTAL
[7 empty] | 59.85% | 19.74% | 20.49% |  | 0%
Physicist |  |  |  |  | 1 | 94165.0956 | 157335.75 | 31051.2172 | 32232.568 | 220619.5352 | 0 | 220619.5352
Engineering (mechanical, electrical) |  |  |  |  | 1 | 70531.9149 | 117848.25 | 23258.1064 | 24142.9664 | 165249.3228 | 0 | 165249.3228
Controls |  |  |  |  | 0.5 | 37327.296 | 62368.3125 | 12308.7856 | 12777.0762 | 87454.1744 | 0 | 87454.1744
Instrumentation |  |  |  |  | 1 | 62838.0016 | 104992.875 | 20721.0158 | 21509.3517 | 147223.2425 | 0 | 147223.2425
Vacuum systems |  |  |  |  | 0.5 | 31419.0008 | 52496.4375 | 10360.5079 | 10754.6758 | 73611.6213 | 0 | 73611.6213
Magnet systems |  |  |  |  | 1.5 | 94257.0024 | 157489.3125 | 31081.5238 | 32264.0275 | 220834.8638 | 0 | 220834.8638
Power supplies |  |  |  |  | 1.5 | 94257.0024 | 157489.3125 | 31081.5238 | 32264.0275 | 220834.8638 | 0 | 220834.8638
Utilities (power, water, AC) |  |  |  |  | 2 | 125676.0032 | 209985.75 | 41442.0317 | 43018.7034 | 294446.485 | 0 | 294446.485
Extraction systems |  |  |  |  | 1 | 74654.592 | 124736.625 | 24617.5713 | 25554.1525 | 174908.3487 | 0 | 174908.3487
ES&H, QA, Admin, training (org. burden) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shift operations |  |  |  |  | 2 | 126831.4032 | 211916.25 | 41823.0282 | 43414.195 | 297153.4732 | 0 | 297153.4732
|  |  | Subtotal |  | 12 | 811957.3121 | 1356658.875 | 267745.3116 | 277931.7441 | 1902335.9307 | 0 | 1902335.9307
E940 manpower support
Physicist, engineering |  |  |  |  | 1 | 82348.5053 | 137592 | 27154.6618 | 28187.7672 | 192934.429 | 0 | 192934.429
Cryo systems engineering, technicians |  |  |  |  | 3 | 188514.0048 | 314978.625 | 62163.0475 | 64528.0551 | 441669.7276 | 0 | 441669.7276
Technicians (instr., vacuum, magnet etc.) |  |  |  |  | 2 | 110288.1767 | 184275 | 36367.8506 | 37751.4739 | 258394.3245 | 0 | 258394.3245
|  |  | Subtotal |  | 6 | 381150.6868 | 636845.625 | 125685.5599 | 130467.2962 | 892998.4811 | 0 | 892998.4811
|  |  | TOTAL |  | 18 | 1193107.9989 | 1993504.5 | 393430.8715 | 408399.0402 | 2795334.4117 | 0 | 2795334.4117
Accel Oprs (15% shift differential only) - 1 week
PERSONNEL (all shift work)
3 MCR |  |  |  |  | 3 |  | 5076.54 | 1001.8877 | 1040.0047 | 7118.4324 | 0 | 7118.4324
1 Scientific |  |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
1 SIEMENS |  |  |  |  | 1 |  | 1323 | 261.1025 | 271.0362 | 1855.1387 | 0 | 1855.1387
1 HP |  |  |  |  | 1 |  | 1323 | 261.1025 | 271.0362 | 1855.1387 | 0 | 1855.1387
Total | [6 empty] | 7722.54 | 1524.0927 | 1582.0772 | 10828.7098 | 0 | 10828.7098
Labor Rates (direct, includes PAB and fringe)
FY 03 | $/hr
techs | 52.5 | PER PRODUCTIVE HOUR
engineers | 67.15 | PER PRODUCTIVE HOUR
designers | 56.25 | PER PRODUCTIVE HOUR
physicist | 89.65 | PER PRODUCTIVE HOUR
PRODUCTIVE HOURS FOR 1 FTE |  |  |  | 1755

## K0PI0 alacart Operations
K0PI0 (E926) - DRAFT
DEDICATED tests - no HEP or RHIC base support (pre/post-ops not included)
One Week - beam to C-target for tests
In FY05 Dollars and reduced NSF indirects, FY2006 Power Costs (estimate for new NYPA Contract)
Cost for 1 week of operatons |  |  | Power Cost | Clock time in hours
9/21/04 - escalated 3%/year FY03-FY05 |  |  | 85 | 168
per MWhr
| Direct | Dept Charges | G&A
Accel Oprs |  |  |  | TOTAL
PERSONNEL (all shift work)
3 MCR | 38920.14 | 7681.1387 | 3089.5174 | 49690.7961
1 Scientific/Professional (1/2 time) | 6585.6 | 1299.7103 | 522.7711 | 8408.0814 | 89.65 | SCIENTIFIC
1 SIEMENS | 10143 | 2001.786 | 805.1609 | 12949.9469 | 67.15 | PROFESSIONAL
1 HP | 10143 | 2001.786 | 805.1609 | 12949.9469 | 52.5 | TECHNICAL
DTS | 21430.18 | 0 | 2571.6216 | 24001.8016 | PRODUCTIVE HOURS FOR 1 FTE |  | 1755
MSTC | 54636.35 | 3824.5445 | 10230.6565 | 68691.551
SPEC PROC | 19669.086 | 1376.836 | 1322.746 | 22368.6681
ES&F
2 Shift Personnel (CAS watch) | 20286 | 4003.5719 | 1610.3218 | 25899.8937
2 Tech Support (75% time) | 15214.5 | 3002.6789 | 1207.7413 | 19424.9203
2 Prof Support (20 hrs per week each) | 2686 | 530.0993 | 213.2172 | 3429.3165
MSTC Experimental Area | 11882.08 | 831.7456 | 2224.9195 | 14938.7451
LINAC
Tech Support (1/4 time) | 2535.75 | 500.4465 | 201.2902 | 3237.4867
DTS | 5092.32 | 0 | 611.0784 | 5703.3984
MSTC | 8699.38 | 608.9566 | 1628.9589 | 10937.2955
SPEC PROC | 41905.55 | 2933.3885 | 2818.1482 | 47657.0867
TOTAL COST | 269828.936 | 30596.6888 | 29863.31 | 330288.9349
ELECTRICITY COSTS (Est. Only)
Based on 11 MW above 3 MW base X $85 Mwhr | 157080 | 0 | 0 | 157080
Sub-TOTAL WEEKLY OPERATING COSTS | 426908.936 | 30596.6888 | 29863.31 | 487368.9349
TOTAL DIRECT COSTS |  |  |  | 457505.6248
| HOURLY RATE |  |  | 19062.7344
3 (8HR) SHIFTS
| Full Cost Recovery |  |  | 25734.6914
Rate
Full Cost Recovery Fee (0%) |  |  |  | 0
TOTAL WEEKLY OPERATING COSTS |  |  |  | 487368.9349
Cost for 1 shift of operation |  |  |  | 23208.0445

## MECO alacart Operations
MECO (E940) - DRAFT
DEDICATED tests - no HEP or RHIC base support (pre/post-ops not included)
One Week - beam to C-target for tests
In FY05 Dollars and reduced NSF indirects, FY2006 Power Costs (estimate for new NYPA Contract)
Cost for 1 week of operatons |  |  | Power Cost | Clock time in hours
9/21/04 - escalated 3%/year FY03-FY05 |  |  | 85 | 168
per MWhr
| Direct | Dept Charges | G&A
Accel Oprs |  |  |  | TOTAL
PERSONNEL (all shift work)
3 MCR | 38920.14 | 7681.1387 | 3089.5174 | 49690.7961
1 Scientific/Professional (1/2 time) | 6585.6 | 1299.7103 | 522.7711 | 8408.0814 | 89.65 | SCIENTIFIC
1 SIEMENS | 10143 | 2001.786 | 805.1609 | 12949.9469 | 67.15 | PROFESSIONAL
1 HP | 10143 | 2001.786 | 805.1609 | 12949.9469 | 52.5 | TECHNICAL
DTS | 21430.18 | 0 | 2571.6216 | 24001.8016 | PRODUCTIVE HOURS FOR 1 FTE |  | 1755
MSTC | 54636.35 | 3824.5445 | 10230.6565 | 68691.551
SPEC PROC | 19669.086 | 1376.836 | 1322.746 | 22368.6681
ES&F
2 Shift Personnel (CAS watch) | 20286 | 4003.5719 | 1610.3218 | 25899.8937
2 Tech Support (separator 75% time) | 15214.5 | 3002.6789 | 1207.7413 | 19424.9203
2 Prof Support (20 hrs per week each) | 2686 | 530.0993 | 213.2172 | 3429.3165
MSTC Experimental Area | 23764.16 | 1663.4912 | 4449.839 | 29877.4902
LINAC
Tech Support (1/4 time) | 2535.75 | 500.4465 | 201.2902 | 3237.4867
DTS | 5092.32 | 0 | 611.0784 | 5703.3984
MSTC | 8699.38 | 608.9566 | 1628.9589 | 10937.2955
SPEC PROC | 41905.55 | 2933.3885 | 2818.1482 | 47657.0867
TOTAL COST | 281711.016 | 31428.4344 | 32088.2295 | 345227.68
ELECTRICITY COSTS (Est. Only)
Based on 7.4 MW above 3 MW base X $85 Mwhr | 105672 | 0 | 0 | 105672
Sub-TOTAL WEEKLY OPERATING COSTS | 387383.016 | 31428.4344 | 32088.2295 | 450899.68
TOTAL DIRECT COSTS |  |  |  | 418811.4504
| HOURLY RATE |  |  | 17450.4771
3 (8HR) SHIFTS
| Full Cost Recovery |  |  | 23558.1441
Rate
Full Cost Recovery Fee (0%) |  |  |  | 0
TOTAL WEEKLY OPERATING COSTS |  |  |  | 450899.68
Cost for 1 shift of operation |  |  |  | 21471.4133

## K0PI0 D6 Operations Cost
K0PI0 (E926) - DRAFT
DEDICATED tests - no HEP or RHIC base support (pre/post-ops not included)
One Week - including tune-up - LOW INTENSITY to D6-line
In FY05 Dollars and reduced NSF indirects, FY2006 Power Costs (estimate for new NYPA Contract)
Cost for 1 week of operatons |  |  | Power Cost | Clock time in hours
9/21/04 - escalated 3%/year FY03-FY05 |  |  | 85 | 168
per MWhr
| Direct | Dept Charges | G&A
Accel Oprs |  |  |  | TOTAL
PERSONNEL (all shift work)
3 MCR | 38920.14 | 7681.1387 | 3089.5174 | 49690.7961
1 Scientific/Professional (1/2 time) | 6585.6 | 1299.7103 | 522.7711 | 8408.0814 | 89.65 | SCIENTIFIC
1 SIEMENS | 10143 | 2001.786 | 805.1609 | 12949.9469 | 67.15 | PROFESSIONAL
1 HP | 10143 | 2001.786 | 805.1609 | 12949.9469 | 52.5 | TECHNICAL
DTS | 21430.18 | 0 | 2571.6216 | 24001.8016 | PRODUCTIVE HOURS FOR 1 FTE |  | 1755
MSTC | 54636.35 | 3824.5445 | 10230.6565 | 68691.551
SPEC PROC | 19669.086 | 1376.836 | 1322.746 | 22368.6681
ES&F
2 Shift Personnel (CAS watch) | 20286 | 4003.5719 | 1610.3218 | 25899.8937
2 Tech Support (separator and other, 75% time) | 15214.5 | 3002.6789 | 1207.7413 | 19424.9203
2 Prof Support (20 hrs per week each) | 2686 | 530.0993 | 213.2172 | 3429.3165
MSTC | 11882.08 | 831.7456 | 2224.9195 | 14938.7451
MSTC (D6) | 11882.08 | 831.7456 | 2224.9195 | 14938.7451
LINAC
Tech Support (1/4 time) | 2535.75 | 500.4465 | 201.2902 | 3237.4867
DTS | 5092.32 | 0 | 611.0784 | 5703.3984
MSTC | 8699.38 | 608.9566 | 1628.9589 | 10937.2955
SPEC PROC | 41905.55 | 2933.3885 | 2818.1482 | 47657.0867
TOTAL COST | 281711.016 | 31428.4344 | 32088.2295 | 345227.68
ELECTRICITY COSTS (Est. Only)
Based on 12 MW above 3 MW base X $85 Mwhr | 171360 | 0 | 0 | 171360
Sub-TOTAL WEEKLY OPERATING COSTS | 453071.016 | 31428.4344 | 32088.2295 | 516587.68
TOTAL DIRECT COSTS |  |  |  | 484499.4504
| HOURLY RATE |  |  | 20187.4771
3 (8HR) SHIFTS
| Full Cost Recovery |  |  | 27253.0941
Rate
Full Cost Recovery Fee (0%) |  |  |  | 0
TOTAL WEEKLY OPERATING COSTS |  |  |  | 516587.68
Cost for 1 shift of operation |  |  |  | 24599.4133