WIN

Monthly Plan

************************ MAY *************************

| Sentel: | NASA: |
| --- | --- |

Develop Purchase Schedule

Deliver Purchase Schedule

************************ JUNE *************************

| Sentel: | NASA: |
| --- | --- |

Initial Equipment Purchase

Detailed Design

User Interface

Database Design

Network Software

Data Compression

Meet with PRACA team to develop user’s guide

Initiate procedure for AD installation

************************ JULY *************************

| Sentel: | NASA: |
| --- | --- |

Initial Equipment Purchase

Continue Detailed Design

Network Roaming

Data Compression S/W

Programming & Testing

Network Roaming Software Development

Data Compression Software Development

Continue meeting with PRACA team to develop user’s guide

Integrate lab prototype

************************ AUGUST *************************

| Sentel: | NASA: |
| --- | --- |

Continue Detailed Design

User Interface (PRACA)

Database Design (PRACA)

Network S/W (PRACA)

Network Roaming

Data Compression

Develop Functional Test Plan

Deliver Critical Design Review Package

Critical Design Review

Continue Programming & Testing

Network Roaming

Data Compression Software Development

Develop S/W Programmer’s Manual

Develop PRACA requirements

Deliver PRACA requirements

********************* SEPTEMBER **********************

| Sentel: | NASA: |
| --- | --- |

Continue Detailed Design

User Interface (PRACA)

Database Design (PRACA)

Network S/W (PRACA)

Develop Functional Test Plan

Continue Programming & Testing

Network Roaming

Data Compression Software Development

Continue Developing S/W Programmer’s Manual

*********************** OCTOBER ************************

| Sentel: | NASA: |
| --- | --- |

Deliver Functional Test Plan

Deliver PRACA CDR Package

PRACA Critical Design Review

Continue Programming & Testing

Data Compression Software Development

Network Roaming

User I/F (PRACA)

Database S/W (PRACA)

Network S/W (PRACA)

Continue Developing S/W Programmer’s Manual

Integration and Test

Test Portable Computer Battery Life

Test Data Compression S/W

Test Network Roaming

Test User Interface & Database Segment (PRACA)

Test Network S/W (PRACA)

Develop of Acceptance Test Procedures

Install Wireless equipment in O&C and SSPF

*********************** NOVEMBER ************************

| Sentel: | NASA: |
| --- | --- |

Deliver Network Roaming Application

Deliver Data Compression Application

Continue Programming & Testing

User I/F (PRACA)

Database S/W (PRACA)

Network S/W (PRACA)

Continue Developing S/W Programmer’s Manual

Continue Integration and Test

Test Network Roaming

Test Network S/W (PRACA)

Test Data Compression S/W (PRACA)

Test User Interface & Database Segment (PRACA)

Continue development of Acceptance Test Procedures

Integrate Data Compression Application with prototype

Integrate Network Roaming Application with prototype

*********************** DECEMBER ************************

| Sentel: | NASA: |
| --- | --- |

Test System Readiness Review

Deliver User Interface & Database Application (PRACA)

Deliver Network S/W Application (PRACA)

Beta Testing at KSC

Continue Developing S/W Programmer’s Manual

Continue Integration and Test

Test Network Roaming

Test Network S/W (PRACA)

Test Data Compression S/W (PRACA)

Test User Interface & Database Segment (PRACA)

Continue development of Acceptance Test Procedures

Integrate Network S/W Application with prototype

Integrate User Interface & Database Application with prototype

************************ JANUARY *************************

| Sentel: | NASA: |
| --- | --- |

System Documentation

Develop Maintenance Manual

Develop User’s Manual

Continue Integration and Test

Test Data Compression S/W

| Test Network Roaming | Complete Preliminary Acceptance Test Procedure |
| --- | --- |

************************ FEBRUARY *************************

| Sentel: | NASA: |
| --- | --- |

Continue System Documentation

Develop Maintenance Manual

Develop User’s Manual

Final Delivery

COTS Documentation

Training/Operations Manual

| Acceptance Test | Develop Final Acceptance Test Procedure |
| --- | --- |

************************ MARCH *************************

| Sentel: | NASA: |
| --- | --- |

Continue System Documentation

Develop Maintenance Manual

Develop User’s Manual

Continue Final Delivery

COTS Documentation

Training/Operations Manual

Acceptance Test

Deliver S/W Programmer’s Manual

Deliver Maintenance Manual

Deliver User’s Manual

Final Report