## items
| topic | owner | backup? | who | draft | final
BI-1 | summary | IRM
BI-2 | value | IRM
BI-3 | technical | CS-OMIS |  | David, Linda
BI-4a | costs | EX
BI-4b | DME costs | CS-ISD
BI-4c | cost assumptions | EX
BI-5 | internal customers | CS-ISD |  | Hassan, Katie
BI-5a | internal references | CS-ISD |  | Hassan, Katie
BI-6 | external customers | CS-ISD |  | Hassan, Katie
BI-6a | external references | CS-ISD |  | Hassan, Katie
BI-7 | metrics | CS-ISD |  | David, Karen
BI-8 | migration strategy | CS
BI-9 | cost model | EX
BI-9a | pricing model | EX
BI-10 | availability | CS-OMIS |  | David, Linda
BI-11 | compliances | CS-ISD |  | David, Katie
BI-12 | keeping current | CS-ISD |  | David, Katie
BI-13 | customer satisfaction metrics | CS-ISD |  | David, Katie
C1.1
C1.2
C1.3
C1.4
C1.5
C1.6
C1.7
T1.1
T1.2
T1.3
T1.4
T1.5
C2.1
C2.2
C2.3
C2.4
C2.5
C2.6
C2.7
C2.8
C2.9
C2.10
T2.1
T2.2
T2.3
T2.4
C3.1
C3.2
T3.1
T3.2
T3.3
T3.4
T3.5
T3.6

## cost model
Component | unit cost | units | total | work time - days | elapsed time - days
Requirements definition
Systems Analyst
Project Manager
Technical Writer
Development
Systems Analyst | 80
Database Administrator | 95
Web Systems Programmer | 80
QA Systems Tester | 60
Project Manager
Instructional Systems Designer
Implementation
Network Administrator
Database Administrator
Application Administrator
Web Systems Programmer
QA Systems Tester
Project Manager
Instructor
Operations & Maintenance
technical support (type)
backups
product/network troubleshooting
scheduled upgrades
emergency patches
end user helpdesk staffer
infrastructure upgrades

## responsibilities
Component | Required | Optional | JSAS | Customer
Requirements definition | X |  | X | X
Systems Analyst
Project Manager
Technical Writer
Development |  | X | X | X
Systems Analyst |  | X
Database Administrator |  | X
Web Systems Programmer |  | X
QA Systems Tester |  | X
Project Manager |  | X
Instructional Systems Designer |  | X
Branding alterations | X |  | X
replace State logos & references | X |  | X
Remove CISP | X |  | X
Implementation | X |  | X
Network Administrator | X |  | X
Database Administrator | X |  | X
Web Systems Programmer | X |  | X
QA Systems Tester | X |  | X
Project Manager | X |  | X
Instructor |  | X
Infrastructure maintenance | X |  | X
Infrastructure refreshment | X |  | X
Conform to minimum configuration | X |  |  | X
Operations & Maintenance | X |  | X
technical support (type)
backups | X |  | X
product/network troubleshooting | X |  | X | X
scheduled upgrades | X |  | X
emergency patches | X |  | X
end user helpdesk staffer | X |  | X | X
infrastructure upgrades | X |  | X

## pricing model - turnkey
Component | unit cost | units | total | work time - days | elapsed time - days
Requirements definition
Systems Analyst | 80 | 16 | 1280
Project Manager | 85 | 12 | 1020
Technical Writer | 65 | 24 | 1560
Development
Systems Analyst | 80 | 40 | 3200
Database Administrator | 95 | 40 | 3800
Web Systems Programmer | 80 | 240 | 19200
QA Systems Tester | 60 | 40 | 2400
Project Manager | 85 | 40 | 3400
Instructional Systems Designer |  |  | 0
Implementation
Network Administrator | 95 | 8 | 760
Database Administrator | 95 | 16 | 1520
Web Systems Programmer | 80 | 16 | 1280
QA Systems Tester | 60 | 0 | 0
Project Manager | 85 | 40 | 3400
Instructor |  |  | 0
Infrastructure maintenance |  |  | 0
Infrastructure refreshment |  |  | 0
Operations & Maintenance
technical support (type) | 0 |  | 0
backups | 0 |  | 0
product/network troubleshooting | 0 |  | 0
scheduled upgrades | 1000 | 1 | 1000
emergency patches | 1000 | 1 | 1000
end user helpdesk staffer | 56 | 40 | 2240
infrastructure upgrades | 0 |  | 0
47060

## pricing model - hosted
Component | unit cost | units | total | subtotals
Requirements definition
Systems Analyst | 80 | 16 | 1280
Project Manager | 85 | 12 | 1020
Technical Writer | 65 | 24 | 1560 | 3860
Development Registration/Tracking
Systems Analyst | 80 | 40 | 3200
Database Administrator | 95 | 24 | 2280
Web Systems Programmer | 80 | 120 | 9600
QA Systems Tester | 60 | 40 | 2400
Project Manager | 85 | 40 | 3400 | 20880
Development* - Cyber Course
Systems Analyst | 80 |  | 0
Database Administrator | 95 |  | 0
Web Systems Programmer | 80 |  | 0
QA Systems Tester | 60 |  | 0
Project Manager | 85 |  | 0
Instructional Systems Designer | 80 |  | 0
Branding change |  | 1 | 1000 | 1000
Implementation
Network Administrator | 95 | 80 | 7600
Database Administrator | 95 | 40 | 3800
Application Administrator |  |  | 0
Web Systems Programmer | 80 | 40 | 3200
QA Systems Tester | 60 | 60 | 3600
Project Manager | 80 | 120 | 9600
Instructor |  |  | 0
Infrastructure maintenance | 90 | 8 | 720
Infrastructure refreshment |  |  | 0 | 28520
Operations & Maintenance
technical support (type)
backups | 60 | 24 | 1440
product/network troubleshooting | 100 | 48 | 4800
product/network troubleshooting | 90 | 10 | 900
scheduled upgrades | 1000 | 1 | 1000
emergency patches | 1000 | 1 | 1000
end user helpdesk staffer (tier 2) | 60 | 4 | 240
infrastructure upgrades | 95 | 40 | 3800
end user helpdesk staffer (tier 1&2) | 56 | 80 | 4480
second tier help desk (ISD) | 75 | 80 | 6000 | 23660
77920
* three tiers of course development
Tier 1: Remove DoS branding and replace with other agency branding (graphics, references to DoS, etc.)
and remove CSIP section - $1,000
Tier 2: Replace agency-specific content where CSIP content was (one module) - $298.00/hr.,
short timeframe to launch (1-2 months)
Tier 3: Course customization and development - $298.00/hr., may take some time for deployment
of modified course (3-6 months)