National Cooperative Soil Survey - Federal Lands Advisory Group (FLAG) Plan for Completing Soil Survey’s and Ecological Sites for the Nation

Presented by Pete Biggam, FLAG Chair, at the National Cooperative Soil Survey Conference

June, 2007

Introduction

This plan was developed by NRCS and NCSS partners in the States, and the Federal Lands Advisory Group (FLAG) whose goal is to develop cooperative solutions for completion and update of soil and potential natural vegetation inventories of the nation, develop common priorities and a common plan that ensures the effective use of agency resources while recognizing the unique missions and objectives of each agency.  FLAG is a national level group whose membership includes those federal agencies actively participating in the soil survey of the U.S. including Bureau of Indian Affairs (BIA), Bureau of Land Management (BLM), Department of Defense (DoD), Forest Service (FS), National Park Service (NPS), and National Resource Conservation Service (NRCS).

Bureau of Indian Affairs (BIA)

The BIA as the primary contact for Native Americans lands desires the completion of primarily 1:24,000 scale soil surveys to support the land management decision making processes. Soil surveys are needed to meet needs for farming, community planning, land development, grazing and forest management. Soil survey and ecological site data are necessary to accomplish land health assessments, grazing permit renewal, energy and mineral permitting and leasing, restoring natural fire processes, restoring health of the land, maintaining clean water and air, and invasive plant control.  Soil information is fundamental in assessing soil capabilities, limitations, and vulnerability to degradation and loss of capacity to sustain the health of the land.

Bureau of Land management (BLM)

The BLM desires the completion of primarily 1:24,000 scale soil surveys on public lands to support the land management decision making process. Soil survey and ecological site data are necessary to accomplish rangeland health assessments, grazing permit renewal, energy and mineral permitting and leasing, restoring natural fire processes, restoring health of the land, maintaining clean water and air, and invasive plant control.  Soil information is fundamental in assessing soil capabilities, limitations, and vulnerability to degradation and loss of capacity to sustain the health of the land.  All public land activity that disturbs the soil benefits from the information and interpretations provided in soil surveys.  Most soil and ecological mapping on public land has been accomplished via reimbursable agreements with the NRCS.

Department of Defense (DoD) - Army

Each Service’s natural resources management implementing guidelines require soils planning level survey as part of an installation’s INRMP.  Each Service either names NRCS as the source from which to obtain soils data or requires that the soil survey be done to NCSS standards and procedures.  Each installation’s mission normally dictates the level of detail needed.  E.g. The Army’s standard is a 1:12,000 soil survey to support installations where millions of miles of vehicle (from ATV’s through main battle tanks) traffic and other land intensive mission training takes place.  On those installations that DoD is closing, clean up requirements often need soil surveys to understand the fate and transport of chemicals and constituents of concern.  Installations needing a soil survey enter into an agreement with the NRCS.  At the installation’s request, the soil survey may be restricted from public access due to national security concerns.

Forest Service (FS)

The National Forest System uses soil resource inventories and terrestrial ecological unit inventories to develop land and resource management plans as well as project plans.  For over fifty years the Forest Service has endeavored to acquire soil data, devise, formulate maps and develop interpretations for land management prescriptions for land managers.  Over the years, the format and level of detail required for displaying soil information has changed and become more data intensive.  Additionally, the Forest Service has pursued an ecological approach to land stewardship.  This evolution has increased the need of soil resource inventories to collect and classify vegetation data in conjunction with progressive inventories along with data storage.   The focus for the Forest Service is on correlating and data base development for areas mapped by Forest Service and on completing surveys at primarily 1:24,000 scale where no modern soil resource inventory or terrestrial ecological unit inventory exists.

National Park Service (NPS)

The NPS Soil Inventory and Monitoring Program is acquiring appropriate, detailed geospatial soil data bases which will define the distribution of soil types, determine their physical, chemical and biological characteristics, and provide interpretations needed to assess soil capabilities, limitations, and vulnerabilities to degradation, as well as promoting a soil conservation ethic and supporting soil resources management, vital signs monitoring, ecological restoration activities, and facilities development decisions within the agency.

The NPS is currently working with NRCS, via Interagency Agreements, to support dedicated soil survey crews in strategic locations to map NPS lands as well as refine and/or develop ecological site descriptions to meet agency needs.

National Resource Conservation Service (NRCS)

NRCS completes surveys and ecological sites on private lands, including Native American lands based on the kinds of information needed to manage those lands.  Traditionally this has meant a Soil Survey at a scale of 1:12,000 to 1:24,000 on cropland and urban land areas, at a scale of 1:24,000 to 1:62,500 on range and forestlands and at a scale of 1:250,000 to 1:1,000,000 to provide a general level of information where more detailed information is not needed or has not been developed.  The soil survey’s show the locations and extent of soils, data about the physical and chemical properties of those soils, and information derived from that data about potentialities and problems of use on each kind of soil in sufficient detail to meet all reasonable needs for farmers, agricultural technicians, community planners, tax commissioners, engineers, homeowners, developers, ranchers, foresters and other land managers, and scientists in planning and transferring the findings of research and experience to specific land areas.

In addition, NRCS provides expertise to enable the NCSS to develop and maintain a uniform system for mapping and assessing soil resources so that soil information from different locations can be shared, regardless of which agency collects it. NRCS also provides training in soil survey to Federal agencies and assists other Federal agencies with their soil inventories on a reimbursable basis.

Status of Soil Survey

Significant progress has been made, but large part of the U.S. remains and many of these lands are intermingled especially in the West.  These intermingled areas make it very inefficient to map only agency or private land areas.   In addition, coordination and priorities have largely been competed at the region, state, forest level, district or county levels with sporadic and fluctuating funding levels.

Plan Actions

In order to accelerate the initial soil survey the NCSS will complete the following actions:

- Re-focus states with initial mapping remaining away from update and maintenance to of older soil surveys to completing the initial soil survey.

- Evaluate production rates for states with initial mapping remaining and where necessary revise rates in order to increase mapping rates.

- Detail agency staff, provide overtime for agency staff and contract for additional staff.

- Develop ecological site descriptions concurrent with completion of these soil surveys.

- Exploit technology to accelerate mapping rates and improve overall quality.

- Review and correlate soil surveys completed by Forest Service and others and input these data into the designated database.  Establish state office staff dedicated to this function.

- Establish monthly teleconferences and biannual meetings to monitor progress and resolve problems.

- Coordinate mapping according to joint priorities in order to maximize efficiencies.

- Shift funding NRCS funding for non-federal lands from states where the initial soil survey is completed to states where initial soil surveys remain.

- Shift SSURGO funding to hire new employees or equivalent contractors to map non-federal lands.

- Increase FY 07 funding from BLM by $600 thousand and Forest Service by to between $500 thousand and $1 million. NPS increases FY07 funding by $500,000 to $ 3.0 million

- Increase FY 08 funding for FS by 12 million per year for a 5 year total of $60 million and funding for BLM by 7.4 million per year for 5 year total of $37 million.

Agency Annual Plans

Bureau of Land Management - First and Second Priority Areas (average mapping rate is 500,000 acres per year in Alaska and 100,000 acres per year for rest of U.S.)

| States | Acres Remaining | FY 07 Acres | FY 08 Acres | FY 09 Acres | FY 10 Acres | FY 11 Acres | FY 12 Acres |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alaska | 13,271,000 |  | 2,654,200 | 2,654,200 | 2,654,200 | 2,654,200 | 2,654,200 |
| Arizona | 2,467,000 |  | 493,400 | 493,400 | 493,400 | 493,400 | 493,400 |
| California* | 12,165,000 |  | 2,433,000 | 2,433,000 | 2,433,000 | 2,433,000 | 2,433,000 |
| Colorado | 35,000 |  |  |  |  | 35,000 |  |
| Idaho | 134,000 |  |  |  |  | 67,000 | 67,000 |
| Montana | 389,000 |  |  |  | 129,667 | 129,667 | 129,667 |
| Nevada | 1,796,000 |  | 359,200 | 359,200 | 359,200 | 359,200 | 359,200 |
| New Mexico | 1,184,000 |  |  | 296,000 | 296,000 | 296,000 | 296,000 |
| Oregon | 6,036,000 | 1,006,000 | 1,006,000 | 1,006,000 | 1,006,000 | 1,006,000 | 1,006,000 |
| Utah | 2,206,000 |  | 441,200 | 441,200 | 441,200 | 441,200 | 441,200 |
| Wyoming | 5,830,000 | 971,667 | 971,667 | 971,667 | 971,667 | 971,667 | 971,667 |
| Total | 32,242,000 | 1,977,667 | 8,358,667 | 8,654,667 | 8,784,333 | 8,886,333 | 8,851,333 |
| AK SY@ 500,000 | 27 | 0 | 5 | 5 | 5 | 5 | 5 |
| AK Cost | $2,123,360 |  | $424,672 | $424,672 | $424,672 | $424,672 | $424,672 |
| Lower 48 SY@ 100,000 | 322 | 20 | 57 | 60 | 61 | 62 | 62 |
| Lower 48 Cost | $25,793,600 | $1,582,133 | $4,563,573 | $4,800,373 | $4,904,107 | $4,985,707 | $4,957,707 |
| Total Cost | $27,916,960 | $1,582,133 | $4,988,245 | $5,225,045 | $5,328,779 | $5,410,379 | $5,382,379 |

Bureau of Land Management - First Priority (Average Rate 100,000 acres per year

| States with Initial Mapping | Priority One Acres Remaining | FY 07 Acres | FY 08 Acres | FY 09 Acres | FY 10 Acres | FY 11 Acres | FY 12 Acres |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Arizona | 2,467,000 |  | 493,400 | 493,400 | 493,400 | 493,400 | 493,400 |
| California | 1,619,000 |  | 323,800 | 323,800 | 323,800 | 323,800 | 323,800 |
| Colorado | 35,000 |  |  |  |  | 35,000 |  |
| Idaho | 118,000 |  |  |  |  | 59,000 | 59,000 |
| Montana | 389,000 |  |  |  | 129,667 | 129,667 | 129,667 |
| Nevada | 836,000 |  |  | 209,000 | 209,000 | 209,000 | 209,000 |
| New Mexico | 1,184,000 |  |  | 296,000 | 296,000 | 296,000 | 296,000 |
| Oregon | 5,524,000 | 920,667 | 920,667 | 920,667 | 920,667 | 920,667 | 920,667 |
| Utah | 1,235,000 |  | 247,000 | 247,000 | 247,000 | 247,000 | 247,000 |
| Wyoming | 4,777,000 | 796,167 | 796,167 | 796,167 | 796,167 | 796,167 | 796,167 |
| Total | 18,184,000 | 1,716,833 | 2,781,033 | 3,286,033 | 3,415,700 | 3,509,700 | 3,474,700 |
| Staff Years @ 100,000 | 182 | 17 | 28 | 33 | 34 | 35 | 35 |
| Total Cost | $14,547,200 | $1,373,467 | $2,224,827 | $2,628,827 | $2,732,560 | $2,807,760 | $2,779,760 |

U.S. Forest Service – Correlation and Database

| States with Initial Mapping | Acres Remaining | FY 07 Acres | FY 08 Acres | FY 09 Acres | FY 10 Acres | FY 11 Acres | FY 12 Acres |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Arizona | 3,350,033 | 0 | 670,007 | 670,007 | 670,007 | 670,007 | 670,007 |
| California | 1,851,601 | 0 | 462,900 | 462,900 | 462,900 | 462,900 | 0 |
| Colorado | 4,924,750 | 0 | 984,950 | 984,950 | 984,950 | 984,950 | 984,950 |
| New Mexico | 1,860,678 | 0 | 620,226 | 620,226 | 620,226 | 0 | 0 |
| Utah | 2,696,514 | 0 | 539,303 | 539,303 | 539,303 | 539,303 | 539,303 |
| Wyoming | 4,114,184 | 822,837 | 822,837 | 822,837 | 822,837 | 822,837 | 0 |
| Total | 18,797,760 | 822,837 | 4,100,222 | 4,100,222 | 4,100,222 | 3,479,996 | 2,194,259 |
| Staff Years @ 500,000 |  | 8 | 41 | 41 | 41 | 35 | 22 |
| Total Cost Per Yr | $501,273.60 | $131,654 | $656,036 | $656,036 | $656,036 | $556,799 | $351,082 |

U.S. Forest Service – Mapping

| States with Initial Mapping | Acres Remaining | FY 07 Acres | FY 08 Acres | FY 09 Acres | FY 10 Acres | FY 11 Acres | FY 12 Acres |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alabama | 15,000 | 0 | 15,000 | 0 | 0 | 0 | 0 |
| Alaska | 439,000 | 0 | 87,800 | 87,800 | 87,800 | 87,800 | 87,800 |
| Arizona | 2,625,563 | 300,000 | 465,113 | 465,113 | 465,113 | 465,113 | 465,113 |
| Arkansas | 250,000 | 0 | 83,333 | 83,333 | 83,333 | 0 | 0 |
| California | 663,783 | 0 | 132,757 | 132,757 | 132,757 | 132,757 | 132,757 |
| Colorado | 3,244,572 |  | 648,914 | 648,914 | 648,914 | 648,914 | 648,914 |
| Florida | 250,000 | 0 | 83,333 | 83,333 | 83,333 | 0 | 0 |
| Georgia | 125,000 | 0 | 62,500 | 62,500 | 0 | 0 | 0 |
| Idaho | 14,141,190 | 0 | 2,828,238 | 2,828,238 | 2,828,238 | 2,828,238 | 2,828,238 |
| Illinois | 29,720 | 0 | 0 | 29,720 | 0 | 0 | 0 |
| Maine | 40,040 | 0 | 15,000 | 40,040 | 0 | 0 | 0 |
| Michigan | 166,060 | 0 | 0 | 0 | 83,030 | 83,030 | 0 |
| Minnesota | 2,098,336 |  | 419,667 | 419,667 | 419,667 | 419,667 | 419,667 |
| Mississippi | 550,000 | 0 | 110,000 | 110,000 | 110,000 | 110,000 | 110,000 |
| Missouri | 273,188 | 0 | 0 | 0 | 54,638 | 54,638 | 54,638 |
| Montana | 7,736,712 | 0 | 1,547,342 | 1,547,342 | 1,547,342 | 1,547,342 | 1,547,342 |
| Nevada | 2,325,128 | 0 |  | 581,282 | 581,282 | 581,282 | 581,282 |
| New Hampshire | 578,187 | 0 | 115,637 | 115,637 | 115,637 | 115,637 | 115,637 |
| New Mexico | 3,812,585 | 300,000 | 702,517 | 702,517 | 702,517 | 702,517 | 702,517 |
| New York | 262,900 | 0 | 0 | 87,633 | 87,633 | 87,633 | 0 |
| Oregon | 9,670,572 | 200,000 | 1,894,114 | 1,894,114 | 1,894,114 | 1,894,114 | 1,894,114 |
| Pennsylvania | 109 | 0 | 109 | 0 | 0 | 0 | 0 |
| Texas | 155,724 | 0 | 100,000 | 55,724 | 0 | 0 | 0 |
| Utah | 985,119 |  | 197,024 | 197,024 | 197,024 | 197,024 | 197,024 |
| Vermont | 109,002 | 0 | 100,000 | 9,002 | 0 | 0 | 0 |
| Virginia | 40,000 | 0 | 40,000 | 0 | 0 | 0 | 0 |
| Washington | 4,016,862 | 200,000 | 763,372 | 763,372 | 763,372 | 763,372 | 763,372 |
| W. Virginia | 214,000 | 0 | 71,333 | 71,333 | 71,333 | 0 | 0 |
| Wyoming | 1,076,450 | 0 | 215,290 | 215,290 | 215,290 | 215,290 | 215,290 |
| Total | 55,894,802 | 1,000,000 | 10,698,395 | 11,231,688 | 11,172,369 | 10,934,369 | 10,763,706 |
| Staff Years @ 100000 |  | 10 | 107 | 112 | 112 | 109 | 108 |
| Total Cost Per Yr | $7,440,070.24 | $800,000 | $8,558,716 | $8,985,350 | $8,937,895 | $8,747,495 | $8,610,965 |

Natural Resources Conservation Service and Bureau of Indian Affairs – Mapping

| States with Initial Mapping | Acres Remaining | Average Mapping Rate | FTE Required to complete Soil Survey | Current (2007 to 2011) Soil Scientist FTE | Out of State Soil Scientist Details FTE | FTE Contract Soil Scientist | FTE Required for ESD | Current 2007 to 2011 FTE for ESD | Date Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Alabama | 1,509,119 | 37,728 | 40 | 30 | 6 |  |  |  | 3/31/2010 |
| Alaska | 15,293,924 | 243,534 | 63 | 29 | 40 |  | 0 | 0 | 9/30/2011 |
| Arizona | 5,955,738 | 88,892 | 67 | 50 | 10 | 7 | 31 | 5 | 9/30/2011 |
| California | 6,322,310 | 61,085 | 104 | 118 | 6 | 0 | 52 | 13 | 9/30/2011 |
| Florida | 273,510 | 39,073 | 7 | 15 | 0 | 0 |  |  | 12/31/2009 |
| Georgia | 1,860,381 | 37,208 | 50 | 30 | 20 |  |  |  | 9/30/2009 |
| Maine | 2,500,000 | 38,462 | 65 | 50 | 15 |  |  |  | 9/30/2011 |
| Minnesota | 2,523,850 | 35,005 | 72 | 50 | 22 | 0 | 0 | 0 | 9/30/2011 |
| Mississippi | 1,199,616 | 34,275 | 35 | 20 | 15 |  |  |  | 12/31/2009 |
| Montana | 1,521,674 | 43,107 | 35 | 90 | 14 | 0 | 4 | 3 | 12/31/2010 |
| New York | 1,794,600 | 40,786 | 44 | 40 | 4 |  |  |  | 12/31/2010 |
| Oregon | 3,849,845 | 59,228 | 65 | 45 | 20 |  | 30 | 3 | 9/30/2011 |
| Texas | 5,567,487 | 64,738 | 86 | 200 |  |  | 49 |  | 10/1/2010 |
| Utah | 2,822,631 | 49,520 | 57 | 30 | 20 | 10 | 20 | 10 | 9/30/2011 |
| Vermont | 366,200 | 40,689 | 9 | 15 |  |  |  |  | 12/31/2009 |
| Virginia | 814,275 | 39,915 | 20 | 45 |  |  |  |  | 9/30/2009 |
| Washington | 794,703 | 51,271 | 16 | 65 |  |  | 6 |  | 9/30/2009 |
| Wyoming | 8,108,642 | 49,143 | 165 | 116 | 98 |  | 20 | 10 | 9/30/2011 |
| Totals | 63,078,505 | 58,537 | 1,000 | 1,038 | 290 | 17 | 211 | 43 |  |

National Park Service Priorities - Mapping (average mapping rate is 500,000 acres per year in Alaska and 100,000 acres per year for rest of U.S.)

| States with Initial Mapping | Acres Remaining | FY 07 Acres | FY 08 Acres | FY 09 Acres | FY 10 Acres | FY 11 Acres | FY 12 Acres |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alaska | 48,563,764 | 8,093,960 | 8,093,960 | 8,093,960 | 8,093,960 | 8,093,960 | 8,093,964 |
| Arizona | 240,458 | 120,000 | 120,458 |  |  |  |  |
| California | 5,888,293 | 888,293 | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 | 1,000,000 |
| Colorado | 158,654 |  | 80,000 | 78,654 |  |  |  |
| Florida | 2,367,095 |  | 473,419 | 473,419 | 473,419 | 473,419 | 473,419 |
| Minnesota | 218,910 |  |  |  | 100,000 | 100,000 | 18,910 |
| Montana | 1,013,572 |  | 213,572 | 200,000 | 200,000 | 200,000 | 200,000 |
| New Mexico | 313,051 |  | 104,350 | 104,350 | 104,351 |  |  |
| South Dakota | 242,756 | 80,919 | 80,919 | 80,918 |  |  |  |
| Texas | 191,265 |  | 91,265 | 100,000 |  |  |  |
| Utah | 1,443,427 | 240,572 | 240,571 | 240,571 | 240,571 | 240,571 | 240,571 |
| Virginia | 199,045 | 66,349 | 66,348 | 66,348 |  |  |  |
| Washington | 1,663,057 | 277,177 | 277,176 | 277,176 | 277,176 | 277,176 | 277,176 |
| West Virginia | 88,006 | 45,000 | 43,006 |  |  |  |  |
| Wyoming | 2,658,280 | 443,050 | 443,046 | 443,046 | 443,046 | 443,046 | 443,046 |
| Total | 65,249,633 | 10,255,320 | 11,328,090 | 11,158,442 | 10,932,523 | 10,828,172 | 10,747,086 |
| Alaska Staff Years @ 500,000 ac/yr | 97 | 16 | 16 | 16 | 16 | 16 | 16 |
| Alaska Total Cost Per Yr | $7,776,000 | $1,296,000 | $1,296,000 | $1,296,000 | $1,296,000 | $1,296,000 | $1,296,000 |
| Lower 48 Staff Years @ 100,000 ac/yr | 166 | 22 | 32 | 30 | 28 | 27 | 27 |
| Lower 48 Total Cost Per Yr | $13,300,000 | $1,728,000 | $2,587,200 | $2,404,800 | $2,270,400 | $2,187,200 | $2,122,400 |
| Total Cost | $21,076,000 | $3,024,000 | $3,883,200 | $3,700,800 | $3,566,400 | $3,483,200 | $3,418,400 |

Summary of All Agencies – Mapping and Ecological Site Description Development

| Agency | Prioritized Acres Remaining (millions) | Required Staff Years for Soil Mapping | Required Staff Years for Ecological Site Development | Total Staff Years Required | Cost per Staff Year | Total Projected Cost (millions) |
| --- | --- | --- | --- | --- | --- | --- |
| BLM | 32.2 | 350 | 115 | 465 | $110k | $51.15 |
| USFS | 55.9 | 558 | 184 | 742 | $110k | $81.60 |
| NPS | 65.2 | 263 | 87 | 347 | $110k | $38.17 |
| DoD - Army | 4.8 | 88 | 29 | 117 | $110k | $12.87 |
| Tribal and Private Lands NRCS/BIA | 63 | 1000 | 306 | 1306 | $110k | $143.66 |
| TOTALS | 221.1 | 2259 | 721 | 2977 | $110k | $327.45 |