## Sheet1
|  |  |  | SAIC-FREDERICK, INC. |  | CONTINGENCY RESERVE LOG - EXAMPLE
PROJECT |  |  |  | TRANSACTION DESCRIPTION |  | COST
Date Initiated | Risk ID # | Work Order # | Trend # | Title | Description | Increase ($K) | Decrease ($K) | Reserve Balance ($K) | Comments
|  |  |  | ESTABLISHMENT OF CONTINGENCY RESERVE | OPENING BALANCE |  |  | 125
2004-02-12 | 1a | 123456 | 1 | Unforeseen subsurface conditions | Subcontractor will need to halt work, additional design required to address conflicts, $10K of the $12K used. Remaining $2K reallocated to item 3 |  | -10 | 115
2004-03-14 | 1c | 123456 | 2 | Unforeseen subsurface conditions | Realignment of project to avoid interference with previously unidentified live utilities, entire $30K used. |  | -30 | 85
2004-03-17 | 1b | 123456 | 3 | Unforeseen subsurface conditions | Removal of previously unidentified abandoned utilities. Entire 5K plue $2K of item 1 used. |  | -7 | 78
2004-04-01 | 1d | 123456 | 4 | Unforeseen subsurface conditions | Subsurface rock increases excavation time and effort |  | -25 | 53 | Risk item not incurred, reallocated to Risk 20
2004-05-04 | 12 | 123456 | 5 | Delays at factory for shop testing of new systems | Schedule slip that impacts installation of connected utilties and delays completion of work by lower tier subcontractors. |  | -20 | 33
2004-06-12 | 13a | 123456 | 6 | Customer initiated cahnges to final design | Replacement of countertops that were previously schedule for reuse in the refurbished lab. |  | -15 | 18
2004-07-02 | 13b | 123456 | 7 | Customer initiated cahnges to final design | Installation of additional storage space |  | -5 | 13
2004-08-01 | 20 | 1123456 | 8 | Startup delayed due to inclement weather | Two week delay due to unforeseen weather conditions that adversely affect startup | 25 |  | 38 | New risk item