# DETAILED ANALYSIS and DESIGN PHASE

# 4.1  		Introduction

_____________________________________________________________

## 4.1.1  	Purpose

During the Detailed Analysis and Design Phase, the Project Manager and the System Development Manager work closely together to:

- Complete business process engineering of the functions to be supported,

- Complete component selection.

- Develop detailed data and process models,

- Refine functional and system requirements that are not easily expressed in data and process models,

- Refine the high level architecture and logical design to support the system, functional, and electronic records management requirements,

- Continue to identify and mitigate risk that the technology can be phased-in and coordinated with the business.

There are three key reviews during the Detailed Analysis and Design Phase: the Detailed Level Requirements Review, Logical Design Review, and the Technical Design Review.  This phase is completed when the Technical Review Board approves the high level architecture and system requirements, revised economic analysis, the logical design including the business process description, and the technical design.  This approval is provided at these three reviews.

## 4.1.2  	Overview

When practicable, the deployment of the new AIS should be planned to coincide with the implementation of new business processes and procedures.

Detailed logical models of business data and processes needed to guide system development are created in the Detailed Analysis and Design Phase, and a description of the technical architecture is refined to guide the allocation of computing resources and capabilities.  When practicable, the deployment of the new AIS should be planned to coincide with the implementation of new business processes and procedures.  The Project Manager and the System Development Manager should continue to assess both business and technical risks and seek additional management support as necessary to manage those risks.  Both the Project Manager and the System Development Manager may wish to document project risks and risk management activities in a risk management matrix for future reference.

## 4.1.3  	Tasks

The primary tasks performed during the Detailed Analysis and Design Phase are as follows:

- Consolidate and affirm business needs,

- Implement AIS project management infrastructure including requirements, configuration, and data management support services and utilities,

- Revise plans to document changes in project scope including changes in business, schedule, and technical requirements,

- Revise plans to document changes in available resources including budget, skills, staff, and training,

- Update list of candidate reuse components, and complete reuse component selection.

- Complete electronic records management requirements,

- Identify data acquisition, conversion, and validation strategies,

- Refine the technical architecture and build architectural prototype,

- Identify design tools, techniques, and procedures,

- Perform detailed AIS analysis and design, and

- Continue planning for AIS testing, training, deployment, operation and business transition, and

- Define and refine detailed requirements and allocate requirements to design.

## 4.1.4  	Activities and Documentation

Detailed Analysis and Design Phase activities and documentation requirements as summarized in the following table must conform to the indicated Technical Standard and Guidelines or other standards as noted.

The set of system requirements that satisfies the Business Case is contained in the Functional Baseline as indicated under the “Functional” subheading in Table 4.1.4.  Work products and design documents included in the Logical Design (Allocated) Baseline are identified under the “Logical Design” subheading in Table 4.1.4.

The Configuration Management TSG, IT-212.2-06, provides additional information about these baselines.  Published standards and guidelines may be augmented with Tailoring Agreements.

|  |  |  |  |  |  | Baseline |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Work Product | TSG/ Standard | Who’s Responsible | Must Create | Should Update | Must Update | Functional | Logical Design | Must Complete |
| Business Case | IT-212.2-13 | Program Sponsor, Project Manager |  |  | X |  |  |  |
| Project Management Plan and supporting baseline project schedules | IT-212.2-01 | Project Manager, System Development Manager |  |  | X |  |  |  |
| AIS Project Quality Assurance Plan | IT-212.2-04 | Office of System Product Assurance |  | X |  |  |  |  |
| Data Management Plan | IT-212.2-05 | Office of Data Management |  |  | X |  |  |  |
| AIS Configuration Management Plan | IT-212.2-06 | Office of System Product Assurance |  | X |  |  |  |  |
| System Boundary Agreement | IT-212.2-10 | Project Manager, System Development Manager |  |  | X |  | X | X |
| Concept of Operations | IT-212.2-11 | Program Sponsor, Project Manager |  |  | X | X | X |  |
| Detailed Design (includes data model, screen shots and report layouts) | IT-212.2-12 | System Development Manager, System Architect | X |  |  | X | X |  |
| Interface Design Definition | IT-212.3-14 | System Development Manager | X |  |  |  |  | X |
| Economic Analysis | IT-212.2-13 | Project Manager, System Development Manager |  |  | X |  |  |  |
| Business Transition Plan | IT-212.3-05 | Program Sponsor, Project Manager | X |  |  |  |  | X |
| Requirements Specification, Part 2 (Completed through lower level requirements) | IT 212.3-11 | Project Manager, System Development Manager | X |  | X |  | X |  |

|  |  |  |  |  |  | Baseline |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Work Product | TSG/ Standard | Who’s Responsible | Must Create | Should Update | Must Update | Functional | Logical Design | Must Complete |
| Requirements Traceability Matrix | IT-212.3-11 | Office of System Product Assurance | X |  |  |  | X |  |
| Test Plan | IT-212.3-01 | Office of System Product Assurance | X |  |  |  |  | X |
| Training Plan | IT-212.3-02 | Project Manager, System Development Manager | X |  |  |  |  | X |
| AIS Security Plan (only if sensitive data) | IT-212.2-08 | Project Manager, System Development Manager |  |  | X |  | X |  |
| Operational Support Plan | IT-212.5-01 | Project Manager, System Development Manager | X |  |  |  |  | X |

Table 4.1.4  Detailed Analysis and Design Phase Activities and Documentation Requirements (Concluded)

# 4.2  		Detailed Requirements Analysis

_____________________________________________________________

Business requirements are intended to state in a concise, complete, and unambiguous manner what the system must do to meet business needs.

Business requirements are intended to state in a concise, complete, and unambiguous manner what the system must do to meet business needs.  Business requirements should not introduce unnecessary design assumptions or technical constraints.  In this phase, the high level data and functions defined in the Concept Phase are transformed into a detailed description from which the system can be developed.  This description will use a combination of textual and graphical representations to express the requirements in a form that users can readily understand.  The functional, data, and support requirements must be approved by the Program Sponsor.  Direct involvement of supported users and business area experts is essential to developing functional and data requirements.  See IT-212.3-11, Requirements Management, for a description of the requirements definition process and documentation requirements.

## 4.2.1  	Functional and Data Requirements Definition

Complete, user-oriented functional and data requirements for the system must be analyzed, defined, and documented.  Screens, reports, and diagrams are useful in documenting the functional and data requirements.  Analysis, definition, and documentation of requirements  ensures :

- All requirements can be traced to the System Boundary Agreement and Concept of Operations.

- Business process descriptions contained in the Concept of Operations are further refined.  The detailed design is captured in the Detailed Design Document and must be consistent with the Concept of Operations.

- Reuse of existing USPTO software components is based on the list of candidate components.  Components identified in the USPTO reuse repository should be evaluated against the AIS requirements to determine if the component meets the system needs as-is, requires a defined set of enhancements, or is incompatible with the AIS requirements.

- The USPTO reuse repository is extended by selecting candidate components to be developed in parallel with the AIS development effort.  For each component selected, a component specification should be defined to document the services offered by the component.

- A logical model is constructed that describes the fundamental processes and data needed to support the desired business functionality.  This logical model will show how processes interact and how processes create and use data.  These processes will be derived from the activity descriptions provided in the System Boundary Agreement and Concept of Operations.  For projects involving migration, old data elements should be mapped to new data elements.

- Functions and entity types contained in the logical model are extended and refined from those provided in the Concept Phase.  End-users and business area experts will evaluate all identified processes and data structures to ensure accuracy, logical consistency, and completeness.

- An analysis of business activities and data structures is performed to produce work products such as, entity-relationship diagrams, process hierarchy diagrams, and process dependency diagrams.

- A detailed analysis of the current technical architecture, application software, and data is conducted to ensure that limitations or unique AIS requirements have not been overlooked.

These requirements must include considerations for capacity and growth.  Where feasible, the I-CASE tool will be used to assist in this analysis, definition, and documentation.

## 4.2.2  	Support Requirements

Additional requirements that affect the design or use of the system must be defined in the Detailed Analysis and Design Phase as indicated below.

- Functional and technical training needed for development, deployment, and operation of the AIS, including associated training schedules and costs, must be coordinated with the business area training representative, system users, and training organizations, such as the Work Force Effectiveness Division and the Patent Academy, in a timely manner.  Section 6.6 provides additional information on training.

- Requirements for logistical and network support needed to develop, deploy, and operate the AIS are identified in this phase and are documented in the Detailed Design and in the Operational Support Plan.  These documents may be updated during follow-on phases.

- AIS review, testing, evaluation, certification, and security requirements are identified, including associated schedules and costs.  Timely coordination with all support organizations involved in addressing these requirements must be provided, particularly for independent, third-party organizations.

- Plans needed to support system development, deployment, training, operation, and maintenance must be developed and coordinated with system users and support organizations, and must be implemented in a timely manner.

- The justification for developing or enhancing an AIS application must always be expressed in business terms.  The specific business needs that must be addressed are referred to as “performance requirements.”  In addressing performance requirements, project management is able to demonstrate that the AIS addresses a set of real business needs and objectives.  Performance requirements focus on improving customer satisfaction, work force accuracy, productivity, responsiveness, and reliability.

## 4.2.3  	Requirements Traceability

Requirements will be captured in a requirements traceability matrix as described in the Requirements Management TSG, IT-212.3-11 for designated AIS projects.  This matrix must show the traceability of the detailed requirements contained in the Requirements Specification, Part 2 to the Detailed Design Document The high level requirements are recorded in the System Boundary Agreement, the Concept of Operations, and the Requirements Specification, Part 1.

## 4.2.4 	Detailed Level Requirements Review

The products of the detailed requirements analysis are reviewed by the Technical Review Board at the Detailed Level Requirements Review. The purposes of this review are to:

- Confirm functional and data requirements,

- Review the candidate component list and selected reusable components.

- Review data and process models (e.g., entity relationship and process hierarchy diagrams),

- Confirm the decomposition of AIS into subsystems (if applicable), and

- Approve the functional baseline.

The documents that are reviewed are: Requirements Specification, Requirements Traceability Matrix, and any changes to documents approved by the Technical Review Board during the Concept Phase. Requirements documents will be validated against the System Boundary Agreement and the Project Management Plan and will be reviewed for completeness and consistency.  See IT-212.2-04, Quality Assurance, for additional guidance in preparing review materials, and attending and conducting Detailed Level Requirements Review.

# Business Transition Planning

______________________________________________________________________________________

Special attention must be given to reducing any adverse impact that may result from the transition process.

Once the Concept of Operations has been accepted by the Program Sponsor, the Project Manager will work with the business area to plan how the organization will migrate to the desired business process.  The Project Manager will use the Concept of Operations TSG, IT-212.2-11, as the guideline for designing and planning transition activities.

## 4.3.1  	Transition Activities

Transition activities cover all personnel, business process, budget, and organizational changes.  Each transition activity is a required task and includes activities such as: revising policies, procedures, and job descriptions, providing training, establishing standard office formats, and providing necessary facilities and infrastructure to accommodate computer systems or work activities. In developing the transition activities, the Project Manager should coordinate with USPTO management to work with the unions to identify specific activities regarding labor management relations that must be implemented to provide a smooth transition to the new business processes.  The accumulation of all transition activities will form the Business Transition Plan (refer to IT-212.3-05).  All transition and change management activities will be documented and tracked in the Project Management Plan according to IT-212.2-01.

## 4.3.2  	Preparing the Organization for Change

Special attention must be given to reducing any adverse impact that may result from the transition process.  Project Managers should prepare their organization to effectively cope with change by building consensus among key personnel in affected groups. This can be accomplished by establishing more effective communications with internal and external customers, effectively managing labor relations through early and frequent communications, and by openly discussing anticipated changes with employees.

# 4.4  		AIS Technical Architecture and Detailed Design

_____________________________________________________________

In the Detailed Analysis and Design Phase, the technical architecture for the AIS is described in sufficient detail to guide the integration of applications and data to be developed in later life cycle phases .

A technical architecture is a detailed design of the AIS hardware and software components, and their interrelationships.  In the Detailed Analysis and Design Phase, the technical architecture for the AIS is captured in the Detailed Design Document and described in sufficient detail to guide the integration of applications and data to be developed in later life cycle phases as specified in the Detailed Design TSG, IT-212. 4-12.  The allocated baseline is established by mapping detailed requirements to the architectural elements identified in the high level architecture.

The detailed design must show the major types of processing platforms, how they interconnect, and the allocation of processing and storage resources to ensure that business requirements can be satisfied within system boundary constraints.  An analysis of the architecture's capabilities must be conducted to determine performance and growth constraints in hardware, operating system software and utilities, and support software.  All external system interfaces and internal subsystem interfaces must be identified and defined as specified in the Interface Design Definition, IT-212.3-14. The following policies are applicable to defining the technical architecture for this phase.

## Use of Existing System Components or Commercial Off-The-             Shelf (COTS) Products

The use of reusable components and COTS products, which comply with the USPTO Technical Reference Model, may significantly reduce the effort required to develop, test, and deploy the AIS...

The use of reusable components and/or COTS products, which comply with the USPTO Technical Reference Model, may significantly reduce the effort required to develop, test, and deploy the AIS, and should be a consideration in defining the AIS architecture.  Design of new systems, subsystems, or components should be initiated only after a review of COTS products and existing USPTO system components indicates that COTS or existing PTO system components can not be used or economically modified to satisfy functional requirements.

## 4.4.2  	Design Characteristics

The Detailed Design must comply with the USPTO Technical Reference Model.  The technical architecture will:

- Define the hardware, software, and network components in which the AIS will operate,

- Show how functional, data, and electronic records management requirements will be allocated among these components, and

- Describe the means used to interconnect these components.

Characteristics of the detailed design specified during the Detailed Analysis and Design Phase should establish confidence that the system components, when integrated, will meet all functional, performance, and support requirements.  The detailed design establishes a level of uniformity for further AIS design and development.  Architectural limitations, such as the ability to handle changing user needs, increased performance, and upward compatibility to new technologies, must be determined, and if necessary, classified as project risks.  The Detailed Design must:

- Allow for maximum automated generation of application-specific code and databases using the CASE tool.

- Allow for maximum reuse of existing system components.

- Employ COTS software products wherever economically feasible.

- Ensure that the application software can be processed on hardware and system software that is either currently available in the USPTO inventory or has been approved for acquisition and delivery in sufficient lead-time to allow for use during the test process of the Development Phase.

- Provide for the collection of performance metrics.

- Provide for including designer-added software capabilities for internal controls to facilitate functional and technical audits of the AIS.

- Specify functional and technical requirements for integration of the AIS with other PTO business processes, as needed.

- Handle sensitive information as specified in security related policies and requirements.

## 4.4.3  	Prototyping

In the Detailed Analysis and Design Phase, emphasis should be given to architectural prototypes that demonstrate the ability to integrate the preferred reusable components or COTS products into a coherent system that can satisfy functional, performance, and support requirements.

The use of prototyping is encouraged.  Prototypes can be useful in refining requirements and may significantly enhance both user and developer understanding of requirements.  Prototypes can also be used to validate portions of the technical architecture against the functional requirements, technical specifications, and may be used to obtain performance measures.  In the Detailed Analysis and Design Phase, emphasis should be given to architectural prototypes that demonstrate the ability to integrate the preferred reusable components or COTS products into a coherent system that can satisfy functional, performance, and support requirements.

## 4.4.4	Peer Reviews

Peer reviews will be conducted on designated critical AIS projects to identify and remove defects from the products early and efficiently.  Peer reviews can be particularly effective when used to review the work products and documentation developed during the Detailed Analysis and Design and Development phases of the life cycle.  AIS or infrastructure project development documentation will be reviewed in accordance with the Quality Assurance TSG, IT-212.2-04.  For designated AIS projects, reviews, inspections and walk-throughs will be scheduled, conducted, tracked, and the results reported in accordance with the project's Quality Assurance Plan.

# 4.5  		Subsystem Identification, Definition and Management

_____________________________________________________________

## Evolutionary Development and Incremental Delivery of Capabilities

Based upon an analysis of the business processes, the Project Manager and the System Development Manager should focus on providing end users with needed capabilities as early as practical.

The Project Manager and the System Development Manager are encouraged to follow an evolutionary development approach and divide up the AIS Project into several smaller components or subsystems.  Based upon an analysis of the business processes, the Project Manager and System Development Manager should focus on providing end users with needed capabilities as early as practical.  Typically each subsystem performs a unique function and supports an easily identifiable segment of the desired business process.  Subsystem identification and definition occurs early in the Detailed Analysis and Design Phase.

Subsystems must be identified in the high level architecture and sufficiently documented to support adequate subsystem testing, integration, and integration testing.  The Project Manager and the System Development Manager allocate requirements to subsystems based upon commonality of purpose in such a manner as to minimize the number of interactions that must occur between distinct subsystems.  Interfaces between subsystems will be identified in terms of shared entities and functional services.  Project management must update the Quality Assurance Plan to show the documents and reviews planned for each subsystem.

The Project Management and Business Transition Plans should be reviewed and updated to ensure that subsystem deployment is synchronized with changes in business practices and procedures.  A Functional Baseline may be established at the end of the Detailed System Analysis Subphase and subsystem changes controlled in accordance with the Configuration Management TSG, IT-212.2-06.

## 4.5.2  	Subsystem Project Management

The System Development Manager will designate a Lead Analyst for each subsystem to be developed.  The Detailed Design Document and the Interface Design Definition will  reflect the scope, requirements, performance measures, cost, and schedule for the system, including the subsystems.  The individual subsystems will be controlled and coordinated within the boundaries established by the project System Boundary Agreement.  See IT-212.2-12 and IT-212.3-14 for guidance on developing and documenting the Detailed Design Document and the Interface Design Definition, respectively.

# 4.6  		COTS Detailed Analysis and Design Considerations

_____________________________________________________________

COTS software products seldom provide the functionality necessary to address all business requirements.  System Development Managers will not modify the COTS product.  USPTO unique requirements not provided by the COTS product will be satisfied through application program interfaces. Unless the COTS software firm fully supports USPTO unique modifications and makes them generally available to the public, the software package is no longer a COTS package.  At this point there is a significant risk to the USPTO that the former COTS package may not perform as expected or be supported over time.  Moreover, if the System Development Manager implements a modification in a COTS product, it may be very costly, if not impossible, to obtain vendor support in resolving software performance issues, even those apparently unrelated to the modification.

The System Development Manager must consider the time and skills needed to integrate COTS components into an AIS.  Developers must specify, design, code, document, and test “in-house” software that will support COTS integration.  When constructing COTS integration software, it may be necessary to verify COTS specifications and performance through unit testing or with prototypes.  The System Development Manager must also keep in mind that new versions or COTS upgrades may alter the external interface to the COTS package.  Software developers may find that it is necessary to design, integrate, and test integration software for new COTS releases to ensure compatibility with the existing AIS and other COTS components of the AIS.  The System Architect will approve the selection of COTS software products.

# 4.7  		Project Risk Management

_____________________________________________________________

During this phase the Project Manager and System Development Manager will continue to identify and evaluate risks to AIS project requirements, cost, and schedule.  Issues related to managing AIS project requirements, creating AIS designs and supporting plans, and establishing realistic Subsystem Boundary Agreement conditions, contribute to project risks during this phase.  Risks associated with an inability to quantify, verify, or test requirements can also begin to affect AIS project performance during this phase.  The most significant risks during this phase, however, are typically risks that result from an inability to monitor or evaluate the effectiveness and timeliness of AIS analysis and design.  Peer reviews can provide useful information used to identify risk classes, establish risk management criteria, and establish risk management measures associated with analysis and design activities. The risk management section of the Project Management TSG (IT-212.2-01) provides additional guidance for managing AIS project risks.

# 4.8  		AIS Security

_____________________________________________________________

The AIS project  team may apply information provided in the preliminary risk assessment to prototype security measures and safeguards.  Developers may use this information to enhance back-up, contingency, and operational support plans.

During the Detailed Analysis and Design Phase project management will initiate preliminary steps to systematically identify and analyze AIS security requirements.  The Project Manager should work closely with the security analysts in the Office of Information Systems Security (OISS) in analyzing security requirements.  The AIS project team may apply information provided in the preliminary risk assessment to prototype security measures and safeguards.  The System Development Manager may also use this information to develop back-up, contingency, and operational support plans.  The Project Manager will advise the Program Sponsor, the CIO, the Systems Development Manager, and the OISS on matters of significant security threats.

## 4.8.1  	Security Analysis and Design

Both the Project Manager and the System Development Manager must work closely with USPTO security analysts to identify, analyze, and prioritize AIS security issues during this phase.  With the assistance of AIS security specialists the AIS project team will determine what security features, assurances, and operational practices are appropriate to address these issues.  In designing the AIS, the System Development Manager must incorporate these security requirements into the AIS design specifications.  AIS security analysts will evaluate security requirements, designs, and supporting plans upon request and will advise project management, the Program Sponsor, CIO, or the Technical Review Board regarding areas of weakness or needed improvement.

### 4.8.2  	Determining Security Requirements

Security requirements should be developed at the same time system requirements are defined.  These security requirements can be expressed as technical features (e.g., log-in procedures or other access controls), assurances (e.g., background checks for system developers and users), or operational practices (e.g., awareness and training).  The Project Manager, System Development Manager, OSAE, and USPTO security analysts must actively work together to ensure that the technical designs reflect the system’s security needs.  AIS security requirements, like other system requirements, are derived from a number of sources including law, policy, applicable standards and guidelines, functional needs of the system, risk assessment, and cost-benefit trade-off and are documented in the risk analysis.

## 4.8.3  	Incorporating Security Requirements into Specifications

Security analysts will provide the Project Manager with reports that identify, estimate, and evaluate significant security issues, and, if requested, will research and recommend safeguards that address these issues.  This analysis can result in voluminous amounts of information that must be validated, updated and organized into detailed security requirements and specifications.

During the development of AIS security specifications, it may become necessary for the Project Manager to re-examine initial risk assessments to ensure that all requirements are compatible and feasible to implement.  The Project Manager must be able to determine that security features and practices will work correctly and effectively as early in the system life as possible.  The Project Manager will brief the Program Sponsor, CIO, or Technical Review Board as recommended by the security analyst.  Based upon the recommendations of the Project Manager, the Program Sponsor or the CIO may assign additional staff or allocate additional resources to ensure the development of that adequate AIS security specifications.

4.9  	Logical Design Review

_____________________________________________________________

The Logical Design Review will confirm that the business area logical model is sufficiently complete, correct, and stable to allow for the Development Phase to begin.

The products of the detailed requirements analysis, including the high level architecture and support plans must be reviewed by the Technical Review Board.  The Logical Design Review will confirm that the business area logical model is sufficiently complete, correct, and stable to allow for the physical design to begin.  Deficiencies identified in the logical model must be resolved, and changes generated by the review must be incorporated into the logical design as directed by the Technical Review Board.  The High Level Architecture will be reviewed to verify its ability to satisfy the approved functional, data, and support requirements.  Components of the logical model and other requirements shall be allocated to components of the technical architecture.  Traceability shall be demonstrated to ensure that decisions concerning the high level architecture account for all allocated requirements.  Issues governing the possibility of future change in the business or information technology infrastructure and the ability of the information and technical architectures to endure those changes shall be identified and appropriately addressed.  This includes an analysis of the performance and growth requirements for the system throughout its planned operational use.  Support plans will be validated against the Project Management Plan and will be reviewed for completeness and consistency.  The support plans which are reviewed are: Test Plan, Training Plan, components of the Operational Support Plan including provisions for network and computer equipment support, and any changes to plans approved by the Technical Review Board during the Concept Phase.  The Logical Design Review (which may be conducted as one or more events) will be conducted in accordance with IT-212.2-04, Quality Assurance.  The approved High Level Architecture and approved products of detailed requirements analysis shall be placed in a Logical Design (allocated) Baseline under configuration control.

## Technical Design Review

______________________________________________________________________________________

The Technical Design Review is conducted during the Detailed Analysis and Design Phase to evaluate the appropriateness of the technical design.  This review verifies that the system conforms to the infrastructure baseline.  The products of the Detailed Analysis and Design Phase, and updates to existing plans and specifications must be reviewed by the Technical Review Board.  The Technical Design Review will confirm that the AIS or infrastructure system design is complete, correct, and ready for the Development Phase to begin. The Technical Design Review will be conducted in accordance with IT-212.2-04, Quality Assurance.

## Analysis and Design Considerations

_______________________________________________________________________

The overriding consideration when beginning to implement the final code and architecture for a system is to thoroughly understand the requirements and design.  The following should be in place to begin development or existing problems/design holes will only be amplified down the road with project delays, unhappy users, and cost overruns.

- Requirements should be known in detail.  Functional requirements should be linked to the finished design.  Detailed finalized screen formats, menu items, fields (mandatory and optional), and report layouts are necessary to proceed.

- The database design should be complete.  The physical design and its mapping to interfaces, screens fields and reports columns must be solid.

- The mapping of legacy data to the new physical database should be established for all fields.  Methods for handling rejected conversion data and illegal data values should be in place.

- User access levels should be known.  The functionality, data, and fields each user type is allowed to access should be detailed.

- An estimate of frequency and size of all transactions, number of users, user screen use, report volumes should be created.  This will ensure that the architecture and hardware products are sufficient to support required response times and data volumes.

- Key Volume Indicators (KVI), process static reporting, management information requirements, maintenance hooks, and other enterprise-wide requirements should be addressed in this phase.

- Design elements that are not defined because the requirements are not finalized due to technical risk elements that require prototyping should be identified in the Detailed Design Document and completed in the Development Phase.