FORREMS PERFORMANCE MONITORING REPORT 2004

# EXECUTIVE SUMMARY

USAID/FORREMS selected three biodiverse ecosystems to achieve Strategic Objective Number Five (5) SO5 “Improved Natural Resource Management in and Outside Protected Areas by and for Stakeholders”.

FORREMS project implementing partners comprise KWS, FD, KEFRI, AWF/LWF, NK and NEMA in collaboration with community stakeholders in three (3) focal areas through Participatory Forest Management (PFM), Range Rehabilitation and Environmental Management. Partners have formed teams providing leads in Mukogodo Landscape, Mt. Kenya and Arabuko Sokoke Forest (ASF).

Mukogodo focal area implementing partners include AWF/LWF, KEFRI, NEMA, FD, and KWS. FD and KWS work jointly in Mt. Kenya, whereas ASF implementing team includes NK, FD, KWS, KEFRI and NMK.

FORREMS M&E committee developed clear and measurable reference indicators as guiding parameters for the achievement of SO5 through four Intermediate Results (IRs);

IR 5.1 ‘Site Specific Initiatives For NRM Implemented Outside Protected Areas’,

IR 5.3 ‘Improved Management of Protected Areas’ and

IR 5.4 ‘Environmental Policy and Legislative Reform Advanced’.

Partners identified problems and needs relevant in their areas of activity and laid workplans leading to the achievement of the Strategic Objective.

- Mukogodo activities have achieved high land use change. A wide range of tools and technologies have been adapted for participatory dry land conservation. The following Nature Based Enterprises (NBEs) have been established under FORREMS; hay bailing, fodder production, agro-forestry, and seedling production. Aloe farming has also gained support from the FORREMS program.

- In NW Mt. Kenya, fifty-three (53) ha of degraded sites have been mapped and identified for reforestation or restocking. This exercise, including seedling procurement, involved individual and CBO stakeholders who benefited financially.  Fourty-two (42) ha have been reforested through the rehabilitation program of Magacha block in Irangi forest. Boundary mapping between plantation forests and indigenous forests has been proposed and Terms of Reference (TOR) put in place. A reconnaissance survey has been conducted for Two hundred and fifty (250) ha set for commercial plantation improvement. Mount Kenya Joint Management Task Force  (MKJMTF) has been revived under the MOU and TORs set.

- Arabuko Sokoke Forest includes the forest adjacent dwellers within a five (5) Km belt around the forest reserve. Project target areas include Dida, Mida, Kararacha, Kakuyuni and Mabuani. The main activities in 2003/04 have been the completion of the Pilot Participatory Forest Management in Dida, consolidation of the existing nature based enterprises, Aloe vera farming and creation of community structures that will facilitate the delivery of the project objectives. Specific activities include agro-forestry in community lands, beekeeping, butterfly farming, eco-tourism enterprises. Around the forest 22ha of woodlots have been planted. A sum of 2,043 stakeholders have benefited through workshops and training.

Through the FORREMS program some partner institutions have been strengthened through staff training for improved decision-making in NRM inside and outside protected areas. Equipment such as vehicles, computers, digital cameras, LCD projector, etc have also been procured.

# 1.0	INTRODUCTION

## Project Background

USAID’s Forestry/Range Rehabilitation and Environmental Management Strengthening initiative (FORREMS) is a four and-a-half year program within the Mission’s Natural Resource Management (NRM) portfolio. Subject to availability of funds, it has an estimated funding level of about $5.1 million and should conclude in September 2006. FORREMS will support two components:

Strengthening the Government of Kenya NRM institutions through capacity building, technical assistance and material support with focus to improving forest management, rangeland conservation and environmental management.

To involve community user groups in NRM through organizational capacity building to facilitate active participation of CBOs in conservation and Nature Based Enterprises. The community beneficiaries will have more incentives to contribute to improved NRM through PFM.

## FORREMS Intermediate Results

The FORREMS program will contribute to the strategic objective number five (5) “ Improved natural resource management in targeted biodiverse areas by and for stakeholders”, through the following three (3) Intermediate Results;

{Contributing to each of these IRs is a set of Sub-IRs as explained in the Results Framework.(Appendix I)}

- IR 5.1 Site specific initiatives for NRM implemented outside PAs

- IR 5.3 Improved Management of PAs

- IR 5.4 NRM and Environmental policy and legislative reform advanced

## 1.3	brief on project sites

The FORREMS program’s geographic focus has been selected on the basis of rich biodiversity, critical water resources, remnant indigenous forests, the potential for significant economic benefits to local communities and USAID’s strategic NRM objective for Kenya. These focal areas include:

- Mukogodo division in Laikipia district

- North West Mt. Kenya, and

- Arabuko Sokoke Forest in North Coast.

### 1.3.1	MUKOGODO LANDSCAPE

The area for project implementation comprises Mukogodo forest reserve measuring 26,000 ha including the neighboring four group ranches namely Kuri kuri, Makurian, Lekuruki and Il Ngwesi, located in Mukogodo Division, Laikipia district, Rift Valley Province. The landscape also borders large-scale private ranches of Borana, Lodiaga, Lewa Downs Conservancy and Isiolo District.  Maasai communities who have a strong tradition of natural resource governance and management inhabit the project area.  The group ranch committees are responsible for resource allocation, distribution and management within the group ranch.  The communities have divided the forest reserve into four areas with each ranch being responsible for management of its portion of the forest. Most parts of the group ranch are degraded due to overgrazing and soil erosion. There is potential for development of nature-based enterprises in four group ranches.  Prior to the inception of FORREMS program, two group ranches, Lekuruki and Iingwesi group ranches had  developed community lodges namely Tassia and Il Ngwesi. Multiple stakeholder involvement in Natural Resources Management is aimed at making natural resources more responsive to local needs. The argument is that if decision making can be brought closer to the primary users, then resources will be more efficiently, equitably and sustainably managed in line with their local long-term interests. The four group raches cover a total area of 61,516 ha and the area identified for conservation is approximately 11,022 ha.

Site Specific Interventions

- Rehabilitation of degraded rangelands

- On-farm tree planting

- Natural resource inventories,

- Developing and implementing integrated land use plans

- Participatory forest management initiatives

- Enterprise development

- Water points development

- Fodder/grass bulking

- Capacity building in community organization maintenance.

### 1.3.2	MT. KENYA

Mt. Kenya is located on the Eastern side of the Great Rift Valley. The Northern slopes reach the Equator 180km North of Nairobi. It covers Nyeri and Kirinyaga districts in Central Province and Meru Central, Meru South and Embu districts in Eastern Province.

FORREMS identified Mt Kenya as a focal area on the basis of its rich biodiversity, critical watershed, critical habitat, indigenous forests, potential for significant economic benefits to the local communities.

Six forest stations1 covering 98,105 ha in North West Mt. Kenya were chosen as target areas. This is because they are prone to fires, high human/wildlife conflicts, wildlife/plantation conflicts and illegal activities. Other areas of consideration include Irangi and Imenti forests.

Mt Kenya is surrounded by a high potential agricultural area with a population of 450,000 individuals. Illegal activities threaten conservation of indigenous tree species and commercial plantations. These activities also threaten the continuity of the National/forest reserve (N/FR). Incidences of encroachment into the PAs are high. Community forest user groups are collaborating with FD and KWS within PFM framework.

Site Specific Interventions at Mt Kenya

- Rehabilitation of indigenous forest;

- PFM in plantation management

- Woodlots and fuel wood harvesting;

- Professional training in forest management;

- Infrastructure development;

- On-farm forestry;

- Timber marketing;

- Support to key CBOs

- Advancing a management partnership between KWS and FD;

- Development of management plans.

### 1.3.3    ARABUKO SOKOKE FOREST

The Arabuko-Sokoke Forest (ASF) lies close to the Indian Ocean in Kilifi and Malindi Districts of Coast Province, Kenya. In the 1960s, ASF covered an area twice as large as the 41,765 ha it covers today. It is the last large remnant of the north-coast forests that once dominated Kenya's coastal fringe, and is a globally important forest for biodiversity conservation as well as a vitally important resource for the local communities. ASF is a dominant feature of the local landscape and regulates fresh water flow to the adjacent Mida Creek and mangrove forest. The creek and mangrove in turn provide fish nurseries, important over-wintering grounds for migrant waders, and a nutrient and sediment trap protecting the Watamu coral reef. The Watamu/Arabuko area is the only place in Kenya where reef, beach, creek and forest occur together in this way, offering considerable potential for a landscape approach to Natural Resource Management (NRM).

Project sites, location and area

The project is targeting the forest adjacent dwellers within a 5-kilometer belt around the ASF. There are 18 sub-locations extending around the forest, with 51 villages actually bordering on the forest and having a population of about 104,000 people. The project is administered from the Gede Forest Station and the marketing of the nature based products at the Gede Ruins Museum.

Site Specific Interventions

- Advancing PFM,

- Expanding and diversifying nature-based enterprises,

- Establishing a monitoring and evaluation program,

- Strengthening institutions and partnerships,

- Ecosystem management inside and outside the Forest (agro-forestry, alternative fuel supply, fire control, boundary marking, rehabilitation and restoration, problem animal control, linking with District Environmental Committees in planning and problem solving),

- Gender, equity, empowerment

- Advancing policy.

# INSTITUTIONAL PARTNERS

### Kenya Wildlife Service (KWS)

The mandate of KWS is to conserve and manage wildlife in Kenya.   KWS has five sections that participate in FORREMS – the Central Monitoring and Evaluation Unit, Forest Coordination Unit (‘Forestry’), Ecological Monitoring,  GIS  and Laikipia Station (KWS mandate)

### 1.4.2 	Forest Department (FD)

The Forest Department collaborates with KWS, NMK, KEFRI, AWF/LWF, NEMA, Community Forest User Groups and other relevant stakeholders in drafting guidelines and approving management plans for improved management of forests consistent with the proposed forest policy framework and anticipated new forest legislation.

The mandate of the Forest Department is to contribute to the growth of the natural resource sector by enhancing development, conservation and management of all forest resource base in the country. This entails ensuring an increasing supply of forestry products and services for meeting the basic and industrial needs of the present and future generations.

### 1.4.3 Kenya Forestry Researcy Institute (KEFRI)

KEFRI collaborate with FD, KWS, NEMA and AWF/LWF in Laikipia and FD, PACT Kenya in Taita Taveta.  In Arabuko Sokoke forest, KEFRI is one of the main working with FD, KWS, NMK and Nature Kenya. KEFRI has shared their experiences in Dryland Rehabilitation, PFM, development of strategic plan, and on-farm tree planting with community members during awareness creation meetings. KEFRI brings demonstrated expertise in the use of these technologies to FORREMS and has played a vital role in extending these management practices to stakeholders.

### 1.4.4	African Wildlife Foundation (AWF) / Laikipia Wildlife Forum (LWF)

These bring to bear strong NRM and business development skills.   The Laikipia Wildlife Forum has “ on the ground presence” and a strong constituency through its membership.   The partnership demonstrates improved rangeland and dryland forest management practices among local communities, channeling FORREMS funds to priority NRM developments such as water

points and expanding economic enterprises through business development and training. AWF/LWF works within all the thirteen group ranches including Mukogodo forest and Samburu Nature.

### National  Environmental Management Authority (NEMA)

NEMA is empowered under the Environmental Management and Coordination Act (EMCA) to develop guidelines and regulations relating to overall environmental conservation and management and to ensure all users of Kenya’s natural resources comply with these regulations. NEMA is also involved in Environmental Assessment and establishment of environmental protection guidelines.

NEMA has two main objectives:

a) To develop the guidelines and regulations that will operationalize EMCA (e.g., guidelines for EIA and environmental audits, for environmental screening and for conservation orders and environmental easements). Further the FORREMS Program will support infrastructure development.

b) To build the capacity of local authorities to ensure compliance with EMCA.  Here, a particular area of focus will be to assist local partners in the use of these guidelines in planning development activities.  At the local level, partners will also work with DECs to address conservation priorities through action plans for managing marine resources, forests and rangelands and with resources to implement and leverage resources in support of plans. Additional support will help establish functional offices and enable DECs to interact with communities in establishing environmental easements

### 1.4.6	Nature Kenya (NK)

The key role of Nature Kenya is program management and coordination, ensuring the delivery of planned activities to achieve the planned outputs to the intermediate results under 5.1, 5.2, 5.3 and 5.4. Nature Kenya is implementing the project with the Arabuko Sokoke Forest Management Team (ASFMT) that comprises of officers from the KWS, FD, NMK and KEFRI stations in Malindi and Kilifi Districts. At the community level Nature Kenya works with Forest Adjacent Dwellers Association  (FADA), an umbrella of CBOs around ASF, to engrain PFM and nature based enterprises. Nature Kenya and the ASFMT are building their capacity to participate in Natural Resource Management at ASF ecosystem.

## 1.5	Anticipated Project Results

As progress towards SO5 objective, target results for the first year of implementation have been set. The performance indicators have been projected as follows:

- Positive land use change is expected at 6,113 ha across the three focal areas. Positive land use change will be indicated by number of hectares under improved NRM. This will constitute land management actions, dedicated to natural resource conservation, protection and/or improved management. At the project sites, areas under improved management will be delineated using participatory mapping and GIS.

- Number of stakeholders directly or indirectly benefiting from involvement in improved NRM is expected to total 661 persons in the year 2004. The direct beneficiaries will receive funding, training, technical assistance, resource or financial returns under the program. Indirect beneficiaries are those who receive ‘spin-offs’ or ‘down stream’ positive impact. Disaggregation by gender will be done to determine male/female participation.

- Appropriate conservation tools and technologies adapted for positive land use change will facilitate conservation, protection and sustainable utilization of natural resources. The disaggregation is by geographic area and by gender. Performance target set for year one: five (5) tools and/or technologies in use.

- Organizational capacity of community user groups strengthened. The Organizational Capacity Assessment (OCA) tool has been identified as an important tool to “score” strengths and weaknesses of organizations, thereby the performance will be determined by Organisational Capacity scores of targeted CBOs. FORREMS stakeholders will be trained on Organisational Development to facilitate results.

- Increased benefits from NBEs measured by the number and type of NBEs established i.e. initiated and operational. Revenue generation and other benefits for participants from NBEs is expected from the three focal areas. An increase in number and type of enterprises will contribute to the rural economy.

- Financial and non-financial benefits generated by NBEs: Income in the form of salaries or wages, ‘dividends’ paid from operational profits are expected to double baseline from the third year of programme implementation.

- Functionality of information systems for decision-making:  Index scores are expected to increase, reflecting the level of functionality of improved monitoring, evaluation and reporting systems. This will improve access to accurate information necessary for improved NRM for decision-making.

- Level of NRM and Environmental policy/legislation advancement. The forest policy and bill were targeted for level III i.e. finalization of policy intervention.

1.6	PROJECT MONITORING

### 1.6.1	Linkage to S05 Result Framework

The results framework provided by USAID for the FORREMS program is both a planning and a management tool (Appendix II). It is central to the strategic plan and provides a program-level framework for implementing partners to gauge progress toward the achievement of results and to adjust relevant programs and activities accordingly. The results framework provides an important opportunity for the operating unit to work with its partners and community members to build consensus and ownership around shared objectives and approaches to meeting those objectives.  The results Frameworks therefore functions as an effective communication tool because it succinctly captures the key elements for achieving an objective (i.e. program intent and content).

### 1.6.2	Indicator Reference Sheets

Monitoring and Evaluation workshops have been held at Naivasha, Karen, KWS safari walk and Nanyuki with the M&E task force specifically to develop reference data sheets (Appendix III). The Monitoring and Evaluation committee developed eight indicators for use in measuring the performance of the partners activities in the three focal areas. Three other indicators are still being developed. These include:

- Level of policy & legislative advancement,

- Advancement in ‘competence’ in developing policy and administrative frameworks,

- Advocacy capacity index of targeted groups

These Indicators are either quantitative or qualitative in nature and were generated based on the SO5 results framework.  The indicators were selected according to expected relevance to measure the impact of the FORREMS interventions inside and outside the Protected Areas.

The indicator reference sheets were constructed using a participatory approach. USAID team collaborated closely with development partners, counterparts and beneficiaries during the indicator selection process.

In addition to a precise definition of each indicator, the Performance Indicator Reference Sheet also includes concise information on:

- The relationship of the indicator to the SO, Intermediate Results and related program objectives;

- A plan for data collection (methods, sources, frequency, estimated cost, and responsible organizations or individuals;

- A plan for data analysis, reporting and review (method of analysis, presentation of data, review of data, and targeted reporting population;

- A discussion on quality issues (dates for assessments, limitations, and actions taken to address limitations);

- Information for the performance data table (method of calculation, notes on baseline and targets);

Other comments / information as relevant

# 2.0	Performance Results for 2004

2.1		Table 2 : Showing Summary Of Key Results During 2004 In Focal Areas

| IR | Indicator | Target | Actual | Mukogodo | Mt Kenya | Arabuko-Sokoke | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SO5 Improved NRM in targeted areas by and for stakeholders | Land use change | 6,113ha | 11,294 ha | Range rehabilitation Agroforestry nurseries established A total of 30 ha | 42ha Reforestated, Magacha block | 22ha on farm woodlots planted under PFM 11,200ha Operat. Forest Mgt. Plan and guidelines | Positive land use change has thus far been achieved. |
|  | No. of stakeholders benefiting from involvement in improved NRM | 661 | 2884 | 688: beneficiaries through Inventory training, Forest scouts training, M&E workshop, Organisational development training, Sensitisation and awareness meetings | 153: beneficiaries:- Financial wages to casuals hired for vegetation mapping, seedlings sales by CBO members, senior staff trained in program management, PMP, NRM and Participatory resource management planning | 2043: stakeholders benefited through workshops and training. | Target achieved |
| 5.1 Site specific initiatives for NRM implemented outside PAs & 5.3 Improved management of protected areas | Conservation tools and technologies in use | 5 | 27 | 15: Conservation demo areas on community land, Agroforestry and farm forestry, Tree nurseries on community land and gazetted land, Conservation trusts, NRM plans on GoK lands and community lands,Water management, PFM, grazing management systems, Natural resource fora, Natural resource networks, NBEs, Resource mapping | 6: M&E systems and databases, NRM plans on GoK lands and community lands, Natural resource fora a, Rehabilitation | 6: Buffer zones, Agroforestry (nurseries management, Community nurseries identified farmers identified, species selection), M&E systems and databases, PFM, Natural resource fora , Resource mapping | Number of conservation tools and technologies in use are more than those targeted. Out of twenty (20), fifteen (15) are in use. |
| 5.4.1 Constituencies for NR conservation established | Organisation capacity of community user groups |  |  | Natural resource management, conflict management, Governance and administration | None | None | Partners did not receive OCA training so performance measurement for this indicator was limited. |
|  | Number of NBEs established |  | 9 NBEs Established | 4 NBEs: Hay bailing and fodder production, agroforestry, seedling production, NTFPs | Nil | 5NBEs:Ecotourism, Apiculture, Agroforestry, Aloe farming, Butterfly farming |  |
| 5.11 Site specific initiatives for NRM implemented outside PAs | Financial benefits generated by NBEs |  | US $ 3164 | Nil | Nil | US $ 3164 | More Financial benefits expected in 2005 Non-financial benefits are likely to accrue from financial benefits |

Environmental and NRM policy and legislative reform advanced

Status of policy and legislation environment encouraging community incentives for NRM:

- Forest policy being finalized for presentation to the cabinet and publication into sessional paper after parliamentary approval. It scores 60% (see table 3).

- Forest bill 2004 debated in June 2004, rejected, and will be tabled before parliament as from December 2004. It scores 60%

## 2.2	Challenges And Lessons Learned

Issues Affecting Project Implementation

- The community was very eager to start implementing therefore initiation of projects’ activities was successful. In particular, the proposed projects at Mukogodo were in line with the community’s wishes.

- Through the FORREMS project, implementing partners have been borrowing expertise from each other to enrich their activities on the project sites. Efficiency and strength in teamwork has been realized through focal area implementing teams.

- Awareness, sensitization and organizational capacity building fora have assisted community members to understand project issues.

- Clear lines of responsibility and understanding between partners in the project areas, making it easy to execute work as well as monitor and evaluate progress.

Challenges

- Funds for implementation of single activities held by different partners hence joint workplans and budget are very important. While this may work in some areas, it may be necessary to provide funds to various partners to enable them fully implement those activities where they have a comparative advantage

- Challenges in procurement of equipment due to long process of DA1 forms approval

- Community members appear to be very sensitive about their status in the forest as some of them reside in the forest and have fear of being evicted.  It’s important to maintain the status quo until the planning and PFM process is completed

- Partners have not been prompt in ensuring that the activities and budget flow reach the ground to create impacts.

- Heavy rains that pounded the area in January-March 2004 made roads impassable and delayed implementation of activities.

- Some office bearers of the ILMAMUSI/Mukogodo FAT were not very effective because they were committed in other leadership positions. This hampered progress of key community activities.

- Land claims by the Maasai in Laikipia and consequent invasions of some key farms made area unstable hence threatening key activities.

- The implementation period, eight (8) months was insufficient for accomplishing the first year workplan activities since USAID funds for the project were released late.

Lessons Learned

- Sub-committees appear to be the best arrangement for steering activities since activities under sub-committees were progressing better than work left to specific institutions.

- Local community groups and committees need support to improve their capacity to be able to fully implement their activities e.g. the ILMAMUSI committee.

- Projects, particularly the NBEs that address immediate community needs but also contribute to the conservation of the environment should be emphasized for increased support from communities and impact.

## 2.3	Opportunities and Prospects

- The FORREMS partners will assist the CBOs running tree nurseries in sourcing for market to target commercial tree farmers within the focal areas and buyers from urban areas. In the long term, this would lead to achievement of projected targets and self-sustainability.

- Proposed emergency fire plans will be developed and implemented across borders collaboratively between FD and KWS. This will cover cover the forest reserves and national parks/reserves as well as the adjacent community lands. Concerns by FORREMS partners over including other potential stakeholders such as the Armed Forces Fire Brigade/Engineering Unit have been raised.

- There is room for enjoining KEFRI’s technical and research capacity to complement other partners input to Mt. Kenya project activities such as vegetation cover surveys and rehabilitation prescriptions for the degraded sites and NBE consultancy for market openings.

- Dead wood from senile cedar in the Mukogodo forest reserve protected area in abundant. In the Forest Act a subsidiary legislation which covers the use of forest products exists. This product could be allocated for sale by FD and proceedings ploughed back to the conservation initiatives for Mukogodo under the subsidiary legislation.

- Grazing management plans which consider the needs of the pastoral communities adjacent to the forest reserves will be useful. These, once developed and implemented will facilitate easements as well as relieve fragile protected natural resources bases (i.e. water catchments, indigenous forests) off pressure from livestock and human degrading impacts.

- Improving caves at Naro Moru for eco-tourism to benefit Community Based Organizations in Mt. Kenya ecosystem.

# 3.0	baseline performance indicators and data

### Performance Data Table (PDT)

The PDT (Appendix V) shows targets set for each of the eight indicators. The revised indicators 1 & 2 are in the revised PDT shown in Appendix V. Both of these tables give the baselines and actual performances of the FORREMS activities. From these, the trend of the activities can be determined as declining, stable/constant or increasing (Appendix IV & V)

.

The PDT is meant for guiding partners evaluate the performance of their activities against set targets

The M&E FORREMS workshops decided upon indicator target levels for the Financial Years based on the feasibility of achieving them within the context of available resources. The Performance and thus the targets are expected to increase annually.

### Data Quality Assessments

For  data quality,  all indicators are expected be subjected to quality assessment process whereby they are evaluated on a ten (10) point criteria  as shown below:

- Direct (the measure closely tracks the result it is intended to measure).

- Objective ( the measure is operational precise and uni-dimensional).

- Adequate (the number of measures tracked for a given result should be the minimum necessary to ensure progress toward the result is sufficiently captured)

- Practical (Data can be collected on a timely basis and at reasonable cost)

- Attributable to FORREMS (the extent to which a result is caused by FORREMS sponsored activities)

- Management useful (measure should be deemed useful by program management staff)

- Level of Results Achieved (Measure should reflect progress at the FORREMS program level)

- Reliable (Data is sufficiently reliable quality for confident decision making)

- Quantitative (Indicators are numerical where possible)

- Disaggregated (Indicator data can be disaggregated by gender, age, location, or other dimension where appropriate)

## 3.1	LAND USE CHANGE

Indicator Reference Sheet: FORREMS Indicator #1

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: None FORREMS Result #1: same as SO statement

Indicator: Same as SO level indicator #1--Land use change in target areas tools & technologies in use

DESCRIPTION

Precise Definition(s): Hectares of land under positive use in the FORREMS target areas of NE Laikipia, N Mt. Kenya and the North Coast. ‘Positive use’ refers to land management actions that are purposefully dedicated to natural resource conservation, protection and/or improved management. These actions may occur inside gazetted National Parks, National Reserves, Forest Reserves or Trust Lands or outside these areas on community lands or private farms. Examples of ‘positive land use change’ are the initiation or expansion of: participatory forest management in gazetted Reserves; agroforestry or conservation farming on farms adjacent to Protected Areas; conservation areas, sanctuaries or easements established on community or private lands; tree nurseries and conservation ‘demo’ areas on community or private land; and areas within gazetted Reserves that are managed under site-specific guidelines or operational plans.

Unit of Measure: Number of hectares under improved NRM

Disaggregated by: Geographic area, gender (male/female owned or managed farms)

Justification/Management Utility: This indicator measures the FORREMS program’s direct contribution at the SO level. It tracks FORREMS’ impact on the SO’s stated goal of improving land use in support of biodiversity conservation and sustainable NRM. This is an important measure of the validity of the SO’s development hypothesis -- that increased benefits to rural households from NRM coupled with improved Protected Area management structures will 1) lead to increases in the amount of land under improved NRM and 2) decrease the depletion of biodiversity and the degradation of natural ecosystems.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: Delineate areas under improved management using participatory mapping, GIS and remote sensing (aerial photography, satellite imagery).

Method of Acquisition by USAID: Quarterly Reports and Performance Assessment Reports from partners and independent evaluations

Data Source(s): KWS, Forest Department, Africa Wildlife Foundation, NEMA, Nature Kenya and KEFRI

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Expensive—possibly $15,000/year

Responsible Individual(s) at USAID: Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: August 2004, USAID will take the lead and work closely with FORREMS partners.

Known Data Limitations and Significance (if any): Not Applicable

Actions Taken or Planned to Address Data Limitations: Not Applicable

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Site visits & audit of partner data

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: See ‘Data Collection Method’ above.

Presentation of Data: Display targets and actual performance in performance summary data table segregated by geog area and gender where applicable. Tables, charts, graphs or maps will be used to present data.

Review of Data: Review with FORREMS M&E sub-committee and Program Steering Committee in April & October also in SO portfolio reviews, monthly meetings, or activity or program-level reviews with implementing partners.

Reporting of Data: CBJ, Annual Report, annual FORREMS PMP report, program briefs to the Ambassador or success stories.

OTHER NOTES

Notes on Baselines/Targets: The baseline amount for this indicator is ‘zero’ (0) ha. Targets have been set for FY ’04, the first year in which the initiatives of FORREMS partners could be expected to start ‘paying off’ at the SO level. Location of Data Storage: KWS CM&E Other Notes:

THIS SHEET LAST UPDATED ON: 11 /10 /03

Key Results over the Reporting Period

## LAND USE CHANGE

Hectares of land under positive use in the FORREMS target areas of NE Laikipia, NW Mt. Kenya and the North Coast. ‘Positive use’ refers to land management actions that are purposefully dedicated to natural resource conservation, protection and/or improved management. These actions may occur inside gazetted National Parks, National Reserves, Forest Reserves or Trust Lands or outside these areas on community lands or private farms. Examples of ‘positive land use change’ are the initiation or expansion of: participatory forest management in gazetted Reserves; agroforestry or conservation farming on farms adjacent to Protected Areas; conservation areas, sanctuaries or easements established on community or private lands; tree nurseries and conservation ‘demo’ areas on community or private land; and areas within gazetted Reserves that are managed under

site-specific guidelines or operational plans.

3.1.1	MUKOGODO LANDSCAPE

A total of 11,022 ha  (to be confirmed) in Mukogodo Forest has been identified as a conservation area in four (4)  community group ranches namely: Ilngwesi, Makurian, Kurikuri and Lekuruki.

- In Makurian GR, a range rehabilitation demonstration area measuring 18 ha has been designated and set aside. Conservation techniques applied include; barbed wire-post fence to keep off animals, water harvesting and spreading terraces, grass reseeding, soil and water microcatchments.

- One (1) tree nursery at Dol Dol by FD. This is in a plot, of about 20 ha which will include a proposed campsite.

- In Ilngwesi GR, an area measuring 65 ha has been set aside for hay production.

- In Lekuruki GR, hay bailing demonstration site measuring 12 ha was set aside and fenced.

- Two (2) private  tree nurseries at Ethi and Chumvi  were established as a result of concern over the impact of degradation - 20,000 seedlings each

- Naibunga Conservancy which is outside Mukogondo, a total of 17,200 ha in 9 community  group ranches has been set aside for conservation. Naibunga conservancy is made up of land designated for conservation in Koija, Tiamamut, Kijabe, Nkilorit, Morpusi, Ilpolei, Munishoi, Musul and Ilmotiok group ranches.

3.1.2	MT. KENYA

42 ha were reforested with mixture of Prunus africanum, Fagara microphylla, Vitex keniensis indigenous pioneer tree species in Irangi forest Magacha block jointly by Bill Woodley Trust/COMPACT, forest community user groups, with FD and KWS Forest Program providing technical guidance. The MKJMTF visited Magacha block in June 2004 and found that survival was above average.

In NW Mt. Kenya 100 ha of degraded sites have been designated for rehabilitation. 43 ha in Nyeri and 10 ha in Meru Central were mapped and identified. Nine thousand (9000) indigenous tree seedlings were procured from CBOs for restocking or reforestation on these sites. Due to insufficient short rains in April/June the enrichment planting was deferred to October/November/December 2004. No land use change is yet effected in NW Mt. Kenya.

3.1.3	ARABUKO SOKOKE FOREST

An Operational Forest Management Plan and Guidelines for PFM implementation developed for the 11,200 ha under the Dida PFM pilot area: 7,000 ha and 4,200 ha under community and gazetted forest respectively.

Around the forest, 22 ha of woodlots were planted.

## land Use change in target areas RESULTS Contd’

FORREMS Results: Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: None

Indicator: Land use change in target areas tools & technologies in use

INDICATOR DESCRIPTION : Hectares of land under positive use in the FORREMS target areas of Mukogodo Landscape, NW Mt. Kenya and Arabuko Sokoke Forest. ‘Positive use’ refers to land management actions that are purposefully dedicated to natural resource conservation, protection and/or improved management. These actions may occur inside gazetted National Parks, National Reserves, Forest Reserves or Trust Lands or outside these areas on community lands or private farms. Examples of ‘positive land use change’ are the initiation or expansion of: participatory forest management in gazetted Reserves; agroforestry or conservation farming on farms adjacent to Protected Areas; conservation areas, sanctuaries or easements established on community or private lands; tree nurseries and conservation ‘demo’ areas on community or private land; and areas within gazetted Reserves that are managed under site-specific guidelines or operational plans.

Unit of Measure: Number of hectares under improved NRM

Disaggregated by: Geographic area, gender (male/female owned or managed farms)

COMMENTS: During 2004, out of the expected target of 6,113ha in the first year of project implementation, 82ha of land have been brought under improved positive land use change. Central Monitoring and Evaluation Unit – KWS-Hqs, have received reports over this period from implementing partners, for data analysis and validation. Data Sources include; KWS, Forest Department, Africa Wildlife Foundation, NEMA, Nature Kenya and KEFRI Baseline = 90,113 ha Cummulative total area brought under positive land use change: 90,095ha.

| LAND USE CHANGE IN PROJECT SITES |
| --- |
| Baseline (b): 90,113ha |
| PROJECT SITE | Sub-unit targeted for land use change | Specify type of positive land use change in target area |
| 1) Mukogodo Landscape |  |
| Year | Expected results | Actual results |  |
| 2004 | 1,893ha | 18ha | Makurian Group Ranch | Range rehabilitation demo area has been identified and is currently under conservation with active participation by the Mukogodo community. |
|  | Nil | Nil | Ilngwesi Group Ranch | Land set aside for hay bailing; 65ha |
|  | Nil | Nil | Lekuruki (Sieko) Group Ranch | hay bailing demo site set aside and fenced;12ha |
|  | Nil | Nil | Ethi Private Ranch | 20,000 seedlings planted |
|  | Nil | Nil | Chumvi Private Ranch | 20,000 seedlings planted |
| 2) Mt. Kenya |  |  |
| Year | Expected results | Actual results |  |
| 2004 | Nil | 42ha | Magacha block in Irangi forest | Reforestation of 42 ha with indigenous species. In NW Mt. Kenya 43 ha of degraded sites have been identified for rehabilitation. |
| 3) Arabuko Sokoke |
| Year | Expected results | Actual results |  |
| 2004 | 4200 ha |  | PFM Area | Operational Forest Management Plan and Guidelines for PFM implementation developed for 11,200 ha under the Dida PFM pilot area: 7,000 ha and 4,200 ha under community and gazetted forest respectively. This is yet to be implemented. |
|  | 20 ha | 22ha | Adjacent farm woodlots | 22 ha of woodlots planted. |

3.2	NUMBER OF STAKEHOLDERS BENEFITTING FROM INVOLVEMENT IN IMPROVED NRM

Indicator Reference Sheet: FORREMS Indicator #2

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: None FORREMS Result #2: same as SO statement

Indicator: Same as SO level indicator #2— Number of stakeholders benefiting from involvement in improved NRM use

DESCRIPTION

Precise Definition(s): Number of stakeholders directly or indirectly benefiting from involvement in initiatives under FORREMS that improve NRM. ‘Stakeholders’ are defined as individuals or institutions committing time or resources to or benefiting from the FORREMS program. The term refers to individual farmers or resource users, community-based associations or user groups, NGOs or GoK institutions. ‘Benefits’ are improvements in such parameters or conditions as revenue or income, financial position, accessibility to resources, capacity to perform within institutional mandates, or institutional sustainability. There are two categories of beneficiaries of FORREMS initiatives —direct and indirect. ‘Direct’ beneficiaries are those stakeholders that receive funding, training, technical assistance, resource access or financial returns under the program. ‘Indirect’ beneficiaries are those who receive ‘spin-offs’ or ‘downstream’ positive impacts from FORREMS. For example, butterfly farmers directly benefit from TA that improves market access leading to higher financial returns for pupae sold. On the other hand, a registered Group Ranch member indirectly benefits if the institutional capacity of the management committee to govern and manage funds is enhanced.

Unit of Measure: Number of individuals

Disaggregated by: Type of benefit (direct or indirect). Direct beneficiaries will be disaggregated by gender

Justification/Management Utility: This indicator measures the FORREMS program’s direct contribution at the SO level. It tracks FORREMS’ impact on the SO’s stated goal of increasing the number of Kenyans benefiting from improved land management, biodiversity conservation and sustainable NRM. This is an important component of the internal logic and validity of the SO’s development hypothesis -- that increases in the amount of land under improved NRM and decreases in the depletion of biodiversity or in the degradation of natural ecosystems really do stem from increased ‘benefits’ to stakeholders. It will be important to develop mechanisms that test this hypothesis through direct assessment of ‘cause and effect’.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: Identify direct and indirect beneficiaries for FORREMS activities, perform incremental counts and maintain a cumulative database.

Method of Acquisition by USAID: Quarterly Reports, performance assessment reports

Data Source(s): KWS, Forest Department, Africa Wildlife Foundation, NEMA, Nature Kenya & KEFRI

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Inexpensive; probably < $1,000/year.

Responsible Individual(s) at USAID: Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: August 2004, USAID will take the lead and work closely with FORREMS partners.

Known Data Limitations and Significance (if any): Not Applicable

Actions Taken or Planned to Address Data Limitations: Not Applicable

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Site visits and audit of partner data

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: Data will be analyzed using simple arithmetic tools and graphics packages

Presentation of Data: Display targets and actual performance in performance summary data table segregated by type benefit and gender. Tables, charts and graphs will be used to present data.

Review of Data: Review with FORREMS M&E sub-committee & Program Steering Committee in April & October; portfolio review, monthly meetings, activity or program-level reviews with all implementing partners.

Reporting of Data: CBJ, Annual Report, Annual FORREMS PMP report, program briefs to the Ambassador, success stories.

OTHER NOTES

Notes on Baselines/Targets: Beneficiary baselines start at ‘zero’ (0) for new initiatives and with the most recent ‘tally’ for initiatives that are continuing under FORREMS. Location of Data Storage: KWS CM&E Other Notes:

Key Results over the Reporting Period

## Number Of Stakeholders Benefiting From Involvement In Improved NRM

Number of stakeholders directly or indirectly benefiting from involvement in initiatives under FORREMS that improve NRM. ‘Stakeholders’ are individuals or institutions committing time or resources to or benefiting from the FORREMS program. The term refers to individual farmers or resource users, community-based associations or user groups, NGOs or GoK institutions. ‘Benefits’ are improvements in such parameters or conditions as revenue or income, financial position, accessibility to resources, capacity to perform within institutional mandates, or institutional sustainability. There are two categories of beneficiaries of FORREMS initiatives —direct and indirect. ‘Direct’ beneficiaries are those stakeholders that receive funding, training, technical assistance, resource access or financial returns under the program.  ‘Indirect’ beneficiaries are those who receive ‘spin-offs’ or ‘downstream’ positive impacts from FORREMS. For example, butterfly farmers directly benefit from TA that improves market access leading to higher financial returns for pupae sold. On the other hand, a registered Group Ranch member indirectly benefits if the institutional capacity of the management committee to govern and manage funds is enhanced.

3.2.1	MUKOGODO LANDSCAPE

In Mukogodo, 518 stakeholders benefited directly and 170 indirectly. Out of the direct beneficiaries only 70 males and 11 females could be disaggregated by gender. Thus the disaggregation is incomplete. However from the preliminary data, it can be deduced that participation of females in NRM in Mukogodo is low.

The following stakeholders in Mukogodo benefited from FORREMS support in the following ways:

- 36 community members were trained in methodologies for natural resource inventory and planning in February 2004 and later in April 2004, the group were involved in the actual data collection for developing the inventories and NRM planning.

- 21 community members (18 male, 3 female) were trained as forest scouts in partnership with KWS to provide security for biodiversity conservation in Mukogodo Forest. They will be coordinated through a community office that is being developed by FORREMS in Mukogodo. The communities are paying these scouts.

- 4 Community members were trained in monitoring and evaluation of community based activities.

- 19 community representatives (16 male, 3 female) from ILMAMUSI participated in an exchange visit to Arabuko Sokoke to learn concerning participatory forest management. This was designed to expose them to and prepare them for PFM, which is being developed in Mukogodo forest.

- 67 community members were trained/reached during meetings to develop the umbrella structure (ILMAMUSI) for participatory forest management. Training also included conflict management and constitution building.

- An office is being developed for the ILMAMUSI forest management committee.

- 188 community members consulted during sensitization meetings for the development of  PFM

- A hay bailing seminar was conducted for Lekuruki group ranch for 12 community members (6 men, 6 women). A hay baler was also procured for the community but training on how to use it is yet to be  conducted.

- Organizational development training was provided for 11 members of Meirishi self help group from Lekuruki. This group will engage in hay production.

- Training was conducted for 21 members of the Makurian demonstration plot committee at Dol Dol in March-April 2004.

- Organizational development training conducted for 18 members of the Naningo Youth Group from Ilngwesi Group Ranch. This was designed to strengthen the group to effectively engage in the hay production program.

- 70 stakeholders attended the national aloe stakeholders’ dialogue workshop convened in Nanyuki to guide the development of the sub-sector.

- Visioning workshop held for 51 participants (38 community representatives, 13 partners) for the Mukogodo Landscape in Nanyuki in October 2003. In this workshop, the overall vision for the Mukogodo landscape was developed.

- 19,150 seedlings distributed to …..no. of farmers

3.2.2	MT. KENYA

In Mt. Kenya, 23 direct beneficiaries were involved. A total of 115 indirectly benefited. It appears the primary contribution of females in improved NRM is marginalized here. At the institutional level 15 KWS and FD staff received technical training from USAID.

3.2.3	ARABUKO SOKOKE FOREST

In ASF, 2,043 stakeholders benefited directly and indirectly i.e. 1,329 males and 714 female (though it is difficult to prove this, it is assumed that this benefit is extended to 4 or 5 other members of the household).

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: None FORREMS Result #2: same as SO statement

Indicator: Same as SO level indicator #2— Number of stakeholders benefiting from involvement in improved NRM use

DESCRIPTION

Precise Definition(s): Number of stakeholders directly or indirectly benefiting from involvement in initiatives under FORREMS that improve NRM. ‘Stakeholders’ are defined as individuals or institutions committing time or resources to or benefiting from the FORREMS program. The term refers to individual farmers or resource users, community-based associations or user groups, NGOs or GoK institutions. ‘Benefits’ are improvements in such parameters or conditions as revenue or income, financial position, accessibility to resources, capacity to perform within institutional mandates, or institutional sustainability. There are two categories of beneficiaries of FORREMS initiatives —direct and indirect. ‘Direct’ beneficiaries are those stakeholders that receive funding, training, technical assistance, resource access or financial returns under the program. ‘Indirect’ beneficiaries are those who receive ‘spin-offs’ or ‘downstream’ positive impacts from FORREMS. For example, butterfly farmers directly benefit from TA that improves market access leading to higher financial returns for pupae sold. On the other hand, a registered Group Ranch member indirectly benefits if the institutional capacity of the management committee to govern and manage funds is enhanced.

Unit of Measure: Number of individuals

Disaggregated by: Type of benefit (direct or indirect). Direct beneficiaries will be disaggregated by gender

Justification/Management Utility: This indicator measures the FORREMS program’s direct contribution at the SO level. It tracks FORREMS’ impact on the SO’s stated goal of increasing the number of Kenyans benefiting from improved land management, biodiversity conservation and sustainable NRM. This is an important component of the internal logic and validity of the SO’s development hypothesis -- that increases in the amount of land under improved NRM and decreases in the depletion of biodiversity or in the degradation of natural ecosystems really do stem from increased ‘benefits’ to stakeholders. It will be important to develop mechanisms that test this hypothesis through direct assessment of ‘cause and effect’.

| #2 STAKEHOLDERS BENEFITING FROM INVOLVEMENTIN IMPROVED NRM |
| --- |
| Name of Focal Area | Type of Benefit | Beneficiaries (Number of individuals) |
|  |  | Number of direct beneficiaries, i.e. those that receive funding, training, technical assistance, resource access or financial returns from the program[1] | Number of indirect beneficiaries (5 next of kins per direct beneficiary) |
|  |  | Male | Female | Total | Value of benefits (Kshs) |  |
| Mukogodo | Inventory training | 31 | 5 | 36 | N/A | 170 |
|  | game scouts | 18 | 3 | 21 | “ |  |
|  | monitoring & evaluation | 5 | 0 | 5 | “ |  |
|  | Visioning workshop | Not determined | Not determined | 37 | “ |  |
|  | OD training/Ilmamusi | Not determined | Not determined | 20 | “ |  |
|  | Exchange visit to ASF (PFM) | 16 | 3 | 19 | “ |  |
|  | Developing of umbrella structure (PFM) | Not determined | Not determined | 67 | “ |  |
|  | Sensitization meetings | Not determined | Not determined | 190 | “ |  |
|  | Institutional training | Not determined | Not determined | 247 | “ |  |
|  | Grand Total | 70 | 11 | 642 | - | 170 |
| Mt Kenya | Financial returns to casual workers in identification of degraded sites for rehabilitation | 10 | 3 | 13 | 7,800 | 65 |
|  | Sale of Seedlings by CBO members | Not determined | Not determined | 10 | 90,000 | 50 |
|  | Technical training for KWS and FD staff funded by USAID. |  |  | 15 |  |  |
|  | Grand Total |  |  | 23 | 97,800 | 115 |
| Arabuko Sokoke Forest | Training, Technical assistance, Resource Assessment, Financial returns | 1,329 | 714 | 2,043* | Not determined | See footnote (*) |

  - CONSERVATION TOOLS AND TECHNOLOGIES IN USE

Indicator Reference Sheet: FORREMS Indicator #3

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1-Site specific initiatives for NRM implemented outside Protected Areas; and 5.3-Improved management of Protected Areas. FORREMS Result #3: Appropriate tools & technologies for forest/range management adopted by communities and/or Government in target areas

Indicator: Conservation tools and technologies in use tools & technologies in use

DESCRIPTION

Precise Definition(s): A conservation “tool or technology” is defined as a device or application of science that facilitates conservation, protection or sustainable utilization of natural resources. Examples of conservation tools or technologies are: 1) Buffer zones around Protected Areas; 2) Land trusts or Conservation trusts; 3) Agroforestry and farm forestry; 4) Monitoring & evaluation systems and databases; 5) Conservation leases and/or easements; 6) NRM plans on GoK, community and private lands and that target a variety of resources (forest products, non-timber forest products, rangeland, wildlife); 7) Water harvesting & management; 8) Participatory forest management; 9) Grazing management systems; 10) Natural resource fora or networks. “Use” means formally adopted, recognized, implemented or followed. ‘Target areas’ are NE Laikipia, N Mt. Kenya and the North Coast.

Unit of Measure: Number of technologies and/or tools in use.

Disaggregated by: Geographic area, gender

Justification/Management Utility: This indicator measures the number of conservation tools / technologies in use by stakeholders. The indicator is quite broad in scope because 1) it applies to both communities and GoK agencies that are using an array of conservation tools to improve NRM, and 2) both communities and GoK are operating inside & outside Protected Areas. This indicator quantifies the adoption of technologies and practices that lead to sustainable use of natural resources. It supports the hypothesis that an increase in the number of conservation tools and technologies in use leads to improved management of the natural resource base and ultimately to positive changes in land use. The number of conservation tools / technologies in use reflects stakeholders’ access to new concepts and management approaches and their ability to put them into practice.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: Assessment of users using ‘rapid’ or ‘formal’ means; use of remotely sensed information (aerial photography, satellite imagery) that identifies/counts applications of tools, technologies and practices in target areas.

Method of Acquisition by USAID: Quarterly Reports, performance assessment reports

Data Source(s): KWS, Forest Department, Africa Wildlife Foundation, NEMA, Nature Kenya and KEFRI

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Expensive—possibly $15-20,000

Responsible Individual(s) at USAID: Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: August 2004, USAID will take the lead and work closely with FORREMS partners.

Known Data Limitations and Significance (if any): Not Applicable

Actions Taken or Planned to Address Data Limitations: Not Applicable

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Site visits and audit of partner data

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: Data will be analyzed using SPSS and other graphical tools

Presentation of Data: Display targets and actual performance in performance summary data table segregated by geog area and gender. Tables, charts and graphs will be used to present data.

Review of Data: Review with FORREMS M&E sub-committee in April & October; Portfolio review, Bi-weekly meetings, activity or program-level reviews with all implementing partners.

Reporting of Data: Annual FORREMS PMP report, program briefs to the Ambassador, success stories.

OTHER NOTES

Notes on Baselines/Targets: Baselines start at ‘zero’ (0) although on-going applications of tools / technologies that are supported under FORREMS will count as ‘new’ starts. Location of Data Storage: KWS CM&E Other Notes:

THIS SHEET LAST UPDATED ON: 11 /10 /03

Key Results over the Reporting Period

## CONSERVATION TOOLS AND/OR TECHNOLOGIES IN USE

A conservation “tool or technology” is defined as a device or application of science that facilitates conservation, protection or sustainable utilization of natural resources.  Examples of conservation tools or technologies are: 1) Buffer zones around Protected Areas; 2) Land trusts or Conservation trusts; 3) Agroforestry and farm forestry; 4) Monitoring & evaluation systems and databases; 5) Conservation leases and/or easements; 6) NRM plans on GoK, community and private lands and that target a variety of resources (forest products, non-timber forest products, rangeland, wildlife); 7) Water harvesting & management; 8) Participatory forest management; 9) Grazing management systems; 10) Natural resource fora or networks.    “Use” means formally adopted, recognized, implemented or followed.  ‘Target areas’ are NE Laikipia, NW Mt. Kenya and Arabuko Sokoke Forest, North Coast.

3.3.1	MUKOGODO LANDSCAPE

Fourteen (14) tools and one (1) technology have been in use by stakeholders. In summary;

- Soil and water conservation terraces and micro catchments, grass re-seeding and perimeter fence integrated in the Makurian rehabilitation demonstration site.

- Conservation trust developed:(i) To manage Naibunga Conservancy and (ii) To strengthen the management of natural resources and associated enterprises in Il Ngwesi group ranch

- The process of developing a strategic management plan for Mukugodo forest has began led by FD and KEFRI.

- A five-year strategic plan has been developed for Ilngwesi group ranch to guide NRM and development in the group ranch.

- The process of NRM planning for the Naibung’a community conservancy consisting of 9 group ranches was completed and draft reports have been produced. In group ranches where the process was completed earlier, aspects of the NRM plan are being implemented.

- The process for participatory forest management of the Mukogodo forest has been initiated.

- On-farm tree planting in ethi & chumvi 19,150 seedlings planted.

- Checklist of important trees and other plants with market potential for NBEs

- Natural resource fora and a network exist in the Mukogodo area. These include ILMAMUSI, focal area teams, and Resource Management Area committees.

- Natural resource inventories, ecological species, and ethno-botanical surveys and socioeconomic surveys conducted in the four (4) GRs.

- M&E systems in place

3.3.2	MT. KENYA

Four (4) tools have been initiated and/or are in use. These include:

- Integrated NRM plan for Mt. Kenya under review

- Fire Management Plan (FMP) for Mt Kenya ecosystem initiated. Six localized FMPs for NW Mt. Kenya will be developed from the ecosystem FMP. Three (3) meetings with Meru Central and Nyeri DFOs have been held to plan on emergency fire plans.

- Rehabilitation of degraded sites – Magacha block in Irangi forest

- M&E system by the MKJMTF

3.3.3	ARABUKO SOKOKE FOREST

At Arabuko-Sokoke Forest 5 tools and 1 technology were adopted.

- Buffer zones around protected areas – woodlots were established on farms that neighbour the forest on the northern border from Kakuyuni to Mida, running along the 20 km fence.

- Agroforestry and farm forestry – 22 ha of wood lots were planted in villages that neighbor the north and east of the forest (Sidzeni 4 ha, Roka 6 ha, Kakuyuni 5 ha, Mkongani 4ha, Mida-Majaoni 3 ha)

- M&E systems and databases - Monitoring protocols and framework were developed for biodiversity. Protocols developed for vegetation, butterflies, birds, and elephant shrews.

- PFM – Operational Forest Management Plan and Guidelines developed. Changing of the Dida Forest Adjacent Forest Association (DIFAAFA) to a society is on-going.

- Natural resource fora and networks – Arabuko-Sokoke Forest Adjacent Association (FADA) committee strengthened and the Arabuko- Sokoke Forum operationalised.

| #3: CONSERVATION TOOLS & TECHNOLOGIES IN USE |
| --- |
| Name of Focal Area | Sub-unit | Specify tools in use | Number of tools and/or technologies in use |
| Mukogodo | Makurian | Conservation demo area | 1 |
|  | Ethi | Agroforestry and farm forestry, Tree nurseries | 3 |
|  | Dol Dol | Tree nurseries | 1 |
|  | IlNgwesi | Conservation trust | 1 |
|  | 4 GRs/Forest reserve | NRM plants, Water management, PFM, Grazing management systems, Natural resource for a & networks, Nature based enterprises | 7 tools; 1 tech |
|  | Chumvi | Tree nurseries | 1 |
| Mt. Kenya | N/FR & NW Mt Kenya | M& E systems; MKJMTF | 1 tool |
|  |  | NRM plans in GoK, community & private lands | 2 tools |
|  |  | Natural resource for a & networks; Workshops, training seminars | 2 tools |
|  |  | Databases (GIS) | 1 technology |
|  | Irangi forest, Magacha block | Rehabilitation; Artificial Reafforestation of wildlife & NRCdegraded sites into indigenous forests | 1 technology |
| Arabuko Sokoke Forest | Kakuyuni to Mida | Woodlots established from, along the 20 km fence. |  |
|  | Sidzeni, Roka, Kakuyuni, Mkongani and Mida-Majaoni | .Agroforestry and farm forestry in |  |
|  |  | M&E systems and databases |  |
|  |  | PFM – Operational Forest Management Plan and Guidelines developed |  |
|  |  | Natural resource fora and networks ; (FADA) committee strengthened and the AS Forum operationalised |  |

## 3.4	Organizational Capacity Of Community User Groups

Indicator Reference Sheet: FORREMS Indicator #4

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders

SO5 Intermediate Result: Site specific initiatives for NRM implemented outside Protected Areas

FORREMS Result #4: Management capacity of community groups improved Indicator: Organizational capacity of community user groups

DESCRIPTION

Precise Definition(s): . ‘Organizational Capacity’ is a reflection of how well user groups perform in seven areas--1) governance, 2) natural resource management 3) administration, 4) financial management, 5) conflict management, 6) sustainability and 7) advocacy. The ‘Organizational Capacity Assessment’ (OCA) tool will be the instrument of assessment. The OCA tool is used to ‘score’ strengths and weaknesses of organizations across 196 items in the seven areas noted above. These items are scored on a scale of 1-6 where 1=needs immediate attention; 2=needs major attention; 3=needs attention on a wide scale; 4=needs attention on a limited scale; 5=acceptable, needs minor attention; and 6=acceptable no need for immediate attention. A modal score is obtained for each set of elements in the seven assessment areas. The seven modal scores are then averaged to give a single ‘measure’ of Organizational Capacity for each organization. Organizations are then ranked according to where their Organizational Capacity scores place them with reference to four levels of organizational development: Nascent (average medial scores < 2.3); Emerging (2.4-3.5); Expanding (3.6-4.8) or Mature (4.9-6.0).

Unit of Measure: Organizational Capacity scores of targeted CBOs

Disaggregated by: CBOs organized in the current year, CBOs organized in the previous years, Mgmt committees of Group Ranches

Justification/Management Utility: FORREMS is designed to strengthen forest and range conservation and environmental governance. Conservation programs and projects outside PAs require competent local organizations to transform labor, land, resources, and technologies into sustained improvements in the livelihoods of local people & in the condition of natural resources. FORREMS will support CBOs to develop and mature. This should improve their competency, and ultimately, increase their impact upon conservation and development in their geographic areas Each CBO will be periodically assessed after receiving support from specific partners responsible for CBO development (e.g AWF, Nature Kenya) in their areas of weakness. This will generate a ‘new’ score that will be compared to previous ones to indicate progress (or lack thereof) in organizational capacity.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: The OCA tool, administered by a team of three that represent FORREMS partners not directly involved in the development of a specific CBO. This should lend some objectivity to the evaluation process.

Method of Acquisition by USAID: Quarterly reports, performance assessment reports

Data Source(s): OCA report forms

Frequency/Timing of Data Acquisition: Biennially

Estimated Cost of Data Acquisition: $20,000

Responsible Individual(s) at USAID: Mr. Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: August 2004 Known Data Limitations and Significance (if any): N/A Actions Taken or Planned to Address Data Limitations: N/A Date of Future Data Quality Assessments: September 2006 Procedures for Future Data Quality Assessments: Repeat methods used in 1st Data Quality assessment (DQA)

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: Compare the target values to the OCA values to determine the status and trends of CBO development. Report qualitative information describing organizational capacity development efforts.

Presentation of Data: Display targets and actual performance data in Performance Summary Data Table.

Review of Data: Review with FORREMS M&E Sub committee in April and October

Reporting of Data: Annual FORREMS PMP report

OTHER NOTES

Notes on Baselines/Targets: Baselines start at the OCA score of supported CBOs at the start of FORREMS assistance. Location of Data Storage: KWS CM&E Unit Other Notes:

THIS SHEET LAST UPDATED ON: 11/10/03

Key Results over the Reporting Period

ORGANISATIONAL CAPACITY OF COMMUNITY USER GROUPS

Precise Definition(s): . ‘Organizational Capacity’ is a reflection of how well user groups perform in seven areas--1) governance, 2) natural resource management 3) administration, 4) financial management, 5) conflict management, 6) sustainability and 7) advocacy. The ‘Organizational Capacity Assessment’ (OCA) tool will be the instrument of assessment. The OCA tool is used to ‘score’ strengths and weaknesses of organizations across 196 items in the seven areas noted above. These items are scored on a scale of 1-6 where 1=needs immediate attention; 2=needs major attention; 3=needs attention on a wide scale; 4=needs attention on a limited scale; 5=acceptable, needs minor attention; and 6=acceptable no need for immediate attention. A modal score is obtained for each set of elements in the seven assessment areas. The seven modal scores are then averaged to give a single ‘measure’ of Organizational Capacity for each organization. Organizations are then ranked according to where their Organizational Capacity scores place them with reference to four levels of organizational development: Nascent (average medial scores < 2.3); Emerging (2.4-3.5); Expanding (3.6-4.8) or Mature (4.9-6.0).

Unit of measure: Organisational capacity scores of targeted CBOs

Disaggregated by: CBOs organized in the current year, CBOs organized in the previous years, management committee of group ranches

3.4.1	MUKOGODO LANDSCAPE

- Community members were trained in Natural resource inventory and planning methodologies

- Community members were trained as forest scouts in partnership with KWS to provide security for biodiversity conservation

- Community trained in M&E

- Community representatives from the ILMAMUSI were trained in PFM, training also included conflict management and constitution building.

- Gave technical advice on process of developing a strategic forest management plan for Mukogodo landscape

- Conducted visioning workshop

- Created an umbrella community structure for the four group ranches and developed an action plan for the umbrella body

- Community members trained on nursery techniques, management and seedling handling

3.4.2	MT. KENYA

The warden Embu and Senior warden Mt Kenya are laying terms of participatory NRM with ten (10) Forest user groups. The MKJMTF has selected some areas as the main sites from which FORREMS will contribute in improving CBOs’ performance.

3.4.3	ARABUKO SOKOKE FOREST

Organization capacity assessment (OCA) of groups has not been done on any of the targeted CBOs for capacity building. Three groups have benefited:

- Arabuko Sokoke Forest Adjacent Dwellers Association (FADA) - facilitation of regular meetings of delegates at which the groups constitution and structure of association as umbrella reviewed. As community group in charge of electric fence, technical support on establishing a sustainable fence maintenance unit provided. The groups’ Chairman was facilitated to attend national fora to disseminate the ASF experience.

- Dida Forest Adjacent Area Forest Association (DIFAAFA) - review of guidelines for PFM implementation that include roles and responsibilities of members, officials and user groups. Strengthened governance and review constitution, faciliting change of the CBO to a society, one of the requirements for community participation in forest management. Facilitated the Chairman to disseminate the ASF PFM experience at national fora.

- Mangagani Butterfly farmers – assisted in building business planning capacity and investment evaluation, in developing spin off activities from income from butterfly farming.

- Beekeeping farmers in ASF – developed network beekeepers that will facilitate training on modern methods of beekeeping, standardization and quality control and marketing.

| Name of Focal Area | Name of targeted CBO |
| --- | --- |
| Mukogodo Landscape | ILMAMUSI |
|  | Naibunga |
|  | RAMACS |
|  | Orereti |
|  | GR committees |
|  | Rangeland rehab committee |
|  | Grass bulking committee |
|  | Scouts & Guides association |
| Mt. Kenya | NONE |
| Arabuko Sokoke Forest | AS- Forest adjacent Dwellers Association |
|  | Dida Forest Adjacent area Forest Association |
|  | Arabuko Sokoke Management team |
|  | Mangagani Butterfly farmers |

3.5	NATURE BASED ENTERPRISES ESTABLISHED

Indicator Reference Sheet: FORREMS Indicator #5

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1-Site specific initiatives for NRM implemented outside PAs

FORREMS Result: #5-Benefits from nature-based enterprises increased Indicator: Nature-based enterprises established

DESCRIPTION

Precise Definition(s): A nature-based enterprise is one that utilizes or depends upon the surrounding natural resources or environmental goods and services to generate revenue or other benefits for participants. The management of the enterprise strives for sustainability; i.e, an approach to enterprise management that “meets the needs of present participants or beneficiaries without compromising the options and needs of future participants”. Productive or service sectors where one finds nature-based enterprises include ecotourism, agroforestry, apiculture, fodder production and NTFPs. ‘Enterprises’ are those natural resource-based businesses targeted under the FORREMS program. ‘Established’ means initiated and operational. Target areas are currently defined as the 3 FORREMS focal areas – NE Laikipia/Mukogodo, N Mt. Kenya and the N. Coast.

Unit of Measure: Number & type of enterprises

Disaggregated by: Type of business, geographical area

Justification/Management Utility: This indicator is based on the hypothesis that an increase in number and types of enterprises (i.e., diversification of enterprises) contributes to more wealth (revenue/benefits) in the rural economy.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: Consolidated from site performance reports, assessment of enterprises by implementing partners

Method of Acquisition by USAID: Quarterly reports, performance assessment reports

Data Source(s): Focal area base maps, reports, M&E database (built from focal area teams’ reports), performance reports and database of enterprise inventories

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Moderate

Responsible Individual(s) at USAID: Mr. Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: To be conducted in November 2004

Known Data Limitations and Significance (if any): None

Actions Taken or Planned to Address Data Limitations: None

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Repeat methods used in 1st DQA

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: Data are analyzed and summarized by the responsible partners. Analysis includes use of relevant computer packages e.g. SPSS, MS excel, MS Word

Presentation of Data: Tables with disaggregated categories, supporting narratives and maps of occurrence within group ranches and in areas adjacent to PAs.

Review of Data: Review with FORREMS M&E Sub Committee & Program Steering Committee in April/October

Reporting of Data: Annual FORREMS PMP report

OTHER NOTES

Notes on Baselines/Targets: Baselines start with the number of enterprises FORREMS is assisting at the start of its interventions in target areas Location of Data Storage: KWS CM&E unit Other Notes:

THIS SHEET LAST UPDATED ON: 11 /10 /03

Key Results over the Reporting Period

## Nature-Based Enterprises Established

Precise Definition(s): A nature-based enterprise is one that utilizes or depends upon the surrounding natural resources or environmental goods and services to generate revenue or other benefits for participants. The management of the enterprise strives for sustainability; i.e, an approach to enterprise management that “meets the needs of present participants or beneficiaries without compromising the options and needs of future participants”. Productive or service sectors where one finds nature-based enterprises include ecotourism, agroforestry, apiculture, fodder production and NTFPs. ‘Enterprises’ are those natural resource-based businesses targeted under the FORREMS program.  ‘Established’ means initiated and operational.   Target areas are currently defined as the 3 FORREMS focal areas – NE Laikipia/Mukogodo, N Mt. Kenya and the N. Coast.

Unit of measure: Number  and type of enterprises

Disaggregated by: Type of business, Geographic area

3.5.1	MUKOGODO LANDSCAPE

The following nature based enterprises have been established in the Mukogodo area.

- Hay bailing and fodder production in Il Ngwesi GR by Naningo Youth Group (30 persons) at initial stages of strengthening by FORREMS . It has also been initiated in Lekuruki.

- Seedling production at Ethi and Chumvi : two tree seedling nurseries. The seedlings are under production and require 9 months to be ready for planting/sale.

- Apiculture in Naipotaki Cooperative had earlier been initated by CORE and is now being strengthened under FORREMS.

In addition, an enterprise scoping exercise has been conducted and options/scenarios for enterprise development developed. This will be developed or supported during FORREMS.

3.5.2	MT KENYA

No NBE was established by FORREMS project in 2003/2004. Viable enterprises will be selected from the pool of those already in use by various existing forest user groups. Most of the NBEs in use include apiculture, tree seedling nurseries, poles and rafters etc.

3.5.3	ARABUKO SOKOKE FOREST

- Eco-tourism (scenic sites and roads) – road signages and clearance of walking trails in collaboration with the community guides. (how many beneficiaries??)

- Agro-forestry – 22 ha of woodlots, 46,040 trees planted. (how many beneficiaries??)

- Aloe farming – 8,000 suckers procured and under multiplication in community nurseries. Farmers have been identified and soil sampled in the planting area. (how many beneficiaries??)

| #5: NATURE-BASED ENTERPRISES ESTABLISHED |
| --- |
| Name of Focal Area | Type Of NBE Established |
| Mukogodo | Apiculture |
|  | Hay bulking |
|  | Agroforestry |
|  | NTFPs - (herbal medicines, wild fruits, tree seeds, Aloe) |
|  | Tree seedlings nurseries |
| Mt. Kenya | NONE |
| Arabuko Sokoke Forest | Ecotourism (bicycle hire) |
|  | Ecotourism (handicrafts) |
|  | Ecotourism (scenic sites and roads) |
|  | Apiculture (modern technology) |
|  | Apiculture (honey processor) |
|  | Apiculture (business andmarketing plan) |
|  | Agroforestry (woodlots and fodder) |
|  | Aloe farming |
|  | Butterfly farming(business and marketing plans) |

  - FINANCIAL BENEFITS GENERATED BY NATURE-BASED ENTERPRISES

Indicator Reference Sheet: FORREMS Indicator #6

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1-Site specific initiatives for NRM implemented outside PAs.

FORREMS Result: #5- Benefits from nature-based enterprises increased Indicator: Financial benefits generated by nature-based enterprises.

DESCRIPTION

Precise Definition(s): ‘Financial benefits’ are revenues generated by nature-based enterprises that are payable to local community members, landowners, other qualified stakeholders or to support community services. Examples of financial benefits include income in the form of salaries or wages, ‘dividends’ paid from operational profits to members of a group, monies invested in ‘spin-off’ enterprises or funds invested in community infrastructure or services (e.g., school buildings or bursaries, road repair, clinics or posho mills).

Unit of Measure: Amount of net revenue generated by nature-based enterprises and paid out

Disaggregated by: Type of enterprise; gender

Justification/Management Utility: This indicator rests at the heart of the SO5 program, and is central to the SO’s development hypothesis. FORREMS is striving for the sustainable utilization of natural resources, for the conservation of biodiversity and for the improvement of rural economies. The SO realizes that conservation and sustainable NR utilization is virtually impossible without the active participation of rural community members in improved NRM. The SO hypothesizes that financial benefits, flowing directly from profitable, nature-based enterprises, are powerful incentives for communities to maintain or protect the natural resources upon which these enterprises depend. These benefits are also important potential ‘drivers’ for improving rural economies.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: Assessment of the financial records of nature-based enterprises using surveys & audits. Document the amount and intended recipients of net revenues paid out.

Method of Acquisition by USAID: Quarterly reports, performance assessment reports

Data Source(s): Reports from AWF & Nature Kenya

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Moderate--$15,000

Responsible Individual(s) at USAID: Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: November 2004

Known Data Limitations and Significance (if any): N/A

Actions Taken or Planned to Address Data Limitations: N/A

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Same as initial DQA

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: Track changes in the amount net revenues and in the proportions of financial benefits (net revenues) earmarked for various recipients—salaries, ‘dividends’, community infrastructure support.

Presentation of Data: Display targets and actual performance data in Performance Summary Data Table.

Review of Data: Review with FORREMS M&E Sub Committee & Program Steering Committee in April & October

Reporting of Data: CBJ, Annual Report, Annual FORREMS PMP report, program briefs to the Ambassador, success stories

OTHER NOTES

Notes on Baselines/Targets: There are two baseline statistics—1) total net revenue of enterprises at the beginning of FORREMS-assistance and 2) total proportion of net revenues earmarked for various recipients. Location of Data Storage: KWS CM&E Unit Other Notes:

THIS SHEET LAST UPDATED ON: 11/ 10/ 03

Key Results over the Reporting Period

## Financial Benefits Generated By NBEs

Precise Definition(s):  ‘Financial benefits’ are revenues generated by nature-based enterprises that are payable to local community members, landowners, other qualified stakeholders or to support community services. Examples of financial benefits include income in the form of salaries or wages, ‘dividends’ paid from operational profits to members of a group, monies invested in ‘spin-off’ enterprises or funds invested in community infrastructure or services (e.g., school buildings or bursaries, road repair, clinics or posho mills).

Unit of measure:  Amount of net revenue generated by nature based enterprises and paid out

Disaggregated by: Type of enterprise, gender

3.6.1	MUKOGODO

No financial benefits have been generated in the first year.

3.6.2	MT. KENYA

No NBE worked upon by the FORREMS project so far.

3.6.3	ARABUKO SOKOKE FOREST

Agro-forestry ($ 3,164 income to community for sale of seedlings)

  - NON-FINANCIAL BENEFITS ACCRUED FROM NATURE-BASED ENTERPRISES

Indicator Reference Sheet: FORREMS Indicator #7

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1--Site specific initiatives for NRM implemented outside PAs.

FORREMS Result: #5- Benefits from nature-based enterprises increased Indicator: Non-financial benefits accrued from nature-based enterprises

DESCRIPTION

Precise Definition(s): There are several types of ‘non-financial’ benefits from well-managed, financially sound enterprises – 1) improvements in rural livelihoods that result when enterprise managers, boards or individuals chose to invest profits for the ‘greater good’; (i.e, philanthropy), and 2) improved ‘processes’ or capacities that are available to the ‘larger’ community in which the enterprise functions. Examples of the former include improvements in community infrastructures e.g., improved road networks, establishment or refurbishment of new schools or clinics, or improved water systems or sanitation. Examples of the latter include enhanced governance (organizational, managerial, business skills and transparency), enhanced security or increased empowerment/participation on the part of women in organizational decision-making or in NRM when enterprise managers or employees bring their expertise and insights to other community groups or activities.

Unit of Measure: Number of structures or systems that are improved or established as a result of the proceeds from nature-based enterprises.

Disaggregated by: Geographic area

Justification/Management Utility: FORREMS is striving for improved household and rural livelihoods, and these can be measured in part by non-financial benefits that accrue from environmentally sustainable and profitable NRM. The importance of this indicator rests on the notion that the positive impacts of non-financial benefits are complementary to the impacts of direct, financial benefits. In addition, they will probably be felt by a ‘larger circle’ of rural residents than will the financial benefits. For instance, if enterprise profits are invested in roofing a school (i.e, the ‘philanthropy’ noted above), the impact will be felt by many children in the community in contrast to employee wages that support individual families. Tracking this indicator and drawing attention to how sustainable NR utilization improves rural livelihoods on a broad scale are means of enticing more rural dwellers to practice sound NRM. This indicator is closely related to #6, and probably will not be realized without the strong performance of indicator #6.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method: Assessment of the financial records of nature-based enterprises using surveys & audits. Document the community structures and/or institutions that are improved, built or that increase their effectiveness as a result of support from revenues paid out from nature-based enterprises.

Method of Acquisition by USAID: Quarterly reports, performance assessment reports

Data Source(s): Reports from AWF & Nature Kenya

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Expensive-- $15 - 20,000

Responsible Individual(s) at USAID: Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: November 2004

Known Data Limitations and Significance (if any): N/A

Actions Taken or Planned to Address Data Limitations: N/A

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Same as initial DQA

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: Identify the type of non-financial benefits that are derived from the operation of nature-based enterprises. Track the change in the amounts and types of these non-financial benefits over time.

Presentation of Data: Display targets and actual performance data in Performance Summary Data Table.

Review of Data: Review with FORREMS M&E Sub Committee & Program Steering Committee in April & October

Reporting of Data: Annual FORREMS PMP report

OTHER NOTES

Notes on Baselines/Targets: This is probably a new indicator. Thus, baselines would be ‘zero’ (0). Location of Data Storage: KWS CM&E Unit Other Notes:

THIS SHEET LAST UPDATED ON: 11/12//03

Key Results over the Reporting Period

## Non-Financial Benefits From NBE’s

Precise Definition(s):  There are several types of ‘non-financial’ benefits from well-managed, financially sound enterprises – 1) improvements in rural livelihoods that result when enterprise managers, boards or individuals chose to invest profits for the ‘greater good’; (i.e, philanthropy), and 2) improved ‘processes’ or capacities that are available to the ‘larger’ community in which the enterprise functions. Examples of the former include improvements in community infrastructures e.g., improved road networks, establishment or refurbishment of new schools or clinics, or improved water systems or sanitation. Examples of the latter include enhanced governance (organizational, managerial, business skills and transparency), enhanced security or increased empowerment/participation on the part of women in organizational decision-making or in NRM when enterprise managers or employees bring their expertise and insights to other community groups or activities.

Unit of measure: Number of  structures or systems that are improved or established as a result of proceeds from nature based enterprises

Disaggregated by: Geographic area.

3.7.1	MUKOGODO

No non financial benefits have been generated thus far.

3.7.2	MT. KENYA

No non-financial benefits have been realized.

3.7.3	ARABUKO SOKOKE FOREST

The main non-financial benefits have been technical assistance to the Forest adjacent dwellers association (FADA), tree nursery owners, butterfly and beekeeping farmers, and individuals  and CBOs seeking advice on investments of their income from Income Generating Activites.

3.8	FUNCTIONALITY OF INFORMATION SYSTEMS FOR DECISION-MAKING

Indicator Reference Sheet: FORREMS Indicator #8

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.3 Improved Management of Protected Areas

FORREMS Result: #6 Information systems improved for management outside & inside PAs Indicator: Functionality of information systems for decision-making

DESCRIPTION

Precise Definition(s): The ‘functionality’ of a database is a reflection. This indicator presents an indexed score from five (5) criteria representing the degree of functionality of a given information system. Criterion 1: Data are routinely collected and entered into a computerized database; 0 points = no routine data collection or entry is haphazard.; 1 point = data are often collected and entered in a routine fashion; 3 points = data are always collected &entered punctually. Criterion 2: In-depth analyses of data is conducted annually (or more often); YES = 1 point, NO = 0. Criterion 3: Annual (or more often) reports of data analyses and interpretation are produced; YES = 1 point, NO = 0. Criterion 4: Number of copies of results circulated; None = 0, 1-10 = 1 point, 11-25=2 points, 26 or more = 3 points. Criterion 5: Stakeholders can easily obtain the results & reports of data analyses; 0 = Not available, 1 = Not easily accessible; 2 = Moderately accessible; 4 = easily accessible. Thus the maximum points for determining ‘functionality’ of a database is 12. The indexed score is interpreted as follows: 0-4=Not functioning; 5-9=Functional; 10-12=Highly functional. The informations systems being assessed with this indicator are: 1)KWS-GIS, 2) Those that track CBO performance in organizational capacity and financial benefits and 3) databases on land use change Unit of Measure: The index score Disaggregated by: NA

Justification/Management Utility: ‘Functional’ information systems are necessary for improved databases will lead to improved access to accurate information which will then result in improved local NRM decision-making. An increase (or lack thereof) in the indexed score reflects the level of functionality of targeted monitoring databases. It is envisaged that providing Wardens with improved information will result in improved NRM decision-making.

PLAN FOR DATA ACQUISITION BY USAID

Data Collection Method:

Method of Acquisition by USAID: Quarterly reports and Performance Assessment Reports from partners and independent evaluations

Data Source(s): KWS, Forest Department, Africa Wildlife Foundation, NEMA, Nature Kenya and KEFRI

Frequency/Timing of Data Acquisition: Quarterly & annually in October

Estimated Cost of Data Acquisition: Expensive—possibly $15,000/year

Responsible Individual(s) at USAID: Charles Oluchina

DATA QUALITY ISSUES

Date of Initial Data Quality Assessment: August 2004,USAID will take the lead and work closely with FORREMS partners.

Known Data Limitations and Significance (if any): N/A

Actions Taken or Planned to Address Data Limitations: N/A

Date of Future Data Quality Assessments: September 2006

Procedures for Future Data Quality Assessments: Site visits and audit of partner data

PLAN FOR DATA ANALYSIS, REVIEW, & REPORTING

Data Analysis: See ‘Data Collection Method’ above.

Presentation of Data: Display targets and actual performance data in Performance Summary Data Table segregated by geog area and gender where applicable. Tables, charts, graphs or maps will be used to present data.

Review of Data: Review with FORREMS M&E Sub Committee & Program Steering Committee in April & October also in SO portfolio reviews, monthly meetings, or activity or program-level reviews with implementing partners.

Reporting of Data: Annual FORREMS PMP report, success stories.

OTHER NOTES

Notes on Baselines/Targets: The baseline amount for this indicator is ‘zero’ (0) ha. Targets have been set for FY ’04, the first year in which the initiatives of FORREMS partners could be expected to start ‘paying off’ at the SO level. Location of Data Storage: KWS CM&E Unit Other Notes:

THIS SHEET LAST UPDATED ON: 11/12//03

Key Results over the Reporting Period

FUNCTIONALITY OF INFORMATION SYSTEMS FOR DECISION-MAKING

Precise Definition(s):  The ‘functionality’ of a database is a reflection. This indicator presents an indexed score from five (5) criteria representing the degree of functionality of a given information system. Criterion 1: Data are routinely collected and entered into a computerized database; 0 points = no routine data collection or entry is haphazard.; 1 point = data are often collected and entered in a routine fashion; 3 points = data are always collected &entered punctually. Criterion 2: In-depth analyses of data is conducted annually (or more often); YES = 1 point, NO = 0. Criterion 3: Annual (or more often) reports of data analyses and interpretation are produced; YES = 1 point, NO = 0. Criterion 4: Number of copies of results circulated; None = 0, 1-10 = 1 point, 11-25=2 points, 26 or more = 3 points. Criterion 5: Stakeholders can easily obtain the results & reports of data analyses; 0 = Not available, 1 = Not easily accessible; 2 = Moderately accessible; 4 = easily accessible. Thus the maximum points for determining ‘functionality’ of a database is 12. The indexed score is interpreted as follows: 0-4=Not functioning; 5-9=Functional; 10-12=Highly functional. The informations systems being assessed with this indicator are: 1)KWS-GIS, 2) Those that track CBO performance in organizational capacity and financial benefits and 3) databases on land use change

Unit of Measure: The index score

- Besides the FORREMS M&E systems which are used for decision making on the management of the project, several other initiatives are in use to support decision making within the project. These include:

- In the communities, a monitoring system involving forest scouts has been set up. Forest scouts have been trained and deployed to patrol the conservation areas and the Mukogodo forest. An office has been constructed to coordinate their efforts and collate the information. Information collected from their work has been useful in decision making on use of the forest especially through grazing. The information from the scouts will also be very useful for PFM.

- In Makurian, a rangeland rehabilitation committee has been set up to oversee the conservation processes of the range rehabilitation plot. This committee has been monitoring the plot for changes in the area and the information will be very useful for the process.

Data on forest cover of the Aberdares has been acquired from UNEP and fed into the GIS database. Ground Truthing with KWS-GIS operational assistance, has been done in identification of wildlife corridors in and around the Mt Kenya Ecosystem. Vegetation and forest cover digital mapping for the eight 'Forest Conservation Regions' proposed under the new Forests Bill has also been accomplished.

3.9 	LEVEL OF POLICY AND LEGISLATIVE ADVANCEMENT

Forest policy and legislation

FORREMS resources used to facilitate participation in reviewing the Forest Bill 2004. A paper on PFM was presented at the 'MPs' workshop on Forestry (Jan. 2004). The MPs’ concerns of the bill after tabling in the parliament were reviewed.The policy and legal reform process breaks down into six milestone phases as shown below:

(I) Problem identification/diagnosis  (II) pre-formulation and development  (III) Finalisation of policy intervention  (IV) Debate  (V) Adoption  (VI) Implementation and Enforcement

Policy

The Forest Policy 2004 is being finalized for presentation to the Cabinet and publication into a Sessional paper after Parliamentary approval. It is therefore at stage (III)-Finalization of Policy Intervention and it scores 60%. It is hoped that by December 2004 a new forest Policy will be in place. (See table 3 for details on scoring)

Legislation -Forest Bill 2004

The Forest Bill had reached stage (IV)- “Debate” in June 2004, but it was shot down in Parliament and it will be re-introduced again for debate. The Forest Policy/legislation process has scored 60%. Intense lobbying is going on to ensure this time round the Forest Bill gets Parliamentary approval  and hopefully be enacted into Law.

Table 3: Level of Policy/Legislation advancement

| Program Phase (Weight) | Forest Policy | Forest Legislation |
| --- | --- | --- |
|  | 04 | 05 | 06 | 07 | 08 | 04 | 05 | 06 | 07 | 08 |
| I (25) | 25 | - | - | - | - | 25 | - | - | - | - |
| II (20) | 20 | - | - | - | - | 20 | - | - | - | - |
| III (15) | 15 | - | - | - | - | 15 | - | - | - | - |
| IV (10) | - | - | - | - | - | 10 | - | - | - | - |
| V (10) | - | - | - | - | - | - | - | - | - | - |
| VI (10) | - | - | - | - | - | - | - | - | - | - |
| Total (100) | 60 | - | - | - | - | 70 | - | - | - | - |

## 3.10		Advocacy capacity of targeted groups.

Not much was accomplished in terms of policy advocacy except for the few meetings that were held at group ranch level to sensitize members of the new Forest Bill and Policy. The aim was to draw linkages between existing local institutions, site-specific policies, cultural norms, by-laws and our NR legislation. This task will be covered in depth in year two (2) work plan.

## Results by Focal Area

During the first year of FORREMS 2004, the programme’s activities were focused in three areas, namely; Mukogodo, NW Mt. Kenya and Arabuko Sokoke forest at the coast. Background information on each focal area as well as a summation of FORREMS activities and results during the recording period is as follows.

### MUKOGODO FOCAL AREA

### Location, Population and Background

The  area  for project implementation is Mukogodo landscape that includes Mukogodo forest reserve of 26,000 hectares and the neighboring four group ranches namely Kuri kuri, Makurian, Lekuruki and Il Ngwesi, located in Mukogodo Division,  Laikipia district, Rift Valley Province. The landscape also borders large-scale private ranches of Borana, Lodiaga, Lewa Downs Conservancy and Isiolo District.  Maasai communities who have a strong tradition of natural resource governance and management inhabit the project area.  The group ranch committees are responsible for resource allocation, distribution and management within the group ranch.  The communities have divided the forest reserve into four areas with each ranch being responsible for management of its portion of the forest. Even though the area has not been under direct management of Forest Department, the local community has used it for decades with insignificant detriment.

Mukogodo acts as an important dry grazing pasture retreat area for the community.  The forest is also a source of most springs flowing into the group ranches. Some community members reside in the forest but still take care of the forest.  The forest is subdivided into 4 regions with each community group ranch taking care of the forest within its area.  The main livelihood base for the community is livestock keeping.  Most parts of the group ranch are degraded due to overgrazing and soil erosion There is potential for development of nature-based enterprises in four group ranches.  Prior to the inception of  FORREMS program,  two group ranches, Lekuruki and Iingwesi group ranches  had  developed community lodges namely Tassia and Il Ngwesi.

Conservation Resources and Issues

One may argue that if the communities have been conserving the forest for years with minimal noticeable degradation, why then involve the government, which will translate to increased management costs. This is not true because:

- With initiation of settlement schemes around the forest, this is translating to higher use of forest products through construction of permanent houses by the communities.

- Managing the increasing interests and stakeholders in Mukogodo. Being a virgin forest there is a likelihood of opening up the forest for non-consumptive use like eco-tourism. The communities need the government for regulatory purposes and as a guarantor for ensuring local national and global interests and obligations.

- Managing potential conflicts over values, resource use interests and perceptions.

This multiple stakeholder involvement in natural resources management is aimed at making natural resources more responsive to local needs. The argument is that if decision making can be brought closer to the primary users, then resources will be more efficiently, equitably and sustainably managed in line with their local long-term interests.

FORREMS Conservation Strategy for Mukogodo

Table 1: Areas of the Group Ranches Allocated for Conservation

| Group Ranch (GR) | Total Size (ha) | GR area within Forest Reserve (ha) | Areas identified for conservation (ha) | General conservation Strategies | Overall Biodiversity Threats |
| --- | --- | --- | --- | --- | --- |
| Il Ngwesi | 13,172 | 3,985 | To be confirmed | Rangeland rehabilitation and forest restoration | Rangeland degradation (soil erosion, overstocking, overgrazing,) water shortage (watershed destruction), encroachment into the forest; settlement |
| Lekuruki | 18,398 | 10,717 | 2015 | Water development and livestock management |  |
| Makurian | 11,173 | 4,157 | 727 | Rangeland rehabilitation; Agro- biodiversity practices |  |
| Kuri Kuri | 18,773 | 10,690 | 8280 | Enterprise development |  |

Figure 1

Key Results over the Recording Period

During the year 2004 the significant achievements included;

- Land Use Change

A total of 11,022 ha  (to be confirmed) in Mukogodo Forest has been identified as a conservation area in four (4) community group ranches namely: Ilngwesi, Makurian, Kurikuri and Lekuruki.

- In Makurian GR, a range rehabilitation demonstration area measuring 18 ha has been designated and set aside. Conservation techniques applied include; barbed wire-post fence to keep off animals, water harvesting and spreading terraces, grass reseeding, soil and water microcatchments.

- One (1) tree nursery at Dol Dol by FD. This is in a plot, of about 20 ha which will include a proposed campsite.

- In Ilngwesi GR, an area measuring 65 ha has been set aside for hay production.

- In Lekuruki GR, hay bailing demonstration site measuring 12 ha was set aside and fenced.

- Two (2) private  tree nurseries at Ethi and Chumvi  were established as a result of concern over the impact of degradation - 20,000 seedlings each

- Naibunga Conservancy which is outside Mukogondo, a total of 17,200 ha in 9 community  group ranches has been set aside for conservation. Naibunga conservancy is made up of land designated for conservation in Koija, Tiamamut, Kijabe, Nkilorit, Morpusi, Ilpolei, Munishoi, Musul and Ilmotiok group ranches.

- Number Of Stakeholders Benefiting From Involvement In Improved NRM

In Mukogodo, 518 stakeholders benefited directly and 170 indirectly. Out of the direct beneficiaries only 70 males and 11 females could be disaggregated by gender. Thus the disaggregation is incomplete. However from the preliminary data, it can be deduced that participation of female in NRM in Mukogodo is low.

The following stakeholders in Mukogodo benefited from FORREMS support in the following ways:

- 36 community members were trained in methodologies for natural resource inventory and planning in February 2004 and later in April 2004, the group were involved in the actual data collection for developing the inventories and NRM planning.

- 21 community members (18 male, 3 female) were trained as forest scouts in partnership with KWS to provide security for biodiversity conservation in Mukogodo Forest. They will be coordinated through a community office that is being developed by FORREMS in Mukogodo. The communities are paying these scouts.

- 4 Community members were trained in monitoring and evaluation of community based activities.

- 19 community representatives (16 male, 3 female) from ILMAMUSI participated in an exchange visit to Arabuko Sokoke to learn concerning participatory forest management. This was designed to expose them to and prepare them for PFM, which is being developed in Mukogodo forest.

- 67 community members were trained/reached during meetings to develop the umbrella structure (ILMAMUSI) for participatory forest management. Training also included conflict management and constitution building.

- An office is being developed for the ILMAMUSI forest management committee.

- 188 community members consulted during sensitization meetings for the development of  PFM

- A hay bailing seminar was conducted for Lekuruki group ranch for 12 community members (6 men, 6 women). A hay baler was also procured for the community but training on how to use it is yet to be  conducted.

- Organizational development training was provided for 11 members of Meirishi self help group from Lekuruki. This group will engage in hay production.

- Training was conducted for 21 members of the Makurian demonstration plot committee at Dol Dol in March-April 2004.

- Organizational development training conducted for 18 members of the Naningo Youth Group from Ilngwesi Group Ranch. This was designed to strengthen the group to effectively engage in the hay production program.

- 70 stakeholders attended the national aloe stakeholders’ dialogue workshop convened in Nanyuki to guide the development of the sub-sector.

- Visioning workshop held for 51 participants (38 community representatives, 13 partners) for the Mukogodo Landscape in Nanyuki in October 2003. In this workshop, the overall vision for the Mukogodo landscape was developed.

- 19,150 seedlings distributed to …..no. of farmers

- Conservation Tools And Technologies In Use

Fourteen (14) tools and one (1) technology have been in use by stakeholders. In summary;

- Soil and water conservation terraces and micro catchments, grass re-seeding and perimeter fence integrated in the Makurian rehabilitation demonstration site.

- Conservation trust developed:(i) To manage Naibunga Conservancy and (ii) To strengthen the management of natural resources and associated enterprises in Il Ngwesi group ranch

- The process of developing a strategic management plan for Mukugodo forest has began led by FD and KEFRI.

- A five-year strategic plan has been developed for Ilngwesi group ranch to guide NRM and development in the group ranch.

- The process of NRM planning for the Naibung’a community conservancy consisting of 9 group ranches was completed and draft reports have been produced. In group ranches where the process was completed earlier, aspects of the NRM plan are being implemented.

- The process for participatory forest management of the Mukogodo forest has been initiated.

- On-farm tree planting in ethi & chumvi 19,150 seedlings planted.

- Checklist of important trees and other plants with market potential for NBEs

- Natural resource fora and a network exist in the Mukogodo area. These include ILMAMUSI, focal area teams, and Resource Management Area committees.

- Natural resource inventories, ecological species, and ethno-botanical surveys and socioeconomic surveys conducted in the four (4) GRs.

- M&E systems in place

- Organizational Capacity Of Community User Groups

- Community members were trained in Natural resource inventory and planning methodologies

- Community members were trained as forest scouts in partnership with KWS to provide security for biodiversity conservation

- Community trained in M&E

- Community representatives from the ILMAMUSI were trained in PFM, training also included conflict management and constitution building.

- Gave technical advice on process of developing a strategic forest management plan for Mukogodo landscape

- Conducted visioning workshop

- Created an umbrella community structure for the four group ranches and developed an action plan for the umbrella body

- Community members trained on nursery techniques, management and seedling handling

- Nature-Based Enterprises Established

The following nature based enterprises have been established in the Mukogodo area.

- Hay bailing and fodder production in Il Ngwesi GR by Naningo Youth Group (30 persons) at initial stages of strengthening by FORREMS . It has also been initiated in Lekuruki.

- Seedling production at Ethi and Chumvi : two tree seedling nurseries. The seedlings are under production and require 9 months to be ready for planting/sale.

- Apiculture in Naipotaki Cooperative had earlier been initated by CORE and is now being strengthened under FORREMS.

In addition, an enterprise scoping exercise has been conducted and options/scenarios for enterprise development developed. This will be developed or supported during FORREMS.

## Financial And Non-Financial Benefits Generated By NBEs

No financial/Non-financial benefits have been generated in the first year.

MUKOGODO RESOURCE MAP

MT. KENYA FOCAL AREA

## Location, Population and Background

Mt. Kenya is located on the Eastern side of the Great Rift Valley. The Northern slopes reach the Equator 180km North of Nairobi. It covers Nyeri and Kirinyaga districts in Central Province and Meru Central, Meru South and Embu districts in Eastern Province.

The gazetted area of Mt Kenya ecosystem include a 213,831 ha National/forest Reserve (N/FR) under joint MOU management by KWS and FD, and 71,500 ha National Park (NP) under KWS.

FORREMS identified Mt Kenya as a focal area on the basis of its rich biodiversity, critical watershed, critical habitat, indigenous forests, potential for significant economic benefits to the local communities.

Six forest stations1 covering 98,105 ha in North West Mt. Kenya were chosen as target areas. This is because they are prone to fires, high human/wildlife conflicts, wildlife/plantation conflicts and illegal activities. Other areas of consideration include Irangi and Imenti forests.

There are sites whose forests have been degraded by Non Resident Cultivation  (NRC) farmers and wild animals.  Some FORREMs resources will be utilized to rehabilitate plantations and mixed indigenous forests in these areas for commercial forest management and Biodiversity conservation respectively.

- Land Use Change

42 ha were reforested with mixture of Prunus africanum, Fagara microphylla, Vitex keniensis indigenous pioneer tree species in Irangi forest Magacha block jointly by Bill Woodley Trust/COMPACT, forest community user groups, with FD and KWS Forest Program providing technical guidance. The MKJMTF visited Magacha block in June 2004 and found that survival was above average.

In NW Mt. Kenya 100 ha of degraded sites have been designated for rehabilitation. 43 ha in Nyeri and 10 ha in Meru Central were mapped and identified. Nine thousand (9000) indigenous tree seedlings were procured from CBOs for restocking or reforestation on these sites. Due to insufficient short rains in April/June the enrichment planting was deferred to October/November/December 2004. No land use change is yet effected in NW Mt. Kenya.

- Number Of Stakeholders Benefiting From Involvement In Improved NRM

In Mt. Kenya, 23 direct beneficiaries were involved. A total of 115 indirectly benefited. It appears the primary contribution of females in improved natural resource management is marginalized here. At the institutional level 15 KWS and FD received technical training from USAID.

- Conservation Tools And Technologies In Use

Four (4) tools have been initiated and/or are in use. These include:

- Integrated NRM plan for Mt. Kenya under review

- Fire Management Plan (FMP) for Mt Kenya ecosystem initiated. Six localized FMPs for NW Mt. Kenya will be developed from the ecosystem FMP. Three (3) meetings with Meru Central and Nyeri DFOs have been held to plan on emergency fire plans.

- Rehabilitation of degraded sites – Magacha block in Irangi forest

- M&E system by the MKJMTF

- Organizational Capacity Of Community User Groups

The warden Embu and Senior warden Mt Kenya are laying terms of participatory NRM with ten (10) Forest user groups. The MKJMTF has selected some areas as the main sites from which FORREMS will contribute in improving CBOs’ performance.

- Nature-Based Enterprises Established

No NBE was established by FORREMS project in 2003/2004. Viable enterprises will be selected from the pool of those already in use by various existing forest user groups. Most of the NBEs in use include apiculture, tree seedling nurseries, poles and rafters etc.

- Financial Benefits Generated By NBEs

No NBE worked upon by the FORREMS project so far

- Non-Financial Benefits From NBEs

No non-financial benefits have been realized.

## MT. KENYA FOCAL AREA

Arabuko Sokoke Forest

### Location, Population and Background

The Arabuko-Sokoke Forest (ASF) lies close to the Indian Ocean in Kilifi and Malindi Districts of Coast Province, Kenya (see  figure 10).  In the 1960s, ASF covered an area twice as large as the 41,765 ha it covers today. It is the last large remnant of the north-coast forests that once dominated Kenya's coastal fringe, and is a globally important forest for biodiversity conservation as well as a vitally important resource for the local communities. ASF is a dominant feature of the local landscape and regulates fresh water flow to the adjacent Mida Creek and mangrove forest. The creek and mangrove in turn provide fish nurseries, important over-wintering grounds for migrant waders, and a nutrient and sediment trap protecting the Watamu coral reef. The Watamu/Arabuko area is the only place in Kenya where reef, beach, creek and forest occur together in this way, offering considerable potential for a landscape approach to Natural Resource Management (NRM).

The project is targeting the forest adjacent dwellers within a 5-kilometer belt around the ASF. There are 18 sub-locations extending around the forest, with  51 villages actually bordering on the forest and having a population of about 104,000 people (Fig.11). The project is administered from the Gede Forest Station and the marketing of the nature based products at the Gede Ruins Museum.

ASF is one of the most important biodiversity sites in Kenya. It has been ranked as the second most important forest for threatened bird conservation on mainland Africa and is one of 19 Important Bird Areas (IBAs) in Kenya that have been prioritized as critical sites for intensive and immediate conservation action. ASF is part of the East African Coastal Forest/Eastern Arc Forest complex that ranks among the top 25 biodiversity hotspots on earth.

Figure 10: Map Of Arabuko Sokoke Forest Along The Kenyan Coast

Key Results over the Recording Period

During the year 2004 the significant achievements included;

- Land Use Change

An Operational Forest Management Plan and Guidelines for PFM implementation developed for the 11,200 ha under the Dida PFM pilot area: 7,000 ha and 4,200 ha under community and gazetted forest respectively.

Around the forest, 22 ha of woodlots were planted

- Number Of Stakeholders Benefiting From Involvement In Improved NRM

In ASF, 2,043 stakeholders benefited directly and indirectly  (though it is difficult to prove this, it is assumed that this  benefit is extended to 4 or 5 other members of the household.). The direct stakeholder disaggregate, by gender, to 1,329 males and 714 female.

- Conservation Tools And Technologies In Use

At Arabuko-Sokoke Forest 5 tools and 1 technology were adopted.

- Buffer zones around protected areas – woodlots were established on farms that neighbour the forest on the northern border from Kakuyuni to Mida, running along the 20 km fence.

- Agroforestry and farm forestry – 22 ha of wood lots were planted in villages that neighbor the north and east of the forest (Sidzeni 4 ha, Roka 6 ha, Kakuyuni 5 ha, Mkongani 4ha, Mida-Majaoni 3 ha)

- M&E systems and databases - Monitoring protocols and framework were developed for biodiversity. Protocols developed for vegetation, butterflies, birds, and elephant shrews.

- PFM – Operational Forest Management Plan and Guidelines developed. Changing of the Dida Forest Adjacent Forest Association (DIFAAFA) to a society is on-going.

- Natural resource fora and networks – Arabuko-Sokoke Forest Adjacent Association (FADA) committee strengthened and the Arabuko- Sokoke Forum operationalised.

- Organizational Capacity Of Community User Groups

Organization capacity assessment (OCA) of groups has not been done on any of the targeted CBOs for capacity building. Three groups have benefited:

- Arabuko Sokoke Forest Adjacent Dwellers Association (FADA) - facilitation of regular meetings of delegates at which the groups constitution and structure of association as umbrella reviewed. As community group in charge of electric fence, technical support on establishing a sustainable fence maintenance unit provided. The groups’ Chairman was facilitated to attend national fora to disseminate the ASF experience.

- Dida Forest Adjacent Area Forest Association (DIFAAFA) - review of guidelines for PFM implementation that include roles and responsibilities of members, officials and user groups. Strengthened governance and review constitution, faciliting change of the CBO to a society, one of the requirements for community participation in forest management. Facilitated the Chairman to disseminate the ASF PFM experience at national fora.

- Mangagani Butterfly farmers – assisted in building business planning capacity and  investment evaluation, in developing spin off activities from income from butterfly farming.

- Beekeeping farmers in ASF – developed a network beekeepers that will facilitate training on modern methods of beekeeping, standardization and quality control and marketing.

- Nature-Based Enterprises Established

- Eco-tourism (scenic sites and roads) – road signages and clearance of walking trails in collaboration with the community guides. (how many beneficiaries??)

- Agro-forestry – 22 ha of woodlots, 46,040 trees planted. (how many beneficiaries??)

- Aloe farming – 8,000 suckers procured and under multiplication in community nurseries. Farmers have been identified and soil sampled in the planting area. (how many beneficiaries??)

- Financial Benefits Generated By NBEs

Agro-forestry ($ 3,164 income to community for sale of seedlings)

- Non-Financial Benefits From NBEs

The main non-financial benefits have been technical assistance to the Forest adjacent dwellers association (FADA), tree nursery owners, butterfly and beekeeping farmers, and individuals  and CBOs seeking advice on investments of their income from Income Generating Activites.

ASF RESOURCE MAP SHOWING POPULATION DENSITIES AND FOREST-ADJACENT DWELLERS

# Footnotes

Source: KWS Forest Report

1 NaroMoru, Gathiuru, Nanyuki, Mariana ,Mucheene, Meru.

Source: Revised PDT

Source: Revised PDT

Source: LWF/AWF Report

In Nyeri, the distribution of the 43 ha is as follows: Naromoru-10 ha, Nanyuki-23 ha, Gathiuru-10 ha.  Most of the areas were opened for cultivation under NRC and later abandoned. Some are encroachment on the indigenous forest.

In Meru Central 10 ha in Ontulili Block –Ontulili Forest Station was identified and mapped for rehabilitation.

Source: Ayiemba Report

Source: AWF/LWF Report, Kagombe Report

Source: KWS Forest Report

This includes PFOs, DFOs around Mt. Kenya ecosystem and Snr. Warden Aberdares.

* The disaggregation between direct and indirect beneficiaries has not been show, an assumption is made that this benefit is extended to 4 or 5 other members of the household

Kirinyaga Afforestation and Tourism Attraction Group (KAATA),  Kariki Youth Group (KYP),

Irangi Honey Collectors Group (HCG), Gikumbo/Githuthum Moat Self Help Group (GGMSHG),

Ragati Forest Retired Officers Self Help Group (RFROSHG),  Hombe Community Afforestation and Agroforestry Group.(HCAAG),

Mathina Young Women Group (MYWG), Friends of Mount Kenya Forest (FMKF), Kithunguri Beekeepers Group (KBG), Nyagithai/Kariko Moat Group (NMMKMG)

1 NaroMoru, Gathiuru, Nanyuki, Mariana ,Mucheene, Meru.

In Nyeri, the distribution of the 43 ha is as follows: Naromoru-10 ha, Nanyuki-23 ha, Gathiuru-10 ha.  Most of the areas were opened for cultivation under NRC and later abandoned. Some are encroachment on the indigenous forest.

In Meru Central 10 ha in Ontulili Block –Ontulili Forest Station was identified and mapped for rehabilitation.

Kirinyaga Afforestation and Tourism Attraction Group (KAATA),  Kariki Youth Group (KYP),

Irangi Honey Collectors Group (HCG), Gikumbo/Githuthum Moat Self Help Group (GGMSHG),

Ragati Forest Retired Officers Self Help Group (RFROSHG),  Hombe Community Afforestation and Agroforestry Group.(HCAAG),

Mathina Young Women Group (MYWG), Friends of Mount Kenya Forest (FMKF), Kithunguri Beekeepers Group (KBG), Nyagithai/Kariko Moat Group (NMMKMG)

Source: Ayiemba Report