Jan. 17, 06

# ACRONYMS

AWF			African Wildlife Foundation

CBO			Community Based Organization

CM&E			Central Monitoring and Evaluation

CORE 			Conservation of Resources Through Enterprise

EMCA			Environmental Management and Coordination Act

FAT			Focal Area Team

FD			Forest Department

FORREMS	Forest/Rangeland Rehabilitation and Environmental Management Strengthening Initiatives

GIS		 	Geographical Information Systems

GOK 			Government of Kenya

ILMAMUSI	Il Ngwesi, Makurian, Mukogodo (Kurikuri), Sieku (Lekuruki)

IR			Intermediate Result

KEFRI			Kenya Forestry Research Institute

KWS			Kenya Wildlife Service

LUMO		           Lualenyi Mulaba Oza

LWF			Laikipia Wildlife Forum

M&E			Monitoring and Evaluation

MKJMTF		Mount Kenya Joint Management Task Force

NEMA			National Environmental and Management

Authority

NK	 		Nature Kenya

NMK	 		National Museums of Kenya

NRM			Natural Resource Management

OCA			Organizational Capacity Assessment

OD			Organizational development

PA			Protected Area

PAC			Problem Animal Control

PFM			Participatory Forest Management

PMP			Performance Monitoring Plan

PMR			Performance Monitoring Report

PSC			Project Steering Committee

SO5			Strategic Objective Number Five (5)

TA			Technical Assistance

USAID			United States Agency For International Development

# GLOSSARY OF TERMS

Baseline

Baseline is a record of what exists in an area prior to action. It is primarily a benchmark for the future. The baseline values establish the starting point from which change can be measured.

Data Analysis

Concise description of how performance data for individual indicators or groups of related indicators will be analyzed to determine progress on results. Data analysis techniques and data presentation formats are identified.

Data collection method

The approach to data collection taken by the USAID SO Team for each indicator. Note whether it is primary or existing secondary data. Primary data is collected specifically within the context of the SO5 program. Secondary data is collected by another source for some other purpose.

Data limitations

Identify whether data may be weak or limited. Describe actions to be taken to address data limitations.

Data source

The source is the entity from which the data are obtained usually the organizations that conducts the data collection effort. Data sources may include government departments, international organizations, other donors, NGOs, private firms, USAID officers, contractors or activity implementing agencies.

Disadvantaged groups

Groups that have typically or historically been put at a disadvantage usually in their level of involvement in development projects. Disaggregated groups include women, youth, aged, specific ethnicity etc.

Disaggregated

How data will be separated to improve the breadth of understanding of results reported. Typical ways to disaggregate data include geographic location and gender.

Estimated cost of collection

Estimated cost of data collection efforts to the SO or implementing partner. Personnel time to follow normal monitoring and evaluation activities is usually not incorporated.

Frequency of data collection

How often data is to be collected. The frequency of monitoring will depend on the variables being investigated. Depending on the performance indicator, it may make sense to collect data on a quarterly, annual, or less frequent basis. When planning the frequency, and scheduling of data collection, an important factor to consider is management’s needs for timely information for decision making.

Indicator

An indicator means key actions, functions, elements, or objects which by virtue of their physical, biological, economic or organizational attributes, are so closely associated with the system in which they are found as to be indicative of the state or trends (improvement or deterioration) of the system.

Initial Data Quality Assessment

Date when the operating unit reviews the characteristics, attributes, and caliber of data being provided to the SO by implementing partners.

Improved Natural Resource Management

Reversing, halting or reducing the rate of unsustainable use of natural resource base through an integrated management approach.

Management Utility

Description of the usefulness and purpose of the indicator to management decision-making.

Method/Approach of Data Collection

The method/approach of data collection utilized by the operating unit.

Performance Indicator

A performance indicator is a quantitative or qualitative dimension or scale to measure program results against a strategic objective or a program outcome. A performance indicator should be a precise, direct measure of the relevant objective. It should be practical, that is, data is available or can be generated, and Disaggregated by gender where possible and appropriate

Performance Monitoring Plan

A comprehensive performance-monitoring plan is designed to track/project impacts in all program/project phases. The variables to be tracked are carefully selected and they must be of good measure of the anticipated changes. The monitoring plan describes all the indicators to be monitored, the units of measurement, data sources, methodology of data collection, monitoring frequency, responsibility, baseline values and targets set within the planning horizon.

Precise Definition

The indicator definition states what it is that should be measured. They define the variables that help measure change within a given situation as well as information that describes progress and impacts. The definition must be detailed enough to ensure that different people at different times, given the task of collecting data for a given indicator, would collect identical types of data.

Presentation of Data

Concise description of how data results will be displayed such as the use of tables or maps.

Reporting of Data

Concise description of how data results will be chronicled and whether results are appropriate for inclusion in the R4.

Responsible Organisation/Individuals

Responsibility is used here to refer to the institutions or organizations (government counterparts, NGOs, contractors) collecting the monitoring data. For each performance indicator, the responsibility and the operating unit for the timely acquisition of data from their source should be clearly assigned to a particular office, team or individual.

Review of Data

Dates when the operating unit’s review progress (and reliability) of data collection efforts to date and discuss preliminary results. Reviews identify key questions to be resolved.

Stakeholders

The local groups of communities, institutions, organizations and individuals who may have a vested interest in improving the management of natural resources in the target areas (stakeholders may include local government institutions, commercial enterprises, private, group and communal landowners, community based organizations and non-governmental organizations).

Target

Magnitude or level of outputs expected to be achieved. Targets are values against which the actual program/project achievements are measured. They should be realistic and quantitative statements of expected outcomes. If the targets are qualitative, there is need for a detailed statement of expected state of affairs at the end of a planning period.

Target Group

The direct beneficiaries the program/project aims to reach.

Targeted Biodiverse Areas

An area within the USAID management interest based on its biological richness and uniqueness; extent of threat to its natural resources; probability of impact in maintaining critical ecosystem processes; potential for demonstrating innovative approaches with probability of stimulating broad systematic changes of probability of replication; probability of immediate direct benefits to focus communities; capacity and resources of principal partners and compatibility and potential for integration with other mission investments.

Technologies

Technologies are state-of-the-art ideas and practices that combine input into a system to produce higher value output for and by stakeholders.

Tools

Tools refer to packages o complimentary practices intended for application in project operations to achieve set goals and targets for improvement of stakeholders’ welfare.

Unit of Measurement

The unit of measurement is the precise parameter used to describe the magnitude or size of the indicator.

EXECUTIVE SUMMARY

USAID/FORREMS has so far been implemented for two (2 No.) years in selected biodiverse ecosystems to achieve Strategic Objective Number Five (5) SO5 “Improved Natural Resource Management in and Outside Protected Areas by and for Stakeholders”.

Implementing partners comprise KWS, FD, KEFRI, AWF/LWF, NK and NEMA in collaboration with community stakeholders. Partners work in teams providing leads in three focal areas as follows: - Mukogodo focal area implementing partners include AWF/LWF, KEFRI, NEMA, FD; KWS, FD and KEFRI work jointly in Mt. Kenya, whereas Arabuko Sokoke Forest implementing team include NK, FD, KWS, KEFRI and NMK.

At the end of first implementation period – 2004, Partners identified opportunities and made recommendations for furthering SO5 initiatives in their areas of activity then laid strategic workplans, which were implemented delivering following results.

Partners held M&E training workshop during which they revised existing reference indicators and set respective target levels for the future Financial Years based on the feasibility of achieving them within the context of available resources.

- In Mukogodo landscape 19,468 ha (779% of target) of land was improved by individuals and community groups through range rehabilitation, soil and water conservation techniques, pasture management systems, commercial Aloe production, hay production and designation of conservation areas. 325 males and 138 women benefited from involvement. Organizational development support was provided to ILMAMUSI. A natural resources management (NRM) plan for Naibunga conservancy trust was finalized. Financial benefits worthy KShs. 90,000 (US$1,199.98) were earned from sale of trees seedlings and Aloe seedlings (in Rumuruti forest).

- In NW. Mt. Kenya 90 ha (75% of Target) of degraded forest sites were rehabilitated. Other tools distinctive to this focal area are seedlings nurseries and grazing management systems. Integrated management plan was developed from 80% to 90%.  Sale of trees seedlings and honey by community stakeholders were the main sources of financial benefits amounting KShs. 235,800 (US$3,144).

- Arabuko Sokoke Forest project target areas include Dida, Mida, Kararacha, Kakuyuni and Mabuani. Main achievements were the completion of the management plan for  Dida forest area, benefits flow to 2043 persons and development of environmental tools for NRM. Tour guiding fees and sales of trees seedlings and Aloe suckers contributed to income generation of KShs. 2,122,715 (US$ 28,306.87). Specific tools applied include agro-forestry in community lands, beekeeping, butterfly farming, ecotourism enterprises, NRM networks all under the framework of PFM.

Across project sites, FORREMS performance overshot targets in land use change, number of beneficiaries, number of conservation tools in use, level of benefits from nature - based enterprises and legislative advances. However, due to challenges encountered targets were not realized in replication of conservation tools, integrated management planning and organizational capacity strengthening. Nevertheless the high ratio of number of replications to adoptions (7:69) implies strong willingness of communities to apply FORREMS initiatives. PFM, integrated management planning, nurseries for production of seedlings and suckers, farm forestry and land rehabilitation are common tools in use in all project sites. Main streams of benefits flow common in all project sites include casual employment, sale of non-timber forest products (NTFPs), training and infrastructure development. Substantial results have been yielded by policy and legislative efforts in Aloe Sector reforms, forestry and environmental management and coordination.

Incomplete management plans, ongoing initiatives such as PFM processes and organizational development, replication of crucial tools and techniques call for furthering of FORREMS projects so as to wean off community stakeholders for self reliant and sustainable conservation of natural resources.

I. INTRODUCTION

## Project Background

USAID’s Forestry/Range Rehabilitation and Environmental Management Strengthening initiative (FORREMS) is a four and-a-half year program within the Mission’s Natural Resource Management (NRM) portfolio. Subject to availability of funds, it has an estimated funding level of about $5.1 million and should conclude in September 2006. FORREMS will support two components:

Strengthening the Government of Kenya NRM institutions through capacity building, technical assistance and material support with focus to improving forest management, rangeland conservation and environmental management.

To involve community user groups in NRM through organizational capacity building to facilitate active participation of CBOs in conservation and Nature Based Enterprises. The community beneficiaries will have more incentives to contribute to improved NRM through PFM.

OBJECTIVES

The FORREMS' project contributes to USAID Strategic Objective (SO5) “ Improved natural resource management in targeted biodiverse areas by and for stakeholders”, through the following three (3) Intermediate Results; {Contributing to each of these IRs is a set of Sub-IRs as explained in the Results Framework. (Appendix I)}

- IR 5.1 Site specific initiatives for NRM implemented outside PAs

- IR 5.3 Improved Management of PAs

- IR 5.4 NRM and Environmental policy and legislative reform advanced

The specific objectives are to;

- Increase amount of positive land use for conservation

- Increase stakeholders’ accrued benefits from involvement in NRM conservation

- Develop and use appropriate tools and technology for positive land use

- Improve stakeholders’ management of natural resources through advancement of organizations and institutions.

- Enhance performance of nature-based enterprises within the focal areas.

- Increase and improve effectiveness of NRM advocacy by both national and local groups.

## project sites

The FORREMS program’s geographic focus has been selected on the basis of rich biodiversity, critical water resources, remnant indigenous forests, and the potential for significant economic benefits to local communities and USAID’s strategic NRM objective for Kenya. The priority focal areas include:

- Mukogodo division in Laikipia district,

- North West Mt. Kenya,

- Arabuko Sokoke Forest in North Coast and

- Other areas, which include Rumuruti forest, Aberdares, Ngong Hills, Taita Hills, Kwale.

INSTITUTIONAL PARTNERS

### Kenya Wildlife Service (KWS)

The mandate of KWS is to conserve and manage wildlife in Kenya.   KWS has five sections that participate in FORREMS: -

The Central Monitoring and Evaluation Unit (CM&E) serves as the M&E  “institutional home” for USAID/FORREMS project. The Forest Coordination Unit provides technical advise, coordination of forest reserves management and forestry expertise towards SO5 in the FORREMS Target areas. KWS/Laikipia is a member of FAT in the Mukogodo landscape where it has been providing communities with incentives for improved NRM. The Ecological Monitoring Unit collects, analyzes and reports critical information necessary for planning, monitoring and updating biodiversity cover and land use for the USAID/FORREMS focal areas. GIS provides spatial analysis to inform planning and to track the geographic ‘spread’ of FORREMS’ positive impacts in land use and rural livelihoods.

### Forest Department (FD)

The Forest Department collaborates with KWS, NMK, KEFRI, AWF/LWF, NEMA, Community Forest User Groups and other relevant stakeholders in drafting guidelines and approving management plans for improved management of forests consistent with the proposed forest policy framework and anticipated new forest legislation.

The mandate of the Forest Department is to contribute to the growth of the natural resource sector by enhancing development, conservation and management of all forest resource base in the country. This entails ensuring an increasing supply of forestry products and services for meeting the basic and industrial needs of the present and future generations.

### Kenya Forestry Research Institute (KEFRI)

KEFRI collaborate with FD, KWS, NEMA and AWF/LWF in Laikipia and FD, PACT Kenya in Taita Taveta.  In Arabuko Sokoke forest, KEFRI is one of the main partners working with FD, KWS, NMK and Nature Kenya. KEFRI has shared their experiences in Dry land Rehabilitation, PFM, development of strategic plan, and on-farm tree planting with community members during awareness creation meetings. KEFRI brings demonstrated expertise in the use of these technologies to FORREMS and has played a vital role in extending these management practices to stakeholders.

### African Wildlife Foundation (AWF) / Laikipia Wildlife Forum (LWF)

These bring to bear strong NRM and business development skills.   The Laikipia Wildlife Forum has “ on the ground presence” and a strong constituency through its membership.   The partnership demonstrates improved rangeland and dryland forest management practices among local communities, channeling FORREMS funds to priority NRM developments such as water points and expanding economic enterprises through business development and training. AWF/LWF works within all the thirteen group ranches including Mukogodo forest and Samburu Nature.

### National Environmental Management Authority (NEMA)

NEMA is empowered under the Environmental Management and Coordination Act (EMCA) to develop guidelines and regulations relating to overall environmental conservation and management and to ensure all users of Kenya’s natural resources comply with these regulations. NEMA is also involved in Environmental Assessment and establishment of environmental protection guidelines.

NEMA has two main objectives:

a) To develop the guidelines and regulations that will operationalize EMCA (e.g., guidelines for EIA and environmental audits, for environmental screening and for conservation orders and environmental easements). Further the FORREMS Program will support acquisition of materials.

b) To build the capacity of the members of the District Environment Committee to ensure compliance with EMCA.  Here, a particular area of focus will be to assist local partners in the use of these guidelines in planning development activities.  At the local level, partners will also work with DECs to address conservation priorities through action plans for managing marine resources, forests and rangelands and with resources to implement and leverage resources in support of plans. Additional support will help establish functional offices and enable DECs to interact with communities in establishing environmental management regulation guidelines.

### Nature Kenya (NK)

The key role of Nature Kenya is program management and coordination, ensuring the delivery of planned activities to achieve the planned outputs to the intermediate results under 5.1, 5.2, 5.3 and 5.4. Nature Kenya is implementing the project with the Arabuko Sokoke Forest Management Team (ASFMT) that comprises of officers from the KWS, FD, NMK and KEFRI stations in Malindi and Kilifi Districts. At the community level Nature Kenya works with Forest Adjacent Dwellers Association  (FADA), an umbrella of CBOs around ASF, to engrain PFM and nature based enterprises. Nature Kenya and the ASFMT are building their capacity to participate in Natural Resource Management at ASF ecosystem.

## ANTICIPATED RESULTS

As progress towards SO5 objective, target results for the second year of implementation have been set. The performance indicators have been projected as follows:

- Positive land use change is expected at 2,798 ha across the three focal areas. Positive land use change will be indicated by number of hectares under improved NRM. This will constitute land management actions, dedicated to natural resource conservation, protection and/or improved management. At the project sites, areas under improved management will be delineated using participatory mapping and GIS.

- Number of stakeholders directly or indirectly benefiting from involvement in improved NRM is expected to total 3,320 persons in the year 2005. The direct beneficiaries will receive funding, training, technical assistance, resource or financial returns under the program. Indirect beneficiaries are those who receive ‘spin-offs’ or ‘down stream’ positive impact. Disaggregation by gender will be done to determine male/female participation.

- Appropriate conservation tools and technologies adapted for positive land use change will facilitate conservation, protection and sustainable utilization of natural resources. The disaggregation is by geographic area and by gender. Performance target set for year two: five (5) tools and/or technologies in use.

- Number of adaptation and replication of NRM tools, technologies and initiatives were expected to total ____ and ____ respectively.  The number of times an initiative is replicated will indicate the acceptance in application of the tools and technology.

- FORREMS partners targeted to finalize (4 Number) natural resources management plans.  The process includes sensitization, drafting plan, stakeholders' workshop and final development of plan then implementation.

- Organizational capacity of community user groups strengthened. The Organizational Capacity Assessment (OCA) tool has been identified as an important tool to “score” strengths and weaknesses of organizations, thereby the performance will be determined by Organizational Capacity scores of targeted CBOs. FORREMS stakeholders will be trained on Organisational Development to facilitate results. FORREMS expect to conduct 2 OCA exercises and strengthen _____ (___ number) CBOs across the three focal areas.

- Functionality of information systems for decision-making:  Index scores are expected to increase, reflecting the level of functionality of improved monitoring, evaluation and reporting systems. This will improve access to accurate information necessary for improved NRM for decision-making.

- Financial and non-financial benefits generated by NBEs: Income in the form of salaries or wages, ‘dividends’ paid from operational profits are expected to double baseline from the third year of programme implementation.

- Percentage of GOK partners utilizing new M&E systems: All the GOK partners expect to have developed and be utilizing tools for tracking and reporting performance for improved decision making.

- Status of policy and legislation environment to encourage community incentives for natural resources conservation. The Aloe policy development under the wildlife Act was targeted to be complete by the end of the second implementation period.

- Level of NRM and Environmental policy/legislation advancement. The forest policy and bill were targeted for level III (60%) i.e. finalization of policy intervention.

## ROJECT MONITORING

The results framework provided by USAID for the FORREMS program is both a planning and a management tool (Appendix I). It is central to the strategic plan and provides a program-level framework for implementing partners to gauge progress toward the achievement of results and to adjust relevant programs and activities accordingly. The results framework provides an important opportunity for the operating unit to work with its partners and community members to build consensus and ownership around shared objectives and approaches to meeting those objectives.  The results Framework therefore functions as an effective communication tool because it succinctly captures the key elements for achieving an objective (i.e. program intent and content).

DOCUMENT PRESENTATION

This report presents results of activities undertaken during 2005 or the second year of program implementation.  The report is in three main sections;

- Introduction,

- Performance results for 2005 in summary format,

- Specific project site performance, challenges encountered, lessons learned and solutions forwarded.

- Baseline Performance indicator data sheets, which present the program level indicators agreed to evaluate the overall performance of the program and baseline values of the indicators.

II. PERFORMANCE RESULTS FOR 2005

II-1. SUMMARY OF KEY RESULTS

The FORREMS program during the second year of implementation had made the following achievements:-

- Land use change cumulative hectares were 34,232.7 ha out of which a total of 34,150.7 hectares was brought under conservation in this reporting period against the target 2,878 hectares (the target did not include Naibunga conservancy), hence an increase of 33,965.7 hectares (99.5%), compared to 185 hectares in 2004

- Number of stakeholders that benefited were 6,179 in 2005 out of these 3,305 was males and 2,874 females.  Beneficiaries who benefited previously were 105 giving direct beneficiaries a total of 6,074 with 30,370 indirect (with 5 indirect per one direct).

- Forty nine (49 No.) conservation tools and technologies (I.e.  16 tools and 23 technologies) adapted by FORREMS partner for positive land use change in the project sites were used to improve conservation. Notable tools in use were participatory forest management, conservation improvement, water harvesting & management, grazing management systems, natural resource enterprises, natural resource management planning, problem animal control, natural resource networks and monitoring, evaluation systems and databases.

- Number of adoption and replication of NRM tools, technologies and initiatives in targeted and other areas were 8 including hay production, NRM planning, tree nursery, farm forestry, PFM, grazing management, farm forestry and natural resource network.

- Integrated NRM plans finalized were 2 (i.e. Naibunga and Dida) while three (3 No.) (i.e. Mukogodo landscape, Mt. Kenya and Ngong hills Ecosystems) are in draft form.

- Functionality of information systems for decision making for various FORREMS partners are limited in their state of art.  Scores indicated for KWS-GIS and CM&E databases was 7, KEFRI database was rated 8 and Arabuko Sokoke forest management team database rated 5.  This implies that the databases are functional though there is room for improvement.

- Financial benefits to communities from nature-based enterprises was Kshs.2,458,490 (US$ 32,779.87) out of which kshs.2,420,990 (US$32,279.87) was paid off in form of sale in nature based products and guiding fees.

- Non-financial benefits from nature based enterprises included, improved network, i.e. road, security, and communication systems, fencing, reduced grazing pressure, reduced farm invasion hence improved food security and water catchment improvement.

- Organizational capacity of one (1) community user group (ILMAUSI in Mukogodo) was assessed and improved. The OCA score rated 3.0 out of 6.0 (emerging stage). Partners are working on the weaknesses identified to improve the group.  Second OCA to determine impact of actions on CBO’s identified weaknesses is not yet done.

- Percentage of GOK partners utilizing new M&E systems include the chief executives and departmental heads.  However, all the GOK partners are developing tools as a requirement by the government in the performance contracts.

- Status of policy and legislation environment to encourage community incentives for natural resources conservation was reflected by key activities according to set milestones.  A major achievement was the Aloe policy (under wildlife management, which was accepted by KWS board hence 100% achievements.

- Level of environmental policy / legislation advanced according to set milestones, the forest policy made a 70% achievement, Forest Bill 2005 - 80% and EMCA 1999 made achievement of 100%.

## II-2. Table 1: Summary Of progress made towards contractual Requirements IN FOCAL AREAS.

| Indicator | Base year | Baseline | 2004 Target | 2004 Actual | 2005 Target | 2005 Actual | 2006 Actual | 2006 Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Land use change in Ha |  |  |  |  | 2,798 | 34,104.7 |  |  |
| # of stakeholders benefiting |  |  |  |  | 3,320 | 5,828 |  |  |
| # of conservation tools in use |  |  |  |  | 5 | 43 |  |  |
| #conservation tools & techno. replicated |  |  |  |  |  | 8 |  |  |
| # integrated nrm plans developed and implemented |  |  |  |  | 4 | 2 |  |  |
| Functionality of information systems |  |  |  |  |  | 5 - 8 |  |  |
| Financial benefits generated by NBEs |  |  |  |  | Dbl income over B-line | k.shs.2,458,490 (US$ 32,779.87 |  |  |
| Non financial benefits from NBEs |  |  |  |  | Dbl income over B-line | 5 |  |  |
| Organizational capacity of target CBOs |  | ILMAMUSI-3.0 |  |  | ILMAMUSI - __ | 3.0 to __ |  |  |
| Status of policy and legislation environment to encourage community incentives for natural resources conservation |  |  |  |  | Aloe policy-100% | Aloe policy- 100% |  |  |
| Level of environmental policy / legislation advanced |  |  |  |  | Forest policy and legislation – 60% | Forest policy-70% Forest Bill 2005-80% EMCA 1999-100% |  |  |

II-3. RESULTS BY PROJECT SITE

### MUKOGODO LANDSCAPE   (Laikipia Focal Area)

The area for project implementation comprises Mukogodo forest reserve measuring 30,000 hectares including the neighboring four group ranches namely Kuri kuri, Makurian, Lekuruki and Il Ngwesi.  It is located in Mukogodo Division, Laikipia District, Rift Valley Province. The landscape also borders large-scale private ranches of Borana, Loldaiga, Lewa Wildlife Conservancy and Isiolo District.  Maasai communities who have a strong tradition of natural resource governance and management inhabit the project area.  The group ranch committees are responsible for resource allocation, distribution and management within the group ranch.  The communities have divided the forest reserve into four areas with each ranch being responsible for management of its portion of the forest. Most parts of the group ranch are degraded due to overgrazing and soil erosion. There is potential for development of nature-based enterprises in the four group ranches and surrounding areas.

Prior to the inception of FORREMS program, two group ranches, Lekuruki and Il Ngwesi had developed Tassia and Il Ngwesi community lodges. Multiple stakeholder involvement in NRM is aimed at making natural resources more responsive to local needs. The argument is that if decision-making can be brought closer to the primary users, then resources will be more efficiently, equitably and sustainably managed in line with their local long-term interests. The four group ranches cover a total area of 61,516 ha and the area identified for conservation is approximately 11,022 ha.

Specific Interventions

1. Rehabilitation of degraded rangelands (2004-5)

2. On-farm tree planting (2004-5)

3. Natural resources inventories (2004-5)

4. Developing and implementing integrated land use plans (2004-6)

5. Participatory forest management initiatives (2004-5)

6. Enterprise development (2004-6)

7. Water points development (2004-5)

8. Fodder/grass bulking (2004-5)

9.  Capacity building in community organization maintenance (2004)

Key achievements 2005

During the second year of the program implementation,  partners operating in Laikipia focal area reported the following achievements.

- Land measuring 19,468 hectares was brought under positive use through: -

Tree planting   by individuals, community and schools;

Land rehabilitation, soil conservation, gully control, bush clearing and enriched grass planting as well as controlled pasture utilization; Establishment of a quality hay stand; Setting aside and fencing protected areas and Development of utilization guidelines and NRM plan for Naibunga Conservancy Trust.

- Stakeholders in total were 463, men 325 and women 138 who benefited (103 had received benefits previously).  Benefits were received through casual employment, sale of seedlings and prunings, training in fire management, and M&E,.  Awareness creation on NRM, training in hay seed management, entrepreneurship, PFM planning process and resource management & strategic plan development.  Two study tours were conducted and organizational development support provided. Gender empowerment being addressed by supporting project that target women and youth.

- Conservation tools and technologies in use included NRM plans for landscape, PFM, farm forestry, Hay production and M&E systems and data bases development.  Water management included rainwater harvesting, soil conservation, (gully and terracing), dam development, spring protection, rock catchment, rainwater tank development, borehole rehabilitation, run off water drainage, channel damming, gravity pipeline conveyance.  Livestock rearing being the major activity in the area was enhanced through scratching ground to allow regeneration, grass seedling, controlled grazing within site by fencing, pasture bulking for dry season livestock feeding and hay management. Tree planting and community agreeing that no cutting within controlled site. Woodlots and nursery were establishment as well as seed quality management.  Aloe commercial production, nursery establishment and aloe range rehabilitation.  Terrace to control erosion, gabions and check dams were introduced and to control problem animals   predator proof bomas were introduced and 4 completed.

- Adoption and replication of tools, technologies and initiative in target areas included hay production, tree nurseries and NRM planning.  This reflects the community willingness to use the tools.

- Integrated NRM plan for Naibunga conservancy was completed. Major activities implemented are ecotourism & wildlife management, security improvement for wildlife, livestock and other natural resources and sand resources management.   A draft for Mukogodo forest integrated management plan was developed and will be completed next reporting period.

- Financial benefits accrued from nature-based enterprises and in particular sale of tree seedlings amounted to Kshs.80,000 (US$1,066.65) plus K.Shs. 10,000 (US$133.33) from sale of Aloe seedlings in Rumuruti.

- Non-financial benefits received from nature-based enterprises included, trainings, technical assistance, resource access, improved access roads (38km), CDF allocation for fencing off four schools, improved security and communication systems through provision of equipment and training of game scouts and reduced grazing pressure on Mukogodo forest by production of bales for livestock feeds.

- Organizational capacity assessment for ILMAMUSI CBO was done. Results placed the CBO at emerging stage with average score of 3.0 out of 6.0.  The CBO leaders were trained on PFM.  Their AGM was conducted and new leaders elected.

- Improvement of policy and legislative environment to encourage incentives for wildlife conservation included:

#### Awareness creation to selected group ranch stakeholders that

led to registration of a self-help group;

Stakeholders' consensus on aloe sector's guidelines;

45 extension workers trained in aloe husbandry;

30 KWS district wardens training on regulatory roles, formalization of guidelines and

Aloe guidelines accepted by KWS board of directors.

- Progress in establishment of a policy environment supportive of improved NRM was made through Aloe sector policy accepted by KWS board of directors

2004 Achievements

1. Land use change in 2004 (Total of 11,022 hectares)

In Makurian GR, a range rehabilitation demonstration area measuring 18 ha has been designated and set aside. Conservation techniques applied include; barbed wire-post fence to keep off animals, water harvesting and spreading terraces, grass reseeding, soil and water microcatchments. One (1) tree nursery at Dol Dol by FD. This is in a plot, of about 20 ha which will include a proposed campsite. In Il Ngwesi GR, an area measuring 65 ha has been set aside for hay production. In Lekuruki GR, hay bailing demonstration site measuring 12 ha was set aside and fenced. Two (2) private tree nurseries at Ethi and Chumvi were established as a result of concern over the impact of degradation - 20,000 seedlings each Naibunga Conservancy, which is outside Mukogondo, a total of 17,200 ha in 9 community group ranches has been set aside for conservation. Naibunga conservancy is made up of land designated for conservation in Koija, Tiamamut, Kijabe, Nkilorit, Morpusi, Ilpolei, Munishoi, Musul and Ilmotiok group ranches.

2. Number of Stakeholders: Direct (518) and (170) Out of the direct beneficiaries only 70 males and 11 females.

36 community members were trained in methodologies for natural resource inventory and planning in February 2004 and later in April 2004, the group were involved in the actual data collection for developing the inventories and NRM planning. 21 community members (18 male, 3 female) were trained as forest scouts in partnership with KWS to provide security for biodiversity conservation in Mukogodo Forest. They will be coordinated through a community office that is being developed by FORREMS in Mukogodo. The communities are paying these scouts. 4 Community members were trained in monitoring and evaluation of community based activities. 19 community representatives (16 male, 3 female) from ILMAMUSI participated in an exchange visit to Arabuko Sokoke to learn concerning participatory forest management. This was designed to expose them to and prepare them for PFM, which is being developed in Mukogodo forest. 67 community members were trained/reached during meetings to develop the umbrella structure (ILMAMUSI) for participatory forest management. Training also included conflict management and constitution building. An office is being developed for the ILMAMUSI forest management committee. 188 community members consulted during sensitization meetings for the development of PFM A hay-bailing seminar was conducted for Lekuruki group ranch for 12 community members (6 men, 6 women). A hay baler was also procured for the community but training on how to use it is yet to be conducted. Organizational development training was provided for 11 members of Meirishi self help group from Lekuruki. This group will engage in hay production. Training was conducted for 21 members of the Makurian demonstration plot committee at Dol Dol in March-April 2004. Organizational development training conducted for 18 members of the Naningo Youth Group from Il Ngwesi Group Ranch. This was designed to strengthen the group to effectively engage in the hay production program. 70 stakeholders attended the national aloe stakeholders’ dialogue workshop convened in Nanyuki to guide the development of the sub-sector. Visioning workshop held for 51 participants (38 community representatives, 13 partners) for the Mukogodo Landscape in Nanyuki in October 2003. In this workshop, the overall vision for the Mukogodo landscape was developed. 19,150 seedlings distributed.

3. Conservation tools and / or technology in use: Fourteen (14) tools and one (1) technology in use by stakeholders.

Soil and water conservation terraces and micro catchments, grass re-seeding and perimeter fence integrated in the Makurian rehabilitation demonstration site. Conservation trust developed:(i) To manage Naibunga Conservancy and (ii) To strengthen the management of natural resources and associated enterprises in Il Ngwesi group ranch The process of developing a strategic management plan for Mukugodo forest has began led by FD and KEFRI. A five-year strategic plan has been developed for Ilngwesi group ranch to guide NRM and development in the group ranch. The process of NRM planning for the Naibung’a community conservancy consisting of 9 group ranches was completed and draft reports have been produced. In-group ranches where the process was completed earlier, aspect of the NRM plan are being implemented. The process for participatory forest management of the Mukogodo forest has been initiated. On-farm tree planting in Ethi & Chumvi 19,150 seedlings planted. Checklist of important trees and other plants with market potential for NBEs Natural resource fora and a network exist in the Mukogodo area. These include ILMAMUSI, focal area teams, and Resource Management Area committees. Natural resource inventories, ecological species, and ethno-botanical surveys and socioeconomic surveys conducted in the four (4) GRs. M&E systems in place

4. Organizational Capacity of Community Groups

Community members were trained in Natural resource inventory and planning methodologies Community members were trained as forest scouts in partnership with KWS to provide security for biodiversity conservation Community trained in M&E Community representatives from the ILMAMUSI were trained in PFM, training also included conflict management and constitution building. Gave technical advice on process of developing a strategic forest management plan for Mukogodo landscape Conducted visioning workshop Created an umbrella community structure for the four group ranches and developed an action plan for the umbrella body Community members trained on nursery techniques, management and seedling handling

5. Nature Based Enterprises established

Hay bailing and fodder production in Il Ngwesi GR by Naningo Youth Group (30 persons) at initial stages of strengthening by FORREMS. It has also been initiated in Lekuruki. Seedling production at Ethi and Chumvi : two tree seedling nurseries. The seedlings are under production and require 9 months to be ready for planting/sale. Apiculture in Naipotaki Cooperative had earlier been initiated by CORE and is now being strengthened under FORREMS. In addition, an enterprise scooping exercise has been conducted and options/scenarios for enterprise development developed. This will be developed or supported during FORREMS.

6. Financial Benefits Generated by NBES

No financial benefits have been generated in the first year

7. Non-financial benefits from NBES

No non-financial benefits have been generated so far

### Challenges

Lessons learned

Opportunities and prospects

Mukogodo/Laikipia Map

### MT. KENYA

Mt. Kenya is located on the Eastern side of the Great Rift Valley. The Northern slopes reach the Equator 180km North of Nairobi. It covers Nyeri and Kirinyaga districts in Central Province and Meru Central, Meru South and Embu districts in Eastern Province.

FORREMS identified Mt Kenya as a focal area on the basis of its rich biodiversity, critical watershed, critical habitat, indigenous forests, and potential for significant economic benefits to the local communities.

Six forest stations1 covering 98,105 ha in North West Mt. Kenya were chosen as target areas. This is because they are prone to fires, high human/wildlife conflicts, wildlife/plantation conflicts and illegal activities. Other areas of consideration include Irangi and Imenti forests.

A high potential agricultural area surrounds Mt Kenya with a population of 450,000 individuals. Illegal activities threaten conservation of indigenous tree species and commercial plantations. These activities also threaten the continuity of the National/forest reserve (N/FR). Incidences of encroachment into the PAs are high. Community forest user groups are collaborating with FD and KWS within PFM framework.

Specific Interventions

- Rehabilitation of indigenous forest (2004-5)

- PFM in plantation management (2004)

- Woodlots and fuel wood harvesting (2004-5)

- Professional training in forest management (2004-5)

- Infrastructure development (2004-5)

- On-farm forestry (2004-5)

- Timber marketing (2004)

- Support to key CBOs (2004-5)

- Advancing a management partnership between KWS and FD (2004-5)

- Development of management plans (2004-5)

Key achievements 2005

During this period the area team report the following key achievements;

- Increased positive land use change in the area was 89.9 hectares through rehabilitation with seedlings.

- Stakeholders who benefited were 1,536 in total which included 1,081 men and 455 women.  Benefits were mainly through casual employment, sale of seedlings and prunings, firewood collection, training in fire management, M&E, and PFM.

- 5 Conservation tools and technologies in use included nurseries for seedlings production, grazing management systems, PFM, rehabilitation of firebreaks and access roads and beating up.

- Tools that were replicated within the area were tree nursery and grazing management system.

- A draft integrated management plan for Mt. Kenya is over 90% done and some activities proposed in the plan are ongoing.

- Financial benefits were accrued from nature-based enterprises and in particular sale of honey and seedlings amounting to Kshs.235,800 (US$3,144).

- Non-financial benefits from nature-based enterprises included, use of honey for medicinal purposes and local brew.

Achievements in 2004

1. Land use change in 2004 (Total of 185 hectares

A total of 42 ha were reforested within mixture of Prunus africanum, Fagara microphylla, Vitex keniensis indigenous pioneer tree species in Irangi forest Magacha block jointly by Bill Woodley Trust/COMPACT, forest community user groups, with FD and KWS Forest Program providing technical guidance. The MKJMTF visited Magacha block in June 2004 and found that survival was above average. In NW Mt. Kenya 100 ha of degraded sites have been designated for rehabilitation. 43 ha in Nyeri and 10 ha in Meru Central were mapped and identified. Nine thousand (9000) indigenous tree seedlings were procured from CBOs for restocking or reforestation on these sites. Due to insufficient short rains in April/June the enrichment planting was deferred to October/November/December 2004. No land use change is yet effected in NW Mt. Kenya.

2. Number of stakeholders: Total (138); Direct (23) Indirect (115)

Community members beneficiaries were 23 directly involved in improved NRM and a total of 115 indirectly benefited. It appears the primary contribution of females in improved NRM is marginalized here. At the institutional level 15 KWS and FD staff received technical training from USAID

3. Conservation tools and / or technology in use: Four (4) tools have been initiated and/or are in use

Integrated NRM plan for Mt. Kenya under review Fire Management Plan (FMP) for Mt Kenya ecosystem initiated. Six localized FMPs for NW Mt. Kenya will be developed from the ecosystem FMP. Three (3) meetings with Meru Central and Nyeri DFOs have been held to plan on emergency fire plans. Rehabilitation of degraded sites – Magacha block in Irangi forest M&E system by the MKJMTF

4. Organizational Capacity of community groups

Terms of participatory NRM with ten (10) Forest user groups' development on going. MKJMTF selected some areas as the main sites from which FORREMS will contribute in improving CBOs' performance.

5. Nature based enterprises

There were no nature-based enterprises established. Viable enterprises will be selected from the pool of those already in use by various Forest user groups. Most of the NBEs in use include apiculture, tree seedling nurseries, poles and rafters.

Challenges

Lessons learned

Opportunities and prospects

Map

### ARABUKO SOKOKE FOREST

The Arabuko-Sokoke Forest (ASF) lies close to the Indian Ocean in Kilifi and Malindi Districts of Coast Province, Kenya. In the 1960s, ASF covered an area twice as large as the 41,765 ha it covers today. It is the last large remnant of the north-coast forests that once dominated Kenya's coastal fringe, and is a globally important forest for biodiversity conservation as well as a vitally important resource for the local communities. ASF is a dominant feature of the local landscape and regulates fresh water flow to the adjacent Mida Creek and mangrove forest. The creek and mangrove in turn provide fish nurseries, important over-wintering grounds for migrant waders, and a nutrient and sediment trap protecting the Watamu coral reef. The Watamu/Arabuko area is the only place in Kenya where reef, beach, creek and forest occur together in this way, offering considerable potential for a landscape approach to Natural Resource Management (NRM).

Project sites, location and area

The project is targeting the forest adjacent dwellers within a 5-kilometer belt around the ASF. There are 18 sub-locations extending around the forest, with 51 villages actually bordering on the forest and having a population of about 104,000 people as per the 1999 Kenya population census. The project is administered from the Gede Forest Station and the marketing of the nature based products at the Kipepeo Market Centre, Gede Ruins Museum.

NEMA has projects in Magarini Division of Malindi District addressing the rehabilitation of the sand mines in partnership with the local communities. NEMA is operationalizing the EMCA with the Malindi District Environmental committees.

Specific Interventions

Arabuko-sokoke forest

- Advancing and scaling up PFM;

- Expanding and diversifying nature-based enterprises;

- Establishing a monitoring and evaluation program;

- Strengthening institutions and partnerships;

- Ecosystem management inside and outside the Forest (agro-forestry, alternative fuel supply, fire control, boundary marking, rehabilitation and restoration, problem animal control, linking with District Environmental Committees in planning and problem solving); and

- Gender, equity, empowerment and

- Advancing policy.

NEMA sites

- Rehabilitation of sand mines

- Operationalization of EMCA

Key achievements 2005

- Increase in positive land use change was 14,546.8 ha, which include aloe farming with five (5) demonstration plots, woodlots establishment around ASF, sunflower farming and pepper trails.  Participatory forest management inside and outside the protected area. The target of 100 hectares for the year was exceeded because of the increased awareness on tree planting for poles and scaling of PFM to two new sites. The PFM sites were to be delivered in 2006 but 14, 400 hectares were already under PFM in 2005.

- Stakeholders who benefited from involvement in improved NRM at Arabuko-Sokoke were 2,043(1,329 male and 714 female) especially through financial benefits, technical assistance, resource access and training. Stakeholders who benefited from involvement in the NEMA programs were 40 (31 male and 9 female).

- Conservation tools and technologies developed and in use were six (6), these included:

  - Agroforestry and farm forestry

  - Monitoring evaluation systems and databases

  - NRM plans on nature based enterprises such as beekeeping, aloe farming (nursery and on farm), butterfly, sunflower farming and traditional medicine.

  - Participatory forest management

  - Natural resource networks for nature based enterprises and forest associations.

  - Problem animal control using pepper.

On NEMA sites environmental tools for management of natural resources were mainly developed:  operational and training manuals for Provincial Environmental Committees(PECs) and District  Environmental Committee (DECs); Environmentally Significant Areas; Environmental Impact Assessment and Environmental Audits; Economic instruments; Environmental Easements and Restoration Orders and Deposit Bonds criteria.

- Nature based enterprises established were seven in number i.e. apiculture, butterfly farming, sericulture, aloe farming ecotourism guiding, traditional medicine practices, agro/farm forestry.  Establishment of mushroom farming is at survey level while basketry is at production level.

- Financial benefits generated by nature based enterprises at Arabuko-Sokoke amounted to KShs.3,982,791. The income that can be directly attributed to this projects intervention is KShs 2,122,715 (US$ 28,306.87) which was generated from ecotourism guiding, sales of seedlings and Aloe suckers. The project contributed to other income generating activities such as apiculture (KShs. 293,560)and butterfly farming (Kshs.1,566,516) but the project’s target of doubling the participants incomes in these enterprises is yet to be achieved.

- Non financial benefits were mainly in the form of improved networks amongst the stakeholder CBOs for training, production, quality control, value adding and marketing of forest related products, in view of sustainability of the activities/enterprises at the end of the project.

Challenges

- At Arabuko-Sokoke there are several projects with different implementation approaches that made it difficult to ascertain the exact output/impact from specific contributions by the individual projects. The management team has made efforts to harmonize these approaches and recommend that the outputs/impacts be credited to all the projects that contribute to the outputs.

- Different reporting frames for the projects and GoK implementing agents leads to delay in the documentation and reporting for continual use of the data in the day to day management of joint activities. The management has proposed the establishment of a central database where each partner could extract the information they require.

- Incorporation of project activities within departmental workplans so that officers can implement activities and deliver outputs within the projects time frames remains a challenge in view of the current departmental performance contracts.

Lessons learnt

- The Arabuko-Sokoke community is willing to participate in forest conservation and protection activities. This is reflected by the fact that the project exceeded the targets in agro/farm forestry and PFM.

- There is potential for income generation from forest related enterprises but the main challenge is value adding and markets.

###### Opportunities and prospects

Achievements in 2004

1. Land use change in 2004 (Total of 22hectares)

An operational Forest Management Plan and Guidelines from PFM implementation developed for the 11,200ha under Dida PFM pilot area. 7,000 ha and 4,200 ha under community and gazetted forest respectively. Around the forest, 22 ha of woodlots were planted

2. Number of stakeholders: Direct ( ) ; Indirect

In ASF, 2,043 stakeholders benefited directly and indirectly and these included 1,329 males and 714 females. (it is assumed that this benefit is extended to 4 or 5 other members of the household)

3. Conservation tools and / or technology in use: (5 tools; 1 technology adopted)

Buffer zones around protected areas – woodlots were established on farms that neighbour the forest on the northern border from Kakuyuni to Mida, running along the 20 km fence. Agroforestry and farm forestry – 22 ha of wood lots were planted in villages that neighbor the north and east of the forest (Sidzeni 4 ha, Roka 6 ha, Kakuyuni 5 ha, Mkongani 4ha, Mida-Majaoni 3 ha) M&E systems and databases - Monitoring protocols and framework were developed for biodiversity. Protocols developed for vegetation, butterflies, birds, and elephant shrews. PFM – Operational Forest Management Plan and Guidelines developed. Changing of the Dida Forest Adjacent Forest Association (DIFAAFA) to a society is on-going. Natural resource fora and networks – Arabuko-Sokoke Forest Adjacent Association (FADA) committee strengthened and the Arabuko- Sokoke Forum operationalised.

4. Organizational Capacity of Community Groups (OCA not done)

Arabuko Sokoke Forest Adjacent Dwellers Association (FADA) - facilitation of regular meetings of delegates at which the groups' constitution and structure of association as umbrella reviewed. As community group in charge of electric fence, technical support on establishing a sustainable fence maintenance unit provided. The groups’ Chairman was facilitated to attend national fora to disseminate the ASF experience. Dida Forest Adjacent Area Forest Association (DIFAAFA) - review of guidelines for PFM implementation that include roles and responsibilities of members, officials and user groups. Strengthened governance and review constitution, facilitating change of the CBO to a society, one of the requirements for community participation in forest management. Facilitated the Chairman to disseminate the ASF PFM experience at national fora. Mangagani Butterfly farmers – assisted in building business planning capacity and investment evaluation, in developing spin off activities from income from butterfly farming. Beekeeping farmers in ASF – developed network beekeepers that will facilitate training on modern methods of beekeeping, standardization and quality control and marketing.

5. Nature Based Enterprises

Eco-tourism (scenic sites and roads) – road signages and clearance of walking trails in collaboration with the community guides Agro-forestry – 22 ha of woodlots, 46,040 trees planted. Aloe farming – 8,000 suckers procured and under multiplication in community nurseries. Farmers have been identified and soil sampled in the planting area.

Improvements in Office Equipment

FORREMS supported procurement of equipment for enhancing institutional capacity of implementing units as follows: -

KWS

1 digital camera, 1 photocopier/printer/ scanner, purchases by GIS,EMU.

NEMA

FD

KEFRI

NK

IV. BASELINE PERFORMANCE INDICATOR DATA SHEETS

This section presents the indicators selected to evaluate the overall performance over length of the program and baseline values for those indicators recorded as of October 2005. The indicators represent a particular characteristic or dimension of the anticipated results and changes in an indicator over time show the extent to which the result is achieved. Data on actual performance are collected over time and presented annually to assess progress.

Performance Data Table (PDT)

The PDT (Appendix V) shows targets set for each of the eight indicators. The revised indicators 1 & 2 are in the revised PDT shown in Appendix V. Both of these tables give the baselines and actual performances of the FORREMS activities. From these, the trend of the activities can be determined as declining, stable/constant or increasing (Appendix IV & V)

The PDT is meant for guiding partners evaluate the performance of their activities against set targets

The M&E FORREMS workshops decided upon indicator target levels for the Financial Years based on the feasibility of achieving them within the context of available resources. The Performance and thus the targets are expected to increase annually.

Data Quality Assessments

For data quality, all indicators are expected to be subjected to quality assessment process whereby they are evaluated on a ten (10) point criteria as shown below:

- Direct (the measure closely tracks the result it is intended to measure).

- Objective (the measure is operational precise and uni-dimensional).

- Adequate (the number of measures tracked for a given result should be the minimum necessary to ensure progress toward the result is sufficiently captured)

- Practical (Data can be collected on a timely basis and at reasonable cost)

- Attributable to FORREMS (the extent to which a result is caused by FORREMS sponsored activities)

- Management useful (measure should be deemed useful by program management staff)

- Level of Results Achieved (Measure should reflect progress at the FORREMS program level)

- Reliable (Data is sufficiently reliable quality for confident decision making)

- Quantitative (Indicators are numerical where possible)

- Disaggregated (Indicator data can be disaggregated by gender, age, location, or other dimension where appropriate)

IV-1. LAND USE CHANGE IN TARGET AREAS

| FORREMS Results: Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders. |
| --- |
| SO5 Intermediate Result: None |
| Indicator: Land use change in target areas tools & technologies in use |
| Indicator description: Hectares of land under positive use in the FORREMS target areas of Mukogodo Landscape, NW Mt. Kenya and Arabuko Sokoke Forest. Other areas include Rumuruti forest, Aberdares, Ngong, Taita Hills and Kwale. ‘Positive use’ refers to land management actions that are purposefully dedicated to natural resource conservation, protection and/or improved management. These actions may occur inside gazetted National Parks, National Reserves, Forest Reserves or Trust Lands or outside these areas on community lands or private farms. Examples of ‘positive land use change’ are the initiation or expansion of: participatory forest management in gazetted Reserves; agroforestry or conservation farming on farms adjacent to Protected Areas; conservation areas, sanctuaries or easements established on community or private lands; tree nurseries and conservation ‘demo’ areas on community or private land; and areas within gazetted Reserves that are managed under site-specific guidelines or operational plans. |
| Unit of Measure: Number of hectares under improved NRM |
| Disaggregated by: Geographic area, gender (male/female owned or managed farms) |
| COMMENTS: Total cumulative land under positive use was 34,232.7 ha out of which 34,104.7 hectares was contribution made in 2005 as follows, Mukogodo 19,468, Mt. Kenya 89.9 ha, and Arabuko Sokoke 14,546.8 hectares. Other areas brought a total of 46 hectares, namely Ngong Hills 6, and Taita Taveta 40 hectares. |
| Baseline (ha) | 2004 | 2005 | 2006 |
| 90.113 | Target | Actual | Target | Actual | Target | Actual |
|  | 6,153 | 82 | 2,878 | 34,150.7 |  |  |

| LAND USE CHANGE IN PROJECT SITES - Summary |
| --- |
| Baseline (b): 90,113ha |
| PROJECT SITE | Sub-unit targeted for land use change | Specify type of positive land use change in target area |
| 1) Mukogodo Landscape |  |
| Year | Expected results in Ha | Actual results in Ha |  |
| 2005 | 2,500 |  | Makurian Group Ranch (Demo site) | Enriched grass planting Tree planting (3,000 seedlings) Soil conservation control (6km) Gully control (6 ha) Scratching of ground to allow regeneration |
|  |  | 2,000 | Makurian Pastures improvement (Loruk) | Land rehabilitated, gully control, bush clearing (500 ha) |
|  |  | 17,400 | Naibunga Conservancy Trust | Protected land set aside, controlled pasture utilization, NRM plan developed |
|  |  | 14 | Il Ngwesi Group Ranch (hay bulking) | Protected area fenced, quality hay stand established, utilization guidelines developed |
|  |  | 14 | Tassia / Lekuruki (hay bulking) | Protected area fenced, quality hay stand established, utilization guidelines developed |
|  |  | 40 | Mukogodo landscape (Ethi and Chumvi) | 40,000 seedlings distributed to community for planting in communal and individual plots |
| Sub –Total | 2500 | 19, 468 |  | NB: the target did not include Naibunga conservancy |
| 2004 | 1,893 | 18 | Makurian Group Ranch | Range rehabilitation demo area has been identified and is currently under conservation with active participation by the Mukogodo community. |
|  | Nil | Nil | Il Ngwesi Group Ranch | Land set aside for hay bailing; 14ha |
|  | Nil | Nil | Lekuruki (Sieku) Group Ranch | Hay bailing demo site set aside and fenced; 12ha |
|  | Nil | Nil | Ethi Private Ranch | 20,000 seedlings planted |
|  | Nil | Nil | Chumvi Private Ranch | 20,000 seedlings planted |
| Sub –Total |  | 18 |  |  |
| 2) Mt. Kenya |  |  |
| Year | Expected results in Ha | Actual results in Ha |  |
| 2005 |  | 6 | Nanyuki Forest Station | Area rehabilitated with 5,105 seedlings |
|  |  | 5.2 | Naro Moru Forest Station | Area planted with 6,000 seedlings |
|  |  | 6 | Gathiuru Forest Station | 5105 seedlings planted |
|  |  | 14.7 | Mucheene Forest Station | Planted with 15,000 seedlings |
|  |  | 40 | Meru Forest Station | 48000 seedlings planted |
|  |  | 10 | Ontulili Forest Station | 10,000 seedlings |
|  |  | 8 | Marania Forest Station | 8,000 seedlings planted |
| Sub -Total | 120 | 89.9 |  |  |
| 2004 | 40 | 42 | Magacha block in Irangi forest | Reforestation of 42 ha with indigenous species. In NW Mt. Kenya 43 ha of degraded sites have been identified for rehabilitation. |
| 3) Arabuko Sokoke |
| Year | Expected results in Ha | Actual results in Ha |  |
| 2005 | 100 | 11.2 | Dida & Malanga | Aloe farming, Pepper trials |
|  | 78 | 135.6 | Around Arabuko Sokoke Forest | Woodlot established with over 200,000*** seedlings |
|  |  |  | Kakuyuni-Jilore (Northern ASF) | Agroforestry integrating trees and Sunflower farming |
|  | 0 | 14,400 | Kakuyuni-Mabuani PFM | Participatory forest management 0n 5400 ha Inside and 9000 ha outside protected area |
| Sub -Total | 178 | 14546.8 |  |  |
| 2004 | 4200 |  | PFM Area | Operational Forest Management Plan and Guidelines for PFM implementation developed for 11,200 ha under the Dida PFM pilot area: 7,000 ha and 4,200 ha under community and gazetted forest respectively. This is yet to be implemented. |
|  | 20 | 22 | Adjacent farm woodlots | 22 ha of woodlots planted. |
| Sub –Total | 4220 | 22 |  |  |
| Other Areas |
| Year | Expected results in Ha | Actual results in Ha |  |
| 2005 | 30 | 6 | Ngong Hills Forest reserve | Degraded water catchment area rehabilitated with desirable species and fenced off from grazers to improve the catchments quality. |
|  | 30 | 15 | Taita Taveta water catchment areas( LUMO and Kishushe) | Planting indigenous species - 10,000 seedlings |
|  | 50 | 25 | Taita Taveta-(Mbanga ngombe and Mbanga ngware) | Onfarm tree planting / woodlot established for 100 farmers with 20,000 seedlings |
| Sub –Total | 110 | 46 |  |  |
| Grand Total 2005 | 2,908 | 34,150.7 |  |  |

IV-2. NUMBER OF STAKEHOLDERS BENEFITING FROM INVOLVEMENT IN IMPROVED NRM

The number of stakeholders includes those directly or indirectly benefiting from involvement in initiatives under FORREMS that improve NRM. ‘Stakeholders’ are individuals or institutions committing time or resources to or benefiting from the FORREMS program. The term refers to individual farmers or resource users, community-based associations or user groups, NGOs or GoK institutions. ‘Benefits’ are improvements in such parameters or conditions as revenue or income, financial position, accessibility to resources, capacity to perform within institutional mandates, or institutional sustainability. There are two categories of beneficiaries of FORREMS initiatives —direct and indirect. ‘Direct’ beneficiaries are those stakeholders that receive funding, training, technical assistance, resource access or financial returns under the program.  ‘Indirect’ beneficiaries are those who receive ‘spin-offs’ or ‘downstream’ positive impacts from FORREMS. For example, butterfly farmers directly benefit from TA that improves market access leading to higher financial returns for pupae sold. On the other hand, a registered Group Ranch member indirectly benefits if the institutional capacity of the management committee to govern and manage funds is enhanced.

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: None FORREMS Result #2: same as SO statement

Unit of Measure: Number of individuals Data Source(s): KWS, Forest Department, Africa Wildlife Foundation, NEMA, Nature Kenya, KEFRI and KCMI partners Indicator description: This indicator measures the FORREMS program’s direct contribution at the SO level. It tracks programs impact on the SO’s stated goal of increasing the number of Kenyans benefiting from improved land management, biodiversity conservation and sustainable NRM. Number of stakeholders directly or indirectly benefiting from involvement in initiatives under FORREMS that improve NRM. ‘Stakeholders’ are defined as individuals or institutions committing time or resources to or benefiting from the programs. The term refers to individual farmers or resource users, community-based associations or user groups, NGOs or GoK institutions. ‘Benefits’ are improvements in such parameters or conditions as revenue or income, financial position, accessibility to resources, capacity to perform within institutional mandates, or institutional sustainability. There are two categories of beneficiaries of programs initiatives —direct and indirect. ‘Direct’ beneficiaries are those stakeholders that receive funding, training, technical assistance, resource access or financial returns under the program. ‘Indirect’ beneficiaries are those who receive ‘spin-offs’ or ‘downstream’ positive impacts from FORREMS. For example, butterfly farmers directly benefit from TA that improves market access leading to higher financial returns for pupae sold. On the other hand, a registered Group Ranch member indirectly benefits if the institutional capacity of the management committee to govern and manage funds is enhanced. Comment: Total cumulative number of beneficiaries was 8,363 including 2,043 that benefited from 2004. (the direct communities that benefited in 2005 were 6,179 (3, 305 Male, 2874 Female) and indirect beneficiaries were 30,895; FORREMS partners (officers) who benefited were 141, (121 Male 20 Female) 2004 2005 2006 Male Female Total Male Female Total 1,399* 725* 2,584 3,426 2,894 6,320 (108) (30) (138) Figure in brackets ( ) indicate previous beneficiaries

| Name of Focal Area | Type of Benefit | No. of direct beneficiaries | No. indirect beneficiaries (5 next of kins per direct beneficiary |
| --- | --- | --- | --- |
|  |  | Male | Female | Total |  |
| Mukogodo 2005 | PFM Training for CBO leaders and community members | 25(20) | 10(4) | 35(24) | 175 |
|  | Exchange visit by community members to Arusha, Tanzania | 26 | 4 | 30 | 150 |
|  | Exchange visit by community members to Kibwezi, Eastern province-Kenya | 24 (4) | 16 (1) | 40 (5) | 200 |
|  | M akurian demo plots work force | 10 (8) | 25 (16) | 35 (24) | 175 |
|  | ILMAMUSI strategic planning workshop. | 45(20) | 10(4) | 55(24) | 275 |
|  | Naibunga Trust OD and governance training | 22 ( 15) | 3 | 25 (15 ) | 125 |
|  | Technical advice on rehabilitation and onfarm tree planting | 40 | 10 | 50 | 250 |
|  | Training in natural resources valuation | 19 (1) | 10 | 29 | 145 |
|  | Nature based workshop | 25 (7) | 14 (3) | 39 (10) | 195 |
|  | Nature based resource mapping | 8 | 3 | 11 | 55 |
|  | Casual employment in Video script for Mukogodo landscape | 7 | 5 | 12 | 60 |
|  | Casual wages for Dol Dol nursery | 20 | 9 | 29 | 145 |
|  | Sale of seedlings | 5 | 3 | 8 | 40 |
|  | Technical assistance (TA) in operationalizaion of EMCA 1999 | 29 | 6 | 35 | 175 |
|  | Strategic workshop for Mukogodo landscape | 20 | 10 | 30 | 150 |
|  | Sub - total | 325 (75) | 138 (28) | 463 (103) | 2315 |
| Mukogodo 2004 | Inventory training | 31 | 5 | 36 | 170 |
|  | Game scouts | 18 | 3 | 21 |  |
|  | Monitoring & evaluation | 5 | 0 | 5 |  |
|  | Visioning workshop | ND | ND | 37 |  |
|  | OD training/ILMAMUSI | ND | ND | 20 |  |
|  | Exchange visit to ASF (PFM) | 16 | 3 | 19 |  |
|  | Developing of umbrella structure (PFM) | ND | ND | 67 |  |
|  | Sensitization meetings | ND | ND | 190 |  |
|  | Institutional training | ND | ND | 247 |  |
|  | Grand Total | 70 | 11 | 642 | 170 |
| Mt Kenya |  |  |  |  |  |
| Meru Central 2005 | Casual wages | 134 | 85 | 219 | 1,095 |
|  | Sale of seedlings | 310 | 303 | 613 | 3,065 |
|  | PRA funds | 18 | 8 | 26 | 130 |
| Nyeri 2005 | Casual employment, | 29 | 23 | 52 | 260 |
|  | Purchase of seedlings, | 12 | 18 | 30 | 150 |
|  | Sale of prunings, | 69 | 5 | 74 | 370 |
|  | Firewood collection for sale | 40 | 0 | 40 | 200 |
|  | Training in nursery management and seedlings production | 7 | 13 | 20 | 100 |
| Sub - total |  | 1081 | 455 | 1536 | 7680 |
| Mt. Kenya 2004 | Financial returns to casual workers in identification of degraded sites for rehabilitation | 10 | 3 | 13 | 65 |
|  | Sale of Seedlings by CBO members | ND | ND | 10 | 50 |
|  | Technical training for KWS and FD staff funded by USAID. |  |  | 15 |  |
|  | Grand Total |  |  | 23 | 115 |
| Arabuko Sokoke 2005 | Training in NRM | 80 | 212 | 292 | 1460 |
|  | TA | 127 | 251 | 378 | 1890 |
|  | Resources access from forest reserve | 906 | 757 | 1,663 | 8315 |
|  | Financial income from NBEs | 602 | 994 | 1596 | 7980 |
| Sub - total |  | 1715 | 2214 | 3929 |  |
| Arabuko Sokoke Forest 2004 | Training, Technical assistance, Resource Assessment, Financial returns | 1,329 | 714 | 2,043* | See footnote (*) |
|  | Grand Total | 1,329 | 714 | 2,043 |  |
| Other areas 2005 | Scouts training in Rumuruti forest | 25 | 3 | 28 | 140 |
|  | Aloe extensionists’ training | 37 (2) | 6 | 43 | 215 |
|  | Sale of seedlings in Ngong Hills | 12 | 8 | 20 | 100 |
|  | Casual wages /Ngong | 10 | 0 | 10 | 50 |
|  | Water catchment areas in LUMO | 30 | 20 | 50 | 500 |
|  | Onfarm tree planting in Taita | 70 | 30 | 100 | 500 |
|  | Aberdares management planning consultative workshops. |  |  | 158 | 790 |
| Sub total |  | 184 (2) | 67 | 251 (2) | 1255 |
| Grand Total 2005 |  | 3305 (77) | 2874 (28) | 6179 (105) |  |
| FORREMS Partners 2005 | OCA training | 15 | 2 | 17 | 85 |
|  | PFM training in Kitui | 26 (2) | 6 | 32 | 160 |
|  | Training in M&E | 27 (21) | 5 (2) | 32 | 160 |
|  | Training in fire management | 26 (8) | 0 | 26 | 130 |
|  | Training in PFM in Arusha | 7 | 0 | 7 | 35 |
|  | Training in improved NRM for KEFRI officers | 7 | 1 | 8 | 40 |
|  | Technical assistance (TA) in operationalization of EMCA 1999 | 5 | 3 | 8 | 40 |
|  | Strategic NRM planning workshop for Mukogodo landscape | 8 | 3 | 11 | 55 |
|  | National Training (Principles of accounts, accounting for parastatals and information technology | 10 | 17 | 27 | 174 |
| Grand total |  | 121 (31) | 20 (2) | 141 (33) | 705 |

Figures in brackets ( ) indicate beneficiaries who participated previously.

ND - Note determined

IV-3. Number Of Conservation Tools And Technologies In Use Within And Outside Protected Areas

Text summary data

A conservation tool "or technology” is defined as a device or application of science that facilitates conservation, protection or sustainable utilization of natural resources.  Examples of conservation tools or technologies are: 1) Buffer zones around Protected Areas; 2) Land trusts or Conservation trusts; 3) Agroforestry and farm forestry; 4) Monitoring & evaluation systems and databases; 5) Conservation leases and/or easements; 6) NRM plans on GoK, community and private lands and that target a variety of resources (forest products, non-timber forest products, rangeland, wildlife); 7) Water harvesting & management; 8) Participatory Forest Management; 9) Grazing management systems; 10) Natural resource fora or networks.    “Use” means formally adopted, recognized, implemented or followed.  ‘Target areas’ are NE Laikipia, NW Mt. Kenya and Arabuko Sokoke Forest, North Coast.

Tools and technologies in use 2005

1. Participatory Forest Management

- Tree nurseries establishment

- Woodlots establishment

- Farm forestry

- Agroforesrty

- Seed quality management

- Beating up

- Enriched planting

- Non-timber products extraction

2. Conservation improvement

- Conservation demo plots

- Soil conservation terracing

- Gully control

- Aloe for range rehabilitation

3. Water harvesting & management

- Rain water harvesting

- Dam development

- Rock catchment

- Rain water tank development

- Spring water protection

- Off site water conveyance

- Runoff storage in drainage damming

- Gravity pipeline conveyance

- Bole hole rehabilitation

4. Grazing management systems

- Reseeding

- Hay bulking

- Hay storage

- Hay seed management

5. Nature based enterprise

- Conservation trust

- Ecotourism

- Aloe nursery

- Aloe commercial production

6. Natural Resource Management

Planning

- Draft NRM plans

- Completed plans

- Implementation of plans

7. Problem management control

- Predator proof boma

- Pepper for PAC

8.  Natural resource networks

9.  Monitoring and evaluation Systems and

Databases

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1-Site specific initiatives for NRM implemented outside Protected Areas; and 5.3-Improved management of Protected Areas. FORREMS Result #3: Appropriate tools & technologies for forest/range management adopted by communities and/or Government lead agencies in target areas

Indicator: Number of Conservation tools and technologies in use within and outside protected areas tools & technologies in use

Unit of Measure: Number of technologies and/or tools in use Indicator description: A conservation “tool or technology” is defined as a device or application of science that facilitates conservation, protection or sustainable utilization of natural resources. Examples of conservation tools or technologies are: 1) Buffer zones around Protected Areas; 2) Land trusts or Conservation trusts; 3) Agroforestry and farm forestry; 4) Monitoring & evaluation systems and databases; 5) Conservation leases and/or easements; 6) NRM plans on GoK, community and private lands and that target a variety of resources (forest products, non-timber forest products, rangeland, wildlife); 7) Water harvesting & management; 8) Participatory forest management; 9) Grazing management systems; 10) Natural resource fora or networks. “Use” means formally adopted, recognized, implemented or followed. ‘Target areas’ are Mukogodo division in Laikipia district, North West Mt. Kenya Arabuko Sokoke Forest in North Coast and other areas, which include Rumuruti forest, Aberdares, Ngong Hills, Taita Hills and Kwale.

Comment: During the reporting period the number of tools in use were 29 i.e. PFM, conservation improvement, water harvesting & management, grazing management systems, nature based enterprises, problem animal management, natural resource net works, monitoring and evaluation systems and databases.

| Data Sheet #3: CONSERVATION TOOLS & TECHNOLOGIES IN USE |
| --- |
| Name of Focal Area | Sub-unit | Specify tools in use | # of tools and/or technologies in use |
| Mukogodo 2005 | Mukogodo group ranches | Predator proof Boma NRM planning | 1 tech. 1 tool |
|  | Makurian Demo plots | Rain water harvesting Soil conservation terracing Gully control Agroforestry, tree planting, Reseeding | 5 tech. |
|  | Makurian group ranch | Dam development for runoff storage from forest catchment Hay bulking, Hay storage, Hay seed management | 4 tech. |
|  | Momonyot group ranch | Rock catchment development Rain water tank development | 2 tech. |
|  | Il Ngwesi Group Ranch. | Hay bulking, Hay storage, Hay seed management, Spring protection Rain water tank development Off site pipeline for water conveyance | 6 tech. |
|  | Kuri kuri group ranch | Bore hole rehabilitated Ground water storage facility Off site pipeline for water conveyance | 3 tech. |
|  | Lekuruki group ranch | Runoff storage in drainage channel (damming) Gravity pipeline conveyance Tanks storage Hay bulking Hay storage Hay seed management | 6 tech. |
|  | Daiga area (location) | Woodlots establishment Nursery establishment Seed quality management | 3 tech. |
|  | Laikipia east | Aloe nursery established Aloe commercial production Aloe for range rehabilitation | 3 tech |
| Sub total |  |  | 22 |
| Mukogodo 2004 | Makurian | Conservation demo area | 1 tools |
|  | Ethi | Agroforestry and farm forestry, Tree nurseries | 3 tools |
|  | Dol Dol | Tree nurseries | 1tool |
|  | Il Ngwesi | Conservation trust | 1tool |
|  | 4 GRs/Forest reserve | NRM plans, Water management, PFM, Grazing management systems, Natural resource for a & networks, Nature based enterprises | 7 tools; 1 tech |
|  | Chumvi | Tree nurseries | 1 tool |
|  | Grand Total |  | 8 |
| Mt. Kenya 2005 | Naro Moru | PFM Tree nursery | 1 tool 1 tech |
|  | Nanyuki | PFM | 1tool |
|  | Gathiuru | PFM Tree nursery Grazing management system | 2 tools, 1 tech. |
|  | Ontulili Forest station | Rehabilitation of fire breaks and access roads PFM Tree nursery | 1 tool, 2 tech. |
|  | Mucheene, | PFM Tree nursery | 1 tool 1 tech. |
|  | Marania | PFM | 1 tool |
|  | Meru station | PFM Tree nursery | 1 tool 1 tech |
|  | Magacha block in Irangi forest | Beating up | 1tech. |
| Sub-total |  |  | 5 |
| Mt. Kenya 2004 | N/FR & NW Mt Kenya | M& E systems; MKJMTF | 1 tool |
|  |  | NRM plans in GoK, community & private lands | 2 tools |
|  |  | Natural resource for a & networks; Workshops, training seminars | 2 tools |
|  |  | Databases (GIS) | 1 tech. |
|  | Irangi forest, Magacha block | Enrichment planting | 1 tech. |
|  | Sub - total |  | 6 |
| Arabuko Sokoke 2005 |  |  |  |
|  | Gede | PFM Agroforestry/Farm forestry M&E NRM plans Natural resource networks | 4tools 1 tech. |
|  | Roka | Agroforestry/Farm forestry M&E NRM plans Natural resource networks | 3 tools 1 tech |
|  | Ngerenya | Agroforestry/Farm forestry M&E NRM plans Natural resource network | 3 tools, 1 tech. |
|  | Dida | Agroforestry/Farm forestry M&E NRM plans Natural resource networks PFM Pepper for PAC | 4 tools 2 tech. |
|  | Malanga | Agroforestry/Farm forestry M&E NRM plans Natural resource networks | 3 tools 1 tech. |
|  | Mongotini | Agroforestry/Farm forestry M&E NRM plans Natural resource networks PFM | 5 tools |
| Sub - total |  |  | 6 |
| Arabuko Sokoke Forest 2004 | Kakuyuni to Mida | Woodlots established along the 20 km fence. | 1tech |
|  | Sidzeni, Roka, Kakuyuni, Mkongani and Mida-Majaoni | Agroforestry and farm forestry in | 1tool |
|  |  | M&E systems and databases | 1tool |
|  |  | PFM – Operational Forest Management Plan and Guidelines developed | 1tool |
|  |  | Natural resource fora and networks; (FADA) | 1tool |
|  |  | Committee strengthened and the AS Forum operationalised | 1tool |
| Other areas 2005 |  |  |  |
|  | Ngong Hills | Draft management plan. Enrichment planting Eco-tourism. | 2tools 1 tech |
|  | Mt Kenya ecosystem | Draft Ecosystem Plan | 1 tool |
|  | Taita Taveta | Tree nursery Water management Non timber products extraction | 1tool 2 tech |
| Sub - total |  |  | 6 |
| Grand Total 2005 |  |  | 39 (16 tools 23 tech) |

IV-4. Number Of Adoption And Replication Of NRM Tools, Technologies And Initiatives In Target Areas

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse area by and for stakeholders

Intermediate Result: Site specific initiative for improved NRM implemented and replicated inside and outside protected areas

FORREMS Result:#5.1.1 Appropriate tools and technologies for NRM adopted by stakeholders and benefits from nature based enterprises increased.

Indicator: Number of adoption and replication of NRM tools, technologies and initiatives in target areas.

Indicator description : Adoption: - acceptance and application of appropriate tools and technologies that will be applied in various target sites to enhance NRM e.g. number of people practicing agro forestry outside protected areas. Replication: - is multiplication / repetition /copying of successful tools and technologies in target sites e.g. the number of tree nurseries in various sub- units. Tools and technologies: is a device or application of science that facilitates conservation, protection or sustainable utilization of natural resource. E.g. zonation, agro forestry and farm forestry, water easements/ obstruction

Unit of Measure: Number of initiatives adopted and the number of times an initiative is replicated.

Comment: During the reporting period the number of tools replicated were 8 this included 1) hay production, 2) NRM planning, 3) tree nursery, 4) farm forestry, 5) PFM, 6) Grazing Management System, 7) Farm forestry, 8) Natural Resource Network.

| Name of focal area | Original Subunit | Specify tools in use | Number of replicates |
| --- | --- | --- | --- |
| Mukogodo 2005 | Il Ngwesi | Hay production | 3 |
|  | Naibunga | NRM planning | 2 |
|  | Dol Dol | Tree nursery | 10 |
| Mt Kenya 2005 | Meru station | Tree nursery | 6 |
|  | Gathiuru | Grazing management system | 2 |
| ASF 2005 | Dida | Tree nursery | 34 |
|  | Sidzeni | Farm forestry | 5 |
|  | Dida | PFM | 3 |
|  | Dida | Natural resource networks | 2 |
| Other areas | Taita Taveta | Tree nursery | 2 |
| Grand Total |  |  | 69 |

IV-5. Number Of Integrated NRM Plans Developed And Implemented

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1--Site-specific initiatives for NRM implemented outside Protect Areas.

Result: #5.1.2 - Integrated NRM plans implemented Indicator: Number of integrated NRM plans developed and implemented

Indicator description: An integrated NRM plan identifies the range of ways a community needs to use their natural resources and establishes sustainable methods and utilizing those resources over time. Development of integrated community NRM plan means involving communities in identifying management priorities for their natural resources. Development involves, sensitization, drafting the plan, stakeholders' workshop and final documentation of plan). Implementation of the NRM plan is defined in two levels, 1- Initiated: Partnerships or agreements to undertake NRM planning established. Operational: Plan finalized and actions taken into the field. Targeted areas currently defined as Mukogodo division in Laikipia District, North West Mt. Kenya, Arabuko Sokoke Forest in North Coast and other areas, which include Rumuruti forest, Aberdares, Ngong, Taita Hills and Kwale.

Unit of Measure Cumulative number of NRM developed and implemented

Comments: Stakeholders' interest and capacity to undertake improved natural resource management is reflected in their participation. During this reporting period the plans that were completed were 2 (for Naibunga and Dida) 2 are in draft form (for Mt. Kenya at advanced phase, Mukogodo forest and Ngong hills). Activities are being undertaken to improve natural resource management in these areas.

| Data Sheet # 5 Number of Integrated NRM Plans developed and implemented Provide the title of NRM plan developed and ready for implementation. If a plan is completed, indicate action indicated that are being implemented. Give actual figures for specific period. |
| --- |
| Name of Focal Area | NRM Plan Developed | Number of actions in the plan Implemented |
| Mukogodo | NRM plan for Naibunga conservancy | 3 Ecotourism & wildlife management Security improvement for wildlife, livestock & NRs. Sand resource management |
|  | Draft Mukogodo forest integrated management plan | None |
| Mt. Kenya | Draft Mt Kenya Ecosystem integrated management plan | 3 Erection of electric Fence in Kieni West Forest protection Forest rehabilitation |
| Arabuko Sokoke | Dida forest area management plan | NBEs Forest protection |
| Other areas Ngong Hills | Draft Ngong Hills Ecosystem Integrated management plan | 1 Water catchment management |

IV-6. Reference Sheet: #6: Functionality of Information Systems for Decision-Making

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.3 Improved Management of Protected Areas

Result: 5.3.1 Information systems improved for management outside & inside Protected Areas Indicator: Functionality of information systems for decision-making

Indicator description: The ‘functionality’ of a database is a reflection. This indicator presents an indexed score from five (5) criteria representing the degree of functionality of a given information system. Criterion 1: Data are routinely collected and entered into a computerized database; 0 points = no routine data collection or entry is haphazard.; 1 point = data are often collected and entered in a routine fashion; 3 points = data are always collected &entered punctually. Criterion 2: In-depth analyses of data is conducted annually (or more often); YES = 1 point, NO = 0. Criterion 3: Annual (or more often) reports of data analyses and interpretation are produced; YES = 1 point, NO = 0. Criterion 4: Number of copies of results circulated; None = 0, 1-10 = 1 point, 11-25=2 points, 26 or more = 3 points. Criterion 5: Stakeholders can easily obtain the results & reports of data analyses; 0 = Not available, 1 = Not easily accessible; 2 = Moderately accessible; 4 = easily accessible. Thus the maximum points for determining ‘functionality’ of a database is 12. The indexed score is interpreted as follows: 0-4=Not functioning; 5-9=Functional; 10-12=Highly functional. The information's systems being assessed with this indicator are: 1) KWS-Databases 2) Those that track CBO performance in organizational capacity and financial benefits and 3) databases on land use change

Unit of Measure: The index score

Comment: Databases currently used by FORREMS partners are limited in their state of art and rated between 5-8 hence functional. However, there is room for improvement for the next reporting period.

Data sheet #6:

| Functionality of information systems for decision-making: This indicator present and indexed score representing the degree of functionality (indexed score) of a given database. |
| --- |
| Name of Database | a) Data routinely collected and entered into a computerized database | b) In-depth analyses of data is conducted annually | c) Annual reports of data analyses and interpretation are produced | d) Number of copies of results circulated | e) Stakeholders can easily obtain the result | Maximum points |
| KWS - GIS | 1 | 1 | 1 | 2 | 2 | 7 |
| KWS – CM&E | 1 | 1 | 1 | 2 | 2 | 7 |
| KEFRI - FORREMS | 1 | 1 | 1 | 3 | 2 | 8 |
| Arabuko Sokoke Forest Management Team | 1 | 1 | 0 | 1 | 2 | 5 |

IV-7. Reference Sheet: #7 Financial Benefits to Communities From Nature-Based Enterprises

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1-Site specific initiatives for NRM implemented outside PAs.

FORREMS Result: #51.5- Benefits from nature-based enterprises increased Indicator: Financial benefits to communities from nature-based enterprises.

Indicator description: ‘Financial benefits’ are revenues generated by nature-based enterprises that are payable to local community members, landowners, other qualified stakeholders or to support community services. Examples of financial benefits include income in the form of salaries or wages, ‘dividends’ paid from operational profits to members of a group, monies invested in ‘spin-off’ enterprises or funds invested in community infrastructure or services (e.g., school buildings or bursaries, road repair, clinics or posho mills).

Unit of Measure: Amount of net revenue generated by nature-based enterprises and paid out

Comment: In total revenue generated from nature based enterprise during the second year of the project implementation was Kshs.2,458,490 (US$ 32,779.87)and amount paid off was Kshs.2,420,990 (US$.32,279.87).

Data sheet # 7

| Financial Benefits to Communities from Nature Based Enterprises Amount of benefits generated and those that are paid out to the communities are the benefits. Give annual amount and be constant in currency provided (US$ or Ksh.)@ KShs 75 per 1US$ |
| --- |
| Focal Area | Name of Enterprise | Type of Benefit | Amount Generated (K.Shs.) | Amount paid out (K.Shs.) |
| Mukogodo | Ethi tree nursery | Sale of Seedlings | 80,000 | 80,000 |
| Mt. Kenya | Mucheene Bee Keepers | Sale of honey | 12,600 | 12,600 |
|  | Meru Forest Station (Apiculture, tree nursery) | Sale of honey | 43,200 | 43,200 |
|  |  | Sale of seedlings | 120,000 | 120,000 |
|  | Mt. Kenya Community Afforestation and Development Project - Naru Moru | Sale of Seedlings | 60,000 | 60,000 |
| Arabuko Sokoke | ASF Guides Association | Guiding fees | 112,500 | 75,000 |
|  | ASF Nursery Owners | Sale of seedlings | 1,778,925 | 1,778,925 |
|  | Aloe replicators | Sale of Aloe suckers | 231,290 | 231,290 |
| Ngong Hills | Simwaru Landscapers | Sale of seedlings | 10,000 | 10,000 |
| Rumuruti | Laikipia aloe nursery | Sale of aloe seedlings | 10,000 | 10,000 |

IV-8. Reference Sheet: #8 Non-Financial Benefits from Nature-Based Enterprises

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.1--Site-specific initiatives for NRM implemented outside Protect Areas.

FORREMS Result: #5.1.4 Benefits from nature-based enterprises increased Indicator: Non-financial benefits accrued from nature-based enterprises

Indicator description: There are several types of ‘non-financial’ benefits from well-managed, financially sound enterprises – 1) improvements in rural livelihoods that result when enterprise managers, boards or individuals chose to invest profits for the ‘greater good’; (i.e. philanthropy), and 2) improved ‘processes’ or capacities that are available to the ‘larger’ community in which the enterprise functions. Examples of the former include improvements in community infrastructures e.g., improved road networks, establishment or refurbishment of new schools or clinics, or improved water systems or sanitation. Examples of the latter include enhanced governance (organizational, managerial, business skills and transparency), enhanced security or increased empowerment/participation on the part of women in organizational decision-making or in NRM when enterprise managers or employees bring their expertise and insights to other community groups or activities.

Unit of Measure: Number of structures or systems that are improved or established as a result of the proceeds from nature-based enterprises.

Comment: Benefits included improvement is access roads, security and communication network, food production, water catchment, reduced farm invasions and fencing. These benefits are expected to increase community participation in conservation.

Data sheet # 8

| Non Financial Benefits from Nature-Based Enterprise,: These are non-financial benefits derived from operation of nature-based enterprises. Need track change s in amount and types. |
| --- |
| Name of focal area | Name Enterprise | Type of benefit | Number of structures or systems |
| Mukogodo | Il Ngwesi and Tassia Ecotourism | Improved access roads | 38 km ROADS graded and motorable |
|  | Doldol Tree nursery | CDF budget funds | Four schools Fenced |
|  | Ecotourism in Mukogodo | Improved security and communication | 2 repeaters, 2 motor bikes, 5 radios, 20 trained scouts |
|  | Il Ngwesi & Lekuruki Hay Production | Reduced grazing pressure on Mukogodo forest | 3000 bales for livestock feeds |
| ASF 2005 | ASF Bee keepers | Improved network | 1. in production, marketing, information flow |
|  | Muungano wa Wakulima wa Kipepeo(MUWAKI) | Improved network | 1. in production, marketing, information flow and forest protection |
| Rumuruti Forest | Rumuruti Forest/Game Scouts | Reduced farm invasions Improved food security | 8 villages adjacent Rumuruti Forest patrolled |
| Taita Hills | Magonyi Village Forest | Water catchment improvement | Enrichment planting on 18.1 ha |

## IV-9. Reference Sheet: #9 Organizational Capacity of Community User Groups

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders

SO5 Intermediate Result: Site specific initiatives for NRM implemented outside Protected Areas

Result #5.1.5: Awareness of incentives from NRM increased Indicator: Organizational capacity of community user groups improved

Indicator description: ‘Organizational Capacity’ is a reflection of how well user groups perform in seven areas--1) governance, 2) sustainable natural resource management 3) CBO management, 4) financial management, 5) conflict management, 6) CBO sustainability and 7) advocacy. The ‘Organizational Capacity Assessment’ (OCA) tool will be the instrument of assessment. The OCA tool is used to ‘score’ strengths and weaknesses of organizations across 196 items in the seven areas noted above. These items are scored on a scale of 1-6 where 1=needs immediate attention; 2=needs major attention; 3=needs attention on a wide scale; 4=needs attention on a limited scale; 5=acceptable, needs minor attention; and 6=acceptable no need for immediate attention. A modal score is obtained for each set of elements in the seven assessment areas. The seven modal scores are then averaged to give a single ‘measure’ of Organizational Capacity for each organization. Organizations are then ranked according to where their Organizational Capacity scores place them with reference to four levels of organizational development: Nascent (average medial scores < 2.3); Emerging (2.4-3.5); Expanding (3.6-4.8) or Mature (4.9-6.0).

Unit of Measure: Organizational Capacity scores of targeted CBOs

Disaggregated by: CBOs organized in the current year, CBOs organized in the previous years, Mgmt committees of Group Ranches

Comment: One CBO was assessed after FORREMS partners were trained by Pact. Kenya. More CBOs will be accessed during the next reporting period.

Data sheet # 9

| Organizational capacity of community user groups improved: Comment on organization's capacity strengthening or significant accomplishments of group in reporting period. Identify weakness or significant capacity development issues. Provide OCA score if done in reporting period. |  |
| --- | --- |
| Name of focal area Subunit | Name of the CBO and activity | OCA score | Strength or significant developmental accomplishment | Weakness or Capacity building issues |
| Mukogodo | ILMAMUSI Umbrella CBO for collaborative management of Natural Resources | 3.0 – (emerging stage) | OCA conducted 30 community members trained in PFM AGM for CBO | CBO management Financial management Lack of good advocacy strategy |

IV-10. Reference Sheet: #10 Percentage of Targeted GOK Partners Utilizing New M&E Tracking

Systems

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.3 Improved Management of Protected Areas

Result: 5.3.1. Improved availability and analysis of data for decision-making Indicator: Percentage of targeted GoK partners utilizing new M&E tracking systems

Indicator description: The implementation of natural resource management actions will require the availability of information and solid NRM data. Government partners in NRM include KWS, FD, KEFRI and NEMA and are currently improving data management systems and computerizing operations to improve access to data and improved decision-making. Utilizing means data is entered in a timely fashion into the new computer system and is available for decision-making. The users include Wardens, Foresters, District Environmental Committees, etc

Unit of Measure: Percentage

Disaggregated by: Database

Comment: All the GoK partners are developing monitoring tools as a requirement by the government in the performance contracts.

| Percentage of Target GoK Partners Utilizing New M&E Tracking Systems Provide the actual performance of GoK partners that have developed and are utilizing New M&E tracking systems |
| --- |
| Name of Partner | M&E tracking systems in place | Activities accomplished |

IV-11. Reference Sheet #11 Status of Policy and Legislation Environment to Encourage Community Incentives for Natural Resources Conservation

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resource management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.4--Site-specific initiatives for NRM implemented outside Protect Areas.

FORREMS Result: #5.4.1- Awareness of incentives for NRM increased Indicator: Status of Policy and Legislation Environment to Encourage Community Incentives for Wildlife conservation

Indicator description "Status of Policy and Legislation Environment " will be reflected by activities and weighted according to set milestones. Listing of key activities undertaken under SO5 and partners to improve the policy environment. The term "activities" is defined broadly and may include any type of action undertaken by KWS, FD, CBOs, or any other to improve (i.e. build) the policy and legislative environment for wildlife conservation and utilization (consumptive and non-consumptive). Results are annual and are not listed cumulatively. Each individual policy or Act will be rated equally in terms of potential or realized impact in the environment sector. The final weighting of specific areas in this indicator reflects the amount of effort being undertaken and the areas where USAID can most make a difference. The process will be broken down into six (6) milestone phases and weighted as follows: i) Stakeholder consultations to generate issues (20); ii) Parliament passes into act (10); iii) Technical committee to develop draft policy paper (20); iv) Presentation to the Government (10); v) Public debate on the draft (20); vi) Bill drafted and presented to parliament (20).

Unit of Measure: Nominal class data list and numeric scale.

Disaggregated by: Policy, institution

Comment: The indicator will use a point index to provide a qualitative measure of overall progress in the establishment of a policy environment supportive of improved NRM. The index will therefore track the achievement of milestones in policy development process through to implementation of legislation or policy.

Data sheet #11

| Status of Policy and Legislation Environment to Encourage Community Incentives for Natural Resources conservation. This will be reflected by key activities and will be weighted according to set milestone. |
| --- |
| Policy/Legislation/ Act | Phase Achieved weight | Activities accomplished |
| Aloe policy (under Wildlife Management and conservation Act) | 100% | Stakeholders mobilized and consultations done National guidelines developed Regulatory authorities trained Aloe sector policy accepted by KWS Board |

IV-12. Reference #12 Level of policy/legislation advanced

Performance Indicator Reference Sheet

Strategic Objective: Improved natural resources management in targeted biodiverse areas by and for stakeholders.

SO5 Intermediate Result: 5.4--Environmental policy strengthened and legislative reforms advanced.

Result: 5.4.1Policy advocacy index Indicator: Level of policy/legislation advanced

Indicator description: CBOs and interest groups need to strengthen the advocacy skills of their organizations in order to intervene effectively in the policy formulation or reform process. Organizations that promotes improved policy and legal reforms include those that promote forest, coastal, land use and wildlife conservation with GoK, civil society and grass roots community interests. Skills include simply collecting information on the subject at hand to such other tasks as obtaining or allocating human and fiscal resources to advocacy functions, coalition and network building, taking action to influence policy, and monitoring implementation once a policy has been made. Strengthening of these groups will enable them to articulate their positions, negotiate with local government and GoK agencies and to coordinate and network with one another to increase their influence in changing unsustainable NRM. The advocacy index to be utilized to measure progress is a sub-set of the organizational capacity assessment and will be scored concerning one or more advocacy issues for a CBO. The policy reform indicator will use a qualitative measure of overall progress in the establishment of a policy environment supportive of improved NRM. The index will track the achievement of milestones in policy development process through to implementation of legislation or policy. The final weighting of specific milestones areas in this indicator reflect the amount of effort being undertaken and the areas where USAID can most make a difference. The total score needs to be accomplished by a narrative explaining progress or strengths and weaknesses. Each of the index components should be rated on a scale as follows; None, not all, 1, 2, 3, 5, Extensively. The scores for each component are added to form the score of the overall CBO advocacy index, which range from 7 to 35 (given the 7 components present).

Unit of Measure: Milestone phases

Disaggregated by: Individual Policy, Act, institution

Comment: During this reporting period the Forest Policy and Bill made an achievement of about 70 % and 80% respectively.

Data sheet #12

| Level of policy / legislation advanced Results on achievements are based on the milestones and are reported annually. |
| --- |
| Policy/Legislation/ Act | Milestone achieved | Activities accomplished |
| Forest Policy | 70% | Cabinet approval Published as a Sessional paper (No. 9 of 2005) Awaiting parliamentary approval |
| Forest Bill 2005 | 80% | Reintroduced back to parliament Debated and approved by parliament Awaiting Presidential assent into Law |
| EMCA 1999 | 100% | Implementation on-going Developing training and operational manuals for Provincial Enviromental Committees (PECs) and District Enviromental Committee (DECs), Environmentally Significant Areas (ESA), Environmental Impact Assessment (EIA) and Environmental Audits (EA) , Economic instruments, Enviromental Easements and Restoration orders and Deposit bonds criteria. |

APPENDIX I: SO5 RESULT FRAMEWORK

APPENDIX IV:  BASELINE PERFORMANCE INDICATORS AND DATA

APENDIX V: PERFORMANCE DATA TABLE (PDT)

# Footnotes

Does not include Mt Kenya ecosystem covering 270,402 ha

# Text boxes

Strategic objective 5

Improved natural resources management in target biodiverse areas by and for stakeholders

Intermediate Result 5.4

Environmental policy and legislative reform advanced

Intermediate Result 5.1

Site specific initiatives for NRM implemented outside protected areas

Intermediate Result 5.2

Encroachment and subdivision reduced

(SO7, MOA, MLS)

Intermediate Result 5.3

Improved management of protected areas

IR5.1.1

Appropriate NRM tools and technologies adopted

I.R.5.3.1

Improved availability and analysis of data for decision making

IR5.1.3

Improved local decision-making based on monitoring analysis

IR5.1.2

Integrated community NRM plans established

IR5.1.4

Nature-focused business practices improved

I.R.5.4.1

Policy departments within selected GoK environmental institutions strenghthened

I.R.5.4.2

Constituencies supporting improved NRM strenghthened

IR5.1.5

Awareness of incentives for NRM increased

IRs to which USAID contributes but is not primarily responsible

USAID to take material responsibility