October 2, 1995

Deputy Under Secretary for Health

Transition Work Group Reports - Catalog of Comments and Recommendations

All VA Staff

1.  In late July and early August, 1995, six work group reports which set forth ideas and recommendations for implementing Dr. Kizer’s Vision for Change were made available for review by all interested staff throughout the field and in headquarters.  Numerous comments to these reports were received and cataloged by recommendation for each work group report.  In some instances the comments received precipitated revisions to the work group’s original recommendations.

2.  The attached summary document is one of six catalogs of recommendations.  The recommendations were extracted from the work group report.  The catalog includes each original recommendation followed by a summary of the comments received, the work group’s reaction to the comments, the rationale for that reaction, and any resulting change to the recommendation.  In some cases, the “comments” section is followed by “approve” or “disapprove.”  This is an indication of the work group’s reaction to the comments.  It does not indicate a final decision by the Under Secretary.

3.  Please keep in mind as you review these documents that they catalog recommendations of the work groups to Dr. Kizer.  Dr. Kizer is in the process of reviewing the recommendations for final decision and implementation.

4.  It is also important to remember that the restructuring of VHA will evolve over time.  While some changes began on October 1st, many things that need to happen are sequenced in time beyond that date.  This is the reason the July reports did not describe the complete closure on many issues that some reviewers may have expected.  The six work group reports are being summarized and edited to create a new document, Vision for Change - Implementation, which should be distributed in November 1995.  This will be a companion report to the original Vision for Change that was published in March 1995.

5.  Please direct any questions about these documents to Greg Neuner in Headquarters at 202-273-5823.

Thomas L. Garthwaite, M.D.

Attachments

VISN ACTIVATION WORK GROUP

EXECUTIVE SUMMARY OF COMMENTS RECEIVED

IN RESPONSE TO DRAFT REPORT

Over 140 individuals responded to the report of the VISN Activation Work Group.  In general, comments were highly positive with many specific references to the qualify and comprehensives of work and the strength of the approaches suggested.  All comments were carefully reviewed and were captured in one of two ways.  Those referring to specific recommendations were matched with the recommendation and are included in this document.   Those of a general nature were categorized in terms of key thoughts expressed and attached in another document (e\visn\nonrec.doc).  Each comment was reviewed and rationale for agreement or disagreement with the comment was developed.  This Executive Summary will highlight the tone and general themes of the responses.

A number of respondents felt the level of detail in some sections of the document was too great, inhibiting flexibility in the new organizational structure.  The need for flexibility and autonomy at the VISN level in order to achieve the mission intended was stressed.  Others believed that there was not enough detail to fully communicate where certain existing functions would be placed.  Skepticism was expressed regarding the level of autonomy which would actually be delegated and several comments that the report appeared inconsistent in this regard (e.g., VISN Directors have delegated authority for operations yet the size of their staff was limited to 7-10 persons, the staffing plan would need to be submitted for approval, etc.).

One area which obviously needs more elaboration in the reports of both the VISN Activation Work Group and the Headquarters Restructuring Group is that of the role of “special programs” in the proposed reorganization.  It certainly has always been the intent that special programs would be maintained and even strengthened under the new structure.  Several comments from service organizations indicate that this intent may not be as clear as it should be.

Many comments were received relating to the role and composition of the VISN Executive Leadership and Management Assistance Councils.  The manner in which the two groups would function appeared to be unclear in terms of their advisory vs. “operational” relationship.  Specific recommendations were made as to the inclusion of certain individuals and/or groups on the councils.

Proposed staffing within the VISN office generated a number of responses.  The limitation of 7-10 staff for the VISN Office was seen as unnecessarily restrictive and perhaps inadequate.  A number of comments specifically recommended the addition of certain types of staff (i.e., clerical, nursing, social work, etc.)  In particular there were many comments regarding the need to have a strong nursing presence within the VISN.  The recruitment of Clinical Services and Financial Managers before it was known where the VISN Office would be located and who the VISN Director would be was not perceived positively.  There was general concern that in the attempt  to expedite VISN start-up through early recruitment, the applicant pool, quality of applicants and achievement of well functioning “teams” would be sacrificed.

The overall pace of the VISN transition, dissolution of regions and restructuring of Headquarters was viewed by many as exceedingly rapid.  Concern was specifically expressed relating to the fact that so much change would be occurring simultaneously without time to deal with the “people” issues required to create such massive cultural reorientation.

The differences in approach between the recommendation of the VISN Activation Work Group and the Headquarters Restructuring Work Group relating to VISN Support Teams was noted by many.  The contrast between the 11 member team recommended by VISN Activation and the 42+ members of the teams proposed by the Headquarters Restructuring Work Group is significant.  Comments ranged from the belief that the support team proposed by the VISN Activation Work Group was “vital to the success of the implementation”  to the team would provide yet another level of bureaucracy.  There was also concern that current functions perceived to be redundant and unnecessary would be perpetuated in the VSSCs and Operations.  One comment was that the talents and skills of clinicians on the team would be underutilized in what was perceived as an “administrative” role.  Also the issue of salary inequity for individuals working on the support team was acknowledged.

The VSSC has been one of the most heavily debated issues in this process.  Originally, the SSC emerged as a concept to deal with issues outside of Headquarters, but in a forum larger than the VISN.  At that time, the VSSC seemed a reasonable piece of the organization to deal with roll-up functions for finance and construction, larger planning issues and perhaps as a “home” for any region functions which did not neatly fit into other parts of the organization.  As the planning process began and the debate ensued, the need for this function, in view of current computer capabilities, the organization and structure analysis that occurred during the planning process, etc., became less clear and it appeared there might be a time-limited need for the VSSC--to absorb region functions that would gradually be transitioned to VISNs and Headquarters during initial implementation.  Current thinking of the Work Group is that establishment of the VSSC would be redundant, that we should not establish something which we would then phase out in the next six to twelve months.  Hence the recommendation that VSSCs should be established only if a value-added need is determined through analysis of Region functions which the VISNs and CNO office will now be conducting.  This analysis is an important task and must be accomplished without bias.  Many comments support the Work Group’s conclusion that the VSSC is redundant.  This proposed change to the role of VSSCs outlined in the Vision for Change should be carefully considered, and probably adopted, but no final decision should be made until the analysis occurs.

Several comments were received from the General Counsel relating to some of the procedural matters which should be considered in various parts of the implementation (i.e., leasing, legislative changes, etc.).  These comments will be useful as implementation planning proceeds.

Suggestions were made relating to the proposed outplacement program and difficulty which may be encountered in outplacing region staff.  The plan for reassigning remaining region staff to the office of the CNO on October 1 and conducting a thorough review of current region functions drew many comments relating to the need to be “people- sensitive” during the transition. Also many of the respondents wanted more detail regarding exactly where current region functions would be placed and who would hold responsibility for them.  There were specific recommendations regarding which functions were no longer needed, which programs should remain and where they should be placed.

Comments related to affiliations were diverse, ranging from recommending immediate decentralization of education funding and house staff positions to advising that they remain centralized.  The one theme which came through in the comments was agreement that further study would be required and that there should not be a rush to implement change in this area in light of the many other structural and cultural changes which would be undertaken simultaneously.

In summary, while there were not major issues addressed which had not been contemplated and discussed by the Work Group in its deliberations, the comments were quite helpful.  They will be useful as further implementation strategies are developed and recommendations are refined.  The level and thoughtfulness of many responses was indicative that the “field” is indeed engaged in the process.

RefNo

2.1

Recommendation:

| VISN Directors with concurrence of the CNO will determine the organizational structure that best meet the needs of their respective VISN; will support the operation of a fully integrated managed care organization and support the following major functions: leadership, planning, resource management, clinical services management, human resources management, performance measurement, management of affiliations and internal and external stakeholders relations. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.1.1 | determine organizational structure | VISN Directors | 11/15/95 |
| Comments | A/D | Rationale |
| 2.1 |

We received four comments on the flexibility of VISN Directors to develop the VISNs.  Most were supportive of the idea  -- “We believe that flexibility is the key to success.  It is hoped that unneeded services and functions will be eliminated.”

However, one comment disagreed -- “This is the same as ‘no recommendation.’  Specific programmatic requirements can be identified, they are currently being performed by Regional Offices.  They should be stated in the Report and specific plans for their continuation or elimination proposed.”

One other comment was concerned with the concurrence of the CNO for VISN organizational structure -- “This appears to be contrary to the concept of decentralization of responsibility and accountability.”

A

D

D

We are attempting to maintain as many degrees of freedom as possible.  Maximum flexibility will be allowed.

The specific guidance on how to best perform existing regional functions will be forthcoming following the detailed review suggested during the transition process.

The emerging structure of the VISN (particularly during VISN activation) is such that it requires close integration and coordination between VISNs and Headquarters to insure all essential issues are considered when assigning limited numbers of FTE. The intent is not to be restrictive but to assure that discussions occur.

2.1

Three comments were concerned with the staff levels within the VISN office.  “Given the initial functions assigned to the VISNs and the likelihood of assuming other functions, a major concerns whether or not there will be sufficient staffing to accomplish the tasks assigned.”

“Some analytical resources currently at individual facilities may have to be pooled at the VISN level while maintaining adequate resources at the local facility. The use of task forces and councils is essential in streamlining the VISN and VSSC.”

A

A

The recommended 7-10 FTE is for the VISN office itself.  All FTE in all VISN facilities can be utilized to undertake the work of the VISN.

| The need to tap the resources of the VISN is basic to the new organization. |
| --- |
| 2.1 | “Although the report offers a great deal of detail regarding certain aspects of the transition from the Region structure to the VISN organization, adequate information is not available regarding the means by which the VISN Directors will implement the changes necessary to bring the VA into the realm of competition with the private sector. Historically, the VA has been restricted by many issues which impact its operations; without elimination of these restrictions it is uncertain whether the VISN organization can effect necessary changes.” | -- | The need to eliminate unnecessary restrictions is recognized. Attempts will be made to reduce them. The “means” by which a VISN Director will implement change is not prescribed in order to offer maximum flexibility. |
| 2.1 | Another comment stated, “..that while the VISN Director appears to have authority to change modify or delete functions at facilities in his/her area, it’s not clear what authority he/she has in reassigning personnel. Specifically he/she appear to be prohibited from assigning employees, surplused by increased efficiency to the VISN office if the FTE of 10 - 12 is exceeded. For example, with the resource allocation for the entire VISN resting with the CFO (and CEO) he/she cannot accomplish this alone; nor can it be done efficiently and effectively by a “committee or advisory group” (the members of which are certain to have parochial interests). He/She will need a staff working for and with him. That is not to suggest that the fiscal operation at any facility should be abolished but rather to recommend that fiscal staff working on VISN fiscal responsibilities be assigned to the VISN. This is but one example of the probable need for personnel realignment within the VISN.” | A |
|  | 2.1 | “One of the stated goals of the VISN structure is the inclusion of external health care providers as part of the network. However, the VISN reports do not address the process for developing, writing, negotiating, and signing these contracts or who within the VISN has the expertise and authority to complete contracts with external providers.” | A | The intent is to give VISNs full authority to develop needed contractual relationships. |
| 2.1 | One comment agreed that VISN management will need to take advantage of research (HSR&D, Affiliates, VHA Research Service). | A | -- |
| 2.1 | One comment suggested that we add research as a VISN Director responsibility that states, “VISN Directors should encourage research, promote its application to ensure best practices, and publicize its benefits to veteran patients.” | A | There is presently a separate study of research activities and needs. However, VISN Directors’ performance contract will include language specific to maintain and enhance the research mission. |
| 2.1 | “VISN clinical advisory councils such as Mental Health and Long Term Care could strengthen and support efforts, especially if an interdisciplinary membership model is used to share the broadest appropriate knowledge base to address issues and problems facing clinical programs in the VISN.” | A | These will be developed as the VISNs mature. VISN Directors may establish whatever advisory councils deemed necessary to assist in VISN management and operations. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended at this time to the recommendation. |

RefNo

2.2

Recommendation:

| Each VISN Director will establish an Executive Leadership Council consisting primarily of internal stakeholders and a Management Assistance Council consisting primarily of external stakeholders. These councils will represent diverse viewpoints and serve to advise the VISN Director regarding key aspects of VISN operations. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.2.1 | establish Executive Leadership Council | VISN Directors | 10/15/95 |
|  | 2.2.2 | establish Management Assistance Council | VISN Directors | 10/15/95 |
| Comments | A/D | Rationale |
| 2.2 |

There were seventeen (17) comments related to the ELC and the MAC.  Most comments support both councils.  The following comments and questions relate to establishment of these councils--

“How will the members of the councils be selected?  What will be taken into consideration?  Can advisory councils, as outlined, function efficiently in a decremental budgeting environment?”

| “VISN use of advisory/management councils to resolve local issues -- How would these groups relate to national policy and national advisory groups? (What are the limits of ‘local’ issues and ‘loca’ authority?)” | -- |
| --- | --- |

The details of Council membership and organization will be determined as the organization develops based upon individual VISN needs.  Advisory councils can be very helpful and supportive even in a “decremental budgeting” environment.

| Linkage is through VISN Directors and CNO. Limits of authority determined by USH and CNO. |
| --- |
| 2.2 | We received several suggestions for membership to the Executive Leadership Council (ELC). This included such professions as nurses (“The nurse’s broad perspective of the continuum of patient care and support of seamless delivery of systems makes him/her an ideal candidate for inclusion.”) and mental health representatives (“...to reflect the importance of mental health in the composition of VHA health services.”). Other council suggestions included: “Membership should include all the Directors within each VISN initially to assume full representation of all VISN internal stakeholders.”; “The ELC should have external stockholder presence to provide input on special programs for identification and organization of major process and procedure lines at the network level.”; and “Membership in the ELC should include a very broad representation of clinical management expertise to promote service integration and resource development.” | D |

Composition of the ELC should not be mandated but determined by VISN needs.  The intent of the ELC is to have a wide range of members representing the key internal stakeholders.  VISN Directors will be charged with determining membership, however the suggestion will be passed on to those developing VISN Director orientation.

2.2

We also received numerous suggestions for the membership of the Management Assistance Council (MAC).  They included such groups as --  “a broad representation of the community health and social services network”; “For those members of the Puerto Rican community, will distance be taken into consideration?  We feel that it is important to have members of the Puerto Rican community included in the MAC since our health care program is quite different from that in Florida.”; “Include mental health reps at this level.  Add Social Work representatives to insure community liaison and care to long-term patients.”; “The MAC should include consumer groups beyond the VSO’s such as the National Alliance for the Mentally Ill.”; “Consideration should be given to relying of the State Veterans Service Commission staff instead of the VSO officers for meaningful input.”

“What is the Management Assistance Council’s (MAC) authority and responsibility in addition to information collection?”

D

--

A variety of advisory groups will be important to VISN management.  Actual membership to be determined as VISNs mature.  VSO’s are vital to the success of VHA and will be actively involved.

The capacity of the MAC is advisory. It will deal with wide range of issues from that advisory standpoint.

2.2

Other advisory councils were suggested.  These include the following --

“...Research Council to ensure that VISN management (a) is informed of all research activities, (b) is aware of the contributions of the research program to the VISN mission, and (c) receives advice regarding needed organizational changes as experience grows with the VISN structure.  This council should be chaired by an ACOS/R&D or equivalent and members should include representatives from affected universities, Veterans Service Organizations, Offices of Public Affairs, and others as appropriate, e.g., representatives from research regional office, field programs, and R&D centers.”

“Establish a Mental Health Advisory Council for each VISN to insure coordination of services and eliminate duplication of programs.  Include Social Work representatives to insure coordination with community.”

“The Emergency Medical Preparedness Office has proposed the establishment of an Emergency Medical Preparedness Assistance Council, headed by an experienced EMPO Area Emergency Manager from a network facility within the VISN and assisted by other VAMC AEMs and/or Emergency Preparedness Coordinators, to advise and assist the VISN Director and staff in developing and conducting emergency management activities within the VISN. Close coordination will be maintained with EMPO headquarters to coordinate approvals and integration of emergency preparedness activities that cross VISN boundaries.”

D

D

D

Research input can be garnered in a variety of ways.  Need for councils should be evaluated as VISNs mature.  In order to offer flexibility, no specific councils are mandated.

(see above comment)

| Need for Advisory Councils should be evaluated as the VISN matures. It is, however, important that EMPO be an activity receiving high priority. |
| --- |
| 2.2 | “Labor organizations are included as an external stakeholder in the MAC. Labor organizations must be involved as an internal stakeholder in these re-organizations.” | -- | While union members are indeed internal stakeholders, unions themselves are external. It is vital that strong partnerships be developed and highly positive working relationships be maintained with labor partners. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change is recommended at this time. Labor partnership issue may need to be discussed by Headquarters for a policy or philosophy direction. |

RefNo

2.3

Recommendation:

| VISN Directors will be accountable for meeting performance goals established in their performance contracts. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.3.1 | establish and communicate VISN Director performance contracts (new action item) | Chief Network Officer (13) | 10/15/95 |
| Comments | A/D | Rationale |
| 2.3 |

We received four comments regarding this recommendation.  One comments supported making VISN Directors accountable for the success of the VISN while another requested clarity in Headquarters and VISN roles in establishing performance criteria and standards.

One comment related to the VISN Directors Performance Contract period (Jan 1, 1996-Sept. 30, 1996) and  questioned whether this was sufficient time for VISN Directors to put their organizations in place.

The last comment was a lengthy set of questions related to employee education -- “How will or should the VISNs interact with the Office of Employee Education? What access will or should the VISNs have to the 10 Regional Medical Development Centers and 3 National Media Development Centers? What level of funding and/or other support (NRM, equipment, FTE, etc.) should be allocated for employee education? None of the reports include any reference to the VISN Director’s responsibility toward employee education. No performance measures are identified in regard to employee education. Yet, the Education and Training Work Group Report recommends that each VISN Director develop an educational plan, conduct a base line assessment at each network facility, develop measurement tools to assess organizational progress, and measure organizational progress toward culture change.”

A

--

--

Refer to Performance Measurement Work Group.  Performance contracts will be jointly developed between the responsible parties.

Decision for CNO.

| Refer to Education and Training and Performance Measurement Work Groups. |
| --- |
| 2.3 | “It is stated that contracting for services will require significant involvement as it becomes common practice experience has shown, in many cases, that contracting various services outside the facility has resulted in higher costs over time. Cost effectiveness of contracting any service must continually be assessed.” | A | Agree in principle. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended at this time. |

RefNo

2.4

Recommendation:

| Each VISN will be assigned three FTE as of October 1, 1995 (VISN Director, Clinical Services Manager). Needs for other FTE will be developed and presented to the CNO for concurrence and will be made available from the FTE resource pool held by the CNO. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.4.1 | finalize position descriptions and functional statements | VISN Activation Work Group | 7/17/95 | 8/3/95 |
| *2.4.2 | classify positions and develop qualification statements | Human Resources (05) | 7/20/95 | 8/3/95 |
| *2.4.3 | identify strategies for recruitment process | VISN Activation Work Group | 7/20/95 | 7/28/95 |
| *2.4.4 | select preferred recruitment plan | Under Secretary for Health (10) | 7/20/95 | 7/28/95 |
| *2.4.5 | advertise through Centralize Staffing System and pertinent journals and publications | Human Resources (05) | 7/24/95 |
|  | *2.4.6 | “request local examining authority from OPM” changed to “perform job analysis panel by OPM” (revised action item) | Human Resources (05) | 8/8/95 |
|  | *2.4.7 | establish voice mail system to receive inquiries about the vacancy announcement and application procedures | Management Support (163) | 8/4/95 |
|  | 2.4.8 | rank and rate applicants and develop best qualified (BQ) list | Management Support (163) | 9/8/95 |
|  | 2.4.9 | provide BQ list to VISN Directors | 10/1/95 |
| 2.4.10 | make selections | VISN Directors | 10/15/95 |
|  | 2.4.11 | review and approve requests for additional FTE (beyond 3) for full VISN activation. (new action item) | Chief Network Officer (13) |
|  | Comments | A/D | Rationale |
| 2.4 |

We received 26 comments regarding the VISN office staffing.  Three comments recommended a fourth position provide clerical support (a secretary or office manager position) to the VISN office.

One comment recognized that the VISN Directors will have access to staff within their entire VISN, extracting staff from facilities within their VISN to perform needed functions. They recommended “ (1) FTE for only the VISN Director and allow this person to utilize facility staff at his/her discretion? This would eliminate the need for the CNO to be involved with approving the hiring of the remaining (6 - 9) VISN positions.”

A

A

Clerical support will indeed be necessary, however, the VISN Director should have the opportunity to evaluate VISN organizational needs.

| CNO will not be approving and hiring individual VISN staff, only in approving the organizational structure of each VISN. |
| --- |
| 2.4 | Two comments disagreed that remaining VISN staff requires the concurrence of the CNO. | D | As supervisor of the VISN Directors, the CNO has a need to know how each VISN will be structured. |
| 2.4 | “VISN staff will have dual responsibility for operations (day-to-day issues) and implementing change. Operational issues may burden the staff to such an extent that implementing change may become a secondary task. The change that is proposed is a major one. How are the staff of the VISN and the facilities to be educated and trained to make this transition? The tasks currently performed by the Regions are formidable. It would be advisable to recommend/suggest those tasks that could be performed by the facilities and those task to be performed by the VISNs. The tasks to be performed by the VISNs could be grouped into organizational areas that would logically lead to positions of responsibility, i.e., staff.” | A |

(1)  Organizational needs to be evaluated by VISN Director.

(2)  Transitional issues will be a major concern of CNO and VISN Directors.

| (3) Expertise throughout the VISN will be tapped to accomplish the mission. |
| --- |
| 2.4 | Six comments recommended that there be a designated nursing presence at the VISN level or that we mandate that the Clinical Services Manager is a nurse. | -- | Opportunity exists for registered nurses to apply for the position of Clinical Services Manager and for registered nurses to be a part of Executive Leadership Councils. |
| 2.4 | One comment suggested that the Clinical Services Manager should go to a physician “since the appointee should serve as advisor for all clinical programs and have oversight responsibility for contracted service providers (e.g., University physicians contracted services).” | -- | Physicians have the opportunity to apply for both VISN Director and Clinical Services Manager. Other clinical disciplines would also have the needed expertise. |
| 2.4 | One comment recommended that the VISN include representation by a Physician, Nursing, Pharmacy and Social Work. | A | Opportunities for representation do exist. It would be anticipated that a number of advisory bodies would emerge involving key clinical stakeholders. |
| 2.4 | One comment was concerned with the crucial balance to outplace Region and Headquarters staff with the need to allow the VISN Directors the ability to select a few key staff who will work as a cohesive unit. “Employees without the appropriate knowledge and skills will be detrimental to the VISNs mission.” | A | VISN Directors will select all VISN staff. |
| 2.4 | One comment questioned, “What impact does the restructuring have on Regional Nurse Professional Standards Board, i.e., areas of responsibility, mechanisms to process; who is accountable at the VISN level, etc.? Please clarify. Product lines include various specific patient care programs. How will other patient care programs be affected by the restructuring? Patient care is the focus of restructuring and will be affected either directly or indirectly by each restructuring component and each decision made. Therefore, a representative of nursing should be at the table; part of the group in the new structure.” | A | Nurse Professional Standards Boards will need to be addressed as a part of the transition. Clinical Services Manager is an important position with much responsibility and authority (see position description in Appendix 5 of report). Nurses have opportunity to apply for this position. |
| 2.4 | One comment recommended that the CFO participate in selection of and concur with appointment of VISN Financial Managers to strengthen the relationships between the CFO and VISNs. (“What is the intended relationship between CFO and VISN CFOs?”) | A | VISN Directors may seek CFO input at their discretion. However, the VISN Financial Manager is responsible to the VISN Director. It will be very important to establish and maintain effective and positive working relationships with the CFO and his staff. |
| 2.4 | Two other specific functions in the VISN were recommended: (1) “Although strategic planning is listed as a core responsibility of VISNs, planning staff is not included as part of the core VISN staff.” (2) “Recommend a CIO function at each VISN, either as a full-time position or collateral duty of VAMC or VSSC employee. Responsibilities would include coordination of IRM activities at field facilities and informatics/database activities at VSSCs.” | A | (1) The planning function can be undertaken in a number of ways including utilizing existing planners at VISN facilities or the employment of a planner within the VISN office itself. (2) A CIO position has been recommended, either in the VISN office or within the VISN, as determined by the VISN Director. |
| 2.4 |

One comment questioned the announcement of the Clinical Services Manager and Financial Manager positions prior to selection of the VISN Directors.  “This will provide a pool of applicants for VISN Directors to selection from and expedite the process.  While this approach will minimize delay in establishing key positions in each VISN, it may also preclude some people from applying for these positions since they will not know for whom they will be working.”

One comment questioned why the VISN Directors were not involved in the process of selecting Clinical Services and Financial Managers?

One comment suggested that expediting the recruitment and selection processes for VISN Clinical Services and Financial Managers contradicts allowing VISN Directors maximum flexibility in determining their specific organizational structures and staffing requirements.

A

D

The benefit of having these key persons available as soon as possible after the selection the VISN Director was felt to outweigh the disadvantages.

(see above comment)

| Basic organizational decisions were made while attempting to allow maximum flexibility for VISN Directors. VISN Directors will have maximum flexibility in determining remaining VISN staff but these two positions were determined to be critical for all VISNs. |
| --- |
| 2.4 | Three comments related to the requirements for the Clinical Services Manager. (1) “Recommend that education requirements be more specific for VISN positions. Generally, a Master’s Degree would be the minimum.” (2) “It is very important that the incumbent have knowledge and skills that will promote the development and expansion of community services and resources needed to support VHA health care objectives.” (3) “ The position description limits this position to physicians or nurses. Given the responsibility of this position other clinical staff with the requisite experience and expertise should be afforded consideration for this critical community-interactive role.” |

(1) D

(2) A

(3) A

Maybe desirable but cannot be required.

The social service requirements for Veterans will be an integral part of Clinical Services management.

| The intent was to limit the position to those professions covered by Title 38. Within the designation, only physicians, dentists and nurses were deemed to have the appropriate educational backgrounds and skills required for the position. |
| --- |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | Add additional action items as suggested above. |

RefNo

2.5

Recommendation:

| VISN Directors will select, once the organizational plan is approved by the CNO, all their staff. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.5.1 | recruit and select VISN staff | VISN Directors | 1/1/96 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended. |

RefNo

2.6

Recommendation:

| Utilize those individuals currently in “Operations” to provide primary assistance on a time-limited basis to achieve deactivation of regional offices, conduct analyses relating to the elimination or reassignment of current regional activities and provide support for outplacement of staff. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.6.1 | assign Region staff to Chief Network Officer | Chief Network Officer (13) | 10/1/95 |
| Comments | A/D | Rationale |
| 2.6 | “The VISN Activation Plan contains detailed recommendations for issuing press releases, resolving property management questions, renovating offices, and hiring senior staff. However, an orderly process for managing program duties during the transition, and providing administrative and financial support for those activities, is missing.” | D | The plan specifically addresses the orderly transition by transferring all Region staff to the CNO during the transition phase. |
| 2.6 | “Recommendation to utilize existing staff in ‘Operations’ -- Existing staff and their corresponding functions within the current ‘Operations’ structure include individuals assigned primary duties as the operations ‘budget’ person and operations ‘planning’ person. Under the new paradigm being introduced by the Vision for Change, Headquarters program offices are being challenged to redirect their thinking and actions toward a field customer orientation. The new CNO organization should support this new orientation and rely directly upon the CFO for budget support. This will foster Headquarters team building and eliminate duplication of functions within Headquarters. Positions such as planner and budget/resource manager are inappropriate and duplicative within the new CNO organization.” | -- |

(1)  The need for cooperation between the VISN and Headquarters is stressed in the new organization.

| (2) There will be a need for on-site budget and planning expertise in the VISN to deal with daily operational issues. |
| --- |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended. |

RefNo

2.7

Recommendation:

| As soon as deemed possible, appoint members of the VISN Support Team in order to have them on-board to assist with VISN activation and provide immediate interface with the Office of the Chief Network Officer. Team members will also be available to assist newly appointed VISN Directors in their orientation, establishing VISN offices and providing immediate support with other transition activities. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.7.1 | designate routing symbols, T&L numbers, etc. | Policy & Planning (005) and Mgmt. Support office (163) | 10/1/95 |
|  | *2.7.2 | orient VA facilities to transition plan | Chief Network Officer (13) | 9/8/95 |
|  | *2.7.3 | orientation with VISN Directors and key staff | Chief Network Officer (13) | 9/7/95 |
|  | *2.7.4 | establish regular conference calls between Chief Network Officer | Chief Network Officer (13) | 10/2/95 |
|  | 2.7.5 | evaluate Region and decentralized Headquarters functions and determine disposition | Chief Network Officer (13) | 3/31/95 |
| Comments | A/D | Rationale |
| 2.7 | We received 30 comments regarding this recommendation. Most of the comments addressed how our VISN Support Staff model conflicted with that model suggested by the Headquarters Restructuring Work Group. Additional comments include: “Both appear to want to address the operations/ clinical schism which proved to be enervating, at least to many clinical staff, following the last reorganization.”; “The VISN support team concept is sound but will only function well if the people are capable and understand that their mission is to support the VISN offices.”; “The success of this is dependent on the success of the implementation of a ‘flat’ rather than a hierarchical organization.”; “Relationship between VISN and SHG offices, in terms of their roles/responsibilities with clinical programs, needs to be fully described.”; “We have concern that this support would not be responsive to the needs of the VISN but would continue the current hierarchy. This could easily lead the ‘support’ services to drive the efforts of the VISN rather than provide consultation and resource.”; “If decisions/responsibility/actions are decentralized, VISNs would not need technical experts for advocacy in Headquarters, unless Headquarters plans to dictate to VISN directors.”; “Expertise should be provided in as many diverse (and critically important) areas as possible (i.e., have 11 distinct subject areas). Consider replacing redundant subject areas such as admin. and clinician with Quality Assurance, ‘Safety’ and the Information Management since questions in these areas arise from time to time and this type of in-house expertise within the Office of the CNO could be beneficial.”; “Some reference to the desirability of research expertise on the VISN support team would be helpful.”; “The VISN support team as described here is a useful mechanism to advise the CNO and provide a primary contact point for each VISN. The HQ group recommendation is a stronger mechanism for integrating across HQ product lines and disciplines and provides stronger contact in HQ for VISNs. The two ideas can he combined.”; “Eliminate VISN Support Team. This is a valueless layering and perpetuation of present operation model. Adds to bureaucracy.”; “The idea must be conveyed that the VISNs, Headquarters and the individual facilities are a team, each with responsibility and authority even if performing staff functions.”; “One lesson learned from VA’s involvement with National Health Care Reform and VA’s implementation of the proposed reform was that the intermeshing of the clinical manager’s perspective resulted in recommendations that were both patient-centered and cost effective.”; “I agree with the team approach concept, however, I support advertising the positions together with competition for membership on the teams (not reassignment of current Operations HSS staff).”; and “Since EMPO develops policy, implements programs, maintains and coordinates strategic and operational emergency (or contingency) planning at national, network, and local levels for VHA and VA, a close working and coordinating mechanism between designated EMPO Headquarters staff and VISN Support Team must exist.” | A | After meeting with the Coordinating Committee, the Headquarters Restructuring Work Group “VISN Support Team” model was accepted. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | edit the document to reflect the VISN Support team as recommended in the Headquarters Restructuring Work Group Report (Five teams, each composed of 12-14 members; each team will support one or more VISNs). | HQ Restructuring Group | 8/29/95 |

RefNo

2.8

Recommendation:

| Since the primary purpose of service centers is to support VISNs, they should be formally titled “VISN Support Service Centers (VSSC)”. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change needed. |

RefNo

2.9

Recommendation:

| Establish four VSSCs at existing region locations. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| 2.7 | Of the seven comments received on the VSSCs, all supported the elimination or reduction of the VSSCs. Specific concerns include the following: “While the report initially argues for not replicating the services now provided by the Regional offices, the regionally located support centers will result in this undesired outcome. I predict that Quality, Safety, Construction, Risk Management and other staff who currently provide oversight than service will continue doing the same jobs under new titles.”; “Eliminate VISN support centers. This is a valueless layering and perpetuation of present operation model. Adds to bureaucracy.”; “Although for a few months VSSCs could be supportive of routine business during transition, many functions should be transferred to the VISN or be field based.”; “The proposed Board of Directors for the various VISN Support Service Centers (VSSCs) seem to mirror the existing Regions.”; “I am also concerned that the VISN offices housing these VSSCs will somehow take on a greater aura of importance that VISN offices with no special emphasis programs. I recommend that all VSSC activities be consolidated in a central location in the country, geographically separate from any VISN office.”; “With a limited staff, it will be very difficult for a VSSC to adequately provide the highly specialized expert technical and consultative services in addition to the required data development, analysis and consolidation functions.”; “I see the need for at least 2 VSSCs: financial and education. All the rest can be done at the VISN level.” | -- | The issues of SSCs continues to need discussion and refinement. The Vision For Change clearly defines their existence and locations. Work group discussions identified that this may be a transitional need and once all VISNs are operational, the need for VSSCs may disappear--hence the recommendation that they be established only if there is a “value added” need. The suggestion that there be a single VSSC may have merit, however until a full analysis of the continued need for existing Regional functions is completed, no decisions regarding structure and placement of VSSCs should be finalized. |
| 2.9 | “Under paragraph titled Consultation, examples of services that might be included as VSSC functions include risk management and quality assurance. Many of the traditional quality assurance functions are already transitioning towards organization performance and it might be worth while incorporating many of the current functions into planning and performance. This is true for risk management as well although to a lesser extent. However, there is probably a continued need for some kind of JCAHO accreditation consultants and these roles might well be suited to VSSCs. I think it fairly important to not separate quality assurance functions from planning and performance. That almost invites duplication of efforts.” | A | Roles will be determined during the transition phase. |
| 2.9 | “I question the need for 4 VSSCs. I support the VISN directors with small staffs, and cross functional work groups providing information, roll-ups and so on. I am making the assertion that we attain a high level of data base integration, and advance computer programming and platforms in order to perform these functions.” | -- | (see above comment) |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change is recommended at this time. |

RefNo

2.10

Recommendation:

| Adopt VSSC core functions as consultation and data development/analysis. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| 2.10 | Of the five comments we received, two comments disagreed to maintain staff in the VSSC to provide high quality technical and consultative support functions. “We have that expertise within each facility.” One comment questioned the need for VSSCs and the final comment recommended that the VSSCs “should prepare reports, manage databases, and provide technical expertise in accessing VHA databases. Recommend that region staff who currently perform these functions be carried to the VSSCs.” | D | Roles and staffing of the VSSCs will be determined at a later date during the transition phase. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | It is suggested that all VSSC recommendations be combined. |

RefNo

2.11

Recommendation:

| Align VSSCs organizationally under VSSC Board of Directors. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.11.1 | establish four (4) VSSC Board of Directors. | Chief Network Officer (13) | 10/15/95 |
| Comments | A/D | Rationale |
| 2.11 | “The report indicates VISNs and VSSCs are to be configured to draw upon the expertise within a give geographic area to perform necessary tasks. No where is it implied or stated that VISNs will draw upon staff in VSSCs outside their geographic area (i.e., VISN 22 will rely on service within VISN 22 and/or the VSSC in San Francisco; VISN 22 should not have to call on staff in any other VISN or VSSC for assistance. Therefore, it is critical that key functions area available throughout the country and located such that each geographic area has access to those critical functions (either via their local VSSC or within their respective VISN).” | D | The exact configuration of the VSSCs has not been determined. During the transition phase it will be decided how to best configure the VSSCs. The intent would be that they provide a value-added service for multiple VISNs. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | Suggest combining all VSSC recommendations. |

RefNo

2.12

Recommendation:

| Determine exact staffing mix for the VSSCs after VSSC Boards of Directors are established, local needs are determined and region functions are assessed/revised. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.12.1 | begin recruitment of VSSC staff |
| Comments | A/D | Rationale |
| 2.12 | “What is the intent that the host VISN will provide administrative support to the VSSC?” | -- | Logistically easiest. |
| 2.12 | Of the 10 comments submitted, most were concerned with the limitation of staff at the VISN and VSSCs and the functions these offices will perform. “VISNs should have sufficient resources within their respective network and/or within their supporting VSSC to achieve VHA’s goals.” “Increasing staff within a VSSC must be a viable option. But rather than choosing an arbitrary figure of 7 to 10 staff at the VISN and 13 staff at each VSSC, place no restrictions on FTE. If FTE restrictions are necessary, place them on the networks (collection of facilities, VISN and pro-rated portion of the VSSC). Mandating FTE encumbers the VISN Directors.” “A maximum number of FTE (52) should not be prescribed as needs should dictate staffing.” “The VISN Board of Directors should have the flexibility to establish the numbers of FTEE per VSSC including the type positions and their selections.” “I agree that VISN directors should take part in the review and recommendation of VSSCs.” “Given the nature of tasks anticipated for the VSSCs, I think it unlikely all can perform the same function with only 13 staff.” “Will VISN Directors be willing to delegate the authority to provide specific guidance to those at the VSSCs, or will we often grind to a halt while our technical advisors ‘check with the VISN,’ or will the opposite happen and we wait while the VISN Director’s staff seeks technical guidance? I see this slowdown as extremely likely in the construction area, especially if the VISN Director does not employ a construction manager.” “I agree they should not be the ‘ghost of region’s past.’ Fire/Safety, IH, CM may be appropriate roles.” | -- | Clerical staff are included in the 13. The nature of the tasks for VSSCs has yet to be determined. It is conceivable that tasks originally identified for VSSCs in Vision For Change may be assigned elsewhere. The need for and best way to accomplish current and future programs will be considered during the transition phase. VSSCs staff will be consultative only, other than technical expertise. They have no decision making authority |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | Recommend combining all VSSC recommendations. |

RefNo

2.13

Recommendation:

| Create a structure for VSSCs that is flexible and enables the organization to evolve as needs and requirements change. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |
|  | Recommend combining all VSSC recommendations. |

RefNo

2.14

Recommendation:

| Do not include in VSSCs those functions/services that are primarily designed to support VHA Headquarters (e.g. Boston Development Center, Decision Support System). | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.14.1 | determine functions to be assigned to VSSCs | VSSC Board of Directors | 3/31/96 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |
|  | Recommend combining all VSSC recommendations. |

RefNo

2.15

Recommendation:

| Allow VISNs and facilities to shape the future of other consolidated programs (such as Consolidated Mail Outpatient Pharmacies, Central Dental Labs) based on their willingness to purchase services that are high quality and cost efficient. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| 2.15 | “It would be noted that it requires significant resources, time, effort and dedication to establish an efficient and cost effective consolidated program. The savings and cost efficiencies achieved by these programs should provide benefits on a long-term basis and in many cases, our system planning is completed on more of a short-term basis with the focus on immediate returns.” | A | -- |
| 2.15 | “In the establishment of VISN support services centers as a centralized group or as transitional offices, some service centers should be considered unique to clinical specialties. The out-placed National VA Chaplain Center with its Chaplain School component should be considered such a resource.” | A/D | The differences between specialized centers and VSSCs is noted. The need for other type centers will be evaluated. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended. |

RefNo

2.16

Recommendation:

| Colocate VISNs with VA Medical Centers in Boston, MA; Albany, NY; Bronx, NY; Pittsburgh (HD), PA; Bay Pines, FL; Cleveland, OH; Chicago (Hines), IL; Minneapolis, MN; Portland, OR; and Long Beach, CA VISN sites. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.16.1 | prepare press releases to announce VISN sites | Public Affairs Office (80) | 8/7/95 |
|  | *2.16.2 | forward letter to host facilities regarding support for VISN activation activities | Chief Network Officer (13) | 8/7/95 |
|  | *2.16.3 | issue authorization letter and TDA | Chief Network Officer (13) | 8/7/95 |
|  | 2.16.4 | start A/E procurement; advertise for A/E; select A/E; negotiate A/E cost; award A/E design contract | host facility | 8/31/95 |
|  | 2.16.5 | complete design and contract documents | host facility | 10/15/95 |
|  | 2.16.6 | advertise for construction bids | host facility | 10/22/95 |
|  | 2.16.7 | open construction bids | host facility | 12/8/95 |
|  | 2.16.8 | award construction contract | host facility | 12/15/95 |
|  | 2.16.9 | start construction | VISN Office Act-ivation Team | 12/31/95 |
|  | 2.16.10 | complete construction; occupy VISN office | host facility | 3/3/96 |
| Comments | A/D | Rationale |
| 2.16 | “The plans to establish office space prior to selection of VISN Directors is understandable due to the lead time necessary to obtain such space. However, in some instances new leased space will be identified in a community before the VISN Director is able to have any input into the process. While the VISN Directors will not have any choice regarding the city in which the VISN office is to be located, it would be nice if the VISN Director could have some control over the exact location of the office within the selected community. If this cannot be done, then factors such as proximity to the airport, community distances, and proximity to those with whom the VISN staff will be doing business should be carefully considered when selecting the site.” | D | The logistical requirements for establishing VISN Offices require that decisions be made as to their locations as soon as possible. The Work Group deliberated this issue and determined that VISN offices should be established utilizing pre-established criteria. |
| 2.16 | “The reason site selection information is not included in this report is unclear, as the report itself is only a draft report. Comments on recommended sites may be useful during the approval process.” | A | The site selection information was not included in the Report since this it required management approval. |
| 2.16 | “VISN offices need to be located centrally for easy access.” | A | This has been considered in the site criteria. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.17

Recommendation:

| Colocate VISNs with other existing VA functions in Durham, NC; Nashville, TN; Kansas City, OH; and Phoenix, AZ VISN sites utilizing the amended lease process. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.17.1 | prepare reimbursable work authorization to GSA for renovating space, if necessary (new action item) |
|  | 2.17.2 | notify GSA regarding leasing action and agree to additional renovation costs, if necessary (new action item |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

*2.18

Recommendation:

| Establish new leases for VISNs in Atlanta, GA; Omaha, NE; and Denver (Fitzsimons), CO utilizing expedited lease authority. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.18.1 | review bid proposal(s) and determine most advantageous to VA | host facility | 9/8/95 |
|  | *2.18.2 | submit best bid to professional appraiser; complete GSA form 1241E | host facility | 9/8/95 |
|  | *2.18.3 | submit bid for legal review to District Counsel | host facility | 9/8/95 |
|  | *2.18.4 | receive professional appraisal and legal review; execute lease | host facility | 9/14/95 |
|  | 2.18.5 | lessor work with VA to prepare build-out space | host facility | 10/16/95 |
|  | 2.18.6 | inspect space for suitability | host facility | 10/17/95 |
|  | 2.18.7 | occupy space | host facility | 10/24/95 |
| Comments | A/D | Rationale |
| 2.18 |

Three comments were concerned that the new leases will require expedited lease authority.  “The Action Plan should make it clear that local funding for all lease costs must be available at the host facility, or the leased space cannot be procured locally.  In addition, the space must be under 10,000 net usable (now ‘occupiable’) square feet, and cost no more than $300,000 annually, or VA Central Office must procure the space, unless VACO specifically delegates authority for that lease to the host facility.”

“With respect to leasing VISN property, the use of expedited leasing procedures may not be appropriate for some of the VISN leases because the build-out required may be too extensive.  Therefore, reference to standard negotiations procedures should be made in the Action Plan.”

“The Action Plan for leasing should be consistent with Directive 10-94-057. Therefore, insert the statement that a copy of the executed lease and supporting documentation will be forwarded to the Director, Real Property Management Service (084) for inventory control purposes.”

A

A

A

Expedited lease will be used within the limits of the expedited lease authority.

At the present time, build-out requirements for lease space is not anticipated to be significant.

| These comments were included in the Draft report but not distributed. |
| --- |
| 2.18 | “Add a new box for the following action: ‘conduct a site visit and negotiate unique requirements.’ The box should be inserted between ‘conduct market survey of the proposed site,’ and ‘distribute short form ... bid proposals.’ ” | A |
|  | 2.18 | “The Action Plan should make clear that the Offices of the General Counsel and Acquisition and Materiel Management should be consulted and participate in any reviews and approvals routinely necessary. This is of particular importance because of the possible need for certain waivers for the expedited procedure envisioned.” | A |
|  | 2.18 | “Contracting issues (including leasing) must be dealt with as soon as possible in order to make the stated transitions in a timely fashion. The Office of General Counsel and appropriate contracting officials should be included in any future working groups to help identify and address contracting issues at the earliest possible time.” | A | The VISN Activation Team, whose purpose is to coordinate renovation and leasing activities, includes representatives from Management & Field Support Office and Real Property, but does not include Acquisition & Material Management and General Counsel. CNO will consider including these offices. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.19

Recommendation:

| Establish VISNs in Baltimore, MD; Ann Arbor, MI; Jackson, MS; San Francisco, CA; and Dallas, TX utilizing existing Region leases | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.19.1 | modify lease for new space configuration, if necessary (new action item) |
|  | 2.19.2 | prepare supplemental lease agreement for renovation, if necessary (new action item) |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

*2.20

Recommendation:

| Establish a VISN Office Activation Team in Headquarters to coordinate renovation and delegated leasing activities for the preparation of VISN office space. This team should include representatives from the Engineering Management and Field Support Office (138) and Real Property Management Office (084) and be coordinated by the CNO office. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

*2.21

Recommendation:

| Set aside funds in Headquarters to cover renovation and lease costs (FY95/96 NRM funds and All Other, respectively). Once VISN office locations have been approved, TDAs should be sent directly from Headquarters to host (or other designated) facilities to begin planning and design for projects and negotiations for leases. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.22

Recommendation:

| Reassign certain Region furniture and office equipment to VISNs and VSSCs in Baltimore, MD; Ann Arbor, MI; Jackson, MS; and San Francisco, CA. Maintain an inventory of remaining Region furniture and equipment as it becomes available for excess and give priority consideration to redistributing it to new VISNs. Allow new VISNs to purchase furniture and equipment if excessed Region items are not suitable or available in a timely manner. Set aside funds in Headquarters to support furniture and equipment purchases. Redistribute unassigned Region furniture to other facilities within the system utilizing existing excess property programs. | A/D/O | Remarks-K2 |
| --- | --- | --- |
|  | Action Required | Action Office | Target Date | Actual Date |
| *2.22.1 | distribute funds for procurement of furnishings and equipment to Regions | Chief Network Officer (13) | 8/7/95 |
|  | *2.22.2 | determine specific requirements and identify sources for procurement; draft orders (2237) | host facility | 8/7/95 |
|  | 2.22.3 | develop plan showing location of furnishings and equipment; determine resource requirement | host facility | 8/14/95 |
|  | 2.22.4 | submit orders (2237) to host facility A&MM (90) for processing | host facility | 8/21/95 |
|  | 2.22.5 | install furnishings and office equipment to occupy space | host facility | 1/5/96 |
| Comments | A/D | Rationale |
| 2.22 | “The VISN Activation Work Group provided a schedule for VISN office site selection, design, remodel of offices, procurement of office furniture, etc. That schedule will not provide adequate facilities fast enough for VISN directors to set-up their offices and begin functioning.” | -- | We recognize the importance of activating VISNs in a timely fashion; every effort will be made to make this occur. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.23

Recommendation:

| Pursue video conference equipment capability for 22 VISNs and the Office of the CNO. Charge MIRMO with coordinating the specifications for video conference equipment and coordinating equipment purchase, installation, and training. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended at this time. |

RefNo

2.24

Recommendation:

| Develop and submit a legislative initiative to deal with salary discrepancies for senior management staff including VISN Directors and others between Title 38 and SES and within Title 38. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| 2.24 | Several comments were received, all supporting this legislation. Additional comments include: “The most significant of these would be the salary differential that would exist between physicians and others who would all be doing essentially the same jobs.”; “If legislative initiative is introduced to correct the discrepancy between Title 5 and Title 38 for VISN Directors, it should also include the discrepancy presently existing for Medical Center Directors.”; “OMB Circular A-19 requires that before VA makes available to Congress or the public any proposal for or endorsement of Federal legislation, the proposal or endorsement must be submitted to the Office of Management and Budget for coordination and clearance. This report would thus need to be cleared by OMB before it is released to Congress or the public.” | A | The recommendation was specifically developed to deal with this concern. The focal point of the committee was for VISN activation. The concern identified may need to be reviewed within a different arena. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | Change recommendation as above and add actions items indicated. |

RefNo

2.25

Recommendation:

| Region offices will be immediately charged with developing VISN specific “Transition Resource Guides”. These guides will be assigned to the Regional Directors by the AsCMD for Operations to be completed by September 30, 1995 or sooner. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.25.1 | develop “Transition Resource Guides” | Regions | 9/30/95 |
| Comments | A/D | Rationale |
| 2.25 | “Copies of Transition Resource Guides with VISN-specific data should also go to HQ offices, including SHG offices.” | A | Agree. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change recommended at this time. |

RefNo

2.26

Recommendation:

| Effective October 1, 1995, Region employees will be operationally realigned to the CNO, but will remain on the Medical Care Appropriation account; Region functions will be transitionally realigned to the Office of the CNO. A process of critically evaluating Region functions will begin immediately. (Disposition recommendations for all functions will occur no later than March 31, 1996). | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| 2.26 |

We had 19 comments on this subject.  Some of the comments included:

“Careful consideration must be given to Region staff during the transition process to demonstrate the assertion that ‘VHA’s employees are perhaps the greatest strength of the organization.’  To more effectively utilize staff, productively standards should be implemented and cross training should be explored where appropriate.

“During transition the CNO supervisory span of control (Region staff, SSC staff, etc.) may become unwieldy, alternatives may need to be considered.”

“How realistic is it to retain regional offices for 6 months as functions are being reviewed?  Won’t most good staff leave for other positions?”

“The transition process appears too hurried.”

“I am troubled that the ‘plan’ fails to identify what office(s) within the new organization will be responsible for carrying out the 440 tasks currently performed by regional offices.  I agree that it makes sense that VISN support centers be established at existing region locations.  But it makes no sense to leave unresolved the assignment of responsibility for current region responsibilities and allow for additional functions to evolve at the new centers, while planning for only a marginal number of support center staff.”

“The region construction attorneys have served as effective in-house counsel. We believe that service should continue at that level.”

A

A

A

D

A

Every attempt will be made to be as employee-sensitive as possible as evidenced by the planned outplacement program.

Alternatives will be developed as necessary during the transition.

The intent is not to maintain regional offices.  Time frames are tight but we believed that moving quickly is essential.

To assure a smooth transition from the current structure to VISNs, all current region functions will continue until they can be analyzed and either reassigned or eliminated.  Careful consideration is planned to determine the appropriate organizational placement for tasks currently assigned to region staff.

The region construction attorneys have served as effective in-house counsel. We believe that service should continue at that level.

2.26

Some comments provided suggestions and other recommendations such as the following:

“One option available is to use these staff for a specific period of time to perform their current duties, then ask them to train (or become) VISN or facility staff performing these functions.”

“I am concerned that all the requirements of the various work groups may not be doable.  I would suggest that a special work group examine the entire document from ‘an executive point of view’ to identify those functions which must absolutely be performed if the VISNs are to be successful.  It would be much better to do a few tasks and do them well than to attempt too many tasks and, as a result, do them all poorly.”

“The Region functions recommended to be transferred to VISNs are very vague.  In keeping with the concept of management flexibility, the VISN Director should determine how best to accomplish necessary functions.”

“We realize that the working group report does not get to this level of functional detail, but we thought the working group should consider either:  (1) mentioning the VISN formulary process as an example of a new function (previously managed at a medical center) and/or (2) adding action items to the report which would instill the VISN formulary into the first phase of VISN activation.”

“Region staff should be included in the evaluation of Region functions to insure familiarity with subject matter.”

D

A

A

A

A

Staff will be reassigned to the CNO upon the activation date.  These staff will participate in evaluation and realigning functions as appropriate until VISNs are operational and functions are either realigned or eliminated.

The intent of the transition process is to allow for adequate review of existing functions in relation to their elimination or reassignment to VISNs, VSSCs or Headquarters.  These comments will be provided as a part of the VISN Resource Guide.

(see comment above)

This suggestion has merit and should be considered during the transition process.

| The intent would be to involve those knowledgeable about current functions. |
| --- |
| 2.26 | “This report recommends that Region employees be operationally realigned to the Chief Network Officer but continue to be paid from the Medical Care appropriation. Application of the support function versus direct operation rule in this case would require consideration of the function of these Region employees after they are realigned to the Chief Network Officer. If their function would involve the operation of the VA system nationwide, this would be a support function which must be funded from MAMOE. If, on the other hand, the function of these employees would involve the operation of VA facilities on a State-by-State, region-by-region, or facility-by-facility basis, this would be a direct operation function which would have to be funded out of Medical Care funds. Before this report is issued, therefore, the function of these employees should be examined.” | -- | This issue needs clear interpretation. The intent is that the role of region staff would not change nor would the reporting relationship to Headquarters via the CNO (previously the AsCMD for Operations). The only change would be the absence of the region per se and a Regional Director during the brief phase-out period. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.27

Recommendation:

| Seek expedited approval of the Decision Paper on the Special Placement Program from the Under Secretary for Health. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.27.1 | expedite approval of decision paper on special placement program | Chief Network Officer (13) | 8/1/95 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

*2.28

Recommendation:

| Implement the Special Placement Program at the end of the Congressional waiting period. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.28.1 | implement special placement program | Chief Network Officer | 8/7/95 | 9/7/95 |
| *2.28.2 | issue letter informing Region employees of office closures | Under /secretary for Health (10) | 8/7/95 | 8/17/95 |
| *2.28.3 | issue letter implementing special placement program | Chief Network Officer (13) | 8/7/95 | 9/7/95 |
| *2.28.4 | issue letter to all facility Directors and VAMC activities, Regional Directors, OPCs and ROs with OPCs regarding provisions of special placement program | Chief Network Officer (13) | 8/7/95 |
|  | *2.28.5 | survey Region staff for preferences and mobility | Regions | 8/25/95 |
| Comments | A/D | Rationale |
| 2.28 | Of the five comments received, most provided positive support to the outplacement efforts for Region staff. However, they added such comments as “...will be difficult due to downsizing of the work force in the federal government as well as the private sector, and without transfer of Region FTE. It also may be difficult to outplace Region staff in an expeditious manner under current and projected budgetary constraints.”; “This [outplacement] has occurred in the past and is an effective benefit if outplacing staff is to be accomplished expeditiously, especially with buy out authority unlikely. Otherwise, it may be difficult to place staff at higher grades or specialized expertise.”; “May need to place the staff in Medical Centers or ensure buy-outs and early-outs are attractive, especially for grades GS-13 and above.” | A/D | VHA will require full cooperation from all entities to assist in absorbing region staff through the special placement program. The provision of FTE with outplaced staff is not possible due to budgetary constraints. FTE will be reassigned to support the new structure. Outplacement has been utilized on a very limited basis within VHA in the recent past. |
| 2.28 | “The Special Placement Program to assist staff with buy out and early out is commendable. Along these same lines for those of us who are mobile, an electronic data base that would reveal housing for sale or rent by vacating VA employee, would expedite the move-relocation of the transferee.” | A | This suggestion will be provided to the special placement program managers for consideration. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.29

Recommendation:

| Use Special Placement Program developed for region staff as a model for planned parallel efforts for Headquarters employee outplacement. (revised recommendation) | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.30

Recommendation:

| Request specific “buy-out” (Voluntary Separation Incentive Payment) authority as an incentive for increasing attrition. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.30.1 | prepare buy-out authority request | Management Support (163) | 8/1/95 |
|  | *2.30.2 | request buy-out authority (VSIP) | Management Support (163) | 8/7/95 |
| Comments | A/D | Rationale |
| 2.30 | “Report references need for early out and buy out authorities. Early out authority has been approved through 9/30/96; buyouts would require legislation, and we do not anticipate favorable consideration from OMB at this point.” |
|  | Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.31

Recommendation:

| Request an extension of the “Early Out” (VERA) authority. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.31.1 | request extension of Voluntary Early Retirement Authority | Management Support (163) | 8/7/95 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

*2.32

Recommendation:

| Provide all Region employees waiting to relocate a “bona fide” job offer of assignment, at grade and pay retention as a minimum, to a position in VHA although not necessarily in accord with employee preferences, prior to use of RIF procedures or other separation authorities. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.33

Recommendation:

| Remain cognizant of Labor Management considerations and the need to communicate with the VHA National Partnership Council as employee outplacement issues continue to evolve. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.33.1 | notify Partnership Council of program parameters | Under Secretary for Health (10) |
|  | Comments | A/D | Rationale |
| 2.33 | “Labor partners are indicated as stakeholders, but has anyone contacted them regarding the impact of eliminating some of the current regional functions (e.g., EEO, Fire and Safety, Industrial Hygiene)? For example, the AFGE National Agreement indicated Regional Safety staff will conduct the annual OSH inspections. Should these positions be dramatically reduced or eliminate altogether, how will VHA honor its part of this agreement?” | -- | The National Partnership Council has representatives on the VA Management Assistance Council and the Coordinating Committee for this project. In addition the purpose of this recommendation is to ensure appropriate consideration be given to labor/management issues including existing agreements. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
| 2.33 | No change is recommended at this time. |
| Ongoing |

RefNo

2.34

Recommendation:

| Immediately activate ADP Bulletin Board System to be accessed by all Region and Regional Division Offices composed of the following: an employment survey instrument to state location and occupation preferences; a resume library which may be reviewed by prospective employers; and, a list of applicable VHA vacancies. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.34.1 | utilize IRM/ADP bulletin board system | Regions | 8/7/95 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.35

Recommendation:

| Widely disseminate the Employee Handbook developed by the Office of Human Resource Management. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.35.1 | distribute employee handbook | Chief Network Officer (13) | 8/7/95 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.36

Recommendation:

| Activate Outplacement Centers and coordinate outplacement activities at all Region sites. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| *2.36.1 | activate outplacement centers located at Regions | Chief Network Officer | 8/7/95 |
| Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.37

Recommendation:

| Develop an instrument, within existing automated systems (i.e., FMS), for the Outplacement Center managers to estimate and track costs for outplacement of staff, relocation expenses, employee pay and benefits consideration, counseling, training, etc. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.37.1 | track and monitor costs of outplacement | Chief Financial Officer (17) |
|  | Comments | A/D | Rationale |
| Proposed Revision | Action Office | Target Date | Actual Date |

RefNo

2.38

Recommendation:

| Immediately appoint a multi-disciplinary Affiliation Task Force charged with reviewing issues identified in response to the draft discussion paper and developing plans for implementation of desired strategies. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
| 2.38.1 | appoint multi-disciplinary task force | Under Secretary for Health (10) | 12/1/95 |
| Comments | A/D | Rationale |
| 2.38 | Of the 28 comments we received on this recommendation, four comments supported Headquarters to manage the affiliations and educational opportunities; six comments recommended this task to the VISNs; and two comments felt the VA Medical Centers in a better position to manage the affiliations. There were many concerned with this subject. Specific comments are noted below. | -- |
|  | 2.38 |

AFFILIATIONS MANAGED AT HEADQUARTERS:  “VA is responsible under law for operating a national education program.  The proposed change would fragment that program into 22 different operations, and would have VA effectively abandon key national responsibilities.”

“The Thibault Committee Report and the Vision for Change both identify research and academic affiliations as intertwined missions with a national policy, planning and execution focus.”

“It is our suggestion that any decentralization of this function receive a great deal of study and be researched thoroughly. Perhaps the function would be best suited in the new VISN system under the direction of the Chief Network Officer.”

D

A

A

While this is true, a reorganization strategy might be developed that meets national goals and promotes local flexibility and needs.  The recommendation is to further review and address this issue.

A special task force has been proposed to complete this work.

Study will be provided by the Task Force.

2.38

AFFILIATIONS MANAGED AT VISNs:  “Affiliation management I believe needs to be at the VISN Director level.  I simply do not see material value added to level and distribution of resident and house staff slots, at the national level.”

“Oversight of the affiliation process at the VISN level would reduce duplication of paperwork for individual facilities who would be affiliating with the same schools.  It would also assist schools in placing students at the most appropriate training sites to meet the students’ training goals and interests. ... If training positions and funding are decentralized, an effort must be made to maintain the integrity of the Social Work graduate training program.”

“Managing affiliations at the VISN level will allow a broad perspective of the needs and abilities of each VISN facility.  It will also take the pressure off the local facility when tough decisions need to be made.”

“If indeed, our budget scenario is as predicted for the next seven years, support of education and research must be at the VISN level.  Otherwise, “carve outs” will be established and the core pool of money will be artificially eroded, much as it has been in the past.”

“VISN offices should play a major role in fostering cooperation with medical school affiliates; such cooperative efforts would include education and research deemed essential to the VHA mission.”

“Suggest a formal point-of-contact within VISNs or VSSC to coordinate interaction with research entities and facilitate access to data sources.”

--

--

--

--

--

--

This issue will be addressed by the proposed task force.

The same argument could be made for all health care disciplines.  The intent of decentralization of funding would be to allow the VISN the opportunity to determine it’s specific training needs and earmark funding accordingly.  The issue will be referred to the proposed task force.

--

Further study by Task Force.

Further study by Task Force.

Further study by Task Force.

2.38

AFFILIATIONS MANAGED AT VAMCs:  “Moving decision making regarding resident education and research to the VISN level carries sole risk.  There is the potential to undermine individual medical center relationships with their medical affiliates.”

“I am concerned with the concept of the VISN Director being required to interpose that position between Deans and Department Chairmen of the professional schools and local VAMC management. Relationships of this kind are built on ongoing day-to-day contacts between local VAMC management and Service Chiefs with the appropriate officials of the professional schools.”

--

A

Not necessarily so if structured correctly.

The Work Group felt it important to further study the relationship between affiliations and their “local” counterparts in view of the need to coordinate activities on a VISN level. The proposed task force would address this very issue in their deliberations.

2.38

Several comments were concerned about changing the management of affiliations and added comments such as:

“There is a discussion about Re-engineering VHA Education and Research Affiliation Agreement and placing them in the VISNs.  It seems to me that if this done it ought to be approached slowly and with caution.  ...  The ramifications and risks of undertaking such a huge re-engineering effort especially early in the life of VISNs seem considerable.”

“The plan puts full authority for decisions about how these training funds will be utilized on the VISN levels.  This could give powerful influential professions on the VISN level the opportunity to direct funds in their preferred directions.  The VA also need to plan on local facility and national level to meet future needs for health care experts.”

“In spite of the fear of lack of oversight, to put a distance between the affiliate and VA executive will not solve any of the problems.  It will put good functioning, mutually beneficial affiliations at risk.”

“There is concern that self-interest in larger VHA facilities within VISNs will result in bias in distribution of resources including FTEs.  There is also concern that the power and influence of local universities could be underestimated.  Local VHAs and Universities are not always “equal partners”. The ability to recruit excellence faculties at VHAs has usually been a function of strength of affiliation agreements.”

“Need to define educational role of Headquarters and local facilities to avoid activities that may be counterproductive in the outcome of education and research and avoid curtailing freedom.”

“Professional and managerial training programs (for other than physicians and nurses) are not addressed in this report which could place associated health trainee leadership training programs at a significant disadvantage.”

“I would question the need to appoint another group to study these issues at this time.”

A

A

--

A

A

D

To be considered by the Task Force.

The Work Group felt it important to further study the relationship between all types of affiliations and their “local” counterparts in view of the need to coordinate activities on a VISN level.  The proposed task force would address these very issues in their deliberations.

Further study by Task Force will address these concerns.

This is in the Task Force charge.

Professional and managed training program were not our charge.

| Other groups have not addressed the affiliations in the context of VISN reorganization. It requires special study that is not “hurried” and this is what is recommended. |
| --- |
| 2.38 | “There should be an ability to disseminate stipends to the field for many programs, including Social Work.” | -- | The proposed action would be to decentralize as much funding as possible from Academic Affairs to VISNs. The issue will be referred to the proposed task force |
| 2.38 | “The Federal Advisory Committee Act requires Federal agencies to follow certain procedures in establishing and using advisory committees. The report suggests establishing an Interdisciplinary Academic Advisory Committee consisting of VA employees, affiliated institution representatives, veterans service organizations, and others. The Committee would provide guidance, counsel, and input for education and research activities. The Committee would be subject to the Federal Advisory Committee Act. We recommend that the report note the applicability of this law to this Committee.” | -- | Noted. |
| 2.38 | “One suggestion that may be helpful for using this report most effectively would be to emphasize the need for inter-rather than multi-disciplinary since the two concepts carry important distinctions in terms of functioning.” | A | Substitute “inter” for “multi”. |
| 2.38 | “It is suggested that the research strategy component be separated out and discussed explicitly.” | D | The Affiliation Task Force should have broad latitude to study this issue and make recommendations. The affiliations are the underpinnings of our vision and mission. |
| 2.38 |

“Recommend all sources of funding for education and training (i.e., RMECS, CEC, CHEPS, GRECCs,etc.) be shifted to a common budget.”

“Tuition support funding should be expanded and made available to a wider range of candidates while flexibility is needed to move tuition reimbursement funding into tuition support. Do not restrict the funding to only clinical employees and expand the categories beyond managed and primary care issues.”

D

--

Not in the perview of the Affiliations Group.

| Not in the perview of the Affiliations Group. |
| --- |
| 2.38 | “I believe the VISN Activation report should focus on the patient care issues which will consume the VISN Directors and all of VHA in the next few years and not divert energy tilting at ‘straw men.’ ” |
| While patient care is indeed our reason for existence, change does not occur without “straw men” proposals to tease out key issues. |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | Change “multi” to “interdisciplinary”. |

RefNo

2.39

Recommendation:

| Charge VISNs upon their activation with enhancing education and research activities by: (a). Identifying mechanisms to become familiar with and track the wide range of academic activities within their facilities; (b). Designing methods to promote collaboration and partnership between affiliates, the VISN and individual clinical care facilities within the VISN; (c). Implementing education realignments and constructing new affiliation agreements that are outgrowths of clinical resource realignments within the VISN. This should occur in consultation with Headquarters; (d). Developing strategies which encourage research activities, promoting growth and development and fostering cooperation and sharing; and (e). Developing approaches for Academic Health Centers and VISNs to jointly develop and integrate health delivery systems to maximize care for veterans and society. | A/D/O |
| --- | --- |

Remarks-K2

|  | Action Required | Action Office | Target Date | Actual Date |
| --- | --- | --- | --- | --- |
|  | Comments | A/D | Rationale |
| 2.39 |

All seven comments we received expressed concern regarding research.  Below are some of their comments:

“The concept of continuing a strong basic science component in our research program, with expanded activities in health services research directed at the care of veterans seems solid.  It is vital that centrally managed peer review be retained.”

“We want to strengthen our research mission through a variety of approaches--including more solicitations/requests for proposals.  Also we need to ensure appropriate feedback/communication links toward getting best practices research into health care practice.  And we need to publicize good research results as a PR initiative.”

“Although affiliations are certainly germane to the VA research project, we believe that the relationship of the research program to affiliations is significantly different from the relationship of the education program to affiliations.”

“Lumping of research and education ‘VA’s Academic Mission’ is confusing and misleading, in that research has a broader purpose, including production of knowledge to help veteran patients and the veterans health care system.”

“The impact on mission changes will profoundly impact existing affiliations.”

A

A

--

A

A

Consistent with recommended actions.

The recommended action does not preclude this.

Research issues do not have to be limited to this document.  It is not a position paper on research--but to ignore it in discussing affiliations would be wrong.

| This could be better dealt with in the paper but does not change recommendations which are simply for VISNs to encourage research. |
| --- |
| 2.39 | “Financial Management -- Suggest adding, after last sentence, ‘VISN Directors will pass through funding (and FTE) for research programs/projects approved in HQ to medical centers where funded investigators are located.’ VISNs are included in the funding channel to ensure that these organizational units are fully informed of all funding flowing into their areas of jurisdiction. VISN Directors will responsible for ensuring a high quality research program.” | A | -- |
|  | Proposed Revision | Action Office | Target Date | Actual Date |
|  | No change is recommended at this time. |