Annex 2

NOAA-Roshydromet MoU

Status Report of Program of Activities for 2006-07

| No. | Project Proposal | Contacts | Key Accomplishments | Next Steps |
| --- | --- | --- | --- | --- |
| Project 1: Numerical Weather Prediction and Observational Data Assimilation |
| 1.1 | Adaptive upper-air observations in support of the THORPEX campain | U.S.: Zoltan Toth Russia: Mikhail Tsyrulnikov | Discussions are currently taking place between Dr. Toth and Dr. Kats, Central Aerological Observatory (CAO), to identify THORPEX needs, funding for additional radiosondes launches. Within THORPEX-IPY, collaboration between Roshydromet and Norwegian Meteorological Service was organized by CAO. | Preparation/Submission of proposal for WMO Voluntary Cooperation Program (VCP) funding; from the Russian side, participation of Roshydromet in the T-PARC experiment within THORPEX and Asia-THORPEX is possible, provided external funding will be available; Preparation of the detailed plan for additional upper-air observations, site selection, observation request, transmission, fine-resolution profiles/formats, and delivery, etc.; further discuss at Second Formal Meeting in Silver Spring |
| 1.2 | Data Assimilation |  |  |  |
| 1.2.1 | Explore and promote adaptation of NOAA’s operational data assimilation methodology for use with Roshydromet weather analysis and numerical weather prediction | U.S. Fuzhong Weng or Steve Lord (to be determined) Russia: Mikhail Tsyrulnikov | A visit to the U.S. (NCEP) by Dr. Elena Astakhova and Dr. Mikhail Tsyrulnikov took place during the period May 14-22, 2007. The following major topics were covered during the visit: (1) ensemble prediction on different time and space scales; (2) data assimilation; and (3) satellite data assimilation. A satellite microwave radiation assimilation scheme was developed in the Hydrometcenter of Russian within the framework of the 3D-Var development taking into account some experience of U.S. colleagues. | Several lines of future collaboration were identified: (1) Ensemble prediction: (a) possible adoption of the ET methodology at the Hydrometcenter of Russia. A visit of 1 to 2 specialists for 7-10 days, if it is financially possible, to NCEP to discuss the results is desireable, and (b) joint research on designing a practical stochastic model-error model to properly represent forecast-model uncertainties (2) Data assimilation: (a) share approaches in flow-dependent and multivariate background-error covariance modeling, and (b) specification of observation-error statistics in satellite data assimilation (3) An investigation into spatial and inter-channel microwave satellite correlations. Further activities to be discussed at April meeting. |
| 1.2.2 | Improvement of analysis quality through development of more adequate probabilistic background-error models | U.S.: Robert (Jim) Purser Russia: Mikhail Tsyrulnikov | (1) There has been an exchange of scientific papers/reports treating the subject of data assimilation (2) A new NOAA/NCEP office note was issued describing the experiments, comparing three methods proposed to extract information from the forecast background field in the operational 3D variational assimilation schemes that can be used to set the parameters of the spatially adaptive and anisotropic covariances that NWS plans to make as the future operational assimilation technique for the global and regional atmospheric forecast models. This note was issued and is freely available on the NCEP web page. (3) Visit of Dr. Elena Astakhova and Dr. Mikhail Tsyrulnikov to NCEP in 2007. (4) New spatial covariance scheme was developed and realized in Hydrometcenter of Russian. Its ability to represent flow-depend covariances, including anisotropy, was demonstrated. The results were reported, in particular, at the seminar at NCEP. The new scheme is used in the Russian 3D-Var system under development. | Both parties consider this activity to be complete. |
| 1.2.3 | Investigate the efficiency of the Ensemble Kalman Filter (EnKF)-based data assimilation and development of new techniques to improve the EnKF performance | U.S. Zoltan Toth Russia: Mikhail Tsyrulnikov | See Item 1.2.1 above | See Item 1.2.1 above |
| 1.3 | Improved Weather Prediction and Modeling Techniques |  |  |
| 1.3.1 | Numerical formulation of global numerical weather prediction (NWP) models using the double trigonometric Fourier series and/or grid-point approach | U.S. Mark Iredell Russia: V. Tsvetkov | Journal and recent-developmental papers were shared on (a) polynomial grids potentially useful in spherical computations (Russia sent to U.S.) and (b) Fibonacci grids on a sphere (U.S. to Russia). The Russian papers were reviewed by U.S. scientists, and it was determined that the techniques presented, while interesting, were not practicable in applying to NOAA’s needs. There has been no Russian interest concerning the U.S. papers. This activity did help NOAA better understand numerical weather prediction modeling being done at Roshydromet. | Both Parties consider this activity to be complete. |
| 1.3.2 | Limited area high-resolution modeling; forecasting with WRF nested grid system for ensembles and air-quality applications | U.S. Jeff McQueen Russia: Igor Trosnikov | (1) NCEP provided Dr. Trosnikov with access to documentation on the WRF NMM system and its capabilities; (2) NCEP provided information to Dr. Trosnikov about a WRF User’s Meeting, held in Boulder, during the summer, and recommended that Dr. Trosnikov consider participating in this meeting; Roshydromet was unable to attend because of financial problems. (3) It was suggested to perform further studies on project 1.3.2 jointly with the studies on project 1.3.3. | Send a specialist from the Hydrometcenter of Russia to the WRF Users’ Workshop and for training in USA (for 2-3 weeks at the expense of WDB if no financial problems arise |
| 1.3.3 | Development of methods for processing results of numerical modeling and forecast for expansion of output information and improvement of forms of its representation | U.S. Jeff McQueen Russia: Inna Rozinkina | (1) NCEP provided information to Dr. Rozinkina about a WRF User’s Meeting, held in Boulder, during the summer, and recommended that Dr. Rozinkina consider participating in this meeting; Roshydromet was unable to attend because of financial problems. (2) NCEP also provided Dr. Rozinkina with access to documentation on the WRF-postprocessor and the list of meteorological products that it can generate. Currently, the Roshydromet laboratory for medium-range forecasting is learning the system and will identify additional products (e.g., aviation, severe weather) that both NOAA and Roshydromet will find useful for expanding the postprocessor system. The Russian laboratory is preparing a response with questions and areas of further development with respect to postprocessing and meteorological product generation. (3) The American side suggested that the Russian specialists should study the unified postprocessing for mesoscale and global models based on the WRF postprocessor and take part in its development. The unified postprocessing problems were discussed during the visit of the Russian specialists, Dr. Elena Astakhova and Dr. Mikhail Tsyrulnikov to NCEP (projects 1.2 and 1.3.4); the American side suggested to organization training of Russian specialists engaged in project 1.3.3 at NCEP. Now the Russian side has started examining the materials and implementing individual parts of the postprocessor software. | Hydrometcenter of Russia should send a representative to one of the next WRF User’s Meeting in Boulder, CO. Roshydromet will identify questions and areas of further development with respect to postprocessing and meteorological product generation. The postprocessor documentation and software should be examined. The Russian side should send an expert to NCEP for training on the problem of organization of the unified postprocessing (for 2-3 weeks at the expense of WDB if no financial problems arise). |
| 1.4 | (1) Develop methods that are ready for operational implementation at Roshydromet for ensemble weather prediction and (2) improve ensemble forecasting methods used at NWS through coordinated research | U.S. Zoltan Toth Russia: Elena Astakhova | See Item 1.2.1 | The quality of the Hydrometcenter EPS real-time runs should be analyzed for long periods and ways to improve it should be identified. |
| 1.5 | (1) Development of long-range forecasting (LRF) methods for improvement of assessments of predictability for various regions of the globe and an exchange of ensemble long-range hindcasts in accordance with the SMIP-2/HFP protocol for possible development of joint forecasting products | U.S. Hualu Pan Russia: D. Kiktev | NCEP has completed a 25-year retrospective forecast for seasonal and interannual time frames and has an operational Climate Forecast System running. Roshydromet is working on development of seasonal forecasting technology and has completed a new 25-year series of historical forecasts on the basis of SMIP-2/HFP protocol. | Exchange of historical forecasts. Assessment of predictability for joint forecast products. To be further discussed at April meeting. To be further discussed at April meeting. |
| 1.6 | Improving telecommunication capacity for the exchange of operational and research information | U.S. Fred Branski Russia: Leonid Bezruk |  | Will further discuss GLORIAD at the Second Formal Meeting in April 2008. |
| Project 2: Operational Hydrology |  |  |  |
| 2.1 | To conduct joint research in the area of studying flash-flood processes and formation with the purpose of developing methods and technologies to provide dangerous flood forecasting in the Kuban River basin | U.S.: Curtis Barrett Russia: Sergey Borshch | Dr. Borshch visited the U.S. during the period October 27 – November 3. He visited the NWS Office of Hydrologic Development and then flew to Minneapolis where he visited with the North Central River Forecast Center and co-located Weather Forecast Office. He also visited with the National Hydrologic Operational Remote Sensing Center. Experts of Hydrometcenter of Russia have executed the complete analysis of processes of flash floods formation which take place on the southwest inflows of the Kuban River Basin. The preliminary equations for the forecasting of rain floods characteristics in this part of the Kuban River Basin are derived. As a results of the executed research, it has been established that the time-spatial resolution of the precipitation data (both observed and forecasted precipitation) should be in limits from 1-3 hours. For detailed and reliable heavy-rain forecasting in the Kuban River Basin, the algorithm of maximum and average intensity of showers forecast in this basin in view of the hydrographic characteristics, the lay of the land, the directions of main mountain ridges and other features of the territory has been developed. | Develop a plan for a workshop to be organized in Russia to discuss the development and implementation of the NWS River Forecast System as a pilot in the Kuban River Basin. |
| 2.2 | Apply Russian forecasting techniques for forecasting ice break up and the probably occurrence of ice jams during breakup to the Yukon River in Alaska and the Red River of the North in Minnesota and North Dakota | U.S.: Robin Radlein Russia: Z. Kopaliana | Data for this activity on the Yukon River were turned over to Dr. Borshch in Minneapolis. He reviewed the data and asked for several format changes. These will be updated and mailed to Dr. Borsch in January 2008. Experts of Hydrometcenter of Russia have analyzed the data received from the American colleagues. As they have received an incomplete data series on the terms of ice break-up (there are a lot of gaps in the lines of ice break-up data), they have executed the extension of all lines of data to a single observational data series. The period from 1987 to 1998 was chosen for the use in further investigations. As a result of the analysis of the data on terms of ice break-up, significant time trends are revealed. In view of this, it was necessary to exclude these trends from the time series of the ice break-up. At the end of March, the discriminated analysis was carried out. It made it possible to find out the informative areas in the field of predictors (fields of geopotential H100 and H500 for January, February, and March). Also, they have executed the component analysis. The experts from the Russian and American sides communicated by email on t he issue of presentation of the meteorological information necessary for the development of ice jams forecast methods. | To be further discussed by electronic mail. Organization of the workshop for acquaintance of the American experts with the Russian experience in the field of development of ice forecast methods in Hydrometcenter of Russia. |
| 2.3 | Development of methods and technologies for long-term background forecasts, with a lead time greater than one month, of spring flood maximum water level and its occurrence date | U.S.: Robin Radlein Russia: Sergey Borshch | (1) NOAA requested a detailed description of what data Roshydromet needs and what the selection criteria should be in order to use the Russian techniques; this was provided (2) NOAA has selected the candidate locations on the Yukon River and Red River of the North for evaluating the timing of breakup and the maximum snow melt runoff. The necessary data is incomplete and has not yet been received by Hydrometcenter of Russia. Dr. Borsch is in correspondence with NOAA on matters of data composition needed for forecasting method development. The Russian side intends to apply methods used in the country for background forecast of the dates of the occurrence and the magnitudes (range) of the maximum flood level and mainly discriminated component and regression analyses. For this purpose, the Russian experts need timing series of the maximum levels occurrence and the maximum levels themselves for the period from 1958 to 2007 at the hydrological level gauges on the Yukon River and Red River. | To be further discussed by electronic mail. In addition, Dr. Borshch has been invited to participate in the 2008 Northern Forum Flood Working Group meeting in Krasnoyarsk (date still unknown) and has accepted, pending the availability of financial resources. |
| Project 3: Space hydrometeorology |  |  |  |
| 3.1 | (a) Access to global ATOVS data from NOAA satellites; (b) negotiation in the area of “Monitoring the Environment, Natural Disaster, Climate, and Anthropogenic Activities” | U.S.: Felix Kogan, Peter Romanov Russia: A. Uspensky | (a) NOAA provided a point of contact at NESDIS who is responsible for the production of ATOVS data. The data are available; however, the requested format might be a problem. (b) NOAA has identified two organization (Hydromet Center and the Institute for Agricultural Meteorology, Obninsk) willing to discuss joint collaboration; a statement of work was prepared and sent to the Russian institutions; Dr. Kogan visited Moscow in mid-September 2006 to further discuss the proposed collabotation with Dr. Kleshenko and Dr. Strashnaiya and Dr. Maximenkova | Both sides consider it inappropriate to continue the cooperation under the activity (a) The second activity (b) will be reformulated more specifically and developed as a separate item under Project 3. |
| Project 4: Cooperation within the framework of the International Polar Year 2007/08 – Arctic, including the implementation of hydrometeorological observatory in Tiksi |
| 4.1 | Implementation of observatory in Tiksi | U.S.: Taneil Uttal, Robert Stone, Sergey Matrosov, Simon Stephenson Russia: Alexander Makshtas, Yury Tsaturov | (1) The weather station in Tiksi was rebuilt; construction was completed in October of 2006 (2) NOAA hosted a joint planning meeting in Boulder from February 27 – March 1, 2007; six Roshydromet scientists participated, including representatives from both Tiksi and Yakutsk. NOAA and Roshydromet coordinated on the design and planning of a climate observatory in Tiski (funding provided by NSF). Construction is scheduled for completion in May 2008. (3) A site survey took place in Russia in August 2007; five representatives from NOAA and one from VECO Polar Resources attended; meetings took place in Moscow, Yakutsk, and Tiksi. Negotiations commenced on operations and facilities support for the Tiksi Observatory. (4) A summary of the Clean Air Facility site survey was prepared and shared with Roshydromet (Uttal). (5) Roshydromet has recovered and digitized historical data from the Tiski weather station. (6) CRN site selection and surveys for Tiksi and Yakutsk completed (Diamond). (7) A joint science steering committee was established with 4 U.S. and 4 Russian representatives. (8) Roshydromet has xinokwrws paperwork to move the surface ozone sampler brought by the NOAA delegation on August 16 form Russian customs; sampler has been shipped to Tiksi for operation. | (1) NOAA Tiksi science plan and draft Roshydromet science plan will be merged. (2) A black carbon sampler will be shipped from NOAA to Roshydromet (Uttal) (3) NOAA will initiate a personnel services contract with Roshydromet for support salaries for meteorologist technician/engineers in Tiksi (Nesterov, Kilmyaninov, and Dikhtyarenko) (4) Roshydromet will provide a contact point for negotiating the facilities contract based on projected observatory operating expenses (Nesterov, Kilmyaninov, and Dikhtyarenko) (5) Roshydromet will provide a contact point for negotiating the personnel services contract (6) Roshydromet will award a communications contract for the Tiksi facility that will result in satellite transfer of data to St. Petersburg (Kilmyaninov and Dikhtyarenko). Details of the communications system will be reviewed by VECO Polar (McKibben) (7) To consider further the feasibility and advisability of implementation of Climate Reference Network (CRN) sites at Tiksi and Yakutsk (8) Roshydromet will pick a Russian contact for a second CRN that is being proposed for Yakutsk (Kuzmich) (9) The Weather Station building report will be submitted to NSF (McKibben) (10) An outreach plan will be developed for the Tiksi community (Kilmyaninov and Uttal) (11) Plans will be developed for an opening ceremony for the Tiksi facility in summer of 2008 (Dmitrieva and Tatusko) (12) To consider the feasibility and advisability of inclusion of the Tiksi Observatory into the GCOS GUAN network. |
| Project 5: Management of climatological data exchange and empirical and statistical study of climate |
| 5.1 | Continuation of on-going data exchange and research activities between NOAA and Roshydromet | U.S. Karsten Shein Russia: Marsel Shaimardanov | Regular updates of numerous electronic data sets that are maintained by the U.S. and/or Russia. Transfer of climatological data, either electronically (i.e., FTP) or via hard media (e.g., CD, DVD) | Continued updates of all jointly held and maintained environmental data sets, especially global climate data sets. Identification and evaluation of new areas of research using these existing data sets and the development of new datasets for addressing specific climate change questions. To be further discussed at April meeting. |
| 5.2 | Management of upper-air data exchange, and empirical and statistical analyses of current and historical change of the free-atmosphere climate | U.S. Imke Durre/Russ Vose Russia: Alexander Sterin | Continued compilation and update of IGRA and CLIMAT upper-air data sets. Upgrade of file parsing protocols to improve FTP transfer of up-to-date data sets. Updated statistical analysis of upper-air data sent from Roshydromet (Sterin) to CDIAC Trends Online publication. | IGRA has been transitioned to operational status and updates are available for download by Roshydromet on a regular basis. To provide further improvement of the IGRA data set organization in order to facilitate annual and monthly downloads for users. Additional development and research of atmosphere climate regarding upper-air data continues to be conducted. To perform the analysis of completeness and quality of upper-air data sets of both sides in order to create a future joint global upper-air dataset for download on a regular basis since 2004. To be further discussed at April meeting. |
| 5.3 | Ground-based data exchange and empirical and statistical analyses of current and historical change of the surface-layer climate | U.S.: Karsten Shein Russia: Vladimir Razuvaev | Several baseline data sets (e.g. GHCN) continue to be maintained, quality controlled, updated and transferred between the U.S. and Russia. Several of these data sets include information on snow depth and snow-water equivalence. Statistical analyses of current and historical change of terrestrial climate are ongoing within the scope of the IPY. | Work to include near-surface (land and ocean) data collected during IPY in operational boundary-layer atmospheric and oceanic datasets and to develop new datasets. Development of key areas for research foci utilizing these data. To be further discussed at April meeting. |
| 5.4 | Management of oceanographic data exchange | U.S. Margarita Conkright-Gregg, Sydney Levitus Russia: Nicolai Mikhailov | At the present time, the U.S. and Russian participating personnel of this activity wish to delay the inclusion of a Statement of Work under the MoU until such time as they may better address oceanographic data exchange protocols and they develop geo areas, parameters, and other characteristics of oceanographic data exchange and also other directions of joint in relation to the stated goals of the MoU. Until that time, work associated with this project will continue under the auspices of the Intergovenmental Oceanographic Commission/World Data Center (IOC/WDC) International Oceanographic Data and Information Exchange (IODE) operations. | This activity will be dropped as a formal activity of the MoU. To be further discussed at the April meeting. |
| 5.5 | To consider the possible duplication of agreed satellite data/products in WDC-B in order to provide redundant archiving and better customer access | U.S.: Howard Diamond Russia: Alexander Sterin, Marsel Shaimardanov | Preliminary discussions on this subject took place in 2005 and 2006. US PI changed to Howard Diamond. | PI Leads to identify candidate satellite data for a test project. WDC-A to coordinate development of project with NCDC/RSAD. It is proposed to postpone the cooperation under this activity until improvements are made to the high-speed capabilities to WDC-B. |
| Project 6: Socio-economic costs and benefits from hydrometeorological services |
| 6.1 | Incorporating economic cost-benefit analysis into NOAA-Roshydromet planning and operations | U.S.: Rodney Weiher, Zoltan Toth Russia: M. Shaimardanov, Alexander Korshunov | Workshop was hosted by Roshydromet in Obninsk from September 10-14, 2007. Rodney Weiher and Jeff Lazo (UCAR) attended. Draft protocol of intentions was prepared detailing major activities of cooperation. | Five major activities identified and to be further discussed at April 2008 meeting: (1) Creation of web site and other interactive means to disseminate the results of economic research on meteorology and to promote future cooperation in research activities of interest to NOAA and Roshydromet. (2) Exchange results of socioeconomic studies on the economic benefits of current and future improved weather forecasts among households and other sectors. (3) Exchange analytical materials of NOAA and Roshydromet conferences and annual meetings by major consumers (sectors of the economy) (4) Workshop/meeting of exchanged data users with NOAA and NCAR’s Research Applications Laboratory (RAL) to discuss the exchange efficiency and the usage of the results of the exchanged data use in climate research. (5) Creation of potential database within Roshydromet containing information on severe weather conditions and hydrometeorological hazards that cause social and economic losses, including the exchange of such data with NOAA |