USDA Service Center ▪  1601 E. Front St., Suite C  ▪  Port Angeles, WA 98362  ▪  360-452-8994

June 6, 2007

Mr. E. Lucien Cox, Jr.
Crosscutting Solutions Program Manager
Applied Sciences Program, DK000
Science Mission Directorate
NASA Headquarters
300 E Street SW

Washington, DC 20546

Dear Lucien:

Re:  Cooperative Agreement NNA06CN06A

6-Month Mid Year Progress Report

Enclosed is our subject Progress Report including all project activities, milestones and performance measures met.  Also enclosed are a separate SNOTEL Report and an Activity Report from Peninsula College.

These documents are being submitted via email as required in the Cooperative Agreement requirements.  Should you desire a signed copy sent via regular mail, please so indicate to Patti Morris, our Grant Administrator at pmorris@wavecable.com.

On behalf of our entire team, we sincerely appreciate the opportunity to work with such outstanding individuals at NASA.  We believe great ideas and solutions will be generated throughout this Cooperative Agreement with NASA.  As presentations have been made to various organizations, the excitement grows within those organizations that also see viable solutions generated from discussion and ideas.

We look forward to a successful three years working with your NASA team.

Sincerely,

Mike Doherty

Mike Doherty, PI

Enclosures

Cc:  Ms. Jennifer Dungan

Technical Officer – MS242-4

|  NASA Ames Research Center
       Moffett Field, CA 94035-1000

Patti Morris, Grant Administrator

NASA Solutions Network Project (NOPSN)

PROGRESS REPORT FOR JUNE 2007

What follows is a discussion of progress on funded tasks for Year 1 of the North Olympic Peninsula Solutions Network.  Although the project award was announced on September 31, 2006, significant work did not occur until January 2007 when subcontracts were placed with the key team members; Pacific Northwest National Laboratory, Idaho National Laboratory, Peninsula College, and Clallam County.  As such, our timelines, schedules, activities, and deliverables presented in Figure 1 and Table 1 reflect a time period of January 2007 to December 2007.

TASK 1:  SOLUTIONS NETWORK COORDINATION

Solutions Network coordination will occur throughout the project.  During Year 1, coordination activities have been principally focused on the establishing a working collaboration with the Dungeness River Management Team, our principle User group, to support Researchers in the development of the Hybrid hydrological model.  The result of this effort was the development of a draft and final Technical Specifications document describing how the Hybrid hydrological model will meet DRMT user needs.  The final Technical Specifications document provided an overview of the current DST employed by NRCS-National Water and Climate Center, and the improvements that will be provided by the Hybrid hydrological model using NASA MODIS sensor data.  The report also summarizes whether the stated DRMT needs can be met by NOPSN under the existing project, require additional investigations of NASA technology, or are best met through other environmental programs.  The draft Technical Specifications document was submitted for DRMT review in February 2007 the final document was provided in March 2007, and is included as Attachment 1.

The NOPSN has also coordinated a variety of internal meetings and workshops to ensure each member of the team understands their roles and responsibilities, and a series of meetings with Federal, State, and local resource management groups, local environmental groups, and members of the public to describe the approach and goals of the NOPSN.  NOPSN team members have also presented this Project at workshops sponsored by the Elwha Research Consortium (ERC) and the Elwha Nearshore Consortium.  Attendance at these presentations has increased our visibility with Consortium members, as well as members of various Federal agencies and the public, and allowed us to interact with a variety of scientists, local regulatory decision-makers, tribal representatives, and other entities and individuals that are conducting environmental investigations prior to the removal of the two Elwha River dams.  We have presented an overview of the project to the local Audubon chapter and the Clallam County Commissioners and their staff.  We are also working collaboratively with Streamkeepers, a nonprofit environmental group on the North Olympic Peninsula.  The result of these presentations has been an increased awareness of the NASA program on the North Olympic Peninsula and a growing sense of collaboration and partnerships with stakeholders that is essential to idea generation.

Members of the NOPSN Team also participated in the first NASA Solutions Network workshop held in Adelphi, Maryland on April 12 & 13, 2007.  Attending for the NOP RC&D Council were Council President and Principal Investigator Mike Doherty; Jeff Ward and Mark Wigmosta, both with the Pacific Northwest National Laboratory; Jerry Sehlke, Idaho National Laboratory; Andy Gordon, National Association of RC&D Councils; and Tony Ingersoll, USDA Natural Resources Conservation Service. This workshop provided us with a clearer picture of NASA’s expectations, allowed us to better understand the approach and scope of NASA researchers, and enabled us to establish a collaborative relationship with WaterNet, the other funded NASA Solutions Network.  The NASA meeting also offered us the opportunity to meet with and discuss our project with Team Member Andy Gordon from NARC&DC, which is headquartered in Washington, DC.

TASK 2:  HYBRID MODEL DEVELOPMENT IN THE DUNGENESS WATERSHED

Under Task 2, the NOPSN team will adapt and enhance an existing hydrological model to utilize NASA MODIS data in a new and innovative way, and also investigate the integration of other NASA technologies.  The resulting Hybrid model will improve stream flow forecasts on the Dungeness River and demonstrate how NASA tools and technologies can be used to improve an existing decision support system.  A Solutions Network Formulation Report will be developed and submitted to the SN Hub website on this Task. Task 2 is divided into six subtasks, which are discussed below:

Task 2.1:  Hybrid Model Application Framework

The NOPSN project team has completed the initial application framework for the Hybrid hydrological model, including development of digital elevation maps for both the Dungeness and Elwha watersheds, and the creation of the computation linkages needed to incorporate NASA MODIS data into the existing hydrological model.

Task 2.2: Feasibility of MODFLOW Linkage

The project team has completed initial consultations with the DRMT to determine whether it is feasible to link the Hybrid model to the existing groundwater model (MODFLOW) used in the Dungeness watershed.  The initial consultations suggest that it may be possible to link the Hybrid model results to MODFLOW by providing recharge estimates at the southern model boundary. Additional evaluations of the model-to-model linkages will be conducted when the Hybrid model is fully functional later this year.

Task 2.3:  Preparation of MODIS Snow Cover Data

The project team is currently processing the MODIS multi-spectral data and snow occurrence maps for the Dungeness and Elwha Basins using the methodology developed under for the Pacific NorthWest Regional Collaboratory (PNWRC) project.  A preliminary MODIS data set is now ready for use and will be integrated into the Hybrid model later this summer.  After initial model runs and calibration, weekly MODIS data will be processed and used to update they Hybrid model to provide daily and weekly stream flow forecasts for the Dungeness.

Associated with snow cover data is the planning and installation of the new SNOw TELemitry (SNOTEL) automated snow predicition station as part of this Project (see attachment 2). Our Project partners, the USDA Natural Resources Conservation Service (NRCS) and Olympic National Park (ONP), have held numerous meetings to plan and site this critical sensor. Presently there are no high-elevation snow measurements in the Olympic Mountains, leaving a huge data gap for validating weather data and the snow’s water equivalent of the MODIS snow occurrence. Since the new station is planned for placement within the Olympic National Park’s Wilderness Area, an Environmental Assessment (EA) is required. This process has already begun with a public announcement in the local media and a request for comments. ONP has received all comments and compiled them for incorporation into the final EA report, which is presently being written. ONP will also be providing an archeology review of the site. A site for this new SNOTEL station was recently selected by NRCS, via helicopter reconnaissance, working in collaboration with ONP staff. The goal is to complete the EA by August 2007 and begin installation of the new SNOTEL station by 9/1/07. It takes about two weeks to install the SNOTEL sensors, via helicopter, so this leaves a short installation window prior to winter snows in the high elevations.

Task 2.4: Hybrid Model Evaluation

The Hybrid Model will be evaluated using recent daily stream flow data from USGS gage 12048000 located on the Dungeness River near Sequim, WA.  This gage has a drainage area of 156 mi2 and has been in continuous operation from June 1937 with no significant regulation or diversion upstream from it.   Model evaluation began in April 2007 and will continue during the Summer and Fall of 2007.   We will also continue the evaluation process in Year 2 to determine how well the Hybrid model results compare to NRCS predictions, and also to the USGS gage on the Dungeness.

Task 2.5:  Hybrid-MODFLOW Model Evaluation

Investigations into the feasibility for linking the Hybrid hydrological model to MODFLOW have occurred as part of Task 2.1.  These investigations will continue in Task 2.5 as the Hybrid model is brought online and calibrated.  The ultimate goal is to use the Hybrid model to improve the predictive power of another decision support tool used in the Dungeness watershed:  the MODFLOW groundwater model which is currently used by resource agencies on the North Olympic Peninsula to evaluate existing groundwater resources and investigate the impacts of increased water needs in response to population growth or changes in water utilization.   Thus, the initial discussion with local resource agencies conducted in February and March 2007, will continue as the Hybrid model becomes functional.

Task 2.6:  Ensemble Stream Flow Forecasts

Under Task 2.6, computational methods will be developed to generate ensemble stream flow forecasts using the Hybrid Model.  Uncertainty in forecasts will be addressed explicitly during generation of ensembles of stream flow forecasts using process models that are driven by predictions of possible future meteorological conditions.  Available meteorological data from past observed water years will be used by the Hybrid Model from the known historical state of the hydrological system and assuming that any water years’ meteorological sequence from this known state is one of several equally possible realizations of future meteorology within the watershed.  The predicted stream flow corresponding to each such meteorological realization then constitutes one member of the stream flow ensemble.  The application will be evaluated using a retrospective analysis with historical stream flow and meteorological data.  Work on this task is expected to occur in December 2007, and continue into Year 2.

### Task 3:  Elwha Evaluation

As described in Task 1, the NOPSN team has began discussions with researchers, resource agency personnel, and other individuals to understand the current and pending research activities in the Elwha River water prior to the removal of two dams.  These collaborations will continue into Year 2, and result in the development of a series of Formulation Reports that describe how NASA tools and technologies can be used to improve existing decision support systems or tools, and augment scientific research.  Initial evaluations have included attendance at technical workshops, and discussions with researchers, resource managers, and tribal representatives.  The initial discussion suggests that stream flow forecasting, sediment transport, oil spill spread and toxicity, septic field leakage, and nearshore impact assessment are areas where NASA technology can be considered.  It is likely that additional applications of existing or emerging NASA products will emerge and will be captured as Formulation Reports.

TASK 8:  PROJECT MANAGEMENT

Project management activities have included subcontract development and implementation with the project team members, development of a project technical work plan, budget and milestone tracking, coordination of biweekly team conference calls and internal workshops.

OTHER ACTIVITIES

At the request of NASA, the NOPSN team has begun to evaluate the feasibility of using other NASA tools and technologies to support work in the Dungeness watershed (Task 6), and begun preliminary transition and dissemination activities associated with the development of the Peninsula College Operations Center, and interactions with other potential local, regional, and national User groups (Task 7).  These tasks were unfunded in Year 1, and were partially supported under Tasks 1 and 8.  Funding for these tasks will be included in our Year 2 budget.  We have also participated in a the first Solutions Network workshop held in Maryland at the request of NASA as part of our yearly program review, and established a collaborative relationship with WaterNet, the other funded Solutions Network.

1.  Subcontract placement delayed work approximately three months, as reflected in the above timeline

Figure 1.  Timeline for Year 1 Tasks1

Table 1.  Year 1 Activities and Deliverables

| Task | Description | Activity or Deliverable | Status |
| --- | --- | --- | --- |
| 1 | Coordination of Network | Final Technical Specifications Document for Dungeness Hybrid Model. | Completed March 2007. |
| 1 | NASA Solutions Network Workshop | Initial program review and opportunity to discuss NOPSN program with NASA and funded researchers. | Completed April 2007. |
| 1 | Coordination of Network | Discussions with the DRMT, Elwha researchers, local groups and stakeholders, and the National Association of RC&Ds. | Ongoing. |
| 2.1 | Hybrid Model Application Framework | DEM development and initial model configuration. | Completed March 2007. |
| 2.2 | Evaluate Hybrid-MODFLOW Linkage | Discussions with DRMT concerning linkage of Hybrid model to MODFLOW. | On Schedule Initial discussions completed March 2007. Follow-on discussions scheduled later in Year 1. |
| 2.3 | MODIS Snowcover Data | Process MODIS Snowcover data and integrate with Hybrid Model. | On Schedule Initial processing completed in March 2007. Additional processing will continue throughout project. |
| 2.4 | Hybrid Model Evaluation | Calibration and validation of model results with Dungeness gage. | On Schedule Initial calibrations occurring from April to December 2007, with final calibrations in early 2008. |
| 2.5 | Hybrid-MODFLOW Linkage | If possible, linkage of Hybrid model with MODFLOW groundwater model | On Schedule Initial discussions in February-March 2007; additional discussions and potential linkage by December, 2007 |
| 2.6 | Ensemble Forecasts | Streamflow forecasting using Hybrid model and MODIS data | On Schedule Initial model runs in December 2007; additional runs in Year 2. |
| 3 | Elwha Evaluation | Discussions with Elwha research groups to determine needs. | On Schedule Initial discussions in February, March, and May 2007. Additional discussions later in Year 1, and Formulation Report development in Year 2. |
| 6 | Evaluate other NASA applications | Determine whether other NASA tools and technologies can be used in the NOP study area | Not Currently Funded; activities expected to occur in November-December 2007. |
| 7 | Transition and Dissemination | Transition of Hybrid model to Peninsula College Operations Center; disseminate study results to other potential User groups | Not Currently Funded; activities expected to occur in November-December 2007 |
| 8 | Management and Reporting | Project management, budget tracking, meetings and reporting. | Ongoing. |

# Text boxes

NOP RC&D

Council Members

Mike Doherty

President

David Sullivan

Vice President

Marny Hannan

Secretary

Bill Hannan

Treasurer

Blanchard Matte

Member

Nedra Reed

Member

Rachael Hagaman

Member

Marlin Holden

Member

Laurie Medlicott

Member

Larry Crockett

Member

Will Purser

Member

Mark Madsen

Member

Linda Rotmark

Member

Lawrence Graves

Member

Frank Needham

Member

Nash Huber

Member

John Boulton

Member

Katherine Baril

Advisor

Curtis Buess

Advisor