A.   	Introduction

The world coffee market has changed considerably in the past five years due to structural changes in demand, and increased coffee production in Brazil and Vietnam.  Coffee prices dropped to their lowest levels in 30 years during 2000/2001 as a result of worldwide oversupply.  The crisis is most apparent in Central America and the Dominican Republic, where prices at the farm level have fallen below the cost of production for most coffee producers, causing serious economic hardship.

USAID has responded to this situation by designing a program to help the Central American countries and the Dominican Republic compete in the upscale segments of the coffee market.  The comparative advantage of Central America and the Dominican Republic is in producing high quality coffee.  The region’s competitive advantage lies in the agro-ecological conditions (altitude, micro-climates and soil) that give it the potential to improve quality and/or shift production toward quality coffees.  Other advantages include the presence of bourbon variety coffee, the “washed coffee” industrial process, a tradition of producing coffee, processing capacity, and an abundance of labor.  Therefore, the overall strategy for USAID’s work in this sector is to promote rural prosperity by increasing the competitiveness of small and medium producers of quality coffee, and by diversifying the rural economy.  Enhanced quality and productivity, improved business linkages, market-oriented policies, and sound environmental management are essential elements of the program.

The Quality Coffee Program (QCP) will focus on the small- to medium-scale producers and processors – who are likely to be at a disadvantage regarding access to technology, information, and credit – as the primary beneficiaries.  The QCP will also take advantage of the natural endowments that Central America and DR small coffee farmers have in producing quality and premium coffees (altitude, microclimates, cultivars, and low pesticide use) while focusing on promoting quality coffees that sell at higher premiums.

The purpose of this project is to help the Dominican Republic maintain competitive advantage in the production and marketing of high and special quality coffees by supporting the implementation of Specialty Coffee Internet Map Servers.

The activity builds upon prior work by EDC in Dominica, Peru and the Dominican Republic.  It is proposed for immediate implementation, an intense period of activity for 2 years, and a final period for assistance as local ownership is operationalized.  The activity will utilize the most recent and powerful GIS and map server technology with the potential to enhance international market competitiveness for quality or specialty commodity products.  The EDC has pioneered and prototyped this integration of “transforming technologies” which include Geographic Positioning Systems (GPS), Remote Sensing (RS), Internet Map Servers (IMS), and the Internet for transparent transactions and marketing opportunities.

B.	Goals and Objectives

The activity will develop the necessary tools and integrated databases in a collaborative manner with national experts responsible for national systems.  EDC will provide assistance to help define the field, monitoring, and tracking requirements for effective specialty coffee systems.  The information derived from the field, either at the farm level or through associations, will be fully integrated in an Internet Map Server accessible database.  Capabilities for presenting the data, developing query systems, and displaying client-driven information will be developed.  The IMS server will reside on a national web site. Clients will be able to access a web-based system which will provide audited coffee or parcel information in a fully transparent manner.  The entire activity will be implemented in full collaboration with national participants, with whom EDC will develop the funding and operational framework to sustain the effort over time.  EDC activities will have the following overall goals:

- Secure data from project counterparts for sustainable tree crop growers that will allow the development of GPS-GIS Parcel based information systems to document the parcel practices, natural resource management approaches, parcel history, and environmental, biodiversity, and ecological protection.

- Incorporate the above in a tansparent Internet map serving system to provide credibility, authenticity, and trace back capabilities as well as detailed querying capabilities for various clients and as a management tool.

- Develop capacity and transfer a sustainable operational system to a local organization.

###### C.	Project Activities

EDC completed Phase I of this activity in the Dominican Republic in 2001.  A firm foundation was established in 2001, with financial support provided by USAID/DR to EDC and national counterparts, taking the first steps to establish a Specialty Coffee Internet Map Server, national land use/cover databases and maps, and a Clearinghouse system for spatial data dissemination.  Phase II will continue this work with an emphasis on the implementation of a fully operational Specialty Coffee Internet Map Server.  Full implementation implies national ownership and maintenance of the system, and the incorporation of the components of the SCIMS into both management plans and marketing systems.  Because of a hiatus during 2002 the EDC will initially reassess national capacities and needs, review these with USAID/DR, and then proceed to provide project guidance, training, capacity building and technical assistance as full implementation is achieved.  EDC will continue to work closely with national and regional counterparts to reach project objectives and overall goals.

# Role of National Counterpart Agencies: The successful completion of this activity requires strong support for the necessary activities proposed, commitment on the part of participating organizations to initiate their counterpart roles and responsibilities, and the development of capabilities to continue these activities in a sustainable manner.  National project coordination will be undertaken by the principal institutions responsible for establishing coffee sector policies in each country. These institutions will be responsible for establishing data collection parameters, collecting farm data and georeferenced information (with the use of GPS units), providing the certification criteria and query criteria to incorporate into the IMS, inventorying and collecting the spatial data needed for IMS operation, and selecting a staff member to be hired part-time by the project to act as national coordinator.

These mechanisms need to be extended and complemented to incorporate existing - and potential - specialty coffee small farmers, new spatial data sets, ecological and environmental data, improved data catalogs and spatial data inventories, improved land use/cover maps, and an assorted gamut of data and information produced in response to the needs of the coffee sector in the Dominican Republic.  Anticipated organizational collaboration and responsibilities are as follows:

- CODOCAFE will continue to provide the extension experts to delimit the participants in the coffee sector, secure the data for the SCIMS database, and cooperate with all entities.

- IDIAF, in close cooperation with all partners, will provide national technical support and GIS capability.  They will compile and assemble the data in quality controlled and IMS compatible databases, and will either receive and maintain the completed SCIMS or support its operation from some other server.

- ADOCAFES and other quality coffee organizations will incorporate the contents and approaches provided by the SCIMS into effective marketing and PR strategies.

- DIGEORTE will assist with the land cover/use mapping for specialty coffee areas and continue the product initiated in Phase I.

Specific Work Plan Tasks:  The activities described below are a continuation of the tasks initiated in Phase I.  These activities will be reviewed, revised as necessary, and agreed upon with counterparts and USAID/Dominican Republic prior to startup.

(i)         Update and complete an effective web site.

- Complement WEB Site development initiated during first project phase. WEB site will include features such as: a section on how to obtain coffee samples, exporter’s information, meteorological data, links to specialty coffee WEB sites, a catalog describing the spatial data sets in the IMS, section on coffee cooperatives and coffee mills, statistical data on coffee production and export, information on national and international coffee agencies (i.e. Codocafe, Adocafes, SCAA, Idiaf, Ministry of Agriculture).

- Adapt the WEB site design to feature a strong marketing approach, based on reviews undertaken by marketing specialists and local partners’ recommendations.

- Plan for the transfer of “Web site ownership” from EDC to national institutions. A partner agency that is willing and capable of hosting and maintaining the WEB site is selected, and all WEB site content and data are transferred to selected agency. EDC staff provides the needed training for agency to operationalize and sustain the site.

- Assist the development of registration and Web-based PR activities.

- Consider and decide what on-line access and sales efforts to promote.

- Evaluate on-line transactions related to coffee export and clearance.

- Facilitate the development of marketing systems with national partners.

- Promote the development of new coffee WEB sites by exporters, business councils, government agencies and farmers and cooperatives, and assist their integration with the quality coffee WEB site and IMS described herein.

(ii)	Incorporate additional environmental and ecological datasets relevant to conservation, biodiversity and Specialty Coffee certification needs into the IMS.

- Initiate processing and querying procedures for Specialty Coffee IMS.

- Identify geographic or thematic areas where data are not available or of dubious or poor quality, and plan for acquisition of better quality data sets or for the development of new ones.

- Analyze and combine spatial data sets to produce environmental messages targeted at the coffee market.

- Evaluate and implement appropriate on-line procedures to monitor biodiversity and conservation protection.

- Complete land cover/use mapping to monitor forest conservation and meet coffee program needs.

- Secure and make available SRTM DEM data at 90m posting and work toward release of 30m data.

- Establish environmental management and biodiversity conservation priorities and configure IMS to support these. For example, the project can undertake spatial analyses to evaluate impact of coffee farms on adjacent forest cover or coffee corridors within farm areas, assist shade grown coffee certification by providing some of the basic data needed, or determine which farms are growing coffee in steep slopes that cause soil erosion, among many other possibilities.

(iii)	Incorporate the certification criteria into the IMS query facility.

- Study ways of incorporating certification parameters evaluated in 2001 and new elements into the query facility and the farm data collection forms. Advice and input are expected from the Quality Coffee Project funded by the French Development Agency now defining marketing and certification schemes. For example, data to assist fair trade certification can be gathered at each coffee farm and incorporated into the databases of the IMS, or data for shade grown coffee can be obtained from remote sensing images that allow analysis of coffee production upon forest cover and biodiversity.

- Anticipate and include cooperation with approaches provided by the QCP partners.

(iv)	Provide advanced training in appropriate GPS techniques to extension specialists already trained in basic GPS use and basic training to new extension specialists covering new pilot areas.

- Evaluate the need for counterparts to purchase additional GPS units of ArcPad units with parcel and land cover maps.

- Determine need for laptop computers and associated software.

- Provide training and field experience in direct support of cooperating coffee organization(s).

- Incorporate training materials into a brief bi-lingual training manual.

(v)	Provide training in Internet Map Server (IMS) technology to appropriate national personnel.

- Train key national counterparts on the use of IMS software and general maintenance of the Coffee IMS module.

- Cooperate with ESRI to coordinate and provide the training for the implementation of a national GIS Global Map/GSDI project.

- Secure funding for integrated ArcGIS training in Ministry of Agriculture as a part of Component 3.

(vi)	Update, finalize, and implement the Internet Map Server.

- Incorporate new query capabilities, based on the new spatial data sets incorporated and modifications to the farm data collection forms.

- Upgrade IMS interface established for pilot system implemented during 2001, based on consultations with partner institutions and feedback from users.

- Evaluate local institutional capabilities to host and maintain the IMS system.

- Install latest version of ArcIMS.

- Transfer fully functional IMS to national counterpart.

- Provide continuing backstopping for IMS operation following transfer.

- The new IMS will incorporate: 10 new spatial datasets, metadata describing all spatial data, five or more new query criteria, climatic data, data on farms and cooperatives from all the main quality coffee producing areas of the country, upgraded interface, new tools.

(vii)	Assist new counterpart agencies to evaluate additional uses of the IMS.

- Meet with Ministry of Agriculture officials to study possible ways of exploiting the IMS capabilities for crop monitoring and subsidy planning and control.

- Meet with Agribusiness Council (JAD) representatives to evaluate their interest in the IMS concept and possible cooperation with on-going JAD activities and support for coffee.

- Assist counterparts to prepare a proposal for smallholder implementation to be funded by JAD.

- Coordinate with Rural Cadastral System representatives to evaluate linkages between the two projects.

# d.	Reports and Deliverables for Dominican Republic

These proposed deliverables are identified at a collected level, and are directly tied to the activities described above.

- IMS training provided to five or more national counterparts.

- Advanced training workshop for GPS and field applications with manuals completed for more than 15 national counterparts.  Completion of a manual specific for SCIMS GPS applications in Spanish to support local trainers for future resources.

- Completed data sets (parcel and land cover) for selected coffee sectors included in the IMS. More than 10 new data layers are incorporated.

- Workshop conducted with coffee organization(s) to define criteria for certification.  The cooperating organizations will summarize a report of certification criteria. Two workshops will be organized for this purpose.

- Training provided to two or more national counterparts to complete the land use/cover in coffee areas and satellite data.  Appropriate integrated databases and maps completed.

- Accuracy assessments of land cover, field data, and forest-monitoring interpretations completed.

- A functional IMS server completed, installed, and made operational in a national organization.

- The Dominican Coffee Web Site upgraded and incorporating the IMS.  The web site will be transferred to a national organization.

- Metadata for coffee data sets completed and incorporated in the D.R. Clearinghouse.

- IMS development integrated with marketing strategies formulated by counterparts.

- Plan for national implementation presented at an international coffee meeting, and work published.

- Prepare and distribute annual reports to counterparts.

- Complete a final report with access to all developed data.

Quarterly progress reports will be submitted to USAID/GCAP, USAID/DR, and QCP counterparts within 15 days of the end of the quarter.  Trip reports for technical assistance, organization, and presentations will be completed.  A final report will be prepared within 60 days of the project completion.