# SUGGESTED STEPS IN ORGANIZING VEGETATION MAPPING & CLASSIFICATION PROJECTS  (prepared by Angela Evenden, Northern Colorado Plateau Network)

| STEP 1: PROJECT SCOPING AND PLANNING |
| --- |
| The important first step is to formulate and organize the vegetation mapping project at either a single park or multi-park level. This involves bringing together park and network staff, potential partners and cooperators to determine the scope and details of the anticipated mapping project(s). WASO NPS Veg Map Program Staff are available to provide guidance during the scoping process. Suggested topics to address during initial scoping meeting are listed below. Please keep in mind that each project will be unique and that a park or group of parks may have additional questions depending on the overall scope of the desired project. It will be important to identify anticipated timeframes for the overall project at this time. Vegetation mapping projects for a mid-sized park may take 3 to 4 years from start to completion, depending on overall complexity and resolution of classification and mapping. Project planning also involves obtaining and reviewing existing vegetation data (e.g. plant association lists, vegetation plot data). The results of this review will help determine the scope of work associated with the project. Sources of funding need to be identified and matched with the scope of the project(s). Parks and networks should work with WASO NPS Veg Map Staff (Karl Brown and Chris Lea) in developing overall project proposals. |
| Tasks | Description of Task | Who might be involved? |
| Initial Project Scoping Meeting or Conference Call(s) Single or Multi-park | Address during scoping: Determine whether the project will be NPS only or conducted in partnership with adjacent landowners (BLM, USFS, TNC etc.). Determine project mapping area boundary (include park unit plus area in the environs, include partner lands if applicable). Determine whether the project will be a ‘basic’ veg map project or if it will include more detail on specific ecosystem attributes (e.g. fire and fuels data, special biological or ecological features). Determine level of resolution of mapping & classification effort (association vs. alliance vs. ecological system). Determine what will be used as base map (orthophotography, satellite imagery or other alternative). Select scale (1:10K to 1:12K), and type of photography (true color, infrared, platform). Determine plot and observation point field sampling approach. Determine methods for mapping and spatial database development (traditional photo interpretation, automated image analysis, or hybrid approach). Identify base cartographic layers available for the veg map project area (e.g. soils, geology, roads, trails, DEMs, park boundary etc.). Determine remaining project tasks and timeframes (see other steps below – vegetation classification, description & key development, accuracy assessment, final products). Identify who could accomplish the work and possible cooperators | Park Staff Network Staff WASO Veg Map Partners Cooperators NatureServe |
| Assemble Existing Information and Data | Compile preliminary list of plant associations for project area (used to estimate number of plots needed for classification) Identify, obtain and review existing plot data for project area and determine whether suitable for use in project - follow guidelines developed by TNC for assessing utility of existing data. | NPS Staff or Cooperator |
| Project Funding Proposal and Workplan | Identify potential funding resources (look for opportunities to leverage and partner) Work with WASO NPS Veg Map Staff in developing a project funding proposal Develop a project workplan identifying tasks and detailed information on accomplishing the work (who, what, where and when). | NPS Staff WASO VegMap Staff Partners |

| STEP 2: AQUIRE AERIAL PHOTOGRAPHY OR OTHER MAPPING BASE |
| --- |
| During scoping, project members will have identified the type of imagery desired as the base map for the vegetation mapping effort. This step involves acquiring the imagery. |
| Tasks | Description of Task | Who is involved? |
| Acquire Imagery | Veg Map project staff will procure existing imagery or contract for services to acquire new imagery/photography to use as a base map. Imagery specifications will need to be determined, such as: Type of imagery – true color or infrared aerial photography, satellite platform,etc. Timing of photography/imagery – seasonally and time of day (e.g. near summer solstice and noon to minimize shadow effects in terrain with extreme vertical relief; or a certain season to capture phenology which maximizes expression of vegetation patterns) Format – film, digital, etc. Scale (e.g. 1:12,000) In some cases parks may choose to orthorectify existing aerial photography and create a new digital coverage (this may work for small project areas) Imagery Area Considerations. It is helpful to consider the ground area for the imagery to be acquired in relation to the defined veg map project area. Ultimately the base imagery is used for many more purposes than just the veg map project. With this in mind the networks/parks may want the base imagery to extend beyond the vegmap project area boundary. Aerial flights for orthophotography are typically flown at fairly high elevations and the photography taken usually encompasses an area exceeding the veg map project mapping area. For very little additional cost networks/parks could acquire a slightly larger surrounding area in the orthophoto coverage. The point here is carefully think about the imagery coverage boundaries and what will best serve the parks in the long term. Some veg map projects have conducted a QA/QC procedure on the digital base ortho coverage. | NPS Staff Cooperators |

| STEP 3: FIELD PLOT AND OBSERVATION POINT DATA COLLECTION AND ENTRY |
| --- |
| In the scoping step, based on the analysis of existing data, networks/parks will have determined whether new vegetation data is needed to support classification and mapping efforts. Most projects will rely entirely on or partially on new field data being collected. Several tasks related to collecting vegetation field data are identified below. |
| Tasks | Description of Task | Who is involved? |
| Identify Types of Field Data | Determine types of field data to be collected: vegetation plots (releves); fire/fuels data, observation points, other. | NPS Staff |
| Plot Sampling Design | For vegetation plots: Estimate the number of vegetation plots needed (e.g. 3 to 5 plots for each expected plant association) Determine sampling approach for vegetation plot locations (e.g. gradsect or other) If applicable, develop sampling framework (e.g. conduct gradsect analysis) | NPS Staff and/or Cooperators |
| Field Sampling Protocols & Database Development | Protocols. This task involves documenting field sampling protocols for the types of data identified above (e.g. plots, observation points, fire/fuels, accuracy assessment). Protocols should not only address what data are collected but how the data are collected (e.g. GPS use, data loggers, etc.) Although core data components have been standardized at the national program level, specific documentation for use by field crews has not been standardized. Parks may desire additional field data. A field manual and accompanying field forms documenting field sampling protocols should be developed, tested and finalized well in advance of the field season. There are several examples of existing veg map project field manuals and forms from completed veg map projects. Databases. A database matched to the field forms needs to be in place prior to field work. The NPS/USGS veg map program developed a database to house plot data (but not other types of field data). More recently some networks and parks have developed other more flexible Access database applications to house all types of field data (plots, observation points, AA points, fuels). Ground photos (or digital movies) are taken as part of the field sampling effort. A database and protocol for managing project photographs needs to be developed. | NPS Staff and/or Cooperators |
| Conduct Field Data Collection | Conduct pre-field season planning with parks and veg map project staff; secure necessary research permits, backcountry permits, campsites, etc. Assemble field manuals, field forms, maps, photography and equipment to conduct field work. Hire field crew (can be NPS and/or cooperator crews) Provide field based training for all crew members in the protocols (the more emphasis put on this step the higher quality the data and products). It may be helpful to have NatureServe participate in the training session, given their involvement in the classification work. Oversee and manage field data collection | NPS Staff and/or Cooperators NatureServe (?) |

| Field Data Entry and QA/QC | Enter field data into the project database either electronically (e.g. downloads of GPS or data logger units) and/or manually. Develop and implement a thorough QA/QC procedure for ensuring that electronic data field data are complete and accurate. Ensure proper storage of original field forms. Process all project photography, ensure that slides or print photos are sufficiently labeled and archived and that digital photos/movies are fully documented with associated information (e.g. plot number, photographer, caption, etc.) | NPS Staff and/or Cooperators |
| --- | --- | --- |

| STEP 4: PLANT ASSOCIATION CLASSIFICATION ANALYSIS, DESCRIPTION AND KEY |
| --- |
| Once the field data (or previously existing data) are in electronic form the classification analysis can proceed. During this analysis plant associations are classified according to the National Vegetation Classification Standard (NVC). NatureServe is a primary partner in analyzing and/or reviewing classification results and in developing global descriptions for the associations. |
| Tasks | Description of Task | Who is involved? |
| Conduct Classification Analysis | Electronic vegetation plot data are subjected to multivariate classification procedure (ordination and clustering algorithms). This step is typically by an academic or ecological services contractor). The classification is first produced in a ‘preliminary’ form and may not be finalized until the entire project is complete. Develop crosswalk of final plant associations to plots/observation points used for classification. | NatureServe NPS Staff and/or Other Cooperators |
| Plant Association Descriptions | For the final classified plant associations prepare local and global descriptions. Typically NatureServe ecologists are responsible for the global portion of the descriptions, where other cooperators or NPS staff may develop the local descriptions. These descriptions will be included in the final report. | NatureServe NPS Staff Other Cooperators? |
| Plant Association Field Key | Develop dichotomous key to plant associations (illustrated is good). The key will be used by field crews during accuracy assessment and included as a product in the final report. | Cooperators and/or NPS Staff NatureServe |

| STEP 5: VEGETATION MAPPING AND SPATIAL DATABASE DEVELOPMENT |
| --- |
| Ideally the field plot data collection and classification steps are completed prior to initiation of mapping. However, in some cases these steps are conducted concurrently. It is useful to have the classification results to help inform development of map class concepts. |
| Tasks | Description of Task | Who is involved? |
| Mapping Protocols and Spatial Database Structure | Develop clear documentation for photo interpreters and cartographers to use in attributing vegetation map polygons (e.g. density, height, pattern, other modifiers, etc.). Determine upfront all data fields that will be linked to the final spatial database (e.g. map class code & name, NVC classification, information, etc.) | NPS Staff |
| Photo Signature Development | Examine aerial photography or satellite imagery to identify signatures for mapping purposes (either determined through manual photo interpretation techniques or computer assisted image analysis such as eCognition). | NPS Staff Cooperators NatureServe |
| MapClass Legend, Crosswalk and Descriptions | Based on the interpretable signatures develop legend describing the concept of the map class. Develop a crosswalk between the map classes and classified plant associations. Hold a map legend meeting with network and/or park staff and other cooperators to solicit agreement regarding map class concepts. Develop map class descriptions including the visual signature, ecological concepts of the map classes, corresponding plant associations – illustrated with ground (plot photos) and photo signature ‘snapshots’ from the imagery. These descriptions will be included in the final report. | NPS Staff Cooperators |
| Conduct Mapping Spatial Database Development | Conduct vegetation mapping per identified protocol (e.g. traditional photo interpretation, digitize & transfer; image analysis/hybrid approaches, etc.) Document in written form (w/illustration and/or photos) the mapping protocol used. This will be included in the final report. | NPS Staff and/or Cooperators |
| Draft Map Production | Develop draft final digital map with associated attribute data. | NPS Staff and/or Cooperators |

| STEP 6: ACCURACY ASSESSMENT (AA) |
| --- |
| Accuracy assessment is conducted for the draft final digital vegetation map. |
| Tasks | Description of Task | Who is involved? |
| Select AA Points | Follow national NPS/USGS Veg Map protocol in selecting random points for AA field data collection. | NPS or cooperator GIS staff |
| Field Sampling Protocols & Database Development | AA field data collection protocols and field forms are documented in overall veg map project field manual (see Step 3 above). Project database is designed to house AA field data (see Step 3 above) | NPS Staff and/or Cooperators |
| AA Point Field Data Collection | Conduct pre-field season planning with parks and vegmap project staff; secure necessary research permits, backcountry permits, campsites, etc. Assemble and copy field manuals, field forms, maps, photography and equipment to conduct field work. Load AA points in GPS units for navigation. Hire field crew (can be NPS and/or cooperator crews) Provide field based training for all crew members in the protocols (the more emphasis put on this step the higher quality the data and products). Oversee and manage AA point field data collection | NPS Staff and/or Cooperators |
| AA Data Entry and QA/QC | Enter field data into the project database either electronically (e.g. downloads of GPS or data logger units) and/or manually. Develop and implement a thorough QA/QC procedure for ensuring that electronic data field data are complete and accurate. Ensure proper storage of original AA field forms. Process all AA related photography, ensure that slides or print photos are labeled and archived and that digital photos are documented with associated information (e.g. plot number, photographer, caption, etc.) | NPS Staff and/or Cooperators |
| AA Analysis | Follow national protocol in conducting accuracy assessment analysis. Results are presented in a contingency table indicating user and producer accuracy levels for each sampled map class. | NPS Staff and/or Cooperators |
| AA Meeting | Review AA results and prepare recommendations on how to address problems of low accuracy (e.g. combination of map classes). Hold meeting with park staff and project cooperators to review the AA results, discuss suggested ‘fixes’ to accuracy problems, and make decisions on map classes for the final vegetation map. | NPS Staff and/or Cooperators |
| Final Map Adjustment based on AA | Make changes to the final map class legend and spatial map layer based on decisions from the AA meeting. Conduct QA/QC procedure. | NPS Staff and/or Cooperators |

| STEP 7: FINAL REPORT, SPATIAL DATA AND METADATA |
| --- |
| The last step is to assemble a set of deliverables documenting the entire project start to finish and delivering the information is useful formats. FGDC compliant metadata are compiled. Final products need to be distributed in user friendly interfaces. All final products will be posted to the NPS/USGS Veg Map Program website (http://biology.usgs.gov/npsveg/). Geodatabase applications show excellent promise for delivering veg map products in a more user friendly interface. The WASO I&M Program is conducting a pilot veg map geodatabase project. |
| Tasks | Description of Final Deliverables | Who is involved? |
| Final Report | A typical vegetation mapping report will include the following chapters documenting methods and results: Introduction & Background Vegetation Classification Vegetation Mapping Accuracy Assessment & Recommendations References Appendices may include: Ecological System Descriptions Field Data Collection Instructions & Forms Description of Project Database Project Plant Species List (crosswalked to ITIS) Final Plant Association Classification Local & Global Plant Association Descriptons Plant Association Key (Illustrated) Map Class Descriptions (Illustrated) Accuracy Assessment Matrix *See Effigy Mounds VegMap Report for a good example. | NPS Staff and/or Cooperators |
| Final Map and Spatial Database | Final spatial database (line work with attributes per mapping protocol). Printed map to include with final report. Project metadata. | NPS Staff and/or Cooperators |
| Field Database | Access database with all field data (plots, fuels, observation points, AA points etc.) Hard copies of field datasheets. | NPS Staff and/or Cooperators |
| Photographs | Database with all digital photographs and/or digital movies. If applicable, labeled slides for archiving. | NPS Staff and/or Cooperators |
| Aerial Photography or other Imagery | Digital orthophotography or other imagery used for the project. If applicable, stereo photography in hard copy and/or digital form. Aerial photo indices. | NPS Staff and/or Cooperators |
| Other Spatial Data | Plots, observation point and AA point location coverages. | NPS Staff and/or Cooperators |