Attachment A

Statement of Work for the National Institute for Literacy

## Technical Assistance for the Gathering of Information

## on Adult & Adolescent Literacy Research Studies

## Solicitation Number: ED-07-R-0104

# I. 	Background

The National Institute for Literacy was established to ensure that literacy would have a place on the federal policy agenda and to invigorate a national effort to improve adult literacy.  Its primary activities to strengthen literacy across the lifespan are authorized by the U.S. Congress under two laws, the Adult Education and Family Literacy Act (AEFLA) in the Workforce Investment Act and the No Child Left Behind Act (NCLB).  The AEFLA directs the Institute to provide national leadership regarding literacy, coordinate literacy services and policy, and serve as a national resource for adult education and literacy programs. The NCLB law directs the Institute to disseminate information on scientifically based reading research pertaining to children, youth, and adults as well as information about development and implementation of classroom reading programs based on the research.

The Institute’s authorizing laws organize its activities into four general areas: program improvement; policy and technical assistance; information dissemination, including dissemination of scientifically based reading research and effective reading programs based on scientific research; and coordination of research support.  To carry out these duties, the Institute has concentrated its efforts on projects that could bring about significant improvement across the adult education system and enhance the use of findings from scientific research in reading instruction for all ages.  Together, the Institute’s authorizing laws reinforce a focus on disseminating critical information on reading across the lifespan while allowing the Institute to address broader challenges associated with improving the effectiveness of the adult literacy service delivery system.

The Institute is a preparing a comprehensive effort called the Literacy Research Initiative (LRI) that will gather and highlight research and research-based materials on reading, writing, math and other areas on its website.  The LRI will describe the findings of research studies and note reports and journal articles connected to the studies.  In addition, there will be citations of published materials, links to abstracts of studies, and ancillary materials generated through some of the studies.  The Institute envisions that the LRI will bring together information on federally and non-federally funded research, including evaluation research on literacy and basic skills to create a comprehensive picture of the knowledge base on literacy.

# II.   	Purpose of the Acquisition

The Institute seeks a contractor to gather and write up information on federally and non-federally funded adult and adolescent research studies on literacy, basic skills, and evaluation research to post on the LRI.  The first phase of this project will focus on the development of a template that will organize the information to be gathered as well as  gathering information on reading, writing, math, and evaluation research from such agencies as the Department of Labor, National Science Foundation, National Institute of Child Health and Human Development and other agencies across the government.

# Scope of Work

The contractor shall perform the following tasks and submit associated deliverables listed below.

Task 1:  Participate in a post-award meeting with Institute staff.

  - The contractor shall attend a post-award meeting at the Institute’s offices in Washington, DC within 10 business days of the contract award to discuss contract tasks, timeline, and answer questions.

  - The contractor shall provide a written summary of the post-award meeting to Institute staff no later than 5 days after the conclusion of the post award meeting (see performance schedule) to be submitted via electronic mail.

Task 2:  Develop a template for the information to be collected and described on the LRI.

2.1	The contractor shall draft a template for use in collecting and displaying

information for the LRI database and submit to the Institute for comments.  The template shall include all possible forms of information including text describing:

a. Research and evaluation projects

b. Citations

c. Ancillary research materials

d. Links to sources

e. Background papers

f. Book chapters

g. Journal articles with links to online abstracts

The template shall include public and private fields.  The private field will contain background information such as contact information, press submission dates, etc for contractor and Institute use only.

2.2       The contractor shall submit revised draft template in response to Institute

comments and resubmit to Institute.

2.3       The contractor shall submit revised draft template in response to Institute

comments.

2.4       Submit final template.

2.5	The contractor shall work with the Institute’s technical contractor to test and validate the online form to ensure that the database functions effectively.

Task 3:  Develop a work plan

  - The contractor shall prepare a work plan for that identifies the methodology for gathering the information required to fill out the approved template developed in Task 2 and submit it to the Institute for review and comment.

- The work plan should prioritize in the following order:

  - Adult reading research.

  - Adolescent reading research.

  - Other federally funded adult and adolescent research on reading, writing, and math.

  - Federally funded evaluation research for adult literacy and adolescent literacy.

  - Non-governmentally funded adult and adolescent research on reading, writing, math and evaluation research.

  - The contractor shall revise the work plan in response to Institute comments.

  - Submit the work plan for final Institute approval.

Task 4.  Collect information as described in the approved Work Plan developed in Task 3.

  - The contractor shall gather information to populate the online database.

  - Enter information collected into the online database for Institute review.

  - Revise text for approval based on Institute comments.

  - Submit final text online.

Task 5:  In Press Submissions

5.1 The contactor shall keep track of all in press submissions so that these may be posted

as soon as the information is published and submit a periodic report monthly listing

the in press submissions.

# Task 6:  Progress Reports

6.1 The contractor shall submit monthly progress reports that will include, at minimum, the following: status of work, problems encountered, corrective action(s) taken, etc.

# IV. Optional Tasks

The contractor shall:

Task 7: Gather literacy research information on reading, writing, math, and evaluation research from non-federal agencies and organizations.

  - The contractor shall gather information to populate the online database.

  - Enter information collected into the online database for Institute review.

  - Revise text for approval based on Institute comments.

7.4 Submit final text online.

Task 8: Continue to update information collected in Task 4 on a monthly-basis for one additional year.

8.1 The contractor shall gather information to populate the online database.

8.2 Enter information collected into the online database for Institute review.

8.3 Revise text for approval based on Institute comments.

8.4 Submit final text online.

Task 9:  Continue monthly in press submission reports for Task 5 for one additional year.

9.1 The contactor shall keep track of all in press submissions so that these may be posted

as soon as the information is published and submit a periodic report monthly listing

the in press submissions.

Task 10: Continue monthly progress reports for Task 6 for one additional year.

6.1 The contractor shall submit monthly progress reports that will include, at minimum, the following: status of work, problems encountered, corrective action(s) taken, etc.

### V. Government Furnished Materials

### For more information:

### Adult Literacy Research Consortium (Network): http://www.nifl.gov/nifl/nat_research.html

Adolescent Literacy Research Consortium (Network): http://www.ed.gov/about/offices/list/ovae/pi/hs/adollit_pg3.html

In addition, the Institute will provide contact information for the researchers listed for the adult literacy and adolescent literacy federally funded research grants referenced above in the online links at the post-award meeting.

Research Agenda Themes Document

Scan of Foundation and Non-Governmental Organizations (supporting document to the Research Agenda Themes Document)

### VI. Schedule of Deliverables

| TASK | DELIVERABLE | DUE DATE |
| --- | --- | --- |
| Task 1 | Post Award Meeting Notes | Within 5 days of the Post Award Meeting |
| Task 2.1 | Submit Draft Template | October 15, 2007 |
| Task 2.2 | Submit Revised Template | October 29, 2007 |
| Task 2.3 | Submit Revised Template | November 9, 2007 |
| Task 2.4 | Final Template | November 21, 2007 |
| Task 3.1 | Draft Work Plan | October 15, 2007 |
| Task 3.2 | Revise Work Plan | October 24, 2007 |
| Task 3.3 | Final Work Plan | November 13, 2007 |
| Task 4.2 | Submit text for Institute Review | Monthly |
| Task 4.3 | Revise text | Monthly |
| Task 4.4 | Submit final text online | Monthly |
| Task 5 | In Press Submissions | Monthly |
| Task 6 | Progress Reports | Monthly |
| Optional Task 7 | Submit text for Institute Review | Monthly |
| Optional Task 8 | Continue with Task 4 | Monthly |
| Optional Task 9 | Continue with Task 5 | Monthly |
| Optional Task 10 | Continue with Task 6 | Monthly |

### VII. Performance Period

The performance period for this contract shall be twelve months from the time of contract award – September 2007 to September 30, 2008.  Optional year –October 2008 to September 2009.