## SCC List
Standard Cost Categories for Capital Projects
(Rev.8, June 2, 2006)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES

## SCC Definitions
Standard Cost Categories for Capital Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put construction in 10 through 50. Put design, administration, testing, etc. in 80.
(Rev.8, June 2, 2006)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (rail, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of who is performing the work. In your written description of the scope and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. For guideway and track elements associated with yards, see 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs.
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, ventilation structures and equipment, station power and lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, and life safety systems; finishes and equipment. Include all construction materials and labor regardless of who is performing the work.
Place all guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. . .Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ." See http://www.fta.dot.gov/17973_18027_ENG_HTML.htm
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, ventilation structures and equipment, facility power and lighting, safety systems such as fire detection and prevention, security surveillance, access control, and life safety systems; finishes and equipment. Include fueling stations, alternative fueling stations. Include all construction materials and labor regardless of who is performing the work.
Where a support facility shares structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of who is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks and other hazardous materials and treatments not listed.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, landscape, site and station furniture, site lighting, signage, public artwork, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditiions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of who is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | Include land that is leased, purchased or acquired through payment or for free, if the value of such land is used as local match to the Federal funding of the project. Include existing buildings and other structures on land. Include permanent surface and subsurface easements, costs for trackage rights.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include streetcar.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include Locomotive Diesel, Locomotive Electric, Trailer Cars, Self-Propelled Electric (EMU), Self-Propelled Diesel (DMU).
70.04 | Bus | Include STD 40 ft bus, STD 35 ft bus, 30 ft bus, <30 ft bus, School, Articulated, Commuter/Suburban, Intercity, Trolley STD, Trolley Articulated, Double Decker, Used, Used School Bus, Dual Mode.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES |  | See Cats. 60 and 70 for professional services related to ROW/Land and Vehicles. Cat. 80 includes all professional, technical and management services (and related professional liability insurance costs) related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the preliminary engineering, final design, and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, Before and After studies, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. As required, use back-up worksheets to track detailed costs within each of the line items. (Note that costs for alternatives analysis and NEPA work done before FTA approval to enter preliminary engineering (PE), regardless of funding source, are not included in an FFGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PE should be omitted from these worksheets whereas costs incurred after FTA approval to enter PE should be included.)
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the Allocated Contingency worksheet.
Subtotal (10 - 90)
100 FINANCE CHARGES |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the New Starts funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the New Starts project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation Calculation to YOE worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TEAM Scopes ALIs
14-Series TEAM Scopes / Activity Line Items Required for all grants that serve a New Starts Project
(Rev.8, June 2, 2006)
1. HOW DO THE SCC AND TEAM RELATE? TEAM is for grants management. Many grants can serve a major capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management, day to day as well as at important milestones. To manage major capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TEAM. TEAM and the SCC support each other but TEAM doesn't duplicate the level of information in the SCC. The idea is to keep grants budgets simple and focus on cost management. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for New Starts projects, from the very first grant that funds Preliminary Engineering all the way to through the FFGA. These grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 Fixed Guideway Mod, 5309 New Starts, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has only 10 pairs of Scopes and ALIs. This is intentionally simple. Do not mix and match Scopes and ALIs or change the standard text. For example, put only guideway costs under the Guideway Scope. If kept simple, the information will be clean and produce a reliable database at the program-wide level. 4. WHAT'S WITH THE VEHICLES? For now, use 14-Series SCOPE (14070) and 13-Series ALIs. | 14010 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
| 140110 | Guideway & Track Elements |  | .02 Bus STD 35 FT
.03 Bus 30 FT
| 14020 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
| 140220 | Stations, Stops, Terminals, Intermodal |  | .05 Bus School
.06 Bus Articulated
| 14030 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
| 140330 | Support Facilities: Yards, Shops, Admin Bldgs |  | .08 Bus Intercity
.09 Bus Trolley STD
| 14040 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
| 140440 | Sitework & Special Conditions | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14050 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
| 140550 | Systems | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14060 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
| 140660 | ROW, Land, Existing Improvements | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 14070 | VEHICLES | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
| 13____ | Note! Please use the 13-Series ALIs for vehicles. | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14080 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
| 140880 | Professional Services | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14090 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
| 140990 | Unallocated Contingency | 13.16.XX | .30 Cable Car
.31 People Mover
| 14100 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
| 141010 | Finance Charges | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## BUILD Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name | [6 empty] | Today's Date |  | 2006-05-18
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2006
Phase | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 100000 | 12000 | 112000 | 12444.4444 | 38.94% | 25.19% | 129846.5014 | 1.1593
10.01 | Guideway: At-grade exclusive right-of-way | 9 | 100000 | 12000 | 112000 | 12444.4444 |  |  | 129846.5014
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) |  |  |  | 0 |  |  |  | 0
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0 |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0 |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 18 | 100000 | 20000 | 120000 | 6666.6667 | 41.72% | 26.98% | 141226.7383 | 1.1769
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 18 | 100000 | 20000 | 120000 | 6666.6667 |  |  | 141226.7383
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  |  |  | 0
20.05 | Joint development |  |  |  | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 9 | 10000 | 2000 | 12000 | 1333.3333 | 4.172% | 2.698% | 14309.752 | 1.1925
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  |  |  | 0
30.02 | Light Maintenance Facility |  | 10000 | 2000 | 12000 |  |  |  | 14309.752
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 9 | 16800 | 2800 | 19600 | 2177.7778 | 6.815% | 4.408% | 21587.2626 | 1.1014
40.01 | Demolition, Clearing, Earthwork |  | 500 | 100 | 600 |  |  |  | 660.8346
40.02 | Site Utilities, Utility Relocation |  | 4500 | 500 | 5000 |  |  |  | 5506.9547
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0 |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 2800 | 200 | 3000 |  |  |  | 3304.1728
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 9000 | 2000 | 11000 |  |  |  | 12115.3004
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  |  |  | 0
50 SYSTEMS |  | 9 | 20300 | 3700 | 24000 | 2666.6667 | 8.345% | 5.397% | 28543.2322 | 1.1893
50.01 | Train control and signals |  | 7000 | 2000 | 9000 |  |  |  | 10703.7121
50.02 | Traffic signals and crossing protection |  | 2500 | 500 | 3000 |  |  |  | 3567.904
50.03 | Traction power supply: substations |  | 4500 | 500 | 5000 |  |  |  | 5946.5067
50.04 | Traction power distribution: catenary and third rail |  | 4500 | 500 | 5000 |  |  |  | 5946.5067
50.05 | Communications |  | 900 | 100 | 1000 |  |  |  | 1189.3013
50.06 | Fare collection system and equipment |  | 900 | 100 | 1000 |  |  |  | 1189.3013
50.07 | Central Control |  | 0 | 0 | 0 |  |  |  | 0
Construction Subtotal (10 - 50) |  | 9 | 247100 | 40500 | 287600 | 31955.5556 | 100% | 64.67% | 335513.4864
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 9 | 17000 | 4000 | 21000 | 2333.3333 |  | 4.722% | 24348.5564 | 1.1595
60.01 | Purchase or lease of real estate |  | 17000 | 4000 | 21000 |  |  |  | 24348.5564
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  |  |  | 0
70 VEHICLES (number) |  | 10 | 22000 | 8000 | 30000 | 3000 |  | 6.746% | 34987.9315 | 1.1663
70.01 | Light Rail | 10 | 22000 | 8000 | 30000 | 3000 |  |  | 34987.9315
70.02 | Heavy Rail |  |  |  | 0 |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0 |  |  |  | 0
70.04 | Bus |  |  |  | 0 |  |  |  | 0
70.05 | Other |  |  |  | 0 |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0 |  |  |  | 0
70.07 | Spare parts |  |  |  | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES |  | 9 | 65500 | 19000 | 84500 | 9388.8889 | 29.38% | 19% | 92741.9141 | 1.0975
80.01 | Preliminary Engineering |  | 12000 | 3000 | 15000 |  |  |  | 16463.0617
80.02 | Final Design |  | 17000 | 3000 | 20000 |  |  |  | 21950.7489
80.03 | Project Management for Design and Construction |  | 9000 | 3000 | 12000 |  |  |  | 13170.4493
80.04 | Construction Administration & Management |  | 9000 | 3000 | 12000 |  |  |  | 13170.4493
80.05 | Insurance |  | 2500 | 2000 | 4500 |  |  |  | 4938.9185
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 3000 | 1000 | 4000 |  |  |  | 4390.1498
80.07 | Surveys, Testing, Investigation, Inspection |  | 3000 | 1000 | 4000 |  |  |  | 4390.1498
80.08 | Start up |  | 10000 | 3000 | 13000 |  |  |  | 14267.9868
Subtotal (10 - 80) |  | 9 | 351600 | 71500 | 423100 | 47011.1111 |  | 95.14% | 487591.8884
90 UNALLOCATED CONTINGENCY |  |  |  |  | 21155 |  |  | 4.757% | 24494.9672 | 1.1579
Subtotal (10 - 90) |  | 9 |  |  | 444255 | 49361.6667 |  | 99.9% | 512086.8556
100 FINANCE CHARGES |  |  |  |  | 440.4067 |  |  | 0.09904% | 500 | 1.1353
Total Project Cost (10 - 100) |  | 9 |  |  | 444695.4067 | 49410.6007 |  | 100% | 512586.8556 | 1.1527
Allocated Contingency as % of Base Yr Dollars w/o Cont. |  |  |  |  | 20.34%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 5%
YOE Construction Cost per Mile (X000) | [8 empty] | 37279.2763
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | 53066.5471
YOE Total Project Cost per Mile (X000) | [8 empty] | 56954.0951
Note on J3: Year of Base Year Dollars should match the year in "Today's Date."
Note on J6: YOE Dollars automatically arrive from Inflation Worksheet.
Note on F76: Enter finance charges on Inflation Worksheet.
Note on J8: YOE costs for individual line items within a Category are derived as a percentage of the YOE cost of the Category.

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  | (Rev.8, June 2, 2006)
Project Sponsor Name |  | Today's Date | 2006-05-18
Project Name and Location
Phase
Describe elements of the project and/or the entire project to explicate the unit costs shown on the Main Worksheet. As an example -- a project may include ten miles of on-grade guideway and one-quarter mile of aerial structure for a river crossing. Because of its uniqueness within the project, the aerial component (two-tracks) may have a high unit cost when compared with the unit cost for a ten-mile long two-track aerial structure. The unit cost for the longer aerial structure benefits from the economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context and site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc. Below, expand lines and delete lines as required to accommodate your commentary.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY
Subtotal (10 - 90)
100 FINANCE CHARGES
Total Project Cost (10 - 100)
Allocated Contingency as % of Base Yr Dollars w/o Cont.
Unallocated Contingency as % of Subtotal (10 - 80)
YOE Construction Cost per Mile (X000)
YOE Total Project Cost per Mile Not Including Vehicles (X000)
YOE Total Project Cost per Mile (X000)

## Inflation
I N F L A T I O N W O R K S H E E T | [5 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name |  |  |  | Today's Date |  | 2006-05-18
Project Name and Location |  |  |  | Yr of Base Year $ |  | 2006
Phase |  |  |  | Yr of Revenue Ops |  | 2012
Below, show all project costs in the year in which they occurred or are planned to occur through the completion of the project or the fulfillment of the New Starts funding commitment, whichever is expected to occur later in time.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 112000 | 112000 | 2009: 22000; 2010: 20000; 2011: 50000; 2012: 20000; 2014: 0; 2015: 0; 2016: 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 120000 | 120000 | 2010: 30000; 2011: 50000; 2012: 40000; 2013: 0; 2014: 0; 2015: 0; 2016: 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 12000 | 12000 | 2011: 6000; 2012: 6000; 2013: 0; 2014: 0; 2015: 0; 2016: 0
40 SITEWORK & SPECIAL CONDITIONS | 19600 | 19600 | 2008: 5000; 2009: 10000; 2010: 4000; 2011: 600; 2013: 0; 2014: 0; 2015: 0; 2016: 0
50 SYSTEMS | 24000 | 24000 | 2011: 14000; 2012: 10000; 2013: 0; 2014: 0; 2015: 0; 2016: 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 21000 | 21000 | 2010: 10000; 2011: 9000; 2012: 2000; 2013: 0; 2014: 0; 2015: 0; 2016: 0
70 VEHICLES (number) | 30000 | 30000 | 2010: 12000; 2011: 12000; 2012: 6000; 2013: 0; 2014: 0; 2015: 0; 2016: 0
80 PROFESSIONAL SERVICES | 84500 | 84500 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 5000 | 11000 | 15000 | 15000 | 15000 | 10500 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21155 | 21155 | 2007: 2000; 2008: 2000; 2009: 2000; 2010: 2000; 2011: 3000; 2012: 10155; 2013: 0; 2014: 0; 2015: 0; 2016: 0
100 FINANCE CHARGES | 440.4067 | 440.4067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.8037 | 90.851 | 87.9913 | 85.2216 | 82.5391 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 444695.4067 | 444695.4067 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 7000 | 18093.8037 | 49090.851 | 93087.9913 | 159685.2216 | 104737.5391 | 0 | 0 | 0 | 0
Inflation Rate |  |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325
Compounded Inflation Factor |  |  | 0.83546 | 0.86052 | 0.88634 | 0.91293 | 0.94031 | 0.96852 | 1 | 1.0325 | 1.0661 | 1.1007 | 1.1365 | 1.1734 | 1.2115 | 1.2509 | 1.2916 | 1.3336 | 1.3769
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 129846.5014 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24215.4677 | 22729.5186 | 58670.5698 | 24230.9453 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 141226.7383 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34094.2778 | 58670.5698 | 48461.8906 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 14309.752 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7040.4684 | 7269.2836 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 21587.2626 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5330.2812 | 11007.0308 | 4545.9037 | 704.0468 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 28543.2322 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16427.7595 | 12115.4727 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 24348.5564 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11364.7593 | 10560.7026 | 2423.0945 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 34987.9315 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13637.7111 | 14080.9367 | 7269.2836 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES | 92741.9141 |  | 835.4564 | 1721.0403 | 1772.6715 | 1825.8516 | 1880.6272 | 1937.046 | 2000 | 5162.5 | 11726.6187 | 16510.5462 | 17047.1389 | 17601.1709 | 12721.2463 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 24494.9672 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065 | 2132.1125 | 2201.4062 | 2272.9519 | 3520.2342 | 12303.2625 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 500 |  | 2008: 100; 2009: 100; 2010: 100; 2011: 100; 2012: 100
Total Project Cost (10 - 100) | 512586.8556 |  | 835.4564 | 1721.0403 | 1772.6715 | 1825.8516 | 1880.6272 | 1937.046 | 2000 | 7227.5 | 19289.0125 | 54034.4508 | 105792.2613 | 187376.4588 | 126894.4791 | 0 | 0 | 0 | 0
Note on E33: Enter Finance Charges on this line
Note on E20: Insert estimated inflation rates for each year. The YOE dollars will be calculated automatically. Please provide a note if your assumptions regarding inflation have changed from your last submission of this SCC worksheet.
Note on K21: In the Base Year no inflation multiplier is used.

## Schedule
S C H E D U L E |  |  | (Rev.8, June 2, 2006)
Project Sponsor Name | Today's Date |  | 2006-05-18
Project Name and Location | Yr of Base Year $ |  | 2006
Phase | Yr of Revenue Ops |  | 2012
|  | Start Date | End Date | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
Preliminary Engineering |  | 2005-01-01 | 2006-06-01
Design Build and Baseline Alternatives
Cost estimating, scheduling, ridership forecasting
Reviews
Develop FEIS, receiving Record of Decision
Submit request / receive FTA approval to enter Final Design
Final Design |  | 2006-06-01 | 2008-09-01
Develop design/contract docs for Build Alternative
Cost estimating, scheduling, ridership forecasting
Reviews
Submit request / receive FTA approval for FFGA
Bid period and award
Construction
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 2008-09-01 | 2012-01-01
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 2008-09-01 | 2012-01-01
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 2008-09-01 | 2012-01-01
40 SITEWORK & SPECIAL CONDITIONS |  | 2008-09-01 | 2012-01-01
50 SYSTEMS |  | 2008-09-01 | 2012-01-01
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 2008-09-01 | 2009-09-01
70 VEHICLES (number) |  | 2008-09-01 | 2012-01-01
80 PROFESSIONAL SERVICES |  | 2003-01-01 | 2012-01-01
90 UNALLOCATED CONTINGENCY |  | 2008-09-01 | 2012-01-01
100 FINANCE CHARGES |  | 2008-09-01 | 2012-01-01
Revenue Ops
Revenue Operations |  | 2012-01-01
Before and After Study: Two years post Rev Ops |  |  | 2014-03-01
Fulfillment of the New Starts funding commitment |  |  | 2012-09-01
Completion of project, close-out, resolution of claims |  |  | 2014-03-01

## BUILD Annualized
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name | [6 empty] | Today's Date |  | 2006-05-18
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2006
Phase | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 7% rate) [.07/1 - (1.07)^-no. yrs] | Annualized Cost (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 112000 | 32906.815 | 7000 | 151906.815 |  |  | 10635.7354
10.01 | Guideway: At-grade exclusive right-of-way | 9 | 112000 | 32906.815 | 7000 | 151906.815 | 125 | 0.070015 | 10635.7354
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.077234 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 18 | 120000 | 35257.3018 | 10000 | 165257.3018 |  |  | 11670.3925
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 18 | 120000 | 35257.3018 | 10000 | 165257.3018 | 70 | 0.07062 | 11670.3925
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 12000 | 3525.7302 | 0 | 15525.7302 |  |  | 1124.9921
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.02 | Light Maintenance Facility |  | 12000 | 3525.7302 |  | 15525.7302 | 50 | 0.07246 | 1124.9921
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 19600 | 5758.6926 | 1000 | 26358.6926 |  |  | 2216.825
40.01 | Demolition, Clearing, Earthwork |  | 600 | 176.2865 |  | 776.2865 | 125 | 0.070015 | 54.3516
40.02 | Site Utilities, Utility Relocation |  | 5000 | 1469.0542 |  | 6469.0542 | 125 | 0.070015 | 452.93
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.070015 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 3000 | 881.4325 |  | 3881.4325 | 125 | 0.070015 | 271.758
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 11000 | 3231.9193 | 1000 | 15231.9193 | 20 | 0.094393 | 1437.7854
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | 0 |  | 0 | 100 | 0.070081 | 0
50 SYSTEMS |  |  | 24000 | 7051.4604 | 500 | 31551.4604 |  |  | 2514.6696
50.01 | Train control and signals |  | 9000 | 2644.2976 | 500 | 12144.2976 | 30 | 0.080586 | 978.6653
50.02 | Traffic signals and crossing protection |  | 3000 | 881.4325 |  | 3881.4325 | 30 | 0.080586 | 312.7907
50.03 | Traction power supply: substations |  | 5000 | 1469.0542 |  | 6469.0542 | 50 | 0.07246 | 468.7467
50.04 | Traction power distribution: catenary and third rail |  | 5000 | 1469.0542 |  | 6469.0542 | 30 | 0.080586 | 521.3178
50.05 | Communications |  | 1000 | 293.8108 |  | 1293.8108 | 20 | 0.094393 | 122.1266
50.06 | Fare collection system and equipment |  | 1000 | 293.8108 |  | 1293.8108 | 25 | 0.085811 | 111.0226
50.07 | Central Control |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
Construction Subtotal (10 - 50) |  |  | 287600 | 84500 | 18500 | 390600 |  |  | 28162.6146
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 21000 |  | 1000 | 22000 |  |  | 1540.3271
60.01 | Purchase or lease of real estate |  | 21000 |  | 1000 | 22000 | 125 | 0.070015 | 1540.3271
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.070015 | 0
70 VEHICLES (number) |  | 10 | 30000 |  | 1655 | 31655 |  |  | 2716.3319
70.01 | Light Rail | 10 | 30000 |  | 1655 | 31655 | 25 | 0.085811 | 2716.3319
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.04 | Bus | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
80 PROFESSIONAL SERVICES |  |  | 84500
80.01 | Preliminary Engineering |  | 15000
80.02 | Final Design |  | 20000
80.03 | Project Management for Design and Construction |  | 12000
80.04 | Construction Administration & Management |  | 12000
80.05 | Insurance |  | 4500
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 4000
80.07 | Surveys, Testing, Investigation, Inspection |  | 4000
80.08 | Start up |  | 13000
Subtotal (10 - 80) |  |  | 423100
90 UNALLOCATED CONTINGENCY |  |  | 21155
Subtotal (10 - 90) |  |  | 444255 | 84500 | 21155 | 444255 |  |  | 32419.2736
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.
Note on H8: Useful Life changes shown in green.

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [9 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name | [7 empty] | Today's Date |  | 2006-05-18
Project Name and Location
Phase
| YOE Cost (X000) | Double- check Total | Federal 5309 New Starts Funds | Federal Other Funds | Local Funds | 50% | 50% | 80% | 20% | 60% | 40% | 50% | 50%
[6 empty] | Federal 5309 New Starts | Local 1 | Federal 5307 | Local 2 | Federal CMAQ | Local 3 | Federal Other | Local 4
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 129846.5014 | 129847 | 1847 | 14000 | 114000 | 1847 | 100000 |  |  |  |  | 14000 | 14000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 141226.7383 | 141227 | 70000 | 35000 | 36227 | 70000 | 1227 |  |  |  |  | 35000 | 35000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 14309.752 | 14310 | 10000 | 2000 | 2310 | 10000 | 310 |  |  |  |  | 2000 | 2000
40 SITEWORK & SPECIAL CONDITIONS | 21587.2626 | 21587 | 20000 | 0 | 1587 | 20000 | 1587
50 SYSTEMS | 28543.2322 | 28543 | 543 | 16800 | 11200 | 543 |  |  |  | 16800 | 11200
60 ROW, LAND, EXISTING IMPROVEMENTS | 24348.5564 | 24349 | 4349 | 0 | 20000 | 4349 | 20000
70 VEHICLES (number) | 34987.9315 | 34988 | 34000 | 0 | 988 | 34000 | 988
80 PROFESSIONAL SERVICES | 92741.9141 | 92742 | 2742 | 72000 | 18000 | 2742 |  | 72000 | 18000
90 UNALLOCATED CONTINGENCY | 24494.9672 | 24495 | 495 | 2000 | 22000 | 495 | 20000 |  |  |  |  | 2000 | 2000
100 FINANCE CHARGES | 500 | 500 | 500 | 0 | 0 | 500
Total Project Cost (10 - 100) | 512586.8556 | 512588 | 144476 | 141800 | 226312 | 144476 | 144112 | 72000 | 18000 | 16800 | 11200 | 53000 | 53000
Percentage of Total Project Cost | 100% |  | 28.19% | 27.66% | 44.15% | 28.19% | 28.11% | 14.05% | 3.512% | 3.277% | 2.185% | 10.34% | 10.34%
|  |  | 28.19% | 71.81%
100%
Describe Sources of Local Funds below:
Local 1:
Local 2:
Local 3:
Local 4:
Note on H6: Below indicate type, percentage match etc. Use grey cells for Federal sources. Delete examples not used.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R | [6 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name |  |  |  |  | Today's Date |  | 2006-05-18
Project Name and Location
Phase
Total Project Cost In YOE Dollars |  |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
At right, costs automatically arrive from the Inflation Worksheet. Below insert fund sources and amounts for each year. | 512586.8556 | double check | 835.4564 | 1721.0403 | 1772.6715 | 1825.8516 | 1880.6272 | 1937.046 | 2000 | 7227.5 | 19289.0125 | 54034.4508 | 105792.2613 | 187376.4588 | 126894.4791
Federal 5309 New Starts | 144476 | 144476 | 2009: 44000; 2011: 100476
Local 1 | 144112 | 144112 | 2007: 337; 2008: 1289; 2009: 6000; 2010: 100024; 2011: 19787; 2012: 16675
Federal 5307 | 72000 | 72000 | 2012: 72000
Local 2 | 18000 | 18000 | 2008: 18000
Federal CMAQ | 16800 | 16800 | 2000: 835; 2001: 1721; 2002: 1773; 2003: 1826; 2004: 1881; 2005: 1937; 2006: 2000; 2007: 4827
Local 3 | 11200 | 11200 | 2007: 1566; 2009: 4034; 2010: 1949; 2011: 3651
Federal Other | 53000 | 53000 | 2007: 498; 2010: 3843; 2011: 48659
Local 4 | 53000 | 53000 | 2011: 14781; 2012: 38219
Total Funds in YOE Dollars | 512588 | 512588 | 835 | 1721 | 1773 | 1826 | 1881 | 1937 | 2000 | 7228 | 19289 | 54034 | 105816 | 187354 | 126894 | 0 | 0 | 0 | 0

## BASELINE Main
M A I N W O R K S H E E T - B A S E L I N E A L T E R N A T I V E | [8 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name | [6 empty] | Today's Date |  | 2006-05-18
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2006
Phase | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | Baseline Alternative Cost Parameters (X000) see 5/06 New Starts Reporting Instructions for additional info
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 8000 | 1000 | 9000 | 1000 | 26.63% | 14.83%
10.01 | Guideway: At-grade exclusive right-of-way |  |  |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 9 | 8000 | 1000 | 9000 | 1000 |  |  | 1000/route mile
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 1000/route mile
10.04 | Guideway: Aerial structure |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 36 | 6000 | 1000 | 7000 | 194.4444 | 20.71% | 11.53%
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 36 | 6000 | 1000 | 7000 | 194.4444 |  |  | 200/station
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0
20.05 | Joint development |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 9 | 4000 | 1000 | 5000 | 555.5556 | 14.79% | 8.239%
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0
30.02 | Light Maintenance Facility |  | 4000 | 1000 | 5000
30.03 | Heavy Maintenance Facility |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 9 | 8300 | 1800 | 10100 | 1122.2222 | 29.88% | 16.64%
40.01 | Demolition, Clearing, Earthwork |  | 5000 | 100 | 5100
40.02 | Site Utilities, Utility Relocation |  | 1000 | 500 | 1500
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 1000 | 200 | 1200
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 1000 | 1000 | 2000
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 200 |  | 200 |  |  |  | 5/on-grade space
40.08 | Temporary Facilities and other indirect costs during construction |  | 100 |  | 100
50 SYSTEMS |  | 9 | 2305 | 392 | 2697 | 299.6667 | 7.98% | 4.444%
50.01 | Train control and signals |  |  |  | 0
50.02 | Traffic signals and crossing protection |  | 1125 | 200 | 1325 |  |  |  | 25/intersection
50.03 | Traction power supply: substations |  |  |  | 0
50.04 | Traction power distribution: catenary and third rail |  |  |  | 0
50.05 | Communications |  | 600 | 72 | 672 |  |  |  | 12/bus and 12/sign
50.06 | Fare collection system and equipment |  | 180 | 20 | 200 |  |  |  | 10/bus
50.07 | Central Control |  | 400 | 100 | 500 |  |  |  | 15-25 /bus
Construction Subtotal (10 - 50) |  | 9 | 28605 | 5192 | 33797 | 3755.2222 | 100% | 55.69%
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 9 | 1000 | 200 | 1200 | 133.3333 |  | 1.977%
60.01 | Purchase or lease of real estate |  | 1000 | 200 | 1200
60.02 | Relocation of existing households and businesses |  |  |  | 0
70 VEHICLES (number) |  | 20 | 10000 | 3000 | 13000 | 650 |  | 21.42%
70.01 | Light Rail |  |  |  | 0
70.02 | Heavy Rail |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0
70.04 | Bus | 20 | 10000 | 3000 | 13000 | 650 |  |  | 400 conventional or 650 articulated bus
70.05 | Other |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0
70.07 | Spare parts |  |  |  | 0
80 PROFESSIONAL SERVICES |  | 9 | 9800 | 0 | 9800 | 1088.8889 | 29% | 16.15% | Max 35%*Const.Cost
80.01 | Preliminary Engineering |  | 2000 |  | 2000
80.02 | Final Design |  | 3500 |  | 3500
80.03 | Project Management for Design and Construction |  | 2000 |  | 2000
80.04 | Construction Administration & Management |  | 1500 |  | 1500
80.05 | Insurance |  | 500 |  | 500
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 150 |  | 150
80.08 | Start up |  | 150 |  | 150
Subtotal (10 - 80) |  | 9 | 49405 | 8392 | 57797 | 6421.8889 |  | 95.24%
90 UNALLOCATED CONTINGENCY |  |  |  |  | 2889.85 |  |  | 4.762% | Max 5%*Subtotal (10 - 80)
Subtotal (10 - 90) |  | 9 |  |  | 60686.85 | 6742.9833 |  | 100%
100 FINANCE CHARGES |  |  |  |  | NA
Total Project Cost (10 - 100) |  | 9 |  |  | 60686.85 | 6742.9833 |  | 100%
Total Base Year Cost per Mile Not Including Vehicles (X000) | [5 empty] | 5298.5389
Allocated Contingency as % of Base Yr Dollars w/o Cont. |  |  |  |  | 16.99%
Note on J9: Please note that these cost parameters include allocated contingency.

## BASELINE Annualized
A N N U A L I Z E D C O S T - B A S E L I N E A L T E R N A T I V E | [8 empty] | (Rev.8, June 2, 2006)
Project Sponsor Name | [6 empty] | Today's Date |  | 2006-05-18
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2006
Phase | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 7% rate) [.07/1 - (1.07)^-no. yrs] | Annualized Cost (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 9000 | 2609.6991 | 1000 | 12609.6991 |  |  | 1016.1703
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 125 | 0.070015 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 9 | 9000 | 2609.6991 | 1000 | 12609.6991 | 30 | 0.080586 | 1016.1703
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.077234 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 18 | 7000 | 2029.766 | 1000 | 10029.766 |  |  | 708.2973
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 18 | 7000 | 2029.766 | 1000 | 10029.766 | 70 | 0.07062 | 708.2973
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.05 | Joint development | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 |  | 0 | 50 | 0.07246 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 |  | 0 | 30 | 0.080586 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 5000 | 1449.8328 | 200 | 6649.8328 |  |  | 481.8459
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.02 | Light Maintenance Facility |  | 5000 | 1449.8328 | 200 | 6649.8328 | 50 | 0.07246 | 481.8459
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 10100 | 2928.6623 | 200 | 13228.6623 |  |  | 995.3947
40.01 | Demolition, Clearing, Earthwork |  | 5100 | 1478.8295 | 200 | 6778.8295 | 125 | 0.070015 | 474.6188
40.02 | Site Utilities, Utility Relocation |  | 1500 | 434.9498 |  | 1934.9498 | 125 | 0.070015 | 135.4753
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.070015 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 1200 | 347.9599 |  | 1547.9599 | 125 | 0.070015 | 108.3802
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 2000 | 579.9331 |  | 2579.9331 | 20 | 0.094393 | 243.5274
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 200 | 57.9933 |  | 257.9933 | 20 | 0.094393 | 24.3527
40.08 | Temporary Facilities and other indirect costs during construction |  | 100 | 28.9967 |  | 128.9967 | 100 | 0.070081 | 9.0402
50 SYSTEMS |  |  | 2697 | 782.0398 | 0 | 3479.0398 |  |  | 293.6794
50.01 | Train control and signals |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
50.02 | Traffic signals and crossing protection |  | 1325 | 384.2057 |  | 1709.2057 | 30 | 0.080586 | 137.7387
50.03 | Traction power supply: substations |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
50.04 | Traction power distribution: catenary and third rail |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
50.05 | Communications |  | 672 | 194.8575 |  | 866.8575 | 20 | 0.094393 | 81.8252
50.06 | Fare collection system and equipment |  | 200 | 57.9933 |  | 257.9933 | 25 | 0.085811 | 22.1385
50.07 | Central Control |  | 500 | 144.9833 |  | 644.9833 | 30 | 0.080586 | 51.9769
Construction Subtotal (10 - 50) |  |  | 33797 | 9800 | 2400 | 45997 |  |  | 3495.3876
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 1200 |  | 0 | 1200 |  |  | 84.0178
60.01 | Purchase or lease of real estate |  | 1200 |  |  | 1200 | 125 | 0.070015 | 84.0178
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.070015 | 0
70 VEHICLES (number) |  | 20 | 13000 |  | 490 | 13490 |  |  | 1698.4178
70.01 | Light Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.04 | Bus | 20 | 13000 |  | 490 | 13490 | 12 | 0.1259 | 1698.4178
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
80 PROFESSIONAL SERVICES |  |  | 9800
80.01 | Preliminary Engineering |  | 2000
80.02 | Final Design |  | 3500
80.03 | Project Management for Design and Construction |  | 2000
80.04 | Construction Administration & Management |  | 1500
80.05 | Insurance |  | 500
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 150
80.08 | Start up |  | 150
Subtotal (10 - 80) |  |  | 57797
90 UNALLOCATED CONTINGENCY |  |  | 2889.85
Subtotal (10 - 90) |  |  | 60686.85 | 9800 | 2890 | 60687 |  |  | 5277.8232
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.
Note on H8: Useful Life changes shown in blue.

## By-Segment
Major Capital Project Costs - By Segment |  |  | (Rev.8, June 2, 2006)
Project | (please insert your project name) |  | Today's Date
Location | (insert location) |  | Yr of Base Year Dollars
Project ID | 0
Number of Route Miles in the Segment |  |  | Number of Stations
Segment No. ___ of ___ (attach plan of segment and typical sections through segment, along with cost estimate per typical section)
|  | Low costs in Base Yr (X$000) for potential cost savings* | "Most Likely" cost estimate in Base Yr (X$000) | High costs in Base Yr Dollars (X$000) for potential cost increases*
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 | 0 | 0
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 | 0 | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS |  | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0 | 0 | 0
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
TOTAL SEGMENT COST |  | 0 | 0 | 0
* Describe the risks, uncertainties, and opportunities associated with this segment, that prompted the inclusion of a low or high cost, in addition to a "most likely cost" for particular line items. |  |  | Using costs from this column, total all segments and insert into Main Worksheet Base Yr Dollars Total (X$000)

## Project-wide
Major Capital Project Costs - Project-wide |  |  | (Rev.8, June 2, 2006)
Project | (please insert your project name) |  | Today's Date
Location | (insert location) |  | Yr of Base Year Dollars
Project ID | 0
Total Number of Route Miles in Project |  |  | Number of Stations
Project-wide Costs
|  | Low costs in Base Yr (X$000) for potential cost savings* | "Most Likely" cost estimate in Base Yr (X$000) | High costs in Base Yr Dollars (X$000) for potential cost increases*
50 SYSTEMS |  | 0 | 0 | 0
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
70 VEHICLES (number) |  | 0 | 0 | 0
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES |  | 0 | 0 | 0
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES
TOTAL PROJECT-WIDE COST |  | 0 | 0 | 0
* Describe the risks, uncertainties, and opportunities associated with this segment, that prompted the inclusion of a low or high cost, in addition to a "most likely cost" for particular line items. |  |  | Insert costs from this column into Main Worksheet Base Yr Dollars Total (X$000)

## A3T1
Table 1 - BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 129846.5014
10.01 | Guideway: At-grade exclusive right-of-way | 129846.5014
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0
10.03 | Guideway: At-grade in mixed traffic | 0
10.04 | Guideway: Aerial structure | 0
10.05 | Guideway: Built-up fill | 0
10.06 | Guideway: Underground cut & cover | 0
10.07 | Guideway: Underground tunnel | 0
10.08 | Guideway: Retained cut or fill | 0
10.09 | Track: Direct fixation | 0
10.1 | Track: Embedded | 0
10.11 | Track: Ballasted | 0
10.12 | Track: Special (switches, turnouts) | 0
10.13 | Track: Vibration and noise dampening | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 141226.7383
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 141226.7383
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0
20.05 | Joint development | 0
20.06 | Automobile parking multi-story structure | 0
20.07 | Elevators, escalators | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 14309.752
30.01 | Administration Building: Office, sales, storage, revenue counting | 0
30.02 | Light Maintenance Facility | 14309.752
30.03 | Heavy Maintenance Facility | 0
30.04 | Storage or Maintenance of Way Building | 0
30.05 | Yard and Yard Track | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 21587.2626
40.01 | Demolition, Clearing, Earthwork | 660.8346
40.02 | Site Utilities, Utility Relocation | 5506.9547
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 3304.1728
40.05 | Site structures including retaining walls, sound walls | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 12115.3004
40.07 | Automobile, bus, van accessways including roads, parking lots | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0
50 SYSTEMS |  | 28543.2322
50.01 | Train control and signals | 10703.7121
50.02 | Traffic signals and crossing protection | 3567.904
50.03 | Traction power supply: substations | 5946.5067
50.04 | Traction power distribution: catenary and third rail | 5946.5067
50.05 | Communications | 1189.3013
50.06 | Fare collection system and equipment | 1189.3013
50.07 | Central Control | 0
Construction Subtotal (10 - 50) |  | 335513.4864
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 24348.5564
60.01 | Purchase or lease of real estate | 24348.5564
60.02 | Relocation of existing households and businesses | 0
70 VEHICLES (number) |  | 34987.9315
70.01 | Light Rail | 34987.9315
70.02 | Heavy Rail | 0
70.03 | Commuter Rail | 0
70.04 | Bus | 0
70.05 | Other | 0
70.06 | Non-revenue vehicles | 0
70.07 | Spare parts | 0
80 PROFESSIONAL SERVICES |  | 92741.9141
80.01 | Preliminary Engineering | 16463.0617
80.02 | Final Design | 21950.7489
80.03 | Project Management for Design and Construction | 13170.4493
80.04 | Construction Administration & Management | 13170.4493
80.05 | Insurance | 4938.9185
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 4390.1498
80.07 | Surveys, Testing, Investigation, Inspection | 4390.1498
80.08 | Start up | 14267.9868
Subtotal (10 - 80) |  | 487591.8884
90 UNALLOCATED CONTINGENCY |  | 24494.9672
Subtotal (10 - 90) |  | 512086.8556
100 FINANCE CHARGES |  | 500
Total Project Cost (10 - 100) |  | 512586.8556

## A3T2
Table 2 - Inflated BCE
| Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Inflation Factor | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 100000 | 12000 | 112000 | 1.1593 | 129846.5014
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 100000 | 20000 | 120000 | 1.1769 | 141226.7383
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10000 | 2000 | 12000 | 1.1925 | 14309.752
40 SITEWORK & SPECIAL CONDITIONS | 16800 | 2800 | 19600 | 1.1014 | 21587.2626
50 SYSTEMS | 20300 | 3700 | 24000 | 1.1893 | 28543.2322
60 ROW, LAND, EXISTING IMPROVEMENTS | 17000 | 4000 | 21000 | 1.1595 | 24348.5564
70 VEHICLES (number) | 22000 | 8000 | 30000 | 1.1663 | 34987.9315
80 PROFESSIONAL SERVICES | 65500 | 19000 | 84500 | 1.0975 | 92741.9141
90 UNALLOCATED CONTINGENCY |  |  | 21155 | 1.1579 | 24494.9672
100 FINANCE CHARGES |  |  | 440.4067 | 1.1353 | 500
Total Project Cost (10 - 100) |  |  | 444695.4067 | 1.1527 | 512586.8556

## A3T3
Table 3 - BCE by Source of Funding
| Total Project Cost in YOE Dollars (X000) | Federal 5309 New Starts | Federal 5307 | Federal CMAQ | Federal Other | Local Funds
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 129846.5014 | 1847 | 0 | 0 | 14000 | 114000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 141226.7383 | 70000 | 0 | 0 | 35000 | 36227
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 14309.752 | 10000 | 0 | 0 | 2000 | 2310
40 SITEWORK & SPECIAL CONDITIONS | 21587.2626 | 20000 | 0 | 0 | 0 | 1587
50 SYSTEMS | 28543.2322 | 543 | 0 | 16800 | 0 | 11200
60 ROW, LAND, EXISTING IMPROVEMENTS | 24348.5564 | 4349 | 0 | 0 | 0 | 20000
70 VEHICLES (number) | 34987.9315 | 34000 | 0 | 0 | 0 | 988
80 PROFESSIONAL SERVICES | 92741.9141 | 2742 | 72000 | 0 | 0 | 18000
90 UNALLOCATED CONTINGENCY | 24494.9672 | 495 | 0 | 0 | 2000 | 22000
100 FINANCE CHARGES | 500 | 500 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 512586.8556 | 144476 | 72000 | 16800 | 53000 | 226312
Table 4 - Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds (X000) | Federal/Local Matching Ratio within Source | Federal Funds (X000) | Local Funds (X000)
Federal 5309 New Starts | 288588 | 50/50 | 144476 | 144112
Federal 5307 | 90000 | 80/20 | 72000 | 18000
Federal CMAQ | 28000 | 60/40 | 16800 | 11200
Federal Other | 106000 | 50/50 | 53000 | 53000
Total | 512588 |  | 286276 | 226312
Overall Federal Share of Project |  |  | 55.85%
New Starts Share of Project |  |  | 28.19%

## A3A
[6 empty] | Federal 5309 New Starts |  |  | Federal 5307 |  |  | Federal CMAQ |  |  | Federal Other
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty | YOE Cost (X000) | Total Federal % | Federal 5309 New Starts | Local | Total | Federal 5307 | Local | Total | Federal CMAQ | Local | Total | Federal Other | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 9 | 129846.5014 | 12.2% | 1847 | 100000 | 101847 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 14000 | 28000
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 18 | 141226.7383 | 74.35% | 70000 | 1227 | 71227 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 70000
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | 14309.752 | 83.86% | 10000 | 310 | 10310 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | 21587.2626 | 92.65% | 20000 | 1587 | 21587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14050 | 140550 | SYSTEMS |  | 28543.2322 | 60.76% | 543 | 0 | 543 | 0 | 0 | 0 | 16800 | 11200 | 28000 | 0 | 0 | 0
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | 24348.5564 | 17.86% | 4349 | 20000 | 24349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14070 |  | VEHICLES | 10 | 34987.9315 | 97.18% | 34000 | 988 | 34988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
refer to TEAM Scopes ALIs Worksheet | 13.13.20 | Light Rail Cars | 10 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 13.__.__ | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 13.__.__ | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 13.__.__ | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 13.__.__ | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
14080 | 140880 | PROFESSIONAL SERVICES |  | 92741.9141 | 80.59% | 2742 | 0 | 2742 | 72000 | 18000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0
14090 | 140990 | UNALLOCATED CONTINGENCY |  | 24494.9672 | 10.19% | 495 | 20000 | 20495 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000
14100 | 141010 | FINANCE CHARGES |  | 500 | 100% | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) |  |  |  | 512586.8556 | 55.85% | 144476 | 144112 | 288588 | 72000 | 18000 | 90000 | 16800 | 11200 | 28000 | 53000 | 53000 | 106000

## A4
| Start Date | End Date | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 2008-09-01 | 2012-01-01
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 2008-09-01 | 2012-01-01
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 2008-09-01 | 2012-01-01
40 SITEWORK & SPECIAL CONDITIONS | 2008-09-01 | 2012-01-01
50 SYSTEMS | 2008-09-01 | 2012-01-01
60 ROW, LAND, EXISTING IMPROVEMENTS | 2008-09-01 | 2009-09-01
70 VEHICLES (number) | 2008-09-01 | 2012-01-01
80 PROFESSIONAL SERVICES | 2003-01-01 | 2012-01-01
90 UNALLOCATED CONTINGENCY | 2008-09-01 | 2012-01-01
100 FINANCE CHARGES | 2008-09-01 | 2012-01-01
Revenue Operations | 2012-01-01
Before and After Study: Two years post Rev Ops |  | 2014-03-01
Fulfillment of the New Starts funding commitment |  | 2012-09-01
Completion of project, close-out, resolution of claims |  | 2014-03-01