## Sheet1
Cost Estimate for the Installation of the HFBR Refrigerator for E951
Revision "A" 10/23/02
M. Iarocci
|  | Unburdened | Unburdened | Unburdened | Item Total | *FY 2002 $'s
|  | Capital * | PE Labor * | Labor * | Burdened *,1 | Note 1- See rate assumptions below
Item # | Task Description | Cost K$'s | Cost K$'s | Cost K$'s | Cost K$'s
I | Cryogenic Inst and Ctrls
I-A | Transient Mode Controls | 12 |  | 2
I-B | Replace missing refrigerator temperature controls | 5
I-C | Remove and reconnect all component control wiring |  |  | 3
I-E | Cable Tray and Installation |  | 3
| Burdened Subtotal | 24.99 | 4.14 | 9.35
38.48
II | Cryogenic Supply, Return, and CD Return Lines
II-A | Modify and Install Supply, Return, Return Transfer Lines, Mag to Ref. | 6 | 3 | 3
II-B | Supports for Transfer Lines | 4
II-C | Labor for X-fer removal at HFBR | 1
| Burdened Subtotal | 16.17 | 4.14 | 5.61
25.92
III | Refrigerator and Interface Valve Box
III-A | Modify Interface Box for continuous transient cooldown mode | 30 | 2 | 4
III-B | Refrigerator | 0
III-C | Disconnect at HFBR |  | 0.5 | 1
III-D | Rigging and Position at AGS | 1 | 2.2
III-E | Reconnect Basic Components at AGS |  |  | 3
| Burdened Subtotal | 45.57 | 6.486 | 14.96
67.016
IV | Helium Compression, Storage, Recovery.
IV-A | GHe Storage (1 tank), disconnect, move, and reinstall | 0 | 3 | 0.25
IV-B | Misc. Process Piping and installation | 0 |  | 1
IV-C | Misc. Equip., Vac Pump, Air Compressor, Air Drier, etc. | 2 | 1 | 0.5
IV-D | Helium Compressor | 0
IV-E | Footings/ Oil Containment for Helium Compressor | 0.5 | 5
IV-F | Remove (Tech+Elect), Transport (rigging), and Relocate Compressor Skid |  | 3 | 1
IV-G | Warm Compressor Piping to Refrigerator (welding, supports, tech, leakcheck) | 1 | 6.5 | 2
IV-H | Cooling Water Piping/ Closed Loop Exchanger (disconnect, relocated at AGS, reconnect) | 2 | 1 | 2
| Burdened Subtotal | 8.085 | 26.91 | 12.6225
47.6175
V | Project Management for Conceptual Hardware Definition, Scheduling, Cost Estimates, Etc., and Cryogenic Engineering Support
V-A | Project Leader/ engineer ( 8 months.)(Part Time) |  |  | 16
| Burdened Subtotal | 0 | 0 | 29.92
29.92
VI | AC Power to Cryogenic Equipment
VI-A | High Voltage Eq. & Feeds | 50
VI-B | Transformer | 40
VI-C | Low Voltage Eq. & Feeds | 35
VI-D | Misc Lighting, Grounding, Power | 30
VI-E | Outside AC Receptacles & Lighting | 10
| Burdened Subtotal | 242.55 | 0 | 0
242.55
|  | Unburdened | Unburdened | Unburdened | Item Total
|  | Capital * | PE Labor * | Labor * | Burdened *,1
Item # | Task Description | Cost K$'s | Cost K$'s | Cost K$'s | Cost K$'s
VII | Concrete Footings
VII-A | Helium Storage Tank Footing | 8
VII-B | Slabs for AC Equip. | 40
| Burdened Subtotal | 70.56 | 0 | 0
70.56
VIII | Enhance Equipment Building (for compressor)
VIII-A | Clean and refurbish building area for compressor installation | 25
VIII-B | Misc. Equip. Bldg.,ODH alarm, fans, etc. | 30
| Burdened Subtotal | 80.85 | 0 | 0
80.85
IX | Operation (1 month-24 hrs/day)
IX-A | Technician |  |  | 15
IX-B | Engineering Yr.. 3-5 (1/3 FTE) |  |  | 1
IX-D | Elec Pwr 30 days (600 HP @ $ .06/ kW-hr.) | 19.3
| Burdened Subtotal | 28.371 | 0 | 29.92
58.291
X | Helium Inventory
X-A | Resident Helium (initial charge) for normal ops | 0.5
X-B | Helium Loss Replacement | 0.5
| Burdened Subtotal | 1.47 | 0 | 0
1.47
Summary:
| Total Unburdened Materials= | 352.8
| Total Burdened Materials= | 518.616
| Total Unburdened DTS= |  | 30.2
| Total Burdened DTS= |  | 41.676
| Total Unburdened Labor= |  |  | 22.75
| Total Burdened Labor= |  |  | 72.4625
| Total Unburdened Operation= |  |  |  | 36.3
| Total Burdened Operation= |  |  |  | 59.761
| Unburdened Total Installation Cost= | 405.75
| Burdened Total Installation Cost= | 632.7545
| Total Unburdened Operation= | 36.3
| Total Burdened Operation= | 59.761
| ** "This cost estimate represents a best judgement based upon laboratory experience in FY 2002 dollars. Appropriate Laboratory burdens and overheads have been applied based upon FY 2002 prevailing rates. Escalation factors, burden and overheads are established each fiscal year and charged. These rates are subject to change." |  |  |  |  | Note 2- The spreadsheet shows burdened and unburdened costs for labor, materials, and DTS. The BNL labor is based upon the employees salary marked up by 187% Material burden for purchases >$25K is marked up by 117.5% and <25K by 147%. PE rates are assumed at $70/hr (burden included). BNL technical, engineering, and scientific unburdened hourly wages are assumed at $25, $33, and $42 per hour respectively.