SCOPE OF SERVICES

“Coulee Baton Micro Watershed Rural Sewer System Improvement Project”

Between the Louisiana Department of Environmental Quality

And the

Acadiana Resource Conservation and Development Council

Introduction

Louisiana passed a law in 2000 requiring all septic systems to have an approved Effluent Reduction System (ERS).  The new law allows for six different ERS types but the most common is absorption field lines.  A common misconception of the homeowner is that because they have never had a blockage or odor problem that their system is functioning properly.  However, all of the soils in the micro watershed have severe limitations with wetness and slow percolation limiting the effectiveness of absorption field lines. In addition to poor soils, over 90% of the homes in the micro watershed are more than 20 years old with inadequate secondary treatment.  A preliminary survey of the micro watershed found that 55 of the 110 homes discharge directly into a public ditch with no secondary treatment of sewage.  Rural communities with aged septic systems are known to be a significant contributor to nonpoint source pollution.  A failing septic system can discharge more than 75,000 gallons of untreated wastewater into ground and surface waters a year.

A major limitation for the micro watershed is assistance for homeowners with potentially failing rural sewage systems. The Acadiana Resource Conservation and Development Council, along with other partnering agencies, propose to develop a three phase project that will:1)demonstrate properly functioning effluent reduction systems 2)provide a cost share component for replacement and repair of aged and or failing syestems for homeowners and 3)implement an educational and outreach program that will highlight proper maintenance of systems, and an explanation of how the systems work, in hopes the homeowners will make better decisions about system maintenance and replacement.

Specific Goals and Objectives

The goal of this project is to address many of the issues and concerns addressed in the Louisiana’s Nonpoint Source Management Plan for 2000 in the Statewide Educational Programs – Home Sewage Systems Section.

- Homeowner education (page 105) will be accomplished with field days, educational talks and town hall meetings.

- Innovative Technologies (page 107) will be accomplished with the effluent reduction system demonstration.

- Improving water quality (page 104) will be addressed through the cost share program to replace aged and failing septic systems.

- Building partnerships with state and federal agencies and non profits (page 108) will be promoted by the 12 cooperating state, federal and non profit organizations working with the Coulee Baton Micro Watershed.

Deliverables

The Acadiana Resource Conservation and Development Council agrees to develop information packets which will announce the Sewer System Improvement Project to potential participants.  A town hall meeting will be held within the micro watershed within 60 days of project initiation to discuss project parameters, demonstration goals and to outline the cost share program procedures. From the town hall meeting, participating homeowners will be identified and a minimum of 3 representative home septic systems will be selected for the effluent reduction demonstration program. Field days will be conducted to demonstrate properly installed and functioning systems, which will be followed by a detailed survey to determine the type and condition of the homeowners current system.  Presentations will also be given on the proper maintenance of systems; an explanation of how systems work; and how homeowners can help them make better decisions about system maintenance and replacement.  After new systems have been demonstrated, the homeowner cost share program will begin. Partnering with local homeowners and with the Vermilion Soil and Water Conservation District, a total match of $207,078 will be available to accomplish this project. A maximum cost share of 60% will be given for the replacement of up to 110 home sewage systems.  The homeowner will provide 40% cash match for the installation of their new system.  This is a voluntary program for homeowners, and although all homeowners will be asked to participate in the program, it is unlikely that 100% participation will be possible due to financial status of homeowners, homes with properly running systems or homes which have recently been repaired or replaced. The Acadiana RC&D Council will communicate with LDEQ on all aspects of the project during the course of the contract term. Quarterly reports, annual reports, invoices and deliverables are to be submitted in a timely manner.  Upon completion of the project, a final report detailing the accomplishments, highlights, and findings learned throughout project implementation are to be submitted.

Monitoring Plan

The LDEQ Project Manager will be responsible for determining if the contractor is making progress by inspecting the project site, and also by ensuring the time line of services is adhered to. Maintaining contact with the contractor is imperative, and may be done so through the use of email, mail, fax, or telephone. The Department also requires the contractor to submit quarterly reports and also annual reports for all activities accomplished during those reporting periods.  A final report is to be submitted highlighting accomplishments, obstacles, and findings, once the project is completed.  All work should be completed in a timely matter.

Project Start and End Date

This project will begin 14 days once final approval is given, and will be completed by July 2009.  The following tentative schedule of activities will be followed:

June 2008 		Town Hall Meeting-Community Involvement

August 2008		Effluent Reduction System Selection and Installation

October 2008		Field Day of new demonstration systems

December 2008	Homeowner Cost Share Program

July 2009		Final Report

#### Project Element 1 – Outreach and Education

Task 1.1:

Town Hall Meeting-Community Involvement

A major component of this project is outreach and education. All residents within the micro watershed will be able to participate in a town hall meeting where project parameters will be discussed.  Town hall meetings create environments where all partnering agencies and organizations can interact with the homeowners and can provide needed information and assistance in a non threatening way.

Deliverable: A detailed survey will be conducted with the homeowner to determine the type and condition of the current system.  A town hall meeting will be held within the micro watershed within 60 days of project initiation to discuss project parameters, demonstration goals and to outline the cost share program procedures.

Schedule: 	Months 1 – 2

Payment: 	Federal: $3,221 	Match: $2,645		Total: $5,866

Project Element 2 – Effluent Reduction Demonstration Systems

Task 2.1:

Effluent Reduction Selection

From the survey results and town hall meetings, participating homeowners will be identified and a minimum of 3 representative home septic systems will be selected for the effluent reduction demonstration program.

Deliverable: These new systems will demonstrate the effective use of a Rock Plant Filter, Spray Irrigation and or Gravel Filtration Beds.  The type of demonstration system used will be determined by soil type, space limitations and home owner preference.  The systems will be installed following Louisiana Administrative Code Title 51 by certified installers.

Schedule: 	Months 3 – 6

Payment: 	Federal: $20,687 	Match: $8,127		Total: $28,814

Task 2.2:

Field Day

These demonstration systems will have an education and outreach component.  A field day will be held to demonstrate properly installed and functioning systems.  The field day will be open to the public with the targeted audience being the state agencies involved with sewage system oversight, private installers of septic systems and homeowners from the surrounding watersheds.

Deliverable: At this field day presentations will be given on proper maintenance of systems, explanation of how systems work, and how homeowners can make better decisions about system maintenance and replacement.  Presentations will use the Home Sewer Awareness toolkit for the following topics: “Saving Money by Maintaining Your Home Sewer System”, “Why Do Home Sewer Systems Fail?”, and “The Hazards of Failing Home Sewer Systems.” Demonstrating properly functioning effluent reduction systems will help alleviate the current misconceptions of these systems.  They will also allow homeowners and private installers to see the systems in place and obtain needed knowledge to install permitted sewer systems across the state.

Schedule: Months 5-9

Payment: 	Federal: $4,021 	Match: $3,174		Total: $7,195

Project Element 3 – System Replacement Cost Share Program

Task 3.1:

Homeowner Cost Share Program

After new systems have been demonstrated, the homeowner cost share program will begin.  Once the program is announced and advertised the application period will be open for 60 days.  Homeowners will complete a pre- application with the Vermilion SWCD.  Pre applications will be ranked based on age of system, type of discharge system currently used, and potential volume contributed to the micro watershed.  The ranking criteria and application will be developed once the project is funded.  A SWCD employee will assist the homeowners in gathering the needed information to receive a permit from the Louisiana Department of Health and Hospitals.  Homeowners will then follow proper procedures and obtain all necessary permits.

Deliverable: Once permits are completed, a maximum cost share of 60% will be given for the replacement of a minimum of 10 home sewage systems.  The homeowner will provide 40% cash match for the installation of their new system.  A certified installer will be used for all new systems.

Schedule: 	Months 7-14

Payment: 	Federal: $264,000 	Match: $182,632	  Total: $446,632

*Note: For this task only, invoices may be submitted monthly for reimbursement

#### Project Element 4- Quarterly Reports, Annual Reports and Final Report

The Acadiana RC&D Council will communicate with LDEQ on all aspects of the project during the course of the contract term. Quarterly reports, annual reports, invoices and deliverables are to be submitted in a timely manner.

Task 4.1:

Quarterly Reports

Quarterly monitoring reports which include narrative documentation of all project activities and results will be submitted to LDEQ.  Accompanying deliverables, as required by individual tasks upon their completion, shall accompany monitoring reports.  Comprehensive analysis and interpretation of project results will be included in the monitoring reports as available.  Invoices must also accompany these monitoring reports.

Deliverables: Monitoring reports, with attached deliverables, which detail progress to date will be submitted throughout the duration of the project and will specify any problems or issues encountered during the course of the project.

Federal Payment: Payment provided by task accomplished (See Table 1. Schedule and Cost by Task).

Schedule:  Draft monitoring reports are due the 10th of the month following each calendar quarter (Jan. 10th, Apr. 10th, Jul. 10th, and Oct. 10th) for all quarters until the final report is submitted to EPA or the contract term period expires.  Draft monitoring reports can be submitted via electronic submission.  Acceptable forms of electronic submission are MS Word or MS Excel accompanied by a PDF version of that quarterly report.  Electronic submittal templates will be provided by the LDEQ project officer.

In addition, final monitoring reports including an invoice/request for payment are due via hard copy by the 30th of each month following each calendar quarter (Jan. 30th, Apr. 30th, Jul. 30th, and Oct. 30th) for all quarters until the final report is submitted to EPA or the contract term period expires.

Payment: 	Federal: $0 	Match: $3,500		Total: $3,500

Task 4.2:

Annual Report

An annual report will be submitted to LDEQ documenting all project activities during the corresponding federal fiscal year (Oct.1 – Sept. 30).  These reports will show the results achieved and the impact of BMPs on water quality.  Previously submitted deliverables may be referenced rather than included in the annual report.  In addition, cooperator is required to present the progression of their project at the LDEQ in Baton Rouge during the Section 319 annual project review session in November.

Deliverables: Annual reports will document the results of project accomplishments during that federal fiscal year.  The annual report to LDEQ should be an analysis of results, as applicable, rather than a description of activities, and cooperator will make a presentation to the LDEQ on project progress/status in November.

Federal Payment: Payment provided by task accomplished (See Table 1 Schedule and Cost by Task).

Schedule: (1) Annual reports are due by October 30th following the end of the reporting period.  (2) Section 319 Project Review Session - Beginning second (2nd) Wednesday and Thursday of November, 2008, and each second (2nd) Wednesday and Thursday of November thereafter until the draft final report is submitted to EPA.

Payment: 	Federal: $0 	Match: $3,500		Total: $3,500

Task 4.3:

Final Report

Develop and submit a final report upon completion of the project to LDEQ and eventual EPA approval. Upon incorporation of LDEQ revisions to the draft final, triplicate copies of the final report and all deliverables shall be submitted to LDEQ.

Deliverables:  The Final project report will detail the accomplishments, highlights, and findings learned throughout project implementation. Provide final report to LDEQ and EPA for review, comment, and approval. Once the report is EPA approved, provide a digital copy and hard copy of the document.

Federal Payment: $12,500  	Match: $3,500		Total: $16,000

NOTE:  Ten Percent (10%) of the federal funds contracted will be retained until the final report is completed and has been accepted by DEQ and EPA.

Schedule: Months 15-16. Final report draft is due and must be submitted within 60 days prior to the contract end date.  Failure to meet this requirement will be considered an incompletion of task during contract term period and will result in a 3% deduction of the federal funds contracted from the final payment.

Final report addressing all comments, concerns, and revisions must be approved by LDEQ and EPA before this task can be considered complete and final payment of federal funds can be paid to the cooperator.

Table 1.  Schedule and Cost by Task

| Task | Description | Federal | Match | Total | Schedule |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Town Hall Meeting- Community Involvement | $3,221 | $2,645 | $5,866 | Months 1-2 |
| 2.1 | Effluent Reduction Selection | $20,687 | $8,127 | $28,814 | Months 3-6 |
| 2.2 | Field Day | $4,021 | $3,174 | $7,195 | Months 5-9 |
| 3.1 | Homeowner Cost Share Program | $264,000 | $182,632 | $446,632 | Months 7-14 |
| 4.1 | Quarterly Reports | $0 | $3,500 | $3,500 | Due the month following each quarter |
| 4.2 | Annual Report | $0 | $3,500 | $3,500 | Due October of each year during project period |
| 4.3 | Final Report | $12,500 | $3,500 | $16,000 | Months 15-16 |

Totals			    $304,429    $207,078   $511,507

Table 2.  Budget by Category

Budget Justification

Personnel				Federal: $25,929		Match: $19,073

The Acadiana RC&D Council will provide a project coordinator to oversee all aspects of grant coordination between partners and LDEQ.  The Council will also have an administrative assistant working on budget, billing and fiscal management.  The Vermilion SWCD will also provide an administrative assistant to assist with the cost share program and assist homeowners with the protocols for installation of septic systems.  Both the Council and SWCD will utilize volunteer board members to serve as match and to assist with outreach and field day activities.

Fringe Benefits			Federal: $0			Match: $5,720

Fringe benefits are calculated as 26.5% of salaries

Materials and Supplies		Federal: $270,000		Match: $172,000

Three (3) systems will be installed during the effluent reduction demonstration portion of this project.  Each system will cost $4,500 and they will be installed at no cost to the homeowner. $2,500 will be used to procure native wetland plant material and to cover other cost associated with these atypical systems.  One Hundred and Ten (110) homes will be targeted for the installation of new home septic systems during the homeowner participation portion of this project.  Each system will cost an average of $3,750 installed by a licensed contractor.  This cost includes removal and disposal of old system.  Each homeowner will pay 40% of this installation cost.

Outreach and Field Days 		Federal: $8,500		Match: $3,849

Homeowner and septic system installers involvement is key to the success of this project.  This will be achieved through technology transfer, field days, town hall meetings and public presentations.  In kind match will include travel and time to prepare information for these events.

Federal funds will not be utilized for travel expenses.

Indirect Cost			Federal: $0.00		Match: $12,156

Indirect cost will include telephone, computer usage, supplies, printers, printing, paper supplies, postage, duplication services, renting of facilities, and liability insurance cost for events.

Match

The Acadiana Resource Conservation and Development Council and the Vermilion Soil and Water Conservation District with local homeowners will provide $207,078 in matching funds for the project.

Table 3. Matching Funds

| Matching Funds (40%) | 2008 | 2009 | Total |
| --- | --- | --- | --- |
| Acadiana RC&D Council Inc. | 9,768 | 8,750 | 18,518 |
| Vermilion SWCD | 5,250 | 11,310 | 16,560 |
| Homeowner/Stakeholder Match | 86,000 | 86,000 | 172,000 |
| Total Matching Funds | 101,018 | 106,060 | 207,078 |

Requested Funds

The Acadiana Resource Conservation and Development Council is requesting $304,429 to complete the Coulee Baton Micro Watershed Rural Sewer System Improvement Project.  Partnering with local homeowners and with the Vermilion Soil and Water Conservation District a total match of $207,078 will be available to accomplish this project.  Total budget for this project is $511,507.