## Instructions
The Integrated HLP
The Integrated High Level Plan brings together all the Products and Program areas within the CORE Workspace. In addition to providing structure and a means for communicating our successes and best practices, the HLP will also be an engine for driving scope accross CORE. This workbook contains the Detailed Plan and the Dependencies tab(s).
Tracking Dependencies
Tracking dependencies in the HLP is quick and easy. 1. Simply put the item number of the dependant task you want to link your task to in the 'Deps' column. 2. If no other changes need to be made, Hit the 'Process Dependencies' Button 3. If a Dependencies Tab already exists, all data will be overwritten, if the tab does not exist, then a new tab will be added marked 'Dependencies' 4. If a Dependency is linked and has crossed its target date, it will show up on the list of items that are at Risk. 5. Review the Dependencies Tab with the newly created line items and dates reflected.
Adding/Removing Tasks
Adding/Removing tasks in the HLP easy, while there are a couple of things you should be aware of when doing so: 1. When Adding a new task always make sure to following the number scheme in the 'Tasks' column 2. Take time to accurately create the linkage between tasks. 3. Make sure that the End Date is not Before the Start Date 4. Make sure to fill in 'Key' Column appropriately so that tasks can be tied to the (RUP Menthodology and appear color coordinated) 5. When removing a task, Please make sure to select the entire row and hit Right Click and then Delete. 6. When removing a task, aslways make sure that dependencies are delinked, this may cause errors in reporting and result in inaccurate reports.
Key
The Key below shows the different categories which a task could be added under. Always mark a task to its appropriate category.
Color Coordination on the timelines is driven by the Start, End and the Key Columns.
| H | Heading | (Only to be used at the Highest Level)
| I | Inception
| E | Elaboration
| C | Construction
| T | Transition
| M | Milestone

## Dependencies
Task Item: 3.162 is dependant upon task: 3.161 with an End date of: 11/7/2008 5:00:00 PM is currently at Risk.
Task Item: 5.03 is dependant upon task: 5.04 with an End date of: 11/10/2008 is currently at Risk.
Task Item: 5.04 is dependant upon task: 5.06 with an End date of: 10/20/2008 is currently at Risk.
Task Item: 5.05 is dependant upon task: 5.04 with an End date of: 11/10/2008 is currently at Risk.
Task Item: 5.07 is dependant upon task: 5.04 with an End date of: 10/17/2008 is currently at Risk.
Task Item: 7.100 is dependant upon task: 7.99 with an End date of: 10/30/2008 5:00:00 PM is currently at Risk.
Task Item: 7.25 is dependant upon task: 7.24 with an End date of: 7/8/2008 5:00:00 PM is currently at Risk.
Task Item: 7.31 is dependant upon task: 7.30 with an End date of: 7/16/2008 5:00:00 PM is currently at Risk.
Task Item: 7.32 is dependant upon task: 7.30 with an End date of: 7/16/2008 5:00:00 PM is currently at Risk.
Task Item: 7.93 is dependant upon task: 7.92 with an End date of: 10/3/2008 2:20:00 PM is currently at Risk.
Task Item: 7.94 is dependant upon task: 7.92 with an End date of: 10/3/2008 2:20:00 PM is currently at Risk.
Task Item: 7.95 is dependant upon task: 7.93 with an End date of: 10/6/2008 2:20:00 PM is currently at Risk.
Task Item: 7.97 is dependant upon task: 7.96 with an End date of: 10/21/2008 10:40:00 AM is currently at Risk.
Task Item: 7.98 is dependant upon task: 7.97 with an End date of: 10/22/2008 2:20:00 PM is currently at Risk.
******* Scanned Through ALL Rows in the Detailed Plan. Exiting! *******

## Detailed Plan
******* Scanned Through ALL Rows in the Detailed Plan. Dependency: 5.12, was not imported from a Project Plan! Continuing*******
CORE Program - Detailed Plan
[9 empty] | July |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April
[5 empty] | Start | Due | Completed
| Task | Deps. | Tasks | Key | Date | Date | Date | Status | 2008-07-14 | 2008-07-21 | 2008-07-28 | 2008-08-04 | 2008-08-11 | 2008-08-18 | 2008-08-25 | 2008-09-01 | 2008-09-08 | 2008-09-15 | 2008-09-22 | 2008-09-29 | 2008-10-06 | 2008-10-13 | 2008-10-20 | 2008-10-27 | 2008-11-03 | 2008-11-10 | 2008-11-17 | 2008-11-24 | 2008-12-01 | 2008-12-08 | 2008-12-15 | 2008-12-22 | 2008-12-29 | 2009-01-05 | 2009-01-12 | 2009-01-19 | 2009-01-26 | 2009-02-02 | 2009-02-09 | 2009-02-16 | 2009-02-23 | 2009-03-02 | 2009-03-09 | 2009-03-16 | 2009-03-23 | 2009-03-30 | 2009-04-06 | 2009-04-13 | 2009-04-20 | 2009-04-27 | 2009-05-04 | 2009-05-11 | 2009-05-18 | 2009-05-25 | 2009-06-01 | 2009-06-08 | 2009-06-15 | 2009-06-22 | 2009-06-29
R
|  |  | CORE Integration Detailed Plan | H | 2008-03-03 08:00 | 2009-05-26 17:00 |  | G | [45 empty] | 2009-05-26 17:00
| 1 |  | caDSR
| 1.45 |  | CDE Browser 4.0.0.1 (Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.47 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.51 | 1.47 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.53 | 1.51 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.54 | 1.53F | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.56 | 1.54 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.58 | 1.57 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.64 | 1.62 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.66 | 1.64 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.71 | 1.70 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.73 | 1.72 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.77 | 1.75 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.80 | 1.79 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 1.84 |  | UML Model Browser 4.0.0.1 (Template) | H | 2008-10-06 08:00 | 2008-12-23 17:00 |  | G | [23 empty] | 2008-12-23 17:00
| 1.86 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.90 | 1.86 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.92 | 1.90 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.93 | 1.92F | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.95 | 1.62 | Develop Software (timebox) | C | 2008-11-05 08:00 | 2008-11-19 17:00 |  | G | [18 empty] | 2008-11-19 17:00
| 1.97 | 1.96 | Construction Complete | M | 2008-11-19 17:00 | 2008-11-19 17:00 |  | G | [18 empty] | 2008-11-19 17:00
| 1.103 | 1.101 | Conduct QA testing | T | 2008-11-21 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.105 | 1.103 | QA testing Complete | M | 2008-12-01 17:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.110 | 1.109 | User Acceptance Testing | T | 2008-12-03 08:00 | 2008-12-05 17:00 |  | G | [20 empty] | 2008-12-05 17:00
| 1.112 | 1.111 | UAT Complete | M | 2008-12-12 17:00 | 2008-12-12 17:00 |  | G | [21 empty] | 2008-12-12 17:00
| 1.116 | 1.114 | Deploy to Production | T | 2008-12-15 08:00 | 2008-12-16 17:00 |  | G | [22 empty] | 2008-12-16 17:00
| 1.119 | 1.118 | Deploy to Sandbox | T | 2008-12-18 08:00 | 2008-12-19 17:00 |  | G | [22 empty] | 2008-12-19 17:00
| 1.123 |  | Form Builder 4.0.0.1 (Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.125 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.129 | 1.125 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.131 | 1.129 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.132 | 1.131 | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.134 | 1.132 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.136 | 1.135 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.142 | 1.140 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.144 | 1.142 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.149 | 1.148 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.151 | 1.150 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.155 | 1.153 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.158 | 1.157 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 1.162 |  | Metadata Cleanup(Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.164 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.168 | 1.164 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.170 | 1.168 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.171 | 1.170 | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.173 | 1.171 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.175 | 1.174 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.181 | 1.179 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.183 | 1.181 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.188 | 1.187 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.190 | 1.189 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.194 | 1.192 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.197 | 1.196 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 1.201 |  | Semantic Tools 4.0.0.2(Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.203 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.207 | 1.203 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.209 | 1.207 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.210 | 1.209 | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.212 | 1.210 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.214 | 1.213 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.220 | 1.218 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.222 | 1.220 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.227 | 1.226 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.229 | 1.228 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.233 | 1.231 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.236 | 1.235 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 1.240 |  | Metadata Loader [NMDP] Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.242 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.246 | 1.242 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.248 | 1.246 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.249 | 1.248 | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.251 | 1.249 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.253 | 1.252 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.259 | 1.257 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.261 | 1.259 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.266 | 1.265 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.268 | 1.267 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.272 | 1.270 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.275 | 1.274 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 1.279 |  | Curation Tool 4.0.0.1 (Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.281 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.285 | 1.281 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.287 | 1.285 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.288 | 1.287 | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.290 | 1.288 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.292 | 1.291 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.298 | 1.296 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.300 | 1.298 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.305 | 1.304 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.307 | 1.306 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.311 | 1.309 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.314 | 1.313 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 1.318 |  | Sentinel Tool 4.0.0.1 (Template) | H | 2008-10-06 08:00 | 2008-12-08 17:00 |  | G | [21 empty] | 2008-12-08 17:00
| 1.320 |  | Agree Iteration Scope | I | 2008-10-06 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.324 | 1.320 | Update Project Plan | M | 2008-10-10 17:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 1.326 | 1.324 | Agree Preliminary Design | E | 2008-10-14 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.327 | 1.326 | Elaboration Complete | M | 2008-10-20 17:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 1.329 | 1.327 | Develop Software (timebox) | C | 2008-10-21 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.331 | 1.330 | Construction Complete | M | 2008-11-03 17:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 1.337 | 1.335 | Conduct QA testing | T | 2008-11-05 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.339 | 1.337 | QA testing Complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 1.344 | 1.343 | User Acceptance Testing | T | 2008-11-14 08:00 | 2008-11-18 17:00 |  | G | [18 empty] | 2008-11-18 17:00
| 1.346 | 1.345 | UAT Complete | M | 2008-11-25 17:00 | 2008-11-25 17:00 |  | G | [19 empty] | 2008-11-25 17:00
| 1.350 | 1.348 | Deploy to Production | T | 2008-11-26 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 1.353 | 1.352 | Deploy to Sandbox | T | 2008-12-03 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
R
| 2 |  | caAdapter
| 2.125 |  | caAdapter - CMPS Module | H | 2008-05-05 08:00 | 2009-02-24 17:00 |  | G | [32 empty] | 2009-02-24 17:00
| 2.126 |  | 1st Iteration | C | 2008-05-05 08:00 | 2009-02-24 17:00 |  | G | [32 empty] | 2009-02-24 17:00
| 2.127 |  | Inception | I | 2008-05-05 08:00 | 2008-09-16 17:00 |  | R | [9 empty] | 2008-09-16 17:00
| 2.143 |  | Elaboration | E | 2008-07-31 08:00 | 2008-09-10 17:00 |  | R | [8 empty] | 2008-09-10 17:00
| 2.152 |  | Construction | C | 2008-08-28 08:00 | 2009-01-21 17:00 |  | G | [27 empty] | 2009-01-21 17:00
| 2.153 |  | Core Engine | C | 2008-08-28 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 2.161 |  | Implement Validations | C | 2008-12-04 08:00 | 2009-01-14 17:00 |  | G | [26 empty] | 2009-01-14 17:00
| 2.170 |  | Enhance Mapping UI | C | 2008-10-31 08:00 | 2009-01-14 17:00 |  | G | [26 empty] | 2009-01-14 17:00
| 2.176 |  | Mapping & Transformation (M&T) Scenarios | C | 2008-10-17 08:00 | 2008-11-07 17:00 |  | G | [16 empty] | 2008-11-07 17:00
| 2.187 |  | Persistence Module | C | 2008-12-02 08:00 | 2008-12-19 17:00 |  | G | [22 empty] | 2008-12-19 17:00
| 2.192 |  | Webservice Portal | C | 2008-12-19 08:00 | 2009-01-08 17:00 |  | G | [25 empty] | 2009-01-08 17:00
| 2.196 | 2.195 | Deliverable: Enhancements to Webservice Portal* | M | 2009-01-08 08:00 | 2009-01-08 17:00 |  | G | [25 empty] | 2009-01-08 17:00
| 2.197 |  | Internal Integration Test | C | 2009-01-14 08:00 | 2009-01-20 17:00 |  | G | [27 empty] | 2009-01-20 17:00
| 2.201 |  | QA - Test Plan and Test Cases | T | 2008-10-01 08:00 | 2008-10-21 12:00 |  | R | [14 empty] | 2008-10-21 12:00
| 2.203 | 2.202 | Deliverable: Draft System Test Plan and test cases | M | 2008-10-14 17:00 | 2008-10-14 17:00 |  | R | [13 empty] | 2008-10-14 17:00
| 2.207 |  | Documentation | T | 2008-09-29 08:00 | 2009-01-21 17:00 |  | G | [27 empty] | 2009-01-21 17:00
| 2.223 |  | Transition | H | 2009-01-21 08:00 | 2009-02-24 17:00 |  | G | [32 empty] | 2009-02-24 17:00
| 2.225 | 2.224 | Execute all test cases | T | 2009-01-21 08:00 | 2009-02-03 17:00 |  | G | [29 empty] | 2009-02-03 17:00
| 2.226 | 2.225 | Deliverable: QA Test Results | M | 2009-02-03 08:00 | 2009-02-03 17:00 |  | G | [29 empty] | 2009-02-03 17:00
| 2.228 | 2.227 | Deliverable: Deploy to Staging server | M | 2009-02-09 08:00 | 2009-02-09 12:00 |  | G | [30 empty] | 2009-02-09 12:00
| 2.233 | 2.232 | Deliverable: Production System | M | 2009-02-24 08:00 | 2009-02-24 17:00 |  | G | [32 empty] | 2009-02-24 17:00
| 3 |  | caCORE SDK
| 3.111 |  | SDK 4.1 Iteration 3 | H | 2008-07-07 08:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 3.112 |  | Defect Fixes | C | 2008-07-07 08:00 | 2008-08-28 17:00 |  | R | [6 empty] | 2008-08-28 17:00
| 3.121 |  | Grid Integration | C | 2008-07-07 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 3.132 |  | Grid XML Serialization | C | 2008-07-15 08:00 | 2008-08-18 17:00 |  | R | [5 empty] | 2008-08-18 17:00
| 3.133 | 3.117 | XSD Import statements (GF#12414) | C | 2008-07-15 08:00 | 2008-07-17 17:00 |  | R | 2008-07-17 17:00
| 3.134 |  | GME Namespace (GF#12415) | C | 2008-07-18 08:00 | 2008-08-14 17:00 |  | R |  |  |  |  | 2008-08-14 17:00
| 3.141 | 3.140 | Permissile values (GF#6137) | C | 2008-08-15 08:00 | 2008-08-18 17:00 |  | R | [5 empty] | 2008-08-18 17:00
| 3.142 |  | Validation | C | 2008-08-22 08:00 | 2008-09-08 12:00 |  | R | [8 empty] | 2008-09-08 12:00
| 3.146 |  | QA | C | 2008-08-11 08:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 3.151 |  | caAdapter, SIW Bug fixes complete | M | 2008-10-24 17:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 3.152 | 3.151 | Integration Test - GME | C | 2008-09-29 08:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 3.154 | 3.157 | Update database scripts | T | 2008-10-21 08:00 | 2008-10-22 17:00 |  | R | [14 empty] | 2008-10-22 17:00
| 3.155 | 3.154 | QA database scripts | T | 2008-10-23 08:00 | 2008-10-23 17:00 |  | R | [14 empty] | 2008-10-23 17:00
| 3.156 |  | Update documentation | T | 2008-09-29 08:00 | 2008-10-17 17:00 |  | R | [13 empty] | 2008-10-17 17:00
| 3.157 | 3.156 | Prepare release notes | T | 2008-10-20 08:00 | 2008-10-20 17:00 |  | R | [14 empty] | 2008-10-20 17:00
| 3.158 |  | Receive Clearance From the Grid team on GME Namespace UAT testing | M | 2008-10-27 08:00 | 2008-10-27 08:00 |  | R | [15 empty] | 2008-10-27 08:00
| 3.159 | 3.156 | Create release packaging | T | 2008-10-27 08:00 | 2008-10-27 17:00 |  | R | [15 empty] | 2008-10-27 17:00
| 3.160 | 3.159 | QA release packaging | T | 2008-10-28 08:00 | 2008-10-28 17:00 |  | R | [15 empty] | 2008-10-28 17:00
| 3.161 | 3.160 | Update zope website | T | 2008-10-29 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 3.162 | 3.161 | Update Gforge website | T | 2008-10-31 08:00 | 2008-10-31 17:00 |  | G | [15 empty] | 2008-10-31 17:00
| 3.163 | 3.162 | Push to production | T | 2008-11-03 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 3.164 | 3.163 | 4.1 release complete | M | 2008-11-12 17:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
R
| 4 |  | COPPA
| 5.01 |  | Construction - (Iteration 2) | C | 2008-08-25 | 2008-09-13 |  | R | [8 empty] | 2008-09-13 | [42 empty] | #REF!
| 5.02 |  | Inception - Create localized Datatypes in caDSR | I | 2008-08-25 | 2008-10-13 |  | R | [13 empty] | 2008-10-13 | [37 empty] | #REF!
| 5.03 | 5.04 | Localized Data Types Completed in QA | E | 2008-09-10 | 2008-10-12 |  | R | [12 empty] | 2008-10-12
| 5.04 |  | Create Macro for Uploading COPPA VD's into caDSR | C | 2008-10-09 | 2008-10-17 |  | R | [13 empty] | 2008-10-17
| 5.04 |  | Receive BRIDGE Model | M | 2008-10-17 | 2008-10-17 |  | R | [13 empty] | 2008-10-17
| 5.05 | 5.04 | Handover Model to caDSR Team | M | 2008-10-13 | 2008-10-13 |  | R | [13 empty] | 2008-10-13
| 5.06 |  | Construction - (Iteration 3) | C | 2008-09-15 | 2008-10-20 |  | R | [14 empty] | 2008-10-20
| 5.07 | 5.04 | Test Loading Model into caDSR | M | 2008-10-14 | 2008-11-10 |  | G | [17 empty] | 2008-11-10
| 5.08 |  | Construction - (Iteration 4 (RC1) | C | 2008-10-20 | 2008-11-17 |  | G | [18 empty] | 2008-11-17
| 5.09 |  | Construction - (Iteration 5 (RC2) | C | 2008-11-17 | 2008-12-15 |  | G | [22 empty] | 2008-12-15
| 5.04 | 5.06 | Annotate & review Model | E | 2008-10-13 | 2008-11-10 |  | G | [17 empty] | 2008-11-10
| 5.11 |  | Feedback & Review Session 1 | E | 2008-10-20 | 2008-10-27 |  | R | [15 empty] | 2008-10-27
| 5.12 |  | Feedback & Review Session 2 | E | 2008-11-03 | 2008-11-10 |  | G | [17 empty] | 2008-11-10
| 5.13 | 5.12 | COPPA Model Finalized | M | 2008-12-15 | 2008-12-15 |  | G | [22 empty] | 2008-12-15
| 5.14 |  | Transition (Iteration1) | T | 2008-12-15 | 2009-01-15 |  | G | [26 empty] | 2009-01-15
| 5.15 |  | UAT | T | 2008-12-15 | 2008-12-22 |  | G | [23 empty] | 2008-12-22
| 5.16 | 5.12 | Register Model in caDSR | M | 2008-12-22 | 2008-12-22 |  | G | [23 empty] | 2008-12-22
| 5.17 |  | Transition (Iteration2) | T | 2009-01-05 | 2009-01-29 |  | G | [28 empty] | 2009-01-29
| 5.18 |  | CTRP 1.0 GO LIVE | M | 2009-01-29 | 2009-01-29 |  | G | [28 empty] | 2009-01-29
5.19
| 5 |  | GME NameSpace |  |  |  |  | R
| 5.01 |  | GME Component Testing | T | 2008-08-18 | 2008-09-01 |  | R | [7 empty] | 2008-09-01
| 5.02 |  | GME Alpha 2 Integration Testing | T | 2008-09-15 | 2008-09-29 |  | R | [11 empty] | 2008-09-29
| 5.03 |  | Bug Fixes & Retest (SDK Integration) | T | 2008-10-01 | 2008-10-17 |  | R | [13 empty] | 2008-10-17
| 5.04 |  | GME Beta Testing | T | 2008-10-01 | 2008-10-17 |  | R | [13 empty] | 2008-10-17
| 5.05 |  | GME Beta Testing Completed | M | 2008-10-17 | 2008-10-17 |  | R | [13 empty] | 2008-10-17
| 5.06 |  | GME End to End Testing | T | 2008-10-20 | 2008-10-24 |  | R | [14 empty] | 2008-10-24
| 5.07 |  | GF#17143 Need Fix | M | 2008-10-24 | 2008-10-24 |  | R | [14 empty] | 2008-10-24
| 5.08 |  | GF#1769 Need Fix | M | 2008-10-24 | 2008-10-24 |  | R | [14 empty] | 2008-10-24
| 5.09 |  | GF#17257 Need Fix | M | 2008-10-24 | 2008-10-24 |  | R | [14 empty] | 2008-10-24
| 5.10 |  | GF#17271 Need Fix | M | 2008-10-24 | 2008-10-24 |  | R | [14 empty] | 2008-10-24
| 5.11 |  | GME End To End Testing Completed | M | 2008-10-24 | 2008-10-24 |  | R | [14 empty] | 2008-10-24
| 5.12 |  | GME Acceptance Testing | T | 2008-11-01 | 2008-11-15 |  | G | [17 empty] | 2008-11-15
| 5.13 |  | GME Acceptance Testing Complete | M | 2008-11-15 | 2008-11-15 |  | G | [17 empty] | 2008-11-15
| 6 |  | Common Logging Module(CLM)
R
R
R
R
R
R
| 7 |  | Common Security Module (CSM)
| 7.2 |  | Release 4.1 | H | 2008-03-03 08:00 | 2008-11-14 17:00 |  | G | [17 empty] | 2008-11-14 17:00
| 7.15 |  | Create scope/requirement document | E | 2008-06-09 08:00 | 2008-06-19 17:00 |  | R
| 7.22 | 7.15 | Revise Task Plan | E | 2008-06-20 08:00 | 2008-06-20 17:00 |  | R
| 7.23 |  | Update Scope | E | 2008-07-02 08:00 | 2008-07-03 17:00 |  | R
| 7.24 | 7.23 | Perform LOE | E | 2008-07-04 08:00 | 2008-07-08 17:00 |  | R
| 7.25 | 7.24 | Milestone - Scope Approved | M | 2008-07-08 17:00 | 2008-07-08 17:00 |  | R
| 7.26 | 7.24 | Revise Iteration Schedule | E | 2008-07-09 08:00 | 2008-07-10 17:00 |  | R
| 7.27 | 7.26 | Milestone - Iteration Schedule Approved | E | 2008-07-11 08:00 | 2008-07-11 12:00 |  | R
| 7.28 | 7.27 | Update Scope if Necessary | E | 2008-07-11 13:00 | 2008-07-14 10:00 |  | R | 2008-07-14 10:00
| 7.29 | 7.24 | Document Iteration Design | E | 2008-07-09 08:00 | 2008-07-14 17:00 |  | R | 2008-07-14 17:00
| 7.30 | 7.29 | Design Review / Update | E | 2008-07-15 08:00 | 2008-07-16 17:00 |  | R | 2008-07-16 17:00
| 7.31 | 7.30 | Milestone - Iteration Design Approved | M | 2008-07-16 17:00 | 2008-07-16 17:00 |  | R | 2008-07-16 17:00
| 7.32 | 7.30 | Milestone - Meet with caTissue | M | 2008-07-16 17:00 | 2008-07-16 17:00 |  | R | 2008-07-16 17:00
| 7.62 |  | BDA Effort | C | 2008-05-12 08:00 | 2008-06-13 17:00 |  | R
| 7.63 |  | CSM caGrid User Migration | C | 2008-07-17 08:00 | 2008-08-13 17:00 |  | R |  |  |  |  | 2008-08-13 17:00
| 7.70 | 7.64 | Attribute Security - Strict and Loose Flag behavior | C | 2008-08-14 08:00 | 2008-08-18 17:00 |  | R | [5 empty] | 2008-08-18 17:00
| 7.71 | 7.70 | Support @Filter annotations for security filters | C | 2008-08-19 08:00 | 2008-08-28 17:00 |  | R | [6 empty] | 2008-08-28 17:00
| 7.72 | 7.71 | Consider 'extra-lazy' collection attributes | C | 2008-08-29 08:00 | 2008-09-02 17:00 |  | R | [7 empty] | 2008-09-02 17:00
| 7.73 | 7.72 | CSM API Deadlock Issue in MySQL | C | 2008-09-03 08:00 | 2008-09-04 17:00 |  | R | [7 empty] | 2008-09-04 17:00
| 7.74 | 7.81 | not-null=true column un-populatable in mysql 5.0.45 | C | 2008-09-02 08:00 | 2008-09-08 17:00 |  | R | [8 empty] | 2008-09-08 17:00
| 7.75 | 7.73 | AuthorizationManager Method updates (GF# 14574,14575,12309) | C | 2008-09-05 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 7.76 | 7.74 | LdapHelper Blank Password | C | 2008-09-09 08:00 | 2008-09-10 17:00 |  | R | [8 empty] | 2008-09-10 17:00
| 7.77 | 7.76 | FireFox Compatibilty for Instance Level Screen | C | 2008-09-11 08:00 | 2008-09-15 17:00 |  | R | [9 empty] | 2008-09-15 17:00
| 7.78 | 7.75 | Domain Object Updates (GF# 14577, 4195,9045,10408) | C | 2008-09-22 08:00 | 2008-09-23 17:00 |  | R | [10 empty] | 2008-09-23 17:00
| 7.79 | 7.78 | Postgres SQL Script update | C | 2008-09-24 08:00 | 2008-09-25 17:00 |  | R | [10 empty] | 2008-09-25 17:00
| 7.80 | 7.77 | Provide Unlock User option in UPT | C | 2008-09-16 08:00 | 2008-09-19 17:00 |  | R | [9 empty] | 2008-09-19 17:00
| 7.81 |  | Post BDA Updates | C | 2008-08-15 08:00 | 2008-09-01 17:00 |  | R | [7 empty] | 2008-09-01 17:00
| 7.85 |  | QA Activities | C | 2008-07-18 08:00 | 2008-10-09 17:00 |  | R | [12 empty] | 2008-10-09 17:00
| 7.89 |  | User Center Design Review/Modifications | C | 2008-09-29 08:00 | 2008-10-20 14:20 |  | R | [14 empty] | 2008-10-20 14:20
| 7.94 | 7.92 | Submit Stage Request | C | 2008-10-20 14:20 | 2008-10-22 14:20 |  | R | [14 empty] | 2008-10-22 14:20
| 7.97 | 7.85 | Integration Support | T | 2008-10-10 08:00 | 2008-11-04 17:00 |  | G | [16 empty] | 2008-11-04 17:00
| 7.98 | 7.88F | Update database scripts | T | 2008-10-03 08:00 | 2008-10-07 14:20 |  | R | [12 empty] | 2008-10-07 14:20
| 7.99 | 7.98 | QA database scripts | T | 2008-10-07 14:20 | 2008-10-09 09:20 |  | R | [12 empty] | 2008-10-09 09:20
| 7.100 | 7.93 | Update CSM documentation | T | 2008-10-20 14:20 | 2008-10-29 10:40 |  | R | [15 empty] | 2008-10-29 10:40
| 7.101 | 7.100 | Create CSM Grid User Migration Module documentation | T | 2008-10-29 10:40 | 2008-11-11 10:40 |  | G | [17 empty] | 2008-11-11 10:40
| 7.102 | 7.104 | Create release packaging | T | 2008-11-12 14:20 | 2008-11-13 14:20 |  | G | [17 empty] | 2008-11-13 14:20
| 7.103 | 7.102 | Prepare release notes | T | 2008-11-13 14:20 | 2008-11-14 17:00 |  | G | [17 empty] | 2008-11-14 17:00
| 7.104 | 7.101 | Update zope website | T | 2008-11-11 10:40 | 2008-11-12 14:20 |  | G | [17 empty] | 2008-11-12 14:20
| 7.105 | 7.94F | Submit Production Request | T | 2008-10-29 14:20 | 2008-10-31 14:20 |  | G | [15 empty] | 2008-10-31 14:20
| 7.106 | 7.105 | Push to production | T | 2008-10-31 14:20 | 2008-11-14 14:20 |  | G | [17 empty] | 2008-11-14 14:20
| 7.107 | 7.106 | 4.1 release complete | M | 2008-11-14 17:00 | 2008-11-14 17:00 |  | G | [17 empty] | 2008-11-14 17:00
R
| 8 |  | Enterprise Vocabulary Services (EVS) - API
R
R
R
R
R
R
R
| 9 |  | EVS - BioPortal
R
R
R
R
R
R
R
| 10 |  | EVS - Protégé
| 10.10 |  | QA Test | H | 2008-10-06 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 10.11 | 10.20 | Round 1 | C | 2008-10-06 08:00 | 2008-10-22 17:00 |  | R | [14 empty] | 2008-10-22 17:00
| 10.15 |  | Round 2 | C | 2008-10-23 08:00 | 2008-11-12 17:00 |  | G | [17 empty] | 2008-11-12 17:00
| 10.20 |  | Perform QA Build | C | 2008-10-03 08:00 | 2008-10-03 17:00 |  | R | [11 empty] | 2008-10-03 17:00
| 10.24 | 10.27 | Perform Testing | T | 2008-11-13 13:00 | 2008-11-25 12:00 |  | G | [19 empty] | 2008-11-25 12:00
| 10.25 | 10.27 | Test Support/ Critical Bug Fixes | T | 2008-11-13 13:00 | 2008-11-25 12:00 |  | G | [19 empty] | 2008-11-25 12:00
| 10.27 | 10.18 | UAT/Release Candidate Build | T | 2008-11-13 08:00 | 2008-11-13 12:00 |  | G | [17 empty] | 2008-11-13 12:00
| 10.28 | 10.24 | Production Deployment | T | 2008-11-25 13:00 | 2008-11-26 12:00 |  | G | [19 empty] | 2008-11-26 12:00
R
| 11 |  | Lex EVS
| 11.1 |  | Training & Transition | H | 2008-04-15 08:00 | 2008-08-07 17:00 |  | R |  |  |  | 2008-08-07 17:00
| 11.2 |  | NCI/Mayo Training | I | 2008-04-28 08:00 | 2008-04-30 17:00 |  | R
| 11.3 |  | Online Training prep for Bootcamp | I | 2008-04-22 08:00 | 2008-04-23 12:00 |  | R
| 11.4 | 11.5 | Bootcamp | I | 2008-07-10 08:00 | 2008-07-11 17:00 |  | R
| 11.5 | 11.7 | caBig meeting | I | 2008-07-07 08:00 | 2008-07-09 17:00 |  | R
| 11.6 |  | Gforge transition to LexEVS | I | 2008-04-24 08:00 | 2008-04-25 17:00 |  | R
| 11.7 |  | EVS Code Transition | I | 2008-04-15 08:00 | 2008-08-07 17:00 |  | R |  |  |  | 2008-08-07 17:00
| 11.8 |  | Project Planning | H | 2008-03-24 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00
| 11.9 |  | Create initial Project plan and assign resources | E | 2008-03-24 08:00 | 2008-04-11 17:00 |  | R
| 11.10 |  | #13871 - Maintain project plan | E | 2008-03-24 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00
| 11.11 |  | Meetings and status reporting | E | 2008-09-26 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00
| 11.12 |  | EVS 4.1 Release | H | 2008-03-24 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00
| 11.13 |  | Support for 4.1 | C | 2008-03-24 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00
| 11.14 |  | Gforge #7011 | C | 2008-03-24 08:00 | 2008-04-04 17:00 |  | R
| 11.15 |  | Gforge #14008 | C | 2008-05-07 13:00 | 2008-05-09 12:00 |  | R
| 11.16 |  | #14483 Supported hierarchies | C | 2008-07-08 08:00 | 2008-07-08 17:00 |  | R
| 11.17 |  | caDSR bug fixes | M | 2008-04-07 08:00 | 2008-04-07 08:00 |  | R
| 11.18 |  | EVS 4.2 Release | H | 2008-03-24 08:00 | 2008-11-04 10:00 |  | G | [16 empty] | 2008-11-04 10:00
| 11.19 |  | Planning | E | 2008-04-03 08:00 | 2008-04-09 17:00 |  | R
| 11.20 |  | Draft Scope Document | E | 2008-04-03 08:00 | 2008-04-09 17:00 |  | R
| 11.21 |  | Development & Unit Test | C | 2008-03-24 08:00 | 2008-09-24 17:00 |  | R | [10 empty] | 2008-09-24 17:00
| 11.22 |  | Gforge Items | C | 2008-03-24 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00
| 11.23 |  | #8670 (SMQ) | C | 2008-03-24 08:00 | 2008-05-05 12:00 |  | R
| 11.24 |  | Investigation | C | 2008-03-24 08:00 | 2008-04-18 17:00 |  | R
| 11.25 | 11.24 | Development | C | 2008-04-21 08:00 | 2008-04-30 12:00 |  | R
| 11.26 | 11.25 | Testing | C | 2008-04-30 12:00 | 2008-05-05 12:00 |  | R
| 11.27 |  | 13500 - Meddra loader | C | 2008-03-25 08:00 | 2008-04-28 17:00 |  | R
| 11.28 | 11.25 | Investigation | C | 2008-03-25 08:00 | 2008-04-28 17:00 |  | R | [6 empty] | 2008-08-27 08:48
| 11.29 | 11.28 | use current | M | 2008-04-28 17:00 | 2008-04-28 17:00 |  | R | [11 empty] | 2008-09-30 08:48
| 11.30 |  | 13501 - HL7 loader | C | 2008-04-14 08:00 | 2008-06-05 17:00 |  | R | [12 empty] | 2008-10-09 08:48
| 11.31 |  | Investigation | C | 2008-04-14 08:00 | 2008-05-02 17:00 |  | R |  |  | 2008-07-29 17:00
| 11.32 | 11.31 | Development & Testing | C | 2008-05-05 08:00 | 2008-05-22 17:00 |  | R |  |  |  |  | 2008-08-11 17:00
| 11.33 | 11.32 | Verification | C | 2008-05-23 08:00 | 2008-06-05 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 11.34 |  | 13565 (LOINC loader) | C | 2008-04-15 08:00 | 2008-05-12 17:00 |  | R
| 11.35 |  | Investigation | C | 2008-04-15 08:00 | 2008-04-28 17:00 |  | R
| 11.36 | 11.35 | Development & testing & verification | C | 2008-04-29 08:00 | 2008-05-12 17:00 |  | R | 2008-07-18 17:00
| 11.37 |  | #12357 (loader & presentation props) | C | 2008-05-14 08:00 | 2008-06-18 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 11.38 | 11.33 | #8672 (complex props) | C | 2008-06-06 08:00 | 2008-07-14 17:00 |  | R | 2008-07-14 17:00 | [10 empty] | 2008-09-29 10:48
| 11.39 |  | #13193 (manifest load) | C | 2008-05-05 08:00 | 2008-06-18 17:00 |  | R | [9 empty] | 2008-09-19 17:00
| 11.40 |  | UMLS | C | 2008-06-13 08:00 | 2008-06-18 17:00 |  | R | [10 empty] | 2008-09-26 17:00
| 11.41 |  | Other loads, UI | C | 2008-05-05 08:00 | 2008-06-18 17:00 |  | R | [11 empty] | 2008-09-29 10:48
| 11.42 | 11.30 | #8442 (lazy loading) | C | 2008-06-06 08:00 | 2008-06-09 17:00 |  | R
| 11.43 | 11.40 | #13026 (SAB/VSAB data load) | C | 2008-06-19 08:00 | 2008-07-02 17:00 |  | R
| 11.44 |  | #7891 (eliminate restriction methods) | C | 2008-06-16 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00
| 11.45 |  | #12995 (DB info to GUI) | C | 2008-06-30 08:00 | 2008-07-01 17:00 |  | R
| 11.46 |  | #10884 (method for copyright/security) | C | 2008-07-02 14:20 | 2008-07-09 14:20 |  | R
| 11.47 | 11.39 | #14252 CL CUI | C | 2008-06-19 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00
| 11.48 |  | #15043 (defer to 5.0) | C | 2008-07-04 08:00 | 2008-07-14 17:00 |  | R | 2008-07-14 17:00
| 11.49 |  | #15044 (defer to 5.0) | C | 2008-07-04 08:00 | 2008-07-14 17:00 |  | R | 2008-07-14 17:00
| 11.50 |  | Beta release | C | 2008-07-15 08:00 | 2008-07-15 17:00 |  | R | 2008-07-15 17:00
| 11.51 |  | Release Candidate | C | 2008-07-29 08:00 | 2008-07-29 17:00 |  | R |  |  | 2008-07-29 17:00
| 11.52 |  | #12802 (mapping doc) | C | 2008-06-03 08:00 | 2008-09-24 17:00 |  | R | [10 empty] | 2008-09-24 17:00
| 11.53 |  | #13873 - Generate release notes | T | 2008-08-19 08:00 | 2008-08-21 17:00 |  | R | [5 empty] | 2008-08-21 17:00
| 11.54 | 11.74F | #13874 -Update Tech/Developer guides | T | 2008-08-13 08:00 | 2008-09-19 08:48 |  | R | [9 empty] | 2008-09-19 08:48
| 11.55 |  | Testing (Internal & NCI) | C | 2008-07-07 08:00 | 2008-11-04 10:00 |  | G | [16 empty] | 2008-11-04 10:00 | 2008-11-10 10:00
| 11.56 |  | #13872 - Test Case/Plan development | C | 2008-07-07 08:00 | 2008-07-17 17:00 |  | R | 2008-07-17 17:00
| 11.57 |  | Develop Junit tests for all Gforge items | C | 2008-07-07 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00
| 11.58 |  | Internal Testing | C | 2008-07-14 08:00 | 2008-07-28 08:48 |  | R |  |  | 2008-07-28 08:48
| 11.59 | 11.50 | Confirm list of sources for 4.2 Release | C | 2008-07-16 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00
| 11.60 | 11.50 | Post 4.2 Sources and related files to Gforge | C | 2008-07-16 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00
| 11.61 |  | Send email to Systems team for QA, Stage & Prod environment request | C | 2008-08-13 08:00 | 2008-08-13 09:00 |  | R |  |  |  |  | 2008-08-13 09:00
| 11.62 |  | Dev Tier | C | 2008-07-28 08:48 | 2008-08-25 08:48 |  | R | [6 empty] | 2008-08-25 08:48
| 11.63 | 11.58 | Promote to NCI Dev | C | 2008-07-28 08:48 | 2008-07-29 08:48 |  | R |  |  | 2008-07-29 08:48
| 11.64 | 11.63 | Pre-QA verification/Junit testing | C | 2008-07-29 08:48 | 2008-08-19 08:48 |  | R | [5 empty] | 2008-08-19 08:48
| 11.65 | 11.64 | Bug fixes | C | 2008-08-19 08:48 | 2008-08-21 08:48 |  | R | [5 empty] | 2008-08-21 08:48
| 11.66 | 11.65 | 2nd run for pre-QA verification | C | 2008-08-21 08:48 | 2008-08-25 08:48 |  | R | [6 empty] | 2008-08-25 08:48
| 11.67 |  | QA | C | 2008-08-08 08:00 | 2008-09-30 13:48 |  | R | [11 empty] | 2008-09-30 13:48
| 11.68 | 11.58 | Draft Deployment Request | C | 2008-08-08 08:00 | 2008-08-14 17:00 |  | R |  |  |  |  | 2008-08-14 17:00
| 11.69 | 11.62 | #13877 - Promote to QA | C | 2008-08-25 08:48 | 2008-08-28 08:48 |  | R | [6 empty] | 2008-08-28 08:48
| 11.70 | 11.69 | Execute Test Cases | C | 2008-08-28 08:48 | 2008-09-04 08:48 |  | R | [7 empty] | 2008-09-04 08:48
| 11.71 | 11.70 | Schedule AppScan test | C | 2008-09-04 08:48 | 2008-09-05 08:48 |  | R | [7 empty] | 2008-09-05 08:48
| 11.72 | 11.71 | Execute AppScan | C | 2008-09-05 08:48 | 2008-09-09 08:48 |  | R | [8 empty] | 2008-09-09 08:48
| 11.73 | 11.72 | Bug Fixes | C | 2008-09-09 08:48 | 2008-09-16 08:48 |  | R | [9 empty] | 2008-09-16 08:48
| 11.74 | 11.73 | Redeploy to QA w/fixes | C | 2008-09-16 08:48 | 2008-09-19 08:48 |  | R | [9 empty] | 2008-09-19 08:48
| 11.75 | 11.74 | Re-execute testing | C | 2008-09-19 08:48 | 2008-09-30 13:48 |  | R | [11 empty] | 2008-09-30 13:48
| 11.76 |  | Staging | C | 2008-10-03 08:00 | 2008-10-09 17:00 |  | R | [12 empty] | 2008-10-09 17:00
| 11.77 | 11.74 | Draft Deployment Request | C | 2008-10-03 08:00 | 2008-10-03 10:00 |  | R | [11 empty] | 2008-10-03 10:00
| 11.78 |  | #13878 - Promote to Staging | C | 2008-10-03 08:00 | 2008-10-07 17:00 |  | R | [12 empty] | 2008-10-07 17:00
| 11.79 | 11.78 | Execute Tests | C | 2008-10-08 08:00 | 2008-10-09 17:00 |  | R | [12 empty] | 2008-10-09 17:00
| 11.80 | 11.79 | Redeployment for caDSR fix | C | 2008-10-15 08:00 | 2008-10-28 17:00 |  | R | [15 empty] | 2008-10-28 17:00
| 11.81 |  | 4.2 Deployment | C | 2008-10-15 08:00 | 2008-10-28 17:00 |  | R | [15 empty] | 2008-10-28 17:00
| 11.82 |  | Dev | C | 2008-10-15 08:00 | 2008-10-15 17:00 |  | R | [13 empty] | 2008-10-15 17:00
| 11.83 |  | QA | C | 2008-10-16 08:00 | 2008-10-21 17:00 |  | R | [14 empty] | 2008-10-21 17:00
| 11.84 | 11.82 | Deploy to QA | C | 2008-10-16 08:00 | 2008-10-17 17:00 |  | R | [13 empty] | 2008-10-17 17:00
| 11.85 | 11.84 | Test in QA | C | 2008-10-20 08:00 | 2008-10-21 17:00 |  | R | [14 empty] | 2008-10-21 17:00
| 11.86 |  | Stage | C | 2008-10-22 08:00 | 2008-10-28 17:00 |  | R | [15 empty] | 2008-10-28 17:00
| 11.87 | 11.85 | Deploy to Stage | C | 2008-10-22 08:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00 | 2008-10-28 17:00
| 11.88 | 11.87 | Test in Stage | C | 2008-10-27 08:00 | 2008-10-28 17:00 |  | R | [15 empty] | 2008-10-28 17:00
| 11.89 | 11.80 | Production | H | 2008-10-29 08:00 | 2008-11-04 10:00 |  | G | [15 empty] | 2008-10-30 17:00 | 2008-11-04 10:00
| 11.90 |  | 4.2 | T | 2008-10-29 08:00 | 2008-11-04 10:00 |  | G | [13 empty] | 2008-10-15 17:00 |  |  | 2008-11-04 10:00
| 11.91 |  | Draft Deployment Request | T | 2008-10-29 08:00 | 2008-10-29 10:00 |  | R | [14 empty] | 2008-10-21 17:00 | 2008-10-29 10:00
| 11.92 | 11.91 | #13879 - Promote to Production | T | 2008-10-29 10:00 | 2008-11-03 10:00 |  | G | [13 empty] | 2008-10-17 17:00 |  |  | 2008-11-03 10:00
| 11.93 | 11.92 | Execute Test cases | T | 2008-11-03 10:00 | 2008-11-04 10:00 |  | G | [14 empty] | 2008-10-21 17:00 |  | 2008-11-04 10:00
| 11.94 |  | #13880 - Grid Enablement | C | 2008-03-24 08:00 | 2008-11-05 10:00 |  | G | [15 empty] | 2008-10-30 17:00 | 2008-11-05 10:00
| 11.95 |  | caGrid xsd generation & validation | C | 2008-03-24 08:00 | 2008-05-12 12:00 |  | R | [15 empty] | 2008-10-28 17:00
| 11.96 |  | Enhanced Prototype | C | 2008-03-24 08:00 | 2008-06-05 17:00 |  | R | [15 empty] | 2008-10-30 17:00
| 11.97 |  | Service Metadata | C | 2008-03-24 08:00 | 2008-05-02 17:00 |  | R | [17 empty] | 2008-11-10 10:00
| 11.98 |  | Query | C | 2008-03-24 08:00 | 2008-05-02 17:00 |  | R | [17 empty] | 2008-11-10 10:00
| 11.99 |  | Extensions | C | 2008-03-24 08:00 | 2008-05-02 17:00 |  | R | [15 empty] | 2008-10-31 10:00
| 11.100 |  | Prepare for caBIG annual meeting | C | 2008-06-02 08:00 | 2008-06-05 17:00 |  | R | [16 empty] | 2008-11-05 10:00
| 11.101 | 11.99 | Phase 1 Grid Implementation | C | 2008-05-05 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00 | [16 empty] | 2008-11-10 10:00
| 11.102 |  | Service Metadata | C | 2008-05-05 08:00 | 2008-06-13 17:00 |  | R | [17 empty] | 2008-11-10 10:00
| 11.103 |  | Query | C | 2008-05-05 08:00 | 2008-06-13 17:00 |  | R | [15 empty] | 2008-10-31 12:00
| 11.104 |  | Extensions | C | 2008-05-05 08:00 | 2008-06-13 17:00 |  | R | [16 empty] | 2008-11-05 10:00
| 11.105 |  | DLB API updates | C | 2008-07-11 08:00 | 2008-07-17 17:00 |  | R | 2008-07-17 17:00 | [16 empty] | 2008-11-10 10:00
| 11.106 | 11.105 | Check code into DVS | C | 2008-07-18 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00 | [15 empty] | 2008-11-07 10:00
| 11.107 | 11.101 | Create Architectural review checklist | C | 2008-07-21 08:00 | 2008-07-21 09:00 |  | R |  | 2008-07-21 09:00
| 11.108 |  | Submit ARC to Systems Team | C | 2008-07-28 08:00 | 2008-07-28 09:00 |  | R |  |  | 2008-07-28 09:00
| 11.109 |  | Meeting with Systems team | C | 2008-08-01 08:00 | 2008-08-01 09:00 |  | R |  |  | 2008-08-01 09:00
| 11.110 |  | Deploy to NCI Dev | C | 2008-08-14 08:00 | 2008-08-15 17:00 |  | R |  |  |  |  | 2008-08-15 17:00
| 11.111 | 11.110 | Send email to Systems team for QA, Stage & Prod environment request | C | 2008-08-13 08:00 | 2008-08-13 09:00 |  | R |  |  |  |  | 2008-08-13 09:00
| 11.112 | 11.111 | Deploy to remaining NCI tiers (QA, Stage, Prod) | C | 2008-08-25 08:48 | 2008-11-05 10:00 |  | G | [16 empty] | 2008-11-05 10:00
| 11.113 | 11.69S | QA | C | 2008-08-25 08:48 | 2008-08-27 08:48 |  | R | 2008-07-18 17:00 | [5 empty] | 2008-08-27 08:48
| 11.114 | 11.78S | Stage | C | 2008-10-28 08:00 | 2008-10-29 17:00 |  | R | [12 empty] | 2008-10-06 17:00 |  |  | 2008-10-29 17:00
| 11.115 | 11.92 | Prod | T | 2008-11-03 10:00 | 2008-11-05 10:00 |  | G | [16 empty] | 2008-11-05 10:00
| 11.116 |  | Design document | C | 2008-07-21 08:00 | 2008-07-29 17:00 |  | R |  |  | 2008-07-29 17:00
| 11.117 | 11.116 | Finalize design document | C | 2008-08-01 08:00 | 2008-08-11 17:00 |  | R | 2008-07-17 17:00 |  |  |  | 2008-08-11 17:00
| 11.118 | 11.116 | Schedule review meeting with Avanash | C | 2008-08-12 08:00 | 2008-08-12 17:00 |  | R | 2008-07-18 17:00 |  |  |  | 2008-08-12 17:00
| 11.119 |  | #13881 - Expanded LexBig Model | C | 2008-03-24 08:00 | 2008-09-12 17:00 |  | R |  | 2008-07-21 09:00 | [6 empty] | 2008-09-12 17:00
| 11.120 |  | Model adjustments | C | 2008-03-24 08:00 | 2008-05-19 12:00 |  | R |  |  | 2008-07-28 09:00
| 11.121 | 11.120 | Model verification | C | 2008-05-19 08:00 | 2008-06-20 17:00 |  | R |  |  | 2008-08-01 09:00
| 11.122 |  | Milestone: Completed model submitted to NCI | C | 2008-07-18 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00 |  |  |  | 2008-08-15 17:00
| 11.123 | 11.122 | Model annotations | C | 2008-08-14 08:00 | 2008-09-12 17:00 |  | R |  |  |  |  | 2008-08-13 09:00 |  |  |  | 2008-09-12 17:00
| 11.124 |  | Upload updated Model to NCI | C | 2008-08-14 08:00 | 2008-08-14 17:00 |  | R |  |  |  |  | 2008-08-14 17:00 | [11 empty] | 2008-11-07 10:00
| 11.125 | 11.124 | Review/annotations by NCICB Support | C | 2008-08-15 08:00 | 2008-09-08 17:00 |  | R | [6 empty] | 2008-08-27 08:48 |  | 2008-09-08 17:00
| 11.126 | 11.125 | Review changes | C | 2008-09-08 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00 |  |  |  | 2008-10-06 17:00
| 11.127 | 11.123 | #13882 - Silver Level Compatibility | C | 2008-07-28 08:00 | 2008-09-29 10:48 |  | R | [11 empty] | 2008-09-29 10:48 |  |  |  |  | 2008-11-07 10:00
| 11.128 | 11.126 | Load Model to caDSR Sandbox | C | 2008-09-15 08:00 | 2008-09-19 17:00 |  | R |  |  | 2008-07-29 17:00 | [6 empty] | 2008-09-19 17:00
| 11.129 | 11.128 | Load Model to Production | C | 2008-09-22 08:00 | 2008-09-26 17:00 |  | R |  |  |  |  | 2008-08-11 17:00 | [5 empty] | 2008-09-26 17:00
| 11.130 |  | Create Submission package | C | 2008-07-28 08:00 | 2008-09-29 10:48 |  | R |  |  |  |  | 2008-08-12 17:00 | [6 empty] | 2008-09-29 10:48
| 11.131 |  | Investigation | C | 2008-07-28 08:00 | 2008-08-15 17:00 |  | R |  |  |  |  | 2008-08-15 17:00 |  |  |  | 2008-09-12 17:00
| 11.132 | 11.131 | Review/correct data model description powerpoint | C | 2008-08-18 08:00 | 2008-08-20 17:00 |  | R | [5 empty] | 2008-08-20 17:00
| 11.133 | 11.132 | Prepare/revise requirements documents | C | 2008-08-21 08:00 | 2008-08-27 17:00 |  | R | [6 empty] | 2008-08-27 17:00
| 11.134 | 11.128 | UML load | C | 2008-09-22 08:00 | 2008-09-26 17:00 |  | R | 2008-07-18 17:00 | [9 empty] | 2008-09-26 17:00
| 11.135 | 11.134 | Semantic Connector Report | C | 2008-09-08 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 11.136 | 11.135 | Value Domain Report | C | 2008-09-04 08:00 | 2008-09-04 17:00 |  | R |  |  |  |  | 2008-08-14 17:00 |  |  | 2008-09-04 17:00
| 11.137 | 11.136 | Vocabulary Report | C | 2008-09-05 08:00 | 2008-09-05 17:00 |  | R | [7 empty] | 2008-09-05 17:00 | 2008-09-08 17:00
| 11.138 | 11.128 | Full CDE User Report | C | 2008-09-22 08:00 | 2008-09-23 17:00 |  | R | [8 empty] | 2008-09-12 17:00 |  | 2008-09-23 17:00
| 11.139 | 11.128 | Standards Report | C | 2008-09-22 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00 | 2008-09-29 10:48
| 11.140 | 11.139 | API Description Document | C | 2008-09-17 08:00 | 2008-09-29 08:48 |  | R | [9 empty] | 2008-09-19 17:00 |  | 2008-09-29 08:48
| 11.141 | 11.140 | Adopter test log | C | 2008-09-18 08:00 | 2008-09-29 10:24 |  | R | [10 empty] | 2008-09-26 17:00 | 2008-09-29 10:24
| 11.142 | 11.140 | Pointers to CVS for objects input/output | C | 2008-09-29 08:48 | 2008-09-29 10:48 |  | R | [11 empty] | 2008-09-29 10:48
| 11.143 |  | EVS 5.0 Release Planning | T | 2008-08-25 08:00 | 2008-09-26 17:00 |  | R |  |  |  |  | 2008-08-15 17:00 | [5 empty] | 2008-09-26 17:00
| 11.144 |  | Draft Scope | T | 2008-09-18 08:00 | 2008-09-24 17:00 |  | R | [5 empty] | 2008-08-20 17:00 |  |  |  |  | 2008-09-24 17:00
| 11.145 |  | Draft Requirements | T | 2008-08-25 08:00 | 2008-09-19 17:00 |  | R | [6 empty] | 2008-08-27 17:00 |  |  | 2008-09-19 17:00
| 11.146 | 11.145 | Draft Project Plan | T | 2008-09-22 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00
[8 empty] | R | [8 empty] | 2008-09-12 17:00
R
| 12 |  | Lex EVS Gridservice
| 12.1 |  | LexEVS Grid Service 4.2 | H | 2008-06-30 08:00 | 2008-11-05 17:00 |  | G | [13 empty] | 2008-10-13 17:00 |  |  | 2008-11-05 17:00
| 12.2 |  | Documentation | H | 2008-07-21 08:00 | 2008-09-03 17:00 |  | R | [7 empty] | 2008-09-03 17:00
| 12.3 |  | Draft Design Document | E | 2008-07-21 08:00 | 2008-07-29 17:00 |  | R |  |  | 2008-07-29 17:00 | [8 empty] | 2008-10-03 17:00
| 12.4 | 12.3 | Review Draft Design Document | E | 2008-07-30 08:00 | 2008-07-31 17:00 |  | R |  |  | 2008-07-31 17:00 | [5 empty] | 2008-09-12 17:00
| 12.5 | 12.4 | Update Draft Design Document | E | 2008-08-01 08:00 | 2008-08-11 17:00 |  | R |  |  |  |  | 2008-08-11 17:00 |  |  |  |  | 2008-09-15 17:00
| 12.6 | 12.5 | Design Document Approval (Technical Team) | E | 2008-08-12 08:00 | 2008-08-13 17:00 |  | R |  |  |  |  | 2008-08-13 17:00 | [8 empty] | 2008-10-13 17:00
| 12.7 | 12.6 | Milestone: Design Documentation Approved | E | 2008-08-14 08:00 | 2008-08-14 17:00 |  | R | 2008-07-15 17:00 |  |  |  | 2008-08-14 17:00
| 12.8 | 12.28 | Final Updates based on Management Acceptance Presentation | E | 2008-08-29 08:00 | 2008-09-03 17:00 |  | R | 2008-07-17 17:00 | [6 empty] | 2008-09-03 17:00
| 12.10 |  | Modeling | H | 2008-07-18 08:00 | 2008-10-03 17:00 |  | R |  | 2008-07-21 17:00 | [9 empty] | 2008-10-03 17:00
| 12.11 |  | Model complete and sent to NCI team | E | 2008-07-18 08:00 | 2008-07-18 17:00 |  | R | 2008-07-18 17:00 |  | 2008-08-01 17:00
| 12.12 | 12.11F | Complete Model Annotations and Updates | E | 2008-08-04 08:00 | 2008-08-08 17:00 |  | R |  |  |  | 2008-08-08 17:00 |  | 2008-08-21 17:00
| 12.13 | 12.12 | Review Model Annotations and Updates | E | 2008-08-11 08:00 | 2008-09-05 17:00 |  | R | [7 empty] | 2008-09-05 17:00
| 12.14 | 12.13 | Finalize Model Updates (based on review feedback) | E | 2008-09-08 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00 |  |  | 2008-10-02 17:00
| 12.15 | 12.14 | Load Model to caDSR Sandbox | E | 2008-09-15 08:00 | 2008-09-26 17:00 |  | R | [10 empty] | 2008-09-26 17:00 |  |  | 2008-10-13 17:00
| 12.16 | 12.15 | Load Model to caDSR Production | E | 2008-09-29 08:00 | 2008-10-03 17:00 |  | R | [11 empty] | 2008-10-03 17:00 |  | 2008-10-13 17:00
| 12.17 | 12.29 | Incorporate Changes from Design Meeting (Depending on Changes) | E | 2008-09-05 08:00 | 2008-09-11 17:00 |  | R | [8 empty] | 2008-09-11 17:00
| 12.18 | 12.17 | Milestone: Modeling Complete | M | 2008-09-12 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 12.20 |  | Grid Implementation | H | 2008-06-30 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 12.21 |  | Service Metadata | C | 2008-06-30 08:00 | 2008-07-04 17:00 |  | R
| 12.22 | 12.21 | Query | C | 2008-07-07 08:00 | 2008-07-10 17:00 |  | R
| 12.23 | 12.22 | Extensions | C | 2008-07-11 08:00 | 2008-07-16 17:00 |  | R | 2008-07-16 17:00
| 12.24 | 12.29 | Incorporate Changes from Design Meeting | C | 2008-09-05 08:00 | 2008-09-11 17:00 |  | R | [8 empty] | 2008-09-11 17:00
| 12.25 | 12.24 | Milestone: Grid Implementation Complete | M | 2008-09-12 08:00 | 2008-09-12 17:00 |  | R | [8 empty] | 2008-09-12 17:00
| 12.27 |  | Management Acceptance | H | 2008-08-22 08:00 | 2008-09-15 17:00 |  | R | [9 empty] | 2008-09-15 17:00
| 12.28 | 12.7FS | Presentation of Design and Modeling Efforts | E | 2008-08-22 08:00 | 2008-08-22 17:00 |  | R | [5 empty] | 2008-08-22 17:00
| 12.29 | 12.28, | Milestone: Approval of Design | M | 2008-09-04 08:00 | 2008-09-04 17:00 |  | R | [7 empty] | 2008-09-04 17:00
| 12.30 | 12.29 | Implementation Presentation | C | 2008-09-15 08:00 | 2008-09-15 17:00 |  | R | [9 empty] | 2008-09-15 17:00
| 12.31 | 12.30 | Milestone: LexEVS Grid Services Approved | M | 2008-09-15 17:00 | 2008-09-15 17:00 |  | R | [9 empty] | 2008-09-15 17:00
| 12.33 |  | Deployment | H | 2008-07-14 08:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
| 12.34 |  | Modify Code Structure to that of EVS Grid Service | C | 2008-07-14 08:00 | 2008-07-15 17:00 |  | R | 2008-07-15 17:00
| 12.35 | 12.34 | Incorporate convenience scripts from EVS Grid Service | C | 2008-07-16 08:00 | 2008-07-17 17:00 |  | R | 2008-07-17 17:00
| 12.36 | 12.35 | Check codebase into LexEVS SVN Repository | C | 2008-07-18 08:00 | 2008-07-21 17:00 |  | R |  | 2008-07-21 17:00
| 12.37 |  | ARC | C | 2008-07-21 08:00 | 2008-08-01 17:00 |  | R |  |  | 2008-08-01 17:00
| 12.38 |  | Finalize ARC for submission | C | 2008-07-21 08:00 | 2008-07-25 17:00 |  | R |  | 2008-07-25 17:00
| 12.39 | 12.38 | Schedule/Attend ARC Meeting | C | 2008-07-28 08:00 | 2008-08-01 17:00 |  | R |  |  | 2008-08-01 17:00
| 12.40 | 12.36 | Deploy to DEV (Using Automated Build Process) | C | 2008-07-31 08:00 | 2008-08-21 17:00 |  | R | [5 empty] | 2008-08-21 17:00
| 12.41 |  | Milestone - Dependency on EVS API 4.2 DEV Deployment | M | 2008-07-31 08:00 | 2008-07-31 08:00 |  | R |  |  | 2008-07-31 08:00
| 12.42 |  | Jboss installation | C | 2008-08-05 08:00 | 2008-08-13 17:00 |  | R |  |  |  |  | 2008-08-13 17:00
| 12.43 | 12.42 | Promote to NCI Dev (1st NCI Deployment) | C | 2008-08-14 08:00 | 2008-08-15 17:00 |  | R |  |  |  |  | 2008-08-15 17:00
| 12.44 | 12.43 | Execute Junit Tests/Bug Fixes | C | 2008-08-18 08:00 | 2008-08-21 17:00 |  | R | [5 empty] | 2008-08-21 17:00
| 12.45 |  | Deploy to QA | C | 2008-08-22 08:00 | 2008-09-05 17:00 |  | R | [7 empty] | 2008-09-05 17:00
| 12.46 | 12.44 | Draft Deployment Request | C | 2008-08-22 08:00 | 2008-08-22 10:00 |  | R | [5 empty] | 2008-08-22 10:00
| 12.47 |  | Milestone - Dependency on EVS API 4.2 QA Deployment | M | 2008-08-28 08:00 | 2008-08-28 08:00 |  | R | [6 empty] | 2008-08-28 08:00
| 12.48 | 12.47 | Promote to QA | C | 2008-08-28 08:00 | 2008-09-01 17:00 |  | R | [7 empty] | 2008-09-01 17:00
| 12.49 | 12.48 | Execute Junit Tests/Bug Fixes | C | 2008-09-02 08:00 | 2008-09-03 17:00 |  | R | [7 empty] | 2008-09-03 17:00
| 12.50 | 12.48 | Schedule AppScan Test | M | 2008-09-04 08:00 | 2008-09-04 08:00 |  | R | [7 empty] | 2008-09-04 08:00
| 12.51 | 12.50 | Execute AppScan | C | 2008-09-04 08:00 | 2008-09-05 17:00 |  | R | [7 empty] | 2008-09-05 17:00
| 12.52 |  | Deploy to STAGE | C | 2008-10-01 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 12.53 |  | Draft Deployment Request | C | 2008-10-01 08:00 | 2008-10-01 10:00 |  | R | [11 empty] | 2008-10-01 10:00
| 12.54 |  | Milestone - Dependency on EVS API 4.2 STAGE Deployment | M | 2008-10-06 08:00 | 2008-10-06 08:00 |  | R | [12 empty] | 2008-10-06 08:00
| 12.55 | 12.54 | Promote to Staging | C | 2008-10-06 08:00 | 2008-10-07 17:00 |  | R | [12 empty] | 2008-10-07 17:00
| 12.56 |  | Milestone - Dependency on EVS API 4.2 STAGE Deployment with caDSR Fix | M | 2008-10-28 08:00 | 2008-10-28 08:00 |  | R | [14 empty] | 2008-10-24 08:00 | 2008-10-28 08:00
| 12.58 | 12.57 | Execute Tests | C | 2008-10-30 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 12.59 |  | Deploy to PRODUCTION | T | 2008-10-31 08:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
| 12.60 | 12.58 | Draft Deployment Request | T | 2008-10-31 08:00 | 2008-10-31 10:00 |  | G | [15 empty] | 2008-10-31 10:00
| 12.61 |  | Milestone - Dependency on EVS API 4.2 PROD Deployment | M | 2008-11-03 08:00 | 2008-11-03 08:00 |  | G | [16 empty] | 2008-11-03 08:00
| 12.62 | 12.61 | Promote to Production | T | 2008-11-03 08:00 | 2008-11-04 17:00 |  | G | [16 empty] | 2008-11-04 17:00
| 12.63 | 12.62 | Execute Test cases | T | 2008-11-05 08:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
| 12.65 | 12.63 | Milestone: LexEVS Grid Services Released | M | 2008-11-05 17:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
R
| 13 |  | BioMed GT
| 13.1 |  | Inception | H | 2008-09-29 08:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 13.9 |  | Elaboration | H | 2008-09-29 08:00 | 2008-11-18 12:00 |  | G | [18 empty] | 2008-11-18 12:00
| 13.10 |  | Iteration 5 | E | 2008-09-29 08:00 | 2008-10-02 17:00 |  | R | [11 empty] | 2008-10-02 17:00
| 13.11 |  | Requirements | E | 2008-09-29 08:00 | 2008-09-29 17:00 |  | R | [11 empty] | 2008-09-29 17:00
| 13.12 |  | Determine Gforge items to include in Iteration | E | 2008-09-29 08:00 | 2008-09-29 17:00 |  | R | [11 empty] | 2008-09-29 17:00
| 13.13 | 13.11 | Analysis and Design | E | 2008-09-30 08:00 | 2008-09-30 17:00 |  | R | [11 empty] | 2008-09-30 17:00
| 13.14 |  | Determine effort for Gforge items | E | 2008-09-30 08:00 | 2008-09-30 17:00 |  | R | [11 empty] | 2008-09-30 17:00
| 13.15 | 13.13 | Project Management | E | 2008-10-01 08:00 | 2008-10-02 17:00 |  | R | [11 empty] | 2008-10-02 17:00
| 13.16 |  | Update Confluence Wiki | E | 2008-10-01 08:00 | 2008-10-02 17:00 |  | R | [11 empty] | 2008-10-02 17:00
| 13.17 | 13.36 | Iteration 6 | E | 2008-10-31 08:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
| 13.18 |  | Requirements | E | 2008-10-31 08:00 | 2008-10-31 17:00 |  | G | [15 empty] | 2008-10-31 17:00
| 13.19 |  | Determine Gforge items to include in Iteration | E | 2008-10-31 08:00 | 2008-10-31 17:00 |  | G | [15 empty] | 2008-10-31 17:00
| 13.20 | 13.18 | Analysis and Design | E | 2008-11-03 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 13.21 |  | Determine effort for Gforge items | E | 2008-11-03 08:00 | 2008-11-03 17:00 |  | G | [16 empty] | 2008-11-03 17:00
| 13.22 | 13.20 | Project Management | E | 2008-11-04 08:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
| 13.23 |  | Update Confluence Wiki | E | 2008-11-04 08:00 | 2008-11-05 17:00 |  | G | [16 empty] | 2008-11-05 17:00
| 13.24 | 13.17 | Iteration 7 | E | 2008-11-06 08:00 | 2008-11-11 17:00 |  | G | [17 empty] | 2008-11-11 17:00
| 13.25 |  | Requirements | E | 2008-11-06 08:00 | 2008-11-06 17:00 |  | G | [16 empty] | 2008-11-06 17:00
| 13.26 |  | Determine Gforge items to include in Iteration | E | 2008-11-06 08:00 | 2008-11-06 17:00 |  | G | [16 empty] | 2008-11-06 17:00
| 13.27 | 13.25 | Analysis and Design | E | 2008-11-07 08:00 | 2008-11-07 17:00 |  | G | [16 empty] | 2008-11-07 17:00
| 13.28 |  | Determine effort for Gforge items | E | 2008-11-07 08:00 | 2008-11-07 17:00 |  | G | [16 empty] | 2008-11-07 17:00
| 13.29 | 13.27 | Project Management | E | 2008-11-10 08:00 | 2008-11-11 17:00 |  | G | [17 empty] | 2008-11-11 17:00
| 13.30 |  | Update Confluence Wiki | E | 2008-11-10 08:00 | 2008-11-11 17:00 |  | G | [17 empty] | 2008-11-11 17:00
| 13.31 | 13.24 | Continued Iteration planning | E | 2008-11-12 08:00 | 2008-11-18 12:00 |  | G | [18 empty] | 2008-11-18 12:00
| 13.32 |  | Determine iterations for CTCAE work | E | 2008-11-12 08:00 | 2008-11-13 12:00 |  | G | [17 empty] | 2008-11-13 12:00
| 13.33 | 13.32 | Determine iterations for feature requests | E | 2008-11-13 13:00 | 2008-11-14 17:00 |  | G | [17 empty] | 2008-11-14 17:00
| 13.34 | 13.33 | Determine iterations for new users | E | 2008-11-17 08:00 | 2008-11-18 12:00 |  | G | [18 empty] | 2008-11-18 12:00
| 13.35 |  | Construction | H | 2008-04-02 08:00 | 2009-05-21 17:00 |  | G | [44 empty] | 2009-05-21 17:00
| 13.36 | 13.10 | Iteration 5 - CTCAE | C | 2008-10-14 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 13.37 |  | Implementation | C | 2008-10-14 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 13.38 |  | Bug fixes for CTCAE | C | 2008-10-20 08:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 13.39 |  | Create dummy SOC | C | 2008-10-20 08:00 | 2008-10-21 17:00 |  | R | [14 empty] | 2008-10-21 17:00
| 13.40 |  | Add delete status to CTCAE | C | 2008-10-14 08:00 | 2008-10-14 17:00 |  | R | [13 empty] | 2008-10-14 17:00
| 13.41 |  | Remove split status from CTCAE | C | 2008-10-14 08:00 | 2008-10-14 17:00 |  | R | [13 empty] | 2008-10-14 17:00
| 13.42 |  | Add child concept investigation | C | 2008-10-24 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 13.43 |  | Deployment | C | 2008-10-24 08:00 | 2008-10-29 17:00 |  | R | [15 empty] | 2008-10-29 17:00
| 13.44 |  | Deploy to BMI Dev3 | C | 2008-10-24 08:00 | 2008-10-24 12:00 |  | R | [14 empty] | 2008-10-24 12:00
| 13.45 | 13.44 | Deploy to NCI Mayo Dev | C | 2008-10-24 13:00 | 2008-10-24 17:00 |  | R | [14 empty] | 2008-10-24 17:00
| 13.46 | 13.49 | Deploy to NCI QA | C | 2008-10-27 13:00 | 2008-10-29 12:00 |  | R | [15 empty] | 2008-10-29 12:00
| 13.47 | 13.46S | Create Deployment Request for Stage | C | 2008-10-27 13:00 | 2008-10-29 12:00 |  | R | [15 empty] | 2008-10-29 12:00
| 13.48 |  | Test | C | 2008-10-27 08:00 | 2008-10-29 17:00 |  | R | [15 empty] | 2008-10-29 17:00
| 13.49 | 13.45 | Mayo Dev testing | C | 2008-10-27 08:00 | 2008-10-27 12:00 |  | R | [15 empty] | 2008-10-27 12:00
| 13.50 | 13.46 | QA testing | C | 2008-10-29 13:00 | 2008-10-29 17:00 |  | R | [15 empty] | 2008-10-29 17:00
| 13.51 |  | Iteration 6 | C | 2008-10-27 08:00 | 2008-11-13 12:00 |  | G | [17 empty] | 2008-11-13 12:00
| 13.52 |  | Implementation | C | 2008-10-27 08:00 | 2008-11-06 17:00 |  | G | [16 empty] | 2008-11-06 17:00
| 13.53 |  | Bug fixes | C | 2008-10-27 08:00 | 2008-10-28 17:00 |  | R | [15 empty] | 2008-10-28 17:00
| 13.54 |  | Single concept updates | C | 2008-10-27 08:00 | 2008-10-31 17:00 |  | G | [15 empty] | 2008-10-31 17:00
| 13.55 |  | Workflow proposal | C | 2008-10-27 08:00 | 2008-10-31 17:00 |  | G | [15 empty] | 2008-10-31 17:00
| 13.56 | 13.55 | Testing for workflow | C | 2008-11-03 08:00 | 2008-11-04 17:00 |  | G | [16 empty] | 2008-11-04 17:00
| 13.57 |  | Add child concept | C | 2008-10-31 08:00 | 2008-11-06 17:00 |  | G | [16 empty] | 2008-11-06 17:00
| 13.58 |  | Complete LexWiki evidence attachment | C | 2008-10-27 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 13.59 | 13.52 | Deployment | C | 2008-11-07 08:00 | 2008-11-13 12:00 |  | G | [17 empty] | 2008-11-13 12:00
| 13.60 |  | Deploy to BMI Dev3 | C | 2008-11-07 08:00 | 2008-11-07 12:00 |  | G | [16 empty] | 2008-11-07 12:00
| 13.61 | 13.60 | Deploy to NCI Mayo Dev | C | 2008-11-07 13:00 | 2008-11-10 12:00 |  | G | [17 empty] | 2008-11-10 12:00
| 13.62 | 13.65 | Deploy to NCI QA | C | 2008-11-11 13:00 | 2008-11-12 12:00 |  | G | [17 empty] | 2008-11-12 12:00
| 13.63 | 13.62S | Create Deployment Request for Stage | C | 2008-11-11 13:00 | 2008-11-12 12:00 |  | G | [17 empty] | 2008-11-12 12:00
| 13.64 |  | Test | C | 2008-11-10 13:00 | 2008-11-13 12:00 |  | G | [17 empty] | 2008-11-13 12:00
| 13.65 | 13.61 | Mayo Dev testing | C | 2008-11-10 13:00 | 2008-11-11 12:00 |  | G | [17 empty] | 2008-11-11 12:00
| 13.66 | 13.62 | QA testing | C | 2008-11-12 13:00 | 2008-11-13 12:00 |  | G | [17 empty] | 2008-11-13 12:00
| 13.67 | 13.51 | Iteration 7 | C | 2008-11-13 13:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 13.68 |  | Implementation | C | 2008-11-13 13:00 | 2008-11-28 12:00 |  | G | [19 empty] | 2008-11-28 12:00
| 13.69 |  | Load Radlex | C | 2008-11-13 13:00 | 2008-11-20 12:00 |  | G | [18 empty] | 2008-11-20 12:00
| 13.70 | 13.69 | Load NPO | C | 2008-11-20 13:00 | 2008-11-28 12:00 |  | G | [19 empty] | 2008-11-28 12:00
| 13.71 | 13.68 | Deployment | C | 2008-11-28 13:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 13.72 |  | Deploy to BMI Dev3 | C | 2008-11-28 13:00 | 2008-11-28 17:00 |  | G | [19 empty] | 2008-11-28 17:00
| 13.73 | 13.72 | Deploy to NCI Mayo Dev | C | 2008-12-01 08:00 | 2008-12-01 17:00 |  | G | [20 empty] | 2008-12-01 17:00
| 13.74 | 13.77 | Deploy to NCI QA | C | 2008-12-02 13:00 | 2008-12-04 12:00 |  | G | [20 empty] | 2008-12-04 12:00
| 13.75 | 13.74S | Create Deployment Request for Stage | C | 2008-12-02 13:00 | 2008-12-04 12:00 |  | G | [20 empty] | 2008-12-04 12:00
| 13.76 |  | Test | C | 2008-12-02 08:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 13.77 | 13.73 | Mayo Dev testing | C | 2008-12-02 08:00 | 2008-12-02 12:00 |  | G | [20 empty] | 2008-12-02 12:00
| 13.78 | 13.74 | QA testing | C | 2008-12-04 13:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 13.79 |  | Enhancements development | C | 2008-09-29 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 13.80 |  | Simpler results page | C | 2008-09-29 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 13.81 |  | Semantics form - dialog box | C | 2008-09-29 08:00 | 2008-10-10 17:00 |  | R | [12 empty] | 2008-10-10 17:00
| 13.82 |  | Change/enlarge font sizes | C | 2008-09-29 08:00 | 2008-10-01 17:00 |  | R | [11 empty] | 2008-10-01 17:00
| 13.83 |  | Change color of + and - | C | 2008-09-29 08:00 | 2008-09-30 17:00 |  | R | [11 empty] | 2008-09-30 17:00
| 13.84 |  | Add functionality to open new page clicking category | C | 2008-09-29 08:00 | 2008-10-03 17:00 |  | R | [11 empty] | 2008-10-03 17:00
| 13.85 |  | Adding propose retirement | C | 2008-09-29 08:00 | 2008-10-03 17:00 |  | R | [11 empty] | 2008-10-03 17:00
| 13.86 |  | CTCAE work | C | 2008-04-02 08:00 | 2009-05-21 17:00 |  | G | [44 empty] | 2009-05-21 17:00
| 13.87 |  | Complete Iteration 2 of Wiki | C | 2009-03-02 08:00 | 2009-03-10 17:00 |  | G | [34 empty] | 2009-03-10 17:00
| 13.88 |  | Iteration 3 of CTCAE | C | 2008-04-02 08:00 | 2008-04-08 17:00 |  | R
| 13.89 |  | Develop terminological view of CTCAE | C | 2009-03-25 13:00 | 2009-04-22 13:00 |  | G | [40 empty] | 2009-04-22 13:00
| 13.90 |  | Develop Export for final CTCAE4 | C | 2009-04-22 13:00 | 2009-05-13 13:00 |  | G | [43 empty] | 2009-05-13 13:00
| 13.91 |  | Final CTCAE3 proposal processing | C | 2009-05-19 08:00 | 2009-05-21 17:00 |  | G | [44 empty] | 2009-05-21 17:00
| 13.92 |  | Transition | H | 2008-10-30 08:00 | 2009-05-26 17:00 |  | G | [45 empty] | 2009-05-26 17:00
| 13.93 |  | Iteration 5 | T | 2008-10-30 08:00 | 2008-10-31 12:00 |  | G | [15 empty] | 2008-10-31 12:00
| 13.94 | 13.50 | Deploy to Stage | T | 2008-10-30 08:00 | 2008-10-30 17:00 |  | G | [15 empty] | 2008-10-30 17:00
| 13.95 | 13.50 | Stage/Production testing | T | 2008-10-30 08:00 | 2008-10-30 12:00 |  | R | [15 empty] | 2008-10-30 12:00
| 13.96 | 13.95 | Review/Acceptance by users | T | 2008-10-30 13:00 | 2008-10-31 12:00 |  | G | [15 empty] | 2008-10-31 12:00
| 13.97 |  | Iteration 6 | T | 2008-11-12 13:00 | 2008-11-17 17:00 |  | G | [18 empty] | 2008-11-17 17:00
| 13.98 | 13.62 | Deploy to Stage | T | 2008-11-12 13:00 | 2008-11-14 12:00 |  | G | [17 empty] | 2008-11-14 12:00
| 13.99 | 13.98 | Stage/Production testing | T | 2008-11-14 13:00 | 2008-11-14 17:00 |  | G | [17 empty] | 2008-11-14 17:00
| 13.100 | 13.99 | Review/Acceptance by users | T | 2008-11-17 08:00 | 2008-11-17 17:00 |  | G | [18 empty] | 2008-11-17 17:00
| 13.101 |  | Iteration 7 | T | 2008-12-02 13:00 | 2008-12-05 17:00 |  | G | [20 empty] | 2008-12-05 17:00
| 13.102 | 13.77 | Deploy to Stage | T | 2008-12-02 13:00 | 2008-12-04 12:00 |  | G | [20 empty] | 2008-12-04 12:00
| 13.103 | 13.102 | Stage/Production testing | T | 2008-12-04 13:00 | 2008-12-04 17:00 |  | G | [20 empty] | 2008-12-04 17:00
| 13.104 | 13.103 | Review/Acceptance by users | T | 2008-12-05 08:00 | 2008-12-05 17:00 |  | G | [20 empty] | 2008-12-05 17:00
| 13.106 |  | Deployment of Iteration 2 CTCAE | T | 2009-03-11 08:00 | 2009-03-12 17:00 |  | G | [34 empty] | 2009-03-12 17:00
| 13.107 |  | 2nd deployment of Iteration 2 with changes | T | 2009-04-07 08:00 | 2009-04-08 17:00 |  | G | [38 empty] | 2009-04-08 17:00
| 13.108 |  | Deployment of Final CTCAE | T | 2009-05-22 08:00 | 2009-05-26 17:00 |  | G | [45 empty] | 2009-05-26 17:00
R
| 14 |  | Enter New Project Name |  |  |  |  | R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
R
| END | END | END | END | END | END
Formulas:
Start = MIN([Start, row below]:G661)
Due = MAX([Due, row below]:H661)
Note on C194: 17143 - Receive error message when open xmi
Note on C195: 17169 - Error when using CaAdapter GME_10_10_2008 open xsd and xmi files
Note on C196: 17257 - Test failed on newSample.xmi in caAdapter\GME\beta_2008_10_20 for GME (
Note on C197: 17271 - caadapter4_0_Bin_10_10_08 generated GME NAMESPACE TAG failed in SDK_41_10142008
Note on C147: This is for the cross product implementation for GME Namespaces
Note on C151: caAdapter Fixes for GME Namespace
Note on C152: caAdapter Fixes for GME Namespace
Note on C157: GME Namespace
We Are Here

## Projects
caDSR
caAdapter
caCORE SDK
COPPA | Warning:
GME NameSpace | Project Names Are Case Sensitive, Please be careful NOT to add the same project twice.
Common Logging Module(CLM)
Common Security Module (CSM) | Please make sure to copy over the Project name to the "Detailed Plan Tab"
Enterprise Vocabulary Services (EVS) - API | Under Col "E" or "Tasks" Col.
EVS - BioPortal
EVS - Protégé
Lex EVS
Lex EVS Gridservice
BioMed GT