# US CMS Storage Manager Milestones

Milestones are separated into two levels. Level 3 milestones are internal within the Storage Manager project, Level 2 milestones are internal to the US CMS DAQ project and Level 1 milestones are communicated to the overall US CMS project. The Tag refers to the milestone type (hardware or software) and the responsible institution.

| Milestone | Date | Type | Tag | Description |
| --- | --- | --- | --- | --- |
| Prototype Hardware System functional | Jan 28, 2008 Met Jan 24 | L2 | Hardware MIT | Basic functionality of DAQ configuration writing data to SATABeasts |
| Pre-production SMProxyServer version ready for Commissioning | Jan 31, 2008 Met Jan 28 | L2 | Software FNAL | SMProxyServer for DQM archiving and event serving ready for commissioning |
| First SM software version for realistic trigger tables for HLT processing | Jan 31, 2008 Met Jan 30 for SM, (Feb 11 for SM-proxy) | L2 | Software FNAL | First SM Software version with multiple HLT output modules to handle calibration, debug physics, and exception streams. |
| Start of Full DAQ SM function tests | Feb 1, 2008 Met Jan 28 (No multi-HLT, ProxyServ) | L2 | Integration MIT | Functionality and rate tests using the full CMS DAQ including multiple HLT output modules and SMProxyServer. |
| Logger to SATABeast measurements completed | Feb 4, 2008 Met Feb 25 | L2 | Hardware MIT | Complete the preliminary low-level logger-to-SATABeast transfer measurements with current hardware. |
| Connect CERN Tier0 through fiber link | Feb 8, 2008 Met Feb 13 | L2 | Hardware CERN | Fiber link provided by CERN IT |
| Start of SMProxyServer commissioning | Feb 11, 2008 Met Mar 13 during GRUMM | L2 | Software FNAL Integration MIT | Proxy Server commissioning |
| SM code and error handling review | Feb 20, 2008 Met Feb 13 | L3 | Software FNAL | Code review for SM software, and to get input for full error handling and monitoring |
| Tier0 Mock Data Transfer tests | Feb 25, 2008 Met Feb 20 | L2 | Integration MIT | Connectivity with Tier0 and rate tests |
| Prototype SMProxyServer Hardware ready | Feb 29, 2008 Met Apr 22, (production version) | L2 | Hardware CERN | SMProxy Server Hardware available for testing |
| Production SMProxyServer version ready | Mar 1, 2008 Met May 11 | L2 | Software FNAL | Production version of SMProxyServer application ready |
| Prototype Hardware System Ready | Mar 3, 2008 Met Mar 7 | L1 | Hardware MIT | Prototype hardware system ready for CMS operation during March GR |
| SM version with first version error handling and monitoring | Apr 7, 2008 Met May 11 | L2 | Software FNAL Integration MIT | SM software with first version of error handling and monitoring |
| Demonstrate 1/3 full system supports design requirements | Apr 15, 2008 Met Apr 16 | L1 | Hardware MIT Software FNAL | Demonstrate system meets design requirements |
| Produce Disaster Recover Plan | Apr 21, 2008 Draft Mar 6, still waiting for feedback from EvF/DAQ; In progress for hardware | L2 | Software FNAL Hardware Integreation MIT | Plan for error handling, monitoring and disaster recovery documented and design of test procedures |
| Storage Manager Review | May 30, 2008 | L2 | L1 | Storage Manager Review |
| Prototype System Available for CMS | May 5, 2008 Met May 2 (Cruzet-1) | L2 | Hardware MIT | Prototype system integrated with CMS startup DAQ |
| SM software ready for CMS startup | Jul 31, 2008 | L1 | Software FNAL | SM software ready for CMS startup conditions |
| Upgrade SM hardware for CMS startup | Jun 2, 2008 Met Apr 8 | L1 | Hardware MIT | Upgrade hardware for CMS startup (92TB disk) |
| Error handling and performance assessment review | Sep 30, 2008 | L3 | Software FNAL Hardware Integration MIT | Review of error handling and performance from experience with runs |
| SM second version of error handling, and first performance optimization | Nov 30, 2008 | L2 | Software FNAL | SM software version with additional error handling and initial optimization for performance |
| SM Code and SM performance Review | Jan 15, 2009 | L3 | Software FNAL | Review of SM software code and performance |
| SM version with planned error handling, and second performance optimization | Mar 31, 2009 | L2 | Software FNAL | SM software version with planned error handling and more optimized for performance |
| Storage Manager Review | Apr 30, 2009 | L2 | L2 Software FNAL Hardware Integration MIT | Storage Manager Review |
| SM version with planned performance optimization | July 15, 2009 | L2 | Software FNAL | SM software version that includes optimization for the final SM hardware |
| SM software ready for final SM hardware | Aug 15, 2009 | L1 | Software FNAL | SM software ready for final hardware setup |

Storage Manager Milestones