GENETIC VARIATION AMONG SWITCHGRASSES FOR AGRONOMIC TRAITS, FORAGE QUALITY, AND BIOMASS FUEL PRODUCTION

K.P. Vogel

Research Geneticist

USDA-ARS, Lincoln, NE

Cooperating Scientists

| Univ. of Nebraska Lowell Moser, Forage Agronomist and Physiologist Richard Perrin, Agricultural Economist USDA-ARS-Lincoln Gary Varvel, Soil Scientist Vacant, Forage Agronomist/Rangeland Scientist | USDA-ARS-Mandan, ND Jon Hanson, Rangeland Scientist John Berdahl, Plant Breeder - Forages Albert Frank, Plant Physiologist Joseph Krupinsky, Plant Pathologist Mark Liebig, Soil Scientist Holly Johnson, Rangeland Scientist |
| --- | --- |
| South Dakota State University Kevin Kephart, Dean of Experiment Station, Forage Agronomist Arvid Boe, Plant Breeder - Forages James Doolittle, Soil Scientist Thomas Schumacker, Soil Scientist Douglas Malo, Soil Scientist Jin-Ho Lee, Soil Scientist Kenneth Higgins, Wildlife Biologist Vance Owens, Forage Agronomist | USDA-NRCS John Kimble, Soil Scientist Susan Samson-Liebig, Soil Scientist |
| University of Wisconsin Michael Casler, Plant Breeder- Forages | USDA-ARS- Fort Collins, CO. Ronald Follett, Soil Scientist |

1997-2001 Objectives:

(1) 	Continue studies to determine the feasibility of producing F1 switchgrass hybrid cultivars and quantify the extent of heterosis for biomass yield;

(2)	Continue the development of  switchgrass cultivars for USDA Plant Hardiness Zones  2,3, 4, and 5 using conventional grass breeding methods and evaluate improved strains in regional trials;

(3) 	Continue molecular genetic studies on classifying switchgrass germplasm and developing molecular genetic markers;

(4) 	Evaluate, develop, and test switchgrass cultivars for Northern Midwest and Great Lakes States (Hardiness zones 2,3, & upper 4) in cooperation with Dr. Michael Casler at the University of Wisconsin.

In 1999,  project  expanded at the request of the Oak Ridge National Laboratory:

(5) 	Development of a white paper on the assessment of the potential for genetic modification of herbaceous plants for fuel feedstock;

(6) 	Establish switchgrass field trials in North Dakota in cooperation with the USDA-ARS Northern Plains Research Laboratory, Mandan, ND (ARS-Mandan) to assess the biomass yield of switchgrass cultivars in North Dakota;

(7) 	Establish switchgrass field trials in South Dakota in Cooperation with South Dakota State University (SDSU) via a Specific cooperative Agreement to assess the biomass yield of switchgrass cultivars in South Dakota.

In 2000 at the request of DOE, additional objectives were added:

(8)	Determine the biomass yields of switchgrass grown on commercial scale production fields in potential production regions of Nebraska, South Dakota, and North Dakota.   Determine the economic costs associated with switchgrass biomass production using commercial scale farm equipment by participating farmers.   Research managed and coordinated by ARS-NE and the Univ. of Nebraska.

(9)	Determine and quantify the environmental benefits associated with switchgrass biomass production in the upper plains including changes in soil carbon levels and other changes in soil quality.

(A)	Compare carbon sequestration and yields of switchgrass grown for biomass compared with no-till corn at varying productivity levels induced by N fertility treatments. ARS-NE, ARS-CO, NRCS.

(B)	Evaluate carbon sequestration in switchgrass fields in on-farm trials and adjacent crop land.  ARS-NE, ARS-Mandan, NRCS.

(C)	Evaluate the efficiency and extent of soil carbon storage in selected switchgrass stands throughout ND, SD, and MN; in doing so, determine the potential effects of switchgrass on soil quality. ARS-Mandan.

(10.)  Evaluate the yield potential and production economics of managing former CRP grasslands as a biomass cropping system.  Determine the best agronomic practices for converting and managing former CRP for use in biomass production.  Determine effects of management practices including harvesting schemes on wildlife habitat quality.  Determine effect of management of former CRP as a biomass crop on soil quality including changes in soil carbon.  Research managed and coordinated by South Dakota State University (SDSU).

(11.)  Develop new technologies and plant germplasm to address specific production problems including:

(A) Develop methods for quantifying switchgrass seed quality in terms of its capability to produce established plants under field conditions.  Cooperative  research, R. Masters & L. Moser, ARS-NE and Univ. of Nebraska.

(B)	 Identify, evaluate, and obtain agronomic information that will lead to the registration of herbicides for controlling weeds in switchgrass during establishment.  R. Masters, ARS-NE.

(C) Determine the mineral nutrient requirements of switchgrass in the upper Great Plains.  ARS-Mandan.

(D) 	Determine if cultivars need to be developed for the more arid sections of the Northern Plains region and determine genetic variation in elite breeding lines for biomass production in semi-arid environments.  Arvid Boe, SDSU.

(E)  Monitor and identify disease problems associated with growing switchgrass as a biomass fuel crop and seed production of switchgrass. Joe Krupinsky, ARS-Mandan

1997- 2001 Accomplishment by Objectives.

(1) 	Continue studies to determine the feasibility of producing F1 switchgrass hybrid cultivars and quantify the extent of heterosis for biomass yield;

a.   Basic genetic study completed that demonstrated that switchgrass has a prefertilization incompatibility system that is similar to the S-Z system that exists in other grasses.   Two post fertilization incompatibility systems exist, one among ploidy levels that restrictions the production of viable seed from between ploidy level crosses.   Manuscript completed , will be submitted to Crop Science in Nov.

b.   Field evaluation of two sets of hybrids was completed.  Results indicate that heterosis for biomass yields exists by progeny of some populations and plants from those populations. Upland and lowland ecotypes as represented by Summer and Kanlow represent distinct heterotic groups.   Manuscript in preparation.

c.  A seed production study was completed to determine if acceptable yields of switchgrass seed could be obtained from space-transplanted seed production fields as compared to row and solid stands.  Results were positive.  Manuscript in preparation.

Research will continue in new project.

(2)	Continue the development of  switchgrass cultivars for USDA Plant Hardiness Zones  2,3, 4, and 5 using conventional grass breeding methods and evaluate improved strains in regional trials;

a. Research continued with several populations.  New selection criteria developed.  Seedling tiller number at six weeks.   A.S. Smart Ph.D Dissertation.

Table 2.3. Mean tiller number and shoot weight averaged over two experiments of populations developed by two cycles of divergent selection for seedling tiller number while selecting for high shoot weight in switchgrass seedlings 6 to 8 wk after planting.

| Population | Cycle | Mean tiller number | Shoot weight g plant-1 |
| --- | --- | --- | --- |
| Base | 0 | 1.62 | 0.39 |
| SWMT | 1 | 2.05 | 0.39 |
| SWMT | 2 | 2.01 | 0.41 |
| SWST | 1 | 1.41 | 0.45 |
| SWST | 2 | 1.23 | 0.52 |

Table 4.1. August plant height (H), leaf width (W), leaf length (L), and number of tillers per plant (T) averaged over two experiments, measured on big bluestem and switchgrass mature plants developed by divergent selection for seedling tiller number while selecting for high shoot weight.

| Species | Type † | H cm. | W mm | L mm | T |
| --- | --- | --- | --- | --- | --- |
| Switchgrass | SWMT-C2 | 84 | 8.9 | 33 | 119 |
|  | SWST-C2 | 92 | 11.4 | 38 | 80 |

Table 4.3.  Number of tillers per plant (T), yield per plant (YPP), and yield per tiller (YPT) measured with a single end-of-season harvest on 10 October 2000 from second production year of big bluestem and switchgrass space-planted transplants developed by divergent selection for seedling tiller number while selecting for high shoot weight in Lincoln, NE.

| Species | Type† | T | YPP | YPT |
| --- | --- | --- | --- | --- |
| Switchgrass | SWMT-C2 | 301 | 853 g | 2.8 g |
|  | SWST-C2 | 201 | 1029 g | 5.1 g |

3.  Molecular Genetics Studies.

a.   Determined that chloroplast DNA in switchgrass is maternally inherited.   Demonstrated that normal chromosome pairing occurs in upland/lowland tetraploid hybrids indicating that they have the same genome.

Martinez-Reyna, J.M., K.P. Vogel*, Carol Caha, and Donald J. Lee. 2001.  Meiotic stability, chloroplast DNA polymorphisms, and morphological traits of upland x lowland switchgrass reciprocal hybrids. Crop Sci. 41:1579-1583.

b.  Parent clones and progenies of Summer x Kanlow hybrids were sent to Oak Ridge and Univ. of Georgia for use in marker research.

In future, emphasis will be on devloping populations that differ for specific traits to be used in marker studies.

4.  Breeding switchgrass for the Upper Midwest and Lake States.

Research conducted by Dr. Michael Casler, Univ. of Wisconsin.

Research reported by Dr. Casler.

Objectives Added in 1999.

Objective 5.  White paper.

a.   “White paper” entitled   “Genetic Improvement of Switchgrass and Other Herbaceous Plants for use as Biomass Fuel Feedstock” was prepared  by K. P. Vogel and H. G. Jung, USDA-ARS, and delivered to the Oak Ridge National Laboratory on 15 February, 2000.

Paper expanded and published as:

Vogel, K.P. and H.G. Jung. 2001.  Genetic modification of herbaceous plants for feed and fuel.  Critical Reviews in Plant Sciences. 20:15-49.

Objective 6. Evaluate switchgrass field trials in North Dakota to assess the biomass yield of switchgrass cultivars in North Dakota

a.   Research conducted and reported  by ARS- Mandan.

Objective 7.   Evaluate switchgrass cultivars in field trials in South Dakota.

a.   Research conducted and reported by South Dakota State University (SDSU).

Additional Objectives Added in FY 2000.

Objective 8.   Determine the biomass yields of switchgrass grown on commercial scale production fields in potential production regions of Nebraska, South Dakota, and North Dakota.

Determine the economic costs associated with switchgrass biomass production using commercial scale farm equipment by participating farmers.

USDA-ARS Lincoln provides technical support for the project and Dr. Richard Perrin, University of Nebraska Agricultural Economist  conducts economic analysis on the project and manage farmer contracts via a Specific Cooperative Agreement between the University of Nebraska and USDA-ARS.

In 2000,   Contracts established with 4 farmers in Nebraska.  Fields planted.  Due to a severe drought, establishment problems developed, however, only one field had to be replanted in 2001.

In 2001,   Contracts established with 4 farmers in South Dakota and three farms in North Dakota. Fields were planted.   Stand failure occurred on one farm.

Biomass yields were harvested on three of the Nebraska Farms in 2001.  Yield and economic data were collected.

Objective 9.  Determine and quantify the environmental benefits associated with switchgrass biomass production in the upper plains including changes in soil carbon levels and other changes in soil quality.

Objective 9A.  A multi-purpose study. Objectives are:

Determine soil C fixation with switchgrass biomass production in comparison to no-till corn;

Compare production economics of ethanol production for corn vs switchgrass biomass with field scale plots;

Determine the extent of N and soil mineral utilization in switchgrass grown as a biomass crop during a ten year period.    Biomass and corn yields will be harvested for 10 years.

Cooperating  scientists are  K. Vogel USDA-ARS Lincoln - biomass production; Gary Varvel, USDA-ARS Lincoln - corn production; Ron Follett, USDA-ARS Ft. Collins, John Kimble and Susan Samson-Leibig, USDA-NRCS-NSSC, Lincoln, NE.

Map, Tables 20 & 21.

Objective 9B.  Evaluate carbon sequestration in switchgrass fields in on-farm trials and adjacent crop land.  ARS-NE, ARS-Mandan and NRCS.

The switchgrass biomass production fields in the on-farm trials in Nebraska, South Dakota, and North Dakota are being used to obtain field scale estimates of carbon sequestration.

Baseline soil samples were collected on all fields either prior to planting or within six weeks of switchgrass emergence.

Soils will be sampled at the end of the five year period.

Objective 9C. Evaluate the efficiency and extent of soil carbon storage in selected switchgrass stands throughout ND, SD, and MN; in doing so, determine the potential effects of switchgrass on soil quality. ARS-Mandan conducting research.  Report by ARS Mandan.

Objective 10. 	 Evaluate the yield potential and production economics of managing former CRP grasslands as a biomass cropping system.  Research managed, coordinated, and reported  by South Dakota State University (SDSU).

Determine the best agronomic practices for converting and managing former CRP for use in biomass production.

Determine effects of management practices including harvesting schemes on wildlife habitat quality.

Determine effect of management of former CRP as a biomass crop on soil quality including changes in soil carbon.

Objective 11. Develop new technologies and plant germplasm to address specific production problems including:

Objective 11A.  Develop methods for quantifying switchgrass seed quality in terms of its capability to produce established plants under field conditions.  Cooperative  research, ARS-NE and Univ. of Nebraska.

Several tests were evaluated on seed lots of three cultivars differing in seed size and conventional germination percentages including:

Germination Rate Index,

Emergence from a graded series of planting depths in sand and;

Accelerated aging 45 or 50o C at high humidity.

Two tests appear to have promising on assessing seed quality.  They are:

1. Emergence from 1.5 to 2 in planting depth in sand and emergence in sand,

2. Acclerated aging at 50o C for 12 to 24 hrs.

Additional laboratory work will be conducted to refine the tests followed by field evaluation trials.

Objective 11B.  Identify, evaluate, and obtain agronomic information that will lead to the registration of herbicides for controlling weeds in switchgrass during establishment.

Based on research conducted previously, the herbicide Plateau is registered for use on planting warm-season grasses and legumes for CRP type plantings.  It is “hot” on Panicums and should be used on switchgrass only when stand loses can be tolerated.

In 2000, a series of experiments were established to evaluate the herbicide “Paramount” for establishment of switchgrass.   Stands were evaluated in late spring of 2001 and biomass yields were harvested in late August or early September.  Data are in the process of being summarized.

Data will indicate that Paramount is a very effective herbicide to use for establishing switchgrass particularily when tank mixed with a broad leaf herbicide such as atrazine.

BASF supplied Paramount for use on on-farm trials in NE, SD, and ND.  Farmers who used Paramount had excellent weed control the establishmeny year and had yields of 2 to 3 tons dry matter per acre.   Farmers who did not use it had weed problems and had reduced yields and did not harvest stands.

Paramount = quinclorac.   Cleared for use in KS, NE, SD, ND, MT, WY, CO, UT, ID, WA, OR for sorghum and wheat and it currently has a supplemental label for use on non-cropland acres.

It is effective in controlling barnyard grass, green, yellow, and giant foxtail, and crabgrass. Also controls some broadleaf weeds.  Primarily used for control of grassy weeds. Rate is 8 oz./acre.

Cotton is highly susceptible to Paramount and it will likely not be marketed in states with significant acres of cotton.  Other sensitive species are Solanaceae, Umbelliferae,   Leguminoseae (alfalfa, green bean) Chenopodiceae, Compositeae

Objective 11C.  Determine the mineral nutrient requirements of switchgrass in the upper Great Plains.  ARS-Mandan

Objective 11D.  Determine if cultivars need to be developed for the more arid sections of the Northern Plains region and determine genetic variation in elite breeding lines for biomass production in semi-arid environments (SDSU).

Objective 11E. Monitor and identify disease problems associated with growing switchgrass as a biomass fuel crop and seed production of switchgrass. Joe Krupinsky, ARS-Mandan.

Additional New Information on Switchgrass:

Switchgrass toxin: Disogenin

Research completed by USDA-ARS Poisonous Plants Research Laboratory at Logan, Utah demonstrates that switchgrass biomass contains the steroidal saponins that have been implicated in the poisoning of she ep and horses.

After hydrolsis of the saponins, diosgenin was determined to be the major sapogenin in switchgrass.

In Kleingrass (Panicum coloradum), the major sapogenin is yamogenin.

Both compounds affect liver function.

Switchgrass and Kleingrass forage are not believed to affect beef cattle.

Thirteen large round bales of switchgrass were trucked to the USDA PPRL for feeding trials.

In 2002, we will sample switchgrass throughout the growing season and send samples to the PPRL to determine concentration levels during the growing season and by plant part.

Lee, Stephen T.; Bryan L.Stegelmeier, Dale R. Gardner, and Kenneth P. Vogel. 2001.  The isolation and identification of steroidal sapogenins in switchgrass.  J. Natural Toxins 10:273-281.

Proposed New Project 2001-2006.

Objective 1.   Develop improved cultivars of switchgrass for use in biomass energy production fields in the Northern Great Plains and the Midwest.  ARS-Lincoln, Univ. of Wisconsin-Madison, South Dakota State University, ARS-Mandan.

A.   Continue research on developing basic breeding and genetics information  to development F1 hybrids of switchgrass.  ARS-Lincoln.

B.  Develop switchgrass cultivars with improved biomass yields for use in the Central Great Plains and Midwest states at the same latitude. ARS-Lincoln

C.  Develop switchgrass cultivars for use in the Northern latitudes of the Great Plains and Midwest states.  University of Wisconsin-Madison.

D. Determine if there are significant genotype x environment interaction effects for switchgrass biomass yields between the humid and more arid regions of the Northern Great Plains.  South Dakota State University.

E.  Determine adaptation and productiviy of experimental strains and check cultivars of switchgrass when managed for biomass production in the Great Plains and the Midwest.  ARS-Lincoln, ARS-Mandan, Univ. of Wisconsin-Madison, South Dakota State University.

Objective 2.  Develop management practices for rapidly converting CRP grasslands into biomass energy production fields in the Northern Great Plains and quantify biomass yields and associated environment effects.  South Dakota State University.

Objective 3.  Determine the field scale yields of switchgrass grown as a dedicated biomass energy crop in the Northern Great Plains, quantify the economic costs of production, and monitor associated environmental effects.  ARS-Lincoln, University of Nebraska-Lincoln, and ARS-Mandan.

Objective 4.   Quantify environmental effects of switchgrass grown as a biomass energy crop in the Northern Great Plains including carbon sequestration.

A.   Determine carbon sequestration of switchgrass grown for biomass in comparative study with no-till corn at varying productivity levels induced by N fertility treatments. ARS-NE, ARS-CO, NRCS.

# B.  Determine effect of managing former CRP grasslands for biomass energy crop production on soil quality including changes in soil carbon concentration.  SDSU.

C.  Evaluate carbon sequestration in switchgrass fields in on-farm trials and adjacent crop land.  ARS-NE, ARS-Mandan, NRCS.

D. Evaluate soil carbon storage in old switchgrass stands throughout ND, SD, and MN and adjacent cropland to determine the potential effects of switchgrass managed as a biomass crop on soil carbon. ARS-Mandan.

E.  Develop a carbon budget for switchgrass in the Northern Great Plains to evaluate the relationship between biomass production and carbon storage of switchgrass. ARS-Mandan.

F.  Determine effects of management practices on converting CRP grasslands and cropland into perennial biomass crop production fields on wildlife habitat quality. SDSU.

Objective 5.   Develop improved management methods and strategies to enhance establishment success, determine mineral nutrient requirements of switchgrass for biomass production, and identify pathogens that can limit productivity of switchgrass.

A.  Develop methods for quantifying switchgrass seed quality in terms of its capability to produce established plants under field conditions.  ARS-NE and Univ. of Nebraska.

B.  Determine the mineral nutrient requirements of switchgrass in the upper Great Plains.  ARS-Mandan.

C.  Monitor and identify disease problems associated with growing switchgrass as a biomass fuel crop and seed production of switchgrass.  ARS-Mandan