Issuance Date:  March 05, 2009

Deadline for receipt of Questions:  March 26, 2009

Closing Date for Submission of Applications:  April 20, 2009

Closing Time for submission of Applications: 14:00 (Nigeria Time)

Subject:   	USAID/Nigeria Request for Applications (RFA) Number USAID-Nigeria-HPN-09-012-RFA: Targeted States High Impact Project (TSHIP)

Dear Sir/Madam:

The United States Agency for International Development (USAID), Nigeria mission is seeking applications from organizations to fund a program entitled “Targeted States High Impact Project (TSHIP).”  The authority for the RFA is found in the Foreign Assistance Act of 1961, as amended.

The Recipient will be responsible for ensuring achievement of the program objectives.  Please refer to the Program Description for a complete statement of goals and expected results.

Pursuant to 22 CFR 226.81, it is USAID policy not to award profit under assistance instruments.  However, all reasonable, allocable, and allowable expenses, both direct and indirect, which are related to the grant program and are in accordance with applicable cost standards (22 CFR 226, OMB Circular A-122 for non-profit organization, OMB Circular A-21 for universities, and the Federal Acquisition Regulation (FAR) Part 31 for-profit organizations, and the Mandatory Standard Provision “Allowable Costs (DEC 2003) for public international organizations), may be paid under the grant.

Subject to the availability of funds, USAID intends to provide approximately $93,200,000 in total USAID funding to be allocated over a five (5) year period.  USAID reserves the right to fund any or none of the applications submitted.

For the purposes of this program, this RFA is being issued and consists of this cover letter and the following:

1.	Section A – Cooperative Agreement Application Format;

2.	Section B – Selection Criteria;

3.	Section C – Program Description;

4.	Section D - Certifications, Assurances, and Other Statements

of Applicant/Grantee;

5.	Section E – Annexes

For the purposes of this RFA, the term "Grant" is synonymous with "Cooperative Agreement"; "Grantee" is synonymous with "Recipient"; and "Grant Officer" is synonymous with "Agreement Officer".

The preferred method of distribution of USAID assistance solicitation information is internet at www.grants.gov.  Click on “Search for Grant Opportunity,” then click on “Browse by Agency” and choose U.S. Agency for International Development, then click on the Opportunity titled “Targeted States High Impact Project (TSHIP).”  If you have difficulty registering or accessing the Request for Applications (RFA), please contact the Grants.gov Helpdesk at 1-800-518-4726 or via e-mail at support@grants.gov for technical assistance.  Receipt of this RFA through grants.gov must be confirmed by written notification to the contact persons noted below.  It is the responsibility of the recipient of the solicitation document to ensure that it has been received from Grants.gov in its entirety.  USAID bears no responsibility for data errors resulting from transmission or conversion processes.

Any questions concerning this RFA should be submitted in writing to Ugo Oguejiofor, Acquisition & Assistance Specialist via e-mail to uoguejiofor@usaid.gov and to abujasolicitations@usaid.gov with copy to Michael Glees at mglees@usaid.gov .  The deadline for submission of questions on this RFA is March 26, 2009 as specified on the first page of this letter.  If you decide to submit an application, it must be received by the closing date and time indicated at the top of this cover letter, at the place designated below for receipt of applications.  Facsimile (fax) submissions are not authorized.

Applicants are requested to submit their applications by e-mail attachment, followed by the hard copies.  See Section A: Preparation and Submission Guidelines and Submission of Applications by E-Mail for full submission instructions.  Applications and modifications thereof shall be submitted in envelopes with the name and address of the applicant and RFA Number – “USAID-Nigeria-HPN-09-012-RFA”.  It is recommended that applicants use courier service instead of international mail for submission of the hard copies.  Following is the submission address:

By Courier or Hand Delivery

Ugo Oguejiofor

Acquisition and Assistance Specialist

USAID/Nigeria

7 – 9 Mambilla Street (Off Aso Drive)

Maitama, Abuja

Nigeria

Tel (234)9-461-9300 (Ext. 9308)

uoguejiofor@usaid.gov

Applicants are requested to submit both technical and cost portions of their application in separate volumes.  To be eligible for award, the applicant must provide all required information in its application, including the requirements found in any attachments to the solicitation in Grants.gov.  Applicants should retain for their records one copy of all enclosures which accompany their applications.  Award will be made to the responsible applicant(s) whose application(s) offers the greatest value.

REQUEST FOR APPLICATIONS

USAID-Nigeria-HPN-09-012-RFA

USAID/NIGERIA

TARGETED STATES HIGH IMPACT PROJECT (TSHIP)

March 05, 2009

TABLE OF CONTENTS

Page

SECTION A – COOPERATIVE AGREEMENT APPLICATION FORMAT …………1

- Preparation and Submission Guidelines……………………………………….1

- Technical Application Format ………………………………………………...3

## 3.	Cost/Business Application Format ……………………………………………9

4.	Cooperative Agreement Award ……………………………………………….11

5.	Authority to Obligate the Government………………………………………...12

6. 	Environmental Compliance Guidance…………………………………………12

SECTION B – SELECTION CRITERIA …………………………………………………14

SECTION C – PROGRAM DESCRIPTION ……………………………………………17

Part A 	- 	Acronyms …………………………………………………………...17

Part B 	-	Introduction …………………………………………………………18

Part C 	-	Background …………………………………………………………21

Part D	-	Technical Approach and Program Interventions ……………………35

Part E 	-	Performance Monitoring and Indicators……………………………..45

Part F	- 	Monitoring and Evaluation ………………………………………….50

Part G 	-	Reporting Requirements …………………………………………….50

Part H 	-	Management Review and Evaluations ………………………………51

Part I 	-	Supporting Information ……………………………………………...52

Part J 	-	Substantial Involvement ……………………………………………..52

Part K	-	Designation of Key Positions and Personnel ………………………………53

SECTION D – CERTIFICATIONS, ASSURANCES AND OTHER STATEMENTS OF

RECIPIENT ……..………………………………………………………...54

PART I – Certifications and Assurances …………………………………………….54

Certifications, Assurances, & Other Statements of Recipient:

http://www.usaid.gov/policy/ads/300/303sad.pdf

PART II – Forms …………………………………………………………………….54

# http://www.grants.gov/agencies/approved_standard_forms.jsp

# Standard Form 424: www.grants.gov/techlib/SF424-V2.0.pdf ;

Standard Form 424A:http://www.grants.gov/techlib/SF424A-V1.0.pdf

Standard Form 424B: http://www.grants.gov/techlib/SF424B-V1.0.pd

OMB Circular A-133 or Similar Audits

SECTION E – ANNEXES …………………………………………………………………55

Annex 1 – List of Reference Documents ……………………………………………56

Annex 2 - Initial Environmental Examination …………………………………...…57

Annex 3 – Branding Strategy and Marking Plan ……………………………………64

Annex 4 – Other Provisions………………………………………………………….74

SECTION A – COOPERATIVE AGREEMENT APPLICATION FORMAT

## 1.	PREPARATION AND SUBMISSION GUIDELINES

All applications received by the deadline will be reviewed for responsiveness and programmatic merit in accordance with the specifications outlined in these guidelines and the application format.  Section B addresses the selection criteria and procedures for the applications.

Applications are to be submitted electronically via e-mail attachments, in accordance with the instructions below “Procedures for Submission of Applications by E-mail,” to be followed by hard copies.

Applications shall be submitted in two separate volumes: (1) technical and (2) cost/business application.  In addition to the e-mail submission, applicants shall submit an original and four (4) hard copies of the technical application and an original and one (1) hard copy of the cost/business application to the address specified on the cover letter.  Faxed applications will not be considered.

The hard copies of applications and modifications thereof shall be submitted in sealed envelopes or packages addressed to the office specified in the cover letter of this RFA, with the RFA number, the name and address of the applicant, and whether the contents contain technical and/or cost applications noted on the outside of the envelopes/packages.  Provided that the e-mail submissions have been successfully received by the due date, the hard copy submissions need not arrive by the due date.  However, they must be received no later than two weeks after receipt of the e-mail submission.  It is recommended that applicants use courier service instead of international mail for submission of the hard copies.  The submission address is specified in the RFA cover letter.

The application should be prepared according to the structural format set forth below in (2) Technical Application Format and (3) Cost/Business Application Format.  Applications must be submitted no later than the date and time indicated on the cover page of this RFA, to the location indicated on the cover letter accompanying this RFA.  Applications which are received late or incomplete run the risk of not being considered in the review process.  Late applications will be considered for award only if the Agreement Officer determines it is in the Government’s interest.

Applicants should retain for their records one copy of the application and all enclosures which accompany their application.  Erasures or other changes must be initialed by the person signing the application.  To facilitate the competitive review of the applications, USAID will consider only applications conforming to the format prescribed below.

Any prospective applicant desiring an explanation or interpretation of this RFA must request it in writing by the Deadline for Receipt of Questions indicated on the cover letter of this RFA, to the e-mail address set forth in the RFA cover letter to allow a reply to reach all prospective applicants before the submission of their applications.  Oral explanations or instructions given before award of a Cooperative Agreement will not be binding.  Any information given to a prospective recipient concerning this RFA will also be furnished to all other prospective recipients as an amendment to this RFA, if that information is necessary in submitting applications or if the lack of it would be prejudicial to any other prospective recipients.

Procedures for Submission of Applications by E-Mail

- Before sending your documents to USAID as e-mail attachments, convert them into Microsoft Word (for narrative text), Excel (for tables).  Documents requiring signature may be sent as scanned documents.

- Once sent, check your own e-mails to confirm that your attachments were indeed sent. If you discover an error in your transmission, re-send the material again and note in the subject line of the e-mail that it is a “corrected” submission.  Do not send the same e-mail more than one time unless there has been a change, and if so, note that it is a corrected e-mail.  Do not wait for USAID to advise you that certain documents intended to be sent were not sent, or that certain documents contained errors in formatting, missing sections, etc.  Each applicant is responsible for its submissions.

- To avoid confusion, duplication, and congestion problems with our e-mail system, only one authorized person from your organization should send in the e-mail submissions.

- If you send your application by multiple e-mails, indicate in the subject line of the e-mail whether the e-mail relates to the technical or cost proposal, and the desired sequence of multiple e-mails (if more than one is sent) and sequence of attachments (e.g. Organization X, Cost Proposal, Part 1 of 4, etc.).  However, you are requested to consolidate, as much as possible, the various parts of your technical application into one technical application document and the various parts of your cost application into one cost application document.

- The attachments should be formatted in Microsoft Word and/or Excel (version 2000) or PDF format, with a 3MB limit per e-mail.  Because of our system restrictions, if you send zipped files, do not use a “zip” extension as part of the file name.  Also, specify in the body of the e-mail that the attachment contains zipped files.  Applications and modifications thereof shall be submitted with the name and address of the applicant and the RFA number (referenced above) inscribed thereon, via e-mail, to abujasolicitations@usaid.gov .  Due to phone system limitations, faxed applications will not be considered.  Applicants must confirm with Ms. Ugo Oguejiofor at uoguejiofor@usaid.gov, copy Mr. Michael Glees at mglees@usaid.gov that their e-mail submissions were successfully received by the required due date.

Applicants are expected to review, understand, and comply with all aspects of this RFA.  Failure to do so will be at the applicant's risk.  Each applicant shall furnish the information required by this RFA.  On the hard copies of applications, the applicant shall sign the application and the certifications, and print or type its name on the Cover Page of the technical and cost applications.  Erasures or other changes must be initialed by the person signing the application.  Applications signed by an agent shall be accompanied by evidence of that agent's authority, unless that evidence has been previously furnished to the issuing office.

Applicants who include data that they do not want disclosed to the public for any purpose or used by the U.S. Government except for evaluation purposes should:

(a) Mark the title page with the following legend:

"This application includes data that shall not be disclosed outside the U.S. Government and shall not be duplicated, used, or disclosed - in whole or in part - for any purpose other than to evaluate this application.  If, however, a grant is awarded to this applicant as a result of - or in connection with - the submission of this data, the U.S. Government shall have the right to duplicate, use, or disclose the data to the extent provided in the resulting grant.  This restriction does not limit the U.S. Government's right to use information contained in this data if it is obtained from another source without restriction. The data subject to this restriction are contained in pages___."; and

(b) Mark each sheet of data it wishes to restrict with the following legend:

"Use or disclosure of data contained on this sheet is subject to the restriction on the title page of this application."

Unnecessarily elaborate applications that include brochures or other presentations beyond those sufficient to present a complete and effective application in response to this RFA are not desired and may be construed as an indication of the applicant's lack of cost consciousness.  Elaborate art work, expensive paper and bindings, and expensive visual and other presentation aids are neither necessary nor wanted.

Applicants shall confirm receipt of the RFA by written e-mail notification to the contact person specified in the RFA cover letter. Applicants shall also acknowledge receipt of any amendment to this RFA by signing and returning the amendment.  The Government must receive the acknowledgement by the time specified for receipt of applications

2.	TECHNICAL APPLICATION FORMAT

The technical application will be the most important item of consideration in selection for award of the proposed activity.  It should demonstrate the applicant's capabilities and expertise with respect to achieving the goals of this program.

To facilitate the competitive review of the applications, USAID will consider only applications conforming to the format prescribed below:

USAID requests that applications be kept as concise as possible.  Detailed information should be presented only when required by specific RFA instructions.  Technical Applications are limited to 45 pages (Times New Roman 12 point single-spaced type, 1 inch margins) not including the cover page, executive summary, appendices, figures and tables.  While there is no page limit for the annexes, brevity is encouraged.  Shorter applications are encouraged.  USAID requests that applications provide all of the information required by following the general format described below.

The technical evaluation criteria, with the possible points allocated to each are described in SECTION B – “Selection Criteria” below.  The maximum number of points available is 100.  The format of the technical application should follow the outline and order of the technical scoring criteria according to the guidelines provided below.

A suggested format for the Technical Application contains the following sections:

- Cover Page

- Table of Contents

- Executive Summary

- Technical Application

- Technical Approach

- Management

- Illustrative Implementation Plan and First Year Annual Work Plan

- Monitoring and Evaluation Plan

- Annexes (Staffing Plan, CVs/Resumes, Past Performance references, and Letters of Commitment from implementing partners, if any)

Cover page:  A single page that includes project title, RFA number, the name of the organization(s) submitting application, contact person, telephone and fax numbers, e-mail, and address. Any proposed subgrantees (or implementing partners) should be listed separately.  If applicable, the TIN (Tax Identification Number) and DUNS (Data Universal Numbering System) should also be listed on the cover page.

Table of Content:  Listing of all parts of the technical application, with page numbers and attachments.

Executive Summary (not to exceed three pages):   Applicants should briefly describe the technical approach, activities, goals, purposes, and anticipated results.  The Executive Summary should also briefly describe the technical and managerial resources of the applicant’s organization and describe how the overall program will be managed.

Technical Application (maximum 45 pages)

Content of Technical Application – Instructions

A.  Technical Approach

1.  Proposed strategies, approaches, and interventions

- Applicants should describe how they propose to achieve each of the sub-objectives and intended results of this activity and thus accomplish the overarching objective of increased use of high impact MCH/FP/RH interventions in the two potential target states (Bauchi and Zamfara), which is subject to change.

- Applicants should demonstrate their familiarity with national systems, funding mechanisms, programs, policies and guidelines, and show how their program fits within these.

- Applicants should describe how they will coordinate with other USAID cooperating agencies and USG programs, the FMOH, State MOH initiatives, other donor-funded programs, and state and local authorities, as well as indigenous and local partners, in implementing activities.

- Applicants should describe how they will control costs and improve the cost-effectiveness of the program.

2.  Case study: Comparison of health situation, systems, and program considerations in Bauchi and Zamfara

- The applicant should provide a brief (not more than six pages) case study that compares the MCH/FP/RH situations, health systems, and key factors that will affect the determination of approaches to achieving the program’s sub-objectives and objective in each of the two target states.  This analysis might consider similarities and differences in organization and capabilities of the public health system, approaches to the planning and management of local health services, key challenges to effective service delivery, experiences in community mobilization, and the overall donor and government resource and health program environment.

3.  Illustrative Implementation Plan and First Year Annual Work Plan

Applicants are encouraged to design innovative implementation approaches to reach the desired results.  The illustrative implementation plan should include information on critical activities towards achieving the results, a timeline, partners and resources (including human resources) required for carrying out the activity.  The proposed implementation plan should cover the life of project and include a more detailed first-year annual work plan.

B.  Staffing including Key Personnel

Applicants should propose a staffing plan that demonstrates an appropriate balance of skills and accountability.  They should present a plan that enables achievement of the TSHIP results.  The staffing should reflect a diverse staff including personnel who know the language and culture of the selected target states (potentially Bauchi and Zamfara states).   As much as possible staff should be Nigerians that speak the language and understand the culture of the two selected target states (potentially Bauchi and Zamfara).  Applicants are invited to propose and justify any alternative staffing structure, including a different configuration of key staff positions, if they feel that a different structure is more conducive to achieving the desired project results.

Applicants should provide the following information which may be included in an annex.

(1)  A complete staffing plan for each state including Key Personnel and core technical staff, with underlying rationale, including an organizational chart demonstrating lines of  authority and staff responsibility accompanied by  position descriptions.   Staffing plans are expected to include core technical staff, non-program staff and an explanation of how additional technical expertise will be obtained with attention to cost-containment and in order to avoid unnecessary staffing.   USAID envisions all project support infrastructure to be located in the selected target states, potentially Bauchi and Zamfara.  Given the intent to focus efforts at the state level, we do not envision any management of the project to be based in Abuja.

Key Personnel:

The applicant shall propose a maximum of five (5) key personnel by name and position for Chief of Party (COP), Deputy Chief of Party, Senior Financial/Administrative Specialist, Senior Policy Advisor, and Senior Monitoring and Evaluation (M&E) Specialist.  The following descriptions highlight ideal attributes for candidates for the positions:

-	Chief of Party (COP) (to be stationed in one state as team leader for that state will be the overall manager of the project.) The desirable attributes of the Chief of Party are:  a Master’s Degree or higher in public health or social sciences, management or a related advanced degree relevant to the broad areas of MCH and FP/RH.  S/he must have at least 10 years senior level experience designing, implementing and managing large, complex MCH and FP/RH programs or projects in Africa or in developing countries elsewhere.  S/he must demonstrate a strategic vision, leadership qualities, depth and breadth of technical and management expertise and experience, have a positive professional reputation, and strong interpersonal, writing and oral presentation skills.  S/he must have demonstrated experience interacting with government agencies, host country governments and counterparts, and international donor agencies.  S/he must have prior experience as a supervisor, and as director of a project or program.  At least eight years experience living and working in a developing country is desirable.

-	Deputy Chief of Party (DCOP) (to be stationed in one state (separate from the COP) will be team leader for one of the states.)  While the COP will be the overall manager of the project, it is expected that the state where the DCOP is located will be able to act independently in setting program directions, approaches and relationships with state and local governments and other partners.  The desirable attributes of the Deputy Chief of Party are:  a Master’s Degree in public health, a clinical discipline, social sciences or a related advance degree relevant to the field of FP/RH or MCH.  S/he must have at least eight years of mid to senior level experience in designing, implementing or managing large, complex FP/RH or MCH project in/for developing countries.  S/he must have demonstrated leadership qualities, depth and breadth of technical and management expertise and experience, strong interpersonal, writing, oral presentation skills.  Five years experience living and working in a developing country is desirable.

-	Senior Financial/Administrative Specialist will be stationed in the same state as the COP and will have responsibility for the overall project finances.  S/he is expected to develop the project financial plan, to include monitoring and reporting systems that meet USG requirements, and manage contracting activities.  The desirable attributes of the Senior Financial/Administrative Specialist are:  a Master’s Degree or higher in Business Administration, Finance or other relevant fields.  S/he must have at least eight years experience in administrative and financial management of large international projects including experience in the management of USAID projects.  S/he must have familiarity with USAID financial regulations and management systems as well as experience and skills in developing and managing large budgets.  S/he should be proficient in relevant computer applications and databases. S/he must possess excellent organizational, analytical, oral and written communications skills, demonstrated supervisory skills, and ability to work well on teams.

-	Senior Policy Advisor is expected to assist the FMOH, the National Planning Commission (NPC), the two states and other relevant policy-making bodies in linking the states up to the federal level regarding proposed policy changes and assist the two states in the implementation of federal policies where appropriate.  The senior policy advisor will work with the program team in his/her designated state to identify key constraints and issues that can be addressed through policy and strategy, and to bring the experience, results, and perspective of state and local programming to those policy and strategy discussions.  (Nigerian or relevant African experience is highly desirable).   The desired attributes of the Senior Policy Advisor are:  a Master’s Degree or higher in fields relevant to health policy in developing countries.  S/he must have at least eight years senior level experience designing, implementing and managing complex policy programs in Africa or in developing countries elsewhere.  S/he should have depth of experience in FP/RH and/or MCH program implementation in developing countries and expertise in strategy and policy development.  S/he should also have recognized stature in health development, demonstrated ability to work effectively in policy and political environments, the ability to establish effective relationships with senior leaders, and good understanding of evidence-based approaches to program and the use of operational research.  S/he must have demonstrated strong interpersonal, writing and oral presentation skills.

-	Senior Monitoring and Evaluation (M&E) Specialist will be stationed in the same state as the DCOP and will have responsibility for the overall project monitoring and evaluation.  The desirable attributes of the Senior M&E Specialist are:  a Master’s degree or higher in fields relevant to monitoring and evaluation.  S/he must have at least five years senior level experience in monitoring and evaluating complex systems improvement programs in Africa or developing countries elsewhere.  S/he must have demonstrated a depth and breadth of technical and management expertise, strong interpersonal, writing and oral presentation skills.

(2)  Brief descriptions of each of the five proposed key staff should be included in the body of the application, showing how they meet the requirements above.  Each key personnel position requires USAID approval, as noted in substantial involvement provisions (Section C, part J).

Other Proposed Core Technical Personnel:

It is desired that the following core technical positions be included in the applicant’s personnel workforce for each of the two states:

- Additional Senior Policy Advisor (for state 2)

- Senior Health Systems Advisor;

- Senior Maternal and Child Health (MCH) Advisor;

- Senior Family Planning/Reproductive Health (FP/RH) Advisor;

- Assistant Financial Specialist.

A list of other core technical staff (and other personnel deemed critical to the project) including one-page summary biographic statements should be included in the staffing plan.  These persons should have the specific technical knowledge and skills to manage and support activities under the award.  The applicant must propose specific expertise in operations and evaluation research, with evidence of proposed staff having generated effective research that resulted in improved programming or policy.  Depending on the program proposed by the applicant, other areas of expertise could include, but are not limited to: MCH and FP/RH technical and program skills, training and performance improvement, health care management and organization, quality assurance, supply and logistics, health management information, human resource management, knowledge management, community mobilization and development and monitoring and evaluation.  (Nigeria or relevant West African experience and local language skills are highly desirable).  It is not necessary to include résumés of part-time staff, support staff, or consultants.

C.   Management and Institutional Capacity

Applicants should demonstrate that they have managerial, technical and institutional capacities to achieve the results outlined in this program description.  Applicants are encouraged to propose creative collaborative partnerships with NGOs, private voluntary organizations, South-to-South partners, faith-based organizations, and indigenous Nigerian organizations and firms to implement activities.

The Applicant should describe its proposed management and administrative structure; policies and practices for overall implementation of the program including personnel, financial, and logistical support; and coordination.

D.  Monitoring and Evaluation Plan (M&E)

It is anticipated that the final M&E Plan and the Performance Management Plan (PMP) for the first year will be completed by the awardee and approved by USAID approximately six months after the project is awarded.  This will allow the awardee to conduct base line and systems’ assessments and hold discussions at the state and Local Government Authority (LGA) levels during the start up phase of the project.   These final plans will have process and outcome/impact indicators with plans on how to generate the data needed to measure the impact of the program.

Applicants should propose an illustrative monitoring and evaluation approach that will track progress in achievement of the TSHIP objective and each of the four sub-objectives under the Award.

Noting this, applicants should describe how they anticipate the data will be regularly collected and reported to facilitate results reporting from USAID/Nigeria to USAID/Washington.  Applicants should describe how overall impact of TSHIP activities will be assessed, including how baselines will be established and how changes in status will be measured and attributable to TSHIP activities.  Applicants should also describe how the data collected would be used to make mid-term corrections or other changes.

ANNEXES:

The technical application shall contain the following four annexes:  staffing plans for each state including key personnel, curriculum vitae/ résumés, past performance references, and letters of commitment from implementing partners, if any.

Staffing Plan:  A staffing plan for each state including proposed core technical staff.  See proposed core staff above.

Curriculum vitae/résumés should be provided for each key and core technical and home office personnel.  They should be limited to a maximum of three pages per person.

Past performance references:  Applicant should describe all contracts, grants and cooperative agreements that the primary applicant (as well as any partners substantially involved in implementation) has implemented involving similar or related programs over the past three years. Include the following for each award listed: name and address of the organization for which the work was performed; current telephone number and e-mail address of responsible representative of the organization for which the work was performed; contract/grant name and number (if any); annual amount received for each of the last three years; term of award, i.e., beginning and ending dates; and a brief description of the program.

Letters of commitment should be provided from all proposed implementing partners. Such letters do not have to be exclusive to one Applicant.

## 3	COST/BUSINESS APPLICATION FORMAT

The Cost or Business Application is to be submitted under separate cover from the technical application.  Certain documents are required to be submitted by an applicant in order for the Agreement Officer to make a determination of responsibility.  However, it is USAID policy not to burden applicants with undue reporting requirements if that information is readily available through other sources.

The following sections describe the documentation that applicants for an Assistance award must submit to USAID prior to award.   While there is no page limit for this portion, applicants are encouraged to be as concise as possible, but still provide the necessary detail to address the following:

A.   Include a budget with an accompanying budget narrative which provides in detail the total costs for implementation of the program your organization is proposing. The budget should be structured according to Section C - PROGRAM DESCRIPTION, Part I.2: Proposed Funding Sources and Funding Levels and have a breakdown by objective, program elements and sub-activity. The budget narrative must provide detailed budget notes and supporting justification of all proposed budget line items.  It must clearly identify the basis of all costs, such as market surveys, price quotations, current salaries, historical experience, etc.  A summary of the budget must be submitted using Standard Form 424, 424A and 424B, which can be downloaded from http://www.grants.gov/agencies/approved_standard_forms.jsp   The full budget must include:

- the breakdown of all costs associated with the program according to costs of, if applicable, headquarters, regional and/or country offices;

- the breakdown of all costs according to each partner organization involved in the program;

- the costs associated with external, expatriate technical assistance and those associated with local in-country technical assistance;

- the breakdown of the financial and in-kind contributions of all organizations involved in implementing this Cooperative Agreement;

- potential contributions of non-USAID or private commercial donors to the expected Cooperative Agreement;

-	the name, annual salary, and expected level of effort of each person charged to the activity.  Provide resumes showing work experience and annual salary history for at least the three most recent years for major personnel.

- if not included in an indirect cost rate agreement negotiated with the U.S. Government, the applicable fringe benefit rates for each category of employees, and an explanation of the benefits included in the rate.

- the same individual information for consultants must be provided as for regular personnel.

- a breakdown of allowances by specific type and by person, and they must be in accordance with the applicant's policies.

- travel, per diem and other transportation expenses detailed to include number of international trips, expected itineraries, number of per diem days and per diem rates.

- financial plans for all proposed sub-grants and subcontracts, with the same format and level of detail as those of the applicant.

- separate cost line items for other direct costs such as supplies, communication costs, photocopying, visas, passports and other general costs.

B.  A current Negotiated Indirect Cost Rate Agreement (NICRA);

C.  Required Certifications and Representations, included in Section D Certifications, Assurances and Other Statements;

D.  Details regarding the level of cost share your organization is proposing for this activity.  USAID encourages applicants to contribute cost sharing.  Cost sharing may be proposed from any available and interested local and international funding sources, including but not limited to, government and public institutions, individuals, corporations, NGOs, and foundations.  While there is no stated minimum required cost share amount, applicants are encouraged to give serious consideration to the amount they propose as a signal of the applicant's commitment to the activity.  See also Section B Selection Criteria, under costs.

E.  Applicants who do not currently have a Negotiated Indirect Cost Rate Agreement (NICRA) from their cognizant government agency shall also submit the following information:

- copies of the applicant's financial reports for the previous 3-year period, which have been audited by a certified public accountant or other auditor satisfactory to USAID;

- projected budget, cash flow and organizational chart;

- A copy of the organization's accounting manual.

F.   Applicants should submit any additional evidence of responsibility deemed necessary for the Agreement Officer to make a determination of responsibility.  The information submitted should substantiate that the Applicant:

- Have adequate financial, management and personnel resources and systems, or the ability to obtain such resources as required during the performance of the award.

- Has the ability to comply with the award conditions, taking into account all existing and currently prospective commitments of the applicant, nongovernmental and governmental.

- Has a satisfactory record of performance.  Past relevant unsatisfactory performance is ordinarily sufficient to justify a finding of non-responsibility, unless there is clear evidence of subsequent satisfactory performance.

- Has a satisfactory record of integrity and business ethics; and

- Is otherwise qualified and eligible to receive an award under applicable laws and regulations (e.g., EEO).

An award shall be made only when the Agreement Officer makes a positive determination that the applicant possesses, or has the ability to obtain, the necessary management competence in planning and carrying out assistance programs and that it will practice mutually agreed upon methods of accountability for funds and other assets provided by USAID.  For the organizations that are new to USAID, or organizations with outstanding audit findings, it may be necessary to perform a pre-award survey.

G.   Applicants that have never received a grant, cooperative agreement, or contract from the U.S. Government are required to submit a copy of their accounting manual.  If a copy has already been submitted to the U.S. Government, the applicant should advise which Federal Office has a copy.

H.  Certificate of Compliance: Submit a copy of your Certificate of Compliance if your organization's systems have been certified by the USAID/Washington's Office of Acquisition and Assistance (M/OAA).

4. 	COOPERATIVE AGREEMENT AWARD

The Government will award one (1) cooperative agreement resulting from this RFA to the responsible applicant whose application conforming to this RFA offers the greatest value (see Section B of this RFA). The Government may (a) reject any or all applications, (b) accept other than the lowest cost application, (c) accept more than one application, (d) accept alternate applications, and (e) waive informalities and minor irregularities in applications received.

The Government will award the cooperative agreement on the basis of initial applications received, and may not conduct discussions or negotiations.  Therefore, each initial application should contain the applicant's best terms from a cost and technical standpoint. As part of its evaluation process, however, USAID may elect to discuss technical, cost or other pre-award issues with one or more applicants.  Alternatively, USAID may proceed with award selection based on its evaluation of initial applications received and/or commence negotiations solely with one applicant.

A written award mailed or otherwise furnished to the successful applicant within the time for acceptance specified either in the application or in this RFA (whichever is later) shall result in a binding cooperative agreement without further action by either party.  Before the application's specified expiration time, if any, the Government may accept an application, whether or not there are negotiations after its receipt, unless a written notice of withdrawal is received before award. Negotiations or discussions conducted after receipt of an application do not constitute a rejection or counteroffer by the Government.

Neither financial data submitted with an application nor representations concerning facilities or financing, will form a part of the resulting cooperative agreement unless explicitly stated otherwise in the agreement.

To be eligible for award of a cooperative agreement, in addition to other conditions of this RFA, organizations must have a politically neutral humanitarian mandate, a commitment to non-discrimination with respect to beneficiaries and adherence to equal opportunity employment practices.  Non-discrimination includes equal treatment without regard to race, religion, ethnicity, gender, and political affiliation.

Applicants are reminded that U.S. Executive Orders and U.S. law prohibits transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism.  It is the legal responsibility of the recipient to ensure compliance with these Executive Orders and laws.  This provision must be included in all subcontracts/sub-awards issued under the cooperative agreement.

Foreign Government Delegations to International Conferences: Funds in the cooperative agreement may not be used to finance the travel, per diem, hotel expenses, meals, conference fees or other conference costs for any member of a foreign government's delegation to an international conference sponsored by a public international organization, except as provided in ADS Mandatory Reference "Guidance on Funding Foreign Government Delegations to International Conferences http://www.info.usaid.gov/pubs/ads/300/refindx3.htm or as approved by the Agreement Officer.

5.	AUTHORITY TO OBLIGATE THE GOVERNMENT

The USAID Agreement Officer is the only individual who may legally commit the Government to the expenditure of public funds.  No costs chargeable to the proposed agreement may be incurred before receipt of either a fully executed Agreement or a specific written authorization from the Agreement Officer.

6.  ENVIRONMENTAL COMPLIANCE GUIDANCE

1a)	The Foreign Assistance Act of 1961, as amended, Section 117 requires that the impact of USAID’s activities on the environment be considered and that USAID include environmental sustainability as a central consideration in designing and carrying out its development programs. This mandate is codified in Federal Regulations (22 CFR 216) and in USAID’s Automated Directives System (ADS) Parts 201.5.10g and 204 (http://www.usaid.gov/policy/ADS/200/), which, in part, require that the potential environmental impacts of USAID-financed activities are identified prior to a final decision to proceed and that appropriate environmental safeguards are adopted for all activities. Recipient’s environmental compliance obligations under these regulations and procedures are specified in the following paragraphs of this RFA.

1b)	In addition, the contractor/recipient must comply with host country environmental regulations unless otherwise directed in writing by USAID.  In case of conflict between host country and USAID regulations, the latter shall govern.

1c)	No activity funded under this CA will be implemented unless an environmental threshold determination, as defined by 22 CFR 216, has been reached for that activity, as documented in a Request for Categorical Exclusion (RCE), Initial Environmental Examination (IEE), or Environmental Assessment (EA) duly signed by the Bureau Environmental Officer (BEO). (Hereinafter, such documents are described as “approved Regulation 216 environmental documentation.”)

2)	An Initial Environmental Examination (IEE)

IEE 34Nigeriax_SO13_Soc Sector and IEE 33Nigeria3_NetMark_PERSUAP have been approved for Increased Use of Social Sector Services funding this RFA. The IEE covers activities expected to be implemented under this Cooperative Agreement. USAID has determined that a Negative Determination with conditions applies to one or more of the proposed activities. This indicates that if these activities are implemented subject to the specified conditions, they are expected to have no significant adverse effect on the environment. The applicant shall be responsible for implementing all IEE conditions pertaining to activities to be funded under this solicitation. This will include proactive monitoring of the use and effectiveness of ITN pesticides, including household use, exposure and disposal of the product, watching for potential adverse impacts on humans or on local aquatic ecosystems.

3a)	As part of its initial Work Plan, and all Annual Work Plans thereafter, the recipient, in collaboration with the USAID Agreement Officer’s Technical Representative (AOTR) and Mission Environmental Officer or Bureau Environmental Officer, as appropriate, shall review all ongoing and planned activities under this CA to determine if they are within the scope of the approved Regulation 216 environmental documentation.

3b)	If the recipient plans any new activities outside the scope of the approved Regulation 216 environmental documentation, it shall prepare an amendment to the documentation for USAID review and approval. No such new activities shall be undertaken prior to receiving written USAID approval of environmental documentation amendments.

3c)	Any ongoing activities found to be outside the scope of the approved Regulation 216 environmental documentation shall be halted until an amendment to the documentation is submitted and written approval is received from USAID.

[END OF SECTION A]

SECTION B - SELECTION CRITERIA

1.	OVERVIEW

The selection criteria presented below have been tailored to the requirements of this particular RFA.  Applicants should note that these criteria serve to: (a) identify the significant matters which applicants should address in their applications and (b) set the standard against which all applications will be evaluated.  To facilitate the review of applications, applicants should organize the narrative sections of their applications in the same order as the selection criteria. USAID reserves the right to determine the resulting level of funding for the agreement award.

The technical applications will be evaluated in accordance with the Technical Evaluation Criteria set forth below.  The cost/business applications of all applicants submitting a technically acceptable application will be evaluated by the Agreement Officer in accordance with the criteria specified below in COST EVALUATION CRITERIA.  To the extent that they are necessary (if award is made based on initial applications), negotiations will then be conducted with all applicants whose applications, after technical review and evaluation, have a reasonable chance of being selected for award.  Award will be made to the responsible applicant whose application offer the greatest value, cost and other factors considered. Applicants are specifically advised that until a grant document is received and duly signed by a Grant or Agreement Officer, no program expenditures will be paid by USAID/Nigeria.

To the extent necessary, if award is not made on the initial applications, USAID may request clarification and supplemental materials from applicants whose applications have a reasonable chance of being selected for award.  The entry into discussion is to be viewed as part of the evaluation process and shall not be deemed by USAID or the applicants as indicative of a decision or commitment upon the part of USAID to make an award to the applicants with whom discussions are being held.

2.	TECHNICAL EVALUATION CRITERIA (100 POINTS)

Technical evaluation of applications will be based on the extent and appropriateness of proposed approaches and feasibility of achieving the strategic objectives, in accordance with the following criteria.

2.1.  Technical Approach						                               40/100

(1)	The scoring of the technical approach is based on the overall quality of proposed strategies, approaches, and capabilities, as follows:

- Technical and programmatic quality of proposed approaches to achieve each of the sub-objectives and intended results of this activity and thus accomplish the overarching objective of increased use of high impact MCH/FP/RH interventions in the two target states. (15 points)

- Familiarity with national systems, funding mechanisms, programs, policies, strategies, and guidelines, and how the proposed program fits within these. (5 points)

- Proposed coordination with other USAID cooperating agencies and USG programs, the FMOH, State MOH initiatives, other donor-funded programs, and state and local authorities, as well as indigenous and local partners, in implementing activities. (5 points)

- Mechanisms and approaches to control costs and improve the cost-effectiveness of the program. (5 points)

(2)  	Case study (5 points)

(3)	Illustrative Implementation Plan and First Year Annual Work Plan.  Plan for rapid start up of the project, including the first year plan of activities and timeline (5 points)

2.2.	Staffing/Key Personnel                                                                                     (30/100)

a.	Key Personnel (15 points)

- The five proposed key personnel have requisite experience and expertise and meet or exceed requirements specified in Section A.  They have breadth and dept in technical expertise and experience in management, design and implementation of complex programs.

- The proposed key personnel, individually and collectively, show evidence of the ability to build collaborative relationships with the Government of Nigeria and other donors currently working in the target states.

b.	Other Proposed Core Technical Personnel (15 points)

- The staffing pattern and the number and type of positions proposed are responsive to the technical requirements and Applicants approach, with an optimal configuration for efficiency and cost containment.

- The proposed technical specialists demonstrate a mix of practical technical skills necessary for achieving the main results of this Project.

- Qualified Nigerians are proposed for leadership, technical and managerial positions.

2.3.	Management and Institutional Capacity   	                                                    (15/100)

The management and institutional capacity will be evaluated according to the following criteria.

- Management and administrative structure, policies, and practices for overall implementation of the program including personnel, financial, and logistical support; the role and level of effort for staff supporting these functions; and a realistic plan for monitoring the technical and financial activities and the reporting on results.

- How applicant will work with local partners, other USAID programs and other implementing organizations to achieve results; and how management is structured in a way that is mutually reinforcing, optimally efficient and effective in its use of technical and financial resources, and not duplicative.

- Demonstration of the Applicant’s institutional capacity, organizational systems and competence to creatively plan, implement, monitor and report on the range of activities outlined in this RFA.

- Demonstration of the Applicant’s past performance and how it meets or exceeds the Eligibility Criteria provide in the RFA.  Documentation should demonstrate organizational capabilities including past performance of each partner receiving at least 15 percent of project funds.

2.4. 	Monitoring and Evaluation (M&E)		                                        (15/100)

The M&E Plan will be evaluated according to the following criteria.

- The application presents a comprehensive M&E approach to monitoring and evaluation, with the understanding that it may be modified during the start-up phase of the project.  .  The approach should include illustrative indicators for outputs, intermediate outcomes (both system and intervention-related), and impact, describing how these levels of indicator will be used in a linked manner to monitor progress toward MCH/FP/RH outcome and impact performance targets.  The description of the M&E approach should also illustrate how data on these indicators will be collected or generated, and how the program will work to shift from parallel, program-specific data collection to use of local and state level data where possible.  Examples of illustrative targets and benchmarks should be provided that relate to achieving the results outlined in the program description.

- The plan should describe the methodology to be use for data collection that is cost effective and timely.

- The monitoring and evaluation plan includes a detailed plan for oversight of compliance with USAID family planning legal and policy requirements.

SUMMARY:

Technical Approach					 40 points

Staffing/Key Personnel				 30 points

Management and Institutional Capacity		 15 points

Monitoring and Evaluation 				 15 points

TOTAL 						100 points

[END OF SECTION B]

SECTION C:  PROGRAM DESCRIPTION

PART A.	ACRONYMS

ADB		African Development Bank

AIDS		Acquired Immune Deficiency Syndrome

AIF		Access to Finance

AMTSL	Active Management of the Third Stage of Labor

ANC		Antenatal Care

AOTR		Agreement Officer’s Technical Representative

ART		Anti-Retroviral Therapy

BASICS	BASIC Support for Institutionalizing Child Survival

BCC		Behavior Change Communication

CA		Cooperative Agreement

CC		Community Coalition

CDIA		Canadian International Development Agency

CHEW		Community Health Extension Workers

COMPASS	Community Participation for Action in the Social Sector

COP/DCOP	Chief of Party/Deputy Chief of Party

CPR		Contraceptive Prevalence Rate

CPS		Country Partnership Strategy

CS		Child Survival

DfID		Department for International Development (UK)

EC		European Commission

EmONC	Emergency Obstetric and Newborn Care

ENHANSE	Enabling HIV/AIDS and TB and the Social Sector Environment

FP		Family Planning

FP/RH		Family Planning and Reproductive Health

FMOH		Federal Ministry of Health

GAVI		Global Alliance for Vaccines and Immunization

GHAIN	Global HIV/AIDS Initiative Nigeria

GON		Government of Nigeria

HEW		Health Extension Worker

HIV/AIDS	Human Immuno-deficiency Virus

HMO		Health Maintenance Organization

IEC		Information, Education, and Communication

IMNCH	Integrated Maternal, Newborn, and Child Health Strategy

IPD 		Immunization-Plus Day

IPT		Intermittent Prevention Treatment

IR		Intermediate Results

IUD		Intrauterine Device

ITN		Insecticide Treated Nets

JICA		Japan International Cooperation Agency

LAM		Lactational Amenorrhea Method

LAPMS	Long Acting and Permanent Methods

LGA		Local Government Authority

LLN		Long Lasting Nets

LOP		Life of Project

MCFW	Managed Care Family Wellness

MCH		Maternal and Child Health

MDG		Millennium Development Goal

M&E		Monitoring and Evaluation

NDHS		Nigerian Demographic and Health Survey (2003)

NEEDS	National Economic Empowerment and Development Strategy

NGO		Non-Governmental Organization

NPC		National Planning Commission

NPHCDA	National Primary Health Care Development Agency

ORT		Oral Rehydration Therapy

OVC		Orphans and Vulnerable Children

PEPFAR	President’s Emergency Plan for AIDS Response

PHC		Primary Health Care

PMI		Presidential Malaria Initiative

PMP		Performance Management Plan

PMTCT	Preventing Mother to Child Transmission

PPT		Prepackage Treatment

PRIME	Partnership to Reinforce Immunization Efficiency

PRRINN	Partnership for Reviving Routine Immunization in Northern Nigeria

PSP-One 	Private Sector Partnerships One

RBM		Roll Back Malaria

RFA		Request for Applications

SDM		Standard Days Method

SEEDS 	State Economic Empowerment and Development Strategy

SFH		Society for Family Health

SMOH		State Ministry of Health

SPHCDA	State Primary Health Care Development Agency

TFR		Total Fertility Rate

TSHIP		Targeted States High Impact Project

TT		Tetanus Toxoid

UNICEF	United Nations Children’s Fund

USAID	United States Agency for International Development

USG		United States Government

VOA		Voice of America

WHO		World Health Organization

PART B.  INTRODUCTION

Overview of Planned Activity

USAID/Nigeria plans to implement a 5-year family planning, reproductive health, and maternal and child health (MCH/FP/RH) program through a Cooperative Agreement whose overall primary objective is to increase the use of selected high impact interventions in the two selected target Nigerian states, potentially Bauchi and Zamfara, through public sector health services.  A strongly associated sub-objective (section C, below) is to draw on the program investments in these two states to develop evidence and experience that will inform and improve policies, programs, and resource allocation in other states and in Nigeria as a whole.

The program to be implemented under this proposed Cooperative Agreement has been developed under USAID/Nigeria’s new strategy for its MCH/FP/RH activities (see “Referenced Documents” and associated links, below).  Under this strategy, the program to be supported under this RFA is part of a larger, multi-agreement program that will be implemented by USAID/Nigeria.  It is anticipated that this broader program will include five complementary mechanisms (see Figures 1 and 2 below)

Figure 1

Mechanism 1: Public sector support in two states, (potentially Bauchi and Zamfara) (this agreement) Mechanism 2: National policy level support Mechanism 3: Social marketing of MCH/FP/RH commodities and services (national) Mechanism 4: Non-social marketing private sector partnerships (multiple states) Mechanism 5: Buy-ins to USAID/Washington projects for specialized technical expertise

Recommended Mechanisms

Central Policy Representation

PART C. 	BACKGROUND

1.	 Nigeria’s Health Situation

Nigeria is the largest country in Africa, with a population of approximately 140 million people.  It has been ranked 158 out of 177 countries in the United Nations Development Program, a combined index for overall quality of life (2007-2008 UNDP Human Development Report).

The health system has been neglected for the past two decades, resulting in devastating statistics.  In the recent 2008 Report on the State of the World’s Mothers, Nigeria ranked 70 out of 71 less developed countries as one of the worst places in the world to be a mother.  The total fertility rate is 5.7 children per woman and the prevalence of modern contraceptive methods is only 8.9 percent (Nigerian Demographic Health Survey (DHS)).  Maternal mortality hovers at 800 per 100,000 lives births, with the rate being at least three times that in the northern States.  The 2003 NDHS indicates that consumers are choosing to forego treatment or to pay for treatment with unskilled providers.  Sixty-six percent of deliveries take place in the home, with only 35 percent attended by a skilled provider.

About one million Nigerian children die each year before their fifth birthday.  This figure represents about ten percent of the global total, although Nigeria’s population is just two percent of the world’s population.  The infant mortality rate is 100 per 1,000 live births and the under five mortality rate is 200 per 1,000 live births (NDHS).  Communicable diseases, particularly malaria, pneumonia, and diarrhea, often in association with malnutrition are the major causes of mortality and morbidity, especially among children.  Malaria remains largely unchecked and kills more people, especially children, than any other disease.  These statistics suggest that the national healthcare system is in a crisis state and is struggling to meet even the bare minimum of any national health sector standard.

In general, development, health, and fertility indicators in Nigeria are worst in the states of the northern region.  For example, the 2003 NDHS found the under-five mortality rate across the North Western states to be 269/1,000 and in the North Eastern states to be 260/1,000, while the rate in next highest region (“South South,” including the delta region) was 176/1,000 and in the South Eastern states was 103/1,000.  In the North Western states, complete immunization was only 3.7 percent (12.9 per cent nationally) and women’s literacy was 20.9 percent (48.2 per cent nationally).  Many health indicators in Nigeria (infant and child mortality, immunization, oral rehydration therapy use, and others) have actually declined since the NDHS survey in 1990.

2.	 Nigeria’s Health System

Nigeria operates through a three-tier health system.

The Federal Ministry of Health (FMOH) generally provides policy and technical guidance for the health sector and supports and manages tertiary level care, research, and academic “centers of excellence.”  The FMOH also contributes to human resource capacity development through the training of medical doctors, nurses, midwives, and community health officers at all levels.  Along with other sectors, international donor aid to the health sector is overseen by the National Planning Commission.

The Federal Ministry of Finance (FMOF) provides funds to the FMOH, the states and the Local Government Authorities (LGAs) based on the National Revenue Allocation Formula.

State Ministries of Health (SMOH) also have important policy setting and technical direction roles within their states. In addition, they fund and manage state hospitals, maternities, and teaching colleges.  SMOHs also are responsible for the development of health manpower for secondary and primary health care, from midwives and nurses to Community Health Extension Workers (CHEWS).  The FMOF channels funds to the LGAs through the states.  State governments allocate funding to Local Government Areas (LGAs), generally in the form of non-earmarked grants that are meant to include funding for health services.

Local government is presently tasked with planning, managing, staffing, supporting, and implementing primary health care services.  About 71 percent of Nigerians have access to a primary health care (PHC) facility that is within a five km radius of their homes; however, many of these centers are not functional due to lack of equipment, essential supplies and qualified staff.  Up to 64 percent of the PHC facilities have not received any drugs from the government in the past two years.  LGAs are made up of approximately five to ten wards.  Each ward contains a collection of settlements or communities.  Originally established for election purposes, wards do not have an official government function.  Wards usually have traditional leaders who settle disputes, advocate for the ward and mobilize the community around issues, such as polio and other interventions.

The LGA level especially remains a critical “missing link” in making Nigeria’s health system function.  The fragmentation of responsibility at this level (personnel are managed by the Ministry of Local Government and the resources for payment of the personnel are from the LGA) and especially the lack of capacity and a defined structured approach to priority setting, resource allocation, and health services management at this level, make the LGA level perhaps the weakest link in effective health service delivery.

In actual terms, the blurring of the roles of each of these tiers sometimes contributes to overlapping and unclear (or contested) responsibilities or fragmented support of service delivery.  The picture is further complicated by the roles of other government institutions.  Most important among these is the National Primary Health Care Development Agency (NPHCDA).  In the years prior to Nigeria’s latest military dictatorship, the NPHCDA was established as a strong federal institution that was directly involved in establishing primary health care services nationwide.  However, the NPHCDA waned in importance under the Sani Abacha lead government from 1993 until 1998.  The lead role for the NPHCDA was never substantially re-established despite the return of non-military government in the late 1990s and the fact that it remains a legal entity.

To strengthen primary health care delivery services, some states are setting up their own “State Primary Health Care Development Agencies;” and other states are putting in place different mechanisms aimed at controlling resources and/or management of primary health care.  Some states have taken no substantive action to deal with the shortcomings of funding, planning, management, staffing, and support of PHC.  Given the critical importance of PHC in achievement of the objectives of USAID’s program under this agreement, this evolving institutional issue will be an important contextual factor in the program’s implementation.

3.	 Ongoing USAID MCH/FP/RH Activities

USAID/Nigeria is currently implementing a portfolio of projects and activities upon which the new proposed program described under this RFA and the other components of its portfolio will strategically build and expand.  The present portfolio includes:

NetMark (2004-2009):  NetMark supports reduction of malaria associated morbidity and mortality by increasing the use of insecticide treated nets (ITNs), particularly by pregnant women and children under-five.  Key activities include:  Support to local net manufacturers to increase quality, quantity, sale, and distribution of a variety of local ITN; and mass awareness, demand creation and adoption of long lasting net (LLNs) technology.

Improving Reproductive Health in Nigeria (IRHIN) (2005-2010): The Society for Family Health (SFH), a Nigerian NGO, in a consortium with other partners, manages this contraceptive social marketing project to improve the distribution of contraceptive commodities nationwide, train providers, provide technical support, and supervision and monitor activities in three states.

Community Participation for Action in the Social Sector (COMPASS) Project (FP/RH, MCH/Child Survival, Malaria and Polio (5/04-5/09):  COMPASS/FP/RH works in 51 local government areas in five states to provide an integrated FP/RH and MCH package in 557 public and 143 private health facilities to increase community participation in the provision of social services.  COMPASS/MCH/Child Survival provides support to health facilities for the reduction of morbidity and mortality caused by preventable childhood disease.  The project works with health workers and community coalitions to provide improved routine immunization, improved prevention and treatment of diarrhea, improved maternal and young child nutrition and treatment of childhood illnesses.  COMPASS/Polio supports the implementation of Immunization Plus Days in eight northern states. COMPASS/Malaria increases access to and use of proven malaria interventions ITNs and Intermittent Preventive Treatment (IPT) through antenatal clinics, immunization activities and community coalitions using an integrated approach towards reducing malaria in pregnant women and child under five.

Global HIV/AIDS Initiative Nigeria (GHAIN) (2004-2009):  This project integrates family planning services into HIV prevention, care and treatment services.

Prepackaged Treatment (PPT) (11/04-11/09):  This project through a social marketing mechanism provides access to prepackaged anti malarial treatment.  Children less than five years are the target.

DELIVER (10/06-9/11):  This project improves the availability of contraceptive supplies in the public sector by strengthening Nigeria’s supply systems.

ACCESS (1/06-6/09):  This project supports the utilization of quality Emergency Obstetric and Newborn Care services (EmONC) including birth spacing/reproductive health and family planning) by pregnant women, mothers and their newborns in three states .  The ACCESS project works in two LGAs in Zamfara. Because the ACCESS project may be extended for another year, it is anticipated that the new project will need to coordinate closely with ACCESS in Zamfara to ensure a smooth transition of EmONC services in Zamfara from ACCESS to the new project.

Immunization Basics(10/06-5/09):   This project supports the development of the human and organizational capacity needed to strengthen delivery of quality routine immunization services.

Private Sector Partnerships One (PSP-One) (10/06-9/09):  This project supports the delivery of FP/RH and other health products and services through the private sector.  Working through Health Management Organizations (HMOs), PSP-One conducts Managed Care and Family Wellness (MCFW) and Access to Finance (ATF) trainings for private providers.  PSP-One also works with the Nigerian NGO, Society for Family Health (SFH) in the distribution of social marketed contraceptives.

Enabling HIV/AIDS and Social Sector Environment (ENHANSE) (6/04-6/09):  The ENHANSE project strengthens the policy environment for FP/RH by addressing the key constraints to access and utilization of FP/RH services through policy reform.

Voice of America (VOA) Hausa Services (10/06-9/08):  This activity supports the production of Hausa language radio programming, which reaches listeners in northern Nigeria and neighboring countries.  The messages include information and education on child spacing, child health, and malaria.

ACQUIRE – Fistula Care(10/06-10/11):  This project supports comprehensive fistula prevention, repair, community-based integration, and family planning activities.

4.  Summarized Key Findings (and Recommendations) from Recent Evaluations and Assessments of these Activities

- While the COMPASS activity sought to build on potential synergies between two social sector program areas (health and education), the lack of congruence in delivery approaches and target groups reduced the effectiveness of programming in each area.

    - It was recommended that future activities in each of these areas should be implemented separately, although synergies among them should still be sought where the potential exists.

  - For a number of reasons, both political and historical, USAID’s MCH/FP/RH activities have been implemented in six states and a large number of LGAs.  Sometimes one element of a program (e.g., maternal health care improvement) might be implemented in some states or areas, while other elements (e.g., immunization) are being carried out in others.  In other cases, multiple program elements might be carried out in shared or overlapping areas, but by different Implementing Partners (IPs) with somewhat different approaches to similar service delivery problems.  This geographic and programmatic fragmentation of USAID’s MCH/FP/RH program investments has resulted in the influence of those investments often being less than the sum of its parts.

A lack of sufficient influence is especially true at the state and national levels, where the sub-division of USAID activities among multiple implementing mechanisms and projects has resulted in USAID’s investments sometimes being seen as relatively small in comparison with those of other donors and with limited leverage.  (In reality, not considering PEPFAR resources, USAID is probably the third largest health sector donor in Nigeria [at $49 million in FY 2008], behind DfID and the World Bank – with PEPFAR resources, USAID is the largest health donor.)

    - It was recommended that USAID should achieve greater effectiveness, impact, and influence from its program investments by concentrating those investments geographically and by bringing the separate components of its MCH/FP/RH program into a smaller number of integrated activities with larger scope and scale (ideally, working at the level of whole states).

    - It was also recommended that USAID should plan and carry out its MCH/FP/RH assistance and support within an overarching framework to further increase the coherence and effectiveness of its programming and to assure coherence among implementing partners and activities in different program areas and at different levels of the health system.

  - The USAID health strategy and immunization teams agreed that the “Immunization Plus Days,” which are intended both to strengthen polio eradication activities and also to effectively deliver other interventions, appear to be falling short in both and in realizing potential synergies.

    - It was recommended that USAID have separate investments to support the extraordinary efforts of polio eradication and accelerated measles control campaigns, while its core MCH/FP/RH programming  should focus on strengthening routine immunization, building on the work already done in this area in Bauchi and Sokoto (as well as the work of the DfID PRRINN and EU PRIME projects). A limited amount of polio resources should be incorporated into USAID’s state-level program support mechanisms, to allow these state level activities to develop “win-win” relationships with polio eradication and accelerated measles activities.  However, in general, USAID support for these campaign activities should be carried out through a separate mechanism, with a state level focus on routine immunization.

  - The primary focus of much of USAID’s public sector support in MCH/FP/RH has been on improving the service delivery level.  This work has given USAID important first-hand experience on the sorts of service delivery improvements that are required and that are feasible.  However, the impact and endurance of such project-achieved service delivery improvements is limited in the absence of improvement in the functioning and capability of key components of the public health system.

    - It was recommended that, specifically for its work in the public sector, USAID should expand its focus from mainly direct engagement in improving delivery at the point of service to achieving such service delivery improvement through support for improvement in the capabilities and functioning of critical components of the health system at state, local, primary care, and community levels.  The outcome of these improved capabilities must continue to be measured in terms of improved health services and outcomes at the population level.  It was recognized that this process will be at best medium term, with outcome level improvement likely to require several years of investment.  It was also realized that such improvement is only likely to be achieved at scale in states that are clearly committed to reform and to resolving the important constraints on health care delivery effectiveness that exist.

  - USAID’s support for delivery of family planning commodities and services through social marketing has demonstrated substantial success at scale in increasing contraceptive prevalence.  More recently, there has also been significant success in social marketing of insecticide-treated bed nets and malaria treatment.  A recent USAID-supported assessment of additional opportunities to work with Nigeria’s dynamic private sector, along with the government’s recently adopted Public-Private Partnership strategy, have opened the door for potentially important additional non-social marketing (NSM) interactions with the private sector in health.

    - It was therefore recommended that USAID should continue to mobilize the power of the private sector by expanding the scope of its social marketing program to additional MCH/RH commodities and services, and also pursue NSM activities that have the potential of delivering high impact goods, services, and/or information in sustainable and scalable ways.  [USAID/Nigeria plans to act on this recommendation through mechanisms other than the proposed agreement under this RFA.]

  - Virtually all project-specific evaluations (as well as evaluations of USAID’s earlier MCH/FP/RH activities in Nigeria) recognized the important success and effective approaches that these projects and activities have achieved through mobilization and engagement of communities.

    - It was recommended that in its planned future work with the public sector, including the proposed work under this RFA, USAID should incorporate and build on these experiences in successful community mobilization and engagement, as an essential element of a functional health systems approach in Nigeria.

  - Evaluation of USAID’s work in health policy indicated that, while some important policy steps had been achieved, in many ways the policy work at the federal level was divorced from the program experience of USAID’s other MCH/FP/RH activities.  At the same time, many central policies were not being translated into effective policy, program, and investment at the state and local level.

    - It was recommended that USAID should maintain a role in central policy dialogue (especially in areas where it had direct program engagement or comparative advantage, such as health care financing), but that USAID’s work in health policy support needs to be much more tightly connected to the experience and needs of state, local, and community-level health care programming.

5.  Related Activities of Other Donors

The World Health Organization in Nigeria (WHO):  WHO has numerous national projects that address various public health problems.  These include:  Communicable Disease Prevention and Control: HIV/AIDS, Malaria and Tuberculosis Control; Non Communicable Disease Control; Child, Adolescent Health and Reproductive Health; Emergency Preparedness and Response; Health Promotion; Sustainable Development; Health and Environment; Nutrition and Food Safety; Health Systems Strengthening; and Essential Medicines.

UK Department for International Development (DfID):  DfID projects include the Partnership for Transforming Health Systems (PATHS);  Health Commodities and Equipment Procurement (HCP); Partnership for Reviving Routine Immunization in Northern Nigeria (PRRINN); Support to Health Reform Foundation of Nigeria  (HERFON); Bridging the Gap (pilot in Niger State to show that basic health services can be provided in a sustainable way at the LGA level); and the National Malaria Project, PATHS2 (has not begun implementation).  DfID also has several projects that focus exclusively on various aspects of the HIV/AIDS problem.

Canadian International Development Agency (CIDA):  CIDA projects include the School College of Health Technology and PHC Project, the Nigeria Evidence-based Health Systems Initiative, support to WHO Polio Eradication Phase IV, and purchase of Contraceptive and Safe Motherhood Kits

World Bank:  The World Bank projects include the Health Systems Development Project II, which ends in 2008; the HIV/AIDS Program Development Project; the Malaria Booster Project which ends in 2012, and the Avian Influenza Control and Human Pandemic Preparedness and Response Project.  A new health sector project is being prepared.

European Commission (EC) Delegation:   EC projects include the European Union Partnership to Reinforce Immunization Efficiency (PRIME), support to routine immunization in Kano, integrated sexual and reproductive health service delivery in Northern Nigeria, and support to control of Avian Influenza.

UNICEF:  The projects supported by UNICEF under the Accelerated Child Survival and Development strategy include malaria and under-five mortality reduction, immunization services, nutrition, including micronutrients, and HIV/AIDS prevention and care.

African Development Bank (ADB):  The ADB supports the Health System Development Project, ending December 2008.

Government of Japan/Japan International Cooperation Agency (JICA):  JICA projects include the infectious diseases prevention for children, through UNICEF; the attachment of an expert to the Directorate of Public Health, Lagos State (ends August 2008); the Asia-Africa Knowledge Co-Creation Project, which ends October 2008;  the Project on Improvement of Maternal and Child Health in Lagos State (planned); support to the HIV/AIDS National Response through provision of equipment and country-focused training; and training and dialogue programs that train health professionals in the public sector.

Bill & Melinda Gates Foundation:    The foundation is initiating support for an urban reproductive health initiative that will be implemented in five cities.

6.  Partnership Environment and New Opportunities

The program of work being solicited under this RFA is being started at a time when there are important new opportunities for USAID’s MCH/FP/RH support to be linked with other actions and investments, in ways that go beyond “coordination and communication” to actually achieve strategic complementarity, leverage, and greater impact.  This new environment includes important overarching strategies and agreements on donors’ cooperation with each other and with the Nigerian government.  It also includes new initiatives and funding sources that can be leveraged strategically.

One key reality to which these strategies and agreements respond is that – despite the significant level of resources being provided by USAID and other donors – these external resources are small in relation to Nigeria’s own public sector resources for health, and also in relation to the resources spent by Nigerian citizens on their own families’ health.  As a result, USAID expects work proposed and carried out under this RFA to proactively and effectively identify opportunities for complementarity of resources and approaches with those of other donors and partners, and to strategically influence partners’ investments and the investments of the Nigerian health system itself (at all levels) to achieve improved health outcomes and impact at the greatest scale possible.

The major partnership and leveraging opportunities at present include:

  - The “Country Partnership Strategy” (CPS):  The CPS was developed by the World Bank Group and the U.K.’s DfID in 2005 as a positive response in support of both the “National Economic Empowerment and Development Strategy (NEEDS)” and the “State Economic Empowerment and Development Strategies (SEEDS)” drafted by a number of states.  The NEEDS and SEEDs provide overarching strategic approaches to development across sectors, including the health sector, and the CPS in turn places increased external investment into the context of these strategies, links that support to Nigeria’s efforts in reform of governance across sectors, and provides a framework for donor coordination.  Among the important principles of the CPS is to support national initiatives for human development, specifically strengthening of the health system.  New investment activities by the World Bank and DfID are being framed within the CPS.  USAID/Nigeria has committed itself to the CPS as an overarching development assistance framework (consistent with the U.S. Government’s commitment to the principles of the Paris Declaration on Aid Effectiveness) and intends to become a signatory to the updated version of the CPS presently under development.

  - National “Integrated Maternal, Newborn, and Child Health Strategy (IMNCH)”:  The national IMNCH Strategy was developed in 2006 through collaboration among the FMOH, donor partners, and leading NGOs and health care professional organizations.  It has been officially adopted as policy at the federal level, and roll-out of implementation is being planned and initiated in selected states through cooperative action by the FMOH, state officials, and partners.  The IMNCH Strategy represents a useful programmatic and technical framework as well as a coherent focus for advocacy regarding the need to strengthen delivery of basic MCH services.  As such, in states that are attempting to use the IMNCH Strategy as an organizing framework for improving and expanding those services, USAID expects to support this strategy [recognizing that the comprehensive package of MNCH interventions and services identified in the IMNCH Strategy is broader than the more limited, but more generally feasible, set of interventions identified for USAID support in this RFA – the more basic package in this RFA is seen as a foundation for the later addition of additional interventions in a phased, state-specific process].

  - “Millennium Development Goal (MDG)funds”:  The federal government holds a substantial amount (billions of dollars) of “Debt Forgiveness” funds from international donors and lenders that are intended to be used to achieve social development and poverty reduction in support of achieving the “Millennium Development Goals” in Nigeria.  These funds are held and disbursed by a special office attached to the Office of the President.  They are generally being allocated in response to proposals by federal ministries and state governments.  The MDG Fund administrator has stated that funds will only be allocated in support of credible proposals that both support achievement of MDG targets and reflect commitment by the proposing entity to fundamental governance reform, transparency, and the strengthening of essential oversight and management capabilities.  [One activity that might be supported in one or both of the target states under this proposal would be to work with state government and partners to develop, and then implement, successful proposals for support from the “MDG Fund.”]

  - Global Alliance for Vaccines and Immunization (GAVI) Health Systems Strengthening funding:  Nigeria has been awarded approximately $45 million by GAVI to support health system strengthening activities that will increase the availability and use of both immunization and other MCH services in wards with the worst health indicators.  These funds might be available to support selected aspects of systems strengthening in the states targeted under this RFA.

  - Malaria Booster Project:  Nigeria is a priority country for the World Bank’s “Malaria Booster” program, which is operating in seven states.

  - Global Fund to Fight HIV/AIDS, Tuberculosis and Malaria:  Nigeria won Round 2 and Round 4 malaria grants totaling $95 million, of which about $30 million have yet to be spent.  Nigeria submitted a Round 8 grant request for more than $850 million.  Thus, there are likely to be substantial resources available for malaria activities with which the work under this RFA can interact and to some extent integrate.

These broad opportunities for partnership and leveraging are in addition to the opportunities to cooperate and synergize with the state-specific activities being supported by several donor and international organization partners (including those listed above).  Key partners in the target states have expressed their willingness and enthusiasm for strategic cooperation with USAID’s MCH/FP/RH program support.  The development of the CPS, a new government climate that permits and promotes improved partner coordination, and the development or proposed development of state-level strategic plans for the health sector in a number of states offer substantive opportunities for influence, leverage, and impact.  USAID intends to take advantage of these opportunities as a key feature of work under this RFA.

7.  Potential for Synergy with Other USAID/Nigeria Assistance Activities

There are a number of other areas of USAID assistance where MCH/FP/RH investment can complement, and be complemented by other health and non-health investments in ways that deliver “win-win” outcomes.  Most prominent among these are:

a.  PEPFAR

FP/MCH/HIV Integration:

There is an opportunity to strengthen the linkages between FP/MNCH and HIV/PEPFAR programming within USAID and in collaboration with other donors and the Government.  This includes strengthening the communication and collaboration between PEPFAR/USAID-supported projects and the MCH/FP/RH program where these programs are currently being implemented.  This collaboration is likely to be enhanced by PEPFAR’s ongoing development of global guidance for integrating MCH and FP activities with HIV programming, including:

- linking prevention of mother to child transmission (PMTCT) (for example, linked to antenatal care plus [ANC+]);

- using primary and community services (as they develop) to support follow-up and treatment of HIV-exposed and infected children and HIV+ mothers;

- delivering integrated messages through a range of  communication channels; and

- capitalizing on antenatal and primary care visits to address relevant HIV, RH and MCH issues.

PEPFAR’s investments in immunization safety can be linked to USAID’s investments in strengthening immunization services in primary health care (PHC).  At the referral level, PEPFAR can strengthen PMTCT platforms, which can then improve the quality of other FP, PPFP, and MCH services, especially ANC, delivery, and post-partum/newborn services.

Reportedly, PEPFAR-supported prevention, care, and treatment activities are beginning to move from the hospital level to the local, PHC, and community levels in some states.  Since there is presently limited capacity at these levels - and therefore much opportunity for strengthening capacity, service delivery, and communication - it is likely that there may be significant opportunities for “win-win” wrap-around and integrated MCH/FP/RH and HIV/AIDS investments.  These should be proactively defined and pursued.

In addition, PEPFAR has developed an effective logistics system that is parallel to other logistics systems.  The potential for leveraging that system may also be explored.

PEPFAR OVC

Since FY2004, USAID/Nigeria has provided leadership under the PEPFAR program for activities focused on orphans and vulnerable children (OVC). This PEPFAR component is supported by a 10% earmarked providing approximately $10 million in FY08. The OVC component of the program works in collaboration with Ministry of Women's Affairs and Social Services and provides services through community-based organizations (NGOs and faith-based organizations).  These implementing partners offer a comprehensive array of programs for eligible children and their families. There are more than 32 implementing partners with programs in 9 focus states. Services include assistance with education, health services, protection (legal and social), food and shelter, psychosocial support and assistance with livelihoods and job training.  Health services are generally obtained through LGA primary or secondary health facilities.  Occasionally, services are obtained from private church based health care providers. This is a logical area for collaboration as community partners have well developed support programs with primary and secondary healthcare facilities.  Wherever possible, these are co-located with ARV treatment facilities. It is clear that there are opportunities for leveraging resources and collaborative planning to strengthen provider capacity and build services. This could support efforts to bring existing services into compliance with existing OVC standards of care and simultaneously strengthen capacity of facilities that serve the general population.

An important feature of the OVC program is its focus on community outreach. Implementing partners work at the community and household level with community leaders to identify the most vulnerable children and defined their needs and the needs of their extended families. This provides a logical opportunity for enhanced outreach and strengthening of community-based monitoring and follow-up of women who may have registered for PMTCT/FP/MCH services but who have been lost to follow-up.  Recruitment and referral of new patients requiring PMTCT/FP/MCH services, but who have not registered could be integrated into existing community outreach. The OVC program is already in dialogue with the ARV treatment component of PEPFAR and Tuberculosis (TB) services to explore these options. Building on this existing platform could significantly strengthen and accelerate outreach FP and MCH services.

b.   Water and Sanitation:

In FY 2009, USAID/Nigeria is planning to allocate two million dollars in water and sanitation funds to local governance activities, municipal water systems, and actual hardware investments (e.g., bore holes) in communities.  To the greatest extent possible, USAID will work to co-locate these and future activities in the health focus states, and to seek maximum benefit to community health through joint planning of these activities.  For example, water installation might be focused on Primary Health Care facilities as part of efforts to increase functionality of those facilities.  Community organizations assisted by either MCH/FP/RH or governance activities might be given the capability to support maintenance and repair (“software components”) of water facilities, complementing installations by either USAID or DoD.  In addition, through PEPFAR the Mission already supports point-of-use water treatment, focused on HIV-affected families and communities, and these activities might be expanded to other households through MCH/FP/RH social marketing of water purification products.  Again, congruence with health focus states may create opportunities for joint planning and mutually supportive implementation.

c.   Governance:

In addition to focusing its health inputs under its new program, USAID/Nigeria sees additional potential impact through the application of USAID’s governance expertise alongside its health investments.  In many respects, USAID’s MCH/FP/RH programming already includes strong governance elements, especially through community organization and “empowerment” (development of self-responsibility for health outcomes) and through communities’ representation of their own interests and demands with local government.  However, substantial value could be added to USAID’s direct health activities by bringing governance expertise to some of the key challenges faced in improving health services.  Two areas where this could be especially beneficial are:

- strengthening the now ill-defined functionality  and accountability of Local Government Authorities in supporting, managing, and financing primary health care services (as well as education), and

- implementing public-private partnerships.

While many of USAID/Nigeria’s current health activities effectively involve a governance dimension, the program being proposed under this RFA can potentially do more to create partnerships between state governments, LGAs and civil society for the betterment of health systems.  At the same time, the new governance program being developed by USAID/Nigeria may find important opportunities to systematically strengthen key governance functions by focusing on such important and concrete outcomes as those in health and education.

8.  Reference Documents

A full compendium of USAID relevant documents is available in annexes posted at http://www.usaid.gov/ng brief summary of the major annexes is found below:

a. Maternal, Child, Reproductive Health and Family Planning Strategic Approach; USAID/Nigeria, September 2008. http://www.usaid.gov/ng/downloads/hpndraftstrategy%20(pdf,%20111kb).pdf

b. Immunizations Today and Way Forward - Promising Support by USAID/Nigeria; M. Harvey, C. Lee, E. Ogden.  (May 12-24, 2008)

http://www.usaid.gov/ng/downloads/immunizationstoday%20(pdf,%20341kb).pdf

c. An Evaluation of the USAID/Nigeria Social Sector Projects:  ENHANSE and 	COMPASS; J. Holfeld, et al.  June 2008.

http://www.usaid.gov/ng/downloads/compassenhansevaluation%20(pdf,%20387%20kb).pdf

d.  The Ground is Softening for the USAID/Nigeria Health Portfolio, Considerations for the Present and Future; J. Holfeld, P. MacDonald, January 2007 (Is that date correct) http://www.usaid.gov/ng/downloads/thegroundisoftening%20(pdf,%20166kb).pdf

Additional relevant materials include and are posted at:

e. Broken Promises, Human Rights, Accountability, and Maternal Death in Nigeria; Center for Reproductive Rights. 2008. www.reproductiverights.org/pdf/pub_nigeria2.pdf

f. National Integrated Maternal, Newborn, Child Health Strategy; Government of Nigeria

http://www.who.int/pmnch/countries/sampleplans/en/index.html

9.  Rationale for design of the public sector MCH/FP/RH support program

The program for which proposals are being solicited under this RFA has been designed in response to USAID/Nigeria’s new Maternal, Child, Reproductive Health and Family Planning Strategic Approach, the findings of evaluations and assessments of its present and past health portfolio, and the opportunities for greatest scale and sustainability of impact through its support for MCH/FP/RH services in the public sector.  In this context, key aspects of the program design include:

- Focusing on two states (potentially Bauchi and Zamfara):  This key aspect responds to the recommendation to focus USAID’s program geographically, and to do so in states that offer the greatest opportunity for USAID’s investment to support the achievement of impact at scale and influence on programming in other states and nationally.

The criteria for selection of the two potential focus states were:

- levels of need (health indicators)

- commitment of the state to health issues and good governance

- ratio of USAID MCH/FP/RH resources to population

- planned or ongoing presence of other USAID programs with which MCH/FP/RH can interact in a win-win investment approach

- other donor presence and potential for coordination (and openness of the state to donor collaboration)

- requests by the states for USAID partnership

- private sector opportunities

- previous USAID experience and investment that can be built on and leveraged for expanded impact (and the results of that previous investment), and

- potential zonal and regional influence of the state.

| Indicator | Bauchi | Zamfara |
| --- | --- | --- |
| Population | 4,676,465 | 3,259,846 |
| No. of LGAs | 20 | 14 |
| No. of PHCs | 1,140 | 585 |
| No. of Hospitals | 16 | 18 |
| Tertiary Hospital | 2 | 1 |
| <5 Mortality | 260/1000 | 269/1000 |
| Maternal Mortality | 1,549/100,000 | 1,500/100,000 |
| CPR | 2% | 1-3% |
| State Commitment | --ANC, delivery and <5 services are free in all government hospitals, --All general hospitals are under going renovation, --New doctors, nurses and midwifes have recently been employed and deployed to all health facilities, --Purchase and distribution of hospital equipment to all general hospitals. -- 2008 budgetary allocation for health >10% (approximately 8 billion Naira) of the total budget --120 million naira counterpart funds | --Free MCH services --Construction and renovation of health facilities through MDG funds --Employment of health personnel across the state ---2008 budgetary allocation for health 7.6% (approximately 6.7 billion Naira) --Supplies of hospital consumables and the construction of Millennium Hospital |
| Other Donors | WHO, UNICEF, UNFPA, EU-PRIME Action Aid, WaterAid and CIDA | WHO, UNICEF, DfID, PRRINN, and EU PRIME |
| USAID Projects | Previous: Vision, Current: PSP-One, IRHIN, GHAIN, COMPASS, COMPASS/Polio, ImmunizationBasics, ACQUIRE/Fistula Care, DELIVER, and CEDPA | Current: ACCESS, ACQUIRE/Fistula Care, and COMPASS/Polio |

Sources: National census, 2005; Needs Assessment of Safe Motherhood -Bauchi; Federal Ministry of Health Situation Analysis of Newborn Care, 2008; Zamfara State Budget, 2008

In focusing the program in these two potential states, with the intention of achieving state-level impact, USAID/Nigeria recognizes and emphasizes that full ownership by the state of all activities, approaches, and investments under this program is absolutely essential and will be a criterion for evaluation of the implementing organization’s performance.

- Reducing fragmentation of USAID’s MCH/FP/RH program:  The program under this RFA brings together what were formerly separate components of MCH and FP/RHsupport and adds to them, providing for delivery and use of a core package of MCH/FP/RH interventions.

- Moving from a principal focus on service delivery to an expanded focus that includes system and capacity strengthening:  The program under this RFA continues an overall focus on the achievement of increased use of high impact interventions, but emphasizes strengthening the systems, service delivery, community, and behavioral capacities and approaches required to increase and sustain their use in the Nigerian context.

- At same time, building on USAID’s deep experience in primary health care and community engagement for health in Nigeria:  The proposed program does not abandon work on improved service delivery at the point of service, nor on the engagement of communities in support of those services and in the promotion of their own health.  Instead, it is intended to encompass its work in a broader system strengthening context, recognizing that in many cases the constraints on effective delivery and promotion of health services are the result of failures in the system, management, and resource allocation and utilization.  .

- Maximizing complementarity of USAID resources with other (partner and Nigerian) resources:  The proposed program recognizes that USAID resources, although significant, are small in relation to both the unmet need for MCH/FP/RH interventions and the resources being provided (with inadequate impact) by the federal, state, and local governments of Nigeria and by Nigerians themselves.  This fact means that to achieve effect, outcome change, and impact at scale this program must identify and operationalize opportunities to strategically leverage its resources and comparative advantages against those of other USAID programs, other donors and international organizations, and government.

- Mobilizing the resources and capabilities of the private sector:  Once again, the program to be implemented under this RFA is NOT the intended mechanism for USAID’s social marketing activities nor for the exploration of major new ventures with the private sector.  However, the organization implementing the program under this RFA can and should support the development of public-private partnerships where a state identifies value-added of such partnerships.  Examples could include contracting out of support services (from transport to laundry to financial management support) or of clinical services (for example, contracting private midwives to attend deliveries at primary or community level) or including private practitioners (M.D.s, nurses, midwives, pharmacists, patent medicine vendors) in relevant training activities.  Another “private sector” dimension could be applying private sector principles to the public health system, such as the use of innovative human resource incentive or management approaches, or the use of performance-based financing at various levels of the system.

- Assuring the connection between program and policy:  This connection between program and policy needs to exist in two dimensions, both of which have been weak.  One is the adaptation and application of national policy and strategy (e.g., the IMNCH Strategy) at state and local levels.  However, probably more important – especially in relation to USAID’s comparative advantage of “having a seat at the table and its feet on the ground” – is the need to systematically “uplink” the needs, experience and evidence of programming at the state, local, and community levels to the development of national and state health policy.  The program under this RFA is intended to do this in part by placing  senior policy advisors at the national level who will be responsible for bringing forward and representing the program’s actual experience (and the evidence generated from that experience) in policy dialogue.  The program will also carry out this policy-informing function by applying solid operations and evaluation research capabilities to key areas of the system and service delivery to generate credible evidence from programming; by identifying, applying, and disseminating successful approaches (whether USAID-supported or not) to resolving key constraints and improving health care effectiveness; and (with government and partners) by supporting experience sharing activities focused on key areas of system and service delivery function.

PART D.	 TECHNICAL APPROACH AND PROGRAM INTERVENTIONS

1.  Program Framework

Objective:  The objective of the program being solicited under this RFA is “Increased Use of High Impact Interventions in selected target states” (potentially Bauchi & Zamfara)

This objective has important implications for the approach to be proposed:

    - The program aims for measurable improvement of health outcomes at the state level in these two targeted states

    - The results of all program investments and activities – whether in policy, system strengthening, service delivery improvement, community mobilization, behavior change, or other areas – will be evaluated in terms of their contribution to measurable improvement in health outcomes during the project and at its conclusion.  This means that determination of priority for program activities needs to focus on the pay-off of those activities in terms of improving those outcomes.  The connection of program activities and investment with outcome change needs to be explicit in the year-by-year planning and implementation process, in consultation with USAID.

    - Because USAID MCH/FP/RH resources by themselves are not sufficient to achieve state-level impact, the implementing organization, with USAID, will need to identify and operationalize appropriate opportunities for partnering and for leveraging partner and Nigerian resources.

2.  “Packages” of selected high impact FP/RH/MNCH interventions for the program

The Nigerian health system is weak and its needs are great.  Indicators of maternal and child health are exceptionally poor, particularly in the northern states, including Bauchi and Zamfara.  The challenge is to identify a very selective set of interventions that, taken as a package:

- reduce some of the major causes of maternal and child morbidity and mortality

- require reasonable and replicable inputs for delivery, and

- contribute to key elements of a functioning health system (both public and private sector), so that other interventions can later be introduced on the “platform” established by this program.

While the final determination will need to be made with focus state and local governments and with partners, the interventions considered as most appropriate for this program are:

a.  Family planning:  With total fertility rate (TFR) over seven in the north, and averaging around 5.5 nationally, early and closely-spaced births contribute to poor maternal, infant and child health indicators, as well as strained family resources and other health problems.  Assessments and evaluations have highlighted recent increases in the acceptability of FP and the success of a number of community-based approaches.  This program’s family planning interventions should include an adequate range of methods to assure that women can choose an appropriate method for their situation, although weaker systems like Nigeria’s may not be able to provide every method.  The minimum choice of methods that should be made available in the Nigerian context at the current stage of health system development includes pills, condoms, injectables, lactational amenorrhea method (LAM), Standard Days Method (SDM) and Intrauterine Devices (IUDs).  Experience in Nigeria and elsewhere in Africa suggests that there will potentially be especially high demand for injectable contraceptives.  All of these methods, with the possible exception of IUDs, can be made available by trained primary health care workers (either at a facility, or by outreach into the community) and community level workers.  In addition to method provision, there is a need for behavior change communication (BCC), including both mass media and interpersonal approaches, to promote “healthy timing and spacing” messages and to make the link between family planning and the health of mothers and children.

b. “Antenatal care+”:  In a population where demand for preventive services is relatively weak, it is significant that a majority of women make at least one antenatal care visit, and that a significant number of women make two or more visits.  These visits provide a window of opportunity for provision of a package of high-impact interventions:  TT, IPT and ITNs for malaria prevention, iron supplementation and nutritional counseling, counseling on exclusive breast feeding, LAM, and transition to other FP methods. These antenatal visits also should be used to counsel mothers and provide reminder materials on danger signs of pregnancy, delivery, and the post-partum and newborn period, on planning for use of referral facilities in case of these complications, and on basic newborn care.  They should also be used to identify other MCH needs, such as routine immunizations or counseling on the use of ORT for diarrhea.  The use of a systematic screening tool such as that developed by the Population Council at the antenatal visit could assist in identification of unmet needs for maternal, infant and child health interventions, and filling these gaps.  Of course, a sine qua non for the applicability of this tool is the availability of the necessary services at site (or less desirably, by referral) to fill the identified needs.

c. Recognition of Complicated Pregnancy and EmOC:  During the next five years, USAID’s efforts through this program need to help develop and support a transitional approach with four basic components:

- increasing availability of skilled attendance for birth at home, PHC, and referral level facilities

- increasing utilization of these skilled birth attendants and facilities for delivery

- assuring recognition of danger signs and complications of pregnancy and delivery, and removing barriers to timely movement of women experiencing these complications to appropriate referral facilities, and

- strengthening the capacity of these referral facilities to resolve life-threatening pregnancy, delivery, and post-partum/post-abortion complications.

Presently, most PHC facilities in USAID-assisted states, including Bauchi and Zamfara, do not have skilled birth attendants.  While future efforts will include developing and supporting assistance for routine delivery at the PHC level, at present the appropriate approach to increasing institutional delivery for even routine deliveries is to channel demand to referral level facilities and strengthen their capability.  Immediate and sustained efforts also need to focus on getting complicated pregnancies and births to these secondary facilities, including recognition by families and community workers of the danger signs and complications of pregnancy and child birth that require facility-based care, planning how that care will be accessed, and establishing a system to transport women to the appropriate facility.  This approach could have a major impact on maternal mortality in the near term.

At the same time, analysis of numbers of births and the capacity of hospital facilities in an area where USAID is working in the North indicates that those facilities, when operating at capacity, could handle only about 20 percent of all births in their catchment areas.  Therefore, in the long term, it is probably not feasible or advisable to promote births by all women in these referral facilities.  Thus, beginning immediately, there should be a concurrent focus on building alternative sources of adequate care for routine deliveries, either through strengthened and staffed PHC facilities, increased training of lower level community health workers (e.g., female junior community health extension workers) who can attend uncomplicated births and detect complications, or contracting out of midwifery services to trained midwives.

Finally, there are specific technologies whose introduction at appropriate levels could produce significant impact in reducing maternal mortality: the two most important are the use of either oxytocin (potentially in UniJect) or misoprostol to prevent and control post-partum hemorrhage, and the use of magnesium sulfate to treat eclampsia.

d.  Routine Immunization:  As noted above, USAID has concluded that its investments to support the extraordinary efforts of polio eradication and accelerated measles control campaigns, as well as other campaign approaches, including the “Immunization Plus Days,” should be separated from its support for improving routine immunization as part of basic heath services.  Therefore, in the program under this RFA, the focus will be on strengthening routine immunization, building on the highly regarded work already done in this area in Bauchi and Sokoto. A limited amount of polio resources will be incorporated into this program to allow the program to develop “win-win” relationships with polio eradication and accelerated measles activities.  However, in general, USAID support for these campaign activities will be carried out through a separate mechanism potentially WHO, with the focus of this program being on routine immunization.

Immunization is an essential function of a working primary health care system, including the upstream management, logistics, and monitoring required to implement it.  USAID has had some success in strengthening the ability to plan, implement, and monitor routine immunization at state, local, PHC facility and community levels.  This program will should work to synthesize this experience, and collaborate with DfID and the EU in combining this experience with that of the PRRINN and PRIME projects, to develop a coherent approach and program materials that can be used to support states and local governments in strengthening routine immunization.

In line with the findings of USAID’s immunization assessment team, the key foci of work in supporting routine immunization as part of PHC should include strengthening facilities and building structural and human capacity to:

- ensure vaccine and vaccination supplies at service delivery points;

- increase the number of service delivery points reliably providing immunizations;

- increase and sustain high levels of attendance during immunization sessions;

- establish monitoring at LGA and health facility levels; and

- strengthen efficient data management and quality of services using the Reach Every Ward approach at LGAs, health facilities and community levels.  .

The importance of child immunization should also be a component of BCC messages through a range of channels including outreach and mass media.  Community health committees should raise awareness on the importance of immunization, and antenatal visits should be used as an opportunity to identify children in need and to counsel mothers on the importance of fully immunizing their next child.  Community organization can be also used to organize the population for routine outreach (which is a key component of routine immunization in settings with low facility coverage) and also for extraordinary campaigns, as are implemented for polio and measles.

Overall, to achieve these results, this program will support:

- decentralized ownership of routine immunization at the state and LGA levels;

- increased and sustained immunization coverage through community planning;

- strengthened health worker, facility, and government capacity; and,

- through these inputs, development of a functional and affordable approach to improving routine immunization services as a core component of primary health care.

e.  Vitamin A:  Program efforts will focus on maximizing coverage of vitamin A through multiple channels, with emphasis on increasingly doing this through primary services and community mobilization.  Routine outreach (as opposed to polio and measles campaigns and IPDs) is a core function of PHC facilities and should be used to the maximum to achieve high levels of vitamin A coverage.  Delivery at PHC facilities and other facilities will also be strengthened – this will require knowing children’s vitamin A capsule administration status (as well as their immunization status), making the use of immunization and child health cards retained by mothers an important element.  Community identification of children needing vitamin A and immunization can contribute to increased coverage, as can focused community-organized “child health days.”  With vitamin A supplies and delivery strategies being driven by other partners, it will be necessary for USAID-supported health systems strengthening activities to help maximize the effect of these investments through improved planning and organization; however, the emphasis should be on increasingly delivering vitamin A through less intensive and disruptive approaches than IPDs.

f.  Treatment of child illness (“Malaria-plus”):  About 110 million cases of malaria are diagnosed each year in Nigeria, accounting for more than 60% of outpatient visits and 30% of hospitalizations.  Malaria is the leading cause of mortality in children under five, killing an estimated 300,000 children a year.  USAID and other partners (World Bank “Malaria Booster” program, Global Fund) are making substantial investments in improving the availability and use of effective treatment (Artemesinin-based Combination Therapy) through the public sector and private channels.  These investments can act as the leading edge of a package of appropriate care-seeking and treatment of malaria, diarrhea (with ORT), and pneumonia – thus addressing the other two leading causes of post-neonatal infant and child death - again in both public and private services.

For malaria, the package will also include provision and promotion of use of insecticide-treated bed nets (ITNs).  This program will focus on ITN distribution and promotion through effective public sector channels.  At the community level, there are important opportunities for BCC and organization around obtaining ITNs and their use by pregnant women and children under five.

The framework for the proposed program has four Sub-Objectives:

Sub-Objective 1 - Strengthen state and local government capacity to deliver and promote use of high impact MCH/FP/RH interventions (estimated 35% of Level of Effort {LOE})

Expected Results

- Major systems deficiencies, constraints, and opportunities for improved delivery of high impact MCH/FP/RH interventions identified (in each state)

- Technical capacity of key state, local and ward health system managers strengthened

- Critical elements of resource allocation, planning, management, organization, and financial management improved at state and local government levels

- Availability, quality, and use of information for decision-making increased

- Availability of essential commodities, drugs, vaccines and equipment at PHC facilities and essential referral levels assured

- Required staff at PHC facilities and essential referral levels present, supported, and effectively managed

- Capacity to plan and implement effective behavior change/communication activities strengthened

Statement of Intent

In the selected targets states (potentially Bauchi and Zamfara), this program will work with the state and local governments and with development partners to identify and help overcome key system obstacles that reduce the effective delivery and use of the program’s identified packages of “core” MCH/FP/RH interventions.  Both states, and the Nigerian health system as a whole, have been the subjects of multiple health system assessments; it is anticipated that the implementing organization for this program will be cognizant of these assessments, carrying out additional assessment activities only as needed to fill key information gaps.  The program should focus on both the need and opportunity to make the greatest improvements in key system functions in applying USAID resources and comparative advantages.  If strategic or investment plans for strengthening the health system exist or are developed in the state, these plans will serve as the starting framework for program activity; additional areas of work can be proposed to and agreed upon by the government.  In all assessment and planning activities, the implementing organization will work directly with state and relevant local government representatives to assure agreement and ownership of planned activities.

It is expected that the implementing organization will provide strong staff capability in key aspects of health systems strengthening, with access to additional expertise that may be required through the resources of its own organization and any sub-grantees.

In its annual plan submission to USAID, the implementing organization will demonstrate how the proposed investments and activities in systems strengthening are strategically and operationally related to increasing use of the core package of MCH/FP/RH interventions.

As noted in Section B.9. above, USAID recognizes that it does not have adequate resources to carry out all the improvements required by the health systems in these two states.  Therefore, it intends that the implementing organization will work with USAID, state and local governments, and development partners to identify and use opportunities for complementarity and leverage of USAID resources.  USAID also expects that this program will identify and utilize opportunities for complementarity with other USG programs, such as logistics, training, and behavior change/communication investments made by PEPFAR and USAID malaria activities and any investments in strengthening key functions of state or local government by USAID’s governance program.

As indicated in “Expected Results” above, USAID anticipates that many of the program’s activities under this Sub-Objective will focus on strengthening “classic” components of public sector health systems. However, USAID also understands the potential utility of partnerships and linkages with the private sector that may be useful in strengthening or carrying out key health system functions: examples might include developing and applying government capacity to contract out either support functions or clinical services, or increasing the capacity of private health care providers where this capacity increases the effectiveness of delivering high impact MCH/FP/RH interventions.

Illustrative Approaches

- Promote the collection and use of data for decision making

- Assist in supporting “decentralization” both to ensure community participation and to increase the ability of LGAs to manage health facilities in a participatory, accountable and transparent manner.

- Support coordinated and consistent sector management (planning, budgeting, program implementation and performance management) and the development of systems to carry out those management functions, particularly at the LGA level

- Work with the DELIVER project to strengthen the logistics systems within the states

- Increase the number and effectiveness of health providers at the PHC facility level

- Improve the technical quality and skills development aspects of training institutions in the development of critical health care cadres

- Improve personnel management to increase the effective use, support, and retention of primary and essential referral level health care staff.

Sub-Objective 2 – Strengthen the delivery and promotion of high impact FP/RH/MNCH interventions at PHC facilities and essential referral levels (estimated 30% of LOE)

Expected Results

- Technical capacity and skills of PHC facility and essential referral level staff increased

- Delivery of standards-based care at primary and referral facilities expanded

- Provision of health services through appropriate outreach and facility-community linkages maximized

- HW performance improved through strengthened supervisory systems and community oversight

- Communication by health workers at the health facility and community levels improved and expanded

- Appropriate and timely referral and counter-referral between referral facilities and PHC clinics increased.

Statement of Intent

Given the low coverage of essential health services in Nigeria and the nature of the burden of disease, increasing the coverage and effectiveness of primary health care services is a critical requirement for improving the health and population status of Nigeria’s families.  In the selected target states (potentially Bauchi and Zamfara), this program will apply, and wherever possible build upon, the extensive experience and investments of predecessor USAID-supported activities in improving the effectiveness and quality of PHC services and of referral level services where they are essential to delivery of key MCH/FP/RH interventions (for example, in the provision of emergency obstetric care).

In selected areas, these predecessor activities and the work of other development partners and the federal and state governments have:

- developed improved training and skill-building approaches for PHC staff;

- technically updated diagnosis and treatment approaches (including updated “standing orders”);

- developed and applied quality improvement approaches for PHC and essential referral level services;

- identified the support required for effective participation of PHC workers in outreach, community mobilization, and campaign activities;

- developed materials and training to support improved communication between PHC health workers and their clients; and

- helped PHC workers and their supervisors establish improved links with the communities  they serve.

USAID intends that this work and other essential efforts to improve coverage, quality, and utilization will be continued and extended under this program.  Again, recognizing that USAID’s MCH/FP/RH resources are limited, expansion of improved PHC at the state level will require a greater degree of stepping back from actual points of service delivery to take more systemic, scalable, and leveraged approaches to PHC.

Illustrative Approaches

- Increase the number and functionality of PHC workers

- Support the development and/or application of effective, level-appropriate skills-based training for PHC and essential referral level personnel

- Ensure use of standards-based management for facility and community-based services.

- Identify feasible approaches to supervision and other approaches to maintain and ensure quality (including community supervision and incentive-based approaches)

- Identify additional mechanisms to encourage health service accountability to the community

- Identify approaches to maximize community outreach by and effectiveness of CHEWs and “Junior CHEWs”

- Facilitate improved coordination and collaboration between community and facility-based services.

Sub-Objective 3 – Strengthen the roles of households and communities in promotion, practice, and delivery of high impact MCH/FP/RH interventions (estimated 25% of LOE)

Expected Results

- Family planning, child spacing and healthy mother and child behaviors established as cultural and community norms

- Knowledge and awareness of the benefits of appropriate health practices increased

- Recognition of illness, malnutrition and other health complications increased

- Appropriate health care seeking behaviors increased

- Delivery of basic health services and provision of essential health information through appropriate community channels maximized

- Community organization and participation in outreach and other health activities increased

- Community participation in advocacy and oversight of local health services increased

- Communication and service delivery links between community and facility enhanced

Statement of Intent

USAID’s experience in support of MCH/FP/RH programming in Nigeria has generated a substantial and successful body of experience in mobilizing communities to participate in and advocate for healthcare activities.  USAID’s programs have also demonstrated successful approaches to reaching households and improving preventive, promotive, and care-seeking practices.  As with Sub-Objective Two, the program’s work under this Sub-Objective will continue and extend this experience, with the final target of strengthening community engagement and household-level practices across the two states.

Illustrative Approaches

- Identify and address, as feasible, key obstacles to appropriate practices and care seeking behavior

- Increase IEC/BCC and social mobilization in communities

- Increase use of demonstrated family and community-based information tools (e.g. immunization card) and communication materials

- Support organization, capacity building, and engagement of community groups such as health committees, women’s groups, youth groups, market women’s groups, and others as relevant in appropriate health activities

- Establish roles for community representatives in oversight of local health services and representation of community needs with local government

- With government, identify and help operationalize appropriate, expanded roles for community health workers and volunteers in detection and management of child illness and complicated pregnancies and deliveries.

Sub-Objective 4 - Improve policies, programming, and resource allocation at state and federal levels (estimated 10% of LOE)

Expected Results

- Critical policy, resource, and program constraints on improving MCH/FP/RH outcomes are clearly identified and effectively addressed at the national and state levels

- Credible evidence is developed from USAID-supported program experience through operations and evaluation research

- Evidence, experience and issues identified from program experience in selected target states (potentially Bauchi and Zamfara) are represented in strategy and policy dialogue with federal and state decision-makers

- Important policy and strategy decisions at national level are effectively adapted and applied in the selected target states (potentially Bauchi and Zamfara)

- USAID and other development partners speak with “one voice” in dialogue with government

- Selected target states (potentially Bauchi and Zamfara) develop successful proposals for MCH/FP/RH funding under Nigeria’s “MDG Fund,” GAVI Health Systems Strengthening support, and other new funding sources

Statement of Intent

As noted in section B.4. Summarized key findings (and recommendations) from recent evaluations and assessments of these activities above, USAID/Nigeria has supported policy dialogue at the federal level through a dedicated mechanism (ENHANSE).  While this activity has had some influence, USAID believes that policy and strategy dialogue at the federal level, and in the two states that are the focus of this program, needs to be more tightly linked to the realities of program experience at the state, local, and community levels.  Under this program, USAID’s engagement in policy dialogue will be strengthened by the presence of two highly experienced and effective senior policy advisors in Abuja.  The senior advisors will not be in charge of field operations of the program, but will rather be responsible for working with USAID, the team leaders of program operations in the two states, state and local officials in the two states, and development partners to link program experience to policy dialogue in Abuja and with state and local government.  The policy advisors, and program leaders in the two states, will also be positioned to help states adapt and apply key MCH/FP/RH strategies and policies coming from the federal level (for example, the IMNCH Strategy).

A second critical dimension of introducing program experience into policy and strategy deliberations is the need to produce systematic documentation and credible (whenever possible, quantitative) evidence.  To do this, USAID intends this program to include and apply a strong capacity in operations and evaluation research.  USAID notes that many programs focus first on implementation and hope to carry out “documentation” and “lessons learned analyses” retrospectively; however, in USAID’s experience, these approaches seldom produce influential and credible evidence.  Thus, USAID intends that the operations and evaluation research of the program will be applied prospectively and strategically to document the results of approaches aimed at improving effectiveness in critical aspects of systems strengthening, primary care service delivery, or community/household engagement.  It is expected that the senior policy advisor, state team leaders, state officials, relevant partners, and USAID/Nigeria will consult periodically to identify the most relevant areas for this operations and evaluation research.

Finally, USAID expects that the program will participate in the planning and implementation of experience-sharing activities (consultations, exchange visits, etc.) that will allow the selected target states (potentially Bauchi and Zamfara) to benefit from successful program solutions in other states, and that will allow other states and federal officials to benefit from program successes in the selected target states.

Illustrative Approaches

- Participate in/conduct analyses of policy, resource, and program constraints on improving MCH/FP/RH outcomes

- Apply operations and evaluation research to key areas of health system function, PHC and essential referral service delivery, or household/community health activities

- Engage in strategy and policy development processes at state and federal levels

- Participate in regular and ad hoc coordination activities with development partners at the state and federal level

- Provide technical and analytic support to development of proposals for MCH/FP/RH funding from the “MDG Fund,” GAVI Health Systems Strengthening funding, and other sources

PART E.	PERFORMANCE MONITORING AND INDICATORS

The program will be characterized by robust monitoring and evaluation, using strategic information for decision making, analysis, and programming. The program should continuously gather and analyze data and information to refine and improve its activities and should be results-oriented, producing measurable positive outcomes and impact. Applications should include detailed plans to monitor and evaluate program performance. Upon award, the selected recipient will work with USAID/Nigeria’s Agreement Officer’s Technical Representative (AOTR) to ensure that indicators are aligned with the U.S. Foreign Assistance Standard Indicators and also measure results and impacts of the program.

Performance monitoring under this program shall include two components, which may for some indicators overlap.

1.  OP Indicators

  - From the beginning of the program, the awardee shall be required to report annually the data on USAID-specific “Operational Plan” (“OP”) indicators relevant to the USAID program.   The current indicators are listed below, but are subject to future modification.  The specific OP indicators to be reported on shall be determined in consultation with USAID/Nigeria as relevant to the actual program being implemented.

- Number of improvements to laws, policies, regulations, or guidelines related to improved access to and use of health services drafted with USG Support

- Number of institutions (States/LGAs/PHC Centers ) with improved MIS as a result of USG Assistance

- Number of people trained in child health and nutrition through USG-supported health area program

- Number of people trained in maternal/newborn health through USG-supported programs

- Number of medical and para-medical practitioners trained in evidence-based clinical guidelines

- Number of antenatal care (ANC) visits by skilled provider

- Number of deliveries with a skilled birth attendant (SBA) in USG-assisted programs

- Number of cases of child diarrhea treated in USAID-assisted programs

- Number of cases of child pneumonia treated with antibiotics by trained facility or community health workers in USG-supported programs

- Number of children less than 12 months of age who received DPT3 form USG-supported program

- Number of children under five years of age who received Vitamin A from USG-supported program

- Couple years of protection (CYP) in UGS-supported program

- Number of people trained in FP/RH with USG funds

- Number of USG-assisted service delivery points providing FP counseling or services

- Number of USG-assisted service delivery point experiencing stock-outs of specific tracer drugs

- Performance Indicators

  - In addition, USAID shall require monitoring and annual reporting of program-specific performance indicators relevant to achievement of the program’s objectives and each of the sub-objectives.  Targets for at least a sub-set of these indicators for each state, and for the program overall, shall be agreed upon among USAID, the awardee, and state-level counterparts; these targets shall be established for the end of Year 2 (of the 5 year program), and a new set of end-of program targets shall be developed at the beginning of Year 3.

USAID acknowledges that it is inappropriate to specify these objective and sub-objective level indicators and targets at this point, prior to assessments and negotiations with each state.  A number of “illustrative indicators,” at these levels are identified here.  However, USAID intends that, before the end of Year 1, the awardee, in consultation with USAID and state authorities, will have identified the principal foci of systems, PHC, community, and policy activities for the first years of the program and shall then propose a Performance Management Plan (PMP) for USAID approval that includes both process and outcome/impact indicators and targets relevant to the planned work under the program.  The PMP shall also include plans on how to generate the data needed to measure the impact of the program.

Illustrative Performance Indicators:

Objective Level –

  - Modern contraceptive prevalence rate

  - The proportion of birth intervals that are 36 months or longer

  - Percent of births to mothers under age 18

  - Percentage of women seen at ANC at least one (and at least four) times during their last pregnancy

  - Percent of pregnant women receiving intermittent preventive therapy with an appropriate antimalarial

  - Percent of deliveries attended by skilled attendants

  - Vitamin A supplementation coverage among children 6-59 months

  - Percent of infants exclusively breastfed through age six  months

  - Percent of pregnant women/children under age five sleeping under ITNs

  - Percent of children under five with fever receiving an appropriate antimalarial

  - Percent of children who received DPT3/measles immunizations by age 12 months

  - Percent cases of child pneumonia treated with appropriate antibiotic

  - Percent of children with diarrhea receiving oral rehydration therapy/zinc treatment for diarrhea

Sub-Objective 1 -

  - Number/percent of LGAs with:

    - Managers for health programming identified and trained

    - Adequate health plans in place

    - Functioning information systems providing specified key information

    - Etc.

  - Number/percent of PHC facilities with essential staff

  - Number of state, local and ward health systems managers trained (in specific areas)

  - Number/percent of PHC facilities with less than one week of stock-out of tracer drugs/commodities in preceding six months

  - State MoH has adequate:

    - Planning and budget process

    - Information system

    - Position descriptions for key technical, communication, and management staff

    - Staff with appropriate technical and program experience (in relation to position descriptions)

    - Etc.

Sub-Objective 2 -

  - Number of visits to public health providers in target LGAs for (specific) MCH/FP/RH services (increase based on baseline data.) (alternate: percent of expected cases of [condition] using PHC services for care)

  - Percent of PHC providers demonstrating adequate levels of competence (in specified key services) in relation to evidence-based standards

  - Percent of PHC workers receiving at least one adequate supervisory session during past six months

  - Percent of PHC facilities that offer routine immunization

  - Number of community visits by CHEWs and Junior CHEWs

Sub-Objective 3 -

  - Change in percent of women/men who desire to limit or space number of children

  - Percent of households with knowledge of key symptoms/danger signs/appropriate care-seeking for specified MNCH conditions

  - Percent of households practicing selected preventive behaviors

  - Number of community-level health volunteers engaged in LGA-approved community health activities

  - Number of communities that have engaged with LGA officials on health care delivery

  - Number of beneficiaries of specified community-level health services.

Sub-Objective 4 -

- Number of improvements to laws, policies, regulations or guideline related to improved access to and use of health services drafted with USG support

- Number of program-based operations/evaluation research activities conducted

- Number of meetings held with other development partners to discuss appropriate position in discussions with the GON and States

Note: USAID intends that, to the greatest extent possible, data collection for monitoring and reporting purposes be collected through state and local information systems themselves, in ways that contribute to the strengthening of those systems.  However, USAID also recognizes that – especially for OP indicators and during the early stages of program assistance when local information systems may be especially weak, program-specific data collection and reporting systems may need to be used to complement or stand in place of, state and local systems.

“Overarching Considerations”

- A “holistic” approach to achieving the program Objective -  Although the program framework for achievement of the program objective identifies four Sub-Objectives, USAID’s intent is that the program will be viewed and implemented as a coherent whole, so that key actions at the policy/resource, system, primary care, and community household levels are strategically connected to address the major opportunities for and constraints to achieving the Objective:

  - State ownership – This program is intended to be primarily a partnership among USAID and the two selected states.  While USAID foresees that the experiences and approaches developed in these states will be systematically drawn upon to inform broader policy and program, the central focus is at the state level. For this reason, the Chief of Party and Deputy Chief of Party will each be located in one of the states and will function as team leader for their state component of the program.  In addition to this decentralized approach, USAID intends that activities under the program be understood and perceived by each state to be intrinsic support to their programming, not a semi-autonomous or parallel USAID-supported activity.  Establishing that ownership and engagement by state and local authorities will be essential for at-scale success and ultimate sustaining of program contributions, and will therefore be a primary criteria for evaluation the performance of the COP/DCOP and the state teams.

  - “Parity” between the two states – Although the nature of USAID agreements requires one COP, who will be in one state, a corollary to state “ownership” of the program is that the programs of each state are to be seen as independent and equal.  There will be opportunities for shared technical resources, experiences, tools, materials, and other exchanges that will be of mutual benefit, and the program is expected to take advantage of these.  However, one state program is not viewed as subsidiary to the other.

  - Gender – The situation and autonomy of women is a major factor in accessing essential health services.  It is also a key factor in achieving control of their fertility and in maintaining and improving their own health and that of their families.  This situation will vary between and within states, but must be taken into consideration.  Appropriate opportunities to support the empowerment of women and improving their access to resources and information should be proactively identified and taken into consideration in service delivery, community mobilization, communication, and other programming activities.  At the same time, the important role of men as gatekeepers and as self-perceived responsible parties for family welfare also needs to be understood and taken into consideration in the program’s activities.

  - Community as part of the “system” – USAID’s experience both in Nigeria and throughout the world confirms that communities can play effective and critical roles in public health through mobilization of resources, active engagement in assuring availability and quality of services, actual delivery of services, transmission of information and support for behavior change, and other actions.  For this reason, USAID envisions the community as an essential part of the health system, not as a separate entity that exists outside a health system that ends at the last facility.  (In fact, in some of its most important experiences, such as Nepal, the health system works from the community up, not down from the center.)  USAID intends that this program will embody this vision of community as a core component of the health system, and will operationalize it in the program implementation.

  - Governance – USAID also holds a vision of government that responds to the needs of people and engages people affected by government practices.  As noted, many of USAID’s health activities in Nigeria have actively applied this vision to the planning, funding, oversight, and implementation of health services and health communication.  At the same time, USAID’s governance programming works to strengthen these key characteristics of good government.  Thus, USAID intends that this program will work with health systems and health care delivery to embody this vision, and to interact with broader governance programming where such opportunities exist.

  - Strategic complementarity of investment and activities with other USG and partner investments – For many reasons, USAID intends that strategic complementarity of investment and programming will be a fundamental characteristic of this program, for many reasons.  On one level, USAID and the U.S. Government subscribe to the principles of the Paris Declaration on Aid Effectiveness, which calls for harmonization of donor actions and alignment of those actions with country-led plans and programs.  At the national level USAID/Nigeria is committed to the CPS and recognizes the important new opportunity that exists for donors to help catalyze needed change by working together, sharing experiences, and speaking with one voice.  In terms of resources, the relatively limited USAID resources for MCH/FP/RH clearly will benefit by being applied wherever appropriate with malaria, HIV/AIDS, and other USG programs, as well as with the investments of other donors in these areas, immunization, and other programming.

PART F.	MONITORING AND EVALUATION

Monitoring of results is a key element of USAID programs.  USAID/Nigeria seeks data and information to improve performance and effectiveness as well as to inform planning and management decisions.  Accurate and timely monitoring will enable TSHIP to adapt to changing conditions and make mid-course correction as necessary.  Data also must be available to demonstrate program impact. Specific indicators and targets for achievement of the activity objective and each of the four sub-objectives will be developed by the implementing agency and submitted as part of the overall monitoring and evaluation plan (M&E plan) for this activity.  The M&E plan submitted by the implementing partner will be subject to approval of the Agreement Officer’s Technical Representative (AOTR).

Indicators and targets for each sub-objective should illustrate how TSHIP will contribute to improved delivery of MCH/FP/RH services.  Measurement of achievement under the award should directly relate to the technical assistance and other support provided under this project.

PART G.  REPORTING REQUIREMENTS

The recipient shall submit reports to the USAID AOTR as described below.

1.	Annual Work Plan:  The recipient shall prepare detailed Annual Work Plans, with detailed cost information to the AOTR for approval.  The format shall be established by USAID.  The first Annual Work Plan will be due within 45 days of the award and will cover the period from effective date of award through September 30, 2009.  The subsequent Annual Work Plans will cover the period October-September (The USAID fiscal year) and are due by August 31.

2.	Performance Management Plan (PMP):   The Recipient shall submit one original and two copies of a performance management plan to the AOTR  The performance reports shall be submitted quarterly and shall contain the following information on activities: 1) explanation of quantifiable output of the programs or projects, if appropriate and applicable; 2) reasons why established goals were not met, if appropriate; and 3) analysis and explanation of cost overruns or high unit costs (recipient must immediately notify USAID of development that have a significant impact on award-support activities.)  Further, notification must be given in the case of problems, delays or adverse conditions which materially impair the ability to meet the objectives of the award.  These notifications must include a statement of the action taken or contemplated and any assistance needed to resolve the situation.

The PMPs are due 30 days after the end of the quarter.  The quarters are based on the USAID fiscal year, i.e., October-December, January-March, April-June, and July-September.  The first Performance Management Plan shall be completed by the awardee and approved by USAID approximately six months after the project is awarded.  Thereafter the reports shall be prepared and submitted quarterly. The first PMP shall be a plan of action that shall identify indicators, establish base line data, and how data will be generated.

The fourth quarter PMP shall report on the quarter and also include an annual report of the project.

3.	Final Performance Report:  The recipient shall submit the original and one copy to the AOTR and one copy to USAID Development Experience Clearinghouse, ATTN:  Document Acquisitions, 1611 N. Kent Street, Suite 200 Arlington, VA 22209-2111 (or email: docsubmit@dec.cdie.org).

The final performance report, to be submitted 90 days after project completion, shall include an executive summary of the Recipient’s accomplishments in achieving results and conclusions about areas in need of future assistance; an overall description of the recipient’s activities and attainment by results by country or region, as appropriate during the life of the CA; an assessment of the progress made toward accomplishing the objective and expected results, significance of these activities; important research findings, comments and recommendations, and a fiscal report that describes how the recipient’s funds were used.

4.        Financial Reporting:  Financial Reports shall be in keeping with 22 CFR 226.52.  In accordance with 22 CFR 226.52 the SF 269 “Financial Status Report” will be required on a quarterly basis, to coincide with USAID’s fiscal year calendar.  The first quarterly report will cover the period of TBD (award date through September 30, 2008). Subsequent reports will cover the three month periods ending in December, March, and June, September.

a.   The recipient shall submit a signed and electronic copy of the SF 269A “Financial Status Report (Short Form)” to the Cognizant Technical Officer with one copy to the Agreement Officer. In block 12. “Remarks” of the SF 269 “Financial Status Report” (or as an attachment to the SF 269 Report), the recipient shall provide, in tabular format,  block 10 “Transactions” information (blocks 10.c through 10.i.) by Fund Source for each of the Results. Quarterly financial SF 269 reports are due 30 calendar days, after the reporting period.

b.   In accordance with 22 CFR 226.70-72, the Recipient shall submit the original of the final financial report to Financial Management Office, one copy to the Agreement Officer, one copy to the Cognizant Technical Officer.

PART H.  MANAGEMENT REVIEW AND EVALUATIONS

The Annual Work Plan shall form the basis for a joint management review by USAID and program staff to review program directions, achievement of the prior year work plan objectives, and major management and implementation issues and to make recommendations for changes as appropriate.  A semi-annual management review shall also be held to review progress.

At any time during program implementation, USAID may conduct one or more evaluations to review overall progress, assess the continuing appropriateness of the project design, and identify any factors impeding effective implementation.  USAID will utilize the results of the valuations to recommend any mid-course changes in strategy if needed and to help determine appropriate future directions.  Site visits may be scheduled at a time convenient to both the Recipient and USAID.

PART I.  SUPPORTING INFORMATION

1.  Period of Performance

The period of performance of this agreement is five (5) years from the date of award.

2.  Proposed Funding Sources and Funding Levels

The Mission estimates that the funding for the TSHIP project will total approximately $93,200,000.00 to be allocated over the program period.  The Cooperative Agreement will be incrementally funded subject to the availability of funds.

3.  Authorized Geographic Code

The authorized geographic code for procurement of goods and services under the cooperative agreement is 935.

4.  USAID Management

The award will have one Agreement Officer’s Technical Representative (AOTR) from the Health, Population and Nutrition (HPN) Team (Investing in People Office).  The AOTR will work in collaboration with AOTRs from other projects that overlap or feed into service delivery, centrally managed USAID/Washington projects that may be working in Nigeria, and other Mission activities that may be able to provide support.  The AOTR will regularly meet with Project senior leadership and staff to track program and activity design, implementation, progress, and evaluation; and conduct semi-annual management reviews and budgetary analyses.

PART J.  SUBSTANTIAL INVOLVEMENT

USAID/Nigeria shall be substantively involved during the implementation of the Cooperative Agreement in the following ways:

1.  Review and comments on the Recipient’s Annual Work Plan will be made by the AOTR.  Significant changes to the work plan will also require review and comments by the AOTR.

2.  Designation of key positions and approval of key personnel by the AOTR.

3.  Approval by the AOTR of the Performance Management Plan and any subsequent changes to the PMP.

4.  Approval by the AOTR of the Recipient’s Monitoring and Evaluation plan.

PART K.	DESIGNATION OF KEY POSITIONS AND PERSONNEL

Certain skilled experienced professional and/or technical personnel are essential for accomplishing the work to be performed. These individuals are defined as ‘Key Personnel’.  The Technical Application must propose Key Personnel and show how their skills and experience support the program.  Proposed Key Personnel positions are, Chief of Party (COP), Deputy Chief of Party, Senior Policy Advisor, Senior Financial/Administrative Specialist, and Senior M&E Specialist.  It is the Applicants’ responsibility to propose a staffing structure and designate senior technical advisors as appropriate.

Contact information for Key Personnel references must also be included, along with a statement of what consideration will be offered if proposed key personnel are no longer available at the time of award.  Curriculum Vitae for proposed key personnel must be included in the annexes.  Applicant may also include short biographical information on non-key personnel.

For purposes of building capacity, cost efficiency and project sustainability, USAID strongly encourages applicants to minimize the use of expatriate staff.  Staff must include some professionals with extensive knowledge of Nigeria.

[END OF SECTION C]

SECTION D  - CERTIFICATIONS, ASSURANCES, AND OTHER STATEMENTS OF RECIPIENT

U.S. AGENCY FOR INTERNATIONAL DEVELOPMENT

# The certifications and forms included on the links below are to be completed and submitted as part of the Cost/Business Application.  Refer to instructions in Section A of the RFA.

PART I - CERTIFICATIONS AND ASSURANCES

Certifications, Assurances, & Other Statements of Recipient:  http://www.usaid.gov/policy/ads/300/303sad.pdf

# PART II – FORMS

# http://www.grants.gov/agencies/approved_standard_forms.jsp

# Standard Form 424: www.grants.gov/techlib/SF424-V2.0.pdf ;

Standard Form 424A:http://www.grants.gov/techlib/SF424A-V1.0.pdf

Standard Form 424B: http://www.grants.gov/techlib/SF424B-V1.0.pdf

OMB CIRCULAR A-133 OR SIMILAR AUDITS

If applicable, please provide the date of your most recent A-133 or similar audit, including findings and results of such audits.

Solicitation No. ________________________________________________________

Application/Application No. _____________________________________________

Date of Application/Application __________________________________________

Name of Recipient _____________________________________________________

Typed Name and Title __________________________________________________

__________________________________________________________

Signature _________________________________________ Date _______________

[END OF SECTION D]

# SECTION E - ANNEXES

LIST OF ANNEXES

ANNEX 1.  LIST OF REFERENCE DOCUMENTS

ANNEX 2.  INITIAL ENVIRONMENTAL EXAMINATION

ANNEX 3.  BRANDING STRATEY AND MARKING PLAN

ANNEX 4.  OTHER PROVISIONS

SECTION E – ANNEXES

ANNEX 1 – LIST OF REFERENCE DOCUMENTS

1. Maternal, Child, Reproductive Health and Family Planning Strategic Approach; USAID/Nigeria, September 2008.

http://www.usaid.gov/ng/downloads/hpndraftstrategy%20(pdf,%20111kb).pdf

2. Immunizations Today and Way Forward - Promising Support by USAID/Nigeria; M. Harvey, C. Lee, E. Ogden.  (May 12-24, 2008)

http://www.usaid.gov/ng/downloads/immunizationstoday%20(pdf,%20341kb).pdf

3. An Evaluation of the USAID/Nigeria Social Sector Projects:  ENHANSE and COMPASS; J. Holfeld, et al.  June 2008.

http://www.usaid.gov/ng/downloads/compassenhansevaluation%20(pdf,%20387%20kb).pdf

4.  The Ground is Softening for the USAID/Nigeria Health Portfolio, Considerations for the Present and Future; J. Holfeld, P. MacDonald, January 2007 (Is that date correct)

http://www.usaid.gov/ng/downloads/thegroundisoftening%20(pdf,%20166kb).pdf

5. Broken Promises, Human Rights, Accountability, and Maternal Death in Nigeria; Center for Reproductive Rights. 2008. www.reproductiverights.org/pdf/pub_nigeria2.pdf

6. National Integrated Maternal, Newborn, Child Health Strategy; Government of Nigeria

http://www.who.int/pmnch/countries/sampleplans/en/index.html

SECTION E – ANNEXES

ANNEX 2 – INITIAL ENVIRONMENTAL EXAMINATION

PROGRAM/ACTIVITY DATA:

Program/Activity No.:	Strategic Objective No. 13 (620-006)

Country/Region:		Nigeria

Program/Activity Title:	Increased Use of Social Sector Services

- BACKGROUND AND PROJECT DESCRIPTION

  - Purpose and Scope of IEE

This document provides an environmental examination of all activities of the USAID/Nigeria Strategic Objective (SO)  13, “Increased Use of Social Sector Services,” to be implemented under the Country Strategic Plan 2004 – 2009. This program of activities was previously covered by IEEs 30Nigeria2SO3BasicEducation.doc and  31Nigeria1 FP HIV AIDS Cs.doc]. This IEE replaces all previous IEEs, with the exception of the Pesticide Evaluation Report and Safer Use Action Plan (PERSUAP) IEE for the NetMark program 33Nigeria3_NetMark_PERSUAP.doc, which is incorporated herein by reference.

  - Background

The health and basic education sectors in Nigeria have been particularly hard hit by the twin impacts of rapid population growth and poor economic performance under the military regimes of the 1980s and 1990s.   The results are high child and maternal morbidity and mortality, low levels of adult literacy and poor academic performance, and high fertility that translates into rapid and unsustainable population growth.  Availability and use of affordable child survival and maternal health measures are low.  At least 15 percent of Nigerian children will die before their fifth birthday, while a Nigerian woman dies every three minutes from causes related to pregnancy and childbirth. Adult literacy declined during the decade of the 1990s, and fewer than 60 percent of children are in school. Health and education indicators are much worse in northern Nigeria than in the rest of the country, demonstrating regional imbalance and inequity. The poor quality of education, coupled with lack of access, is trapping successive generations of the poor deeper into poverty.

Key constraints to the use of social sector services in Nigeria include their poor quality and lack of accessibility.  There is also a need to strengthen the policy environment, given the extremely low resource levels allocated to health and education in the Federal budget.

The powerful linkages between health and education indicators argue for the strategic integration of programs in reproductive health and family planning, child survival and basic education where feasible and practical.  Strategic approaches and interventions developed under SO13 will reinforce and help to sustain the conditions for increased use of health and education services by addressing key constraints and challenges.  USAID experience to date suggests that the greatest return on individual investments will occur through targeted activities in health and education at the community level, such that gains in health status reinforce gains in educational achievement and vice versa.

  - Description of Activities

To maximize the impact of limited USG resources, activities under this SOAG will focus on strengthening social sector services in four states (Kano, Lagos, Bauchi, and Nasarawa) and the Federal Capital Territory (FCT).

Some activities, such as social marketing, policy reform and advocacy, and the Polio Eradication Initiative will be conducted on a national scale.  National level activities do not imply working with the Nigerian federal government on an exclusive nor a priority basis.  Rather, activities that support policy and regulatory changes, advocacy and communication will be implemented through a wide range of stakeholders, including the Nigerian federal government, to ensure ownership and sustainable action.

In consultation with Government of Nigeria Health and Education Ministries and agencies, donors, USAID implementing partners, civil society groups, private sector, and other stakeholders, USAID developed a five-year Country Strategic Plan 2004-2009, which responds to the sustainable development needs of Nigeria.  The Strategic Objective 13 (SO 13) Team will collaborate with USAID’s contracting and legal offices to determine the most appropriate type of instruments to implement activities under this Agreement.  In accordance with USAID’s policies on competitive bidding, USAID will encourage competition in the award of contracts, grants and cooperative agreements in order to identify and fund organizations to achieve the Objective.

The following is a list of specific activities to be undertaken to achieve the Objective, together with illustrative activities that may be undertaken to achieve the Objective. The list is neither exhaustive nor definitive and USAID and the Grantee may consider new opportunities based on their potential for advancing the Objective and its related Intermediate Results.

# IR 13.1 	Improved quality of social sector services

This component aims to improve the quality of health (family planning and child survival) and basic education through technical assistance and training.

Illustrative Activities:

- Train health care workers and teachers to enhance their skills in the delivery of quality health and education services;

- Support the development/revision of critical Standards of Practice (SOP) that can be used uniformly by both public and private providers to ensure that all clients receive quality services;

- Support the development and implementation of pre-service and in-service training curriculum that are based on the standards of practice;

- Support the development and implementation of institutional management systems that are based on performance improvement approaches;

- Promote the use of data for decision-making;

- Share best practices in quality assurance methods, approaches and tools.

##### IR 13.2 	Strengthened enabling environment

This component of the SO is to assist the GON to increase its capacity to implement its policy framework.  Two essential elements of this component include capacity building at the federal, state, local government and community levels and modest sector program assistance to support extension and improvement of Education and Health Management Information System (E/HMIS).

Illustrative activities are as follows:

- Support the development of community partnerships and participatory planning;

- Support the development of improved policies and action plans;

- Advocate for greater national, state and LGA resources and use for health and education;

- Develop donor and private sector partnerships to leverage new resources;

- Improve information systems for management, decision-making and advocacy;

- Develop national, state and local capabilities in planning, implementation and evaluation of programs.

IR 13.3	Expanded demand for improved Social Sector Services

This component aims to improve the quality of health and basic education through technical assistance and training.

Illustrative activities:

- Develop and integrate behavior change communication (BCC)for child survival, reproductive health and basic education;

- Undertake operations research to improve understanding of the factors affecting behavior change and expanded demand;

- Expand and strengthen social marketing for selected products and services;

- Scale up successful models of community mobilization for demand expansion.

IR 13.4   Increased access to services, commodities and materials

Specific Activities:

This component aims to increase access to health and basic education services, commodities and materials through technical assistance and training. Activities, however, may include construction/rehabilitation of clinics and schools, provision of wells and sanitation projects.

Illustrative activities:

- Develop initiatives directed to special groups such as girls, adolescents, Islamic schools, orphans and vulnerable children, faith-based organizations, uniformed services, and hard-to-reach populations;

- Strengthen commodity logistics systems;

- Develop cost-recovery systems, including innovative community financing;

- Improve vaccine security.

2.0   COUNTRY AND ENVIRONMENTAL INFORMATION (BASELINE INFORMATION)

(from “Nigeria Environmental Analysis: Final Report,” April 2002, ARD, Inc.)

Nigeria’s natural environmental resources and the quality of its air, water, and soils are severely threatened. Increasing poverty, high population growth and migration, especially into urban areas, and political/institutional constraints are the underlying causes for environmental degradation in the country.

Nigeria is Africa’s most populous nation; one out of every five people living in sub-Saharan Africa lives here. Its population growth rate is above three percent and rural to urban migration is making the country’s cities some of the largest in the world. Although Nigeria receives considerable revenue from its large multinational oil industry sector, this money rarely trickles down to the populace who are generally poor and growing poorer. This combination of expanding population and increasing poverty puts increasingly severe demands upon the natural environment, the institutional structures and the resources available to manage them. The technical capacity to deal with the enormity of the problem is generally weak and the lack of enforcement of (and compliance with) existing regulations make for huge institutional obstacles when trying to effectively tackle environmental issues.

These causes lead to the major threats of unsustainable use of renewable natural resources, unplanned urban development and oil industry operations that confound sound community practices to manage natural resources for their mutual benefit.

Nigeria presently contains considerable biodiversity as well as some very important tracts of fairly undisturbed tropical forests. Its diversity of natural ecosystems ranges from semi-arid savanna to montane forests, rich seasonal floodplain environments, rainforests, vast freshwater swamp forests and diverse coastal vegetation. Nigeria, in the Niger Delta region, contains the largest remaining tract of mangroves in Africa—the third largest in the world. But all of this is threatened.

Most of the land in Nigeria has been converted to agricultural or pastoral uses and agricultural encroachment threatens the natural areas that remain. Desertification, the loss of soil fertility, insufficient quantities and quality of water and enormous erosion problems have followed in the wake of overuse and mismanagement of the country’s resources. Environmental problems that stem from large unplanned urban centers with inadequate solid and municipal waste disposal practices and the impacts of the oil, mining and manufacturing industries are taking their toil on water and air quality in many areas. Add to this the escalating practices of over-fishing, uncontrolled logging, and many other unsustainable uses of the natural resources that remain, and threats to the survival of significant components of Nigeria’s biodiversity is very real. There is, however, still some hope.

Since the return to democracy in 1999, there has been a renewed interest in environmental management and protection. The newly created Federal Ministry of the Environment (FMoE) is pushing an agenda that makes priority issues of gas flaring, marine and coastal resources degradation, desertification, and industrial and urban pollution. The recently formed Niger Delta Development Commission has a transparent mandate and dynamic leadership to help that unique and resource-rich region seek and develop community-based solutions to the social and environmental problems that have been growing for decades. In many states across the country, there are encouraging signs that public leaders, NGOs and community-based organizations (CBOs) are focusing actively on threats to the environment and donors are moving to help implement environmental activities that result in improved livelihoods for the people of Nigeria.

3.0   EVALUATION OF PROJECT/PROGRAM ISSUES WITH RESPECT TO ENVIRONMENTAL IMPACT POTENTIAL

All the activities under IR 13.1, 13.2 and 13.3 and some activities under IR 13.4 involve technical support, capacity building, meetings and workshops and document and information transfer. None of these activities are expected to have direct effects on the environment.

Some activities under IR 13.4 may involve the development of resource centers and building of modest add-on structures to schools and clinics through grants. The size of the structures to be renovated or built will be modest and widely dispersed among the targeted schools and communities. However, the anticipated construction and renovation can be expected to result in limited impacts on the immediate environment of the schools and the communities. For example, the school grounds can be contaminated by construction debris, borrow pits might be created in some areas to make bricks, creating rain-filled holes that become mosquito breeding sites, and the renovation of painted structures has the potential to create toxic dust, if the structure happens to have been painted with lead-containing paint. These and other potential environmental impacts of small construction activities are described in the Small Scale Construction chapter of the Environmental Guidelines for Small Scale Activities in Africa (EGSSAA), which can be downloaded at www.encapafrica.org.

In addition, it is expected that wells and sanitation projects may be a part of activities under IR 13.4. These interventions are likely to affect the environment directly.  The potential environmental impacts of water supply and sanitation projects are identified in the Water Supply and Sanitation chapter of the EGSSAA. For example, these potential impacts include the potential for wells to deliver water containing arsenic or other contaminants and for sanitation projects to become sources of groundwater contamination, if poorly sited.

4.0   RECOMMENDED MITIGATION ACTIONS (INCLUDING MONITORING AND EVALUATION)

All the activities under IR 13.1, 13.2 and 13.3 and some activities under IR 13.4 relating to provision of support, capacity building in education and health, planning, managing and other essential skills,  involve  strictly technical assistance, training and capacity building. A Categorical Exclusion is recommended for this set of activities, pursuant to 22 CFR 216.2 (c)(2)(i) [technical assistance and training].

For any of the activities under IR 13.4 that will involve minor constructions or add-on buildings in schools, as well as the construction of wells and sanitation projects, a Negative Determination with Conditions is recommended for this set of activities, pursuant to (CFR 216.2(c)(2)(i)). The condition being that program managers will take measures to ensure that these activities are conducted in an environmentally sound manner, as described below.

Small Scale Construction

The conditions for the small scale construction activities are the following:

- All construction activities will be conducted following principles for environmentally sound construction, as provided in Chapter 3: Small Scale Construction of the USAID Environmental Guidelines for Small-scale Activities in Africa, which can be found at www.encapafrica.org.

- For the rehabilitation of existing facilities, and for construction of facilities in which the total surface area disturbed is less than 10,000 square feet, the condition is that these activities will be conducted following principles for environmentally sound construction, as provided in the Small Scale Construction chapter of the USAID Environmental Guidelines for Small-scale Activities in Africa, which can be found at: www.encapafrica.org.

- For the construction of any facilities in which the total surface area disturbed exceeds 10,000 square feet (1,000 square meters), the program will conduct a supplemental environmental review according to guidance in Annex G of the Africa Bureau Environmental Procedures Training Manual (EPTM).  Construction may not begin until such a review is completed and approved by the Mission Environmental Officer.

Potable Water Supply and Sanitation

Both water supply and sanitation activities should be conducted in a manner consistent with the good design and implementation practices described in EGSSAA Chapter 16: Water Supply and Sanitation. The SO Team and implementing partners should closely examine this chapter, as it provides a thorough discussion of program design and implementation issues that can help avoid numerous preventable problems. Another useful reference to consult for good water and sanitation design and implementation principles is the document, “Guidelines for the Development of Small Scale Rural Water Supply and Sanitation Projects in Ethiopia,” by Catholic Relief Services and USAID, July 31, 2003.

Water quality testing is essential for determining that the water from a constructed water source is safe to drink and to determine a baseline so that any future degradation can be detected. Among the water quality tests which must be performed are tests for the presence of arsenic. Any USAID-supported activity engaged in the provision of potable water must adhere to Guidance Cable State 98 108651, which requires arsenic testing. That 1998 cable also anticipates “practical guidelines on sampling and testing for arsenic” that were then under development. The EGAT Bureau completed these guidelines, and the Africa Bureau has packaged them in a document titled, “Guidelines for Determining the Arsenic Content of Ground Water in USAID-Sponsored Well Programs in Sub-Saharan Africa.” The SO team must assure that the standards and testing procedures described in this guideline document are followed for potable water supply activities under this program.

As required by ADS 204.5.4, the SO team must actively monitor ongoing activities for compliance with approved IEE recommendations, and modify or end activities that are not in compliance. If additional activities not described in this document are added to this program, then amended or new environmental documentation must be prepared. The SO team will also ensure that provisions of the IEE concerning mitigative measures and the conditions specified herein along with the requirement to monitor be incorporated in all contracts, cooperative agreements, grants and sub-grants.

SECTION E – ANNEXES

ANNEX 3 – BRANDING STRATEGY AND MARKING PLAN

1.  BRANDING STRATEGY – ASSISTANCE (December 2005)

(a) Definitions

Branding Strategy means a strategy that is submitted at the specific request of a USAID Agreement Officer by an Apparently Successful Applicant after evaluation of an application for USAID funding, describing how the program, project, or activity is named and positioned, and how it is promoted and communicated to beneficiaries and host country citizens. It identifies all donors and explains how they will be acknowledged.

Apparently Successful Applicant(s) means the applicant(s) for USAID funding recommended for an award after evaluation, but who has not yet been awarded a grant, cooperative agreement or other assistance award by the Agreement Officer. The Agreement Officer will request that the Apparently Successful Applicants submit a Branding Strategy and Marking Plan. Apparently Successful Applicant status confers no right and constitutes no USAID commitment to an award.

USAID Identity (Identity) means the official marking for the Agency, comprised of the USAID logo and new brandmark, which clearly communicates that our assistance is from the American people. The USAID Identity is available on the USAID website and is provided without royalty, license, or other fee to recipients of USAID-funded grants or cooperative agreements or other assistance awards or subawards.

(b) Submission. The Apparently Successful Applicant, upon request of the Agreement Officer, will submit and negotiate a Branding Strategy. The Branding Strategy will be included in and made a part of the resulting grant or cooperative agreement. The Branding Strategy will be negotiated within the time that the Agreement Officer specifies. Failure to submit and negotiate a Branding Strategy will make the applicant ineligible for award of a grant or cooperative agreement. The Apparently Successful Applicant must include all estimated costs associated with branding and marking USAID programs, such as plaques, stickers, banners, press events and materials, and the like.

(c) Submission Requirements

At a minimum, the Apparently Successful Applicant’s Branding Strategy will address

the following:

(1) Positioning

What is the intended name of this program, project, or activity?

Guidelines: USAID prefers to have the USAID Identity included as part of the program or project name, such as a "title sponsor," if possible and appropriate. It is acceptable to "co-brand" the title with USAID’s and the Apparently Successful Applicant’s identities. For example: "The USAID and [Apparently Successful Applicant] Health Center."

If it would be inappropriate or is not possible to "brand" the project this way, such as when rehabilitating a structure that already exists or if there are multiple donors, please explain and indicate how you intend to showcase USAID's involvement in publicizing the program or project. For example: School #123,

rehabilitated by USAID and [Apparently Successful Applicant]/ [other donors].

Note: the Agency prefers "made possible by (or with) the generous support of the American People" next to the USAID Identity in acknowledging our contribution, instead of the phrase "funded by." USAID prefers local language translations.

Will a program logo be developed and used consistently to identify this program? If yes, please attach a copy of the proposed program logo.

Note: USAID prefers to fund projects that do NOT have a separate logo or identity that competes with the USAID Identity.

(2) Program Communications and Publicity

Who are the primary and secondary audiences for this project or program?

Guidelines: Please include direct beneficiaries and any special target segments or influencers. For Example: Primary audience: schoolgirls age 8-12, Secondary audience: teachers and parents – specifically mothers.

What communications or program materials will be used to explain or market the

program to beneficiaries?

Guidelines: These include training materials, posters, pamphlets, Public Service Announcements, billboards, websites, and so forth.

What is the main program message(s)?

Guidelines: For example: "Be tested for HIV-AIDS" or "Have your child inoculated."

Please indicate if you also plan to incorporate USAID’s primary message – this aid is "from the American people" – into the narrative of program materials. This is optional; however, marking with the USAID Identity is required.

Will the recipient announce and promote publicly this program or project to host country citizens? If yes, what press and promotional activities are planned?

Guidelines: These may include media releases, press conferences, public events, and so forth.

Note: incorporating the message, “USAID from the American People”, and the USAID Identity is required.

Please provide any additional ideas about how to increase awareness that the American people support this project or program.

Guidelines: One of our goals is to ensure that both beneficiaries and host-country citizens know that the aid the Agency is providing is "from the American people." Please provide any initial ideas on how to further this goal.

(3) Acknowledgements

Will there be any direct involvement from a host-country government ministry? If yes, please indicate which one or ones. Will the recipient acknowledge the ministry as an additional co-sponsor?

Note: it is perfectly acceptable and often encouraged for USAID to "co-brand" programs with government ministries.

Please indicate if there are any other groups whose logo or identity the recipient will use on program materials and related communications.

Guidelines: Please indicate if they are also a donor or why they will be visibly acknowledged, and if they will receive the same prominence as USAID.

(d) Award Criteria. The Agreement Officer will review the Branding Strategy for adequacy, ensuring that it contains the required information on naming and positioning the USAID-funded program, project, or activity, and promoting and communicating it to cooperating country beneficiaries and citizens. The Agreement Officer also will evaluate this information to ensure that it is consistent with the stated objectives of the award; with the Apparently Successful Applicant’s cost data submissions; with the Apparently Successful Applicant’s project, activity, or program performance plan; and with the regulatory requirements set out in 22 CFR 226.91. The Agreement Officer may obtain advice and recommendations from technical experts while performing the evaluation.

2.  MARKING PLAN – ASSISTANCE (December 2005)

(a) Definitions

Marking Plan means a plan that the Apparently Successful Applicant submits at the specific request of a USAID Agreement Officer after evaluation of an application for USAID funding, detailing the public communications, commodities, and program materials and other items that will visibly bear the USAID Identity. Recipients may request approval of Presumptive Exceptions to marking requirements in the

Marking Plan.

Apparently Successful Applicant(s) means the applicant(s) for USAID funding recommended for an award after evaluation, but who has not yet been awarded a grant, cooperative agreement or other assistance award by the Agreement Officer. The Agreement Officer will request that Apparently Successful Applicants submit a Branding Strategy and Marking Plan. Apparently Successful Applicant status confers no right and constitutes no USAID commitment to an award, which the Agreement Officer must still obligate.

USAID Identity (Identity) means the official marking for the Agency, comprised of the USAID logo and new brandmark, which clearly communicates that our assistance is from the American people. The USAID Identity is available on the USAID website and USAID provides it without royalty, license, or other fee to recipients of USAID funded grants, cooperative agreements, or other assistance awards or sub-awards.

A Presumptive Exception exempts the applicant from the general marking requirements for a particular USAID-funded public communication, commodity, program material or other deliverable, or a category of USAID-funded public communications, commodities, program materials or other deliverables that would otherwise be required to visibly bear the USAID Identity. The Presumptive Exceptions are:

Presumptive Exception (i). USAID marking requirements may not apply if they would compromise the intrinsic independence or neutrality of a program or materials where independence or neutrality is an inherent aspect of the program and materials, such as election monitoring or ballots, and voter information literature; political party support or public policy advocacy or reform; independent media, such as television and radio broadcasts, newspaper articles and editorials; and public service announcements or public opinion polls and surveys (22 C.F.R. 226.91(h)(1)).

Presumptive Exception (ii). USAID marking requirements may not apply if they would diminish the credibility of audits, reports, analyses, studies, or policy recommendations whose data or findings must be seen as independent (22 C.F.R. 226.91(h)(2)).

Presumptive Exception (iii). USAID marking requirements may not apply if they would undercut host-country government “ownership” of constitutions, laws, regulations, policies, studies, assessments, reports, publications, surveys or audits, public service announcements, or other communications better positioned as “by” or “from” a cooperating country ministry or government official (22 C.F.R. 226.91(h)(3)).

Presumptive Exception (iv). USAID marking requirements may not apply if they would impair the functionality of an item, such as sterilized equipment or spare parts (22 C.F.R. 226.91(h)(4)).

Presumptive Exception (v). USAID marking requirements may not apply if they would incur substantial costs or be impractical, such as items too small or otherwise unsuited for individual marking, such as food in bulk (22 C.F.R. 226.91(h)(5)).

Presumptive Exception (vi). USAID marking requirements may not apply if they would offend local cultural or social norms, or be considered inappropriate on such items as condoms, toilets, bed pans, or similar commodities (22 C.F.R. 226.91(h)(6)).

Presumptive Exception (vii). USAID marking requirements may not apply if they would conflict with international law (22 C.F.R. 226.91(h)(7)).

(b) Submission. The Apparently Successful Applicant, upon the request of the Agreement Officer, will submit and negotiate a Marking Plan that addresses the details of the public communications, commodities, program materials that will visibly bear the USAID Identity. The marking plan will be customized for the particular program, project, or activity under the resultant grant or cooperative agreement. The plan will be included in and made a part of the resulting grant or cooperative agreement. USAID and the Apparently Successful Applicant will negotiate the Marking Plan within the time specified by the Agreement Officer. Failure to submit and negotiate a Marking Plan will make the applicant ineligible for award of a grant or cooperative agreement. The applicant must include an estimate of all costs associated with branding and marking USAID programs, such as plaques, labels, banners, press events, promotional materials, and so forth in the budget portion of its application. These costs are subject to revision and negotiation with the Agreement Officer upon submission of the Marking Plan and will be incorporated into the Total Estimated Amount of the grant, cooperative agreement or other assistance instrument.

(c) Submission Requirements. The Marking Plan will include the following:

(1) A description of the public communications, commodities, and program materials that the recipient will be produced as a part of the grant or cooperative agreement and which will visibly bear the USAID Identity. These include:

(i) program, project, or activity sites funded by USAID, including visible infrastructure projects or other programs, projects, or activities that are physical in nature;

(ii) technical assistance, studies, reports, papers, publications, audio-visual productions, public service announcements, Web sites/Internet activities and other promotional, informational, media, or communications products funded by USAID;

(iii) events financed by USAID, such as training courses, conferences, seminars, exhibitions, fairs, workshops, press conferences, and other public activities; and

(iv) all commodities financed by USAID, including commodities or equipment provided under humanitarian assistance or disaster relief programs, and all other equipment, supplies and other materials funded by USAID, and their export packaging.

(2) A table specifying:

(i) the program deliverables that the recipient will mark with the USAID Identity,

(ii) the type of marking and what materials the applicant will be used to mark the program deliverables with the USAID Identity, and

(iii) when in the performance period the applicant will mark the program deliverables, and where the applicant will place the marking.

(3) A table specifying:

(i) what program deliverables will not be marked with the USAID Identity, and

(ii) the rationale for not marking these program deliverables.

(d) Presumptive Exceptions.

(1) The Apparently Successful Applicant may request a Presumptive Exception as part of the overall Marking Plan submission. To request a Presumptive Exception, the Apparently Successful Applicant must identify which Presumptive Exception applies, and state why, in light of the Apparently Successful Applicant’s technical proposal and in the context of the program description or program statement in the USAID Request For Application or Annual Program Statement, marking requirements should not be required.

(2) Specific guidelines for addressing each Presumptive Exception are:

(i) For Presumptive Exception (i), identify the USAID Strategic Objective, Interim Result, or program goal furthered by an appearance of neutrality, or state why the program, project, activity, commodity, or communication is ‘intrinsically neutral.’ Identify, by category or deliverable item, examples of program materials funded under the award for which you are seeking exception 1.

(ii) For Presumptive Exception (ii), state what data, studies, or other deliverables will be produced under the USAID funded award, and explain why the data, studies, or deliverables must be seen as credible.

(iii) For Presumptive Exception (iii), identify the item or media product produced under the USAID funded award, and explain why each item or product, or category of item and product, is better positioned as an item or product produced by the cooperating country government.

(iv) For Presumptive Exception (iv), identify the item or commodity to be marked, or categories of items or commodities, and explain how marking would impair the item’s or commodity’s functionality.

(v) For Presumptive Exception (v), explain why marking would not be cost-beneficial or practical.

(vi) For Presumptive Exception (vi), identify the relevant cultural or social norm, and explain why marking would violate that norm or otherwise be inappropriate.

(vii) For Presumptive Exception (vii), identify the applicable international law violated by marking.

(3) The Agreement Officer will review the request for adequacy and reasonableness. In consultation with the Cognizant Technical Officer and other agency personnel as necessary, the Agreement Officer will approve or disapprove the requested Presumptive Exception. Approved exceptions will be made part of the approved Marking Plan, and will apply for the term of the award, unless provided otherwise.

(e) Award Criteria: The Agreement Officer will review the Marking Plan for adequacy and reasonableness, ensuring that it contains sufficient detail and information concerning public communications, commodities, and program materials that will visibly bear the USAID Identity. The Agreement Officer will evaluate the plan to ensure that it is consistent with the stated objectives of the award; with the applicant’s cost data submissions; with the applicant’s actual project, activity, or program performance plan; and with the regulatory requirements of 22 C.F.R.226.91. The Agreement Officer will approve or disapprove any requested Presumptive Exceptions (see paragraph (d)) on the basis of adequacy and reasonableness. The Agreement Officer may obtain advice and recommendations from technical experts while performing the evaluation.

3.  MARKING UNDER USAID-FUNDED ASSISTANCE INSTRUMENTS (December 2005)

(a) Definitions

Commodities mean any material, article, supply, goods or equipment, excluding recipient offices, vehicles, and non-deliverable items for recipient’s internal use, in administration of the USAID funded grant, cooperative agreement, or other agreement or subagreement.

Principal Officer means the most senior officer in a USAID Operating Unit in the field, e.g., USAID Mission Director or USAID Representative. For global programs managed from Washington but executed across many countries, such as disaster relief and assistance to internally displaced persons, humanitarian emergencies or immediate post conflict and political crisis response, the cognizant Principal Officer may be an Office Director, for example, the Directors of USAID/W/Office of Foreign Disaster Assistance and Office of Transition Initiatives. For non-presence countries, the cognizant Principal Officer is the Senior USAID officer in a regional USAID Operating Unit responsible for the non-presence country, or in the

absence of such a responsible operating unit, the Principal U.S Diplomatic Officer in the non-presence country exercising delegated authority from USAID.

Programs mean an organized set of activities and allocation of resources directed toward a common purpose, objective, or goal undertaken or proposed by an organization to carry out the responsibilities assigned to it.

Projects include all the marginal costs of inputs (including the proposed investment) technically required to produce a discrete marketable output or a desired result (for example, services from a fully functional water/sewage treatment facility).

Public communications are documents and messages intended for distribution to audiences external to the recipient’s organization. They include, but are not limited to, correspondence, publications, studies, reports, audio visual productions, and other informational products; applications, forms, press and

promotional materials used in connection with USAID funded programs, projects or activities, including signage and plaques; Web sites/Internet activities; and events such as training courses, conferences, seminars, press conferences and so forth.

Sub-recipient means any person or government (including cooperating country government) department, agency, establishment, or for profit or nonprofit organization that receives a USAID sub-award, as defined in 22 C.F.R. 226.2.

Technical Assistance means the provision of funds, goods, services, or other foreign assistance, such as loan guarantees or food for work, to developing countries and other USAID recipients, and through such recipients to sub-recipients, in direct support of a development objective – as opposed to the internal management of the foreign assistance program.

USAID Identity (Identity) means the official marking for the United States Agency for International Development (USAID), comprised of the USAID logo or seal and new brandmark, with the tagline that clearly communicates that our assistance is “from the American people.” The USAID Identity is available on the USAID website at www.usaid.gov/branding and USAID provides it without royalty, license, or other fee to recipients of USAID-funded grants, or cooperative agreements, or other assistance awards.

(b) Marking of Program Deliverables

(1) All recipients must mark appropriately all overseas programs, projects, activities, public communications, and commodities partially or fully funded by a USAID grant or cooperative agreement or other assistance award or subaward with the USAID Identity, of a size and prominence equivalent to or greater than the recipient’s, other donor’s, or any other third party’s identity or logo.

(2) The Recipient will mark all program, project, or activity sites funded by USAID, including visible infrastructure projects (for example, roads, bridges, buildings) or other programs, projects, or activities that are physical in nature (for example, agriculture, forestry, water management) with the USAID Identity. The Recipient should erect temporary signs or plaques early in the construction or implementation phase. When construction or implementation is complete, the Recipient must install a permanent, durable sign, plaque or other marking.

(3) The Recipient will mark technical assistance, studies, reports, papers, publications, audio-visual productions, public service announcements, Web sites/Internet activities and other promotional, informational, media, or communications products funded by USAID with the USAID Identity.

(4) The Recipient will appropriately mark events financed by USAID, such as training courses, conferences, seminars, exhibitions, fairs, workshops, press conferences and other public activities, with the USAID Identity. Unless directly prohibited and as appropriate to the surroundings, recipients should display additional materials, such as signs and banners, with the USAID Identity. In circumstances in which the USAID Identity cannot be displayed visually, the recipient is encouraged otherwise to acknowledge USAID and the American people’s support.

(5) The Recipient will mark all commodities financed by USAID, including commodities or equipment provided under humanitarian assistance or disaster relief programs, and all other equipment, supplies, and other materials funded by USAID, and their export packaging with the USAID Identity.

(6) The Agreement Officer may require the USAID Identity to be larger and more prominent if it is the majority donor, or to require that a cooperating country government’s identity be larger and more prominent if circumstances warrant, and as appropriate depending on the audience, program goals, and materials produced.

(7) The Agreement Officer may require marking with the USAID Identity in the event that the recipient does not choose to mark with its own identity or logo.

(8) The Agreement Officer may require a pre-production review of USAID-funded public communications and program materials for compliance with the approved Marking Plan.

(9) Sub-recipients. To ensure that the marking requirements “flow down'' to sub-recipients of sub-awards, recipients of USAID funded grants and cooperative agreements or other assistance awards will include the USAID-approved marking provision in any USAID funded sub-award, as follows:

“As a condition of receipt of this sub-award, marking with the USAID Identity of size and prominence equivalent to or greater than the recipient’s, sub-recipient’s, other donor’s or third party’s is required. In the event the recipient chooses not to require marking with its own identity or logo by the sub-recipient, USAID may, at its discretion, require marking by the sub-recipient with the USAID Identity.”

(10) Any ‘public communications’, as defined in 22 C.F.R. 226.2, funded by USAID, in which the content has not been approved by USAID, must contain the following disclaimer:

“This study/report/audio/visual/other information/media product (specify) is made possible by the generous support of the American people through the United States Agency for International Development (USAID). The contents are the responsibility of [insert recipient name] and do not necessarily reflect the views of USAID or the United States Government.”

(11) The recipient will provide the Cognizant Technical Officer (CTO) or other USAID personnel designated in the grant or cooperative agreement with two copies of all program and communications materials produced under the award. In addition, the recipient will submit one electronic or one hard copy of all final documents to USAID’s Development Experience Clearinghouse.

(c) Implementation of marking requirements.

(1) When the grant or cooperative agreement contains an approved Marking Plan, the recipient will implement the requirements of this provision following the approved Marking Plan.

(2) When the grant or cooperative agreement does not contain an approved Marking Plan, the recipient will propose and submit a plan for implementing the requirements of this provision within [Agreement Officer fill-in] days after the effective date of this provision. The plan will include:

(i) A description of the program deliverables specified in paragraph (b) of this provision that the recipient will produce as a part of the grant or cooperative agreement and which will visibly bear the USAID Identity.

(ii) the type of marking and what materials the applicant uses to mark the program deliverables with the USAID Identity,

(iii) when in the performance period the applicant will mark the program deliverables, and where the applicant will place the marking,

(3) The recipient may request program deliverables not be marked with the USAID Identity by identifying the program deliverables and providing a rationale for not marking these program deliverables. Program deliverables may be exempted from USAID marking requirements when:

(i) USAID marking requirements would compromise the intrinsic independence or neutrality of a program or materials where independence or neutrality is an inherent aspect of the program and materials;

(ii) USAID marking requirements would diminish the credibility of audits, reports, analyses, studies, or policy recommendations whose data or findings must be seen as independent;

(iii) USAID marking requirements would undercut host-country government “ownership” of constitutions, laws, regulations, policies, studies, assessments, reports, publications, surveys or audits, public service announcements, or other communications better positioned as “by” or “from” a cooperating country ministry or government official;

(iv) USAID marking requirements would impair the functionality of an item;

(v) USAID marking requirements would incur substantial costs or be impractical;

(vi) USAID marking requirements would offend local cultural or social norms, or be considered inappropriate;

(vii) USAID marking requirements would conflict with international law.

(4) The proposed plan for implementing the requirements of this provision, including any proposed exemptions, will be negotiated within the time specified by the Agreement Officer after receipt of the proposed plan. Failure to negotiate an approved plan with the time specified by the Agreement Officer may be considered as noncompliance with the requirements is provision.

(d) Waivers.

(1) The recipient may request a waiver of the Marking Plan or of the marking requirements of this provision, in whole or in part, for each program, project, activity, public communication or commodity, or, in exceptional circumstances, for a region or country, when USAID required marking would pose compelling political, safety, or security concerns, or when marking would have an adverse impact in the cooperating country. The recipient will submit the request through the Cognizant Technical Officer. The Principal Officer is responsible for approvals or disapprovals of waiver requests.

(2) The request will describe the compelling political, safety, security concerns, or adverse impact that require a waiver, detail the circumstances and rationale for the waiver, detail the specific requirements to be waived, the specific portion of the Marking Plan to be waived, or specific marking to be waived, and include a description of how program materials will be marked (if at all) if the USAID Identity is removed. The request should also provide a rationale for any use of recipient’s own identity/logo or that of a third party on materials that will be subject to the waiver.

(3) Approved waivers are not limited in duration but are subject to Principal Officer Review at any time, due to changed circumstances.

(4) Approved waivers “flow down” to recipients of sub-awards unless specified otherwise. The waiver may also include the removal of USAID markings already affixed, if circumstances warrant.

(5) Determinations regarding waiver requests are subject to appeal to the Principal Officer’s cognizant Assistant Administrator. The recipient may appeal by submitting a written request to reconsider the Principal Officer’s waiver determination to the cognizant Assistant Administrator.

(e) Non-retroactivity. The requirements of this provision do apply to any materials, events, or commodities produced prior to January 2, 2006. The requirements of this provision do not apply to program, project, or activity sites funded by USAID, including visible infrastructure projects (for example, roads, bridges, buildings) or other programs, projects, or activities that are physical in nature (for example, agriculture, forestry, water management) where the construction and implementation of these are complete prior to January 2, 2006 and the period of the grant does not extend past January 2, 2006.

SECTION E – ANNEXES

ANNEX 4 – OTHER PROVISIONS

1. 	APPLICABILITY OF 22 CFR PART 226 (May 2005)

(a) All provisions of 22 CFR Part 226 and all Standard Provisions attached to this agreement are applicable to the recipient and to subrecipients which meet the definition of "Recipient" in Part 226, unless a section specifically excludes a subrecipient from coverage. The recipient shall assure that subrecipients have copies of all the attached standard provisions.

(b) For any subawards made with Non-US subrecipients the Recipient shall include the applicable "Standard Provisions for Non-US Nongovernmental Grantees." Recipients are required to ensure compliance with subrecipient monitoring procedures in accordance with OMB Circular A-133.

2.	“USAID DISABILITY POLICY - ASSISTANCE (December 2004)

(a) The objectives of the USAID Disability Policy are (1) to enhance the attainment of United States foreign assistance program goals by promoting the participation and equalization of opportunities of individuals with disabilities in USAID policy, country and sector strategies, activity designs and implementation; (2) to increase awareness of issues of people with disabilities both within USAID programs and in host countries; (3) to engage other U.S. government agencies, host country counterparts, governments, implementing organizations and other donors in fostering a climate of nondiscrimination against people with disabilities; and (4) to support  international advocacy for people with disabilities. The full text of the policy paper can be found at the following website: http://www.usaid.gov/about/disability/DISABPOL.FIN.html.

(b) USAID therefore requires that the recipient not discriminate against people with disabilities in the implementation of USAID funded programs and that it make every effort to comply with the objectives of the USAID Disability Policy in performing the program under this grant or cooperative agreement. To that end and to the extent it can accomplish this goal within the scope of the program objectives, the recipient should demonstrate a comprehensive and consistent approach for including men, women and children with disabilities.”

3.	“PROHIBITION ON THE USE OF FEDERAL FUNDS TO PROMOTE, SUPPORT, OR ADVOCATE FOR THE LEGALIZATION OR PRACTICE OF PROSTITUTION - ASSISTANCE (JULY 2004)

(a) The U.S. Government is opposed to prostitution and related activities, which are inherently harmful and dehumanizing, and contribute to the phenomenon of trafficking in persons. None of the funds made available under this agreement may be used to promote, support, or advocate the legalization or practice of prostitution. Nothing in the preceding sentence shall be construed to preclude assistance designed to ameliorate the suffering of, or health risks to, victims while they are being trafficked or after they are out of the situation that resulted from such victims being trafficked.

(b) [This subsection (b) only applies to foreign non-governmental organizations and PIOs receiving U.S. Government funds to carry out programs that target victims of severe forms of trafficking as either prime awardees or subawardees.]

(1) For programs that target victims of severe forms of trafficking, as a condition of entering into this agreement or subagreement, the recipient/subrecipient agrees that in its activities outside of the United States and its possessions it does not promote, support, or advocate the legalization or practice of prostitution. The preceding sentence shall not apply to organizations that provide services to individuals solely after they are no longer engaged in activities that resulted from such victims being trafficked.

(2) The following definitions apply for purposes of this clause:

FOREIGN NON-GOVERNMENTAL ORGANIZATION – The term “foreign non-governmental organization” means an entity that is not organized under the laws of any State of the United States, the District of Columbia or the Commonwealth of Puerto Rico.

SEVERE FORMS OF TRAFFICKING IN PERSONS. -- The term ‘‘severe forms of trafficking in persons’’ means—

(A) sex trafficking in which a commercial sex act is induced by force, fraud, or coercion, or in which the person induced to perform such act has not attained 18 years of age; or

(B) the recruitment, harboring, transportation, provision, or obtaining of a person for labor or services, through the use of force, fraud, or coercion for the purpose of subjection to involuntary servitude, peonage, debt

bondage, or slavery.

(c) The recipient shall insert this provision in all sub-agreements under this award.

(d) This provision includes express terms and conditions of the agreement and any violation of it shall be grounds for unilateral termination, in whole or in part, of the agreement by USAID prior to the end of its term.”

4.	DEBARMENT, SUSPENSION, AND OTHER RESPONSIBILITY MATTERS (JANUARY 2004)

(1) The recipient agrees to notify the Agreement Officer immediately upon learning that it or any of its principals:

(a) Are presently excluded or disqualified from covered transactions by any Federal department or agency;

(b) Have been convicted within the preceding three-years period preceding this proposal been convicted of or had a civil judgment rendered against them for commission of fraud or a criminal offense in connection with obtaining, attempting to obtain, or performing a public (Federal, State, or local) transaction or contract under a public transaction; violation of Federal or State antitrust statutes or commission of embezzlement, theft, forgery, bribery, falsification or destruction of records, making false statements, tax evasion, receiving stolen property, making false claims, or obstruction of justice; commission of any other offense indicating a lack of business integrity or business honesty that seriously and directly affects your present responsibility;

(c) Are presently indicted for or otherwise criminally or civilly charged by a governmental entity (Federal, State, or local) with commission of any of the offenses enumerated in paragraph (1)(b); and

(d) Have had one or more public transactions (Federal, State, or local) terminated for cause or default within the preceding three years.

(2) The recipient agrees that, unless authorized by the Agreement Officer, it will not knowingly enter into any subagreements or contracts under this grant with a person or entity that is included on the Excluded Parties List System (http://epls.arnet.gov). The recipient further agrees to include the following provision in any  subagreements or contracts entered into under this award:

DEBARMENT, SUSPENSION, INELIGIBILITY, AND VOLUNTARY EXCLUSION

(DECEMBER 2003)

The recipient/contractor certifies that neither it nor its principals is presently excluded or disqualified from participation in this transaction by any Federal department or agency.

(3) The policies and procedures applicable to debarment, suspension, and ineligibility under USAID-financed transactions are set forth in 22 CFR Part 208.

5.	DRUG-FREE WORKPLACE (JANUARY 2004)

(1) The recipient agrees that it will publish a drug-free workplace statement and provide a copy to each employee who will be engaged in the performance of any Federal award. The statement must

(a) Tell the employees that the unlawful manufacture, distribution, dispensing, possession, or use of a controlled substance is prohibited in its workplace;

(b) Specify the actions the recipient will take against employees for violating that prohibition; and

(c) Let each employee know that, as a condition of employment under any award, he or she

(1) Must abide by the terms of the statement, and

(2) Must notify you in writing if he or she is convicted for a violation of a criminal drug statute occurring in the workplace, and must do so no more than five calendar days after the conviction.

(2) The recipient agrees that it will establish an ongoing drug-free awareness program to inform employees about

(a) The dangers of drug abuse in the workplace;

(b) Your policy of maintaining a drug-free workplace;

(c) Any available drug counseling, rehabilitation and employee assistance programs; and

(d) The penalties that you may impose upon them for drug abuse violations occurring in the workplace.

(3) 	Without the Agreement Officer’s expressed written approval, the policy statement and program must be in place as soon as possible, no later than the 30 days after the effective date of this award, or the completion date of this award, whichever occurs first.

(4) 	The recipient agrees to immediately notify the Agreement Officer if an employee is convicted of a drug violation in the workplace. The notification must be in writing, identify the employee’s position title, the number of each award on which the employee worked. The notification must be sent to the Agreement Officer within ten calendar days after the recipient learns of the conviction.

(5) 	Within 30 calendar days of learning about an employee’s conviction, the recipient must either

(a) 	Take appropriate personnel action against the employee, up to and including termination, consistent with the requirements of the Rehabilitation Act of 1973 (29 USC 794), as amended, or

(b) 	Require the employee to participate satisfactorily in a drug abuse assistance or rehabilitation program approved for these purposes by a Federal, State or local health, law enforcement, or other appropriate agency.

(6) 	The policies and procedures applicable to violations of these requirements are set forth in 22 CFR Part 210.

6. 	EXECUTIVE ORDER ON TERRORISM FINANCING (FEB 2002)

The recipient is reminded that U.S. Executive Orders and U.S. law prohibits transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism.  It is the responsibility of the recipient to ensure compliance with these Executive Orders and laws.  This provision must be included in all subcontracts/sub awards under this agreement.

7.	VOLUNTARY POPULATION PLANNING ACTIVITIES - SUPPLEMENTAL

REQUIREMENTS (JANUARY 2009)

a. 	Voluntary Participation and Family Planning Methods:

(1)	The recipient agrees to take any steps necessary to ensure that funds made available under this award will not be used to coerce any individual to practice methods of family planning inconsistent with such individual's moral, philosophical, or religious beliefs. Further, the recipient agrees to conduct its activities in a manner which safeguards the rights, health and welfare of all individuals who take part in the program.

(2)	Activities which provide family planning services or information to individuals, financed in whole or in part under this agreement, shall provide a broad range of family planning methods and services available in the country in which the activity is conducted or shall provide information to such individuals regarding where such methods and services may be obtained.

b. 	Requirements for Voluntary Family Planning Projects

(1) 	A Family planning project must comply with the requirements of this

paragraph.

(2) 	A project is a discrete activity through which a governmental or nongovernmental organization or public international organization provides family planning services to people and for which funds obligated under this award, or goods or services financed with such funds, are provided under this award, except funds solely for the participation of personnel in short-term, widely attended training conferences or programs.

(3) 	Service providers and referral agents in the project shall not implement or be subject to quotas or other numerical targets of total number of births, number of family planning acceptors, or acceptors of a particular method of family planning. Quantitative estimates or indicators of the number of births, acceptors, and acceptors of a particular method that are used for the purpose of budgeting, planning, or reporting with respect to the project are not quotas or targets under this paragraph, unless service providers or referral agents in the project are required to achieve the estimates or indicators.

(4)	The project shall not include the payment of incentives, bribes, gratuities or financial rewards to (i) any individual in exchange for becoming a family planning acceptor or (ii) any personnel performing functions under the project for achieving a numerical quota or target of total number of births, number of family planning acceptors, or acceptors of a particular method of contraception. This restriction applies to salaries or payments paid or made to personnel performing functions under the project if the amount of the salary or payment increases or decreases based on a predetermined number of births, number of family planning acceptors, or number of acceptors of a particular method of contraception that the personnel affect or achieve.

(5)	No person shall be denied any right or benefit, including the right of access to participate in any program of general welfare or health care, based on the person's decision not to accept family planning services offered by the project.

(6) 	The project shall provide family planning acceptors comprehensible information about the health benefits and risks of the method chosen, including those conditions that might render the use of the method inadvisable and those adverse side effects known to be consequent to the use of the method. This requirement may be satisfied by providing information in accordance with the medical practices and standards and health conditions in the country where the project is conducted through counseling, brochures, posters, or package inserts.

(7) 	The project shall ensure that experimental contraceptive drugs and devices and medical procedures are provided only in the context of a scientific study in which participants are advised of potential risks and benefits.

(8) 	With respect to projects for which USAID provides, or finances the contribution of, contraceptive commodities or technical services and for which there is no subaward or contract under this award, the organization implementing a project for which such assistance is provided shall agree that the project will comply with the requirements of this paragraph while using such commodities or receiving such services.

(9)

i) 	The recipient shall notify USAID when it learns about an alleged violation in a project of the requirements of subparagraphs (3), (4), (5) or (7) of this paragraph;

ii)	the recipient shall investigate and take appropriate corrective action, if necessary, when it learns about an alleged violation in a project of subparagraph (6) of this paragraph and shall notify USAID about violations in a project affecting a number of people over a period of time that indicate there is a systemic problem in the project.

iii)	The recipient shall provide USAID such additional information about violations as USAID may request.

c. 	Additional Requirements for Voluntary Sterilization Programs

(1)	None of the funds made available under this award shall be used to pay for the performance of involuntary sterilization as a method of family planning or to coerce or provide any financial incentive to any individual to practice sterilization.

(2)	The recipient shall ensure that any surgical sterilization procedures supported in whole or in part by funds from this award are performed only after the individual has voluntarily appeared at the treatment facility and has given informed consent to the sterilization procedure. Informed consent means the voluntary, knowing assent from the individual after being advised of the surgical procedures to be followed, the attendant discomforts and risks, the benefits to be expected, the availability of alternative methods of family planning, the purpose of the operation and its irreversibility, and the option to withdraw consent anytime prior to the operation. An individual's consent is considered voluntary if it is based upon the exercise of free choice and is not obtained by any special inducement or any element of force, fraud, deceit, duress, or other forms of coercion or misrepresentation.

(3)	Further, the recipient shall document the patient's informed consent by (i) a written consent document in a language the patient understands and speaks, which explains the basic elements of informed consent, as set out above, and which is signed by the individual and by the attending physician or by the authorized assistant of the attending physician; or (ii) when a patient is unable to read adequately a written certification by the attending physician or by the authorized assistant of the attending physician that the basic elements of informed consent above were orally presented to the patient, and that the patient thereafter consented to the performance of the operation. The receipt of this oral explanation shall be acknowledged by the patient's mark on the certification and by the signature or mark of a witness who shall speak the same language as the patient.

(4)	The recipient must retain copies of informed consent forms and certification documents for each voluntary sterilization procedure for a period of three years after performance of the sterilization procedure.

d.	Prohibition on Abortion-Related Activities:

(1)  	No funds made available under this award will be used to finance, support,

or be attributed to the following activities: (i) procurement or distribution of equipment intended to be used for the purpose of inducing abortions as a method of family planning; (ii) special fees or incentives to any person to coerce or motivate them to have abortions; (iii) payments to persons to perform abortions or to solicit persons to undergo abortions; (iv) information, education, training, or communication programs that seek to promote abortion as a method of family planning; and (v) lobbying for or against abortion. The term "motivate", as it relates to family planning assistance, shall not be construed to prohibit the provision, consistent with local law, of information or counseling about all pregnancy options.

(2)	No funds made available under this award will be used to pay for any biomedical research which relates, in whole or in part, to methods of, or the performance of, abortions or involuntary sterilizations as a means of family planning. Epidemiologic or descriptive research to assess the incidence, extent or consequences of abortions is not precluded.

e.	The recipient shall insert this provision in all subsequent subagreements and contracts involving family planning or population activities that will be supported in whole or in part from funds under this award. The term subagreement means subgrants and subcooperative agreements.

8.	FOREIGN GOVERNMENT DELEGATIONS TO INTERNATIONAL CONFERENCES (JAN 2002)

Funds in this agreement may not be used to finance the travel, per diem, hotel expenses, meals, conferences fees or other conference cots for any member of a government’s delegation to an international conference sponsored by a public international organizations, except as provided in the ADS Mandatory Reference “Guidance on Funding Foreign Government Delegations to International Conferences” or as approved by the Agreement Officer.

9. REGULATIONS GOVERNING EMPLOYEES (AUGUST 1992)

(The following applies to the recipient's employees working in the cooperating country under the agreement who are not citizens of the cooperating country.)

a. The recipient's employees shall maintain private status and may not rely on local U.S. Government offices or facilities for support while under this grant.

b. The sale of personal property or automobiles by recipient employees and their dependents in the foreign country to which they are assigned shall be subject to the same limitations and prohibitions which apply to direct-hire USAID personnel employed by the Mission, including the rules contained in 22 CFR Part 136, except as this may conflict with host government regulations.

c. Other than work to be performed under this award for which an employee is assigned by the recipient, no employee of the recipient shall engage directly or indirectly, either in the individual's own name or in the name or through an agency of another person, in any business, profession, or occupation in the foreign countries to which the individual is assigned, nor shall the individual make loans or investments to or in any business, profession or occupation in the foreign countries to which the individual is assigned.

*An asterisk indicates that the adjacent information is new or substantively revised.

d. The recipient's employees, while in a foreign country, are expected to show respect for its conventions, customs, and institutions, to abide by its applicable laws and regulations, and not to interfere in its internal political affairs.

e. In the event the conduct of any recipient employee is not in accordance with the preceding paragraphs, the recipient's chief of party shall consult with the USAID Mission Director and the employee involved and shall recommend to the recipient a course of action with regard to such employee.

f. The parties recognize the rights of the U.S. Ambassador to direct the removal from a country of any U.S. citizen or the discharge from this grant award of any third country national when, in the discretion of the Ambassador, the interests of the United States so require.

g. If it is determined, either under (e) or (f) above, that the services of such employee should be terminated, the recipient shall use its best efforts to cause the return of such employee to the United States, or point of origin, as appropriate.

10.	PROHIBITION OF ASSISTANCE TO DRUG TRAFFICKERS (JUNE 1999)

a. USAID reserves the right to terminate assistance to, or take other appropriate measures with respect to, any participant approved by USAID who is found to have been convicted of a narcotics offense or to have been engaged in drug trafficking as defined in 22 CFR Part 140.

b. (1) For any loan over $1000 made under this agreement, the recipient shall insert a clause in the loan agreement stating that the loan is subject to immediate cancellation, acceleration, recall or refund by the recipient if the borrower or a key individual of a borrower is found to have been convicted of a narcotics offense or to have been engaged in drug trafficking as defined in 22 CFR Part 140.

(2) Upon notice by USAID of a determination under section (1) and at USAID's option, the recipient agrees to immediately cancel, accelerate or recall the loan, including refund in full of the outstanding balance. USAID reserves the right to have the loan refund returned to USAID.

c. (1) The recipient agrees not to disburse, or sign documents committing the recipient to disburse, funds to a subrecipient designated by USAID ("Designated Subrecipient") until advised by USAID that: (i) any United States Government review of the Designated Subrecipient and its key individuals has been completed; (ii) any related certifications have been obtained; and (iii) the assistance to the Designated Subrecipient has been approved. Designation means that the subrecipient has been unilaterally selected by USAID as the subrecipient. USAID approval of a subrecipient, selected by another party, or joint selection by USAID and another party is not designation.

(2) The recipient shall insert the following clause, or its substance, in its agreement with the Designated Subrecipient:

“The recipient reserves the right to terminate this [Agreement/Contract] or take other appropriate measures if the [Subrecipient] or a key individual of the [Subrecipient] is found to have been convicted of a narcotic offense or to have been engaged in drug trafficking as defined in 22 CFR Part 140.”

[END OF SECTION E]

2008 State of the World’s Mothers, Save the Children, 2008

A percentage of the total level of effort for the project is shown for each Sub-objective.  This is to reinforce earlier discussions that USAID/Nigeria considers the relative level of importance and level of effort needed to achieve results under each sub-objective.