September 6, 2007

EA4-07-012

TO:		EA3/Trent Martin

Alpha Magnetic Spectrometer (AMS) Project Manager

FROM:	EA4/Michelle Rucker

SUBJECT:	Technical Authority Report of AMS Integration Review

Thank you for the opportunity to participate in the Alpha Magnetic Spectrometer Integration Review held in Geneva, Switzerland on July 26-27.  Attached is a summary report of my observations from a Technical Authority point of view.  Please feel free to contact me at 281-244-5569 if you have any questions.

Original initialed by

Michelle Rucker

cc:

EA2/L. Bromley

EA3/S. Porter

EA4/I. Kaye

EA4/J. McManamen

EA4/C. Hansen

NT/W. Bostick

Executive Summary

The Alpha Magnetic Spectrometer (AMS) project conducted a technical interchange meeting and Integration Review in Geneva, Switzerland on July 23-27, 2007.  A Technical Authority review was conducted by assessing AMS integration processes, procedures, and plans with respect to a select set of technical standards.  Due to time and resource limitations a more comprehensive assessment with respect to discipline-specific technical standards was not possible; it is assumed that adherence to discipline-specific standards was adequately assessed at prior design reviews.

Although JPR 8080.5 is not strictly applicable to AMS, the payload appears to comply with most of the design and procedural standards.  Several specific suggestions are provided to ensure project success.

Extent of NPR 7120.5D applicability is unclear; applicability should be verified with the process owner. It is also recommended that all AMS Deviation/Waivers be coordinated with the Technical Authority, in accordance with both NPR 7120.5 and JSC 63722.

Extent of NPR 7123.1A applicability is unclear; applicability should be verified with the process owner.  It is recommended that AMS document project acceptance of risks associated with beginning payload assembly without a comprehensive end-to-end integration review.  To mitigate those risks, it is recommended that partial integration reviews be conducted prior to each individual subsystem integration; this would lower the risk of assembly error and costly rework.

1.  Background

The Alpha Magnetic Spectrometer (AMS) payload is a state-of-the-art particle physics detector containing a large, cryogenic superfluid helium, superconducting magnet. The AMS payload will use the unique environment of space to search for cosmic sources of antimatter, dark matter, and dark energy.  The AMS project is a collaboration of 17 nations, with contributions from over 50 individual educational institutions and industry partners.

The AMS project conducted a technical interchange meeting and Integration Review in Geneva, Switzerland on July 23-27, 2007.

The NASA Johnson Space Center’s (JSC) Engineering Directorate provided a Technical Authority representative to the AMS Integration Review, as authorized per JSC 63722.

2.  Assumptions

The following assumptions were used in preparing this report:

- Scope of this Technical Authority review is limited to integration of the various subsystems together into a single payload

  - Internal integration within each subsystem is the responsibility of the subsystem providers, and is out of scope for the NASA Technical Authority;

  - Technical Authority for integration of the payload to the Shuttle and Space Station programs will be provided by those Program’s Chief Engineers;

- Prior design reviews have assessed the AMS design and determined that technical requirements are adequate to meet the payload’s intended scientific purpose

  - Adherence to discipline-specific standards (welding, soldering, etc.) was assessed by discipline experts at prior design reviews;

- The AMS is classified as a non-NASA payload

  - Therefore many Government Furnished Property (GFP) requirements are not strictly applicable;

3.  References and Definitions

3.1   Reference Documents

EA-WI-023	Project Management of Government Furnished Equipment Flight Projects

JSC 63722		JSC Engineering Technical Excellence and Technical Authority Implementation Plan

JSC 27296	Project Plan for the Alpha Magnetic Spectrometer (AMS)

JPR 8080.5	JSC Design and Procedural Standards

NPR 7120.5	NASA Program and Project Management Processes and Requirements

NPR 7123.1	NASA Systems Engineering Processes and Requirements

3.2   Definitions

Technical Authority – is the authority delegated by the Administrator to the heads of NASA offices and/or functions that are responsible and accountable for supporting the Agency’s programmatic functions.  Technical authorities are the “official voices” of their functional areas; they are the Agency’s subject matter experts and monitor who set, modify, oversee, and ensure conformance to technical requirements. Technical Authorities are independent of programs and projects organizationally and financially

Chief Engineer – subject matter expert in a specific discipline or system or related family of systems who executes the Technical Authority for the assigned program or project

4.  Approach

This Technical Authority review was conducted by assessing AMS integration processes, procedures, and plans with respect to a select set of high-level standards and processes.

5.  Compliance with JPR 8080.5

5.1	JPR 8080.5 Applicability

Although JSC 27296, 	Project Plan for the Alpha Magnetic Spectrometer, does not specifically cite JPR 8080.5 as an applicable document, it does cite EA-WI-023, which in turn cites JPR 8080.5 as applicable.  However, it should be noted that JPR 8080.5 guidelines are specifically intended for human spacecraft design; because the AMS is a payload--not a spacecraft--the recommendations in Section 5.3 below should be considered prudent technical steps to enhance project success, rather than strict requirements.

5.2	Observations

In general, AMS appears to comply with the intent of most JPR 8080.5 Revision A design and procedural standards.  AMS team members answered questions and provided requested information on general processes and procedures, as well as fluid and electrical systems design and handling.

5.3	Recommendations with respect to JPR 8080.5

    - Obtain JSC Materials & Processes concurrence on mitigation steps (conformal coating) taken for electrical components with pure tin internal plating.

Rationale: refer to JPR 8080.5 Standard E-7.

    - Verify that warm helium fittings are unique or clocked such that other fluids cannot be accidentally introduced.

Rational: refer to JPR 8080.5 Standard F-3.

    - Verify adequate strain relief, support, and chafing protection for plumbing and cable runs between subsystems to account for design loads, deflections, and thermal expansions/contractions. Analysis should take into account operational scenarios involving possible temperature differentials across the payload as fluids are moved or vented, and account for shims, brackets, and straps.

Rationale: refer to JPR 8080.5 Standards E-25, F-16 and G-25.

    - Communicate to collaboration hardware providers that caps/bags on tubing should meet flight cleanliness specifications.  Use of plastic push-on caps which can generate particulate should be discouraged.

Rationale: Refer to JPR 8080.5 Standards F-7 and F-19.

    - If fluid quality is important for proper AMS sensor function, then Helium, Carbon Dioxide, and Xenon should be sampled prior to filling for flight, to verify vendor specifications.

Rationale: refer to JPR 8080.5 Standard F-27.

    - Consider replacing glued pins/clip washers on thermal blankets with grommet/lacing

Rationale: To mitigate Foreign Object Debris hazards posed by loose clip washers.  Refer to JPR 8080.5 Standard G-5; Note: this recommendation was captured as AMS action item #150.

    - Include a step in the master integration procedure to check for duplicate part numbers as Acceptance Data Packages arrive, and assign an alternate number if duplicates are found.

Rationale:  Because each collaboration partner is using their heritage part numbering system, there is potential for part number duplication between subsystems.  This has the potential for confusion and possible human error.  Refer to JPR 8080.5 Standards G-10 and G-22.

6.  Compliance with NPR 7120.5 D

6.1	NPR 7120.5 Applicability

Although JSC 27296, 	Project Plan for the Alpha Magnetic Spectrometer, does not specifically cite NPR 7120.5 as an applicable document, it does cite EA-WI-023, which in turn cites NPR 7120.5 as applicable.  Para P2.b of NPR 7120.5 Revision D states:

This NPR applies to all current and future NASA space flight programs and projects (including spacecraft, launch vehicles, instruments developed for space flight programs and projects, research and technology developments funded by and to be incorporated into space flight programs and projects, critical technical facilities specifically developed or significantly modified for space flight systems, and ground systems that are in direct support of space flight operations). This NPR also applies to reimbursable space flight programs/projects performed for non-NASA sponsors. For existing programs and projects, the requirements of this document are applicable to the program/project’s extant phase as of the effective date of this NPR and to phases yet to be completed.

Although this verbiage implies applicability to AMS, it should be noted that the AMS project baseline pre-dates key integration review verbiage in this latest NPR revision.  For this reason, applicability—specifically System Integration Review requirements—should be verified with the process owner.  Recommendations outlined in Section 6.3 below are based on a presumption that Table 2-5 of NPR 7120.5 Revision D, which defines the System Integration Review (SIR) project life cycle phase, is applicable:

The SIR evaluates the readiness of the project to start flight system assembly, test, and launch operations. V&V plans, integration plans, and test plans are reviewed. Test articles  hardware/software), test facilities, support personnel, and test procedures are ready for testing and data acquisition, reduction, and control.

6.2	Observations

The dedicated AMS integration facility at the European Organization of Nuclear Research (CERN) appears to be well-designed and ready to support integration.  A master integration schedule has been developed to help choreograph subsystem hardware deliveries, and individual hardware item schedules are being closely monitored by the integration authority.  Hardware Acceptance Data Packages (ADP) are being prepared.  A spot check of one sample ADP (Helium tank provided by Hans Bieri Engineering) revealed only one minor problem.  Trained personnel supplied by the hardware providers will receive and inspect their hardware at CERN, and assist in integration.  Training and certification of in-line quality personnel is nearing completion. Ground support equipment and tool lists are being developed and coordinated.

Although the general AMS Integration Plan is complete, detailed assembly procedures and verification plans are not yet mature enough to complete a comprehensive System Integration Review.

6.3	Recommendations with respect to NPR 7120.5D

6.3.1	Verify with the process owner the extent of NPR 7120.5 Revision D applicability to AMS (for JSC, EA2/Engineering Services and Management Integration Office serves as the process owner).  Update JSC 27296 if necessary to document any changes from the baseline project plan.

Rationale:  Because the AMS project baseline pre-dates key integration review verbiage in the latest NPR revision, applicability may be subject to interpretation; documenting an agreement now may help avoid misunderstandings at the System Acceptance Review.

6.3.2	Obtain Technical Authority concurrence on all AMS deviations/waivers.

Rationale:  Refer to NPR 7120.5 Revision D, para. 3.4.2.2, and JSC 63722.

7.  Compliance with NPR 7123.1 Revision A

7.1	NPR 7123.1 Applicability

Although JSC 27296, 	Project Plan for the Alpha Magnetic Spectrometer, does not specifically cite NPR 7123.1 as an applicable document, it does cite EA-WI-023, which cites NPR 7120.5, which in turn cites NPR 7123.1 as applicable.  Para P2.d of NPR 7123.1 Revision A states:

The requirements enumerated in this document are applicable to all new programs and projects, as well as to all programs and projects currently in Formulation phase as of the effective date of this document. (See NPR 7120.5 for definitions of program phases.) This NPR also applies to programs and projects in their Implementation phase as of the effective date of this document. However, the technical team may request permission from the designated governing authority to be allowed to continue without complying with all or sections of this NPR.

Recommendations outlined in Section 7.3 below are based on a presumption that Table G-10 of NPR 7123.1A, which outlines SIR entrance & success criteria, is applicable:

| System Integration Review (SIR) |
| --- |
| Entrance Criteria | Success Criteria |
| Integration plans and procedures have been completed and approved. Segments and/or components are available for integration. Mechanical and electrical interfaces have been verified against the interface control documentation. All applicable functional, unit-level, subsystem, and qualification testing has been conducted successfully. Integration facilities, including clean rooms, ground support equipment, handling fixtures, overhead cranes, and electrical test equipment, are ready and available. Support personnel have been adequately trained. Handling and safety requirements have been documented. All known system discrepancies have been identified and disposed in accordance with an agreed-upon plan. All previous design review success criteria and key issues have been satisfied in accordance with an agreed-upon plan. The quality control organization is ready to support the integration effort. | Adequate integration plans and procedures are completed and approved for the system to be integrated. Previous component, subsystem, and system test results form a satisfactory basis for proceeding to integration. Risk level is identified and accepted by program/project leadership, as required. The integration procedures and work flow have been clearly defined and documented. The review of the integration plans, as well as the procedures, environment, and configuration of the items to be integrated, provides a reasonable expectation that the integration will proceed successfully. Integration personnel have received appropriate training in the integration and safety procedures. |

7.2	Observations

7.2.1	Although a general AMS Integration Plan is complete, detailed integration procedures are not yet completed or approved;

7.2.2	Some, but not all, components are available for integration;

7.2.3	Mechanical and electrical interfaces have not yet been verified against the interface control documentation;

7.2.4	Functional, unit-level, and subsystem testing is in progress;

7.2.5	Integration facilities, including clean rooms, ground support equipment, handling fixtures, overhead cranes, and electrical test equipment, appear to be ready and available;

7.2.6	Support personnel training and certification is in progress;

7.2.7	Handling and safety requirements are being developed (hazard reports are complete);

7.2.8	All known system discrepancies have been identified and are being disposed in accordance with an agreed-upon plan;

7.2.9	Open design review issues have been moved to the Open Paper Management Tool, and will be satisfied in accordance with an agreed-upon plan;

7.2.10	The quality control organization is ready to support the integration effort.

  - Recommendations with respect to NPR 7123.1

7.3.1	Verify with the process owner the extent of NPR 7123.1 Revision A applicability to AMS.  Update JSC 27296 if necessary to document any changes from the baseline project plan.

Rationale:  Because the AMS project baseline pre-dates key integration review verbiage in the latest NPR revision, applicability may be subject to interpretation; documenting an agreement now will avoid misunderstandings later.

7.3.2	Incorporate paper product (integration procedures, acceptance data packages, etc.) required delivery dates & review times into the AMS master integration schedule.

Rationale: Staggering integrated procedure review/approval cycles will help prevent a resource bottleneck. Seeing how the ADP review tasks fit into the overall work flow may also help collaboration partners understand the need for timely paper product deliveries. Note: this recommendation was captured during the Integration Review as Action Item #129.

    - Include all integration procedures and drawings in the master document list or tree.  Rationale: will help establish the order in which procedures must be available. Note: this recommendation was captured during the Integration Review as Action Item #129.

    - Document Project acceptance of the risk that integration will begin prior to a comprehensive, end-to-end integration review.

Rationale:  Beginning hardware assembly without a comprehensive, end-to-end integration review poses a higher risk of assembly error, dimensional interferences, re-work, and potential integrated test problems.  If this is an acceptable risk, it should be documented; if this is not an acceptable risk, hardware assembly should be postponed until integration review products are complete.

    - Prior to integrating any two subsystems together, complete all pertinent integration models, procedures, and analyses.  Perform at least a partial SIR using NPR 7123.1A  Table G-10 as a checklist for each subsystem integration.

Rationale:  Even if it is not possible to complete an end-to-end integration review prior to beginning assembly, a detailed subsystem-to-subsystem integration review will mitigate the risk of assembly error and potential rework.

    - Close the one remaining open Critical Design Review Item Disposition (RID) prior to beginning micrometeoroid/orbital debris shield integration.

Rationale: RID 1-17 appears to have potential impacts to the integrated design.

8.  Conclusions

- Although JPR 8080.5 is not strictly applicable to AMS, the payload appears to comply with most of the design and process standards.  Section 5.3 of this report recommends several steps to enhance project success.

- Extent of NPR 7120.5D applicability is unclear.  Section 6.3 of this report recommends applicability be verified with the process owner; regardless of the extent of applicability, it is also recommended that all AMS Deviation/Waivers be coordinated with the Technical Authority, in compliance with JSC 63722.

- Extent of NPR 7123.1A applicability is unclear.  Section 7.3 of this report recommends applicability be verified with the process owner.  It is recommended that AMS document project acceptance of risks associated with beginning payload assembly without a comprehensive end-to-end integration review.  To mitigate those risks, it is recommended that partial integration reviews be conducted prior to each individual subsystem integration; this would lower the risk of assembly error and costly rework.