NASA Earth Science Enterprise

Applications Division

Air Quality Applications Project
Prototyping and evaluating the use of satellite data to improve 
the Community Mesoscale Air Quality(CMAQ) Model

“Project CMAQ” Project Plan

1	Project CMAQ Purpose	3

1.1	Purpose & Scope	3

1.2	Project Goal & Objectives	3

2	Project CMAQ Team	4

2.1	CMAQ Team Partnerships	4

2.2	CMAQ Team Collaboration Roles	4

3	Project CMAQ Work Breakdown Structure	5

4	Project CMAQ Implementation	5

4.1	Implementation Approach	5

4.2	Project CMAQ Deliverables	8

4.3	Project CMAQ Schedule & Milestones	9

4.4	Budget	10

4.5	Performance Measures	10

5	Project CMAQ References	10

6	Project CMAQ Signature Page	11

# Project CMAQ Purpose

## Purpose & Scope

The U.S. Environmental Protection Agency’s Community Multiscale Air Quality (CMAQ) modeling system was developed to improve the environmental management (federal, state, Tribal, and local) community’s ability to evaluate the impact of air quality management practices for multiple pollutants at multiple scales and to improve the scientist’s ability to better probe, understand, and simulate chemical and physical interactions in the atmosphere.

US EPA utilizes monitoring data and air quality simulation models for performing assessments of compliance with the National Ambient Air Quality Standards (NAAQS), and the development of control strategies in the required State Implementation Plans (SIPSs).  Sources of secondary pollutants such as ozone and fine particulate matter are transported over large domains, both regional and continental, as well as locally produced through photochemical and heterogeneous processes.  The effect of global and supra-regional pollution events on regional air quality is not well understood from the current monitoring of surface distributions and current regional modeling domains.  Often the lateral boundary conditions for the regional models are a fixed set of climatological mean values.  The vertical domain of current regional air quality models extends to at most the troposphere, which is inadequate to reflect stratospheric influence.

Regional air quality model simulations may be greatly improved when upper and lateral boundary air pollutant data are available.  Such data can provide more realistic and accurate descriptions of influx of pollutants, and provide a means to account for the contributions of pollutants transported over larger distances.  The goal of this project is to determine if multi-scale modeling and data assimilation frameworks for linking satellite and in-situ measurements of atmospheric chemical species can improve the prediction of large-scale transport and local productions of surface ozone.

## Project Goal & Objectives

The primary objectives of this project are to prototype and evaluate the efficacy of two techniques to provide boundary conditions for ozone into the Models-3 Community Multiscale Air Quality (CMAQ) using satellite retrievals.  The first approach is to provide lateral boundary conditions generated from a global model output through a global assimilation of satellite-observed ozone.  The second approach adds the direct assimilation of satellite ozone retrievals from GOES into the Models-3 Community Multiscale Air Quality (CMAQ) system.

Predicated on adequate and timely funding, this project will meet the following goals and objectives:

A.  By summer 2004, a Task Order or equivalent will be in place to fund the non-NASA work required to evaluate the use of satellite data as boundary conditions in CMAQ.

B.  By March, 2005, results of the analysis will be discussed among the team members and partners in technical meeting(s).

C.  Transition plans for the use of boundary conditions in CMAQ will be formulated based on the project’s outcome and implemented by the user Agency (US EPA).

The project is expected to be complete in 1-2 years.

# Project CMAQ Team

## CMAQ Team Partnerships

The CMAQ project is scientist-led, in a ‘NASA senior researcher/group leader-to-external Agency senior researcher/group leader’ project model.  The Principal Investigator engages a team of NASA, EPA, NOAA, university, and private industry personnel to achieve the project objectives.  The activity is highly collaborative, not directive, and as such requires agreement on shared goals and objectives.  Many of the key participants are not funded by NASA, and participate on the basis of professional respect for the NASA work and close alignment of the work with their functional or research responsibilities.  Consequently, NASA management of these activities is modeled along the lines of Research and Analysis tasks.

NASA’s primary roles in the CMAQ project include the end-to-end responsibility of fostering inter-Agency relationships at the senior researcher/ responsible group leader level, the establishment of inter-Agency mutually-agreed requirements and goals for the project’s evolution, establishment and supervision of the specific jointly-funded task agreement with the CMAQ developers, interpretation of the outcome of the analysis with advice on next steps in EPA’s development of CMAQ.

## CMAQ Team Collaboration Roles

The specific partner organizations for the CMAQ project and their general role in the collaboration are as follows:

1.   NASA air quality applications team at NASA (Code YO )

2.   NASA RAQMS Principal Investigator and co-Investigators  (Code YS )

3.  US EPA ORD/ NERL/Model Evaluation and Applications Research Branch (Alice Gilliland, Chief, CMAQ)

4.  Dr. Daewon Byun, University of Houston, formerly of US EPA (CMAQ Development)

5.  NOAA NESDIS, Office of Research and Applications, Satellite Meteorology and Climatology Division (Dr. Shoba Kondragunta, GOES Data)

6.  Space Science and Engineering Center (SSEC) at the University of Wisconsin  (Drs. Jun Li and Chris Schmidt, GOES ozone algorithms)

In this project, investments by NASA’s Earth Science Division in measurements, models, and analysis will be leveraged to strengthen the understanding of air pollution modeling.  Space based, airborne, and surface measurement networks all contribute significantly to the project’s success.  NASA Research and Analysis program has funded the development of models and analysis tools for the understanding of atmospheric composition that we use in this project, and we gratefully acknowledge this support.

# Project CMAQ Work Breakdown Structure

This project operates under the WBS provided here at top level.

- CMAQ Project Management (D.O.Neil, NASA)

- Test CMAQ with globally assimilated satellite data as boundary conditions (BC).  (Lead,  D. Byun, UH with A. Gilliland, US EPA)

- Evaluate CMAQ performance with globally assimilated satellite data as BC.  (Lead, R.B. Pierce, NASA)

- Test CMAQ with direct assimilation of GOES ozone data..  (Lead, D. Byun, UH with S. Kondragunta, NOAA NESDIS)

- Evaluate CMAQ with direct assimilation of GOES ozone data.  (Lead, R.B. Pierce, NASA)

- Prepare benchmark report.  (Lead, NASA).

# Project CMAQ Implementation

## Implementation Approach

The global ozone analysis that provides lateral boundary conditions is generated from a chemical assimilation approach that assimilates stratospheric as well as tropospheric chemical species. T

he approach involves the joint assimilation of stratospheric profile and total column retrievals. This is a logical extension of the work of Fishman, et al. [1990] who demonstrated that one could extract seasonal tropospheric ozone residuals (TOR) from differences between total O3 and stratospheric column inferred from stratospheric O3 profile measurements. By assimilating both the stratospheric profile and total column measurements physically consistent O3 distributions can be produced. By adequately accounting for the spatial and temporal variations in the stratospheric column, the errors that limited previous daily TOR analyses to the tropics and subtropics [Fishman and Balok, 1999] will be reduced.

The modeling tools used for the global assimilation are the LaRC Lagrangian Chemical Transport Model (LCTM) [Pierce et al., 1997, 1999, 2003], and the LaRC/UW Regional Air Quality Modeling System (RAQMS). RAQMS is a global to regional scale air quality modeling/data assimilation system developed at NASA LaRC in collaboration with researchers at the University of Wisconsin. These models are used to assimilate global satellite observations through a Statistical Digital Filter (SDF) assimilation system [Stobie, 1985, 2000]. SDF is a relatively simple optimal interpolation approach to data assimilation developed at the Goddard Space Flight Center Data Assimilation Office.

The RAQMS global assimilation is decomposed into two parts. Solar occultation measurements are assimilated first. In this step the LCTM is initialized with stratospheric solar occultation measurements which are trajectory mapped to the assimilation times (6 hourly). The solar occultation ozone measurements are retained for up to 5 days, depending on the local chemical lifetime.   The mapped measurements are used to define a local incremental adjustment to the stratospheric ozone within the RAQMS vertical grid structure. The TOMS total column measurements are assimilated next. This step involves determining a total column “first guess” and then TOMS column measurements within +/- 3hrs of the assimilation time are used to define an incremental adjustment to the total column. This incremental adjustment is distributed uniformly as a constant mixing ratio increment within RAQMS. The resulting 6 hourly global chemical analysis will be used to constrain initial and lateral bounary conditions for CMAQ regional chemical predictions.

The specific description of the tasks involved in implementing this project are described below.

Task 1. CMAQ Simulation Runs and Analysis of Results (Case Study Approach – Southern Oxidation Study 1999 (SOS 99))

Using CMAQ version 4.3 with SDF, conduct a model simulation for the SOS 99 period of June 15 –July 15.  The modeling domain shall be the Eastern half of US continent.   The model input datasets (meteorology, emissions, and time dependent lateral boundary condition) covering the SOS 99 period will be provided.  The partners shall work in a collaborative fashion on the development of the methodologies to ingest the lateral and top boundary conditions from global RAMQS simulation into CMAQ v.4.3.  All partners shall work with NASA and the US EPA to benchmark the performance of the CMAQ simulation with lateral boundary conditions as follows:

The Model Evaluation and Applications Research Branch of the Atmospheric Modeling Division within the National Exposure Research Laboratory of US EPA Office of Research and Development has completed a simulation using CMAQ v.4.3 for the period from June 15 to July 15.  The benchmark activity will be a controlled test where the simulation from EPA will be used to define the baseline.  A comparison will be made to identify resulting differences.  The comparison shall include the model predicted concentrations from the baseline CMAQ v.4.3 simulation with the fixed boundary conditions and with the satellite/RAQMS-derived lateral /top boundary conditions against observed (SOS 99) data.  Using standard statistical measures typically used to evaluate model performance (e.g., root mean square, mean bias, normalized mean bias, correlation coefficient, etc.) the contractor shall assess whether the CMAQ v.4.3 simulation with lateral boundary conditions shows better performance.

- Test read of RAQMS 6hrly global chemical fields in Netcdf format. Determine additional auxiliary data requirements from RAQMS.

- Define mapping of RAQMS chemical species into CMAQ CB4 mechanism

- decompose NOy, Ox, families into individual species

- repartition NMHC species to account for RAQMS extension of CB4

(Note: CMAQ does not have long-life species such as Cly and Bry, etc.)

- Define UH CMAQ experimental constraints to assure compliance with previous (no lateral boundary conditions) EPA SOS assessment run

- emission inventories

- chemical mechanism

- vertical/horizontal grid resolution

- CMAQ version

- Acquire 6hr global RAQMS chemical fields/auxiliary data from NASA/LaRC

- map RAQMS chemical fields to CMAQ horizontal, vertical, and temporal resolution

- map RAQMS chemical fields to CMAQ CB4 chemical species

- Acquire meteorological fields (MM5/MCIP) from EPA/ORD for UH CMAQ experiment

- characterize key meteorological parameters affecting pollutant transport

- Acquire emission data sets (SMOKE) for EPA/ORD UH CMAQ experiment

- Perform quality assurance check of the emissions data

- Acquire SOS observation dataset for evaluation

- Obtain SOS analysis data from EPA and NASA/LaRC

8)   Conduct test (short period) CMAQ standard (no BC) assessment run

- verify that UH CMAQ run is identical to EPA SOS99 assessment run

- 9) Conduct June-July, 1999 CMAQ assessment run

Task 2. Evaluation of the impact of GOES ozone on SOS99 CMAQ assessment modeling (in partnership with UW-SSEC)

- Determine appropriate point within CMAQ modeling system to interface UW SDF assimilation

-     should be point in CMAQ time-stepping loop where output files are written

-     assimilation requires gridded first guess ozone field and first guess error field

- SDF column assimilation  interface uses model output history files and outputted first guess error fields

- SDF column assimilation is a separate executable which is spawned from RAQMS and updates the model output history files

- RAQMS then reads in model output history files, replacing first guess ozone with assimilated ozone

- Port SDF (Fortran) software onto UH Linux platform

- Currently running on Linux (RedHat) platform, being implemented SGI UNIX platform

- Modify Makefile for UH parallel Linux machine

- Modify SDF to conduct GOES instead of solar occultation + TOMS assimilation

- replace solar occultation assimilation step (subroutine call) with build of ozone column above CMAQ upper boundary (obtained from RAQMS global ozone)

- total column ozone is CMAQ column to model top + RAQMS global column above

- GOES column assimilation is then identical to TOMS column assimilation procedure

- NOTE: Need to consider replacing CMAQ ozone profile with RAQMS global analyses at levels below CMAQ upper boundary since CMAQ may not provide a good “first guess” in the upper troposphere.

- Implement SDF interface and error growth model in CMAQ

- Acquire GOES ozone column for June-July, 1999

- Jun Li (CIMSS) is PI of the GOES ozone column data project, and Chris Schmit (CIMSS) developed the retrieval

- Provide NASA/LaRC acquired data from CIMSS, and involve NESDIS for providing GOES ozone data to UH

- Acquire software from NASA/LaRC to convert GOES files into SDF input files

- Use ASCII file conversion LaRC

- Repeat step 7 of Task 1, SOS99 CMAQ assessment modeling experiment with SDF assimilation of GOES data

-     error growth model requires estimate of standard deviation of errors, this means that two assimilation runs need to be conducted, the first run assumes a constant (%) model error and the standard deviation of errors are calculated from the increment. The second run is the final one, it uses the standard deviation of errors and the error growth model to estimate the first guess error.

Coordinate with EPA/ORD, NASA/LaRC, and NOAA/NESDIS in statistical evaluation of the impact of lateral BC and GOES assimilation on CMAQ SOS99 assessment experiment

## Project CMAQ Deliverables

The ozone project will be complete in FY05.  Deliverables include:

1.0   Task 1 Deliverable: Evaluation of Global RAQMS-CMAQ simulation results.

2.0   Task 2 Deliverable:  Evaluation of GOES/SDF-CMAQ results.

3.0   A final project technical report of work done, including the following components:

Evaluation report (Dr. Byun)

Benchmarking report (NASA)

4.0   Scientific article will be published in refereed journals for the scientific community.

We expect to initiate a closely related project to evaluate the use of satellite observations of aerosol in CMAQ.   Additional team members will participate in this CMAQ aerosol project, to represent the science expertise in aerosol modeling (Dr. M.Chin) and in aerosol retrievals (MODIS AOD,  Dr. A. Chu; CALIPSO products, Dr. O. Ali, and others).  The CMAQ aerosol project will be further defined in FY05.

## Project CMAQ Schedule & Milestones

Project CMAQ, developed by the IDEA team, is one project under NASA’s National Air Quality Applications Program.  This project is designed to address environmental data needs in modeling for federal decision making.  US EPA and NOAA are partners with NASA in this prototype for the use of satellite data as constraints on the chemical modeling of the lower atmosphere for use in air quality management on behalf of the public.

## Budget

NASA’s Air Quality Program plan assigns $600K for FY 04 and $650 K for FY 05 to Project CMAQ as procurement funding (civil service expenses are excluded from this funding).   Specific expenses in FY 04 and FY05 include support staff to deliver RAQMS results for the CMAQ testing, partial funding to UW-SSEC for transition of assimilation software to US EPA, funding for Dr. Byun, and contractor travel.

## Performance Measures

Progress on the CMAQ project can be assessed through:

- Task in place with Dr. Byun/University of Houston as scheduled.

- Technical interchange meetings occur as scheduled.

- Benchmark report prepared and submitted to NASA HQ.

- Results of this project will be presented in scientific conferences and peer-reviewed journals.

- Additional, informal documentation of progress is demonstrated through occasional key activity reports through the internal NASA reporting system.

# Project CMAQ References

Fishman, Jack; Watson, Catherine E; Larsen, Jack C; Logan, Jennifer A.  Distribution of tropospheric ozone determined from satellite data.  Journal of Geophysical Research, Washington, DC. Vol. 95, no. D4, pp. 3599-3617. 1990.

### Fishman, Jack and Amy E. Balok. Calculation of daily tropospheric ozone residuals using TOMS and empirically improved SBUV measurements: Application to an ozone pollution episode over the eastern United States.  JOURNAL OF GEOPHYSICAL RESEARCH, VOL. 104, NO. D23, PAGES 30,319–30,340, 1999

Fairlie, T. Duncan, R. Bradley Pierce, William L. Grose, Gretchen Lingenfelser, Max Loewenstein, James R. Podolske.  Lagrangian forecasting during ASHOE/MAESA: Analysis of predictive skill for analyzed and reverse-domain-filled potential vorticity.  JOURNAL OF GEOPHYSICAL RESEARCH, VOL. 102, NO. D11, PAGES 13,169–13,182, 1997.

Lingenfelser, Gretchen S., William L. Grose, Ellis E. Remsberg, T. Duncan Fairlie, R. Bradley Pierce.  Comparison of satellite and in situ ozone measurements in the lower stratosphere.  JOURNAL OF GEOPHYSICAL RESEARCH, VOL. 104, NO. D11, PAGES 13,971–13,980, 1999.

R. B. Pierce, J. Al-Saadi, T. D. Fairlie, M. Natarajan, V. L. Harvey, W. L. Grose, J. M. Russell III, R. Bevilacqua,  S. D. Eckermann, D. Fahey, P. Popp, E. Richard, R. Stimpfle, G. C. Toon, C. R. Webster, J. Elkins.  Large-scale chemical evolution of the Arctic vortex during the 1999/2000 winter: HALOE/POAM III Lagrangian photochemical modeling for the SAGE III—Ozone Loss and Validation Experiment (SOLVE) campaign.  JOURNAL OF GEOPHYSICAL RESEARCH, VOL. 108, NO. D5, 8317, doi:10.1029/2001JD001063, 2003.

# Project CMAQ Signature Page

This document contains the project plan to evaluate the use of satellite data as boundary/initial conditions to improve the Community Mesoscale Air Quality Model (CMAQ) under the joint auspices of NASA (Air Quality Applications) and US EPA (Office of Research and Development) with the partnership of environmental data from NOAA.

The National Applications Program has reviewed the plan and agrees that the plan appropriately reflects the goals, objectives, and activities for the program element to serve the Earth Science Applications Program, ESE, NASA, the Administration, and Society.

| Doreen Osowski Neil Air Quality Applications Group Leader NASA Langley Research Center Hampton, VA 23681-0001 |  | Date |
| --- | --- | --- |
| S T Rao Director, Air Quality Modeling Division E243-02 USEPA Mailroom Research Triangle Park, NC 27711 919-541-4542 |  | Date |
| Mitch D. Goldberg Director, Satellite Meteorology and Climatology Division NESDIS HQTR Route: E/RA2 Camp Springs, MD |  | Date |
| Lawrence Friedl Air Quality Program Manager NASA Earth Science Applications Program NASA Headquarters, Washington, DC |  | Date |
| Ronald J. Birk Director, Earth Science Applications Division NASA Earth Science Applications Program NASA Headquarters, Washington, DC |  | Date |

# Text boxes

Earth Science for Society

Accelerating the realization of economic and societal benefits from Earth science, information, and technology